## Revision History
Date | Version | Comment
2020-04-15 | V1.0 | JXU128: define basic APIM issue template

## Guideline
1.视频/图片要对应问题名称，文件夹名称要对应日期，VIN，提AIMS时解释不清的问题须附图
2（1）如果是和其他ECU 相关的，如仪表/AHU/DSP相关的，解决问题需要CAN Log+ USB log; （2）如果是蓝牙/导航/HMI/语音控制相关的，只需要USB log-> 必须； 但如果是HMI 页面布局问题，可以没有Log;
3.如果发生黑屏/重启/系统卡死之类问题，很可能后续一些验证测试如蓝牙播放也是受影响的，所以需要先重启一下；
4. 原则上，今天跑的VOCF, 可以在第二天会议上讨论，这样给大家留出整理的时间。 在会议中，有些新建AIMS, 希望team 第三天反馈给我们AIMS 号( 写明关联上哪个问题)，我们也反馈给team 需要合并的AIMS;
5.提问题时先确认去重，避免重复提问; 不同软件版本的问题可以提，但是同一个软件版本，同一个team, 明显重复的问题要去重；
6.AIMS标题需要中英文都有； 问题描述可以只是中文，但是欢迎也加上英文翻译；
7.AIMS 先进program deck, PMT 经过讨论判断需要提供的信息已经完善，通知AIMS 转到APIM_CIS deck;

## Template
| IssueType | Summary | Component/s | Description | Priority | Environment | LogPath | AIMS | Supplier | Assignee | Affect Version | Label | Label | Label | Label
| 必填 | 必填 | 必填 | 必填 | 必填 | 必填 | 选填 | 选填 | 必填 | 必填 | 必填 | 必填 | 必填 | 必填 | 选填
空模板 |  |  |  | Pre-condition: 复现步骤 Step1: Step2: Step3: Step4: 期待结果: 实际结果: 是否可恢复: 发生频率: 发生时间: 手机型号及操作系统: 福特派版本: 福特派账号: 地点: |  | VehicleLine: VIN(后5位): 软件版本: 小度版本: VMCU: |  |  | Baidu | hlong30 | Phase1_SOP1 | DuerOS_Phase1 | DuerOS_LaunchTst | C519 | R202
填写 指导 | Bug |  |  | Pre-condition: ACC / cranking on/ normal drive （如果要测离线导航，首先说明离线地图+离线导航已经下载；如果是蓝牙音乐，要写蓝牙音频和电话已配对） 复现步骤 Step1: 我在听蓝牙音乐；(之前我在做什什么) Step2: 点击随心听页面，无响应；(我做了什么，发生了什么事情) Step3: 点击主页按键，也是卡滞无响应；(发生之后，我又检查其他项怎么样) 期待结果: 如果和用户体验改进相关的则是必填，例如我希望扩展哪一条语音指令； 实际结果:如果复现步骤已写清楚，则选填； 是否可恢复:重新启动车机才恢复（怎么恢复的） 发生频率:例如是语音命令不响应的，要写3/10 failed; 发生时间:2019/03/27，9:58非常重要！否则改bug的人找不到问题时间在哪里，无从分析log。 手机型号及操作系统:如果是和蓝牙音乐或者手机本地音乐问题，则是必填，需要填写手机型号，IOS or Android 系统版本；如果是用App播放则要说明是网易/QQ/酷我等等，或者是默认播放器？ 福特派版本: 福特派账号: 地点:（如果是和广播信号质量/导航相关是必填） | Immediate Gating
Note on M1: Author: Label for Phase
Note on N1: Author: Test Source
Note on O1: Author: Vehicle Type
Note on P1: Author: Launch Test Team

## Import List
IssueType | Summary | Description | Priority | Supplier | Assignee | Component/s | Product Owner (Ford FO) | Discipline Manager | Affect Version | LogPath | Environment (Hardware Dependency) | Jira | AIMS | Initiator | Label | Label | Label
Bug | 【必发】 | Pre-condition: 复现步骤 Step1: Step2: Step3: Step4: 期待结果: 实际结果: 是否可恢复: 发生频率: 发生时间: 手机型号及操作系统: 福特派版本: 福特派账号: 地点: | Immediate Gating | Baidu | ymao16 | AAR | swu97 | xgu14 | CF15_DCV2.1.PRO hotfix | 百度网盘链接： | Vehicle Series：U625ICA Trend VIN(后6位)：470594 百度软件版本？？： SYNC+版本： SoC版本： MCU版本： 所有硬件相关版本： |  |  | Baidu | CX727 | APIM_CIS | Phase4_LaunchTst
Bug | Phase4:【偶现】 |  |  | Ford |  |  | #N/A | #N/A
Bug |  |  |  | Desay | yyuan33 |  | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
Bug | [6 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
[7 empty] | #N/A | #N/A
Note on P1: Author: Vehicle Type
Note on Q1: Author: Label for Phase
Note on R1: Author: Test Source

## Field
IssueType
Bug
Priority
Immediate Gating
Gating
High
Medium
Low
Supplier.
Baidu
Desay
Ford
Assignee
Label (Phase)
APIM_CIS
Label (Issue Source)
Phase4_IVITst | IVI Software Test Bugs
Phase4_DV | DV Test Bugs
Phase4_ITV | ITV Test Bugs
Phase4_CVPPTst | CVPP Validation Team Test Bugs
Phase4_SupplierTst | Suppliers Test Bugs
Phase4_LaunchTst | Launch team Test Bugs
Phase4_CyverSecurity | Cyver Security Test Bugs
Phase4_SIFI | System Integration Test Bugs
Label (Launch Test Team)
NTT
VOCF
FCPA
R202
SW_Fleet
EOL
Audit
Label (Vehicle Type)
CX727
U725
P702
CD542_L
CD542_H
U625ICA
U554MCA
CD764
Initiator
REC
Baidu
Desay
NTT
VOCF
FCPA
R202
SW_Fleet
EE signoff
Public Audit
CAT

## Release Version
Release version | Description | U725/P702/CD542L |  | CD542H/U625ICA |  | CX727 |  | CX727
External_App | This is not a DuerOS SW version, is a External SW version | AF12_BF1.ENG | AF12_BF1.PRO | BF27_BF1.ENG | BF27_BF1.PRO | CF15_BF1.ENG | CF15_BF1.PRO | CF15_DCV2.ENG
Phase4_BF1_Ford | complete basic function for CD542_L&CD542_H&P702&U725&CX727&U625ICA | AF12_BF2.ENG | AF12_BF2.PRO | BF27_BF2.ENG | BF27_BF2.PRO | CF15_BF2.ENG | CF15_BF2.PRO | CF15_DCV2.PRO
Phase4_BF2_Ford | complete 60% function for P702&U725&CX727&CD542_H&U625ICA | AF12_BF3.ENG | AF12_BF3.PRO | BF27_BF3.ENG | BF27_BF3.PRO | CF15_BF3.ENG | CF15_BF3.PRO | CF15_DCV2.1.ENG
Phase4_BF3_Ford | complete 60% function for CD542_L &100% function for CX727&CD542_H&U625ICA | AF12_BF4.ENG | AF12_BF4.PRO | BF27_BF4.ENG | BF27_BF4.PRO | CF15_BF4.ENG | CF15_BF4.PRO | CF15_DCV2.1.PRO
Phase4_BF4_Ford | complete 100% function for P702&U725 & A bug free for CX727&CD542_H | AF12_BF5.ENG | AF12_BF5.PRO | BF27_BF5.ENG | BF27_BF5.PRO | CF15_BF5.ENG | CF15_BF5.PRO | CF15_DCV2.1.PRO hotfix
Phase4_BF5_Ford | complete 100% function for CD542_L & A/B bug free for CD542_H | AF12_BF6.ENG | AF12_BF6.PRO | BF27_BF6.ENG | BF27_BF6.PRO | CF15_BF6.ENG | CF15_BF6.PRO | CF15_DCV3.ENG
Phase4_BF6_Ford | A bug free for CD542_L&U725 | AF12_BF7.ENG | AF12_BF7.PRO | BF27_BF7.ENG | BF27_BF7.PRO | CF15_BF7.ENG | CF15_BF7.PRO | CF15_DCV3.PRO
Phase4_BF7_Ford | A/B bug free for CD542_L&U725 & A bug free for P702 | AF12_R00.ENG | AF12_R00.PRO | BF27_R00.ENG | BF27_R00.PRO | CF15_R00.ENG | CF15_R00.PRO
Phase4_R00_Ford | Support CD542_L &CD542_H & CX727 PEC | AF12_R01.ENG | AF12_R01.PRO | BF27_R01.ENG | BF27_R01.PRO | CF15_R01.ENG | CF15_R01.PRO
Phase4_R01_Ford | Support CD542_L &CD542_H& CX727 FEC & A/B bug free for P702 | AF12_R02.ENG | AF12_R02.PRO | BF27_R02.ENG | BF27_R02.PRO | CF15_R02.ENG | CF15_R02.PRO
Phase4_R02_Ford | Support CD542_L &CD542_H TT & A bug free for U625ICA | AF12_R03.ENG | AF12_R03.PRO | BF27_R03.ENG | BF27_R03.PRO | CF15_R03.ENG | CF15_R03.PRO
Phase4_R03_Ford | Support P702 PEC & A/B bug free for U625ICA | AF12_R04.ENG | AF12_R04.PRO | BF27_R04.ENG | BF27_R04.PRO | CF15_R04.ENG | CF15_R04.PRO
Phase4_R04_Ford | Support CD542_H PP | AF12_R05.ENG | AF12_R05.PRO | BF27_R05.ENG | BF27_R05.PRO | CF15_R05.ENG | CF15_R05.PRO
Phase4_R05_Ford | Support U725 PEC | AF12_R06.ENG | AF12_R06.PRO | BF27_R06.ENG | BF27_R06.PRO | CF15_R06.ENG | CF15_R06.PRO
Phase4_R06_Ford | Support CD542_L PP & U625ICA PEC | AF12_R07.ENG | AF12_R07.PRO | BF27_R07.ENG | BF27_R07.PRO | CF15_R07.ENG | CF15_R07.PRO
Phase4_R07_Ford | Support P702 TT & CX727 MP2&OKTB & U625ICA FEC | U554MCA |  | CD764
Phase4_R08_Ford | Support U725 FEC & CD542_H MP1 | DL13_BF1.ENG | DL13_BF1.PRO | EL27_BF1.ENG | EL27_BF1.PRO
Phase4_R09_Ford | Support U725 TT/PP & U625ICA TT | DL13_BF2.ENG | DL13_BF2.PRO | EL27_BF2.ENG | EL27_BF2.PRO
Phase4_R10_Ford | Support CD542_H MP2 | DL13_BF3.ENG | DL13_BF3.PRO | EL27_BF3.ENG | EL27_BF3.PRO
Phase4_R11_Ford | Support CD542_L MP1 & CD542_H OKTB & U625ICA PP | DL13_BF4.ENG | DL13_BF4.PRO | EL27_BF4.ENG | EL27_BF4.PRO
Phase4_R12_Ford | Support U725 MP1 & P702 PP & U625ICA MP1 | DL13_BF5.ENG | DL13_BF5.PRO | EL27_BF5.ENG | EL27_BF5.PRO
Phase4_R13_Ford | Support U725 MP2 & P702 debug & U625ICA MP2 | DL13_BF6.ENG | DL13_BF6.PRO | EL27_BF6.ENG | EL27_BF6.PRO
Phase4_R14_Ford | Support CD542_L&U725 OKTB & P702 MP1 | DL13_BF7.ENG | DL13_BF7.PRO | EL27_BF7.ENG | EL27_BF7.PRO
Phase4_R15_Ford | Support P702 MP2 | DL13_R00.ENG | DL13_R00.PRO | EL27_R00.ENG | EL27_R00.PRO
Phase4_BF1_Lincoln | complete basic function for U554 & CD764 | DL13_R01.ENG | DL13_R01.PRO | EL27_R01.ENG | EL27_R01.PRO
Phase4_BF2_Lincoln | complete 60% function for U554 & CD764 | DL13_R02.ENG | DL13_R02.PRO | EL27_R02.ENG | EL27_R02.PRO
Phase4_BF3_Lincoln | complete 100% function for U554 & CD764 | DL13_R03.ENG | DL13_R03.PRO | EL27_R03.ENG | EL27_R03.PRO
Phase4_BF4_Lincoln | A bug free for U554 & CD764 | DL13_R04.ENG | DL13_R04.PRO | EL27_R04.ENG | EL27_R04.PRO
Phase4_BF5_Lincoln | A/B bug free for CD764 | DL13_R05.ENG | DL13_R05.PRO | EL27_R05.ENG | EL27_R05.PRO
Phase4_BF6_Lincoln | A/B bug free for U554 | DL13_R06.ENG | DL13_R06.PRO | EL27_R06.ENG | EL27_R06.PRO
Phase4_BF7_Lincoln | EOL for U554 | DL13_R07.ENG | DL13_R07.PRO | EL27_R07.ENG | EL27_R07.PRO
Phase4_R00_Lincoln | support U554 & CD764 PEC
Phase4_R01_Lincoln | support U554 & CD764 FEC
Phase4_R02_Lincoln | support U554 & CD764 TT
Phase4_R03_Lincoln | support CD764 PP
Phase4_R04_Lincoln | support U554 PP & CD764 MP1
Phase4_R05_Lincoln
Phase4_R06_Lincoln | support U554 MP1
Phase4_R07_Lincoln | support U554 OKTB
AF12_BF1.ENG
AF12_BF2.ENG
AF12_BF3.ENG
AF12_BF4.ENG
AF12_BF5.ENG
AF12_BF6.ENG
AF12_BF7.ENG
AF12_R00.ENG
AF12_R01.ENG
AF12_R02.ENG
AF12_R03.ENG
AF12_R04.ENG
AF12_R05.ENG
AF12_R06.ENG
AF12_R07.ENG
BF27_BF1.ENG
BF27_BF2.ENG
BF27_BF3.ENG
BF27_BF4.ENG
BF27_BF5.ENG
BF27_BF6.ENG
BF27_BF7.ENG
BF27_R00.ENG
BF27_R01.ENG
BF27_R02.ENG
BF27_R03.ENG
BF27_R04.ENG
BF27_R05.ENG
BF27_R06.ENG
BF27_R07.ENG
CF15_BF1.ENG
CF15_BF2.ENG
CF15_BF3.ENG
CF15_BF4.ENG
CF15_BF5.ENG
CF15_BF6.ENG
CF15_BF7.ENG
CF15_R00.ENG
CF15_R01.ENG
CF15_R02.ENG
CF15_R03.ENG
CF15_R04.ENG
CF15_R05.ENG
CF15_R06.ENG
CF15_R07.ENG
DL13_BF1.ENG
DL13_BF2.ENG
DL13_BF3.ENG
DL13_BF4.ENG
DL13_BF5.ENG
DL13_BF6.ENG
DL13_BF7.ENG
DL13_R00.ENG
DL13_R01.ENG
DL13_R02.ENG
DL13_R03.ENG
DL13_R04.ENG
DL13_R05.ENG
DL13_R06.ENG
DL13_R07.ENG
EL27_BF1.ENG
EL27_BF2.ENG
EL27_BF3.ENG
EL27_BF4.ENG
EL27_BF5.ENG
EL27_BF6.ENG
EL27_BF7.ENG
EL27_R00.ENG
EL27_R01.ENG
EL27_R02.ENG
EL27_R03.ENG
EL27_R04.ENG
EL27_R05.ENG
EL27_R06.ENG
EL27_R07.ENG
AF12_BF1.PRO
AF12_BF2.PRO
AF12_BF3.PRO
AF12_BF4.PRO
AF12_BF5.PRO
AF12_BF6.PRO
AF12_BF7.PRO
AF12_R00.PRO
AF12_R01.PRO
AF12_R02.PRO
AF12_R03.PRO
AF12_R04.PRO
AF12_R05.PRO
AF12_R06.PRO
AF12_R07.PRO
BF27_BF1.PRO
BF27_BF2.PRO
BF27_BF3.PRO
BF27_BF4.PRO
BF27_BF5.PRO
BF27_BF6.PRO
BF27_BF7.PRO
BF27_R00.PRO
BF27_R01.PRO
BF27_R02.PRO
BF27_R03.PRO
BF27_R04.PRO
BF27_R05.PRO
BF27_R06.PRO
BF27_R07.PRO
CF15_BF1.PRO
CF15_BF2.PRO
CF15_BF3.PRO
CF15_BF4.PRO
CF15_BF5.PRO
CF15_BF6.PRO
CF15_BF7.PRO
CF15_R00.PRO
CF15_R01.PRO
CF15_R02.PRO
CF15_R03.PRO
CF15_R04.PRO
CF15_R05.PRO
CF15_R06.PRO
CF15_R07.PRO
DL13_BF1.PRO
DL13_BF2.PRO
DL13_BF3.PRO
DL13_BF4.PRO
DL13_BF5.PRO
DL13_BF6.PRO
DL13_BF7.PRO
DL13_R00.PRO
DL13_R01.PRO
DL13_R02.PRO
DL13_R03.PRO
DL13_R04.PRO
DL13_R05.PRO
DL13_R06.PRO
DL13_R07.PRO
EL27_BF1.PRO
EL27_BF2.PRO
EL27_BF3.PRO
EL27_BF4.PRO
EL27_BF5.PRO
EL27_BF6.PRO
EL27_BF7.PRO
EL27_R00.PRO
EL27_R01.PRO
EL27_R02.PRO
EL27_R03.PRO
EL27_R04.PRO
EL27_R05.PRO
EL27_R06.PRO
EL27_R07.PRO

## Componant
Component | Product Owner ID | Discipline Manager ID | FO name | Discipline Manager | FO CDSID | Description
AAR | swu97 | xgu14 | Shi, Stella | Gu, Xiaosheng | jshi32 | CVPP: Auto Air Refresh自动空气净化(硬件联动）
ACC/IACC | mcui5 | lwang70 | Cui, Victor | Wang, Lew | mcui5 | 定速巡航/智能定速巡航
Autosar | yjian | ysun15 | Jian, Ashley | Sun, Evan | yjian
Account - Enhanced Memory | xxu71 | ysun15 | Xu, Xiao Kang | Sun, Evan | xxu71 | 个人化档案（账号）
Account | swu97 | xgu14 | Wang, Johnny | Gu, Xiaosheng | jwang308 | CVPP: Account 账号
Account - Rocket setup | swu97 | xgu14 | Gu, Xiaosheng | Gu, Xiaosheng | xgu14 | CVPP: Rocket setup 账号
Animation | lhan23 | lzhu68 | Han, Lisa | Zhu, Julia | lhan23 | HMI：动效
Audio Management | LLI156 | pxu15 | Li Alvin | Xu, Roger | LLI156 | 音频管理
Authorization | swu97 | xgu14 | Gu, Xiaosheng | Gu, Xiaosheng | xgu14 | CVPP: 车机授权
Baidu Input Method | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 百度输入法
Bluetooth | xyafei | dyu12 | Xu Yafei | Yu, Diven | xyafei | 蓝牙电话，蓝牙音乐，主副驾独立蓝牙系统
Camera - Multi Camera | xwang190 | yzhan142 | Wang, Tom | Zhang, Kerry | xwang190 | 360摄像头
Camera - RePA | xhe22 | lwang70 | He, Michael | Wang, Lew | xhe22 | 远程泊车辅助
Camera - RVC | tzheng4 | yzhan142 | Zheng, Tina | Zhang, Kerry | tzheng4 | 后视摄像头
Climate Control | jli198 | gqu1 | Li, Jun | Qu, Sean | jli198 | Climate control空调温度控制
Clock | xwang65 | wwu28 | Wang Fin | Wu WenZhong, Forrest | xwang65 | 时间日期设置
Connected Embedded Navigation | swu97 | xgu14 | Shi, Stella | Gu, Xiaosheng | jshi32 | CVPP: send to car &car to phone 最后一公里
Cellular data purchase and management | swu97 | xgu14 | Lu, Chao | Gu, Xiaosheng | clu42 | CVPP: 用户流量统计及购买(第三方应用集成）
Customer Connectivity Setting | swu97 | xgu14 | Ge, Haiqing | Gu, Xiaosheng | hge5 | CVPP:Customer Connectivity Setting，用户消息提示
Customer Feedback | swu97 | xgu14 | Wang, Johnny | Gu, Xiaosheng | jwang308 | CVPP:意见反馈
Cyber Security | wding14 |  | Ding Dean |  | wding14 | Cyber Security 网络安全
Desclaimer | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | CVPP: 免责声明
Data & Carrier | swu97 |  | Fan, Henry |  | hfan11 | CVPP:数据埋点
Device Connectivity | [5 empty] | Device Connectivity 设备连接
Diagnostic | xwang65 | wwu28 | Wang Fin | Wu WenZhong, Forrest | xwang65 | Bezel Diagnostics
Digital Scent | XZHAN247 |  | Zhang, Xiaojing |  | XZHAN247 | 数字香氛
DLNA | tjia2 | dyu12 | Jia, Elaine | Yu, Diven | tjia2 | 视频、音乐、图片DLNA投屏到车机显示器区分主副驾，副驾视频播放支持
DAS | ssong18 |  | Song, Amy |  | ssong18 | driver alert system
Digital user tuturial | [5 empty] | Digital user tuturial 玩转车机-快速入门
Digital Owner's Menu | dgeng1 | wwu28 | Geng, Dekang | Wu WenZhong, Forrest | dgeng1 | 电子手册
Electric Vehicle | swu97 |  | Ji, Jerry |  | yji9 | CVPP: 电池动力汽车相关
Ethernet | cguo12 |  | Guo, Cheng Cheng |  | cguo12 | 福特以太网
Entended center display | fliu43 | lzhu68 | Liu, Luisa | Zhu, Julia | fliu43 | HMI: 分屏显示（例如导航分屏显示）
EMC
Emergency Assistance | swu97 |  | Ren, Siyuan |  | sren6 | CVPP: 紧急救援
Engineering mode | xwang65 | wwu28 | Wang Fin | Wu WenZhong, Forrest | xwang65 | Engineering mode 工程模式
EOL | ytian22 |  | Tian, Yuan |  | ytian22 | End of Line feature下线配置，福特ECU诊断
FaceID | tjia2 | dyu12 | Jia, Elaine | Yu, Diven | tjia2 | 人脸识别/驾驶员状态监控/多模手势交互(图像）
Ford Finance/Lincoln Finance | swu97 | xgu14 | Lu, Chao | Gu, Xiaosheng | clu42 | CVPP: Ford Fiance福特/林肯金融 （第三方应用集成）
FNV2 - FCI | dliu79 |  | Liu, Dapeng |  | dliu79
Ford Vehicle feature
FordPass | [5 empty] | 福特派
HardButton | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276
Hardware tuning | YLIU307 |  | Liu Yang |  | YLIU307
HMI | fliu43 | lzhu68 | Liu, Luisa | Zhu, Julia | fliu43 | 快捷面板, Persistant button
HMI - Theme Change | lhan23 | lzhu68 | Han, Lisa | Zhu, Julia | lhan23 | 主题切换
Home Smart Device Control | swu97 | xgu14 | Lu, Chao | Gu, Xiaosheng | clu42 | CVPP:车控家 vehicle to home
IOD | dyu12 | dyu12 | Yu, Diven | Yu, Diven | dyu12 | 仪表行车电脑信息：胎压，安全带，小计里程，行为辅助显示
Illumination | jchen303 | pxu15 | Chen James | Xu, Roger | jchen303 | 亮度调节
Interaction with IPK/HUD | jchen303 | pxu15 | Chen James | Xu, Roger | jchen303 | Supporting interaction with cluster,HUD and RACM.
Launcher- HMI | fliu43 | lzhu68 | Liu, Luisa | Zhu, Julia | fliu43 | HMI:快捷面板/常驻栏/对高配27"屏幕，需要支持双屏和驾驶员屏幕独占模式(超级单屏模式)/屏幕扩展显示/副驾主页/精简屏幕
Launcher - Weather forecast | swu97 | xgu14 | Shi, Stella | Gu, Xiaosheng | jshi32 | CVPP: 天气/副驾天气预报
Launcher - wireless charging module | qlyu | fding | Lyu, Qingtao | Ding, Jack | qlyu | 无线充电模块
IPPT | xlin17 |  | Lin, Shawn |  | xlin17
Location Service | dyu12 | dyu12 | Yu, Diven | Yu, Diven | dyu12 | 仪表指南针
Log system | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 日志拷贝
Lincoln Embrace | YWU150 |  | Wu, Bella |  | YWU150 | 开机动画以及关机动画时出现的灯光效果，如氛围灯，头灯尾灯，内饰灯等
Master reset | swu97 | xgu14 | Ge, Haiqing | Gu, Xiaosheng | hge5 | CVPP: 系统复位
Maintenance and service booking | swu97 | xgu14 | Wang, Johnny | Gu, Xiaosheng | jwang308 | CVPP: 维修保养提醒及在线预约保养（服务生态）
Map - DAT | yli316 |  | Li, Cindy |  | yli316 | 驾驶辅助（地图）
Map - Local Hazard Info | swu97 | xgu14 | Lin, Shawn | Gu, Xiaosheng | xlin17 | CVPP: 当地危险信息提示（地图）
Map - Navigation | xqi14 | dyu12 | Qi, Xuliang | Yu, Diven | xqi14 | 离线/在线导航，AR导航，副驾地图导航
Map - Charge Station Finder | swu97 | xgu14 | Ji, Jerry | Gu, Xiaosheng | yji9 | CVPP: 查找充电桩
Message Center& Notification Pushing | swu97 | xgu14 | Wang, Johnny | Gu, Xiaosheng | jwang308 | CVPP: 消息中心+消息推送
Message Center Client | jxu128 | wwu28 | Xu, Harriet | Wu WenZhong, Forrest | jxu128 | 仪表报警信息
MCU features
Media | xyafei | dyu12 | Xu, Amy | Yu, Diven | xyafei | Media 本地及在线音乐/本地及在线视频播放/副驾在线视频/爱奇艺（内容生态）
Online Mall | swu97 | xgu14 | Lu, Chao | Gu, Xiaosheng | clu42 | CVPP: 在线商城(第三方集成应用）
OTA | swu97 | xgu14 | Pan, Yuan | Gu, Xiaosheng | ypan23 | CVPP: (including: USB Update for TCU and ECG; IVI VMCU, CCPU...)
Power to Box | dyu12 | dyu12 | Yu, Diven | Yu, Diven | dyu12 | 硬件联动
PAAK | swu97 | xgu14 | Wang, Cindy | Gu, Xiaosheng | xwang216 | CVPP: Phone As A Key
Power Flow | dyu12 | dyu12 | Yu, Diven | Yu, Diven | dyu12 | 动力流
Parking Aid | XWANG187 | lwang70 | Wang Lynn | Wang, Lew | XWANG187 | 泊车辅助
Personal Center | [5 empty] | 泊车辅助
Personalization | [5 empty] | Personalization 个性化设置
Power management | jchen303 | pxu15 | Chen James | Xu, Roger | jchen303 | 电源管理
PictureManagement | tjia2 | dyu12 | Jia, Elaine | Yu, Diven | tjia2 | 图片/小视频浏览器; 副驾图片浏览器
Provisioning | swu97 | xgu14 | Cui, Rebecca | Gu, Xiaosheng | hcui2 | CVPP:账号激活
Radio | xwang65 | wwu28 | Wang Fin | Wu WenZhong, Forrest | xwang65 | Radio 在线收音机, 本地收音机
RNR | swu97 | xgu14 |  | Gu, Xiaosheng |  | CVPP:Real Name Registration
RSA | swu97 | xgu14 | Ren, Siyuan | Gu, Xiaosheng | sren6 | CVPP:Roadside Assistance 道路救援
Service & Payment | swu97 | xgu14 | Lu, Chao | Gu, Xiaosheng | clu42 | CVPP:Service & payment 服务生态+支付
Software Update | [5 empty] | Software Update 软件升级
SWDL
System Performance | dgeng1 | wwu28 | Geng, Dekang | Wu WenZhong, Forrest | dgeng1 | System Performance 系统性能
System Setting - Language | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
System Setting - Audio | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
System Setting - BT | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
System Setting - Date | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
System Setting - Display | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
System Setting - Others | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
System Setting - Reset | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
System Setting - Sound | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
System Setting - Wifi | dyu12 | dyu12 | Yu, Diven | Yu, Diven | dyu12 | System Performance 系统性能
System Settings - Input | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
System Settings - Notification | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | System Performance 系统性能
SoftSwitch | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 软button开关切换
System Settings - passenger setting | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 副驾系统设置
System Settings - Charge Port Light Settings | jchen276 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 充电口亮度设置
Stolen Vehicle Services | swu97 | xgu14 | Ren, Siyuan | Gu, Xiaosheng | sren6 | CVPP: 被盗车辆追踪
System Stability | dgeng1 | wwu28 | Geng, Dekang | Wu WenZhong, Forrest | dgeng1 | System Stability 系统稳定性
Tik tok | swu97 | lzhu68 | Shi, Stella | Zhu, Julia | jshi32 | CVPP: 抖音(第三方应用集成）
Theme change | lhan23 | lzhu68 | Han, Lisa | Zhu, Julia | lhan23 | HMI:主题更换
Traveling Shooting | tjia2 | dyu12 | Jia, Elaine | Yu, Diven | tjia2 | 随心拍（内容生态）
Touch Tone | YLIU307 | fding | Liu Yang | Ding, Jack | YLIU307
TSR | ssong18 | lwang70 | Song, Amy | Wang, Lew | ssong18 | Traffic Sign Recognize
User privacy
Vehicle Locator | swu97 | xgu14 | Lu, Chao | Gu, Xiaosheng | clu42 | CVPP: 车辆定位（硬件联动）
Vehicle Health Alert | swu97 | xgu14 | Lu, Chao | Gu, Xiaosheng | clu42 | CVPP:Vehicle Health Alert，Prognostics（远程提醒换机油）
Vehicle Info | swu97 | xgu14 | Ge, Haiqing | Gu, Xiaosheng | hge5 | CVPP: 车辆提示信息
Vehicle Setting on IVI - Windows Control | jxu128 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 车窗控制
Vehicle Setting on IVI - Sunroof Control | jxu128 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 天窗控制
Vehicle Setting on IVI - Trunk Control | jxu128 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 后备箱控制
Vehicle Setting - SDM | jxu128 | wwu28 | Gu, Zhengfu |  | zgu11 | 驾驶模式选择
Vehicle Setting on IVI - Others | jxu128 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 其他车辆设置
Vehicle Setting - V2I | swu97 | xgu14 | Fan, Henry | Gu, Xiaosheng | hfan11 | CVPP:车与基础设施、互联网之间的通信，包括个人通信，移动办公，远程信息处理，基于位置的信息，与汽车相关的移动服务，视频直播，和互联网接入
Vehicle Setting - Lane centering assist | jxu128 | wwu28 | Ni, Anthony |  | hni1 | 高速驾驶辅助，车道中央保持
Vehicle Setting - Lane Change Warning | jxu128 | wwu28 | Zhou, Wu | Zhang, Kerry | wzhou44 | 变道警告，盲点监测
Vehicle Setting - Intelligent Speed Assistance | jxu128 | wwu28 | Song, Amy | Wang, Lew | ssong18 | 智能车速辅助
Vehicle Setting - Lane departure warning | jxu128 | wwu28 | Zhang, Wayne |  | wzhan114 | 车道偏离，车道保持
Vehicle Setting - Collision | jxu128 | wwu28 | Wang, Lynn | Wang, Lew | xwang187 | 碰撞缓解，碰撞预警
Vehicle Setting - Multi-Contoured Seats | jxu128 | wwu28 | Xia,Zhiqiang | Hu, Kevin | zxia13 | 多功能座椅
Vehicle Setting - One Pedal Drive | jxu128 | wwu28 | Chen, Emma | Wu WenZhong, Forrest | jchen276 | 单踏板模式（电动车）
Vehicle Setting - Auto High beam | jxu128 | wwu28 | Song, Amy | Wang, Lew | ssong18 | 自动远光灯
Vehicle Setting - Ambient Lighting | jxu128 | wwu28 | Fu, Theo |  | XFU7 | 氛围灯音乐可视化，呼吸控制
Vehicle Setting - Mykey | jxu128 | wwu28 | Xu, Xiao Kang | Sun, Evan | xxu71
Voice Recognition | xqi14 | dyu12 | Qi, Xuliang | Yu, Diven | xqi14 | Include Content，Nav，Q&A，Vehicle Condition Query，Vehicle Control基础及增强型语音功能，双音区语音识别
Virtual Personal Assistant | FSUO |  | Sophia Suo |  | FSUO | Virtual Personal Assistant
Voice Query | swu97 | xgu14 | Lu, Chao | Gu, Xiaosheng | clu42 | CVPP: 违章查询，鲜花预订 ，机票查询，火车票查询（语音垂类）
Welcome animation | ywu150 | ysun15 | Wu, Bella | Sun, Evan | ywu150 | 开机动画(Power)
WiFi Hotspot | swu97 | xgu14 | Pan, Yuan | Gu, Xiaosheng | ypan23 | CVPP:车载热点
xHEV | swu97 | xgu14 | Ji, Jerry | Gu, Xiaosheng | yji9 | CVPP:电池动力汽车相关
Zone Lighting | dyu12 | dyu12 | Yu, Diven | Yu, Diven | dyu12 | 360 Lighting
硬件降噪 Noice cancellation by hardware | YLIU307 | fding | Liu Yang | Ding, Jack | YLIU307