## Slide 1: Phase5 SW Validation Plan
Think
Point of view
Plan to Implement
Implement
Roger Xu, Zhengxi Xiang, Jiajia Zhou
Date: March 15, 2021
Desired Outcome
Awareness
Decision
Escalation Help

## Slide 2: CDX707 SW Release Plan @03/24
CDX707 VPP
Display(23.6+23.6,11.1 touch)
SW Release for CAF/FO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
06/11
SW Release for REC
PEC
06/13
PA
07/14
FDJ
08/20
TT
08/24
PP
11/09
MP1
02/01
DCV
02/02
DCV Alpha
03/19
DCV Beta
08/02
A0 PCBA
01/25
CDC AHU HW
A1 PCBA
05/25
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
DCV Alpha1
03/31
DCV Alpha2
04/28
DCV Alpha3
05/26
DCV Alpha4
06/23
DCV Beta1
08/18
DCV Beta2
09/15
DCV0
10/20
DCV0.1
11/17
DCV1
12/15
DCV2
01/12
DCV3
02/23
R00
03/23
R01
04/20
R04
05/18
R05
06/15
R05.1
07/13
R05.2
08/10
R06
09/07
R06.1
10/19
R07
11/20
R08 for OKTB
01/15
2021 | 2022 | 2023
07/10-08/20
10/25-1/25
05/15-06/15
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
MP2
03/01
FEC
07/25
OKTB
03/28
DCV0
11/03
DCV1
12/29
DCV2
01/26
DCV3
03/09
R01
05/04
R04
06/01
R05
06/29
R05.1
07/27
R00
04/06
R05.2
08/24
R06
09/21
R06.1
11/02
R07
12/04
R08 for OKTB
01/24
R09 for OTA
04/28 TBD
PEC1
07/26
FEC1
09/06
DCV Beta
07/18

## Slide 3: CDX707 SW Release Plan @06/15
CDX707 VPP
SW Release for CAF/FO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
06/11
SW Release for REC
PEC
06/13
PA
07/14
FDJ
08/20
TT
08/24
PP
11/09
MP1
02/01
DCV
02/02
DCV Alpha
03/19
DCV Beta
08/02
DCV Alpha1
03/31
DCV Alpha2
04/28
DCV Alpha3
05/26
DCV Alpha4
06/23
DCV Beta
07/18
08/01
DCV Beta1
08/18
DCV Beta2
09/15
DCV0
10/20
DCV0.1
11/17
DCV1
12/15
DCV2
01/12
DCV3
02/23
R00
03/23
R01
04/20
R04
05/18
R05
06/15
R05.1
07/13
R05.2
08/10
R06
09/07
R06.1
10/19
R07
11/20
R08 for OKTB
01/15
2021 | 2022 | 2023
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
MP2
03/01
FEC
07/25
OKTB
03/28
DCV0
11/03
DCV1
12/29
DCV2
01/26
DCV3
03/09
R01
05/04
R04
06/01
R05
06/29
R05.1
07/27
R00
04/06
R05.2
08/24
R06
09/21
R06.1
11/02
R07
12/04
R08 for OKTB
01/24
R09 for OTA
04/28 TBD
ENG + PRO
ENG

## Slide 4: Phase5 软件测试流程
JIRA
Supplier Bug Platform( )
Critical Issues
Other Issues
Ford
System Test
Smoke Test
Full/Focus Test
Regression Test
YFVE/Baidu/In-house/ThunderSoft
Priority | Description
Critical (Immediate Gating) | System Satiability issue
 | System Performance issue
 | Function Loss impact Test/Launch
 | Function Safety failure
Critical (Gating) | Main Function Loss/Incorrect
 | High Frequency using Minor Function Loss/Incorrect
iCafe
Redmine

## Slide 5: Phase5 软件验收标准
1. 命名规则：
  SOC:DateBulidNum_F/L+Variant_SWReleaseVersion_ENG/PRO_QNX/Android
  MCU:DateBulidNum_F/L+Variant_SWReleaseVersion_ENG/PRO_MCU
  文件命名详见
2. 文档说明
  该版软件需求点List和合入点Check List 。
  软件release note
  软件test report（summary & 测试用例执行detail）
  DID & DID Report
  注：
  Release Note：由YFVE统一搜集Baidu与In-House部分，整理成一份文档
  需求List/合入点Check List/ Test Report：YFVE、Baidu、In-House提交各自的文档
3. 质量标准：
见Next Slide
Supplier | 需求/修改文档 | 合入点Check List | Release note | Test report | DID&DID Report
YFVE |  |  |  |  | 
Baidu |  |  |  |  | 
In-House |  |  |  |  | 

## Slide 6: Phase5 软件验收标准
要求点 | FDJ | DCV | TT | PP | MP1/MP2
软件完整度 | 模块开发完成度>40% | 模块完成95% | 模块完成100% | 模块完成100% | 模块完成100%
遗留问题、问题关闭情况 | IG级缺陷修复率=100% | IG级缺陷修复率=100% G级缺陷修复率>70% H级缺陷修复率>50% | IG级缺陷修复率=100% G级缺陷修复率>85% H级缺陷修复率>60% M级缺陷修复率>50% | IG级缺陷修复率=100% G级缺陷修复率 =100% H级缺陷遗留≤20个 M级缺陷遗留≤10个 | IG级缺陷修复率=100% G级缺陷修复率 =100% H级缺陷遗留≤5个 M级缺陷遗留≤5个
需求分析完成率 | 需求完成率>50% | 需求完成率=100% | 需求完成率=100% | 需求完成率=100% | 需求完成率=100%
Smoke测试 | Run Rate/Pass Rate 70%/100% | Run Rate/Pass Rate 100%/100% | Run Rate/Pass Rate 100%/100% | Run Rate/Pass Rate 100%/100% | Run Rate/Pass Rate 100%/100%
Integration Test(Interface) | - | Run Rate/Pass Rate 95%/90% | Run Rate/Pass Rate 100%/95% | Run Rate/Pass Rate 100%/100% | Run Rate/Pass Rate 100%/100%
Function Test | - | Run Rate/Pass Rate 95%/90% | Run Rate/Pass Rate 100%/95% | Run Rate/Pass Rate 100%/100% | Run Rate/Pass Rate 100%/100%
System Test | - | - | Run Rate/Pass Rate 90%/90% | Run Rate/Pass Rate 100%/99% | Run Rate/Pass Rate 100%/100%
性能测试 | - | Pass Rate>30% | Pass Rate>80% | Pass Rate=100% | Pass Rate=100%
稳定性测试 | - | Monkey 单模块运行时长达到8小时； 点击频率可以达到500ms | 单模块/系统Monkey运行时长达到24小时； 点击频率可以达到500ms; MTBF值>24小时； | 单模块/系统Monkey运行时长达到48小时； 点击频率可以达到500ms; MTBF值>48小时； | 单模块/系统Monkey运行时长达到48小时； 点击频率可以达到500ms; MTBF值>64小时；
可靠性测试 | - | 某一功能使用频次达到目标设定（具体 功能， 目标具体设定， 比如蓝牙连接 成功率， 回连成功率）Pass Rate>60% | 某一功能使用频次达到目标设定（具体功 能， 目标具体设定， 比如蓝牙连接成功率， 回连成功率）Pass Rate>80% | 系统累计运行达到目标值（待定）， 将多个功能进行 交叉进行， 每一个功能操作次数达到目标值， 看系统 累计运行时长， 包括开关机 Pass Rate=100% | 系统累计运行达到目标值（待定）， 将多个功能进行 交叉进行， 每一个功能操作次数达到目标值， 看系统 累计运行时长， 包括开关机 Pass Rate=100%
兼容性测试 | - | - | Run Rate/Pass Rate 100%/85% | Run Rate/Pass Rate 100%/100% | Run Rate/Pass Rate 100%/100%
预认证测试 | - | 具备Pre-Test开始条件 | 预认证测试通过 | 认证测试通过 | 认证测试通过

## Slide 7: Phase5 Issue Priority定义
Priority | Description | Example
Critical (Immediate Gating) | System Satiability issue | - IVI whole screen black. - IVI system reset automatically - IVI startup black screen
 | System Performance issue | - Screen cannot touch and cannot recover until reset - Shift to gear R, black screen display. - Shift to gear R, RVC displays in about 30 seconds
 | Function Loss impact Test/Launch | - Radio not working, impact Reception Test - EOL function loss, impact production launch
 | Function Safety failure | - 紧急救援Emergency Assistance (EA) - 道路救援Road Side Assitance (RSA) - 儿童座椅报警
Critical (Gating) | Main Function Loss/Incorrect | - Climate Control cannot working - No Seatbelt Chime can be hear from speaker
 | High Frequency using Minor Function Loss/Incorrect | - BT phone cannot be disconnected from IVI - Shift among all the media source can’t memory last song
High | Minor Function Loss/Incorrect | - Can’t order film ticket via VR
 | HMI design impact user experience | - Back button too small
Medium | HMI need improve | 
 | Function logic not friendly need improve | 
Low | Other issue | 

## Slide 8: Phase5 软件需求/合入点模板
ID | JIRA ID | 需求点Title | 需求点Description | 需求来源方 | 合入需求版本 | 影响车型 | 开发方 | 合入点变动描述 | 合入点影响评估 | 合入点是否影响其他车型 | 验证方法 | 验证结果
 | NA | 需求Summary | 这里填写本需求详细描述 | 需求来源于哪个team。 该需求由谁澄清 | 提需求时需要在哪个版本合入这个需求 | 需描述到具体车型的具体系列 | 1. 需求有哪个team负责开发，谁在跟进 |  |  |  |  | 

## Slide 9: Phase5 软件问题评估模板
ID | JIRA ID | Lead Supplier | 问题Category | 问题首次发现方 | 对客户(或者工厂产线/dealer售后)影响 | 问题产生的背景 | 影响车型 | 主线/分支 | 负责人 | 问题root cause | 修复计划（timing等） | 问题修复/验证措施 | 是否合入修复 | 验证时间 | 验证结果
 | NA | YFVE | 这里填写问题领域，如： 导航 地图数据 随心听 AAR 座椅控制 语音识别 系统稳定性 等等 以便team评审时快速筛选 | 问题首次发现方： 1.Baidu 2.YFVE 3.REC EE 4.REC CVPP 5.CAF | 对市面上实际用户的影响。 对工厂产线影响。 对dealer售后的影响。 | 解决什么问题或者添加什么功能而引发的issue | 需描述到具体车型的具体系列 | 发生问题的代码分支编号 | xx | xxx |  | 从代码层面design review，用示意图画出来阐述思路。 测试case制定，测试资源投放明细 | 1.决定合入。 2.暂不合入。 3.无法决定 | xx | PASS/FAIL