## Cover
SOFTWARE RELEASE NOTES
Product/Module Name | Phase5
Rational Team Concert Project Area
Rational Team Concert Team Area
Project ID | 29662
Release Organization

## Ford
Module |  | Feature/Issue Describtion | Remark
Launcher | Fixed Issues | 修正 APIMCIM-8471 APIMCIM-7586 APIMCIM-6545 修正 APIMCIM-3778 APIMCIM-4276 APIMCIM-7827 修正 APIMCIM-5411 修正 APIMCIM-1988
| New Feature | 增加 UEUI V4.0.0（sign off） 增加Launcher Widget画面 增加Launcher Widget编辑画面 增加All App画面
Audio Setting | Fixed Issues | 修正 APIMCIM-8822 APIMCIM-8851 APIMCIM-8854 APIMCIM-8504 APIMCIM-8148 APIMCIM-8146 APIMCIM-6650 APIMCIM-8503 APIMCIM-8682 APIMCIM-8147 修正 APIMCIM-2175 修正 APIMCIM-1283
| New Feature | 增加 UEUI更新内容 v1.6.0（sign off） 增加 触摸提示音 设置 增加 均衡器 设置 增加 音随车速 增加 音量 设置
Vehicle Settings | Fixed Issues | 修正 APIMCIM-8461 APIMCIM-7973 APIMCIM-5443 APIMCIM-7730 APIMCIM-7224 APIMCIM-8646 APIMCIM-8651 APIMCIM-8650 APIMCIM-8667 APIMCIM-8668 APIMCIM-8707 APIMCIM-8669 APIMCIM-8664 APIMCIM-7873 APIMCIM-8036 APIMCIM-6761 APIMCIM-8001 APIMCIM-7879 APIMCIM-8623 APIMCIM-8713 APIMCIM-5609 APIMCIM-8592 APIMCIM-7593 APIMCIM-7592 APIMCIM-7594 APIMCIM-8478 APIMCIM-8726 APIMCIM-7712 APIMCIM-7729 APIMCIM-8347 APIMCIM-7201 APIMCIM-5469 APIMCIM-8715 APIMCIM-8714 APIMCIM-7761 APIMCIM-3545 APIMCIM-8802 APIMCIM-8663 APIMCIM-8723 APIMCIM-7732 APIMCIM-8780 APIMCIM-5833 APIMCIM-8649 APIMCIM-8758 APIMCIM-8804 APIMCIM-8330 APIMCIM-8806 APIMCIM-8662 APIMCIM-8807 APIMCIM-8808 修正 APIMCIM-4135 APIMCIM-7737 APIMCIM-7730 APIMCIM-4407 APIMCIM-5603 APIMCIM-3732 APIMCIM-7754 APIMCIM-7928 APIMCIM-6756 APIMCIM-6748 APIMCIM-8132 APIMCIM-7216 APIMCIM-5934 APIMCIM-5673 APIMCIM-5435 APIMCIM-5936 APIMCIM-5825 APIMCIM-5886 APIMCIM-4200 APIMCIM-5833 APIMCIM-6598 APIMCIM-6905 APIMCIM-6904 APIMCIM-6898 APIMCIM-6600 APIMCIM-3937 APIMCIM-5726 APIMCIM-7201 APIMCIM-5604 APIMCIM-4097 APIMCIM-5552 APIMCIM-8239 APIMCIM-1083 APIMCIM-7761 APIMCIM-5427 APIMCIM-5571 APIMCIM-6571 APIMCIM-7186 APIMCIM-7762 APIMCIM-5607 APIMCIM-3967 APIMCIM-4458 修改 APIMCIM-4415 APIMCIM-5601 APIMCIM-4331 APIMCIM-3456 APIMCIM-5483 APIMCIM-3537 APIMCIM-4485 APIMCIM-4472 APIMCIM-4004 APIMCIM-5577 APIMCIM-5578 APIMCIM-5071 APIMCIM-5416 APIMCIM-5433 APIMCIM-3717 APIMCIM-5604 APIMCIM-5726 APIMCIM-2100 APIMCIM-4364 APIMCIM-3689 APIMCIM-5437 APIMCIM-5743 修正 APIMCIM-3932 修正 APIMCIM-3368、APIMCIM-3540、APIMCIM-2117、APIMCIM-3597、APIMCIM-2107、 APIMCIM-3591、APIMCIM-3003、APIMCIM-3326、APIMCIM-2139、APIMCIM-3485、 APIMCIM-3522、APIMCIM-2128、APIMCIM-2112、APIMCIM-3534、APIMCIM-3525、 APIMCIM-3384、APIMCIM-3529、APIMCIM-3530、APIMCIM-3600、APIMCIM-3527、 APIMCIM-3201、APIMCIM-2113、APIMCIM-3521、APIMCIM-2047、APIMCIM-2141、 APIMCIM-2135、APIMCIM-2133、APIMCIM-2111、APIMCIM-1252、APIMCIM-2262、 APIMCIM-2279、APIMCIM-3213、APIMCIM-3220、APIMCIM-2281、APIMCIM-2263、 APIMCIM-2282、APIMCIM-3193、APIMCIM-2120 修正 APIMCIM-1220、APIMCIM-1262、APIMCIM-1271、APIMCIM-1193、APIMCIM-1219、APIMCIM-1244、APIMCIM-1236、APIMCIM-1214、APIMCIM-1432、APIMCIM-1085、APIMCIM-1287、APIMCIM-1220、APIMCIM-1177、APIMCIM-1221
| New Feature | 增加 UEUI更新内容 v3.4.0(sign off) 增加 DIDC功能 增加 Seat Temperature Control Setting for Remote Start设定 增加 Heated Steering Wheel Setting for Remote Start设定 增加 Power Liftgate Soft switch设定 增加 Traffic Sign Recognition设定 增加 Blindspot Detection设定 增加 手机钥匙Phone as key(PaaK)设定 增加 Ambient Lighting 128 Color设定 增加 Power running boards设定 增加 Park Lock Control 设定 增加 Silent Mode 设定 增加 Alarm System设定 增加 Remote start设定 增加 Windows (remote open/close) 设定 增加 Wipers 设定 增加 Rear liftgate（auto/manual）设定 增加 Tire Mobility Kit 设定 增加 Easy Entry / Easy Exit (Seat Adjustment)设定 增加 Glare Free lighting 设定 增加 daytime lights设定 增加 welcome lights设定 增加 Light Setting-Adaptive headlamps设定 增加 Autolamp delay设定 增加 Lock Setting设定 增加 Mirror Setting设定 增加 Lane Centering Assist设定 增加 Pre Collision Assist设定 增加 Phone Wireless Charging notification 增加 数字香氛 增加 驾驶辅助_车距提示 设置 增加 倒车制动辅助设置 增加 Chimes设置 增加 Passenger Airbag ON/OFF设置 增加 自动驻车 设置项 增加 自动启停 设置项 增加 自动启停阈值 增加 疲劳驾驶预警 设置项 增加 碰撞预警 设置项 增加 车距提示 设置项 增加 自动紧急制动 设置项 增加 转向避险辅助 设置项 增加 灵敏度 设置项 增加 车速限制 设置项 增加 车速限制辅助 设置项 增加 牵引力控制 设置项 增加 逆行提醒 设置项 增加 电动后尾门/后备箱 设置项 增加 斜坡辅助 设置项 增加 陡坡缓降控制 设置项 增加 斜坡起步辅助 设置项 增加 Multi contour seat 设置项 增加 车道偏离预警 设置项 增加 驾驶员警告系统 设置项 增加 自动远光灯 设置项 增加 Drive Modes 设置项 增加 牵引力控制 设置项
HVAC | Fixed Issues | 修正 APIMCIM-9014 APIMCIM-9017 APIMCIM-7292 APIMCIM-7670 APIMCIM-8834 APIMCIM-8833 APIMCIM-9023 APIMCIM-9020 APIMCIM-9019 APIMCIM-9018 APIMCIM-9016 APIMCIM-9027 APIMCIM-9024 APIMCIM-7917 APIMCIM-8829 APIMCIM-8761 修正 APIMCIM-7745 APIMCIM-6994 修正 APIMCIM-3584、APIMCIM-3585、APIMCIM-3036
| New Feature | 增加 UEUI更新内容 V3.5.0（sign off） 增加 Heated Mirrors 增加 Heated Backlight (climate) 增加 AC-Face 设置 增加 AC-Feet 设置 增加 AC On/Off 设置 增加 Auto AC设置 增加 Dual AC 设置 增加 Max AC 设置 增加 Recirc. 设置 增加 Steering wheel heated 设置 增加 Windshield 设置
VHA | Fixed Issues | 修改 APIMCIM-8727 修改 APIMCIM-7659 APIMCIM-3270 APIMCIM-7776 APIMCIM-5718 APIMCIM-5695 修改 APIMCIM-5683 APIMCIM-5722 修正 APIMCIM-3358、APIMCIM-1251、APIMCIM-1246 修正 APIMCIM-1167、APIMCIM-1234、APIMCIM-1251、APIMCIM-1246、APIMCIM-1155、APIMCIM-1138、APIMCIM-1225
| New Feature | 追加 UEUI更新 v3.2.0(sign off) 增加 VHA功能
AAR | Fixed Issues | 修正 APIMCIM-7324 APIMCIM-9032 APIMCIM-8916 APIMCIM-8365 APIMCIM-7752 APIMCIM-7941 APIMCIM-8281 修正APIMCIM-7245 APIMCIM-7204 APIMCIM-7168 APIMCIM-6815 APIMCIM-7035 APIMCIM-7848 APIMCIM-7845 APIMCIM-7989 APIMCIM-7747 APIMCIM-8003 APIMCIM-5657 APIMCIM-3364 修正 APIMCIM-5533 修正 APIMCIM-3364、APIMCIM-3366、APIMCIM-3365、APIMCIM-3531
| New Feature | 追加 UEUI更新 v2.7.1(sign off) 增加 AAR功能
EMR | Fixed Issues | NA
| New Feature | 增加 吹风动效 增加 EMR功能
FAPA | Fixed Issues | 修正 APIMCIM-7261 APIMCIM-7900 APIMCIM-8781 APIMCIM-7253 APIMCIM-7899 APIMCIM-7898 APIMCIM-7897 APIMCIM-8224 APIMCIM-8122 APIMCIM-8203 修正 APIMCIM-4204
| New Feature | 追加 UEUI更新 v2.0.0(sign off) 增加 FAPA功能
RePA | Fixed Issues | NA
| New Feature | 增加 RePA功能
TNC Service | Fixed Issues | NA
| New Feature | 追加 隐私条款功能
Voice Service | Fixed Issues | 修正 APIMCIM-8762 APIMCIM-4381 APIMCIM-3749 APIMCIM-8703 修正 APIMCIM-3356 APIMCIM-3816 APIMCIM-5602 APIMCIM-4451 APIMCIM-5357 APIMCIM-6987 APIMCIM-6942 APIMCIM-6969 APIMCIM-4374 APIMCIM-6814 APIMCIM-6828 APIMCIM-3079 APIMCIM-3238 修正 APIMCIM-5760 APIMCIM-4406 APIMCIM-264 APIMCIM-3258 APIMCIM-5815 APIMCIM-6812 APIMCIM-6810 APIMCIM-5344 APIMCIM-3820 APIMCIM-5610 APIMCIM-5814 APIMCIM-2094 修正 APIMCIM-1247
| New Feature | 追加 TTS通路 追加 语音设置通路 追加 可见即可说通路 追加 车控&蓝牙设置通路
Ford Cloud Service | Fixed Issues | NA
| New Feature | 追加 福特云对接服务
Ford Account | Fixed Issues | 修正 APIMCIM-6851 APIMCIM-6858 APIMCIM-6848 APIMCIM-6853 APIMCIM-7658 修正 APIMCIM-7213 APIMCIM-7259 修正 APIMCIM-5613
| New Feature | 追加 UEUI更新 v3.3.0(sign off) 增加 账号登录 增加 账号登出 增加 账号列表 增加 账号自动登录
3D车模 | Fixed Issues | 修正 APIMCIM-7238 APIMCIM-7777 APIMCIM-7772 APIMCIM-7775 APIMCIM-7774 APIMCIM-7878 APIMCIM-7237 APIMCIM-8955 APIMCIM-9085 APIMCIM-8938 APIMCIM-8971 APIMCIM-8960 APIMCIM-8910 APIMCIM-7770 APIMCIM-7694 APIMCIM-8904 APIMCIM-8959 APIMCIM-8975 APIMCIM-9092 APIMCIM-8908 APIMCIM-7779 修正 APIMCIM-6831 APIMCIM-7977 APIMCIM-7890 APIMCIM-7886 APIMCIM-7735 APIMCIM-7733 APIMCIM-7711 APIMCIM-7707 APIMCIM-7689 APIMCIM-7675 APIMCIM-7660 APIMCIM-6844 APIMCIM-8268 APIMCIM-7887 APIMCIM-7721 APIMCIM-6863 APIMCIM-7229 APIMCIM-5627 APIMCIM-5628 修正 APIMCIM-5624 APIMCIM-5618 APIMCIM-5691 APIMCIM-5625 APIMCIM-5615 APIMCIM-5620 APIMCIM-5621 APIMCIM-5622 APIMCIM-5623 APIMCIM-5642 APIMCIM-5614 APIMCIM-5643 APIMCIM-5626 APIMCIM-5641 APIMCIM-6861 APIMCIM-6860 APIMCIM-6849 APIMCIM-6847 APIMCIM-6823
| New Feature | 增加 UEUI更新 UE v3.8.2(sign off) UI v3.8.0 增加 3D车模2.0功能 增加 3D车模
TA/CA | Fixed Issues | NA
| New Feature | 增加 AES128 CBC加解密方式 增加 TA/CA机制
VehicleControl | Fixed Issues | 修正 APIMCIM-1269
| New Feature | 增加 Fan 设置 增加 Front Row Seat Heated 设置 增加Front Seat Vent 设置 增加Max windshield 设置 增加Passenger temp 设置 增加Rear climate fan设置 增加Rear climate mode设置 增加Rear climate temp设置 增加Auto Dim设置
TP&LBP&FBMP | Fixed Issues | NA
| New Feature | 增加RACM功能通路
CarAudio | Fixed Issues | 修正 APIMCIM-4163 APIMCIM-6909 APIMCIM-3618 APIMCIM-7154 APIMCIM-4140 APIMCIM-1078 修正 APIMCIM-6522 APIMCIM-4078 APIMCIM-4338 APIMCIM-5425 APIMCIM-888 APIMCIM-1078 APIMCIM-4129 修正 APIMCIM-3558 配合百度音源焦点申请时序变更的修改
| New Feature | 增加 内外置功放音源管理 内外置功放切源策略 内外置功放音频策略 内外置功放音频路由 内外置功放音量控制 内外置功放音效设置 lastaudio功能 蓝牙耳机策略和通道管理 蓝牙耳机音量控制 standby音频管理 多mic录音功能管理 音频存储管理
CarPower | Fixed Issues | NA
| New Feature | 增加 电源状态切换 增加 关机流程处理 增加 Inactive/active状态的蓝牙wifi,audio的disbale/enable
CarInput | Fixed Issues | 修正 APIMCIM-8247 APIMCIM-8683 修正 APIMCIM-3088、APIMCIM-3116、APIMCIM-2057、APIMCIM-3683
| New Feature | 增加 Lincoln Park Assist Shortcut key 增加 Drive mode 增加 IVI interface via press physical switch
Enhanced Memory | Fixed Issues | 修正 FCIVIOS-4888
| New Feature | 增加 EnhancedMemory功能
Multi-Display data collection | Fixed Issues | NA
| New Feature | 增加 来电号码及名称显示
SystemPolicy | Fixed Issues | NA
| New Feature | 增加满足限制条件时的应用弹框策略
SOA Gateway | Fixed Issues | NA
| New Feature | 增加SOA Gateway功能
WIR | Fixed Issues | 修正 APIMCIM-3267
| New Feature | 增加WIR功能
CCS | Fixed Issues | 修正 APIMCIM-7669 APIMCIM-5569 修正 APIMCIM-5498 APIMCIM-5583 APIMCIM-5569 修正 APIMCIM-3311、APIMCIM-3318、APIMCIM-3312、APIMCIM-3266、APIMCIM-3321、 APIMCIM-3325、APIMCIM-3323、APIMCIM-3324
| New Feature | 增加 CCS功能
IPPT | Fixed Issues | 修正 APIMCIM-3572 配合V2I要求修改IPPT逻辑
| New Feature | 增加 IPPT功能
Diagnostic(SOA Related) | Fixed Issues | NA
| New Feature | 增加FNV bezel diagnostic功能 TCU和ECG诊断信息获取
IVI Provisioning | Fixed Issues | NA
| New Feature | 增加 Provisioning功能
Diagnostics&Analytics | Fixed Issues | NA
| New Feature | 增加 Diagnostics功能 | 云端上传存在Bug，需要北美对策。
OTA | Fixed Issues | 修正 APIMCIM-8213 APIMCIM-8214 APIMCIM-7895 APIMCIM-8442 APIMCIM-8906 APIMCIM-9059 修正 APIMCIM-6882 APIMCIM-6691 APIMCIM-6487 APIMCIM-6880 APIMCIM-7877 APIMCIM-6903 APIMCIM-7211 APIMCIM-6902 APIMCIM-6908 APIMCIM-6488 修正 APIMCIM-6484 APIMCIM-6485 APIMCIM-6489 APIMCIM-6551 APIMCIM-7034 APIMCIM-6690
| New Feature | 追加 UEUI更新 v2.5.0(Signoff) 增加 SYNC+ USB&OTA更新 增加 ECG&TCU USB&OTA更新
DLNA | Fixed Issues | 修正 APIMCIM-8884 修正 APIMCIM-7650
| New Feature | 增加DLNA功能对接
GNSS | Fixed Issues | NA
| New Feature | 增加GNSS功能
流量统计 | Fixed Issues | NA
| New Feature | 增加云端上传相关功能 增加流量统计功能

## R05_MUST_FIX
问题类型 | 概要 | 经办人 | 优先级 | 状态 | 修复的版本 | 模块
APIMCIM-3545 | Phase 5：【必现】尾灯动画没有pre-animation 显示 | rqi2 | High | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-7240 | MMOTA Test: ASU=OFF, trigger OTA upgrade, the system update reminder pop-up window does not pop up, when it is ready to activate, the system update schedule is not set and the pop-up box does not pop up | jwu187 | Gating | Test | LA_R05_ENG | MMOTA
APIMCIM-3939 | Phase 5：【偶发】空调控制界面点击无作用，无信号下发 | rqi2 | Immediate Gating | Closed with Accept | LA_R04_ENG | Climate
APIMCIM-9234 | Phase 5：【必现】媒体音量调到调节音量到1~5或19~30，发(0x2E3):HMI_HMIMode_St 由OffMode变为On，音量无变化 | yyang179 | Gating | Closed with Accept | LA_R05_ENG | Audio
APIMCIM-8771 | Phase5：【必现】爱奇艺投屏到Card 4，更换主题，点击所有应用按钮，操作屏黑屏 | jchen384 | Immediate Gating | Closed with Accept | LA_R04_ENG | System Stability
APIMCIM-7950 | [100%] MMOTA_China: FOTA目录内存不足时，USB升级SOC时一直卡在下载，且IVI无报错弹窗 | yli391 | Gating | Closed with Accept | LA_R04_ENG | MMOTA
APIMCIM-8761 | Phase 5：【必现】空调界面打开时，打开设置项界面并关闭，空调界面的关闭按键消失 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | Climate
APIMCIM-9066 | Phase 5：【必现】语音无法控制精简屏幕 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | VR
APIMCIM-8623 | Phase 5：after TCS DrvSlipCtlMde_D_Ind signal value changed, DrvSlipCtlMde_D_Rq value shall be update | yzhan482 | Gating | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8714 | Phase 5：【必现】驾驶模式页面应显示每个驾驶模式对应的动画 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8347 | Phase 5：【必发】只显示防眩照明时，点击请求打开，应下发0x2 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8034 | Phase 5：【必现】连接副驾蓝牙耳机，播放副驾QQ音乐，VR：增大/ 减小副驾蓝牙耳机音量，车机无反应 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | VR
APIMCIM-4134 | Phase 5：【必现】唤醒语音：说关闭智能新风，播报错误：打开智能馨风 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | VR
APIMCIM-8008 | Phase 5：【必现】你好，林肯唤醒后，返回主界面无反应 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | VR
APIMCIM-7761 | Phase 5：【必现】QUERY缺少Feature ID: 807/80B | yzhan482 | Gating | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8780 | Phase 5：【必现】智能预测巡航list不应在选中定速巡航时显示 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8715 | Phase 5：【偶现】机油寿命进度条偶现颜色会消失 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-5833 | Phase 5：CDX707 【必现】DE01 BYTE4 BIT7 =FHEV没有显示能量流界面 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-7749 | Phase5[CDX707]:[必现] 空气过滤状态改变，空调界面图标不同步 | xwang310 | Gating | Approval | LA_R05_ENG | AAR
APIMCIM-8970 | Phase 5：【必现】长按VOL key重启车机，会先弹出toast"媒体音频已关闭"，再执行重启 | jxu150 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-8713 | Phase 5：【必现】车道保持系统点击切换模式，切换选中卡顿 | yzhan482 | Gating | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-8851 | Phase 5：【必现】通话音会被平衡/衰减调节所影响 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-8829 | Phase 5：【必现】空调AAR的历史记录页面数值模拟后无显示 | tshan3 | Gating | Approval | LA_R05_ENG | Climate
APIMCIM-8703 | Phase 5：【必现】开机第一次通过语音打开道路救援，无法打开 | hpeng31 | Gating | Approval | LA_R05_ENG | VR
APIMCIM-7253 | Phase5_【CDX707】【黑盒】【必现】【FAPA】发送对应Can信号后，摄像头画面显示不正常 | cchen244 | Gating | Approval | LA_R05_ENG | Fapa
APIMCIM-5469 | Phase 5：【必现】调节某个腰托或支撑等级时，文字list应highlight（FO建议） | yzhan482 | High | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-8528 | Phase 5：【偶现】在主题设置页面，点击“主页”按钮，页面出现闪屏现象，且无法回到主页页面 | mchen127 | Gating | Approval | LA_R04_ENG | Vehicle Setting
APIMCIM-8510 | Phase5:[CDX707][100%]App store输入条件搜索一直显示无结果 | cshengji | Gating | Approval | LA_R05_ENG | appstore
APIMCIM-8512 | Phase5:[CDX707][100%]应用商城里面的app下载完成后卸载不了 | swang218 | Gating | Approval | LA_R05_ENG | appstore
APIMCIM-9267 | Phase 5：【必现】APA Gen8 delUXe - APIM shall support DE03 0x04 FAPA w APA Deluxe while currently it only support 0x06 APA w REPA w APA Deluxe | xwu134 | High | Approval | LA_R05_ENG | Fapa
APIMCIM-8854 | Phase 5：【必现】语音播报会被平衡/衰减调节所影响 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-8822 | Phase 5：外置功放，QQ音乐播放没有声音，但是按键触摸音和chime播放声音正常 | mxia13 | High | Approval | LA_R05_ENG | Audio
APIMCIM-8884 | Phase 5：【必现】WIFI已连接设备热点后，媒体投射中手机热点模式无法连接此设备热点 | jhe83 | Gating | Approval | LA_R05_ENG | DLNA
APIMCIM-8781 | Phase 5：【必现】APA Gen8 delUXe - 动态车位显示区域扩展，小车，扫描线动画，泊入轨迹动画上移 | xwu134 | Gating | Approval | LA_R05_ENG | Fapa
APIMCIM-8919 | Phase 5：【必现】熄火后开关车门，再点火，音乐在播放，但无声 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-8203 | Phase 5: 【偶发】ApaMde_D_Stat=0x1 OFF& Displaymode=0x0 off后APA界面未退出 | wchen154 | Gating | Approval | LA_R05_ENG | Parking Assist
APIMCIM-8057 | Phase 5：【必现】全部应用搜索界面调起键盘收到来电后挂断未留在搜索界面 | yliu350 | Gating | Approval | LA_R05_ENG | Input
APIMCIM-7985 | Phase 5：【必现】不会随着车速的高低改变通话音量 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-7779 | Phase5:【必现】[CDX707]3D车模天窗动画时间较长，动画过程中车模视角回到右侧45度默认视角，再切到左侧45度，车头下压20度，且中途高亮按钮消失。 | xwang310 | Gating | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8122 | Phase 5: 【偶发】所有CAN报文停发后，FAPA界面未退出 | xwu134 | Gating | Approval | LA_R05_ENG | Parking Assist
APIMCIM-7986 | Phase 5：【必现】不会随着车速的高低改变VR播报音量 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-7201 | Phase5:【必现】RbaMnu_D_Rq=0x0(None)时，倒车制动辅助被置灰，但点击后可下发信号 | yzhan482 | High | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-8811 | Phase5:[CDX707][必现]重启车机后授权后的地图又重新变为未授权 | kcheng16 | Gating | Approval | LA_R05_ENG | CCS
APIMCIM-8467 | Phase5:[CDX707][必现]无法获取滤芯状态 | cshengji | Gating | Approval | LA_R05_ENG | AAR
APIMCIM-5526 | Phase5:【必现】CDX707 在没有娱乐流量的情况下，语音打开APP，提示当前网络异常 | lxue15 | Gating | Approval | LA_R05_ENG | VR
APIMCIM-5657 | Phase5:【必现】CDX707 未触发切换外循环的消息横幅 | fwu40 | Gating | Approval | LA_R05_ENG | AAR
APIMCIM-8841 | Phase5:[CDX707][100%]Peform ignition cycle , no sharing popup | qshi14 | Gating | Approval | LA_R05_ENG | CCS
APIMCIM-6548 | Phase5：【必现】[CDX707][HMI走查]诊断分析模块中，长按不会触发开发者模式弹窗 | cwang236 | Gating | Done | LA_R05_ENG | FNV
APIMCIM-8814 | Phase5:[CDX707][100%]Sync failure after ignition on | kyu18 | Gating | Done | LA_R04_ENG | CCS
APIMCIM-8649 | Phase5：【必现】首次进入氛围灯切换动态模式，可下发默认动态颜色信号，但页面没有选中颜色 | yzhan482 | High | Done | LA_R05_ENG | Vehicle Setting

## FIX_BUG
问题类型 | 概要 | 经办人 | 优先级 | 状态 | 修复的版本 | 模块
APIMCIM-9219 | [100%] MMOTA_China: Updating ECG/TCU by USB, download failed. | cchen244 | Immediate Gating | Test | LA_R05_ENG | MMOTA
APIMCIM-4381 | Phase 5：【必现】唤醒车机，语音：回到主界面。无反应 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | VR
APIMCIM-7761 | Phase 5：【必现】QUERY缺少Feature ID: 807/80B | yzhan482 | Gating | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8623 | Phase 5：after TCS DrvSlipCtlMde_D_Ind signal value changed, DrvSlipCtlMde_D_Rq value shall be update | yzhan482 | Gating | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8034 | Phase 5：【必现】连接副驾蓝牙耳机，播放副驾QQ音乐，VR：增大/ 减小副驾蓝牙耳机音量，车机无反应 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | VR
APIMCIM-8467 | Phase5:[CDX707][必现]无法获取滤芯状态 | cshengji | Gating | Approval | LA_R05_ENG | AAR
APIMCIM-8008 | Phase 5：【必现】你好，林肯唤醒后，返回主界面无反应 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | VR
APIMCIM-4134 | Phase 5：【必现】唤醒语音：说关闭智能新风，播报错误：打开智能馨风 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | VR
APIMCIM-9066 | Phase 5：【必现】语音无法控制精简屏幕 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | VR
APIMCIM-9154 | Phase 5: 【必现】自动泊车过程中Controller屏Camera界面和Pano屏360影像界面均存在闪烁 | xwu134 | Gating | Approval | LA_R05_ENG | Parking Assist
APIMCIM-7917 | Phase 5：【必现】空调智能新风界面的座舱新风按键，点击无beep声音 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | Climate
APIMCIM-8761 | Phase 5：【必现】空调界面打开时，打开设置项界面并关闭，空调界面的关闭按键消失 | tshan3 | Gating | Closed with Accept | LA_R05_ENG | Climate
APIMCIM-5526 | Phase5:【必现】CDX707 在没有娱乐流量的情况下，语音打开APP，提示当前网络异常 | lxue15 | Gating | Approval | LA_R05_ENG | VR
APIMCIM-5657 | Phase5:【必现】CDX707 未触发切换外循环的消息横幅 | fwu40 | Gating | Approval | LA_R05_ENG | AAR
APIMCIM-8841 | Phase5:[CDX707][100%]Peform ignition cycle , no sharing popup | qshi14 | Gating | Approval | LA_R05_ENG | CCS
APIMCIM-9451 | Phase 5: 【偶发】【AutoTest】泊车相关功能信号接收有延迟，不响应现象 | yzhu104 | Gating | Approval | LA_R05_ENG | Parking Assist
APIMCIM-9137 | Phase 5: 【偶发】实车“自动泊车”入口点击无响应或响应速度较慢 | wchen154 | Gating | Approval | LA_R05_ENG | Parking Assist
APIMCIM-8811 | Phase5:[CDX707][必现]重启车机后授权后的地图又重新变为未授权 | kcheng16 | Gating | Approval | LA_R05_ENG | CCS
APIMCIM-9098 | [30%] MMOTA_China: Level 1 ASU off 升级MCU，点击“有可用的更新”，偶现无“接受”按钮 | yli391 | Gating | Approval | LA_R05_ENG | MMOTA
APIMCIM-7895 | [100%] MMOTA_China:OTA升级SOC,下载过程中发Shed_Level_Req:3_SHED2_CONTIN或Shed_Level_Req=5_SHED_ENG_OFF,进入安装会报SIM_E1001,OTAM_E1008,OTAM_E1016 | cchen244 | Gating | Test | LA_R05_ENG | MMOTA
APIMCIM-9943 | [100%] MMOTA_China: Level 2/3 update MCU, user consent is wrong | yli391 | Gating | Closed with Accept | LA_R05_ENG | MMOTA
APIMCIM-6548 | Phase5：【必现】[CDX707][HMI走查]诊断分析模块中，长按不会触发开发者模式弹窗 | cwang236 | Gating | Done | LA_R05_ENG | FNV
APIMCIM-7240 | MMOTA Test: ASU=OFF, trigger OTA upgrade, the system update reminder pop-up window does not pop up, when it is ready to activate, the system update schedule is not set and the pop-up box does not pop up | jwu187 | Gating | Test | LA_R05_ENG | MMOTA
APIMCIM-8512 | Phase5:[CDX707][100%]应用商城里面的app下载完成后卸载不了 | swang218 | Gating | Approval | LA_R05_ENG | appstore
APIMCIM-8781 | Phase 5：【必现】APA Gen8 delUXe - 动态车位显示区域扩展，小车，扫描线动画，泊入轨迹动画上移 | xwu134 | Gating | Approval | LA_R05_ENG | Fapa
APIMCIM-7749 | Phase5[CDX707]:[必现] 空气过滤状态改变，空调界面图标不同步 | xwang310 | Gating | Approval | LA_R05_ENG | AAR
APIMCIM-8970 | Phase 5：【必现】长按VOL key重启车机，会先弹出toast"媒体音频已关闭"，再执行重启 | jxu150 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-8713 | Phase 5：【必现】车道保持系统点击切换模式，切换选中卡顿 | yzhan482 | Gating | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-7752 | Phase5:[CDX707][必现]无定位的情况下，外部PM2.5一直显示正在初始化 | cshengji | Gating | Done | LA_R05_ENG | AAR
APIMCIM-8281 | Phase5：[CDX707]Five minutes before ignition, the user actively switches the inner and outer circulation, which affects the automatic circulation | cshengji | Gating | Approval | LA_R05_ENG | AAR
APIMCIM-8365 | Phase5:[CDX707]The air in the car changes from an invalid value to a valid value, and the bullet box should not pop up after the air filter is completed. | cshengji | Gating | Done | LA_R05_ENG | AAR
APIMCIM-7986 | Phase 5：【必现】不会随着车速的高低改变VR播报音量 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-7985 | Phase 5：【必现】不会随着车速的高低改变通话音量 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-7779 | Phase5:【必现】[CDX707]3D车模天窗动画时间较长，动画过程中车模视角回到右侧45度默认视角，再切到左侧45度，车头下压20度，且中途高亮按钮消失。 | xwang310 | Gating | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8077 | Phase 5：【必现】唤醒语音，VR：设置氛围灯颜色为红色。实车不成功 | tshan3 | Gating | Approval | LA_R05_ENG | VR
APIMCIM-9138 | Phase 5: 【必现】多个车位可用时改变目标泊入车位，轨迹动画未更新至新的目标车位 | wchen154 | Gating | Approval | LA_R05_ENG | Parking Assist
APIMCIM-6545 | Phase5：【必现】[CDX707][HMI走查]launcher编辑widget交互中，分页条设计不会随着滑动交互变化 | yqin24 | Gating | Done | LA_R05_ENG | Launcher
APIMCIM-8214 | [100%] MMOTA_China: 关闭车机互联，USB升级直接报错。 | cchen244 | Gating | Closed with Accept | LA_R05_ENG | MMOTA
APIMCIM-8919 | Phase 5：【必现】熄火后开关车门，再点火，音乐在播放，但无声 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-8884 | Phase 5：【必现】WIFI已连接设备热点后，媒体投射中手机热点模式无法连接此设备热点 | jhe83 | Gating | Approval | LA_R05_ENG | DLNA
APIMCIM-8703 | Phase 5：【必现】开机第一次通过语音打开道路救援，无法打开 | hpeng31 | Gating | Approval | LA_R05_ENG | VR
APIMCIM-8829 | Phase 5：【必现】空调AAR的历史记录页面数值模拟后无显示 | tshan3 | Gating | Approval | LA_R05_ENG | Climate
APIMCIM-7253 | Phase5_【CDX707】【黑盒】【必现】【FAPA】发送对应Can信号后，摄像头画面显示不正常 | cchen244 | Gating | Approval | LA_R05_ENG | Fapa
APIMCIM-8854 | Phase 5：【必现】语音播报会被平衡/衰减调节所影响 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-8851 | Phase 5：【必现】通话音会被平衡/衰减调节所影响 | jsun62 | Gating | Approval | LA_R05_ENG | Audio
APIMCIM-8057 | Phase 5：【必现】全部应用搜索界面调起键盘收到来电后挂断未留在搜索界面 | yliu350 | Gating | Approval | LA_R05_ENG | Input
APIMCIM-8203 | Phase 5: 【偶发】ApaMde_D_Stat=0x1 OFF& Displaymode=0x0 off后APA界面未退出 | wchen154 | Gating | Approval | LA_R05_ENG | Parking Assist
APIMCIM-8122 | Phase 5: 【偶发】所有CAN报文停发后，FAPA界面未退出 | xwu134 | Gating | Approval | LA_R05_ENG | Parking Assist
APIMCIM-7897 | Phase5_【CDX707】【黑盒】【偶现】【FAPA】无法进入泊车界面 | xwu134 | Gating | Closed with Accept | LA_R05_ENG | Fapa
APIMCIM-3749 | Phase 5：【必现】多个应用无法用语音打开 | hpeng31 | Gating | Approval | LA_R05_ENG | VR
APIMCIM-7224 | [5/27]CDX707C SDM selection animation not shown in IVI controller | yli158 | Gating | Approval | LA_R05_ENG | Drive Mode
APIMCIM-8224 | Phase 5: 【偶发】有效信号输入后IVI未进入APA界面 | wchen154 | Gating | Approval | LA_R05_ENG | Parking Assist
APIMCIM-5833 | Phase 5：CDX707 【必现】DE01 BYTE4 BIT7 =FHEV没有显示能量流界面 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8715 | Phase 5：【偶现】机油寿命进度条偶现颜色会消失 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8347 | Phase 5：【必发】只显示防眩照明时，点击请求打开，应下发0x2 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8780 | Phase 5：【必现】智能预测巡航list不应在选中定速巡航时显示 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8714 | Phase 5：【必现】驾驶模式页面应显示每个驾驶模式对应的动画 | yzhan482 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8649 | Phase5：【必现】首次进入氛围灯切换动态模式，可下发默认动态颜色信号，但页面没有选中颜色 | yzhan482 | High | Done | LA_R05_ENG | Vehicle Setting
APIMCIM-7670 | Phase 5: 【必现】空调控制界面收起时UI动画异常 | wchen154 | High | Done | LA_R05_ENG | Climate
APIMCIM-8833 | Phase 5：【必现】空调座舱新风按键点击无触摸音 | tshan3 | High | Closed with Accept | LA_R05_ENG | Climate
APIMCIM-8834 | Phase 5：【必现】空调AAR历史记录界面右侧的数据显示不完整 | tshan3 | High | Closed with Accept | LA_R05_ENG | Climate
APIMCIM-9021 | Phase5: CDX707： AAR RHS Unit as ug/m^3 | rqi2 | High | Approval | LA_R05_ENG | AAR
APIMCIM-9460 | Phase5:[100%][CDX707]Will back to lanncher page from 3D Vel Model control page after 15S | lwang200 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9440 | Phase5:[必现][CDX707]车外页打开空调页面后再次关闭空调页面回到了首页 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9443 | Phase5:[100%][CDX707]When the sunroof/body color window is open, click inside -> outside the car, and the window is closed | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9444 | Phase5:[100%][CDX707]Click the fifth TAB color in the body color pop-up window to reset the body color, but neither TAB nor body color can be reset | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9445 | Phase5:[100%][CDX707]3D model shortcut control page, click on any pop-up window... , close the shortcut control page and then go to the Settings page | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9449 | Phase5:[100%][CDX707]The trunk button will disappear when you click the empty space or rotate it, which is inconsistent with the sunroof button and the body color button | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-6512 | Phase 5：【必现】灵敏度选项界面无出触摸反馈音 | hpeng31 | High | Approval | LA_R05_ENG | System Setting
APIMCIM-9099 | [30%] MMOTA_China: Level 2/3 升级MCU，偶现用户授权弹窗出现“内容暂时无法显示” | cchen244 | High | Test | LA_R05_ENG | MMOTA
APIMCIM-7770 | Phase5:【必现】[CDX707]呼出3D车模车内页任意功能设定弹窗，点击空白处对应功能设定弹窗不消失。 | mchen127 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-7772 | Phase5:【必现】[CDX707]天窗初始状态不一样时，3D车模车外页点击全开/透气/舒适，实车天窗表现不一。 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8959 | Phase5:【必现】[CDX707]3D车模快捷控制页，后备箱图标位置显示不合理 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8960 | Phase5:【必现】[CDX707]呼出3D车模车外页任意功能设定弹窗，点击空白处对应功能设定弹窗不消失。 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8975 | Phase5:【必现】[CDX707]进入车内页快捷控制页或打开座椅按摩设置弹窗后熄火，车内视角背景里出现车头 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9187 | Phase5:【必现】[CDX707]3D车模车外页，照明系统故障文本描述与与VHA的车辆健康中的提示不一致 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9205 | Phase5:【必现】[CDX707]车辆熄火后（不熄屏），3D车模首页和车外页，仍然能显示单个轮胎的低胎压信息 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9206 | Phase5:【必现】[CDX707]3D车模车外页，旋转车模时，照明系统故障文字即图标不消失 | yliu404 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-7862 | Phase5[CDX707][必现]：停止发送空调信息，AAR的状态图标显示错误 | xwang310 | High | Approval | LA_R05_ENG | AAR
APIMCIM-9110 | Phase 5：【必现】[CDX707]自由调节内容排序&样式与UI设计不一致 | hyan19 | High | Approval | LA_R05_ENG | Climate
APIMCIM-9024 | Phase 5：【必现】[CDX707]空调面板页面无风量调节框，与UI设计不一致 | hyan19 | High | Approval | LA_R05_ENG | Climate
APIMCIM-8916 | Phase5[偶现]:[CDX707]The color of PM2.5 is displayed abnormally when the message banner of the outer loop is triggered | cshengji | High | Done | LA_R05_ENG | AAR
APIMCIM-7879 | Phase5:[CDX707][100%]Failed to return to the superior menu when disagreeing with the V2I agreement application | kcheng16 | High | Approval | LA_R05_ENG | V2I
APIMCIM-7873 | Phase5:[CDX707][100%]Abnormal document display in V2I start application interface | kcheng16 | High | Approval | LA_R05_ENG | V2I
APIMCIM-7926 | Phase5:[CDX707][100%]Incomplete display of glwoa statement | dnan1 | High | Test | LA_R05_ENG | V2I
APIMCIM-9237 | Phase 5：【必现】[CDX707]3D车模，车内车模后排有一块白色区域，与UI设计不一致 | hyan19 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8001 | Phase5:[CDX707][100%]The TLI statement is inconsistent with the requirements | dnan1 | High | Test | LA_R05_ENG | V2I
APIMCIM-8036 | Phase5:[CDX707][100%]The red light running alarm statement is inconsistent with the design | cchen244 | High | Test | LA_R05_ENG | V2I
APIMCIM-9286 | Phase5：【偶现】点击汽车模型更换颜色按钮更换车身颜色，点击重置车身颜色后，按钮颜色变成红色未重置成初始的白色 | yliu404 | High | Approval | LA_R05_ENG | Launcher
APIMCIM-8905 | Phase5:【必现】[CDX707]3D车模遮阳帘半开的时候，车模遮阳帘动画异常 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8955 | Phase5:【必现】[CDX707]天窗全关时点击舒适\透气\全开或打开天窗后点击全关后，对应的按钮不高亮 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8971 | Phase5:【必现】[CDX707]车内按键打开后备箱后，车模视角一直停留在后备箱打开视角 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9092 | Phase5:【必现】[CDX707]快速滑动选择按摩方式，选中的按摩方式仍然会与其他按摩方式多次来回切换 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8908 | Phase5:【偶现】[CDX707]3D车模执行遮阳帘半关时，动画没有结束时突然回到首页 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8938 | Phase5:【必现】[CDX707]车内按键手动控制天窗时，前一操作结束后6s内进行下一操作，3D车模动画异常 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8720 | Phase 5：【必现】CDX707 车辆状态，左上角缺少关闭按钮 | lzhan249 | High | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-9023 | Phase 5：【必现】[CDX707]空调面板页面，AAR按钮位置与UI设计不一致 | hyan19 | High | Approval | LA_R05_ENG | Climate
APIMCIM-9020 | Phase 5：【必现】[CDX707]空调面板页面无空调开关按钮，与UI设计不一致 | hyan19 | High | Approval | LA_R05_ENG | Climate
APIMCIM-9019 | Phase 5：【必现】[CDX707]自由调节位置与UI设计不一致 | hyan19 | High | Approval | LA_R05_ENG | Climate
APIMCIM-9018 | Phase 5：【必现】[CDX707]空调面板页面无座椅通风加热按钮，与UI设计不一致 | hyan19 | High | Approval | LA_R05_ENG | Climate
APIMCIM-9027 | Phase 5：【必现】[CDX707]AC按钮、AUTO按钮、内循环按钮、MAC A/C，方向盘加热位置与UI设计不一致 | hyan19 | High | Approval | LA_R05_ENG | Climate
APIMCIM-7827 | Phase5:【AutoTest】Monkey测试期间，出现包名为com.ford.sync.controllerlauncher的crash异常 | yliu404 | High | Approval | LA_R04_ENG | System Stability
APIMCIM-7774 | Phase5:【必现】[CDX707]3D车模天窗控制页，依次点击透气→透光，高亮跳回“透气”按钮。 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-7775 | Phase5:【必现】[CDX707]3D车模天窗控制页依次点击透光、舒适，再次点击透光，实车无反应 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-7777 | Phase5:【必现】[CDX707]3D车模车外页天窗控制，点击透光→透气，再次点击透光，实车无反应 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8910 | Phase5:【必现】[CDX707]打开透气（起翘），用户6s无操作后没有自动恢复默认视角 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-7730 | Phase5：【必现】[CDX707][HMI走查] DAT Setting_info book页面视觉布局问题 | mguo15 | High | Done | LA_R05_ENG | DAT Setting
APIMCIM-8683 | Phase 5：【必现】CDX707 自动泊车按键，页面跟UI不一致，缺少手册图标，”导航去停车场“和'自动泊车”位置与卡片与UI不同 | lzhan249 | High | Approval | LA_R05_ENG | Shortcut Keys
APIMCIM-8669 | Phase 5：【必现】CDX707 按摩的高中低样式与UI不一致，按摩模式的样式与位置与UI不一致 | lzhan249 | High | Approval | LA_R05_ENG | Seat
APIMCIM-8664 | Phase 5：【必现】CDX707 多功能座椅整个页面布局与UI不一致，info book位置不对，标题显示一行 | cchen244 | High | Approval | LA_R05_ENG | Seat
APIMCIM-8247 | Phase5：【必现】车辆设置→常用设置中，向下拖动功能，然后等待功能自动回归到相应的位置，会出现重影 | jchen384 | High | Approval | LA_R05_ENG | Shortcut Keys
APIMCIM-9194 | Phase5:【必现】[CDX707]触发冷却液温度过高故障时，3D车模车外页的故障指示指到了后轮位置 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8807 | Phase 5：【必现】CDX707 搜索车锁，一级菜单没高亮并且界面反应太慢 | lzhan249 | High | Approval | LA_R05_ENG | System UI
APIMCIM-8808 | Phase 5：【必现】CDX707 驾驶辅助-车速限制辅助-超速警告，示意图与UI不一致 | lzhan249 | High | Approval | LA_R05_ENG | System UI
APIMCIM-5469 | Phase 5：【必现】调节某个腰托或支撑等级时，文字list应highlight（FO建议） | yzhan482 | High | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-8822 | Phase 5：外置功放，QQ音乐播放没有声音，但是按键触摸音和chime播放声音正常 | mxia13 | High | Approval | LA_R05_ENG | Audio
APIMCIM-9016 | Phase 5：【必现】[CDX707]空调面板无前后除霜按钮 | hyan19 | High | Approval | LA_R05_ENG | Climate
APIMCIM-7878 | Phase5:【必现】[CDX707]D档时点击3D车模车外页后备箱按钮无弹窗提示。 | xwang310 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8802 | Phase 5：【必现】CDX707 车辆设置-机油寿命，info book应该删除 | lzhan249 | High | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-7732 | Phase5：【必现】[CDX707][HMI走查] Vehicle Setting 车辆设置_info book图片资源缺失问题 | cchen244 | High | Done | LA_R05_ENG | Vehicle Setting
APIMCIM-9059 | Phase 5：【必现】CDX707 OTA,更新计划车机未删除info book图标 | mguo15 | High | Test | LA_R05_ENG | OTA
APIMCIM-8147 | Phase5：【必现】音效设置中快速旋转右侧声道平衡按钮，停止后声道要过几秒才会定位到调节的位置。 | xyu61 | High | Approval | LA_R05_ENG | System Setting
APIMCIM-8904 | Phase5:【必现】[CDX707]3D车模天窗全关状态下，遮阳帘仍显示高亮 | yliu404 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8682 | Phase 5：【必现】CDX707 尾灯设置缺少资源并且无法选择 | lzhan249 | High | Approval | LA_R05_ENG | System Setting
APIMCIM-8723 | Phase 5：【必现】CDX707 发动机故障，防暴死系统，冷却液温度过高等缺少车模 | lzhan249 | High | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-8650 | Phase 5：【必现】CDX707 驾驶信息显示页面缺少发动机冷却液表 | lzhan249 | High | Approval | LA_R05_ENG | Driver Info
APIMCIM-8651 | Phase 5：【必现】CDX707 IOD下面缺少能量流和本次行程 | lzhan249 | High | Approval | LA_R05_ENG | Driver Info
APIMCIM-8806 | Phase 5：【必现】CDX707 车辆设置-车锁-离车自动落锁，已删除info book占位图 | lzhan249 | High | Approval | LA_R05_ENG | System UI
APIMCIM-8663 | Phase 5：【必现】CDX707 林肯香氛页面多处与UI不一致 | lzhan249 | High | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-7694 | Phase5:【必现】[CDX707]当天窗处于打开状态时，打开主驾车门，3D车模车外页视角反复跳转。 | yliu404 | High | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8503 | Phase 5：【必现】CDX707 音效设置缺少“开关机提示音”功能 | lzhan249 | High | Approval | LA_R05_ENG | System Setting
APIMCIM-6650 | Phase5：【必现】[CDX707][HMI走查]音效设置_页面视觉布局问题 | hzhu74 | High | Done | LA_R05_ENG | System Setting
APIMCIM-8146 | Phase5：【偶现】系统设置中，拖动媒体音量调节按钮后，按钮左右晃动 | jchen384 | High | Approval | LA_R05_ENG | System Setting
APIMCIM-8148 | Phase5：【偶现】音效设置中车速音量调整和详情页面显示不一致 | jchen384 | High | Approval | LA_R05_ENG | System Setting
APIMCIM-7201 | Phase5:【必现】RbaMnu_D_Rq=0x0(None)时，倒车制动辅助被置灰，但点击后可下发信号 | yzhan482 | High | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-7729 | Phase5：【必现】[CDX707][HMI走查] Vehicle Setting 车辆设置_页面文本内容视觉布局问题 | zjiang38 | High | Done | LA_R05_ENG | Vehicle Setting
APIMCIM-8330 | Phase5：【必现】随心看卡片添加launcher的widget内卡片不可见 | dliu50 | High | Approval | LA_R05_ENG | System UI
APIMCIM-7586 | Phase5：【高频】IVI,点击设置按键，返回主界面，USB音乐，车辆设置，天气小界面依次缓慢显示9：08 | spei2 | High | Approval | LA_R05_ENG | Launcher
APIMCIM-7712 | Phase5_【CDX707】【黑盒】【必现】【Vehicle Settings】开机后立即点击IOD无法进入驾驶信息显示界面 | cxu63 | High | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-5443 | Phase 5：【必现】蓝牙耳机连接成功时，随心听音乐会停顿两下 | xwang314 | High | Approval | LA_R05_ENG | BT Headset
APIMCIM-7292 | Phase5：【必发】IVI，空调界面，返回时，有一条黑色的线从下边向上移动，9：20 | spei2 | High | Approval | LA_R05_ENG | Climate
APIMCIM-7898 | Phase5_【CDX707】【黑盒】【必现】【FAPA】由inactive变active时，点击静音，跳转至active后，退出泊车界面 | xwu134 | High | Closed with Accept | LA_R05_ENG | Fapa
APIMCIM-7737 | Phase5：【必现】[CDX707][HMI走查] DAT Setting_info book图片资源缺失问题 | fwang116 | High | Done | LA_R04_ENG | DAT Setting
APIMCIM-7973 | Phase5：【必现】[CDX707][HMI走查] 儿童安全座椅_蓝牙设置视觉布局问题 | dnan1 | High | Done | LA_R05_ENG | BT Child Seat
APIMCIM-6853 | Phase5：【必现】[CDX707][HMI走查] Face ID_新手引导界面视觉布局问题 | jzhan373 | High | Done | LA_R05_ENG | Account
APIMCIM-7238 | Phase5：【必现】[CDX707][HMI走查] 3D车模_车内视角页面视觉布局问题 | mchen127 | High | Done | LA_R05_ENG | 3D Vehicle model
APIMCIM-9248 | Phase 5：【必现】[CDX707]3D车模-氛围灯模式选择动态颜色，滑动页面没有滑动条 | hyan19 | Medium | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-9017 | Phase 5：【必现】[CDX707]吹风模式三个按钮是独立按钮，没有连在一起，与UI设计不一致 | hyan19 | Medium | Approval | LA_R05_ENG | Climate
APIMCIM-8767 | Phase 5：【必现】[CDX707]桌面点击车模，后备箱图标显示遮挡 | yliu404 | Medium | Approval | LA_R05_ENG | System UI
APIMCIM-8647 | Phase 5：【必现】CDX707 胎压监测在pano屏card1显示不完整，在弹窗后面 | lzhan249 | Medium | Approval | LA_R05_ENG | Driver Info
APIMCIM-9014 | Phase 5：【必现】[CDX707]空调面板关闭按钮位置与UI不一致，且UI规范无“关闭”二字 | hyan19 | Medium | Approval | LA_R05_ENG | Climate
APIMCIM-6851 | Phase5：【必现】[CDX707][HMI走查] 个性化档案_个性化档案界面视觉布局问题 | xli288 | Medium | Done | LA_R05_ENG | Account
APIMCIM-6858 | Phase5：【必现】[CDX707][HMI走查] 个性化档案_toast视觉布局问题 | xli288 | Medium | Done | LA_R05_ENG | Account
APIMCIM-9032 | Phase 5：【必现】[CDX707]AAR左上角关闭按钮与UI设计不一致 | hyan19 | Medium | Approval | LA_R05_ENG | AAR
APIMCIM-8662 | Phase 5：【必现】CDX707 安全开门预警名称不对 | lzhan249 | Medium | Approval | LA_R05_ENG | Funtion Safety
APIMCIM-8668 | Phase 5：【必现】CDX707 多功能座椅调节驾驶侧，选择任意位置调节，文字没高亮（如上部腰托） | lzhan249 | Medium | Approval | LA_R05_ENG | Seat
APIMCIM-8504 | Phase 5：【必现】CDX707 音效设置的info book弹框都太大了，系统设置其他模块的弹框都偏小一点 | lzhan249 | Medium | Approval | LA_R05_ENG | System Setting
APIMCIM-8707 | Phase 5：【必现】CDX707 按摩开关的名称应该修改成“按摩开关” | lzhan249 | Medium | Approval | LA_R05_ENG | Seat
APIMCIM-8804 | Phase 5：【必现】CDX707 车辆设置-车锁-遥控解锁，名称“全部车门“与UI不一致 | lzhan249 | Medium | Approval | LA_R05_ENG | System UI
APIMCIM-8726 | Phase 5：【必现】CDX707 全部应用入口/最近应用入口，图标名称应该是“车辆状态”，而不是“车辆状况” | lzhan249 | Medium | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-7899 | Phase5_【CDX707】【黑盒】【必现】【FAPA】由inactive进入active界面缓慢,4s左右 | mguo15 | Medium | Approval | LA_R05_ENG | Fapa
APIMCIM-8758 | Phase 5：【必现】[CDX707]重置之后重置按钮没置灰依旧高亮 | hyan19 | Medium | Approval | LA_R05_ENG | System UI
APIMCIM-7324 | Phase5：【必现】[CDX707][HMI走查] AAR_popup页面视觉布局问题 | fwang116 | Medium | Done | LA_R05_ENG | AAR
APIMCIM-8478 | Phase 5：【必现】CDX707车辆控制的>颜色没高亮，系统设置和快捷控制的>颜色高亮，保持统一 | lzhan249 | Medium | Approval | LA_R05_ENG | Vehicle Setting
APIMCIM-7900 | Phase5_【CDX707】【黑盒】【偶现】【FAPA】由Active变inactive，界面跳转不回去 | xwu134 | Medium | Closed with Accept | LA_R05_ENG | Fapa
APIMCIM-6848 | Phase5：【必现】[CDX707][HMI走查] 个性化档案_popup视觉布局问题 | xli288 | Medium | Done | LA_R05_ENG | Account
APIMCIM-9238 | Phase 5：【必现】[CDX707]点击3D车模，左上角×未与文字居中对齐 | hyan19 | Low | Approval | LA_R05_ENG | 3D Vehicle model
APIMCIM-8646 | Phase 5：【必现】CDX707 车辆设置-驾驶信息显示-重置数据，确定重置所有数据的弹窗左侧竖线没高亮 | lzhan249 | Low | Approval | LA_R05_ENG | Driver Info
APIMCIM-8667 | Phase 5：【必现】CDX707 按摩弹窗文字第二行应该靠左显示 | lzhan249 | Low | Approval | LA_R05_ENG | Seat
APIMCIM-7594 | Phase5_【CDX707】【黑盒】【必现】【HMI走查】多功能座椅示意图动效未实现 | zjiang38 | Low | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-7592 | Phase5_【CDX707】【黑盒】【必现】【HMI走查】尾灯设置动画视频未实现 | dnan1 | Low | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-7593 | Phase5_【CDX707】【黑盒】【必现】【HMI走查】驾驶模式动效未实现 | dnan1 | Low | Closed with Accept | LA_R05_ENG | Vehicle Setting
APIMCIM-8592 | Phase5: CDX707 lost PK when ENG Run, no horn chrip | yzhan482 | Not Set | Done | LA_R05_ENG | Vehicle Setting
APIMCIM-5609 | Phase5 香氛界面没有改为一页显示 | pliu55 | Not Set | Done | LA_R05_ENG | Vehicle Setting
APIMCIM-8762 | Phase5: CDX707 语音控制香氛关闭，下一次打开香氛香氛浓度会置为关闭，未调出关闭前的浓度 | pliu55 | Not Set | Approval | LA_R05_ENG | VR
APIMCIM-7261 | 1.进入APA 泊车界面后 界面卡死; 2. 雷达乌龟弹出严重滞后且无法关闭；3. 搜到车位后挂N档进入360界面无影像 | jzhu79 | Not Set | Approval | LA_R05_ENG | Fapa
APIMCIM-8471 | Phase5：CDX707 应用卡片页面左右滑动切换时困难，很容易出现卡片误触，而且页面数量标识错误In the card pool, it’s difficult to slide to next page and page quantity indicator icon is incorrect | bliu94 | Not Set | Approval | LA_R05_ENG | Launcher

## R05.1_FIX BUG
问题类型 | 概要 | 经办人 | 优先级 | 状态 | 修复的版本 | 模块 | 备注
APIMCIM-10153 | Phase 5: 【偶发】自动泊车过程中影像画面延迟，卡滞明显 | cai, yufei | Gating | IN PROGRESS | R06 | Fapa | R05.1上降低播报频率，改善问题现象，非最终对策。
APIMCIM-7829 | Phase5:【AutoTest】Monkey测试期间，出现包名为com.android.settings的crash异常 Vehicle_Settting:解决crash问题 | Jiao, Bu Ping | Gating | APPROVAL | R05 | System Stability
APIMCIM-9966 | Phase5： CDX707C Vehicle test: Personal profile can't be associated with Paak CarService：解决Paak问题 | Chen，Deyin | Gating | APPROVAL | R05 | Personalization
APIMCIM-10171 | Phase 5: 【必现】¦P¦界面消失时（比如按“导航到停车场“）IVI未与ADAS 同步（ApaFeat_D_RqDrv信号发送问题） | cai, yufei | High | TEST | R05 | Fapa | 与FO沟通需要跟进修改，暂不变更状态
APIMCIM-10135 | Phase 5: 【偶发】自动泊车过程中影像调取失败 | He, Michael (X.) | Gating | APPROVAL | R05 | Camera, Fapa, Parking Assist
APIMCIM-10156 | Phase 5: 【必现】自动泊车过程中，找到车位，停车后挂N挡，不应切影像（实测切黑屏）； | He, Michael (X.) | High | APPROVAL | R05 | Camera, Fapa, Parking Assist
APIMCIM-9372 | Phase 5：【必现】APA Gen8 delUXe - HintTextID002 shall not be displayed when HMISystemConfig set to "APA_0x4" | He, Michael (X.) | High | APPROVAL | R05 | Fapa
APIMCIM-10639 | Phase5_【CDX707】【黑盒】【必现】【GNSS】gnss卫星状态数据上报频率过高，达1秒60次，导致百度地图卡顿 | zhou, zhangjian (z.) | High | TEST | R05 | GNSS
APIMCIM-10240 | Phase 5：【必现】实车空调风量滑动到0关闭，此时点击+，不能打开空调 | Shan, Tiantian (T.) | Gating | CLOSED WITH ACCEPT | R05 | Climate
APIMCIM-10245 | Phase 5：【必现】实车空调风量滑动到0，点击风量-，风量值自动增大至7 | Shan, Tiantian (T.) | Gating | CLOSED WITH ACCEPT | R05 | Climate
APIMCIM-8920 | Phase5:[必现][CDX707]进LPR mode后，网络异常，网络通道不建立 | shi, qianjun (q.) | Immediate Gating | APPROVAL | R05 | Wireless Interface Router
APIMCIM-8921 | Phase5:[必现][CDX707]Deepsleep后，网络异常，网络通道不建立 Dueros库更新 | shi, qianjun (q.) | Gating | APPROVAL | R05 | Wireless Interface Router
APIMCIM-10137 | Phase 5: 【必现】吹脸模式打开状态，语音输入：“吹脸吹脚模式”,吹脸开关置灰，吹脚高亮。 | Dou, Xinyu (X.) | Gating | APPROVAL | R05 | VR
APIMCIM-10281 | Phase 5：【偶发】歌曲播放器页面一直显示"00:00"，无法播放歌曲 | Yu,Xianhuan | Gating | IN PROGRESS | R06 | Audio | R05.1上Timeout时间从1s变为2s，改善问题现象，非最终对策
APIMCIM-10279 | Phase 5：【偶发】视频播放器页面一直显示"加载中..."，无法播放视频 | Yu,Xianhuan | Gating | IN PROGRESS | R06 | Audio | R05.1上Timeout时间从1s变为2s，改善问题现象，非最终对策