## RL-Revision-History
Release Note Change Record History
Version Number | Release Date | Author | Reviewer | Approver | Content Changes

## Release Content
Software Release Information List |  |  |  | 1. 各方需要提供该格式的release note； 2. 集成方需要整合各方的release content，Fixex Bug list，Open Bug List 的内容； 3. Release note的内容准确性由各个开发方的PM&SWQ来保证，Ford方的System Integration Manager&SWQ 来检查 4. Release note 版本号： After Integration Completed 1.* After Supplier Test Completed 2.* REC(End To End) Test Completed 3.*
Software Release Information Description
Prepared By |  |  | Reviewed By:
Date
Software Version Information
SOC SW Version |  | 示例： SOC User：20230417_0903_CF15_R13.1.PRO.HF1_User SOC Debug：20230417_0903_CF15_R13.1.PRO.HF1_Debug FNV：dueros_SU3_A8.1-bin-1.0.8.62_20220812
General Info |  | SOC SW P/N | 示例： MZ8T-14H379-AM
|  | Main board HW Version | 示例： HW012
|  | MCU SW Version | 示例： MCU：20221212_564_PRO
|  | MCU SW P/N | 示例： MZ8T-14H361-AN
|  | Checksum | 示例：只针对集成后的软件包,有几个软件包就需要有相应数量的checksum a5264b54665725c8dd58ae9dee16c30a or other
Software Release Content
Release Content | 新增功能 | 模块: 语音, APK: DuerOSAuto.protected.apk 1、合入高配语音模型
完善功能
| BUG修复 | bugfix 清单见 《Fixed Bug List》sheet 和 《Change Scope》sheet
| 设计调整 | 暂无
| 遗留问题 | 详见 《Open Bug List》sheet
Software Release Conlusion
针对该版本发布的结论： 1.从计划实现功能的角度，是否有偏差，计划实现需求多少，实际实现需求多少； 2.该版本的测试结论； 3.目前Bug 情况，是否满足该节点的要求； 4.本版本的限制条件以及limitation； 5.从Metrics 的角度，该版本的风险项以及mitigation计划；

## Change Scope
R10修改范围: 5.16 - 5.25 提交到SOP分支的合入修改, R09在 5.16 以后没有任何提交
模块 | 类型 | 描述 | 合入延峰仓库链接 | 测试case/结果 | 需求来源和合入版本说明
语音 | bugfix | [edc-scrum-79750] [bug] 【遮阳帘半开/半关】离线语义解析百分数需要转float [edc-scrum-58140] [bug] 当执行了删除联系人时，【打电话给XXX】TTS反馈：请先同步联系人 [edc-scrum-2627] [bug] 解决偶现吞音问题 | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56398 | pass
| feature | 合入高配语音模型 | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56087 | 唤醒和识别率专项测试 遗留Bug: 开窗场景【你好林肯】需优化，R11合入
地图 | bugfix | fix：FordPhase4Scrum-58636 [bug-地图] 【必现】【设置】1057 导航中，先打开音量按钮，然后在widget点击沿途搜，音量界面和widget同时显示 分析：从widget进入沿途搜时，未隐藏音量条 方案：主动隐藏音量条 fix：FordPhase4Scrum-58372 [bug-地图] 【必现】【组队出行】1545 导航中，队员退出后，队伍面板还是存在，且队员头像也存在 分析：原逻辑根据队员数是否大于2来判断是否需要显示组队排名面板，但当最后一位队员退出组队时，队员数已经小于2，此时就无法更新组队排名面板了 方案：当队员数小于2时直接手动隐藏组队排名面板 fix：FordPhase4Scrum-56860 [bug-地图] 【必现】【CDX707】【路线偏好】选择任意相同偏好，无法自动回到导航态，而进入是操作态 分析：原逻辑是选择相同偏好后不会重新算路，所以没有进入导航态 方案：不管是选择相同还是不同算路偏好，都手动进入导航态 fix：FordPhase4Scrum-58642 [bug-地图] 【必现】【设置】1554 导航中，一直开关AR导航前车碰撞开关按钮，会自动返回导航态 分析：ar相关按钮点击时未重置自动隐藏倒计时 方案：按钮点击时重置倒计时 fix：FordPhase4Scrum-57345 [bug-地图] 【必现】【所见即可说】1647 事件上报页面，语音指令语音上报不可用 fix：FordPhase4Scrum-59801 [bug-地图] 【必现】【AR导航】百度-腾讯大厦，pano显示区间测速 fix：FordPhase4Scrum-59693 [bug-地图] 【代码扫描】高危漏洞6个 fix：FordPhase4Scrum-57711 [bug-地图] APIMCIM-21780 Phase 5：【必现】算路界面点击途经点蒙层，设置车牌toast出现闪屏 【自动创建】 原因：小黄条默认高度跳变导致看起来闪 解决：默认高度设置为小黄条单行高度 fix：FordPhase4Scrum-56754 [bug-地图] 【必现】【CDX707】【组队出行】组队出行邀请好友的二维码样式和需求不一致 分析：当输入给qzing的宽高和二维码原始宽高不能整除时，就会产生白边，此时如果输入宽高为0，qzing会使用二维码原始宽高输出图像 方案：将输入宽高设置为0 fix：FordPhase4Scrum-57715 [bug-地图] APIMCIM-21781 Phase 5：【必现】途经点详情页的按钮样式不统一 【自动创建】 分析：poi详情面板在导航态和非导航态下宽度不一致，所以导航态下显示不下 方案：和UI同事讨论，调整导航态下宽度和非导航态一致 fix：FordPhase4Scrum-59407 [bug-地图] 【必现】【体验问题】1905 离线地图下载完一个后，取消另一个地图的下载，用户还是不能用当前已下载的也不知道需要重启 fix：FordPhase4Scrum-57716 [bug-地图] APIMCIM-21787 Phase 5：【必现】路况预测界面点击子POI，规划路线后显示路线偏好 【自动创建】 分析：算路成功后未能隐藏路况预测面板 方案：调整路况面板隐藏方式，让整个面板隐藏 fix：FordPhase4Scrum-58747 [bug-地图] 【必现】【导航结束卡片】1646 导航结束卡片，切换无数据的类别后，底图还是显示上一个有数据的检索结果和路线 原因：福特定制代码导致该问题，对比主线，主线不会展示无数据类别，所以主线代码中未对切换数据为空的场景做处理 方案：重写主线逻辑，对数据为空的场景做清理算路图层、清理自定义maker处理 fix：FordPhase4Scrum-59166 [bug-地图] 【必现】【设置】1624 调节音量,2s后，音量值不消失 【分析】未按照交互稿实现自动隐藏功能 【方案】在设置mRectFragNaviBubble值后先取消2秒倒计时，再重新开始2秒倒计时 fix：在极端情况下，预计到达时间有可能超过3天 FordPhase4Scrum-59610 | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56371 | pass
账号 | bugfix | [edc-scrum-79004][edc-scrum-79925]车辆信息按pm要求改为请求车辆信息失败时显示本地缓存信息 [edc-scrum-75647]照妖镜问题修复：调用CarService偶发报SecurityException [edc-scrum-73359]【个人中心】修复分屏状态下，主驾点击投屏到副驾屏，个人中心出现闪退的问题 [edc-scrum-75647]照妖镜问题修复：IllegalStateException: already connected or connecting [edc-scrum-77041]修复toast不居中的问题 [edc-scrum-76967]修复707签约管理内容静止不拖动时进度条不隐藏的问题 [edc-scrum-74057]修复707帐号模块的多主题适配问题 [edc-scrum-67856]【707、718】支付模块去掉酒店和外卖 [edc-scrum-73071]车辆信息的info book在退至后台时收起 [edc-scrum-69709]707帐号管理增加空白页展示 [edc-scrum-66828] 解决VIN明文打印日志的问题 [edc-scrum-66828]修正707个人中心开关的位置达到与设计图一致 [edc-scrum-66828]U718不去掉个性化档案，提交DCV3 [edc-scrum-65931]【707、718】删除免密支付成功界面的酒店和外卖卡片 [edc-scrum-63753]707签约管理关闭弹框策略优化 [edc-scrum-64997]签约管理页面tab粒子动效优化，解决语音指令切换tab失败的问题 [edc-scrum-64997]签约管理页面tab粒子动效优化 | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56371 | pass
消息中心 | bugfix | [edc-scrum-78969]消息模板正文改为选填，修改为「消息标题、内容不可同时为空」的校验规则 [edc-scrum-78572]修复tts未播报结束而消息弹窗先关闭的问题 [edc-scrum-75660]照妖镜xCrash问题修复NullPointerException [edc-scrum-76368]修复重启系统后，5级消息在下了列表显示的时间与历史消息中不同步 [edc-scrum-67702]修复Launcher更多应用中历史消息图标在重启后展示图标不对 [edc-scrum-67916]消息中心多选框补充控件放大需求，并修复该需求ui走查问题 | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56371 | pass
输入法 | bugfix | edc-scrum-76462:车牌输入键盘UI优化 edc-scrum-77493:添加非空判断 edc-scrum-67242：1.解决recycleview使用过程中发生的异常； 2.修改加固脚本，so库不参与加固。 | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56371 | pass
场景推荐 | bugfix | 修改跳转传key，支持随心看推荐卡片语音正反馈跳转到播放页 | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56324 | pass
小程序 | bugfix | fix: edc-scrum-77817 UI走查问题修复 fix: edc-scrum-77829、edc-scrum-78287 UI走查问题修复 fix: edc-scrum-78287 Toast位置适配修复 fix: edc-scrum-78310 语音TTS反馈重复问题判断 fix: edc-scrum-78070、edc-scrum-75600 phase5 添加网络判断上层实现 fix: edc-scrum-72771 【707】【小程序】【签约管理】16:41 进入小程序后，取消签约管理，还能正常使用小程序 fix: edc-scrum-74948 【福特phase5】【U718】【小程序】点击查找区域停车场按钮，车位充足便签颜色会变化 fix: edc-scrum-74268、edc-scrum-74265、edc-scrum-74263、edc-scrum-73159、edc-scrum-73288 修复照妖镜平台空指针异常、语音端状态上报异常 | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56203 | 72771:验证失败，RD已修复，R11合入 其他：pass
天气 | bugfix | 天气:fix:【福特phase5】【CDX707】【天气】控制屏与显示屏的网络pm位置名称显示不一致 天气:fix:【福特phase5】【CDX707】【天气】card与天气应用首页车内PM值显示不一致 | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56203 | pass
安全 | bugfix | 隐私管控列表增加pinyin排序&&更新白名单&&修复授权bug | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/56118 | pass
随心看 | bugfix | Phase5: fix: -【707】调整toast触发时，第一次快结束shi，视觉场景缺失问题 edc-scrum-69380 Phase5: fix: 修复同一账号在两个车机播放VIP视频被拦截时继续播放问题[bug-id:edc-scrum-73077] phase5: fix: -爱奇艺视频暂停播放时切换投屏，会自动播放 [bug-id：edc-scrum-73533] Phase5: fix: widget Play按钮置灰时不可点击[bug-id:edc-scrum-73645] phase5: fix: -【偶现】车速大于5km/h副驾有人，进入随心看时弹出"开车不能播放视频"弹窗 [bug-id：edc-scrum-74224] Phase5: fix: 修复快捷面板进度条展示问题[bug-id:edc-scrum-74420] Phase5: fix: 小视频页面加载失败逻辑混乱处理[bug-id:edc-scrum-72649] Phase5: fix: 修复购买VIP会员出现的数组越界[bug-id:edc-scrum-73522] Phase5: fix: 修复协议可以复制搜索的问题[bug-id:edc-scrum-73076] Phase5: fix: 修复切换pano到card1后，安全弹窗显示到pano上问题[bug-id:edc-scrum-73380] Phase5: fix: 修复免责弹窗显示样式错误的问题 [bug-id: edc-scrum-73301] phase: fix: 替换爱奇艺-我的收藏item checkbox动效资源[bug-id:edc-scrum-68063] phase5: fix: 修复非会员账号观看会员视频pano提示异常[bug-id:edc-scrum-66650] Phase5: fix: 语音指令快进快退一点正常处理不播报[bug-id:edc-scrum-65901] phase: fix: 修复小视频每个视频解释时展示重播问题[bug-id:edc-scrum-68005] Phase5: fix: 修复爱奇艺收藏页面进入播放后取消收藏退回收藏页数据不一致问题[bug-id:edc-scrum-65740] Phase5: fix: 调整二维码弹窗加载样式 [bug-id: edc-scrum-63147] Phase5: fix: 去除标题栏的点击事件，增加返回按钮的触摸响应区域 [bug-id: edc-scrum-65949,edc-scrum-65962] phase5: fix: [补充]修复进入播放页偶现播放器初始化过慢导致车速回调崩溃[bug-id:edc-scrum-72673] phase5: fix: 修复退出签约偶现随心看crash问题[bug-id:edc-scrum-72674] phase5: fix: 修复进入播放页偶现播放器初始化过慢导致车速回调崩溃[bug-id:edc-scrum-72673] phase5: fix: 异常播放场景下，添加语音播报兜底[bug-id:edc-scrum-69251] Phase5: fix: -【707】调整目标端状态的发送 edc-scrum-69440 phase5: fix: 修复monkey时因为生命周期导致空指针问题[bug-id:edc-scrum-68228][bug-id:edc-scrum-68225] phase5: fix: 修复非VIP爱奇艺播放页语音/手动切换1080p展示不一致问题[bug-id:edc-scrum-69298] phase5: fix: -解决频繁切换出现crash [bug-id：edc-scrum-76408] phase5: fix: -解决综艺类型从列表点进去出现上一个按钮状态不同步问题 -移除mainActivity从外部启动 [bug-id：edc-scrum-76408] [bug-id：edc-scrum-76389] Phase5: fix: 修复"动漫筛选分类中显示【新类型】而不是【全部新类型】" 并调整UI [bug-id:edc-scrum-75591] Phase5: fix: 修复动漫筛选调整UI最少5个字符的宽度 [bug-id:edc-scrum-75591] Phase5: fix: 修复"影片播放结束后，最近播放观看剩余显示不会归零，会显示影片的全部时长" [bug-id:edc-scrum-73173] phase5: fix: -解决两次点播，第二次视频会暂停的问题 -解决副驾无人，中控暂停的场景，此时车速大于5再点播放，会直接在中控播 [bug-id：edc-scrum-76553] phase5: fix: 第一轮全量走查：pano R 、pano 弹层、Pano 暂停、Pano R简介与封面图、非沉浸态无遮罩问题 phase5: fix: 已暂停与加载中控件重叠及增加背景蒙层优化分屏小屏UE显示规则 phase5: fix: -补充解决投屏蒙版不消失问题； 【bug-id：edc-scrum-77313】 Phase5: fix: 弱网状态下进入短视频显示无网提醒与短视频首页信息展示重叠[bug-id:edc-scrum-79748] Phase5: fix: 点击短视频选集最后一个toast弹框提示当前最后一个，爱奇艺也是的[bug-id:edc-scrum-79796] phase5: fix: -更新基线sdk 3.1.1，exo播放器升级到2.18.2 fix：切换投屏到中控直接进入沉浸态 【bug-id：edc-scrum-77313】 phase5: fix: Pano屏沉浸态/非沉浸态显示有误 | http://222.190.133.163:8090/q/project:android%252Fproject%252Fford_phase5%252Fpackages%252Fapps%252FVideoPlayer+branch:FORD_PHASE5_CDX707_SOP,25 | Pass
随心听 | bugfix | Phase5: fix: 修复有声-清除缓存缺少toast问题[bug-id:edc-scrum-80291] Phase5: fix: 纠正搜索 diff 逻辑，避免 item 错误复用 [stroy-id: edc-scrum-75487] Phase5: fix: 修复点击有声-一键听播放按钮埋点数据[bug-id:edc-scrum-80103] Phase5: fix: 纠正喜马拉雅搜索初始逻辑 [stroy-id: edc-scrum-75487] Phase5: fix: 优化语音场景下从播放页到首页展示异常问题[bug-id:edc-scrum-78120] Phase5: fix: 修复播放列表上次播放错乱的问题,以及大列表 diff 产生的闪烁 [edc-scrum-76080] Phase5: fix: 修复注释测试代码 [edc-scrum-75372] Phase5: fix: 升级 SDK R02-V13 修复 Url 映射问题[bug-id:edc-scrum-76036,edc-scrum-75477] Phase5: fix: 修复有声列表向前加载显示异常的问题 [bug-id:edc-scrum-76161] Phase5: fix: 优化有声购买记录倒计时展示[bug-id:edc-scrum-77184] Phase5: fix: 修复歌手列表页首个item被遮挡问题[bug-id:edc-scrum-76095] Phase5: fix: 列表刷新回调增加队列记忆机制 [bug-id: edc-scrum-74909] Phase5: fix: 修复列表item展位图不统一问题[bug-id:edc-scrum-76078] Phase5: fix: 调整蓝牙耳机连接弹窗比例 [bug-id: edc-scrum-76052] Phase5: fix: 修复自建歌单列表变化时索引异常问题[bug-id:edc-scrum-76087] Phase5: fix: 修复清除歌单后widget展示专辑图片异常问题[bug-id:edc-scrum-76219] Phase5: fix: 修复有声列表页已购专辑文案[bug-id:edc-scrum-76160] Phase5: fix: 修复音乐播放页上次播放列表高亮颜色[bug-id:edc-scrum-76137] Phase5: fix: 添加SearchAndPlayRadio到离线nameSpace中[bug-id:edc-scrum-74893] Phase5: fix: 未签约是，两次语音拉起随心听展示异常问题[story-id:edc-scrum-72707] Phase5: fix: 网络请求Header中添加版本信息 [story-id:edc-scrum-72707] Phase5: fix: 修复播放列表可能更新紊乱的问题[edc-scrum-73300] Phase5: fix: 升级SDK版本，添加电台提连功能，修复电台lastSource失败问题[bug-id:edc-scrum-63127] Phase5: fix: active网络变换时通知客户端网络连接发生变化 [bug-id: edc-scrum-73452] Phase5: fix: 副驾随心听蓝牙耳机弹框逻辑添加防护[story-id:edc-scrum-72707] Phase5: fix: 云听上报埋点添加防护[story-id:edc-scrum-72707] Phase5: fix: 修复电台显示权限对话框时，closeApp后弹出toast问题;添加始终允许权限[bug-id:edc-scrum-73279][bug-id:edc-scrum-69798] Phase5: fix: 修复副驾随心听在USB播放时接收语音歌单后音频叠加和pano展示异常问题[bug-id:edc-scrum-73066][bug-id:edc-scrum-73054] Phase5: fix: 歌词解析添加防护限制死循环[bug-id:edc-scrum-73070][bug-id:edc-scrum-73068] Phase5: fix: 修复副驾随心听在USB音乐界面接收语音歌单后音频叠加和pano展示异常问题[bug-id:edc-scrum-73066][bug-id:edc-scrum-73054] Phase5: fix: 修复副驾随心听电台播放时在断开耳机后再次进入混音问题[bug-id:edc-scrum-72758] Phase5: fix: 增加删除列表相关日志,减少点击间隔[bug-id: edc-scrum-67614] phase5: fix：修复played埋点缺失问题[bug-id:edc-scrum-69236] Phase5 : fix : 电台首页本地电台播放按钮显示逻辑，搜索模块label【task-id : edc-scrum-67119】 phase5: fix: CloseAppProcessor 时通知安全关闭定位弹窗[bug-id:edc-scrum-68138] phase5: fix: 未签约时，LaunchApp不播报"好的"[bug-id:edc-scrum-68424] phase5: fix: 上报start端状态后再次上报前后台状态，避免被覆盖[story-id:edc-scrum-66969] Phase5: fix: 适配card 被覆盖场景的floatingButton vtsExtension[bug-id:edc-scrum-75278] phase5: fix: 调整路由注册时序[bug-id:edc-scrum-67604] phase5: fix: 修复音乐最近播放页面，语音切歌后列表展示逻辑[bug-id:edc-scrum-67094] Phase5: fix: 修复 BaseLifecycleAdapter 页面生命周期缺陷的问题 [bug-id: edc-scrum-66799] phase5: fix: 修复搜索结果列表展示异常问题[bug-id:edc-scrum-67055] Phase5: fix: 修复电台未知节目显示不一致的问题 [bug-id: edc-scrum-67054,edc-scrum-67053] Phase5: fix: APIMCIM-23130【必现】随心听QQ音乐二级界面返回随心听主界面会发生闪屏 | http://222.190.133.163:8090/q/project:android%252Fproject%252Fford_phase5%252Fpackages%252Fapps%252FAudioPlayer+branch:FORD_PHASE5_CDX707_SOP,25 | pass

## Fixed Bug List
Key | Summary | Priority

## Open Bug List
Key | Summery | Frequency | Priority | Affects Version | Repeat step | Risk assessment | Root cause | PCA | ICA | Fix version | Comment | CIA | 1. Must Include Ford & Supplier Open Issue. 2. For the Priority P0/P1, must fill G-K line. 3. For P2/P3/P4, G-K are not mandatory to fill.

## Metrics
Process | Proposed KPI | Target / Norm | Operational Definition | Archivement Time | Week/Month | Comments
SWE.1.Software Requirements Analysis | Software Requirements Reviewed Rate % | 100% | Number of approved(reviewed) Software Requirements/ Number of Software Requirements | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.2.Software Architectural Design | SW Architectural to SW Requirement Coverage Rate | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.3 Software Detailed Design and Unit Construction | Traceable Software requirements(Jira Story) to the code | 100% | All Jira requirements should have a corresponding software unit in GIT | SOP: All requirement Formal release scope : The requirements planned to be released in this version. |  | Using Traceability From Code to Requirement&Change_Template to show the evidence.
SWE.3 Software Detailed Design and Unit Construction | SW detail design to SW Architectural Coverage | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.4 Software Unit Verification | Unit test（Code） coverage | >= 80 % | (Conditions True + Conditions False + Covered Lines)/(2*Conditions + Executable Lines) | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.4 Software Unit Verification | Static Code Analysis Number of Critical Bugs | 0 | Static Code result in Sonar. | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Planned Integration Test cases vs. actual executed integration test cases | 100% | Percentage of SW integration Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Software Integration Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Software Integration Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Software Integration Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | SW architecture design test coverage (HLD with Ready State test cases) | 100% | (Number of HLD SQD have integraton test Case + Number of Interface have integration test case)/(Number of HLD SQD + Number of interface) | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Count of Software Integration Test defects | 0 | Count of Integration Defects | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Planned Qualification test cases vs. actual executed Qualification test cases | 100% | Percentage of SW Qualification Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | SW requirement test coverage | 100% | Percentage of Requirements in Jira that has corresponding test cases in TestRail | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Count of Software Qualification test defects | 0 | Count of Defects raised in the SW Qualification Testing Phase | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.1 Quality Assurance | NC closure rate | 90% | Closed NC/Total NC | Monthly
SUP.1 Quality Assurance | Process Audit compliance | 100% | Percentage of audits completed on time | Monthly
SUP.8 Configuration Management | Nightly builds have a success rate | 100% | Percentage of compliance as defined in the process audit checklist | Every Sprint
SUP.8 Configuration Management | Ba'seline completed Rate | 100% | Count of of actually baseline CI Item number/ Count of Planned baseline CI item Number | Monthly
SUP.8 Configuration Management | CM Audit Passrate | 100% | Passrate of CM Audit Checklist: Count of passed Number in CM Audit Checklist/total planned CM Audit Checklist | Monthly
SUP.9 Problem Resolution Management | Immediate Gating/Gating （Critical） defects for release | 0 | All urgent defects actioned on high priority, | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.9 Problem Resolution Management | Problem closure adherence | 100% | No. of defects closed against no. of defects planned for closure in this release （Include Project deviation issue and Defect） | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.9 Problem Resolution Management | Defect fix time | <40 | Defect fix time | Every Sprint
SUP.9 Problem Resolution Management | Count of IG&G defect @current version | <1 | Count of IG&G defect @current version | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.10 Change Request Management | Change Request status closure % | 100% | No. of Change Requests completed / Total number of change requests raised in the version | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
MAN.3 Project Management | Requirement Completion Rate for sprint/Milestone | > 85% | No. of requirements delivered / No. of requirements committed for this sprint/Milestone | Every Sprint/Milestone
MAN.3 Project Management | Commitment Adherencen for All Requirement | 100% | No. of requirements delivered / No of requirements Committed for all requirement | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
Software Metrics Conlusion
Metrics Summary:

## Sign off Evidence
截图必须包含 ： 版本号 发起sign off 的名字 Approve 者的名字 Sign off的时间 Note： 1. Sign off的版本以供应商测试完的时间点; 2. Milestone release 副总签字,OKTB/OTA 要求总经理签字； Inhouse： Milestone release LL5, OKTB/OTA: LL4;