## RL-Revision-History
Release Note Change Record History
Version Number | Release Date | Author | Reviewer | Approver | Content Changes
1 | 2023-07-24 | whuang54@ford.com | qzhang90@ford.com | qzhang90@ford.com | CDX707 R12 eng1 版本发版
2 | 2023-08-17 | whuang54@ford.com | qzhang90@ford.com | qzhang90@ford.com | CDX707 R12 HF1 版本发版
2.1 | 2023-09-15 | whuang54@ford.com | qzhang90@ford.com | qzhang90@ford.com | CDX707 R12 HF4 版本发版

## Release Content
Software Release Information List |  |  |  | 1. 各方需要提供该格式的release note； 2. 集成方需要整合各方的release content，Fixed Bug list Open Bug List 的内容； 3. Release note的内容准确性由各个开发方的PM&SWQ来保证，Ford方的System Integration Manager&SWQ 来检查 4. Release note 版本号： After Integration Completed 1.* After Supplier Test Completed 2.* REC(End To End) Test Completed 3.*
Software Release Information Description
Prepared By |  |  | Reviewed By:
Date
Software Version Information
SOC SW Version
General Info |  | SOC SW P/N
Main board HW Version
MCU SW Version
MCU SW P/N
Checksum
Software Release Content
Release Content | 新增功能
| 完善功能 | 1.Lidget SYNCCHINAT-3619个性化推荐协议日期修改 SYNCCHINAT-3841替换腾讯SDK SYNCCHINAT-3619优化应用crash后widget在pano投屏 2.VPA SYNCCHINAT-3536多天天气 SYNCCHINAT-3536天气UI变更，加入空气质量显示 SYNCCHINAT-3645蓝牙电话上限数量99个 SYNCCHINAT-3536VPA唤醒后背景图优化 3.Emanual APIMCIM-31508更新GAS手册内容
| BUG修复 | 见Fixed Bug List
设计调整
| 遗留问题 | 见Open Bug List
Software Release Conclusion
针对该版本发布的结论： 1.从计划实现功能的角度，是否有偏差，计划实现需求多少，实际实现需求多少； 2.该版本的测试结论； 3.目前Bug 情况，是否满足该节点的要求； 4.本版本的限制条件以及limitation； 5.从Metrics 的角度，该版本的风险项以及mitigation计划；

## Fixed Bug List
Key | Summary | Priority | Fixed Version
APIMCIM-25955 | Phase 5：【必现】当唤起语音完成一只指令后，再次说“你好林肯”，Controller屏的状态栏会闪一下 | P2 | R12 eng1
APIMCIM-18857 | Phase 5：【必现】语音未在widget,pano R播放视频时，进入精简屏幕，左下角不显示VPA" | P2 | R12 eng1
APIMCIM-24503 | 【必现】[CDX707][HMI走查] 个人时光_页面视觉布局问题) | P3 | R12 eng1
APIMCIM-24015 | Car Bluetooth was not connected to the media and phone originally but it was automatically connected after the passenger left the co-pilot | P2 | R12 eng1
APIMCIM-24010 | After the ACC mode triggers the Smart Order, the brake ignition will be triggered again | P2 | R12 eng1
APIMCIM-25329 | 【CDX707】【100%】【SurpriseMessage】同一时间点多条秘信弹出播放时出现两种异常 - Ford Jira Cloud (atlassian.net) | P2 | R12 eng1
APIMCIM-25328 | 【CDX707】【100%】【SurpriseMessage】精彩回顾中，滑动到靠后秘信，点击播放，停止播放后，页面直接返回到精彩回顾首页 - Ford Jira Cloud (atlassian.net) | P2 | R12 eng1
APIMCIM-20472 | 【Phase V】【CDX707】【A】【自动化】Monkey测试，出现system_server ANR，连续出现几次 | P2 | R12 eng1
APIMCIM-21997 | 【必发】IVI，本地应用，时空密信，精彩回放，播放密信，点击暂停按键背景有个黑框短暂显示11：08 | P2 | R12 eng1
APIMCIM-23016 | [CDX707][VOCF][100%]Switching topics when reviewing spatiotemporal confidential messages can cause abnormal return logic | P2 | R12 eng1
APIMCIM-23785 | Phase 5【AutoTest】Monkey测试期间，出现com.ford.sync.surprisemessage包的crash异常 | P2 | R12 eng1
APIMCIM-24206 | Phase 5【AutoTest】Monkey测试60h，出现com.ford.sync.surprisemessage包的crash异常 | P2 | R12 eng1
APIMCIM-24281 | [CDX707][100%]Expired message not triggered after ignition | P2 | R12 eng1
APIMCIM-24242 | [CDX707][100%]Switch back to Surprise Message from other apps the controller screen is still in the preview screen | P2 | R12 eng1
APIMCIM-24272 | [CDX707][Occasional]The surprise message was not triggered when the time came | P2 | R12 eng1
APIMCIM-21286 | 【高频】IVI，打开时空密信，精彩回顾，显示屏闪一下，实车查看10：40 | P2 | R12 eng1
APIMCIM-25360 | 【CDX707】【marketplace】订阅商城页面，长按页面中文字可进入选中状态 | P2 | R12 eng1
APIMCIM-25512 | 已打开爱车探索时下达指令：关闭爱车探索，播报不全 | P2 | R12 eng1
APIMCIM-27793 | [CDX707][100%]The controller screen still display the surprise message interface after switch to Settings page | P2 | R12 eng1
APIMCIM-25519 | iQiyi will crash and cannot be accessed from iQiyi icon again after pausing the iQiyi video entered through Personal Enjoyment | P2 | R12 HF1
APIMCIM-24009 | No pop-up windows that cannot be saved in Smart Order | P2 | R12 HF1
APIMCIM-25327 | 【CDX707】【100%】【SurpriseMessage】秘信到点弹出时，controller屏上的信封动画出现卡顿 | P2 | R12 HF1
APIMCIM-26615 | [CDX707][50%]Monkey test, Some of ford's applications Crash. | P2 | R12 HF1
APIMCIM-26736 | [CDX707c/U718][100%]Surprise Message, the prompt ""vehicle speed is greater than 5km/h"" needs to be added to toast prompt | P2 | R12 HF1
APIMCIM-23739 | [CDX707][65%]The expired surprise message has no sound | P2 | R12 HF1
APIMCIM-26673 | 【CDX707】【100%】【SurpriseMessage】秘信弹出播放时，语音切换主题，pano屏退出播放，controller屏的信封动画还在 | P3 | R12 HF1
APIMCIM-27093 | 【U718】【100%】【SurpriseMessage】kill掉秘信进程后，秘信播放出现异常 | P2 | R12 HF1
APIMCIM-27229 | 【PhaseV】【CDX707】【A】【Monkey】【2/5】com.ford.sync.electronicmanual内存泄漏 | P2 | R12 HF1
APIMCIM-26591 | [CDX707][Lidget][必现]林肯微界，惊喜视频格式的资料全屏播放时，语音切换主题，pano屏显示异常 | P2 | R12 HF1
APIMCIM-26950 | [CDX707][100%]The Lidget card still displays the New icon when exiting the account | P2 | R12 HF1
APIMCIM-26948 | [CDX707][100%]Entering the Lidget again still displays a login pop-up when loggin the account | P2 | R12 HF1
APIMCIM-27021 | [Phase5][U718][Lidget][必现]切换账号，点击左下角回到主页后，再次进入lidget，内容未更新 | P2 | R12 HF1
APIMCIM-26603 | [CDX707][Lidget][必现]暂停播放，拖动control屏进度条，pano屏视频变化，进度条未同步更新 | P2 | R12 HF1
APIMCIM-26607 | [CDX707][Lidget][必现]普通视频播放暂停时，播放音乐，再播放普通视频，音频焦点未能抢占成功 | P2 | R12 HF1
APIMCIM-28182 | [Phase4][Phase5][Lidget][必现]车端未及时删除已到期惊喜视频 | P2 | R12 HF1
APIMCIM-26474 | 【CDX707】【必现】【DemoMode】使用语音拨打电话后，使用语音打开爱车探索视频，仍会显示“确定”“取消” | P3 | R12 HF1
APIMCIM-26477 | 视频暂停播放状态，语音切换主题后，视频会自动播放 | P3 | R12 HF1
APIMCIM-26401 | Phase 5【AutoTest】Monkey测试16h，出现两次com.ford.sync.lidget包的Crash异常 | P2 | R12 HF1
APIMCIM-26396 | Phase 5【AutoTest】Monkey测试16h，出现一次com.ford.sync.lidget包的ANR异常 | P2 | R12 HF1
APIMCIM-30278 | [CDX707][Lidget][必现]USB升级rom，普通视频加载失败，播放证书丢失 | P2 | R12 HF4
APIMCIM-29091 | 【Phase 5】【CDX707】【必现】上班开始时间与下班时间重叠后保存按钮高亮 | P2 | R12 eng1
APIMCIM-28336 | 【CDX707】【偶现】【DemoMode】动态演示视频播放结束时，语音切换主题后，点击完成，调起了舒享时氛的动态视频 | P2 | R12 eng1
APIMCIM-27957 | [CDX707][100%]The information point for seat adjustment in the interior jumps incorrectly | P3 | R12 eng1
APIMCIM-27558 | [CDX707][VPA][必现]天气显示界面继续查询其他天气 icon未显示天气形象 | P2 | R12 eng1
APIMCIM-26431 | [CDX707][Lidget][必现]未开通lidget权限的账号切换至开通并配置过场景的账号，林肯微界未及时刷新 | P2 | R12 eng1
APIMCIM-26369 | [CDX707][100%]VPA在有lidget背景唤醒时，VPA背景效果不好，环绕试试说有边框 | P3 | R12 eng1
APIMCIM-26301 | [CDX707][100%]Multiple expired messages are not displayed after ignition run | P2 | R12 eng1
APIMCIM-24779 | [CDX707][100%]VPA needs to be optimized when invoke it during video playing | P2 | R12 eng1

## Open Bug List
CIA (Customer Impact Assessment)
Key | Supplier | Summery | Priority | Repeat step | Frequency | Affects Version | Issue Analysis |  |  | ICA | PCA | Planned Fix Version | Data Tagging Analysis | Customer Complain
[7 empty] | Risk assessment （Need FO Confirmation） | XCL Evaluation | Root cause
APIMCIM-29098 | Inhouse | 【Phase V】【CDX707】【B】【VR】【5/5】蓝牙电话已连接已有联系人搜索有1个结果（无号码时），唤醒VR，语音"打电话给XX（名字）"，跳转出该空号码选项，点击空白处会选中该号码并拨出 | P2 | 测试步骤 | 必现 | R12及之前版本 | 特殊场景的问题 | 特殊场景没有处理 | 增加特殊场景处理 | NA | R13 | R13 | NA | NA
APIMCIM-28393 | Inhouse | 【CDX707】【100%】【SurpriseMessage】创建/编辑秘信时，设置过期时间后，预览未置灰，但是点击无反应 | P2 | 测试步骤 | 必现 | R12及之前版本 | 对用户正常使用无影响 | 未实现预览按钮添加时间设置错误的置灰逻辑 | 时间设置错误置灰 | NA | R13 | R13 | NA | NA
APIMCIM-29378 | Inhouse | 【CDX707】【100%】【VR】语音打开时空秘信时，语音提示“当前状态不支持，请稍后重试” | P2 | 测试步骤 | 必现 | R12及之前版本 | 不影响用户正常使用 | 语言指令变更，增加了分屏参数，state从第一个参数变成第二个 | 修改参数调用 | NA | R13 | R13 | NA | NA
APIMCIM-28392 | Inhouse | 【CDX707】【100%】【SurpriseMessage】秘信弹出播放页面，语音切换主题，出现2种异常 | P2 | 测试步骤 | 必现 | R12及之前版本 | 切换主题场景问题 | 语言切换主题，pano屏退出，中控屏重走生命周期 | 切换主题，中控屏退出 | NA | R13 | R13 | NA | NA
APIMCIM-29355 | Inhouse | 【CDX707】【黑盒】【偶现】【Lidget】重启车机后，林肯微界卡片左上角不显示对应的应用名称 | P2 | 测试步骤 | 偶现 | R12及之前版本 | icon显示问题，不影响使用 | 投屏监听服务未绑定成功，导致无法与左侧警告窗交互，导致左上角字体被警告窗遮挡 | 优化注册投屏监听服务，需要在onServiceConnected之后绑定 | NA | R13 | R13 | NA | NA

## Metrics
Process | Proposed KPI | Target / Norm | Operational Definition | Achievement Time | Week/Month | Comments
SWE.1.Software Requirements Analysis | Software Requirements Reviewed Rate % | 100% | Number of approved(reviewed) Software Requirements/ Number of Software Requirements | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.2.Software Architectural Design | SW Architectural to SW Requirement Coverage Rate | 100% | Jira Traceability/Excel Traceability | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.3 Software Detailed Design and Unit Construction | Traceable Software requirements(Jira Story) to the code | 100% | All Jira requirements should have a corresponding software unit in GIT | SOP: All requirement Formal release scope : The requirements planned to be released in this version. |  | Using Traceability From Code to Requirement&Change_Template to show the evidence.
SWE.3 Software Detailed Design and Unit Construction | SW detail design to SW Architectural Coverage | 100% | Jira Traceability/Excel Traceability | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.4 Software Unit Verification | Unit test（Code） coverage | >= 80 % | (Conditions True + Conditions False + Covered Lines)/(2*Conditions + Executable Lines) | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.4 Software Unit Verification | Static Code Analysis Number of Critical Bugs | 0 | Static Code result in Sonar. | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Planned Integration Test cases vs. actual executed integration test cases | 100% | Percentage of SW integration Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Software Integration Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Software Integration Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Software Integration Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | SW architecture design test coverage (HLD with Ready State test cases) | 100% | (Number of HLD SQD have integration test Case + Number of Interface have integration test case)/(Number of HLD SQD + Number of interface) | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Count of Software Integration Test defects | 0 | Count of Integration Defects | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Planned Qualification test cases vs. actual executed Qualification test cases | 100% | Percentage of SW Qualification Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | SW requirement test coverage | 100% | Percentage of Requirements in Jira that has corresponding test cases in TestRail | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Count of Software Qualification test defects | 0 | Count of Defects raised in the SW Qualification Testing Phase | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.1 Quality Assurance | NC closure rate | 90% | Closed NC/Total NC | Monthly
SUP.1 Quality Assurance | Process Audit compliance | 100% | Percentage of audits completed on time | Monthly
SUP.8 Configuration Management | Nightly builds have a success rate | 100% | Percentage of compliance as defined in the process audit checklist | Every Sprint
SUP.8 Configuration Management | Baseline completed Rate | 100% | Count of of actually baseline CI Item number/ Count of Planned baseline CI item Number | Monthly
SUP.8 Configuration Management | CM Audit Pass rate | 100% | Pass rate of CM Audit Checklist: Count of passed Number in CM Audit Checklist/total planned CM Audit Checklist | Monthly
SUP.9 Problem Resolution Management | Immediate Gating/Gating （Critical） defects for release | 0 | All urgent defects actioned on high priority, | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.9 Problem Resolution Management | Problem closure adherence | 100% | No. of defects closed against no. of defects planned for closure in this release （Include Project deviation issue and Defect） | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.9 Problem Resolution Management | Defect fix time | <40 | Defect fix time | Every Sprint
SUP.9 Problem Resolution Management | Count of IG&G defect @current version | <1 | Count of IG&G defect @current version | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.10 Change Request Management | Change Request status closure % | 100% | No. of Change Requests completed / Total number of change requests raised in the version | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
MAN.3 Project Management | Requirement Completion Rate for sprint/Milestone | > 85% | No. of requirements delivered / No. of requirements committed for this sprint/Milestone | Every Sprint/Milestone
MAN.3 Project Management | Commitment Adherence for All Requirement | 100% | No. of requirements delivered / No of requirements Committed for all requirement | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
Software Metrics Conclusion
Metrics Summary:

## Sign off Evidence
截图必须包含 ： 版本号 发起sign off 的名字 Approve 者的名字 Sign off的时间 Note： 1. Sign off的版本以供应商测试完的时间点; 2. Milestone release 副总签字,OKTB 要求总经理签字； Inhouse： Milestone release LL5, OKTB/OTA: LL4;