## 01 测试报告
U625MCA_Emanual
ROM Version | daily | Test Date | 2022/8/3---2022/8/6
APK Version | 1.0.1 | Test Purpose | 新需求
测试环境 | Bench | Milestone | DCV1
IVI SOC version | daily
IVI MCU version | 20220728_LA_NB_daily_ENG
IVI Box | Bench： PART No:R2AT-18D668-EA MODEL:CDC105B IVI No:109JDXEA000010 | 实车：NA | Vin No.：NA
测试结论 | Go
关键风险描述 | NA
测试充分性评估 | 测试范围 | 用例/回归问题单数量（个） | 测试结果（个）
| 1.Emanual全功能测试 | 用例数量：73 回归问题单数量：0 | Pass:68 Fail:5 Block:0
测试项 | 指标检查点 | 内容 | 备注
功能测试 | 用例密度 | 73
| 用例通过率 | 93%
| 缺陷数量 | 7
| 当前版本关键问题 | IG=0,G=0
| 当前模块遗留问题 | 7
性能测试
遗留问题列表
Key | 内容 | 级别 | 类型
APIMCIM-9970 | [U625MCA][Phase5][Emanual][优化]维修保养、经销商列表、快捷指南、道路救援4个搜索页面里的热门搜索，搜索不到结果 | H | NEW
APIMCIM-9934 | [U625MCA][Phase5][Emanual]点击热门搜索-后视镜调节，未搜索到相应结果 | H | NEW
APIMCIM-9933 | [U625MCA][Phase5][Emanual]在搜索页面未搜索到结果时，提示语不正确 | H | NEW
APIMCIM-9931 | [U625MCA][Phase5][Emanual]确认是否清空历史提示框中的‘清空’按钮与‘取消’按钮位置错误 | H | NEW
APIMCIM-9930 | [U625MCA][Phase5][Emanual]点击信息点-车轮和轮胎，跳转至对应页面后，定位错误 | H | NEW
APIMCIM-9929 | [U625MCA][Phase5][Emanual]点击信息点-座椅调节，跳转位置不对 | H | NEW
APIMCIM-9928 | [U625MCA][Phase5][Emanual]点击信息点-打开和关闭天窗，跳转位置不对 | H | NEW

## 02 测试用例
ID | Title | Steps | Status
T90848791 | 外饰_3D图像检查 | 1.停留在‘外饰’ 页签 Stay on the 'Exterior' tab Expected Result: 1.外饰3D图像根据车型，版本显示正确，显示图片仅供参考图释 The exterior 3D view of vehicle could display correctly accorrding to the model and version, and show '360°' and '图片仅供参考‘ at the bottom right | Passed
T90848792 | 外饰_检查3D图像 | 1.停留在‘外饰’ 页签 Stay on the 'Exterior' tab Expected Result: 1.外饰3D图像展示正确且能被切换至‘内饰’页签 The 3D view of exterior could display and can be slided to 'Interior' 2.3D图像可根据操作被旋转，根据车型存在4或6个停止位 3D view could rotate accorrding to the operation, and there exists 4 or 6 stops depending on different models | Passed
T90848793 | 外饰_检查信息点 | 1.点击‘外饰’按钮 Click on 'exterior' option 2.点击图像上信息点 Click on spot 3.点击图像上信息点提示内容 Click on the hint Expected Result: 1.外饰3D图像和内置信息点可正确展示且不互相重叠 The 3D view and the spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘如何打开和关闭发动机舱盖’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'How to open the hood', and could disappear when tapping other area out of the hint 3.跳转至发动机舱盖相关章节，显示包括文本/图片/注释和参考链接 Turn to hood instruction, showing text/picture instructions and references | Passed
T90848794 | 外饰_检查信息点展示-进入‘SYNC+’后返回外饰图片 | 1.点击‘外饰’按钮 Click on 'exterior' option 2.点击图像上信息点 Click on spot 3.点击‘SYNC+’大卡片 Clicking on 'quick entry' 4.点击退出按钮 Click on 'back' button 5.检查信息点和提示信息展示 Check spot and hint display Expected Result: 1.外饰3D图像和内置信息点可正确展示且不互相重叠 The 3D view and the spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘如何打开和关闭发动机舱盖’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'How to open the hood', and could disappear when tapping other area out of the hint 3.跳转至‘SYNC+’章节，显示包括文字图片/注释和参考链接 Turn to quick entry instruction, showing picture/word/dynamic graph/video 4.返回应用主页 Back to home page 5.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848795 | 外饰_检查信息点展示-切换内饰页签后返回外饰图片 | 1.点击‘外饰’按钮 Click on 'exterior' option 2.点击图像上信息点 Click on spot 3.点击‘内饰’页签 Click on 'Interior' tab 4.点击‘外饰’页签 Click on 'Exterior' tab 5.检查信息点和提示信息展示 Check spot and hint display Expected Result: 1.外饰3D图像和内置信息点可正确展示且不互相重叠 The 3D view and the spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘如何打开和关闭发动机舱盖’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'How to open the hood', and could disappear when tapping other area out of the hint 3.跳转至内饰页签 Turn to interior view 4.切换回外饰页签 Switch back to exterior view 5.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848796 | 外饰_检查信息点展示-进入提示信息后返回外饰图片 | 1.点击‘外饰’按钮 Click on 'exterior' option 2.点击图像上信息点 Click on spot 3.点击图像上提示信息 Click on the hint 4.返回应用主页面，检查信息点和提示信息展示 Back to home page and check spot and hint display Expected Result: 1.外饰3D图像和内置信息点可正确展示且不互相重叠 The 3D view and the spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘如何打开和关闭发动机舱盖’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'How to open the hood', and could disappear when tapping other area out of the hint 3.跳转至发动机舱盖相关章节，显示文字/图片/链接Turn to hood instruction, showing text/picture instructions and references 4.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848798 | 外饰_和系统交互后-检查信息点展示 | 1.点击‘外饰’按钮 Click on 'exterior' option 2.点击图像上信息点 Click on spot 3.点击侧边（或底部）栏‘主页’按钮，返回系统主页 Click on 'Home' button to return to DuerOs home page 4.返回应用首页，检查信息点和提示信息展示 Back to E-Manual application and check spot and hint display Expected Result: 1.外饰3D图像和内置信息点可正确展示且不互相重叠 The 3D view and the spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘如何打开和关闭发动机舱盖’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'How to open the hood', and could disappear when tapping other area out of the hint 3.跳转至系统首页 Turn to DuerOS home page 4.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848799 | 外饰_和其他应用交互后-检查信息点展示 | 1.点击‘外饰’按钮 Click on 'exterior' option 2.点击图像上信息点 Click on spot 3.切换至其他应用，例如导航应用 Switch to other application like navigtion 4.返回应用首页，检查信息点和提示信息展示 Back to E-Manual and check spot and hint display Expected Result: 1.外饰3D图像和内置信息点可正确展示且不互相重叠 The 3D view and the spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘如何打开和关闭发动机舱盖’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'How to open the hood', and could disappear when tapping other area out of the hint 3.跳转至导航应用界面 Turn to navigation application 4.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848800 | 验证点击信息点-雨刮和洗涤器，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-雨刮和洗涤器 3、查看是否跳转至雨刮和洗涤器相关页面 | Passed
T90848801 | 验证点击信息点-灯光，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-灯光 3、查看是否跳转至灯光相关页面 | Passed
T90848802 | 验证点击信息点-打开和关闭天窗，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-打开和关闭天窗 3、查看是否跳转至打开和关闭天窗相关页面 | Failed
T90848803 | 验证点击信息点-后备箱门，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-后备箱门 3、查看是否跳转至后备箱门相关页面 | Passed
T90848804 | 验证点击信息点-车门和车锁，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-车门和车锁 3、查看是否跳转至车门和车锁相关页面 | Passed
T90848805 | 验证点击信息点-车轮和轮胎，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-车轮和轮胎 3、查看是否跳转至车轮和轮胎相关页面 | Failed
T90848806 | 验证点击信息点-方向盘，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-方向盘 3、查看是否跳转至方向盘相关页面 | Passed
T90848807 | 验证点击信息点-组合仪表，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-组合仪表 3、查看是否跳转至组合仪表相关页面 | Passed
T90848808 | 验证点击信息点-信息娱乐系统，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-信息娱乐系统 3、查看是否跳转至信息娱乐系统相关页面 | Passed
T90848809 | 验证点击信息点-空调控制，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-空调控制 3、查看是否跳转至空调控制相关页面 | Passed
T90848810 | 验证点击信息点-座椅调节，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-座椅调节 3、查看是否跳转至座椅调节相关页面 | Passed
T90848811 | 验证点击信息点-雨刮和洗涤器，是否跳转至对应页面跳转 | 1、进入电子手册 2、点击信息点-雨刮和洗涤器 3、查看是否跳转至雨刮和洗涤器相关页面
T90848800 | 内饰_检查内饰全景图像（车型和图释） | 1.点击‘内饰’按钮 Click on 'interior' option Expected Result: 1.内饰全景图像根据车型，版本显示正确，右下角显示’图片仅供参考‘图释 The Interior panoramic view of vehicle could display correctly accorrding to the model and version, and show '图片仅供参考‘ at the bottom right | Passed
T90848801 | 内饰_检查信息点展示 | 1.点击‘内饰’按钮 Click on 'interior' option 2.点击图像上信息点 Click on spot 3.点击信息点旁的提示信息 Click on the hint Expected Result: 1.内饰全景图像和内置信息点可正确展示且不互相重叠 The panoramic view and the all spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘空调控制’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'Climate Control', and could disappear when tapping other area out of the hint 3.跳转至空调控制章节，显示文字/图片/链接 Turn to climate control instruction, showing text/picture instructions and references | Failed
T90848802 | 内饰_进入‘标识’后返回内饰页签-检查信息点展示 | 1.点击‘内饰’按钮 Click on 'interior' option 2.点击图像上信息点 Click on spot 3.点击‘SYNC+’ 大卡片 Clicking on 'quick entry' 4.退出‘标识’章节页面 Quit instruction page 5.检查信息点和提示信息展示 Check spot and hint display Expected Result: 1.内饰全景图像和内置信息点可正确展示且不互相重叠 The panoramic view and the all spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘空调控制’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'Climate Control', and could disappear when tapping other area out of the hint 3.跳转至‘SYNC+’相关章节，显示图片/文字/链接 Turn to quick entry instruction, showing picture/word/reference 4.返回应用主页面 Back to home page 5.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848803 | 内饰_切换外饰页签后返回内饰页签-检查信息点展示 | 1.点击‘内饰’按钮 Click on 'interior' option 2.点击图像上信息点 Click on spot 3.切换至‘外饰’页签 Switch to 'Exterior' tab 4.切换回‘内饰’页签 Switch back to 'interior' tab 5.检查信息点和提示信息展示 Check spot and hint display Expected Result: 1.内饰全景图像和内置信息点可正确展示且不互相重叠 The panoramic view and the all spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘空调控制’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'Climate Control', and could disappear when tapping other area out of the hint 3.跳转至外饰页签 Turn to exterior view 4.返回内饰页签 Back to interior view 5.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848804 | 内饰_进入信息页后返回内饰页签-检查信息点展示 | 1.点击‘内饰’按钮 Click on 'interior' option 2.点击图像上信息点 Click on spot 3.点击提示信息 lick on the hint 4.返回应用主页，检查信息点和提示信息展示 Back to home page and check spot and hint display Expected Result: 1.内饰全景图像和内置信息点可正确展示且不互相重叠 The panoramic view and the all spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘空调控制’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'Climate Control', and could disappear when tapping other area out of the hint 3.跳转至空调控制章节，展示文字/图片/链接 Turn to climate control instruction, showing text/picture instructions and references 4.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848805 | 内饰_与系统交互后-检查信息点展示 | 1.点击‘内饰’按钮 Click on 'interior' option 2.点击图像上信息点 Click on spot 3.点击‘后退’按钮，返回系统首页 Click on 'Back' button to return to DuerOs home page 4.返回应用主页，检查信息点和提示信息展示 Back to E-Manual application and check spot and hint display Expected Result: 1.内饰全景图像和内置信息点可正确展示且不互相重叠 The panoramic view and the all spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘空调控制’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'Climate Control', and could disappear when tapping other area out of the hint 3.返回系统首页 Turn to DuerOS home page 4.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848806 | 内饰_与其他应用交互后-检查信息点展示 | 1.点击‘内饰’按钮 Click on 'interior' option 2.点击图像上信息点 Click on spot 3.切换至其他应用，例如导航应用 Switch to other application like navigtion 4.返回电子手册应用，检查信息点和提示信息展示 Back to E-Manual and check spot and hint display Expected Result: 1.内饰全景图像和内置信息点可正确展示且不互相重叠 The panoramic view and the all spots inside could display in the proper area and not overlap each other 2.信息点提示内容正常展示，例如‘空调控制’，当点击其他空白区域后，提示内容被自动隐藏 The hint of the spot coule be display, such as 'Climate Control', and could disappear when tapping other area out of the hint 3.跳转至导航应用 Turn to navigation application 4.图像信息点仍显示但提示信息被自动隐藏 The spot still displays but hint disappears | Passed
T90848789 | 主页卡片检查 | 1.检查首页小卡片数量和名称 Check quick entry quantity and content Expected Result: 1.首页小卡片数量为6，分别为：完整内容，快速访问，车辆安全，维护保养道路救援，标识，多媒体 There are 5 quick entries : Helps, Road Rescue, Maintain, Symbol, Dealer List | Passed
T90848790 | 主页卡片内容和数量检查 | 1.检查首页小卡片数量和名称 Check quick entry quantity and content Expected Result: 1.首页小卡片数量为6，分别为：完整手册，SYNC+，道路救援，维修保养，标识，经销商列表 There are 6 quick entries : All, Quick Entry, Road Rescue, Maintain, Symbol, Dealer | Passed
T90848807 | 首页卡片_通过首页卡片查看用车帮助手册 | 1.点击‘用车帮助’卡片 Click on 'symbol' Expected Result: 1.跳转至完整内容手册-标识章节，显示包括图片/文字 Turn to quick entry instruction, showing picture/word | Passed
T90848808 | 首页卡片_通过首页卡片查看标识手册 | 1.点击‘标识’卡片 Click on 'SYNC+' Expected Result: 1.跳转至标识手册章节，显示包括图片/文字/链接 Turn to SYNC+ instruction, showing picture/word/reference | Passed
T90848809 | 首页卡片_通过首页卡片查看道路救援手册 | 1.点击‘道路救援’卡片 Click on 'Road rescue' Expected Result: 1.跳转至道路救援手册内容，显示包括图片/文字/链接 Turn to Road rescue instruction, showing picture/word/reference | Passed
T90848810 | 首页卡片_通过首页卡片查看维修保养手册 | 1.点击‘维修保养’卡片 Click on 'Maintain' Expected Result: 1.跳转至维修保养手册内容，显示包括图片/文字/链接 Turn to maintain instruction, showing picture/word/dynamic graph/video | Passed
T90848811 | 首页卡片_通过首页卡片查看快速指南手册 | 1.点击‘标识’卡片 Click on 'symbol' Expected Result: 1.跳转至快速指南章节，显示包括图片/文字 Turn to quick entry instruction, showing picture/word | Passed
T90848812 | 首页卡片_通过首页卡片查看经销商列表手册 | 1.点击‘经销商列表’卡片 Click on 'Dealer' Expected Result: 1.跳转至经销商列表手册内容，以列表显示经销商信息 Turn to quick entry instruction, showing all dealer information by list | Passed
T90848813 | 首页卡片_通过首页卡片查看多媒体手册 | 1.点击‘多媒体’卡片 Click on 'Video' Expected Result: 1.跳转至多媒体手册内容，右侧平铺形式排列所有视频介绍 Turn to quick entry instruction, showing all video instructions | Passed
T90848814 | ‘车辆设置’中图标快速跳转 | 1.进入‘车辆设置’-'车辆控制’-‘驾驶辅助’-车道保持系统‘菜单 Select the menu: ‘车辆设置’-'车辆控制’-‘驾驶辅助’-车道保持系统‘ 2.点击手册跳转图标 Click on 'Emanual' icon Expected Result: 1.跳转到手册中‘车道保持系统’章节 Switch to the specific instruction of '车道保持系统’ | Passed
T90848815 | 搜索功能_文字搜索---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on the top of home page 2.输入关键字 Input the key word 3.点击相应的搜索结果 Click on the function wanted to search Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.根据搜索框内的输入字符实时展示搜索结果，收起键盘后搜索结果自动全屏展示 The real-time search results could display, and could be full screen display after closing keyboard 3.跳转至相应功能手册页面 The instructions of the function could display. | Passed
T90848816 | 搜索功能_（异常场景）空格输入搜索结果---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on the top of home page 2.在搜索框内输入空格 Input space Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.除非有字符输入，否则无结果展示 There is no reaction unless the keywords inputted | Passed
T90848817 | 搜索功能_（异常场景）特殊字符输入搜索结果---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on the top of home page 2.使用标点/字母/标志/数字为关键字搜索 Input the keywords with punctuation/characters/signs/numbers 3.点击相应的搜索结果 Click on the result wanted to search Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.根据搜索框内的输入字符实时展示搜索结果，收起键盘后搜索结果自动全屏展示 The real-time search results could display, and could be full screen display after closing keyboard 3.跳转至相应功能手册页面 The instructions of the function could display. | Passed
T90848818 | 搜索功能_（异常场景）常用字符输入搜索结果---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on the top of home page 2.使用常用字符，如’a/的‘作为关键字搜索 Input the key word with common character like 'a'/'的' 3.点击相应的搜索结果 Click on the result wanted to search Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.根据搜索框内的输入字符实时展示搜索结果，收起键盘后搜索结果自动全屏展示 The real-time search results could display, and could be full screen display after closing keyboard 3.跳转至相应功能手册页面 The instructions of the function could display. | Passed
T90848819 | 搜索功能_（异常场景）搜索关键字超过20个字符---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on the top of home page 2.输入关键字搜索，字符长度超过20字 Input the overlength keywords(Maximum 20) 3.点击相应的搜索结果 Click on the result wanted to search Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.超出20字部分无法输入并展示，根据搜索框内的输入字符实时展示搜索结果 The input could be cut off within (20) characters and the real-time search results could display 3.跳转至相应功能手册页面 The instructions of the function could display. | Passed
T90848820 | 搜索功能_未搜索到相关结果---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on the top of home page 2.输入手册中不存在的关键字搜索 Input the key word which is not in the manual Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.显示’抱歉未搜索到相关结果，请尝试使用其他关键词搜索‘ The screen shows 'Sorry, not found' | Passed
T90848821 | 搜索功能_清空搜索框内容---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on the top of home page 2.输入关键字 Input the key word 3.点击搜索框右侧清除图标 Click on the 'Cleanup' button next to the input field Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.根据搜索框内的输入字符实时展示搜索结果，收起键盘后搜索结果自动全屏展示 The real-time search results could display, and could be full screen display after closing keyboard 3.关键字和实时结果被清空 The keyword could be cleanup and the real-time search results disapper | Passed
T90848822 | 搜索功能_搜索历史---应用主页搜索按钮 | 1.根据用例029搜索关键字#1（正常场景） Search the keyword#1 following EM_029 2.根据用例034搜索关键字#2（关键字不存在） Search the keyword#2 following EM_034 3.回到搜索页面查看历史记录情况 Back to Search page to check if the keyword#1 stored in search history but not keyword#2 4.点击搜索历史 Tap the keyword searched before Expected Result: 1.产生用例029预期结果 See results in EM_029 2.产生用例034预期结果 See results in EM_034 3.正常搜索的关键字#1被记录，而手册中不存在的关键字#2未记入搜索历史。若超出20个字符，超出长度部分会被省略号代替。当折叠键盘时，历史记录自动变为全屏展示。 The keyword#1 stored in search history but not keyword#2. If character string is too long to be displayed completely, it will be cut off with '...', and the maximum number of history is 20. The histroy could be full screen if closing keyboard 4.根据输入的关键字展示搜索结果正确 The search results could display correctly | Passed
T90848823 | 搜索功能_清空搜索历史---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on the top of home page 2.点击搜索历史右侧的清空图标 Click on the 'Cleanup' button next to 'Search History' Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.弹出提示‘确定清空搜索历史吗？’，若点击确认，搜索记录被清空，若选择取消，返回搜索界面，记录不会被清空 Pop up a comfirm of 'Are you sure you want to empty all search history?' The search history could be cleanup and only 'Browse history' displays on the screen if choosing 'Empty'. Or the search history could remain if choosing 'Cancel'. | Failed
T90848826 | 搜索功能_清空浏览历史---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on top of home page 2.点击浏览历史右侧的清空图标 Click on the 'Cleanup' button next to 'Browse History' Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.弹出提示‘确定清空浏览历史吗？’，若点击确认，浏览记录被清空，若选择取消，返回搜索界面，记录不会被清空Pop up a comfirm of 'Are you sure you want to empty all browse history?' The browse history could be cleanup and only 'Search history' displays on the screen if choosing 'Empty'. Or the browse history could remain if choosing 'Cancel'. | Passed
T90848827 | 搜索功能_先清空浏览历史，再清空搜索历史---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on top of home page 2.点击浏览历史右侧的清空图标 Click on the 'Cleanup' button next to 'Browse History' 3.点击搜索历史右侧的清空图标 Click on the 'Cleanup' button next to 'Search History' Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.弹出提示‘确定清空浏览历史吗？’，若点击确认，浏览记录被清空，若选择取消，返回搜索界面，记录不会被清空 Pop up a comfirm of 'Are you sure you want to empty all browse history?' The browse history could be cleanup and only 'Search history' displays in the center if choosing 'Empty'. 3.弹出提示‘确定清空搜索历史吗？’，若点击确认，搜索记录被清空，若选择取消，返回搜索界面，记录不会被清空 Pop up a comfirm of 'Are you sure you want to empty all search history?' The search history could be cleanup and only input field on screen if choosing 'Empty'. | Passed
T90848828 | 搜索功能_先清空搜索历史，再清空浏览历史---应用主页搜索按钮 | 1.点击应用主页上方搜索按钮 Click on the search button on top of home page 2.点击搜索历史右侧的清空图标 Click on the 'Cleanup' button next to 'Search History' 3.点击浏览历史右侧的清空图标 Click on the 'Cleanup' button next to 'Browse History' Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.弹出提示‘确定清空搜索历史吗？’，若点击确认，搜索记录被清空，若选择取消，返回搜索界面，记录不会被清空 Pop up a comfirm of 'Are you sure you want to empty all search history?' The search history could be cleanup and only 'Browse history' displays in the center if choosing 'Empty'. 3.弹出提示‘确定清空浏览历史吗？’，若点击确认，浏览记录被清空，若选择取消，返回搜索界面，记录不会被清空 Pop up a comfirm of 'Are you sure you want to empty all browse history?' The browse history could be cleanup and only input field on screen if choosing 'Empty'. | Passed
T90848829 | 搜索功能_文字搜索---内容页搜索按钮 | 1.点击内容页上方搜索按钮 Click on the search button on the top of instruction page 2.输入关键字 Input the key word 3.点击相应的搜索结果 Click on the function wanted to search Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.根据搜索框内的输入字符实时展示搜索结果，收起键盘后搜索结果自动全屏展示 The real-time search results could display, and could be full screen display after closing keyboard 3.跳转至相应功能手册页面 The instructions of the function could display. | Passed
T90848830 | 搜索功能_（异常场景）空格输入搜索结果---内容页搜索按钮 | 1.点击内容页上方搜索按钮 Click on the search button on the top of instruction page 2.在搜索框内输入空格 Input space Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.除非有字符输入，否则无结果展示 There is no reaction unless the keywords inputted | Passed
T90848831 | 搜索功能_（异常场景）特殊字符输入搜索结果---内容页搜索按钮 | 1.点击内容页上方搜索按钮 Click on the search button on the top of instruction page 2.使用标点/字母/标志/数字为关键字搜索 Input the keywords with punctuation/characters/signs/numbers 3.点击相应的搜索结果 Click on the result wanted to search Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.根据搜索框内的输入字符实时展示搜索结果，收起键盘后搜索结果自动全屏展示 The real-time search results could display, and could be full screen display after closing keyboard 3.跳转至相应功能手册页面 The instructions of the function could display. | Passed
T90848832 | 搜索功能_（异常场景）常用字符输入搜索结果---内容页搜索按钮 | 1.点击内容页上方搜索按钮 Click on the search button on the top of instruction page 2.使用常用字符，如’a/的‘作为关键字搜索 Input the key word with common character like 'a'/'的' 3.点击相应的搜索结果 Click on the result wanted to search Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.根据搜索框内的输入字符实时展示搜索结果，收起键盘后搜索结果自动全屏展示 The real-time search results could display, and could be full screen display after closing keyboard 3.跳转至相应功能手册页面 The instructions of the function could display. | Passed
T90848833 | 搜索功能_（异常场景）搜索关键字超过20个字符---内容页搜索按钮 | 1.点击内容页上方搜索按钮 Click on the search button on the top of instruction page 2.输入关键字搜索，字符长度超过20字 Input the overlength keywords(Maximum 20) 3.点击相应的搜索结果 Click on the result wanted to search Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.超出20字部分无法输入并展示，根据搜索框内的输入字符实时展示搜索结果 The input could be cut off within (20) characters and the real-time search results could display 3.跳转至相应功能手册页面 The instructions of the function could display. | Passed
T90848834 | 搜索功能_未搜索到相关结果---内容页搜索按钮 | 1.点击内容页上方搜索按钮 Click on the search button on the top of instruction page 2.输入手册中不存在的关键字搜索 Input the key word which is not in the manual Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.显示’抱歉，未搜索到相关结果，请尝试使用其他关键词搜索‘ The screen shows 'Sorry, not found' | Passed
T90848835 | 搜索功能_清空搜索框内容---内容页搜索按钮 | 1.点击内容页上方搜索按钮 Click on the search button on the top of instruction page 2.输入关键字 Input the key word 3.点击搜索框右侧清除图标 Click on the 'Cleanup' button next to the input field Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.根据搜索框内的输入字符实时展示搜索结果，收起键盘后搜索结果自动全屏展示 The real-time search results could display, and could be full screen display after closing keyboard 3.关键字和实时结果被清空 The keyword could be cleanup and the real-time search results disapper | Passed
T90848836 | 搜索功能_搜索历史---内容页搜索按钮 | 1.根据用例043搜索关键字#1（正常场景） Search the keyword#1 following EM_043 2.根据用例048搜索关键字#2（关键字不存在） Search the keyword#2 following EM_048 3.回到搜索页面查看历史记录情况 Back to Search page to check if the keyword#1 stored in search history but not keyword#2 4.点击搜索历史 Tap the keyword searched before Expected Result: 1.产生用例043预期结果 See results in EM_043 2.产生用例048预期结果 See results in EM_048 3.正常搜索的关键字#1被记录，而手册中不存在的关键字#2未记入搜索历史。若超出20个字符，超出长度部分会被省略号代替。当折叠键盘时，历史记录自动变为全屏展示。 The keyword#1 stored in search history but not keyword#2. If character string is too long to be displayed completely, it will be cut off with '...', and the maximum number of history is 20. The histroy could be full screen if closing keyboard 4.根据输入的关键字展示搜索结果正确 The search results could display correctly | Passed
T90848837 | 搜索功能_清空搜索历史---内容页搜索按钮 | 1.点击内容页上方搜索按钮 Click on the search button on the top of instruction page 2.点击搜索历史右侧的清空图标 Click on the 'Cleanup' button next to 'Search History' Expected Result: 1.跳转至搜索界面，如存在历史搜索记录和历史浏览记录则在此页面展示，若字符过长，则超出部分使用省略号代替 Turn to search page and show 'search history' and 'Browse history' if exist. If character string is too long to be displayed completely, it will be cut off with '...' 2.弹出提示‘确定清空搜索历史吗？’，若点击确认，搜索记录被清空，若选择取消，返回搜索界面，记录不会被清空 Pop up a comfirm of 'Are you sure you want to empty all search history?' The search history could be cleanup and only 'Browse history' displays on the screen if choosing 'Empty'. Or the search history could remain if choosing 'Cancel'. | Passed
T90848870 | 搜索功能_热门搜索-氛围灯 | 1、进入电子手册 2、点击搜索按钮 3、点击热门搜索-氛围灯 4、选择一条记录，点击查看更多 Expected Result: 1、进入电子手册 2、进入搜索页面 3、搜索出氛围灯相关的结果 4、跳转到对应的结果页 | Passed
T90848871 | 搜索功能_热门搜索-后视镜调节 | 1、进入电子手册 2、点击搜索按钮 3、点击热门搜索-后视镜调节 4、选择一条记录，点击查看更多 Expected Result: 1、进入电子手册 2、进入搜索页面 3、搜索出后视镜调节相关的结果 4、跳转到对应的结果页 | Failed
T90848872 | 搜索功能_热门搜索-自动驻车 | 1、进入电子手册 2、点击搜索按钮 3、点击热门搜索-自动驻车 4、选择一条记录，点击查看更多 Expected Result: 1、进入电子手册 2、进入搜索页面 3、搜索出自动驻车相关的结果 4、跳转到对应的结果页 | Passed
T90848873 | 搜索功能_热门搜索-座椅 | 1、进入电子手册 2、点击搜索按钮 3、点击热门搜索-座椅 4、选择一条记录，点击查看更多 Expected Result: 1、进入电子手册 2、点击搜索按钮 3、点击热门搜索-座椅 4、选择一条记录，点击查看更多 | Passed
T90848874 | 搜索功能_热门搜索-胎压 | 1、进入电子手册 2、点击搜索按钮 3、点击热门搜索-胎压 4、选择一条记录，点击查看更多 Expected Result: 1、进入电子手册 2、进入搜索页面 3、搜索出胎压相关的结果 4、跳转到对应的结果页 | Passed
T90848875 | 验证首次进入电子手册，搜索页面是否弹出toast提示 | 1、进入电子手册，点击搜索按钮 2、退出搜索页面，再次进入搜索页面 3、退出搜索页面，再次进入搜索页面 4、退出搜索页面，再次进入搜索页面 Expected Result: 1、进入搜索页面页面，搜索页面弹出toast提示‘你可以试试语音询问“如何使用自适应巡航”’ 2、进入搜索页面页面，搜索页面弹出toast提示‘你可以试试语音询问“如何使用自适应巡航”’ 3、进入搜索页面页面，搜索页面弹出toast提示‘你可以试试语音询问“如何使用自适应巡航”’ 4、进入搜索页面页面，没有弹出toast | Passed
T90848846 | 语音控制_打开/关闭/跳转手册内容 | 1.语音指令： “打开手册”/“关闭手册”/“如何调节座椅” Voice Command: "open Emanual"/"quit Emanual"/"how to adjust the seat setting" Expected Result: 1.根据指令打开/关闭/跳转手册内容 Open/quit/turn to Emanual according to the voice command | Passed
T90848838 | 展示格式_图片放大缩小展示 | 1. 点击手册中的图片 Tap on picture in instruction 2. 再次点击图片 Tap pn picture again Expected Result: 1.图片全屏展示 The picture could turn full screen 2. 图片退出全屏 The picture could back to normal size | Passed
T90848839 | 展示格式_表格展示 | 1. 检查各手册中表格内容 Check the table display Expected Result: 1.表格展示正常，内容展示正确 The tables display correctly | Passed
T90848840 | 展示格式_目录跳转功能 | 1. 进入手册 Start application 2. 点击左侧目录标签 Click on the content on the left side to switch the page Expected Result: 1.手册内容展示正确 The content could display correctly 2. 根据选择的目录跳转章节正确 The instructions could display correctly according to the selected content | Passed
T90848841 | 展示格式_链接跳转功能 | 1. 进入手册 Start application 2. 点击内容页中的链接 Click on the reference link in the instruction page Expected Result: 1.手册内容展示正确 The content could display correctly 2.显示链接且根据链接跳转章节正确 The reference links could display on instruction page, and it could switch to the link page when clicking on the reference link | Passed
T90848842 | 展示格式_上/下一页跳转功能 | 1. 进入手册 Start application 2. 滑动至章节底部，点击‘上/下一页’ Scroll down to the bottom of the page, and click on the 'previous/next' button 3.连续点击‘上/下一页’ Click on the "Previous"/"Next" button continuously Expected Result: 1.手册内容展示正确 The content could display correctly 2.章节底部左右侧分别显示上一页，下一页按钮，点击后章节跳转正确 The 'previous/next' button could display at the bottom of page, and it could switch to the previous/next page when clicking on the button. Also the highlighted header cursor could change correctly. 3. 章节底部左右侧分别显示上一页，下一页按钮，点击后章节跳转正确 It could switch to the previous/next page when clicking on the button. Also the highlighted header cursor could change correctly. | Passed
T90848843 | 展示格式_滑动条功能 | 1. 进入手册 Start application 2. 章节右侧按住滑动条上下拖拽 Dragging the slide bar on the right side of the instruction page Expected Result: 1.手册内容展示正确 The content could display correctly 2.文章内容上下滑动展示 The page can be scrolled up/down by dragging the slide bar | Passed
T90848844 | 交互表现_电子手册和其他应用之间切换 | 1.Voice command:'你好，福特' - ‘打开随心听’ 2.手动返回电子手册应用 Back to E-Manual application Expected Result: 1.切换至随心听应用 It could turn to ‘随心听’ application 2.切换回电子手册应用，展示应用主页 It could turn back to home page of E-Manual | Passed
T90848845 | 交互表现_电子手册和系统之间切换 | 1.点击系统菜单栏-主页按钮 Click on system - 'Home' button 2.手动返回电子手册应用 Back to E-Manual application Expected Result: 1.返回系统首页 It could turn to home page of system 2.切换回电子手册应用，若退出前停留在首页，则返回退出前页面，若退出前停留在详情页，则返回电子手册主页 | Passed