## Cover
SOFTWARE RELEASE NOTES
Product/Module Name | Phase5
Rational Team Concert Project Area
Rational Team Concert Team Area
Project ID | 29662
Release Organization

## YFVE
Main Title | Subtitle |  | Content | Remarks
General information | Release Date |  | 2022-08-25
| Description |  | Engineering Version
| Release Engineer |  | gjin
| Part Number |  | 29662
| Release Target |  | SW Validation
| SW Release Label Name | SOC | 20220824_LC_DCV1_PRO
|  | MCU | 20220824_LC_DCV1_PRO
|  | SW PN | R2CT-14H379-AA005
| Version Information | Kernrel | 4.14.98
|  | TP Firmware | NA
|  | BT Firmware | BCM4339_003.001.009.0164.0739
|  | EOL Spec | NA
|  | SRD | V1.1
|  | SW PN | R2CT-14H361-AA005
|  | Main board HW Version | A1-main
|  | Sub board HW Version | A1-sub
| Tool used to calculate the checksum |  | winMd5Sum
| Diagnosis | Fixed Issues | 关闭切换编程回复NRC87(MCU)
New Feature
| Network | Fixed Issues
|  | New Feature | 关闭DET60(MCU)
| SystemUI | Fixed Issues | 修改bug(SOC)
New Feature
| System_Setting | Fixed Issues | 增加常规和蓝牙设置搜索结果背景图和文字高亮(SOC) 修复热点设置页面无法进入问题，添加点击水波纹效果(SOC) 增加vcs调节背光(SOC) 修改蓝牙已配对列表排序问题(SOC) 修改多主体aar包引用(SOC) 修改媒体投射和WiFi item和info 点击dialog(SOC)
|  | New Feature | NA
| System_UI | Fixed Issues | 修改蓝牙点亮图标以及recents进入进出动画(SOC) (FPHASEVCDC-8899，FPHASEVCDC-8927)(SOC)
|  | New Feature | (FPHASEVCDC-8899，FPHASEVCDC-8927)(SOC)
| Engineer_Mode | Fixed Issues | 新增BT1/WIFI/Ethernet get 接口(SOC) 修改F1D0 F1D1 datalength(SOC) 删除无参的OTA resume函数(SOC) 修改DID 8060 数据内容(SOC) 修改DID 804B datalength(SOC) 删除DID 804B usb故障检测功能(SOC)
|  | New Feature | NA
| OTA | Fixed Issues
|  | New Feature | 生成vbf前删除之前打包的vbf文件夹(SOC) 支持在编译时生成多vbf包(SOC)
| ADAS | Fixed Issues
|  | New Feature | 胡博文：修复ADAS7中3D8 missing LKS_RTT和车道线不会消失(MCU) 胡博文：修复ADAS6中Lan_BiassingInfo_Dsp未赋初始值(MCU) 修复ADAS5中BLIS 信号判断延时处理错误(MCU) ADAS10中逻辑处理错误修正(MCU) ADAS5中逻辑处理错误修正(MCU) 胡博文：修复ADAS6中6.2.3.2.State Matrix for Hwy_Assist_Status_Display需求增加(MCU)
| FrameWork | Fixed Issues
|  | New Feature | 更新仪表软件(SOC)
| Warning | Fixed Issues
|  | New Feature | 修复 安全带 bug(MCU)
| com | Fixed Issues
|  | New Feature | 根据系统需求更改超时接口(MCU)
| seatbelt | Fixed Issues
|  | New Feature | 修复bug 8533，8534(MCU)
| setup | Fixed Issues
|  | New Feature | 修复单双表头传值(MCU) 修改 mvn 燃油 单位 默认值(MCU)
Development System Utilization | PC OS |  | Microsoft Windows XP
| Configuration Management System |  | Git
| Compiler |  | GHS_V6.1.6_201517
| Assembler |  | GHS
Known Issue

## DCV1 fix issue
问题关键字 | 问题ID | 问题类型 | 概要 | 修复的版本 | 报告人 | 状态 | 创建日期 | 经办人 | 模块 | 修复的版本 | 标签 | 标签 | 标签 | 标签 | 标签 | 标签
APIMCIM-7846 | 4020208 | 故障 | Phase 5: 【偶发】台架上电后即出现三角线黑屏 | LC_DCV1_ENG | wchen154 | 待办 | 13/六月/22 10:27 下午 | rsun8 | System Stability |  | CDC_IVITst | MigratingToCloud | U611MCA
APIMCIM-5881 | 3792545 | 故障 | CLONE - Phase 5：【必现】手动切换手机/车辆热点模式开关几次后，开关按钮置灰不可恢复 | FB_DCV1_ENG | xwang314 | Approval | 26/四月/22 4:28 上午 | xwang314 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-5810 | 3788779 | 故障 | Phase 5：【必现】系统复位功能未实现 | LC_DCV1_ENG | wchen154 | Approval | 25/四月/22 4:09 上午 | wchen154 | General Setting |  | CDC_IVITst | MigratingToCloud | U611MCA | U625MCA
APIMCIM-5837 | 3792443 | 故障 | Phase 5：【U611MCA】【必现】旋转VOL旋钮，音量变化时，未弹出音量弹窗 | LC_DCV1_ENG | jsun62 | Approval | 25/四月/22 10:11 下午 | jsun62 | Audio |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-6750 | 3855421 | 故障 | Phase 5：【必现】音频、视频从后台恢复后不能继续播放 | FB_DCV1_ENG | pxu41 | Approval | 10/五月/22 4:47 上午 | pxu41 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-6961 | 3875471 | 故障 | Phase 5：【必现】风量弹框/主副驾温度弹框/座椅调节弹框打开，点击或滑动调节，车机无触摸beep声 | FB_DCV1_ENG | tshan3 | Approval | 16/五月/22 2:16 上午 | tshan3 | Climate |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-7031 | 3886828 | 故障 | Phase 5：【偶发】发生两次900E RAMDUMP后自动重启 | LC_DCV1_ENG | jsun62 | Approval | 18/五月/22 1:48 上午 | jsun62 | System Stability |  | CDC_IVITst | CDC_Phase5 | DCV0_MUST_FIX | MigratingToCloud | U611MCA
APIMCIM-6924 | 3875088 | 故障 | Phase 5：【必现】车速大于5时，图片/视频投屏时无安全提示 | FB_DCV1_ENG | xwang314 | Approval | 14/五月/22 2:39 上午 | pxu41 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-6978 | 3876500 | 故障 | Phase 5：【必现】台架CAN发送Ignition OFF、ACC OFF，车机屏幕未熄屏 | FB_DCV1_ENG | xwang314 | Approval | 16/五月/22 4:06 上午 | xwang314 | Power Management |  | CDC_IVITst | CDC_Phase5 | DCV0_MUST_FIX | MigratingToCloud | U625MCA | U625MCA_DCV1_HF
APIMCIM-7139 | 3896766 | 故障 | Phase 5：【偶现】DLNA搜索到车机设备后，图片/音频/视频无法投屏 | LC_DCV1_ENG | xwang314 | Approval | 19/五月/22 10:58 下午 | xwang314 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-7157 | 3898735 | 故障 | Phase 5：【必现】解除Load Shed模式，Ignition run后IVI无法唤醒 | LC_DCV1_ENG | xwang314 | Approval | 20/五月/22 2:42 上午 | xwang314 | Power Management |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-6946 | 3875779 | 故障 | Phase 5：【必现】VR：更换主题。车机播放了音乐 | FB_DCV1_ENG | tshan3 | Approval | 15/五月/22 10:51 下午 | tshan3 | VR |  | CDC_IVITst | CDC_Phase5 | DCV0_MUST_FIX | Inhouse_Platform | MigratingToCloud | U625MCA
APIMCIM-8425 | 4065869 | 故障 | Phase 5：【必现】USB视频播放器页面，有点难滑动或者点击进度条 | FB_DCV1_ENG | jsun62 | Approval | 27/六月/22 8:03 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-8458 | 4075480 | 故障 | Phase 5：【必现】模拟后排空调的风量，控制栏主空调风量同步变化 | FB_DCV1_ENG | tshan3 | Approval | 29/六月/22 1:50 上午 | tshan3 | Climate |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-8414 | 4065687 | 故障 | Phase 5：【必现】MMInactive状态下,进入EP模式，音源没有恢复播放 | FB_DCV1_ENG | ywu188 | Approval | 27/六月/22 6:48 上午 | ywu188 | Power Management |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-8420 | 4065864 | 故障 | Phase 5：【必现】USB视频播放器页面，长按"下一个"按钮快进时，仍能进入沉浸态播放 | FB_DCV1_ENG | jsun62 | Approval | 27/六月/22 7:56 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-8380 | 4065523 | 故障 | Phase 5：【必现】视频投屏进入沉浸态时，屏幕右上顶部出现闪屏 | FB_DCV1_ENG | xwang314 | Approval | 27/六月/22 2:44 上午 | xwang314 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9266 | 4157011 | 故障 | Phase 5：【必现】蓝牙设备切换，蓝牙音乐不会自动播放 | LC_DCV1_ENG | ygu49 | Approval | 25/七月/22 3:36 上午 | ygu49 | BT Music |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-8433 | 4069597 | 故障 | Phase 5：【必现】车速大于5km/h，点击一个USB视频无反应，也无安全提醒弹窗 | FB_DCV1_ENG | jsun62 | Approval | 27/六月/22 10:59 下午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-8427 | 4065872 | 故障 | Phase 5：【必现】USB视频播放器页面拔出U盘，卡在播放页面，点击返回，任意点击一个视频，随心看闪退 | FB_DCV1_ENG | jsun62 | Approval | 27/六月/22 8:10 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-8426 | 4065871 | 故障 | Phase 5：【必现】USB视频播放器页面，长按"上一个"按钮快退时，快退的时间错误 | FB_DCV1_ENG | jsun62 | Approval | 27/六月/22 8:07 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-8389 | 4064976 | 故障 | Phase 5：【必现】可用网络开关打开，有新wifi在范围内时，无通知图标 | FB_DCV1_ENG | tshan3 | Approval | 27/六月/22 3:11 上午 | tshan3 | WiFi Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-8423 | 4065867 | 故障 | Phase 5：【必现】USB视频播放器页面，长按"下一个"按钮快进时，总是每次3秒的快进 | FB_DCV1_ENG | jsun62 | Approval | 27/六月/22 8:00 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA | U625MCA_DCV1_HF
APIMCIM-9486 | 4167514 | 故障 | Phase 5: 【必现】连接附近可用网络，输入错误密码后取消，此网络被保存在”已保存网络“列表。 | FB_DCV1_ENG | tshan3 | Approval | 28/七月/22 3:44 上午 | tshan3 | WiFi Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9300 | 4159764 | 故障 | Phase 5：【必现】随心听页面点击音效设置，会有页面的跳变 | LC_DCV1_ENG | ygu49 | Approval | 25/七月/22 10:00 下午 | ygu49 | Music |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-9602 | 4175320 | 故障 | Phase 5：【必现】空调界面控制栏，模拟风量无变化 | FB_DCV1_ENG | tshan3 | Approval | 01/八月/22 4:30 上午 | tshan3 | Climate |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9513 | 4167645 | 故障 | Phase 5：【必现】导航播报时，下拉状态栏，不能调节音量大小 | FB_DCV1_ENG | jsun62 | Approval | 28/七月/22 5:45 上午 | jsun62 | Audio |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9592 | 4175128 | 故障 | Phase 5：【必现】USB视频播放时，点击Dock栏随心听按钮，Dock栏的边缘显示视频切割线 | FB_DCV1_ENG | jsun62 | Approval | 01/八月/22 3:06 上午 | jsun62 | Music |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9529 | 4169875 | 故障 | Phase 5：【812】播放随心听，切换蓝牙音乐播放，再切回其他随心听无法播放 | LC_DCV1_ENG | ygu49 | Approval | 28/七月/22 9:45 下午 | ygu49 | Music |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA | U611MCA_DCV1_HF
APIMCIM-9385 | 4163145 | 故障 | Phase 5：【必现】音频投射时，手机QQ音乐选择车机设备，提示已切换投放，但是设备未切换至车机 | LC_DCV1_ENG | kcao12 | Approval | 27/七月/22 1:41 上午 | kcao12 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA | U611MCA_DCV1_HF
APIMCIM-9564 | 4174908 | 故障 | Phase 5：USB音乐中输入法无法完成搜索，且无法隐藏 | FB_DCV1_ENG | ygu49 | Approval | 31/七月/22 11:05 下午 | ygu49 | Input |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA | U625MCA_DCV1_HF
APIMCIM-9595 | 4175305 | 故障 | Phase 5：【必现】模拟上报后除霜/max除霜信号=active/inactive时，点击此button,状态不一致 | FB_DCV1_ENG | tshan3 | Approval | 01/八月/22 3:15 上午 | tshan3 | Climate |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9320 | 4159486 | 故障 | Phase 5：【必现】同时连接主副设备的蓝牙，副卡设备来电时，电话页面显示主卡的状态 | LC_DCV1_ENG | kcao12 | Approval | 26/七月/22 1:28 上午 | kcao12 | BT Phone |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-9603 | 4175327 | 故障 | Phase 5：【必现】空调主驾温度模拟，控制栏一直HI | FB_DCV1_ENG | tshan3 | Approval | 01/八月/22 5:14 上午 | tshan3 | Climate |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9482 | 4167093 | 故障 | Phase 5：【必现】USB音乐搜索页，输入关键字点击完成，无法收起键盘 | FB_DCV1_ENG | jsun62 | Approval | 28/七月/22 3:36 上午 | jsun62 | Music |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA | U625MCA_DCV1_HF
APIMCIM-9594 | 4175132 | 故障 | Phase 5：【必现】车速120km/h，点击一个USB视频播放时，没有安全提醒的toast显示 | FB_DCV1_ENG | jsun62 | Approval | 01/八月/22 3:10 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9382 | 4163144 | 故障 | Phase 5：【必现】音频投射成功后，手机调节音乐音量，车机未同步响应 | LC_DCV1_ENG | kcao12 | Approval | 27/七月/22 1:36 上午 | kcao12 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-9615 | 4184489 | 故障 | Phase 5：【必现】ICP功能未实现 | FB_DCV1_ENG | tshan3 | Approval | 01/八月/22 9:57 下午 | tshan3 | System Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA | U625MCA_DCV1_HF
APIMCIM-5719 | 3784415 | 故障 | Phase 5：【必现】可用网络输入错误密码，弹框提示不正确 | LC_DCV1_ENG | tshan3 | Approval | 22/四月/22 3:15 上午 | tshan3 | WiFi Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-5783 | 3788743 | 故障 | Phase 5：【必现】手动切换手机/车辆热点模式开关几次后，开关按钮置灰不可恢复 | LC_DCV1_ENG | xwang314 | Approval | 25/四月/22 1:22 上午 | xwang314 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-7038 | 3887463 | 故障 | Phase 5：【必现】蓝牙连接只连接媒体时，蓝牙图标不显示 | LC_DCV1_ENG | xwang314 | Approval | 18/五月/22 2:57 上午 | xwang314 | BT Setting |  | CDC_Inhouse | CDC_IVITst | MigratingToCloud | U611MCA
APIMCIM-6777 | 3855720 | 故障 | Phase 5：【必现】蓝牙音乐播放过程中，蓝牙卡片页面所有功能按钮无法点击，且默认封面显示错误，不显示歌唱者 | LC_DCV1_ENG | pxu41 | Approval | 10/五月/22 6:39 上午 | pxu41 | BT Music |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-7118 | 3892382 | 故障 | Phase 5：【必现】WIFI详情页显示不正确 | LC_DCV1_ENG | tshan3 | Approval | 19/五月/22 3:57 上午 | tshan3 | WiFi Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA | U611MCA_DCV1_HF
APIMCIM-7103 | 3892346 | 故障 | Phase 5: 【必现】”温度单位“设置弹窗中未显示当前选择项 | LC_DCV1_ENG | wchen154 | Approval | 19/五月/22 2:07 上午 | wchen154 | General Setting |  | CDC_IVITst | MigratingToCloud | U611MCA
APIMCIM-7088 | 3891710 | 故障 | Phase 5：【必现】USB视频搜索页面，索框初始状态无占位符 | FB_DCV1_ENG | jsun62 | Approval | 19/五月/22 1:33 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-7092 | 3891716 | 故障 | Phase 5：【必现】USB视频播放器页面，快进或快退只显示当前进度不显示总时长 | FB_DCV1_ENG | jsun62 | Approval | 19/五月/22 1:45 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-6947 | 3875780 | 故障 | Phase 5：【必现】蓝牙连接只连接媒体时，蓝牙图标不显示 | FB_DCV1_ENG | xwang314 | Approval | 15/五月/22 10:51 下午 | xwang314 | BT Setting |  | CDC_Inhouse | CDC_IVITst | MigratingToCloud | U625MCA
APIMCIM-6806 | 3860099 | 故障 | Phase 5：【必现】standby下点击屏幕再IGN run后音量调节没有作用，切源恢复 | LC_DCV1_ENG | pxu41 | Approval | 11/五月/22 1:49 上午 | pxu41 | Audio |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA | U611MCA_DCV1_HF
APIMCIM-6803 | 3860081 | 故障 | Phase 5：【必现】进入Extended phone mode，弹出提示后，2s后黑屏，20s后有自动亮屏 | LC_DCV1_ENG | pxu41 | Approval | 11/五月/22 1:16 上午 | pxu41 | Power Management |  | CDC_IVITst | CDC_Phase5 | DCV0_MUST_FIX | MigratingToCloud | U611MCA | U611MCA_DCV1_HF
APIMCIM-7097 | 3891717 | 故障 | Phase 5：【必现】USB视频播放器页面，音量为0时，toast不显示静音icon | FB_DCV1_ENG | jsun62 | Approval | 19/五月/22 1:48 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-7089 | 3891712 | 故障 | Phase 5：【必现】USB视频搜索页面，未搜索到结果时，无任何提示 | FB_DCV1_ENG | jsun62 | Approval | 19/五月/22 1:37 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-7893 | 4021237 | 故障 | Phase 5：【必现】音频投射，左右水平滑动屏幕应无调节进度功能 | LC_DCV1_ENG | xwang314 | Approval | 14/六月/22 7:11 上午 | xwang314 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-7866 | 4021035 | 故障 | Phase 5：【必现】蓝牙音乐播放状态切换设备时，专辑名称显示null | LC_DCV1_ENG | xwang314 | Approval | 14/六月/22 3:25 上午 | xwang314 | BT Music |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-8211 | 4043910 | 故障 | Phase 5：【必现】Ignition_Status=1 off后车机不能进入黑屏进入standby | LC_DCV1_ENG | xwang285 | Approval | 21/六月/22 4:44 上午 | xwang314 | Power Management |  | CDC_IVITst | CDC_Phase5 | DCV0_MUST_FIX | MigratingToCloud | U611MCA
APIMCIM-8419 | 4065863 | 故障 | Phase 5：【必现】USB视频播放器页面，右侧向下滑动音量为0时，音量图标不是Mute态 | FB_DCV1_ENG | jsun62 | Approval | 27/六月/22 7:49 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9263 | 4157001 | 故障 | Phase5：【必现】车机端，点击"搜索设备"，“搜索设备”右图标未展现搜索中状态 | LC_DCV1_ENG | kcao12 | Approval | 25/七月/22 2:41 上午 | kcao12 | BT Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-9544 | 4170495 | 故障 | Phase 5: 【必现】开启/关闭车辆热点模式开关时，无Tost提示 | FB_DCV1_ENG | xwang314 | Approval | 29/七月/22 4:53 上午 | xwang314 | DLNA |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9537 | 4170370 | 故障 | Phase 5：点击屏幕任意空白区域，或任意APP图标无法退出精简屏幕 | LC_DCV1_ENG | ygu49 | Approval | 29/七月/22 1:56 上午 | ygu49 | System Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-9610 | 4184566 | 故障 | Phase 5: 【必现】点击车机端主驾座椅，点击座椅加热的1-3档和通风的1-3档，无信号返回。 | FB_DCV1_ENG | xli318 | Approval | 01/八月/22 9:19 下午 | xli318 | Climate |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-9584 | 4175116 | 故障 | Phase 5：【必现】已连接设备无播放信息时，点击音效按钮未跳转 | FB_DCV1_ENG | xwang314 | Approval | 01/八月/22 2:02 上午 | xwang314 | BT Music |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9531 | 4169746 | 故障 | Phase 5: 【必现】USB音乐中输入法无法完成搜索，且无法隐藏 | FB_DCV1_ENG | tshan3 | Approval | 28/七月/22 10:19 下午 | tshan3 | Input |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA | U625MCA_DCV1_HF
APIMCIM-9558 | 4174904 | 故障 | Phase 5：点击屏幕任意空白区域，或任意APP图标无法退出精简屏幕 | FB_DCV1_ENG | ygu49 | Approval | 31/七月/22 10:35 下午 | ygu49 | System Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9514 | 4167646 | 故障 | Phase 5：【必现】状态栏的音量条上，圆点按钮与蓝色进度条不match | FB_DCV1_ENG | jsun62 | Approval | 28/七月/22 5:54 上午 | jsun62 | Launcher |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9530 | 4169745 | 故障 | Phase 5: 【必现】设置界面，输入法的输入框上方截断，显示不全 | FB_DCV1_ENG | tshan3 | Approval | 28/七月/22 10:18 下午 | tshan3 | Input |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9580 | 4175114 | 故障 | Phase 5：【必现】蓝牙音乐播放状态切换设备时，专辑名称显示null | LC_DCV1_ENG | xwang314 | Approval | 01/八月/22 1:54 上午 | xwang314 | BT Music |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-9488 | 4167603 | 故障 | Phase 5：【必现】USB视频播放时，拔出U盘，toast显示"外部设备已拔出，播"显示不全 | FB_DCV1_ENG | jsun62 | Approval | 28/七月/22 3:45 上午 | jsun62 | Video |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-9572 | 4174921 | 故障 | Phase 5: 【必现】设置中点击搜索，输入框中字体有遮挡 | FB_DCV1_ENG | ygu49 | Approval | 01/八月/22 1:19 上午 | ygu49 | Input |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-7851 | 4020192 | 故障 | Phase 5：【偶现】点击开启/关闭WiFi按钮，听到提示音，按钮没反应 | LC_DCV1_ENG | ywu188 | Approval | 13/六月/22 11:59 下午 | ywu188 | WiFi Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-7850 | 4020191 | 故障 | Phase 5：【必现】WiFi连接上网络后，弹窗会遮挡部分UI | LC_DCV1_ENG | ywu188 | Approval | 13/六月/22 11:40 下午 | ywu188 | WiFi Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U611MCA
APIMCIM-8391 | 4064979 | 故障 | Phase 5：【必现】WiFi连接上网络后，弹窗会遮挡部分UI | FB_DCV1_ENG | tshan3 | Approval | 27/六月/22 3:20 上午 | tshan3 | WiFi Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA | U625MCA_DCV1_HF
APIMCIM-9465 | 4167257 | 故障 | Phase 5: 【必现】问题上报界面最下方，字体显示不完整 | FB_DCV1_ENG | tshan3 | Approval | 28/七月/22 1:31 上午 | tshan3 | System Setting |  | CDC_IVITst | CDC_Phase5 | MigratingToCloud | U625MCA
APIMCIM-2673 | 3455564 | 故事 | 【U6XX MCA】【SYNC+_0021】视频、音乐、图片DLNA投屏到车机显示器区分主副驾/Video Playback and Video and Photo project to Display(Driver and Passenger) via DLNA | FB_DCV1_ENG | dchen96 | Test | 12/二月/22 3:26 上午 | pxu41 | DLNA | LC_DCV1_ENG | Customer-Facing | IVI | MigratingToCloud | U611MCA | U625MCA
APIMCIM-2836 | 3456627 | 故事 | 【U6XX MCA】【SYNC+_Z0038】Embedded Modem Reset/Master reset | FB_DCV1_ENG | dchen96 | Test | 12/二月/22 4:25 上午 | pxu41 |  | LC_DCV1_ENG | Basic-Function | IVI | MigratingToCloud | U611MCA | U625MCA
APIMCIM-2857 | 3456648 | 故事 | 【U6XX MCA】【SYNC+_Z0126】恢复出厂设置 reset（Master Reset） | FB_DCV1_ENG | dchen96 | Test | 12/二月/22 4:25 上午 | pxu41 |  | LC_DCV1_ENG | Basic-Function | IVI | MigratingToCloud | U611MCA | U625MCA

## Baidu (hidden)
| Module |  | Feature/Issue Describtion | Remark
Module Change History (you can change,add or delete this part) | Audio | Fixed Issues | 解决车机usb音乐无声问题（Bug ID xxxx） 解决xxxx（Bug ID xxxx） | 举例
|  | New Feature | 增加xxxx（TASK ID xxxx） 增加xxxx（无） | 举例
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature

## Ford (hidden)
| Module |  | Feature/Issue Describtion | Remark
Module Change History (you can change,add or delete this part) | Audio | Fixed Issues | 解决车机usb音乐无声问题（Bug ID xxxx） 解决xxxx（Bug ID xxxx） | 举例
|  | New Feature | 增加xxxx（TASK ID xxxx） 增加xxxx（无） | 举例
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature
Fixed Issues
New Feature