## 首页
|  |  |  | 文件No. | 页数
|  |  |  | ThunderSoft-QMS-18-JL17 | 3
<Ford Phase5>测试用例执行
历史记录
版本号 | 日期 | 作者/修订者 | 制订/修改内容 |  |  | 评审人/评审日期 | 评审要求
V1.0 | 2021-07-04 | 邓荣祥 | 创建
V1.1 | 2022-03-06 | 陈传勤 | 优化相关模块测试用例
V1.2 | 2022-11-26 | 李可可 | 优化首页内容展示

## Summary-DCV3-1
U625_DCV3-1测试报告
软件版本 | SOC：20230224_FB_DCV3-1_ENG00 MCU：20230223_FB_DCV3-1_ENG00 ECG: ECG2-milestone-2023-01-Bundle-Release_EH_maps-0.0.42.256 TCU: TCU2-milestone-2023-01-modem6-Bundle-Release-China-2.2.2.133 |  |  |  | 测试范围 | 1、所有Fetaure 2、只包含创达开发范围
测试硬件 | B&C |  |  |  | 测试人员 | 姜云腾&关满意&李可可&袁露&杨春明&肖文迪&徐成龙&黄钊敏&赵雅非
测试方法 | 手动 |  |  |  | 测试环境 | 台架
项目经理 | 王龙州 |  |  |  | 项目总监 | 陈凯
总结 | 本轮DCV3-1 Focus测试，涉及模块31个，从测试结果上来看整体Pass率为84.92%，执行率为86.25% 1）由于哈曼侧功放软件未开发完成，导致2个模块阻塞，影响case316条，占失败总数比77.64%，对整体通过率影响较大，涉及模块如下： Car Audio外置（10ch）、CarAudio音源矩阵外置（10ch） 2）Pass率<=70%的模块0个 3）70%<=Pass率<=90%的模块5个 a）个性化设置档案：共4个问题，需Ford分析，Pass率87.50%。 b）MMOTA：共4个问题，其中2个Gating问题，因OTA/USB/VI升MCU和SYNC+，均无法激活成功问题需YF分析，Block相关测试用例27条，Pass率88.31%。 c）AAR：共6个问题，影响相关测试用例8条，Pass率88.06%。 d）3D车模：共3个问题，其中1个Gating问题，阻碍相关测试用例7条，Pass率88.00%。 e）V2I：共2个问题，Pass率90.00% 4）Pass率>90%的模块9个 FNV诊断：存在关键问题APIMCIM-18648，影响case2条——ford 其他详见列表 5）Pass率=100%的模块15个
问题列表
FeatureID | 模块 | DCV3-1通过率 | 影响Case数 | BugID | Bug标题 |  | 严重程度 | 状态 | 归属 | 分析
SYNC+_0126 | Car Audio外置（10ch） | 0% | 180 | NT | 10ch外置功放未升级，无法使用并测试 |  | / | / | /
SYNC+_0126 | CarAudio音源矩阵外置（10ch） | 0% | 136 | NT | 10ch外置功放未升级，无法使用并测试 |  | / | / | /
SYNC+_0165 | 个性化设置档案 | 87.5% | 1 | APIMCIM-16383 | Phase5_【U625】【黑盒】【必现】【EnhanceMemory】切换主题后创建档案页面显示异常 |  | Medium | TO DO | Ford
|  |  | 1 | APIMCIM-16384 | Phase5_【U625】【黑盒】【必现】【EnhanceMemory】创建档案过程中挂非p档，提示弹窗显示异常 |  | Medium | TO DO | Ford
|  |  | 1 | APIMCIM-18783 | Phase5_【U625】【黑盒】【偶现】【EnhanceMemory】创建档案时偶现闪退，无法进入档案页面 |  | High | TO DO | Ford
|  |  | 1 | APIMCIM-16385 | Phase5_【U625】【黑盒】【必现】【EnhanceMemory】切换账号档案弹窗重复弹出 |  | Medium | TO DO | Ford
SYNC+_0223 | MMOTA | 88.31% | 19 | APIMCIM-18588 | Phase5_【U625MCA】【MMOTA】【必现】OTA/USB升MCU/SYNC+，ECGlog打印S1007,进行激活，激活失败 |  | Gating | TO DO | YF
|  |  | 1 | APIMCIM-18544 | Phase5_【U625】【必现】【MMOTA】VI升级SYNC+激活失败后通知中心无弹窗提示“更新失败” |  | High | TO DO | Baidu
|  |  | 8 | APIMCIM-18538 | Phase5_【U625】【必现】【MMOTA】VI升级SYNC+和MCU必现ECG_log报E2130,无法激活成功 |  | Gating | TO DO | Ford
|  |  | 1 | FCIVIOS-14218 | Phase5_【U625】【必现】【MMOTA】VI升级--更新详情-接受和计划、重新计划按钮都是置灰的显示 |  | High | TO DO | TS
SYNC+_0266 | 3D车模 | 88% | 1 | FCIVIOS-10710 | Phase5_【U625MCA】【黑盒】【必现】【3D车模】设置车模颜色，重启机器，车模颜色与重启之前不一致 |  | Medium | TEST | TS | DCV4合入
|  |  | 7 | APIMCIM-15440 | phase5 U625MCA[100%]The color configuration is changedleft ，but the side of the color bar and the 3D vehicle model body has not changed |  | Gatting | TEST | TS | DCV4合入
|  |  | 1 | FCIVIOS-14224 | Phase5_【U625MCA】【黑盒】【必现】【3D车模】分屏模式下点击后备箱按钮，弹窗被截断 |  | High | TO DO | TS | 待分析
SYNC+_0132 | AAR | 88.06% | 1 | FCIVIOS-14197 | Phase5_【U625】【黑盒】【必现】【AAR】分屏状态下，如果副驾已经打开了智能新风界面，主驾无法进入智能新风界面，与其他界面实现不一致，且提示框会一直在主驾上提示 |  | High | TO DO | TS
|  |  | 1 | FCIVIOS-14206 | Phase5_【U625】【黑盒】【必现】【AAR】AAR过滤完成的弹窗未适配主题，请确认是否需要适配 |  | Medium | TO DO | TS
|  |  | 1 | FCIVIOS-14250 | Phase5_【U625】【黑盒】【必现】【AAR】智能新风首页界面显示应该为XX区+PM2.5 |  | Medium | TO DO | TS
|  |  | 1 | FCIVIOS-14242 | Phase5_【U625】【黑盒】【必现】【AAR】温度切为华氏摄氏度时，AAR站点显示的温度与摄氏度的显示一致，未做转换 |  | High | TO DO | TS
|  |  | 2 | APIMCIM-18792 | Phase5_【U625】【黑盒】【必现】【AAR】“取消/切换/外部的空气质量较好，你想换到外循环模式吗？”用户语音回复”切换“无法正常收音 |  | High | TEST | TS | DCV4合入
|  |  | 2 | APIMCIM-16848 | Phase5_【U625】【黑盒】【偶现】【AAR】打开空调系统的”弹窗没有语音播报声 |  | Gating | TEST | TS | DCV4合入
SYNC+_0265 | V2I | 90% | 1 | FCIVIOS-11806 | Phase5_【U625MCA】【黑盒】【必现】【V2I】配置v2i，环境正常，进入车路协同界面不显示使用计划文本 |  | Medium | TO DO | Ford | 待分析
|  |  | 1 | FCIVIOS-14349 | Phase5_【U625MCA】【黑盒】【必现】【V2I】进入v2i点击info，点击续订时间，修改时间点击确定,再次修改时间，续订时间不会递增 |  | High | TO DO | TS | 待分析
SYNC+_Z0037 | FNV诊断 | 92% | 2 | APIMCIM-18648 | Phase5_【U625MCA】【偶现】【FNV】FNV诊断中上传日志到云端，有概率无法连接云端，报503 |  | Gating | TO DO | Ford
SYNC+_Z0036 | Diagnostic (SOA Related) Bezel Diagnostics工程模式 | 93.62% | 3 | FCIVIOS-14184 | Phase5_【U625】【黑盒】【偶现】【BezelDiagnostics】工程模式中ServingCellInfo下面包含3个字段，显示为空 |  | High | TO DO | TS
SYNC+_0132 | VCS | 96.26% | 2 | FCIVIOS-14319 | Phase5_【U625】【黑盒】【偶现】【VCS】蓝牙耳机未连接，唤醒语音助手，query：增大蓝牙耳机音量，TTS：已调高音量 |  | High | TO DO | TS
|  |  | 1 | FCIVIOS-14201 | Phase5_【U625】【黑盒】【必现】【HVAC】语音“主副驾空调温度调到20度”，TTS反馈“主副驾调温度已调到20度” |  | Medium | TO DO | TS
|  |  | 1 | FCIVIOS-14202 | Phase5_【U625】【黑盒】【必现】【HVAC】语音“关闭自动模式”，TTS反馈“自动模式已关闭”，有信号下发 |  | High | TO DO | TS
SYNC+_0126 | CarAudio音源矩阵内置 | 95.59% | 3 | APIMCIM-18661 | Phase5_【U625】【CarAudi内置】【必现】【黑盒】蓝牙音乐/USB音乐/本地视频界面未播放，内置来电铃声中点击播放，挂断电话没有播放 |  | High | TO DO | YF
|  |  | 3 | APIMCIM-18662 | Phase5_【U625】【CarAudio内置】【必现】【黑盒】蓝牙音乐/USB音乐/本地视频界面未播放，外置来电铃声中点击播放，挂断电话没有播放 |  | High | TO DO | YF
SYNC+_Z0004 | Car Audio内置 | 92.78% | 13 | FCIVIOS-14228 | Phase5_【U625】【CarAudio内置】【必现】【黑盒】Chime音Attenuation 6无压制效果 |  | High | TO DO | TS
SYNC+_Z1000 | Launcher | 98.59% | 1 | FCIVIOS-14274 | Phase5_【U625】【黑盒】【必现】【launcher】未填车牌时，账号下方显示限行信息 |  | High | TO DO | TS
SYNC+_Z0210/SYNC+_Z0204/SYNC+_Z0278/SYNC+_Z0281/SYNC+_Z0277/SYNC+_Z0197/SYNC+_Z0187/SYNC+_Z0180/SYNC+_Z0178/SYNC+_Z0183/SYNC+_Z0181/SYNC+_Z0182/SYNC+_Z0206/SYNC+_Z0215/SYNC+_Z0212/SYNC+_Z0217/SYNC+_Z0216/SYNC+_Z0213/SYNC+_Z0201/SYNC+_Z0214/SYNC+_Z0209/SYNC+_Z0211/SYNC+_0074 | Vehicle Setting | 98.72% | 1 | FCIVIOS-14125 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】灯光设置里点击收藏后，切换功能选项 收藏又自动变为未收藏状态 |  | High | TEST | TS | DCV4合入
|  |  | 1 | FCIVIOS-14208 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】巡航控制配置1，点击容限info按钮 无法打开提示弹窗 |  | High | TEST | TS | DCV4合入
|  |  | 1 | FCIVIOS-14119 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】巡航控制的容限入口处不显示对应的数值 |  | High | TEST | TS | DCV4合入
|  |  | 1 | FCIVIOS-14195 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】尾灯设置名称位置未跟随主题颜色适配 |  | High | TO DO | TS
|  |  | 1 | FCIVIOS-14209 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】点击尾灯设置info按钮 无法打开提示弹窗 |  | High | TO DO | TS
|  |  | 1 | FCIVIOS-14196 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】多功能座椅点击座椅渲染图，界面出现座椅残影 |  | High | TEST | TS | DCV4合入
SYNC+_Z0159--SYNC+_Z0177 | HVAC | 96.34% | 3 | NT | HMI未提供吹风动效资源，功能未完成 |  |  |  | TS
SYNC+_0073 | FAPA | 99.43% | 1 | APIMCIM-16546 | Phase5_【U625】【黑盒】【必现】【FAPA】弹出找到泊车位提示弹窗与UI显示不一致 |  | High | 正在进行 | Ford

## 模块详细数据-DCV3-1
模块详细数据
FeatureID | Moudle | Total | Pass | Fail | Block | NT | DCV3-1_Pass Rate （Pass/Total） | DCV3-1_Run Rate （Pass+Fail）/Total | 测试/开发 | DCV3_Pass Rate （Pass/Total） | 通过率是否下降 | 下降主要原因 | 车辆信息 | 测试时长 | Comments | 重点模块
SYNC+_0021 | DLNA |  | 15 | 0 | 0 | 0 |  |  | 李可可/贺金 | 69.57% | 否 |  | / | / |  | 否
SYNC+_Z0060 | Car Power |  | 72 | 0 | 0 | 0 |  |  | 李可可/秦诚 | 100% | 否 |  | / | / |  | 否
SYNC+_Z0081 | Car input |  | 37 | 0 | 0 | 0 |  |  | 李可可/李行键 | 79.37% | 否 |  | / | / |  | 否
SYNC+_0205 | Theme |  | 5 | 0 | 0 | 0 |  |  | 赵雅非/王闯 | 85.71% | 否 |  | / | / |  | 是
SYNC+_Z0153 | Location Service（GNSS） |  | 32 | 0 | 0 | 0 |  |  | 赵雅非/谢鑫 | 98.44% | 否 |  | / | / |  | 是
SYNC+_Z1000 | Launcher |  | 70 | 1 | 0 | 0 |  |  | 李可可/肖梁 | 96.25% | 否 |  | / | / |  | 是
SYNC+_Z0210/SYNC+_Z0204/SYNC+_Z0278/SYNC+_Z0281/SYNC+_Z0277/SYNC+_Z0197/SYNC+_Z0187/SYNC+_Z0180/SYNC+_Z0178/SYNC+_Z0183/SYNC+_Z0181/SYNC+_Z0182/SYNC+_Z0206/SYNC+_Z0215/SYNC+_Z0212/SYNC+_Z0217/SYNC+_Z0216/SYNC+_Z0213/SYNC+_Z0201/SYNC+_Z0214/SYNC+_Z0209/SYNC+_Z0211/SYNC+_0074 | Vehicle Setting |  | 463 | 6 | 0 | 0 |  |  | 关满意、肖文迪/王闯、许超、石松、董晗禹 | 97.56% | 否 |  | / | / |  | 是
SYNC+_Z0050 | 无线充电 |  | 5 | 0 | 0 | 0 |  |  | 赵雅非/秦城 | 100% | 否 |  | / | / |  | 是
SYNC+_0164 | FCS(Account) |  | 18 | 0 | 0 | 0 |  |  | 赵雅非/孙黎 | 96.77% | 否 |  | / | / |  | 是
SYNC+_Z0036 | Diagnostic (SOA Related) Bezel Diagnostics工程模式 |  | 44 | 1 | 2 | 0 |  |  | 赵雅非/王小强 | 100% | 是 | 新增1个偶现问题 | / | / |  | 是
SYNC+_0165 | 个性化设置档案 |  | 28 | 4 | 0 | 0 |  |  | 姜云腾/孙黎 | 87.1% | 否 |  | / | / |  | 否
SYNC+_Z0159--SYNC+_Z0177 | HVAC |  | 79 | 0 | 0 | 3 |  |  | 黄钊敏/窦歆禹 | 96.39% | 否 |  | / | / |  | 是
SYNC+_0132 | VCS |  | 103 | 4 | 0 | 0 |  |  | 黄钊敏、肖文迪、关满意、袁露/张嘉 | 93.69% | 否 |  | / | / |  | 否
SYNC+_0073 | 雷达 |  | 207 | 0 | 0 | 0 |  |  | 黄钊敏/顾佳宁 | 100% | 否 |  | / | / |  | 否
SYNC+_0073 | FAPA |  | 175 | 1 | 0 | 0 |  |  | 赵雅非/顾佳宁 | 98.86% | 否 |  | / | / |  | 是
SYNC+_0126 | Car Audio外置（10ch） |  | 0 | 0 | 0 | 180 |  |  | 姜云腾/杨永恒 | 61.76% | 是 | 哈曼侧功放软件未开发完成 | / | / |  | 是
SYNC+_0126 | CarAudio音源矩阵外置（10ch） |  | 0 | 0 | 0 | 136 |  |  | 姜云腾/杨永恒 | 66.67% | 是 | 哈曼侧功放软件未开发完成 | / | / |  | 是
SYNC+_0126 | CarAudio音源矩阵内置 |  | 130 | 2 | 4 | 0 |  |  | 黄钊敏/杨永恒 | 91.85% | 否 |  | / | / |  | 是
SYNC+_Z0004 | Car Audio内置 |  | 167 | 1 | 12 | 0 |  |  | 黄钊敏/杨永恒、朱昊 | 80.18% | 否 |  | / | / |  | 是
SYNC+_Z0026 | 蓝牙电话交互 |  | 16 | 0 | 0 | 0 |  |  | 赵雅非/许超 | 0% | 否 |  | / | / |  | 是
SYNC+_0129 | 蓝牙儿童座椅 |  | 39 | 0 | 0 | 0 |  |  | 黄钊敏/石松 | 60% | 否 |  | / | / |  | 是
SYNC+_0266 | 3D车模 |  | 66 | 3 | 6 | 0 |  |  | 肖文迪/肖梁 | 94.29% | 是 | 因bugAPIMCIM-15440影响case数7，DCV4合入 | / | / |  | 是
SYNC+_0132 | AAR |  | 59 | 6 | 2 | 0 |  |  | 赵雅非/徐欢 | 89.3% | 是 | 新增6个问题，影响case数8 | / | / |  | 是
SYNC+_Z0155 | 车载热点 |  | 18 | 0 | 0 | 0 |  |  | 李可可/王小强 | 88.89% | 否 |  | / | / |  | 是
SYNC+_Z0043 | WIR |  | 46 | 0 | 0 | 0 |  |  | 李可可/张金海 | 95.35% | 否
SYNC+_Z0033 | Provisioning |  | 4 | 0 | 0 | 0 |  |  | 李可可/卓明琼 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0037 | FNV诊断 |  | 23 | 1 | 1 | 0 |  |  | 李可可/卓明琼 | 93.75% | 是 | 新增一个偶现问题，需Ford分析
SYNC+_Z0032 | CCS |  | 53 | 0 | 0 | 0 |  |  | 李可可/谢鑫 | 98.8% | 否 |  | / | / |  | 否
SYNC+_0122 | VHA |  | 81 | 0 | 0 | 0 |  |  | 肖文迪/肖梁 | 100% | 否 |  | / | / |  | 否
SYNC+_0265 | V2I |  | 18 | 2 | 0 | 0 |  |  | 肖文迪/董晗禹 | 77.27% | 否
SYNC+_0223 | MMOTA |  | 219 | 4 | 25 |  |  |  | 李可可、杨春明、黄钊敏/陈明瑶 | 99.6% | 是 | 新增4个问题，其中APIMCIM-18588影响case数19，该问题需YF分析 |  |  |  | 是
Total | [9 empty] | 90.6%

## 重点模块列表 (hidden)
DLNA
Car Power
Car input
Theme
GNSS
Rear audio
Launcher
Audio 内置
Audio 外置（12ch）
Audio 外置（24ch）
音源矩阵(Ecall-12ch)
音源矩阵(Ecall-24ch)
音源矩阵(Ecall)
Vehicle Setting
数字香氛
无线充电
Multi -display
FCS(Account)
Bezel Diagnostics工程模式
个性化设置档案
HVAC
VCS
雷达
FAPA
powerflow能量流
EMR
蓝牙儿童座椅

## R06.1_Fix (hidden)
Issue key | Summary | Reporter | Status | Assignee | Component/s | Labels | Labels | Priority | Fix Version/s
APIMCIM-13801 | Phase 5：【必现】路试时，副驾有人，打开爱奇艺播放视频，卡顿并闪退 | jsun62 | Approval | jsun62 | Video | CDX707 | Inhouse_Platform | Immediate Gating | LA_R06.1_ENG
APIMCIM-9608 | [100%] MMOTA_China: Upgrade TCU by VI, the sync+ screen turns black when vehicle enters inhibit state | jzhan376 | Approval | jzhan376 | MMOTA | Inhouse_Platform | MigratingToCloud | Immediate Gating | LA_R06.1_ENG
APIMCIM-13273 | 【Phase V】【CDX707】【TOP】【DLNA】【5/5】TCU网环境下媒体投射开关异常，各模式也无法开启关闭 | lshi42 | Approval | zqiu12 | DLNA | CDX707 | Inhouse_Platform | Immediate Gating | LA_R06.1_ENG
APIMCIM-11765 | Phase5:[必现][CDX707]点击车模上的故障预警无法跳转到故障详情页 | xwang310 | Done | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | Immediate Gating | LA_R06_ENG
APIMCIM-13930 | Phase 5：【偶发】实车路试时，后台总是发生com.ford.sync.apa Crash | jsun62 | Approval | jsun62 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13540 | [100%] MMOTA_China: Entering into "preparing to update" page, ignition run, update failure has pop up, but updating progress still dominating the screen. | yli391 | Approval | yli391 | MMOTA | CDX707 | ECG | Gating | LA_R06.1_ENG
APIMCIM-13080 | 【Phase V】【CDX707】【R06.1-Production】【A】【2/20】移动widget card出现重叠或不显示 | zliu151 | Approval | zliu151 |  | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13745 | [10%] MMOTA_China: OTA updating SOC on vehicle, occasionally SOC installation failed. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13230 | Phase 5：【必发】H689272 13：59 在空调界面点击智能新风，提示“获取滤芯状态失败，联系客服 错误代码：-300” | hmo3 | Test | cchen244 | Auto Air Refresh | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12618 | Phase5:[必现][CDX707]发动机没启动IVI上显示车辆故障信息 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10295 | Phase5:[100%][CDX707] [CCS]After powercycle，no ccs sharing popup | qshi14 | Approval | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12602 | Phase5:[必现][CDX707]After Master reset, no ccs sharing popup | qshi14 | Approval | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13303 | [100%] MMOTA_China:Update TCU by VI and the activation conditions are not met, IVI does not pop up the corresponding pop-up according to the type of precondition | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12274 | Phase5:[偶现]DTC 0xE40100 | xhuang93 | In Progress | mzhuo1 | Diagnostic | EOL | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13402 | 【Phase V】【CDX707】【A】【儿童座椅】【5/5】车辆设置中儿童座椅功能无法进入，点击闪退 | zqiu12 | Approval | zqiu12 | BT Child Seat | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13276 | 【Phase V】【CDX707】【A】【TC】【5/5】睡眠唤醒、首次上电或切换两次驾驶模式后，瞬时油耗指示归零 | xdu22 | Approval | xdu22 |  | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13138 | 【Phase V】【CDX707】【A】【Audio】【5/5】24ch功放，播放音乐，触发关机动画，恢复Run状态后，音乐播放无声. | ywang535 | Approval | ywang535 | Audio | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13729 | Phase5_【CDX707】【黑盒】【必现】【MMOTA】VI-TCU，安装结束后，IG=off，车辆不进入激活状态，更新失败 | cyang114 | Closed with Accept | gyuan6 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12714 | [CDX707][Performance][ResponseaTime]Launcher显示到SDM可用响应时间过长，需要优化。 | ljia14 | Approval | ljia14 | System Performance | CDX707 | digitalee | Gating | LA_R06.1_ENG
APIMCIM-12893 | Phase 5：【偶发】断网后，发生com.ford.sync.fnvservice/com.yfve.report Crash | jsun62 | Approval | jsun62 | FNV | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12738 | Phase 5：【偶发】首页widget编辑页，重复快速拖动改变卡片和位置，launcher发生闪退 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12646 | Phase 5：【必现】Launcher主页3D车模不显示 | hzhan238 | Approval | hzhan238 | 3D Vehicle model | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12795 | Phase 5：【必现】唤醒语音：播放/上一首/下一首，USB音乐播放，但Audio off并未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12217 | Phase 5：【偶发】RACM端切源到随心听，随心听播放页显示错误的歌曲信息 | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-11450 | 【R05-回归测试】【广场】【必现】03:15 我的收藏编辑页面退出后会弹应用商店弹窗 | ntian2 | Approval | ntian2 | Launcher | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-11789 | Phase 5：【必现】首页，能把同一个卡片拖到四个widget位上 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12868 | Phase 5：【偶发】蓝牙音乐页面卡死，点击Home键，再次打开随心听显示黑屏 | jsun62 | Approval | jsun62 | BT Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12292 | Phase 5：【必现】播放蓝牙音乐时，RACM端点击Audio off按钮无法关闭媒体音频 | jsun62 | Approval | jsun62 | BT Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12892 | Phase 5：【偶发】爱奇艺播放时，发生四个APP Crash | jsun62 | Approval | jsun62 | Video | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12796 | Phase 5：【必现】唤醒语音：音量大一点/音量小一点，USB音乐未播放，Audio off也未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12864 | 【台架】【偶现】【CDX707】【widget卡片】widget卡片样式变小 | ntian2 | Approval | ntian2 | Map&Navigation | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12941 | 【Phase V】【CDX707】【A】【BT Phone】【5/5】oppo find X 通话车机无声，使用手机铃声来电去电，车机无声 | zqiu12 | Closed with Accept | zqiu12 | BT Phone | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12712 | Phase 5：【偶现】TCU有网的车，连接WiFi，一直显示正在加入网络.. | tshan3 | Approval | tshan3 | WiFi Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12317 | Phase 5：【高频】播放QQ音乐，RACM端点击音乐源按钮，音乐源页面显示空白 | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10872 | Phase 5：【偶现】3D车模位置不正确 | jxu148 | Approval | jxu148 | 3D Vehicle model | CDX707 | CDX707C_UAT_1st | Gating | LA_R06.1_ENG
APIMCIM-11832 | Phase 5：【偶发】爱奇艺播放时，发生com.baidu.iov.dueros.videos ANR | jsun62 | Approval | jsun62 | Video | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-9451 | Phase 5: 【偶发】【AutoTest】泊车相关功能信号接收有延迟，不响应现象 | yzhu104 | Approval | yzhu104 | Parking Assist | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12569 | Phase5:【必现】【CDX707】播放USB音乐->打开地图->导航路线->开始导航，导航播报结束后媒体音量变大，退出地图后恢复正常 | zsu13 | Approval | zsu13 | Audio | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13549 | 【Phase V】【CDX707】【A】【Audio】【1/10】播放音乐，挂断电话后，音乐的声音突然变大. | ywang535 | Approval | ywang535 | Audio | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-11862 | Phase 5：【必现】蓝牙歌曲在播放，但没有退出Audio off | jsun62 | Approval | jsun62 | Audio | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-11221 | Phase5：【偶现】在地图页面，旋转声音按钮调节媒体音量，将媒体音量调整为0后，QQ音乐依然有声音发出 | jchen384 | Approval | jchen384 | Audio | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12924 | Phase 5：【必现】蓝牙音乐播放时，RACM端高亮显示"循环模式"按钮 | jsun62 | Approval | jsun62 | BT Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12887 | Phase 5：【必现】唤醒语音：播放/上一首/下一首，QQ音乐播放，但Audio off并未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13614 | Phase 5：【必发】H689293 13：46 系统设置—音效设置—平衡 衰减—重置失败 必现 | hmo3 | Approval | hmo3 | System Setting | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12220 | Phase 5：【必现】插入U盘后，RACM端不会立即显示USB音乐入口 | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12197 | Phase 5：【偶发】快速连续点击第一个卡片的删除按钮，发生com.ford.sync.controllerlauncher Crash | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13647 | Phase 5：【偶发】【AutoTest】Monkey测试时，出现com.ford.sync.hvac的crash | jsun62 | Approval | jsun62 | BT Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10369 | Phase 5：【必现】无TCU环境下，视频投屏后一直加载中，无法投屏 | xwang314 | Approval | xwang314 | DLNA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12878 | Phase 5：【必现】唤醒语音：音量大一点/音量小一点，Audio off未解除，蓝牙音乐未播放 | jsun62 | Approval | jsun62 | BT Music | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13235 | Phase 5：【偶发】H689272 15：27 点击泊车辅助按键，选择泊车后进入无信息显示的界面，然后退出不了点击下方的菜单也无反应 | hmo3 | Approval | hmo3 | Vehicle Setting | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13016 | Phase 5：【偶发】倒档来车预警影像开关点击无法打开 | sliu141 | Approval | sliu141 | Vehicle Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12140 | Phase 5：【偶发】设置发生com.yfve.settings ANR | jsun62 | Approval | jsun62 | System Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13491 | [100%] MMOTA_China: Upgrade TCU by VI, precondition pop up exist all the time during activation. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-7895 | [100%] MMOTA_China:OTA升级SOC,下载过程中发Shed_Level_Req:3_SHED2_CONTIN或Shed_Level_Req=5_SHED_ENG_OFF,进入安装会报SIM_E1001,OTAM_E1008,OTAM_E1016 | jzhan376 | Approval | jzhan376 | MMOTA | Inhouse_Platform | MigratingToCloud | Gating | LA_R06.1_ENG
APIMCIM-12785 | Phase5:[10%][CDX707]登录账号后首页头像未同步更新 | lxue15 | Approval | lxue15 | Account | CDX707 | CDX707_CVPP | Gating | LA_R06.1_ENG
APIMCIM-12270 | [CDX707][Performance][Stability]monkey test ,vendor.ford.soa happens native crash | rhuang35 | Approval | rhuang35 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12363 | Phase 5：【必现】副驾随心听却支持添加到default卡片 | jsun62 | Approval | jsun62 | Music | CDX707 | CDX707C_UAT_2nd | Gating | LA_R06.1_ENG
APIMCIM-12264 | [CDX707][Performance][Stability]monkey test,com.ford.sync.controllerlauncher happens 1 times crash | rhuang35 | Approval | rhuang35 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12499 | Phase 5：【偶现】 模拟导航无声14:28 | rzhao22 | Approval | rzhao22 | Audio | R06_SIGN_OFF | R061_MUST_FIX | Gating | LA_R06.1_ENG
APIMCIM-12263 | [CDX707][Performance][Stability]monkey test,com.ford.sync.fnvservice happens 2 times crash | rhuang35 | Approval | rhuang35 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10984 | [100%] MMOTA_China: Upgrade TCU by VI, The time displayed in the "System Update Reminder" pop-up is inconsistent with the set time | jzhan376 | Approval | jzhan376 | MMOTA | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12314 | Phase 5：【高频】删除蓝牙设备，RACM端点击蓝牙音乐源按钮，发生多个Crash | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12110 | Phase5:[CDX707]No banner message pops up after filter saturation | cshengji | Approval | cshengji | Auto Air Refresh | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-10920 | [CDX707][Performance][Stability]monkey test,com.yfve.settings happens 3 times crash | sjie2 | Approval | sjie2 | System Stability | CDX707 | digitalee | Gating | LA_R06.1_ENG
APIMCIM-12021 | Phase5:[必现][CDX707]音效设置页面的部分设置项点击无效 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | IACC, | Gating | LA_R06.1_ENG
APIMCIM-10185 | [100%] MMOTA_China: USB plugged to upgrade MCU,during download/ installation/pending activation when upgrade SOC via OTA,the USB upgrade cannot continue after SOC upgrade is canceled. | jzhan376 | Closed with Accept | dliu79 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13050 | Phase5:[100%]CDX707 Authorization time popup text error | jgu37 | Approval | jgu37 | V2I | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13649 | Phase 5：【偶发】【AutoTest】Monkey测试时，出现com.ford.sync.controllerlauncher Crash | jsun62 | Test | zzhou68 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13807 | Phase 5：【偶发】路试时，后台发生com.ford.sync.fnvservice Crash | jsun62 | Approval | jsun62 | FNV | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10694 | Phase 5：【必现】后屏来源播放蓝牙或USB音乐，后屏音频关闭按键交互出错 | tshan3 | Approval | wxie15 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13079 | Phase5:[100%][CDX707]VPA status is about seat when query E-manual | lxue15 | Approval | lxue15 | Virtual Personal Assistant | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13338 | [100%] MMOTA_China: Upgrade TCU by VI,ADB log prints lots of error messages about the statusbar during upgrade process | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13482 | [100%] MMOTA_China: Upgrade TCU by VI, precondition pop up button not match with UI. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-5293 | Phase 5：【812】【必现】唤醒车机，语音:打开分屏。播报：操作失败 | tshan3 | Approval | tshan3 | VR | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13125 | Phase5:[CDX707][Performance][Roadtest]Roadtes test, in the background, the cpu usage rate of controller launcher is as high as 20%, without releasing | sjie2 | Approval | sjie2 | System Performance | digitalee | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13600 | Phase 5：【必发】H689286 1121 车辆启动时开着“安全开门预警”，熄火后再次启动车辆，“安全开门预警”按钮自动关闭后再次开启。必现 | hmo3 | Approval | hmo3 | Vehicle Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13678 | Phase5：【必现】在地图页面，按压中控台上的“¦P¦”按键进入自动泊车页面，自动泊车页面未占满整个页面，操作屏顶部为地图的画面 | jchen384 | Approval | jchen384 | Parking Assist | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13603 | Phase 5：【必发】689306 10：46 主界面点击车模，进入车内，点击林肯香氛按钮，打开林肯香氛，选择其他香氛时开关会有一个关闭开启的现象 必现 | hmo3 | Approval | hmo3 | Drive Mode | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13328 | Phase 5：【必发】H689281 18：53 每次按泊车辅助按键，中控屏都会显示泊车雷达按钮从关闭到打开的现象 | hmo3 | Approval | hmo3 | System Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12430 | Phase 5: 【必现】车钥匙检测提示没有主动get Can信号反馈状态 | xli318 | Approval | xli318 | Vehicle Setting | GIM | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13536 | Phase5:[必现][CDX707]Ambient light is still display opening in 3D car model when the light switch is turned off. | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11837 | phase5：【偶现】偶现点击车路协同闪退到主界面 | lshi42 | Approval | zqiu12 | Vehicle Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11824 | 【Phase V】【CDX707】【A】【RACM】【3/5】后屏source源信息，蓝牙图标显示为随心听，且切源时大概率不显示，插入U盘后，播放源和显示的源信息不同步 | lshi42 | Approval | zqiu12 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10427 | Phase5:[CDX707][偶现]共享位置关闭的情况下，需要定位授权的应用可以选择权限 | qshi14 | Done | qshi14 | User Privacy | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10429 | Phase5:[CDX707][偶现]共享位置打开的情况下，定位授权app提示“"无法开启定位”---请开启“共享车辆位置”后重试 | qshi14 | Done | qshi14 | User Privacy | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12157 | Phase5_【CDX707】【黑盒】【必现】【CarAudio外置】导航声音不在播报的情况下设置，再次导航音量不起效果 | tzhou37 | Closed with Accept | tzhou37 | Audio | CDC707 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13509 | Phase 5：【必发】H689270 1035 首次打开空调出现一条灰色残影。 | hmo3 | Approval | hmo3 | Climate | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12631 | Phase 5：【偶现】已保存的手机热点开启后，车机未自动连接上wifi | hzhan238 | Approval | hzhan238 | WiFi Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12886 | Phase 5：【必现】播放QQ音乐，快进快退时唤醒语音，语音结束后，歌曲播放，但audio off仍未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11124 | 【Phase V】【CDX707】【A】【System Setting】【5/5】音效设置界面进入音乐界面，在音乐界面点击“音效设置”按钮进入音效设置，无法进入音量设置/均衡器/平衡衰减界面. | zqiu12 | Done | zqiu12 | System Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12833 | Sensitive Data(VIN) Disclosure – AccountService | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse | High | LA_R06.1_ENG
APIMCIM-12583 | TLS not Verified – swuservice.apk | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10191 | Phase5:[偶现][CDX707]brandreset清掉授权后， CCS icon图标显示为授权状态图标 | qshi14 | Monitor | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12590 | [100%] MMOTA_China: USB update SOC with corrupt SW file, IVI pop up is wrong. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-8442 | [20%] MMOTA_China: VIL file is empty after USB upgrade ECG success | yli391 | Approval | yli391 | MMOTA | CDx707C | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10901 | Phase 5：【必现】插拔U盘，后排屏音源显示错误 | bliu94 | Approval | bliu94 | Multi-Screen Interaction | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-10896 | Phase 5：【必现】RACM切源，随心听/USB切到蓝牙音乐，RACM音源图标显示error | bliu94 | Approval | bliu94 | Multi-Screen Interaction | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-12931 | Phase 5：【必现】断电再上电，Audio off不被记忆 | jsun62 | Rejected | jsun62 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11801 | Phase 5：【必现】空调内循环按键点击打开与关闭，在按键左侧有动效 | tshan3 | Approval | tshan3 | Climate | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12202 | [100%] MMOTA_China: USB update ECG/TCU, updating progress jump from 0% to 100%. | yli391 | Approval | jwang373 | MMOTA | CDX707 | ECG | High | LA_R06.1_ENG
APIMCIM-10681 | Phase 5：【必现】后屏蓝牙音乐界面，记忆显示了USB的播放模式：随机与循环。 | tshan3 | Approval | tshan3 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12581 | Private keys are found on swuservice.apk | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12194 | Phase5:[100%][CDX707]New user guide screen displays after changing account | lxue15 | Approval | lxue15 | Account | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11813 | Phase5_[CDX707C][必现】【Enhanced Memory】 创建档案时，IVI下发信号CtrStkDsplyOp_D_Rq值错误 | nli52 | Approval | nli52 | Personalization | CDX707 | CDX707C | High | LA_R06.1_ENG
APIMCIM-12188 | Phase5:[100%][CDX707] The content layout of the shared pop-up window is not beautiful, and the text is truncated | qshi14 | Approval | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12040 | Phase5[CDX707][必现]:护航详情同级页面语音无法打开胎压监测页面 | xwang310 | Approval | xwang310 | Vehicle Health Alert | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12556 | Phase 5：【必现】+1屏，删除所有卡片，再添加7个卡片，第四个卡片size偏小 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12557 | Phase 5：【必现】+1屏，长按一个卡片时，点击"保存"按钮，选中的卡片仍显示编辑态 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12326 | [100%] MMOTA_China: Upgrade TCU by VI,"system update successful" pops up when the update progress bar reaches 11% | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12118 | Phase 5：【必现】语音切换声源定位时，tts播报错误 | tshan3 | Approval | tshan3 | VR | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11463 | Phase5：【偶现】退出 Revel@Experience 视频，闪现视频进度条 | jchen384 | Approval | jchen384 | System Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-11237 | 【语音】 【基础功能】 【CDX707】 关闭自动模式tts播报已关闭，但实车上屏幕图标没有变化，仍显示自动模式 | ntian2 | Approval | ntian2 | VR | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12644 | Phase 5：【必现】关闭林肯香氛后3D车模里仍显示香氛打开状态 | hzhan238 | Approval | hzhan238 | 3D Vehicle model | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12587 | Phase 5: 【必现】车辆控制界面，点击下方车辆控制按钮，车辆控制页面不应进行刷新。 | xli318 | Approval | xli318 | Vehicle Setting | GIM | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12130 | Phase 5: 【偶现】导航，Media和电话交互，挂断电话后Media会出现爆音 | jzeng28 | Closed with Accept | tzhou37 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10933 | Phase5_【CDX707】【黑盒】【偶现】【FAPA】在360摄像头环境下，自动泊车不可用偶现无播报 | tzhou37 | Closed with Accept | tzhou37 | Fapa | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-12201 | [100%] MMOTA_China: USB update ECG/TCU/SYNC+, the remaining file number increasing, not decreasing. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-7237 | Phase5：【必现】[CDX707][HMI走查] 3D车模_车辆（车模相关）快捷控制视觉布局问题 | fwang116 | Done | yliu404 | 3D Vehicle model | CDX707 | CDX707C_UAT_1st | High | LA_R06.1_ENG
APIMCIM-11877 | Phase5:[100%][CDX707]点击车身颜色tab会重置色环和车身颜色 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11436 | Phase5：【必现】[CDX707][HMI走查] 点击时的水波纹效果不同 | fwang116 | Done | fwang116 |  | CDX707 | CDX707_HMI | High | LA_R06.1_ENG
APIMCIM-11733 | Phase5_[CDX707C][必现】【Enhanced Memory】 删除个人账号下对应的个性化档案后，再次切换回该账号，会一直提示该账号下个性化档案已删除 | nli52 | Approval | nli52 | Personalization | Inhouse_Platform | TW43 | High | LA_R06.1_ENG
APIMCIM-11623 | Phase5-[CDX707C][必现】【Enhanced Memory】在D/R/L/N档时，IVI界面会弹出个性化保存弹框 | nli52 | Approval | nli52 | Personalization | CDX707 | CDX707C | High | LA_R06.1_ENG
APIMCIM-12351 | Phase5:[必现][CDX707]自定义模式下车门和地板灯光调至最低后返回显示异常 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12426 | Phase5：【必现】[CDX707][HMI走查]_info弹窗置于后台，再次打开后，弹窗重新弹出 | yqin24 | Done | yqin24 | System UI | CDX707 | CDX707_HMI | High | LA_R06.1_ENG
APIMCIM-12554 | Phase 5：【偶现】出风口滑动调节界面与空调主界面重叠 | tshan3 | Approval | tshan3 | Climate | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11439 | Phase5：【必现】[CDX707][HMI走查] 系统按钮动效问题 | fwang116 | Done | fwang116 |  | CDX707 | CDX707_HMI | High | LA_R06.1_ENG
APIMCIM-11874 | Phase5:[100%][CDX707]重置第五个车身颜色tab异常 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12195 | Phase 5：【必现】[CDX707]空调风量调节背景部分过亮，出风口整个偏上 | jyi23 | Approval | jyi23 | Climate | CDX707_HMI | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11988 | Phase5:[偶现][CDX707]车外页熄火需要有“发动车辆才可以使用全部车辆功能”提示 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12002 | Phase5:[必现][CDX707]3D车模页面的音效设置同步不到系统音效设置页面 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-9524 | [100%] MMOTA_China:Click the "Clear" button, the system update plan cannot be cleared | jzhan376 | Approval | jzhan376 | MMOTA | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-9092 | Phase5:【必现】[CDX707]快速滑动选择按摩方式，选中的按摩方式仍然会与其他按摩方式多次来回切换 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | CDX707C_UAT_1st | High | LA_R06.1_ENG
APIMCIM-9541 | [100%] MMOTA_China: Upgrade TCU by VI, the "System update schedule not set" popup does not pop up when pending activation | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12200 | Phase 5：【必现】+1屏的widget编辑状态，点击Home键，再向左滑动到+1屏，状态栏与右上角的按钮重叠，且卡片不晃动 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11790 | Phase 5：【必现】音效设置内的菜单点击时，没有白色背景的点击动效 | jsun62 | Approval | jsun62 | General Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12283 | Phase5：【必现】车模重置车身颜色，最后一个光圈一下重置到初始颜色，需要点击两次重置按钮才能重置到初始的颜色 | jchen384 | Approval | jchen384 | 3D Vehicle model | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12134 | Phase 5: 【必现】导航和QQ音乐交互时，导航播报时QQ音乐不会降音播放 | jzeng28 | Closed with Accept | yyang179 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10571 | Phase5：【必现】[CDX707][HMI走查] Climate空调电动出风口_页面视觉布局问题 | fwang116 | Done | xdou | Climate | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13216 | Phase 5：【必现】CDX707 允许车路协同infobook,授权时间的弹窗“年”字没适配主题，左上角关闭按钮和图标“取消”重复 | lzhan249 | Approval | lzhan249 | V2I | CDX707_HMI | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-12037 | Phase5：【必现】[CDX707][HMI走查]多模块空中升级 (MMOTA) _按钮动效问题 | fwang116 | Done | cyang114 | MMOTA | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-13215 | Phase 5：【必现】CDX707 系统设置进度条颜色没适配 | lzhan249 | Approval | lzhan249 | System Setting | CDX707_HMI | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-13317 | Test Page with Shortcuts – VoiceControlSevice | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-12629 | Phase5:【必现】【CDX707】车外天窗控制界面与主界面重叠 | swang218 | Closed with Accept | wxiao13 | 3D Vehicle model | FCPA | Inhouse_App | Medium | LA_R06.1_ENG
APIMCIM-12816 | Phase 5：【必现】3D车模车辆健康报警和各个故障显示点击没有按钮音效 | hzhan238 | Approval | hzhan238 | 3D Vehicle model | CDX707 | ICV | Medium | LA_R06.1_ENG
APIMCIM-12844 | Exportable Activity DoS – AccountService | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-11966 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_弹窗页面布局问题 | fwang116 | Done | wxiao13 | V2I | CDC_TS_HMI | CDX707 | Medium | LA_R06.1_ENG
APIMCIM-12410 | Phase5：【必现】3D车模顶部的动画和坐享净界主题的动画不一致 | jchen384 | Approval | jchen384 | 3D Vehicle model | CDC_Phase5 | CDX707 | Medium | LA_R06.1_ENG
APIMCIM-12208 | Phase5：【必现】[CDX707][HMI走查]快捷控制-动效问题 | fwang116 | Done | fwang116 | Drive Mode | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12205 | Phase5：【必现】[CDX707][HMI走查]手机无线充电-动效问题 | fwang116 | Done | fwang116 | Wireless Charging | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12206 | Phase5：【必现】[CDX707][HMI走查] _DAT Setting_动效问题 | fwang116 | Done | cxu63 | DAT Setting | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12144 | Phase5：【必现】[CDX707][HMI走查] DIDC-动效问题 | fwang116 | Done | cxu63 | Driver Info | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12039 | Phase5：【必现】[CDX707][HMI走查]遥控启动设置-弹窗动效问题 | fwang116 | Done | zlian2 | Remote Control | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12030 | Phase5：【必现】[CDX707][HMI走查] _launcher_toast动效问题 | fwang116 | Done | lxiao19 | Launcher | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11802 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_视觉布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11806 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_info页面布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11811 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_申请流程页面布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12043 | Phase5：【必现】[CDX707][HMI走查] 诊断分析-动效问题 | fwang116 | Done | cwang236 | FNV | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11807 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_toast布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-10094 | Phase5：【必现】[CDX707][HMI走查] _system UI & launcher_视觉布局问题 | fwang116 | Done | fwang116 | System UI | CDX707 | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-7935 | Phase5：【必现】[CDX707][HMI走查] Face ID_条款界面视觉布局问题 | fwang116 | Done | jzhu79 | FaceID | CDX707 | HMI | Medium | LA_R06.1_ENG
APIMCIM-12654 | Phase 5: 【必现】把主题从"自在航行"切换至“坐享净界”，车辆控制界面右侧的滑条未变蓝色。 | xli318 | Approval | xli318 | Vehicle Setting | GIM | Inhouse_Platform | Low | LA_R06.1_ENG
APIMCIM-10556 | Phase5_[CDX707C][必现】【Enhanced Memory】 After Paak was associated with Profile, the Paak name is wrong | nli52 | Approval | nli52 | Personalization | CDX707 | CDX707C | Low | LA_R06.1_ENG

## R06.1_Fix_TS (hidden)
Issue key | Summary | Reporter | Status | Created | Assignee | Component/s | Affects Version/s | Priority | Labels | Labels | Labels | Labels | Labels | Labels | Labels | Labels
APIMCIM-12874 | Phase 5：【偶现】625实车，连接WiFi后，自动会被关闭 | tshan3 | To Do | 2022-10-21 04:25 | tshan3 | WiFi Setting | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-12903 | Phase 5：【偶发】RACM端显示“音频关闭”，但是点击“关闭”按钮无响应 | jsun62 | In Progress | 2022-10-23 22:50 | bliu94 | Multi-Screen Interaction | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-13437 | Phase 5：【偶发】NTT 707 EPT02 684122 1435 驾驶辅助，开关倒档来车预警，屏幕跳动 | hmo3 | To Do | 2022-11-03 23:52 | hmo3 | Driver Assistance | LA_R06_ENG | High | CAF | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | IVI
APIMCIM-12815 | Phase 5：【必现】已连接wifi网络，下载导航语音包时，依然弹出“非wifi网络将消耗移动流量，是否继续下载"的弹框 | jxu148 | In Progress | 2022-10-20 11:31 | jzhan372 | Map&Navigation | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Plaform | Inhouse_Platform | R061_MUST_FIX
APIMCIM-13822 | Phase 5：【必现】空调开关无法开启 | xwang314 | To Do | 2022-11-12 04:57 | xwang314 | Climate | LA_R06_ENG | Gating | CDC_IVITst | CDC_phase5 | CDX707 | Inhouse_Platform
APIMCIM-12274 | Phase5:[偶现]DTC 0xE40100 | xhuang93 | In Progress | 2022-10-07 03:35 | mzhuo1 | Diagnostic | LA_R05_ENG | Gating | CDC_Phase5 | CDX707 | EOL | Inhouse_Platform | IVI | R061_MUST_FIX | W43 | W44
APIMCIM-13917 | Phase5_【CDX707】【黑盒】【必现】【Audio】进入静音模式后，播放音乐，依旧有声音 | cyang114 | To Do | 2022-11-14 05:01 | cyang114 | Audio | LA_R06_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform | W46
APIMCIM-14001 | Phase 5：【必现】调节座椅页面，未高亮的菜单的"<"按钮都是高亮 | jsun62 | To Do | 2022-11-15 09:02 | jsun62 | Seat | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13737 | 【PhaseV】【CDX707】【A】【RACM】【5/5】RACM无法调节音量 | zqiu12 | To Do | 2022-11-10 01:10 | zqiu12 |  | LA_R06.1_ENG | Gating | CDC_IVITst | CDC_Phase5 | CDC707 | CDX707 | Inhouse_Platform | W46 | YFVE
APIMCIM-13855 | Phase 5：【偶发】空调调出动效异常 | jxu148 | To Do | 2022-11-13 08:32 | xdou | Climate | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-14007 | Phase 5：【偶发】实车路试时，车机突然断网 | jsun62 | To Do | 2022-11-15 09:27 | jzhan372 | Carrier | LA_R06_ENG | Immediate Gating | CDC_IVITst | CDC_Phase5 | CDX707 | CVPPVOCF | Inhouse_Platform | VOCF
APIMCIM-14046 | Phase 5：【必现】历史消息页面，点击未接来电的"通话"按钮，无任何响应 | jsun62 | To Do | 2022-11-16 02:12 | lwang287 | Launcher | LA_R06_ENG | Gating | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-13815 | Phase 5：【必现】副驾随心听总是显示"加载失败"，完全不能用 | jsun62 | In Progress | 2022-11-12 03:08 | jzhan372 | Music | LA_R06_ENG | Gating | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | R07_MUST_FIX_YF | VOCF
APIMCIM-13989 | Phase 5：【偶现】媒体音调节无效，旋钮和音量设置均无效 | cyang114 | To Do | 2022-11-15 03:16 | yyang179 | Audio | LA_R06_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform | TS
APIMCIM-13316 | Exportable Component DoS – Inhouse APPs | xzhan221 | In Progress | 2022-11-02 01:53 | hzhu74 | Cybersecurity |  | Medium | APIM | CDX707 | Cybersecurity | Inhouse_APP | Inhouse_Platform | PenTest | Sync+3.0
APIMCIM-12845 | Lack of APP Hardening-Inhouse | xzhan221 | To Do | 2022-10-21 01:16 | ycai28 | Cybersecurity |  | Medium | APIM | CDX707 | Cybersecurity | Inhouse_Platform | PenTest | Sync+3.0
APIMCIM-13868 | Phase 5：【偶现】路试中Card2突然弹出香氛相关toast | jxu148 | To Do | 2022-11-13 10:40 | wxiao13 | Launcher | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13734 | 【Phase V】【CDX707】【A】【Audio】【5/5】实车LV606 104A 外置功放24CH,平衡/衰减位置不正确. | ywang535 | In Progress | 2022-11-10 00:55 | hzhu74 | Audio | LA_R06.1_ENG | Gating | CDC_IVITst | CDC_Phase5 | CDC707 | CDX707 | Inhouse_Platform | YFVE
APIMCIM-13586 | 【Phase V】【CDX707】【A】【Upgrade】【2/2】OTA整包升级，S1008激活成功后ign run，等待vil上传，等待超过10分钟，没有报S1010 | zqiu12 | To Do | 2022-11-07 02:18 | zqiu12 | MMOTA | LA_R06.1_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-14002 | Phase 5：【必现】调节座椅页面，点击"<"">"按钮，只是高亮其菜单 | jsun62 | To Do | 2022-11-15 09:03 | jsun62 | Seat | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13990 | Phase 5：【偶现】【外置功放】平衡衰减调节无效 | cyang114 | To Do | 2022-11-15 03:23 | yyang179 | Audio | LA_R06_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform | TS
APIMCIM-13863 | Phase 5：【偶发】移动widget，原来的卡片位置黑屏3s | jxu148 | To Do | 2022-11-13 09:33 | cxu63 | Launcher | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | YFVE
APIMCIM-13458 | Phase 5：【偶发】NTT707 EPT02 684122 1445 空调页面风量大小无显示 | hmo3 | To Do | 2022-11-04 02:29 | hmo3 | Climate | LA_R06_ENG | High | CAF | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | IVI | NTT
APIMCIM-14070 | Phase 5：【偶现】挂断蓝牙微信电话后，蓝牙音乐爆音 | jxu148 | To Do | 2022-11-16 03:42 | yyang179 | BT Music | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13688 | Phase 5：【必现】打开车窗后，3D车模的车窗依旧处于关闭关闭状态 | hzhan238 | To Do | 2022-11-08 19:59 | hzhan238 | 3D Vehicle model | LA_R06_ENG | High | CAF | CDC_Phase5 | CDX707 | ICV | Inhouse_Platform | notbug | phase5_launchTst
APIMCIM-13687 | Phase 5：【必现】在3D车模快捷控制页面停止操作15s，车模不会自动关闭 | hzhan238 | To Do | 2022-11-08 19:56 | hzhan238 | 3D Vehicle model | LA_R06_ENG | High | CAF | CDC_Phase5 | CDX707 | ICV | Inhouse_Platform | notbug | phase5_launchTst
APIMCIM-13793 | Phase 5：【必发】707H689274车辆设置中没有车钥匙检测提示选项 | hmo3 | To Do | 2022-11-11 04:28 | yzhan482 | Vehicle Setting | LA_R06_ENG | High | CAF | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | IVI | NTT

## Jira_issue_DCV3-1
Issue key | Summary | Reporter | Status | Created | Assignee | Priority | Components | 归属 | 修改计划(G&IG)
FCIVIOS-14319 | Phase5_【U625】【黑盒】【偶现】【VCS】蓝牙耳机未连接，唤醒语音助手，query：增大蓝牙耳机音量，TTS：已调高音量 | guangdong yuan | Tested | 2023-03-06 02:34 | guangdong yuan | High | VCS | TS
FCIVIOS-14290 | Phase5_【U625MCA】【黑盒】【必现】【VHA】发送信号ig=off，ac=on，车辆状况显示小红点 | wendi Xiao | Tested | 2023-03-03 00:45 | wendi Xiao | High | VHA | TS
FCIVIOS-14274 | Phase5_【U625】【黑盒】【必现】【launcher】未填车牌时，账号下方显示限行信息 | tianqi zhou | Tested | 2023-03-02 06:28 | tianqi zhou | High | Launcher | TS
FCIVIOS-14250 | Phase5_【U625】【黑盒】【必现】【AAR】智能新风首页界面显示应该为XX区+PM2.5 | Chuanqin Chen | Awaiting implementation (migrated) | 2023-03-01 22:19 | huan xu | Medium | HVAC | TS
FCIVIOS-14244 | Phase5_【U625MCA】【黑盒】【偶现】【Monkey】【Vehicale settings】monkey测试中 com.yfve.settings发生ANR | wendi Xiao | 待办 | 2023-03-01 21:09 | wendi Xiao | High | Vehicle Settings | TS
FCIVIOS-14243 | Phase5_【U625MCA】【黑盒】【偶现】【Monkey】【Launcher】monkey测试中 com.ford.sync.controllerlauncher发生ANR | wendi Xiao | Monitor | 2023-03-01 21:05 | wendi Xiao | High | Launcher | TS
FCIVIOS-14242 | Phase5_【U625】【黑盒】【必现】【AAR】温度切为华氏摄氏度时，AAR站点显示的温度与摄氏度的显示一致，未做转换 | Chuanqin Chen | Awaiting implementation (migrated) | 2023-03-01 07:54 | huan xu | High | AAR | TS
FCIVIOS-14229 | Phase5_【U625】【CarAudio内置】【必现】【黑盒】车速音量调整，音量大小无变化幅度 | guangdong yuan | 待办 | 2023-03-01 04:11 | Wei Zheng | High | CarAudio | TS
FCIVIOS-14228 | Phase5_【U625】【CarAudio内置】【必现】【黑盒】Chime音Attenuation 6无压制效果 | guangdong yuan | 待办 | 2023-03-01 03:55 | Wei Zheng | High | CarAudio | TS
FCIVIOS-14226 | Phase5_【U625MCA】【黑盒】【必现】【3D车模】触发照明系统故障，发送信号打开远近灯光，车模仍可以打开远近灯光 | wendi Xiao | Tested | 2023-03-01 02:59 | wendi Xiao | High | 3D Car Model | TS
FCIVIOS-14224 | Phase5_【U625MCA】【黑盒】【必现】【3D车模】分屏模式下点击后备箱按钮，弹窗被截断 | wendi Xiao | Tested | 2023-03-01 02:42 | wendi Xiao | High | 3D Car Model | TS
FCIVIOS-14219 | Phase5_【U625】【MMOTA】【必现】VI升级激活阶段-未进入激活时 Ig=OFF ->ig=RUN后进入系统更新界面会弹出‘需要更改设置’’ | zhangjian zhou | Closed with Accept | 2023-02-28 22:40 | zhangjian zhou | High | MMOTA | TS
FCIVIOS-14209 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】点击尾灯设置info按钮 无法打开提示弹窗 | manyi guan | Awaiting implementation (migrated) | 2023-02-28 05:18 | Chuang Wang | High | Vehicle Settings | TS
FCIVIOS-14208 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】巡航控制配置1，点击容限info按钮 无法打开提示弹窗 | manyi guan | Tested | 2023-02-28 04:53 | manyi guan | High | Vehicle Settings | TS
FCIVIOS-14206 | Phase5_【U625】【黑盒】【必现】【AAR】AAR过滤完成的弹窗未适配主题，请确认是否需要适配 | Chuanqin Chen | 待办 | 2023-02-28 03:21 | huan xu | Medium | AAR | TS
FCIVIOS-14204 | Phase5_【U625】【MMOTA】【必现】系统更新的CCS判断逻辑弹窗区域和UE设计的不一致，多了上方的‘’系统更新‘’标题 | zhangjian zhou | Tested | 2023-02-28 02:44 | zhangjian zhou | Medium | MMOTA | TS
FCIVIOS-14203 | Phase5_【U625】【黑盒】【必现】【HVAC】当前是关闭/打开状态，语音关闭/打开，仍有信号下发 | Yunteng Jiang | Tested | 2023-02-28 02:21 | huan xu | Medium | Climate | TS
FCIVIOS-14202 | Phase5_【U625】【黑盒】【必现】【HVAC】语音“关闭自动模式”，TTS反馈“自动模式已关闭”，有信号下发 | Yunteng Jiang | Tested | 2023-02-28 02:18 | huan xu | Medium | Climate | TS
FCIVIOS-14201 | Phase5_【U625】【黑盒】【必现】【HVAC】语音“主副驾空调温度调到20度”，TTS反馈“主副驾调温度已调到20度” | Yunteng Jiang | Tested | 2023-02-28 02:11 | huan xu | Medium | Climate | TS
FCIVIOS-14199 | Phase5_【U625】【黑盒】【必现】【AAR】lancher界面AAR图标显示与UI图不致 | Chuanqin Chen | 待办 | 2023-02-28 01:47 | Liang Xiao | High | AAR | TS
FCIVIOS-14197 | Phase5_【U625】【黑盒】【必现】【AAR】分屏状态下，如果副驾已经打开了智能新风界面，主驾无法进入智能新风界面，与其他界面实现不一致，且提示框会一直在主驾上提示 | Chuanqin Chen | 待办 | 2023-02-28 01:39 | huan xu | High | AAR | TS
FCIVIOS-14196 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】多功能座椅点击座椅渲染图，界面出现座椅残影 | manyi guan | Tested | 2023-02-28 01:31 | manyi guan | High | Vehicle Settings | TS
FCIVIOS-14195 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】尾灯设置名称位置未跟随主题颜色适配 | manyi guan | 待办 | 2023-02-28 01:24 | manyi guan | High | Vehicle Settings | TS
FCIVIOS-14194 | Phase5_【U625】【黑盒】【必现】【AAR】1）语料“副驾打开智能新风”无法正常打开，2）唤醒副驾小度，语音输入后仍然主驾打开智能新风 | Chuanqin Chen | 待办 | 2023-02-28 01:20 | huan xu | High | AAR | TS
FCIVIOS-14187 | Phase5_【U625MCA】【必现】【Hotspot】里程数设置为小于16km，互联复位后，车载热点开关没有变为关闭状态 | chunming yang | Monitor | 2023-02-27 21:23 | chunming yang | High | WIR | TS
FCIVIOS-14173 | Phase5_【U625】【黑盒】【必现】【HVAC】当前在后排空调页面，点击空白区域退出空调，重新进入后仍在前排空调页面 | Yunteng Jiang | Tested | 2023-02-27 02:32 | huan xu | Medium | Climate | TS
FCIVIOS-14125 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】灯光设置里点击收藏后，切换功能选项 收藏又自动变为未收藏状态 | manyi guan | Tested | 2023-02-24 03:35 | manyi guan | High | Vehicle Settings | TS
FCIVIOS-14120 | Phase5_【U625MCA】【必现】【WIR】连接第二个wifi后，忽略第二个wifi，不会重新连接第一个wifi | chunming yang | Rejected | 2023-02-24 01:22 | Dapeng Liu | High | WIR | TS
FCIVIOS-14119 | Phase5_【U625MCA】【黑盒】【必现】【Vehicle Settings】巡航控制的容限入口处不显示对应的数值 | manyi guan | Tested | 2023-02-24 01:01 | manyi guan | High | Vehicle Settings | TS
APIMCIM-18951 | Phase5_【U625】【CarInput】【偶现】【黑盒】蓝牙音乐播放中，来回多次快速按下硬按键调节audio off/on，on状态下蓝牙音乐不播放 | guangdong yuan | 待办 | 2023-02-24 02:26 | Hang Liu | High | Hardbutton | YF
APIMCIM-18886 | Phase5_【U625MCA】【黑盒】【偶现】【Monkey】【Vehicale settings】monkey测试中 com.yfve.settings发生Crash | wendi Xiao | Test | 2023-03-01 21:41 | Zihao Qiu | High | Vehicle Setting | YF
APIMCIM-18885 | Phase5_【U625MCA】【黑盒】【偶现】【Monkey】【Vehicale settings】monkey测试中 com.yfve.settings发生内存泄漏 | wendi Xiao | 待办 | 2023-03-02 21:30 | Wang Qian | High | Vehicle Setting | YF
APIMCIM-18814 | [U625MCA][Phase5][联合驾趣]发送灯光信号后，需要刷新页面后才显示 | Qian Yang | Test | 2023-03-03 04:06 | Qian Yang | High | Codrive | TS
APIMCIM-18792 | Phase5_【U625】【黑盒】【必现】【AAR】“取消/切换/外部的空气质量较好，你想换到外循环模式吗？”用户语音回复”切换“无法正常收音 | Chuanqin Chen | Test | 2023-03-03 02:39 | Chuanqin Chen | High | Auto Air Refresh | TS
APIMCIM-18783 | Phase5_【U625】【黑盒】【偶现】【EnhanceMemory】创建档案时偶现闪退，无法进入档案页面 | Yunteng Jiang | 待办 | 2023-03-03 01:45 | Li Sun | Medium | Enhanced Memory | Ford
APIMCIM-18781 | Phase5_【U625】【黑盒】【必现】【EnhanceMemory】创建中挂非p档，挂回p档后第一次点击个性化档案入口仍提示非p档弹窗，第二次点击可进入 | Yunteng Jiang | 待办 | 2023-03-03 01:33 | Li Sun | Medium | Enhanced Memory | Ford
APIMCIM-18778 | Phase5_【U625MCA】【黑盒】【偶现】【launcher】点击常用栏所有应用图标无反应 | wendi Xiao | Awaiting implementation (migrated) | 2023-03-03 01:39 | Wang Qian | High |  | YF
APIMCIM-18775 | Phase5_【U625MCA】【黑盒】【必现】【VHA】进入地图导航到远距离，进入vha点击查找附近加油站，退出远距离导航，再次进入vha界面仍显示续航里程不足 | wendi Xiao | 待办 | 2023-03-03 01:11 | Niu Tian | High |  | Baidu
APIMCIM-18710 | Phase5_【U625MCA】【黑盒】【必现】【System Setting】偶现系统卡死现象，随心听和车辆设置均打不开 | zhaomin huang | 待办 | 2023-03-02 03:05 | Yang Hou | Gating | System Setting | YF
APIMCIM-18653 | [U625MCA][必现][relaxMode]语音“打开森林绮境”，TTS播报：“网络未连接” | Hailang Liu | Test | 2023-03-01 04:08 | Cheng Pu | High | Relax Mode | Baidu
APIMCIM-18648 | Phase5_【U625MCA】【偶现】【FNV】FNV诊断中上传日志到云端，有概率无法连接云端，报503 | chunming yang | 待办 | 2023-03-01 03:22 | Xinming Xiao | Gating | FNV | Ford
APIMCIM-18544 | Phase5_【U625】【必现】【MMOTA】VI升级SYNC+激活失败后通知中心无弹窗提示“更新失败” | zhangjian zhou | 正在进行 | 2023-02-28 01:47 | zhangjian zhou | High | MMOTA | TS
APIMCIM-18538 | Phase5_【U625】【必现】【MMOTA】VI升级SYNC+和MCU必现ECG_log报E2130,无法激活成功 | zhangjian zhou | 正在进行 | 2023-02-28 00:57 | Rugang Huang | Gating | MMOTA | YF
APIMCIM-18528 | Phase5_【U625MCA】【Monkey】【Vehicle Settings】执行monkey过程中，com.yfve.settings发生一次ANR | manyi guan | 待办 | 2023-02-27 21:44 | Wang Qian | High | Vehicle Setting | YF