## RL-Revision-History
Release Note Change Record History
Version Number | Release Date | Author | Reviewer | Approver | Content Changes

## Release Content
Software Release Information List |  |  |  | 1. 各方需要提供该格式的release note； 2. 集成方需要整合各方的release content，Fixex Bug list，Open Bug List 的内容； 3. Release note的内容准确性由各个开发方的PM&SWQ来保证，Ford方的System Integration Manager&SWQ 来检查 4. Release note 版本号： After Integration Completed 1.* After Supplier Test Completed 2.* REC(End To End) Test Completed 3.*
Software Release Information Description
Prepared By |  |  | Reviewed By:
Date
Software Version Information
SOC SW Version |  | 示例： SOC User：20230417_0903_CF15_R13.1.PRO.HF1_User SOC Debug：20230417_0903_CF15_R13.1.PRO.HF1_Debug FNV：dueros_SU3_A8.1-bin-1.0.8.62_20220812
General Info |  | SOC SW P/N | 示例： MZ8T-14H379-AM
|  | Main board HW Version | 示例： HW012
|  | MCU SW Version | 示例： MCU：20221212_564_PRO
|  | MCU SW P/N | 示例： MZ8T-14H361-AN
|  | Checksum | 示例：只针对集成后的软件包,有几个软件包就需要有相应数量的checksum a5264b54665725c8dd58ae9dee16c30a or other
Software Release Content
Release Content | 新增功能 | 1、语音: 更新中高配语音模型 2、地图: 经过TDR决议合入LTS版本 3、地图: DCR-U625多屏互动需求 4、签约管理: DCR-Phase5 签约增加主题适配 5、随心听: DCR-随心听多屏互动需求，包括方向盘按键反控，媒体信息传递，后排屏功能 6、语音/车机管家: 依据云听配置位区分语音云听相关指令和云听APP权限管理入口显示/隐藏
| 完善功能 | 1、语音: 合入语音优化：*分屏需求 *可见即可说 *联系人优化
| BUG修复 | bugfix 清单见 《Fixed Bug List》sheet 和 《Change Scope》sheet
| 设计调整 | 暂无
| 遗留问题 | 详见 《Open Bug List》sheet
Software Release Conlusion
针对该版本发布的结论： 1.从计划实现功能的角度，是否有偏差，计划实现需求多少，实际实现需求多少； 2.该版本的测试结论； 3.目前Bug 情况，是否满足该节点的要求； 4.本版本的限制条件以及limitation； 5.从Metrics 的角度，该版本的风险项以及mitigation计划；

## Change Scope
R05 修改范围: 9.4 - 10.17 提交到master分支+R05分支的合入修改
模块 | 类型 | 编号 | 描述 | 合入延峰仓库链接 | 测试结果 | 需求来源和合入版本说明
Account | bugfix | APIMCIM-30077 | [U625MCA][100%]Vehicle information, fill in the wrong license plate, click save, prompt error | http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68173(http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68173) http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68430(http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68430) http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68701(http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68701) http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68711(http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68711) http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/AudioPlayer/+/68046(http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/AudioPlayer/+/68046) http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/AudioPlayer/+/68402(http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/AudioPlayer/+/68402) http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/VideoPlayer/+/68146(http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/VideoPlayer/+/68146) http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/VideoPlayer/+/68407(http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/VideoPlayer/+/68407) http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68700(http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/68700) http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/69447(http://222.190.133.163:8090/c/android/project/ford_phase5/prebuilts/HY11/baidu/+/69447) http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/AudioPlayer/+/69426 http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/VideoPlayer/+/69435 http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/AudioPlayer/+/69425 http://222.190.133.163:8090/c/android/project/ford_phase5/U625MCA/packages/apps/VideoPlayer/+/69420 | Pass
Account | bugfix | APIMCIM-30067 | [U625MCA][100%]The personal center enters the vehicle information page, and the back button in the upper left corner will move |  | Pass
Account | bugfix | APIMCIM-25186 | [HMI WALK-THROUGH][U625MCA][100%]The style of the error message is incorrect |  | Pass
Account, IOT | bugfix | APIMCIM-30941 | [U625MCA][100%]Baidu account authorization copy error |  | Pass
Account, System Stability | bugfix | APIMCIM-29063 | Phase 5:【AutoTest】Monkey测试20h，出现2次包名为com.baidu.iov.faceos的CRASH异常 |  | Pass
BT Music | bugfix | APIMCIM-29909 | 【Phase5】【U625MCA】VID_20230904_144707播放蓝牙音乐，蓝牙音乐app和launcher的显示转接图片不一致 |  | Pass
BT Setting, Input | bugfix | APIMCIM-28656 | Phase 5：【必现】点击键盘上任意内容，气泡中的字符没有放大效果 |  | Pass
Disclaimer | bugfix | APIMCIM-22440 | [U625MCA][100%]副驾打开百度系应用，主驾出现百度协议 |  | Pass
Himalaya | bugfix | APIMCIM-31040 | [U625MCA][100%]Tapping PLAY icon is no response in Suixinting card when the current program needs to be paid. |  | Pass
Himalaya | bugfix | APIMCIM-30952 | [U625MCA][100%]My account UI is loading all the time after turned off CCS. |  | Pass
Himalaya | bugfix | APIMCIM-29680 | [U625MCA][100%] The scrolling effect isn't applied to the title. |  | Pass
Himalaya | bugfix | APIMCIM-29270 | [U625MCA][100%] The purchased program is still locked after paying the program in purchase history. |  | Pass
Himalaya | bugfix | APIMCIM-26577 | [U625MCA][100%] IVI pops up "network error" after tapping the "Purchase" button. |  | Pass
Himalaya | bugfix | APIMCIM-24745 | [U625MCA][100%] IVI displays "Fail to load" after tapping "Buy" button in the purchased album. |  | Pass
Himalaya | bugfix | APIMCIM-22300 | [U625MCA][100%] No TTS broadcasts user to buy VIP after tapping the play button on suixinting card. |  | Pass
Input | bugfix | APIMCIM-30697 | 【Monkey自动化测试】【福特Phase5 U625】进程com.baidu.car.input出现了java.lang.RuntimeException: InputChannel is not initialized., 具体位置在None |  | Pass
Input | bugfix | APIMCIM-30311 | [U625MCA][100%]Input method voice input background is wrong |  | Pass
Launcher | bugfix | APIMCIM-20882 | [U625MCA][100%]所有应用页面百度应用图标问题 |  | Pass
Launcher - Weather forecast | bugfix | APIMCIM-30574 | [U625MCA][100%]There should not be a white line on the left |  | Pass
Launcher - Weather forecast | bugfix | APIMCIM-30322 | [U625MCA][100%]The weather page is missing a mask on the right side |  | Pass
Launcher - Weather forecast | bugfix | APIMCIM-30321 | [U625MCA][100%]Weather background color is inconsistent with UI |  | Pass
Launcher - Weather forecast, System Stability | bugfix | APIMCIM-29055 | Phase 5:【AutoTest】Monkey测试20h，出现1次包名为com.baidu.xiaoduos.weather的ANR异常 |  | Pass
Launcher, Music | bugfix | APIMCIM-30287 | [U625MCA][100%]Clearing all recent apps for the co-pilot should not affect the co-pilot |  | Pass
LHI, Map&Navigation | bugfix | APIMCIM-29081 | [U625MCA][80%]Recording and reporting event failed |  | Pass
Map&Navigation | bugfix | APIMCIM-30700 | 【必现】【u625】【widget】1104 widget卡点显示全白，实际地图底图已经加载 |  | Pass
Map&Navigation | bugfix | APIMCIM-30699 | 【福特phase5 U625】【地图-签约管理】取消协议签约之后点击地图，地图没有拉起签约页面 |  | Pass
Map&Navigation | bugfix | APIMCIM-29521 | Phase 5：【必现，FO签收发生】 导航进入地下车库内，车标未跟随车头方向改变 |  | Pass
Map&Navigation | bugfix | APIMCIM-30703 | 【必现】【埋点】1707最后一公里，未打印全屏 |  | Pass
Map&Navigation | bugfix | APIMCIM-30701 | 【必现】【算路】1736熟路模式中，无法修改组队目的地，点击后添加按钮后，底图拖拽 |  | Pass
Map&Navigation | bugfix | APIMCIM-30686 | [U625MCA][100%]The simulated navigation page is inconsistent with the UI |  | Pass
Map&Navigation | bugfix | APIMCIM-30681 | [U625MCA][100%]The search page along the way in navigation is inconsistent with the UI |  | Pass
Map&Navigation | bugfix | APIMCIM-30667 | [U625MCA][100%]Favorites rename page is inconsistent with UI |  | Pass
Map&Navigation | bugfix | APIMCIM-30665 | [U625MCA][100%]The favorites editing state is inconsistent with the UI |  | Pass
Map&Navigation | bugfix | APIMCIM-30658 | [U625MCA][100%]The personal toolbox page is inconsistent with the UI |  | Pass
Map&Navigation | bugfix | APIMCIM-29543 | CLONE - 【必现】【widget】1117 重启车机或者杀掉地图，首次点击widget的回家按钮无反应，需要点击第二次才行 |  | Pass
Map&Navigation | bugfix | APIMCIM-29498 | Phase 5：【必现，FO签收发生】 导航态，终点连接线太粗（必现） |  | Pass
Map&Navigation | bugfix | APIMCIM-29119 | Phase 5：【必现】 模拟导航中，暂停按钮不正确 |  | Pass
Map&Navigation | bugfix | APIMCIM-29118 | Phase 5：【必现】副驾侧导航结束卡片上没有实景图 |  | Pass
Map&Navigation | bugfix | APIMCIM-29110 | Phase 5：【必现】队员收到队长更改目的地后确认，路况条超出TBT面板 |  | Pass
Map&Navigation | bugfix | APIMCIM-29108 | Phase 5：【必现】我的队伍界面，未设置终点时，定位icon过大 |  | Pass
Map&Navigation | bugfix | APIMCIM-29106 | Phase 5：【必现】系统设置中提示音量调节到最低，导航中不显示静音icon |  | Pass
Map&Navigation | bugfix | APIMCIM-29104 | Phase 5：【必现】合作模式下副驾侧音量值显示不清晰 |  | Pass
Map&Navigation | bugfix | APIMCIM-28999 | Phase 5：【必现】语音说“关闭导航声音”，进入导航音量查看之后，再退出音量页面，音量图标显示错误 |  | Pass
Map&Navigation | bugfix | APIMCIM-28998 | Phase 5：【必现】队长更换目的地后，车机端取消更换目的地，ETA面板显示异常 |  | Pass
Map&Navigation | bugfix | APIMCIM-28996 | Phase 5：【必现】合作模式下，组队出行页面的地址栏主副驾两边显示不一致 |  | Pass
Map&Navigation | bugfix | APIMCIM-28972 | Phase 5：【必现】我的队伍里调起输入框后，蒙层也可以继续点击并响应操作 |  | Pass
Map&Navigation | bugfix | APIMCIM-28941 | Phase 5：【必现】熟路导航到达目的地后，弹出toast”已抵达目的地，即将退出路线雷达” |  | Pass
Map&Navigation | bugfix | APIMCIM-28923 | Phase 5：【必现，FO签收发生】 巡航模式，固定按钮选项和边框间隔过大 |  | Pass
Map&Navigation | bugfix | APIMCIM-28922 | Phase 5：【必现，FO签收发生】 巡航模式，固定按钮选项和边框间隔过大 |  | Pass
Map&Navigation | bugfix | APIMCIM-28917 | Phase 5：【偶现，FO签收发生】结束卡片，副驾侧无图片（偶现） |  | Pass
Map&Navigation | bugfix | APIMCIM-28886 | Phase 5：【必现】导航设置中无隐私设置开关 |  | Pass
Map&Navigation | bugfix | APIMCIM-28883 | Phase 5：【必现】离线地图下载界面，进度条显示不正确 |  | Pass
Map&Navigation | bugfix | APIMCIM-28870 | Phase 5：【必现，FO签收发生】14-11 语音关闭导航播报，音量图标状态未同步 |  | Pass
Map&Navigation | bugfix | APIMCIM-28867 | Phase 5：【偶现】从算路界面返回，详情页显示错误 |  | Pass
Map&Navigation | bugfix | APIMCIM-28864 | Phase 5：【必现】周边搜4S店，搜索结果不显示福特logo |  | Pass
Map&Navigation | bugfix | APIMCIM-28857 | Phase 5：【必现】模拟导航里面，暂停/继续的图标没有转换 |  | Pass
Map&Navigation | bugfix | APIMCIM-28852 | Phase 5：【必现】地址检索页面，点击地址下面公里数的区域，则再去点击地址名，无法发起算路 |  | Pass
Map&Navigation | bugfix | APIMCIM-28849 | Phase 5：【必现】收藏夹中，长按删除收藏的地址，保存后退出再进入收藏夹页面，刚才删除的地址又恢复至收藏夹中 |  | Pass
Map&Navigation | bugfix | APIMCIM-28835 | Phase 5：【必现，FO签收发生】调整导航音量，音量数字显示位置错误 |  | Pass
Map&Navigation | bugfix | APIMCIM-28833 | Phase 5：【必现】在导航设置中调节音量，音量小部件依然显示静音 |  | Pass
Map&Navigation | bugfix | APIMCIM-28827 | Phase 5：【必现】地图卡片上的GPS信号显示不正确 |  | Pass
Map&Navigation | bugfix | APIMCIM-28810 | Phase 5：【必现】移除队友后，界面显示不正确 |  | Pass
Map&Navigation | bugfix | APIMCIM-28698 | Phase 5：【必现】合作模式下，副驾位置的音量值在框体外面，跟主驾不一致 |  | Pass
Map&Navigation | bugfix | APIMCIM-28697 | Phase 5：【偶发】合作模式下，设置里的小地图模式的框体变大 |  | Pass
Map&Navigation | bugfix | APIMCIM-28688 | Phase 5：【必现】事件上报页面，录音之后点击停止，会自动退出事件上报页面 |  | Pass
Map&Navigation | bugfix | APIMCIM-28687 | Phase 5：【必现】事件上报页面，点击输入框，不会直接调起输入法键盘 |  | Pass
Map&Navigation | bugfix | APIMCIM-28680 | Phase 5：【偶发】 POI详情页，信息显示不完整 |  | Pass
Map&Navigation, VR | bugfix | APIMCIM-28860 | Phase 5：【必现】“先去这”按钮文字溢出 |  | Pass
Map&Navigation, VR | bugfix | APIMCIM-28845 | Phase 5：【必现】无法语音切换至提示音播报模式 |  | Pass
Message Center | bugfix | APIMCIM-30659 | [U625MCA][100%]History message page, delete successful toast box too small |  | Pass
Message Center | bugfix | APIMCIM-25479 | [HMI WALK-THROUGH][U625MCA][100%]The message center icon and height display are inconsistent with the design |  | Pass
Message Center, System Setting | bugfix | APIMCIM-29124 | Phase 5：【必现】历史消息app，点击“设置”无任何反应 |  | Pass
Mini App | bugfix | APIMCIM-31084 | [U625MCA][100%]QRcode payment page crash in splash screen when move it from main driving screen to co-pilot screen |  | Pass
Mini App | bugfix | APIMCIM-31081 | [U625MCA][100%]Black screen when calling in movie ticket payment page |  | Pass
Mini App | bugfix | APIMCIM-30908 | [U625MCA][100%]NO gas station information or display one first and display another one after clicking back button when clicking two gas stations together in select gas station page |  | Pass
Mini App | bugfix | APIMCIM-30497 | 【U625】【必现】【服务生态】在电影购票点击搜索框，没有弹出输入键盘 |  | Pass
Mini App | bugfix | APIMCIM-30375 | [U625MCA][100%]The co-pilot can seize the mini app opened by the main driver at any time, and prompts the toast text color to be dark |  | Pass
Mini App | bugfix | APIMCIM-30109 | [U625MCA][100%]Mini app - movie, the payment page pops up to the main driver |  | Pass
Mini App | bugfix | APIMCIM-30091 | [U625MCA][100%]The recently used/my favorites page has no return function, and the layout is inconsistent with the UI. |  | Pass
Mini App | bugfix | APIMCIM-28820 | [U625MCA][25%]Smart parking click to authorize without response |  | Pass
Music | bugfix | APIMCIM-31338 | 【phase5】【U625】【随心听】歌曲播放界面，点击音频设置，再点击左上角返回随心听，返回的是随心听首页不是播放页面 |  | Pass
Music | bugfix | APIMCIM-30599 | [U625MCA][100%]QQ Music deletes songs missing Toast prompt |  | Pass
Music | bugfix | APIMCIM-30594 | [U625MCA][100%]The font color should be white when songs are not checked in QQ music batch editing |  | Pass
Music | bugfix | APIMCIM-30593 | [U625MCA][100%]There are currently no songs in the qq music playlist the prompt is inconsistent with the UI |  | Pass
Music | bugfix | APIMCIM-30589 | [U625MCA][100%]The Himalayan double speed selection page lacks scroll bars |  | Pass
Music | bugfix | APIMCIM-30588 | [U625MCA][100%]Himalayan unsubscribe Toast is inconsistent with UI |  | Pass
Music | bugfix | APIMCIM-30582 | [U625MCA][100%]Ximalaya logout pop-up button is inconsistent with the UI |  | Pass
Music | bugfix | APIMCIM-30581 | [U625MCA][100%]Ximalaya code scanning login page overlaps when there is no network |  | Pass
Music | bugfix | APIMCIM-30580 | [U625MCA][100%]The light effect of Himalayan News should follow the movement of the progress bar |  | Pass
Music | bugfix | APIMCIM-30498 | 【U625】随心听分屏边界处有字时异常高亮显示 |  | Pass
Music | bugfix | APIMCIM-29873 | [U625MCA][100%]When playing music, the launcher card display is inconsistent with the UI |  | Pass
Music | bugfix | APIMCIM-29628 | Phase 5：【必现】QQ音乐播放器进入声音设置页面，左上角返回，没有返回播放器 |  | Pass
Music | bugfix | APIMCIM-28891 | Phase 5：【必现】喜马拉雅/QQ音乐无法播放，无任何toast提示 |  | Pass
Music | bugfix | APIMCIM-26252 | Phase 5：【必现】QQ音乐刷新页面时，刷新成功/失败没有任何提示 |  | Pass
Music | bugfix | APIMCIM-22433 | Phase 5：【必现】全局免唤醒：上一首/下一首。TTS错误 |  | Pass
Music, VR | bugfix | APIMCIM-28961 | Phase 5：【偶现】副驾语音唤醒“上一曲/下一曲”切换主驾的音乐 |  | Pass
Payment | bugfix | APIMCIM-30331 | [U625MCA][100%]Scanning the QR code to pay for Ximalaya membership purchases by the passenger driver should not appear in the main driver’s window |  | Pass
Payment | bugfix | APIMCIM-30330 | [U625MCA][100%]The main driver’s Himalayan payment page should be moved to the co-driver’s page and should not disappear |  | Pass
Smart Scene | bugfix | APIMCIM-31062 | [U625MCA][smartscene]个人时光，进入随心看再返回个人时光，页面出现闪烁 |  | Pass
System Setting, VR | bugfix | APIMCIM-30625 | [U625MCA][100%]Personalized voice broadcast help page slider cannot be completed |  | Pass
System Setting, VR | bugfix | APIMCIM-30624 | [U625MCA][100%]The personalized voice broadcast page slider cannot be completed |  | Pass
User Privacy | bugfix | APIMCIM-30069 | [U625MCA][100%]Signed agreement page, incorrect title |  | Pass
User Privacy | bugfix | APIMCIM-30052 | [U625MCA][100%]Split screen, protocol content is not fully displayed |  | Pass
Video | bugfix | APIMCIM-30696 | 【随心看】未登录车机账号的状态下，语音点播『我要看小猪佩奇』进入随心看首页一直显示加载状态 |  | Pass
Video | bugfix | APIMCIM-30695 | 【U625】【随心看】【分屏语音】副驾搜索结果界面，主驾语音：我要看莲花楼，副驾播放视频，实际应该是主驾播放（另外，主驾搜索结果界面，副驾语音播放，主驾视频播放） |  | Pass
Video | bugfix | APIMCIM-30694 | 【爱奇艺】登录VIP爱奇艺账号，点击个人中心的退出账号，提示退出失败（15：21左右） |  | Pass
Video | bugfix | APIMCIM-30690 | 【爱奇艺】副驾侧连接蓝牙耳机，主驾侧播放爱奇艺后移屏到副驾侧，依旧功放播放 |  | Pass
Video | bugfix | APIMCIM-30689 | 【爱奇艺】副驾驶有人，车速大于5KM，分屏副驾侧播放随心看时取消分屏，无法取消如视频（17：00左右） |  | Pass
Video | bugfix | APIMCIM-31071 | Phase 5：【必现】随心看时，点击常驻栏的all app图标，闪屏 |  | Pass
Video | bugfix | APIMCIM-30882 | [U625MCA][100%]When iQiyi plays a video, the progress bar should not be dragged when sliding with three fingers to move the screen |  | Pass
Video | bugfix | APIMCIM-30867 | Phase 5：【必现】随心看点击个人中心，会员头像显示错误 |  | Pass
Video | bugfix | APIMCIM-30855 | Phase 5：【必现】爱奇艺/小视频播放时，滑动亮度调节，不能到最大值 |  | Pass
Video | bugfix | APIMCIM-30827 | Phase 5：【必现】播放爱奇艺视频，开始播放时视频右侧会闪一下 |  | Pass
Video | bugfix | APIMCIM-30777 | Phase 5：【必现】随心看的提示应该显示错误“登录福特（派）帐号解锁在线视频” |  | Pass
Video | bugfix | APIMCIM-30635 | [U625MCA][100%]Brightness volume adjustment light effect is wrong |  | Pass
Video | bugfix | APIMCIM-30623 | [U625MCA][100%]Variety show playlist page lacks scroll bar |  | Pass
Video | bugfix | APIMCIM-30618 | [U625MCA][100%]Immersive mode should not show the resident bar |  | Pass
Video | bugfix | APIMCIM-30613 | [U625MCA][100%]The IQIYI trial end page is inconsistent with the UI |  | Pass
Video | bugfix | APIMCIM-30605 | [U625MCA][100%]The title size of the IQIYI voice search results page is inconsistent with the UI |  | Pass
Video | bugfix | APIMCIM-30604 | [U625MCA][100%]IQIYI did not find the relevant video page and the UI is inconsistent |  | Pass
Video | bugfix | APIMCIM-30319 | [U625MCA][100%]iQiyi input content should not overlap with the search box |  | Pass
Video | bugfix | APIMCIM-28774 | Phase 5：【必现】随心看中，倍速的提示语不正确 |  | Pass
Video | bugfix | APIMCIM-28637 | Phase 5：【必现】点击首页随心听widget上的本地按钮，TTS会播报“好的” |  | Pass
Video | bugfix | APIMCIM-26900 | Phase 5：【必现】爱奇艺播放时，切R档，视频未暂停 |  | Pass
Video | bugfix | APIMCIM-26550 | Phase 5：【偶现】合作模式，点击随心听应用，不能进入 |  | Pass
Video | bugfix | APIMCIM-26527 | Phase 5：【必现】实车挂入R档，爱奇艺视频仍在播放 |  | Pass
Video | bugfix | APIMCIM-26524 | Phase 5：【偶现】爱奇艺收藏按钮偶现收藏不了 |  | Pass
Video | bugfix | APIMCIM-26381 | Phase 5：【必现】独立模式，爱奇艺源，点击收藏toast提示位置不一致 |  | Pass
Video | bugfix | APIMCIM-26371 | Phase 5：【必现】爱奇艺收藏按钮点击无反应 |  | Pass
Video | bugfix | APIMCIM-26310 | Phase 5 【必现】挂倒挡，随心看爱奇艺视频未暂停播放 |  | Pass
Video | bugfix | APIMCIM-22533 | Phase 5：【必现】独立模式，副驾唤醒语音：打开随心看，总是主驾侧打开随心看 |  | Pass
Video | bugfix | APIMCIM-22528 | Phase 5：【必现】独立模式，副驾点击爱奇艺不显示连接耳机弹窗，点击USB视频播放时显示 |  | Pass
Virtual Personal Assistant | bugfix | APIMCIM-29165 | [Phase5][U625MCA][VPA][必现]主驾唤醒展示swan卡片，副驾立刻软按键立刻唤醒语音，VPA形象异常 |  | Pass
Virtual Personal Assistant | bugfix | APIMCIM-29162 | [Phase5][U625MCA][VPA][必现]车牌限行城市切换查询，TTS播报未及时切换 |  | Pass
Virtual Personal Assistant | bugfix | APIMCIM-28974 | [U625MCA][100%] Voice help center is opened on driver's side by voice on co-driver's side |  | Pass
Virtual Personal Assistant | bugfix | APIMCIM-28971 | [U625MCA][100%] Extending listening time is incorrect( should be set to 20 seconds) |  | Pass
Virtual Personal Assistant | bugfix | APIMCIM-26383 | [U625MCA][100%] The Movie application is opened on Driver's side when VPA query on co-pilot side |  | Pass
Virtual Personal Assistant, VR | bugfix | APIMCIM-30953 | [Phase5][U625MCA][VPA][必现]语料“查看小狗的图片”指令不支持 |  | Pass
Virtual Personal Assistant, VR | bugfix | APIMCIM-28750 | [U625MCA][100%] VPA image display abnormal when waking up again and TTS broadcast is still continued after VPA exits. |  | Pass
VR | bugfix | APIMCIM-30809 | [U625MCA][100%] Any voice cannot be recognized after wake up VPA by pressing VPA icon |  | Pass
VR | bugfix | APIMCIM-31052 | Phase 5：【偶现】VR:半开遮阳帘。播报错误 |  | Pass
VR | bugfix | APIMCIM-30521 | 【U625-中配实车】【语音】10:20 语音：链接蓝牙；并未打开蓝牙开关 |  | Pass
VR | bugfix | APIMCIM-29007 | Phase 5：【必现】副驾唤醒语音后，语音会识别到语音自己说的话 |  | Pass
VR | bugfix | APIMCIM-28944 | Phase 5：【必现】小视频时，可见即可说有动效无效果 |  | Pass
VR | bugfix | APIMCIM-28815 | Phase 5：【必现】免唤醒：上一首/下一首。播报错误 |  | Pass
VR | bugfix | APIMCIM-28811 | Phase 5：【必现】所有应用界面，点击随心看-本地。播报：好的 |  | Pass
VR | bugfix | APIMCIM-27585 | 【U625MCA】【100%】【VR】分屏，主驾或副驾打开电子手册后，另一个屏语音打开电子手册，无法打开，TTS无反应 |  | Pass
VR | bugfix | APIMCIM-26539 | Phase 5：【必现】独立模式，主驾唤醒vr：我想看神探狄仁杰，响应在副驾播放视频 |  | Pass
VR | bugfix | APIMCIM-26530 | Phase 5：【偶现】语音会一直播放“好，音量调到2了” |  | Pass
语音 | bugfix | edc-scrum-113163 | 【UI走查】【625动效走查】【用户反馈】tips尺寸动效 |  | Pass
语音 | bugfix | edc-scrum-113160 | 【UI走查】【625动效走查】【用户反馈】list&icon涟漪，按钮按下缩小 |  | Pass
语音 | bugfix | edc-scrum-113129 | 【UI走查】【625动效走查】【个性化发音人】toast动效更改 |  | Pass
语音 | bugfix | edc-scrum-112841 | 【UI走查】【U625MCA】【智能家居】toast动效错误问题 |  | Pass
语音 | bugfix | edc-scrum-111566 | 【badcase】【U625-中配实车】【语音】14:03 “切换「新贵佳人」的声音”不支持，其他发音人可支持此指令 |  | Pass
语音 | bugfix | edc-scrum-111560 | APIMCIM-30521【U625-中配实车】【语音】10:20 语音：链接蓝牙；并未打开蓝牙开关 |  | Pass
语音 | bugfix | edc-scrum-109505 | 【625】【语音】【车控】座椅通风&温度上下文，文字上屏拒识 |  | Pass
语音 | bugfix | edc-scrum-87478 | 【UI走查】【U625】【智能家居】R00版本toast位置和样式问题需全局修复 |  | Pass
支付及订单 | bugfix | edc-scrum-112840 | 【UI走查】【U625MCA】【支付】toast动效错误问题 |  | Pass
支付及订单 | bugfix | edc-scrum-109786 | 【福特phase5 U625】【支付】随心听语音所见既可说和手动购买偶现支付二维码拉起过程闪退到购买详情页面 |  | Pass
支付及订单 | bugfix | edc-scrum-109293 | 【福特phase5 U6】【支付】分屏模式下，主副驾分别点击不同应用拉起支付二维码页面，最后拉起的一侧页面闪退 |  | Pass
支付及订单 | bugfix | edc-scrum-109283 | 【福特phase5 U6】【支付】分屏模式下主副驾分别点击相同应用拉起支付页面，最后拉起支付页面一侧支付二维码页面闪退 |  | Pass
支付及订单 | bugfix | edc-scrum-109081 | 【福特phase5 U6】【支付】主驾或者副驾支付二维码页面，点击移屏之后页面闪退 |  | Pass
支付及订单 | bugfix | edc-scrum-74254 | 【福特phase5 U6XX】【支付】副驾屏下单支付主驾拉起支付二维码页面，投屏到副驾直接退出并提示失败 |  | Pass
随心听 | bugfix | edc-scrum-114696 | 【625】【随心听】【必现】QQ音乐首页唤醒语音说：个人中心，跳转的是福特账号的个人中心 |  | Pass
随心听 | bugfix | edc-scrum-114036 | 【625】【随心听】【必现】播放QQ音乐点击音效再点击左上角随心听回到随心听页面，点击清空。UI页面异常显示 |  | Pass
随心听 | bugfix | edc-scrum-113684 | 【随心看】主驾侧拉起随心看签约页面，移屏到副驾侧后再次拉起主驾侧随心听，签约完成后未进入随心听应用 |  | Pass
随心听 | bugfix | edc-scrum-113676 | 【随心看】副驾点击随心看签约页面移屏到主驾侧后点击副驾侧随心听应用无法拉起签约页面，如视频 |  | Pass
随心听 | bugfix | edc-scrum-113561 | 【625】【随心听】【必现】QQ音乐首页，唤醒语音说个人中心跳转到了账号的个人中心 |  | Pass
随心听 | bugfix | edc-scrum-111393 | 【随心听】分屏模式下，主驾侧播放随心看，副驾播放随心听并分享音乐到主驾侧，待主驾播放时取消分屏后重新分屏分享音乐，没有弹toast |  | Pass
随心听 | bugfix | edc-scrum-110089 | 【625】【随心听】【必现】1、主驾播放前台播放爱奇艺 2、副驾播放蓝牙耳机随心听-QQ音乐 3、副驾唤醒“打开播放历史”，随心听没有响应爱奇艺去响应了 |  | Pass
随心听 | bugfix | edc-scrum-109365 | 【Phase5】【U625】【随心听】随心听播放歌曲中偶现闪退 15:20 |  | Pass
随心听 | bugfix | edc-scrum-101732 | 31338【phase5】【U625】【随心听】歌曲播放界面，点击音频设置，再点击左上角返回随心听，返回的是随心听首页不是播放页面 |  | Pass
随心听 | bugfix | edc-scrum-92293 | 【U625】【随心听】快捷面板倒影是默认图片 |  | Pass
输入法 | bugfix | edc-scrum-112844 | 【UI走查】【U625MCA】【输入法】toast动效错误问题 |  | Pass
输入法 | bugfix | edc-scrum-109668 | 30697【Monkey自动化测试】【福特Phase5 U625】进程com.baidu.car.input出现了java.lang.RuntimeException: InputChannel is not initialized., 具体位置在None |  | Pass
爱奇艺 | bugfix | edc-scrum-112039 | 【爱奇艺】副驾侧蓝牙耳机播放，移屏到主驾侧依旧蓝牙耳机播放 |  | Pass
爱奇艺 | bugfix | edc-scrum-112035 | 【爱奇艺】分屏模式下，副驾侧连接蓝牙耳机，主驾侧播放后副驾侧先功放后才切蓝牙耳机播放且副驾画音不同步（11：16左右） |  | Pass
爱奇艺 | bugfix | edc-scrum-111583 | 【爱奇艺】主驾点播：我要看莲花楼，弹框提示连接蓝牙耳机弹框，此时点击副驾侧随心看可以双开 |  | Pass
爱奇艺 | bugfix | edc-scrum-110961 | 【爱奇艺】进入个人中心点击登录，提示二维码失效，点击刷新后提示登录失败，如视频 |  | Pass
爱奇艺 | bugfix | edc-scrum-110774 | 【爱奇艺】副驾播放爱奇艺点击倍速切换0.75、1倍速，toast弹框提示文案不全 |  | Pass
爱奇艺 | bugfix | edc-scrum-109959 | 30689【爱奇艺】副驾驶有人，车速大于5KM，分屏副驾侧播放随心看时取消分屏，无法取消如视频（17：00左右） |  | Pass
爱奇艺 | bugfix | edc-scrum-109935 | 【爱奇艺】多个车机登录一个账号，进入爱奇艺VIP视频提示『同一VIP账号同一时刻只能在一台车机上观看VIP视频』点击返回后再次进入，反复多次，视频声音流出，页面依旧拦截提示（16：00左右） |  | Pass
爱奇艺 | bugfix | edc-scrum-109891 | 【U625】【随心看】【分屏语音】随心看未打开，副驾唤醒我要看莲花楼，主驾打开随心看，实际应该是副驾打开 |  | Pass
爱奇艺 | bugfix | edc-scrum-109883 | 30694【爱奇艺】登录VIP爱奇艺账号，点击个人中心的退出账号，提示退出失败（15：21左右） |  | Pass
爱奇艺 | bugfix | edc-scrum-109882 | 【U625】【随心看】【分屏语音】车速大于5，副驾播放视频，主驾语音打开随心看，主驾视频播放安全弹框提示，但是此时视频继续播放未暂停 |  | Pass
爱奇艺 | bugfix | edc-scrum-109788 | 30690【爱奇艺】副驾侧连接蓝牙耳机，主驾侧播放爱奇艺后移屏到副驾侧，依旧功放播放 |  | Pass
爱奇艺 | bugfix | edc-scrum-109729 | 30695【U625】【随心看】【分屏语音】副驾搜索结果界面，主驾语音：我要看莲花楼，副驾播放视频，实际应该是主驾播放（另外，主驾搜索结果界面，副驾语音播放，主驾视频播放） |  | Pass
爱奇艺 | bugfix | edc-scrum-109133 | 【U625】【偶现一次】20:35 副驾爱奇艺前台播放视频，主驾唤醒打开随心看，TTS播报后播放QQ音乐 |  | Pass
爱奇艺 | bugfix | edc-scrum-109103 | 【625】爱奇艺冷启动实车超过6S（冷启动响应时间平均7.45S） |  | Pass
爱奇艺 | bugfix | edc-scrum-109060 | 【爱奇艺】语音点播我想看【神探狄仁杰】/【小猪佩奇】，点击返回有的回到爱奇艺首页，有的回到语音搜索结果页面 |  | Pass
爱奇艺 | bugfix | edc-scrum-109053 | 【爱奇艺】爱奇艺首页语音『我想看神探狄仁杰』，TTS回复为您播放神探狄仁杰第三季第一集，实际进入了语音搜索结果页面，如视频 |  | Pass
爱奇艺 | bugfix | edc-scrum-109049 | 30696【随心看】未登录车机账号的状态下，语音点播『我要看小猪佩奇』进入随心看首页一直显示加载状态 |  | Pass
爱奇艺 | bugfix | edc-scrum-109024 | 【U625】【随心看】独立模式下，主驾唤醒“我要看莲花楼”，不能进入播放页面 |  | Pass
爱奇艺 | bugfix | edc-scrum-108721 | 【U625】【U611】【随心看】【百度埋点】从全屏切换到分屏时，点击主屏爱奇艺/小视频tab，attach信息仍显示的全屏 |  | Pass
爱奇艺 | bugfix | edc-scrum-106158 | 【UI走查】【U625MCA】【爱奇艺】按钮无缩放效果问题 |  | Pass
小程序 | bugfix | edc-scrum-141903 | 【U625】【服务生态】【必现】在副驾打开小程序，副驾移屏到主驾，小程序闪退 |  | Pass
小程序 | bugfix | edc-scrum-109469 | 30497【U625】【必现】【服务生态】在电影购票点击搜索框，没有弹出输入键盘 |  | Pass
小程序 | bugfix | edc-scrum-108752 | 【U625】【服务生态】【必现】打开智慧加油，语音：向左滑/向右滑，页面没有反应 |  | Pass
小程序 | bugfix | edc-scrum-108610 | 【U625】【服务生态】【偶现】系统切换主题设置，进到小程序广场，一直显示加载中 |  | Pass
签约管理 | bugfix | edc-scrum-112839 | 【UI走查】【U625MCA】【签约管理】toast动效错误问题 |  | Pass
安全 | bugfix | edc-scrum-113170 | 【UI走查】【625动效走查】【智能安全管家】动效 |  | Pass
安全 | bugfix | edc-scrum-88631 | 【UI走查】【625第二轮走查】【智能安全管家】优化球文字间距、list投影、文字颜色 |  | Pass
安全 | bugfix | edc-scrum-88625 | 【UI走查】【625第二轮走查】【智能安全管家】蒙层颜色、渐隐更改 |  | Pass
安全 | bugfix | edc-scrum-88622 | 【UI走查】【625第二轮走查】【智能安全管家】由于状态栏更改，全局移动 |  | Pass
bug-地图 | bugfix | FordPhase4Scrum-74447 | 30699【福特phase5 U625】【地图-签约管理】取消协议签约之后点击地图，地图没有拉起签约页面 |  | Pass
bug-地图 | bugfix | FordPhase4Scrum-71101 | 【依赖rom验证】【必现】【u625】【性能】1029 开机1s点击地图widget卡片没有点击音，点击随心听卡片有点击音 |  | Pass
bug-地图 | bugfix | FordPhase4Scrum-74715 | 【必现】【u625】【途径点】1650 算路规划页，点击途径点，点击精准搜，搜索完点击“+”按钮，会自动退出路线规划页 |  | Pass
bug-地图 | bugfix | FordPhase4Scrum-72923 | 【实车验收】【U625】【地图】14-27 导航态，比例尺频繁改变（偶现） |  | Pass
bug-地图 | bugfix | FordPhase4Scrum-70418 | 【必现】【u625】【埋点】1532语音切换车头朝上或者正北朝上，labels : voice和labels : hmi各打印了一次 |  | Pass
bug-地图 | bugfix | FordPhase4Scrum-59731 | 【必现】【u625】【离线下载】1119 离线地图下载当前地区，下载中无显示百分比 |  | Pass
VR | feature | / | 合入中高配模型 |  | Pass
VR | feature | / | 合入语音优化：*分屏需求 *可见即可说 *联系人优化 |  | Pass
地图 | feature | 通过TDR决议 | 合入LTS SDK版本，优化定位相关性能 |  | Pass
地图 | feature | DCR变更需求 | U625多屏互动需求 |  | Pass
签约管理 | feature | DCR变更需求 | DCR-Phase5签约增加主题适配 |  | Pass
随心听 | feature | DCR变更需求 | DCR-随心听多屏互动需求，包括方向盘按键反控，媒体信息传递，后排屏功能 |  | Pass
语音/车机管家 | feature | FO邮件需求 | 依据云听配置位区分语音云听相关指令和云听APP权限管理入口显示/隐藏 |  | Pass
语音 | bugfix | [edc-scrum-143692] | [edc-scrum-143692][Bug]进入用户反馈后点home，再次点击进入用户反馈会闪退 |  | Pass
| bugfix | [edc-scrum-144347] | [edc-scrum-144347] [bug] 【625】【随心听】【副驾随心听必现】语音点播喜马拉雅专辑无响应 |  | Pass
随心看 | bugfix | edc-scrum-144567 | edc-scrum-144567, 【短视频】在副驾侧短视频播放页面，语音：打开爱奇艺收藏，主驾侧执行并打开，出现双开（11：39左右） |  | Pass
| bugfix | edc-scrum-144403 | edc-scrum-144403, 【U625】【必现】随心看播放中，语音点播，会回到爱奇艺首页 |  | Pass
| bugfix | edc-scrum-143075 | edc-scrum-143075, 【爱奇艺】在爱奇艺播放页面，语音：打开爱奇艺收藏，必现闪退到爱奇艺首页，14点21分 |  | Pass
随心听 | bugfix | edc-scrum-144460 | edc-scrum-144460, 【Monkey自动化测试】【福特Phase5625】进程com.baidu.car.radio出现了java.lang.RuntimeException: Error receiving broadcast Intent |  | Pass
| bugfix | edc-scrum-144264 | edc-scrum-144264, 【Monkey自动化测试】【福特Phase5625】进程com.baidu.car.radio出现了java.lang.NullPointerException: Attempt to invoke virtual method |  | Pass
天气 | bugfix | / | 分屏后在副驾打开天气, 再点击主驾天气, 天气在副驾打开 |  | Pass

## Fixed Bug List
Key | Summary | Priority
APIMCIM-30077 | [U625MCA][100%]Vehicle information, fill in the wrong license plate, click save, prompt error | P2
APIMCIM-30067 | [U625MCA][100%]The personal center enters the vehicle information page, and the back button in the upper left corner will move | P2
APIMCIM-25186 | [HMI WALK-THROUGH][U625MCA][100%]The style of the error message is incorrect | P2
APIMCIM-30941 | [U625MCA][100%]Baidu account authorization copy error | P2
APIMCIM-29063 | Phase 5:【AutoTest】Monkey测试20h，出现2次包名为com.baidu.iov.faceos的CRASH异常 | P2
APIMCIM-29909 | 【Phase5】【U625MCA】VID_20230904_144707播放蓝牙音乐，蓝牙音乐app和launcher的显示转接图片不一致 | P2
APIMCIM-28656 | Phase 5：【必现】点击键盘上任意内容，气泡中的字符没有放大效果 | P2
APIMCIM-22440 | [U625MCA][100%]副驾打开百度系应用，主驾出现百度协议 | P2
APIMCIM-31040 | [U625MCA][100%]Tapping PLAY icon is no response in Suixinting card when the current program needs to be paid. | P2
APIMCIM-30952 | [U625MCA][100%]My account UI is loading all the time after turned off CCS. | P2
APIMCIM-29680 | [U625MCA][100%] The scrolling effect isn't applied to the title. | P2
APIMCIM-29270 | [U625MCA][100%] The purchased program is still locked after paying the program in purchase history. | P2
APIMCIM-24745 | [U625MCA][100%] IVI displays "Fail to load" after tapping "Buy" button in the purchased album. | P2
APIMCIM-22300 | [U625MCA][100%] No TTS broadcasts user to buy VIP after tapping the play button on suixinting card. | P2
APIMCIM-30697 | 【Monkey自动化测试】【福特Phase5 U625】进程com.baidu.car.input出现了java.lang.RuntimeException: InputChannel is not initialized., 具体位置在None | P1
APIMCIM-30311 | [U625MCA][100%]Input method voice input background is wrong | P2
APIMCIM-20882 | [U625MCA][100%]所有应用页面百度应用图标问题 | P2
APIMCIM-30574 | [U625MCA][100%]There should not be a white line on the left | P2
APIMCIM-30322 | [U625MCA][100%]The weather page is missing a mask on the right side | P2
APIMCIM-30321 | [U625MCA][100%]Weather background color is inconsistent with UI | P2
APIMCIM-29055 | Phase 5:【AutoTest】Monkey测试20h，出现1次包名为com.baidu.xiaoduos.weather的ANR异常 | P2
APIMCIM-30287 | [U625MCA][100%]Clearing all recent apps for the co-pilot should not affect the co-pilot | P2
APIMCIM-29081 | [U625MCA][80%]Recording and reporting event failed | P2
APIMCIM-30700 | 【必现】【u625】【widget】1104 widget卡点显示全白，实际地图底图已经加载 | P1
APIMCIM-30699 | 【福特phase5 U625】【地图-签约管理】取消协议签约之后点击地图，地图没有拉起签约页面 | P1
APIMCIM-29521 | Phase 5：【必现，FO签收发生】 导航进入地下车库内，车标未跟随车头方向改变 | P1
APIMCIM-30703 | 【必现】【埋点】1707最后一公里，未打印全屏 | P2
APIMCIM-30701 | 【必现】【算路】1736熟路模式中，无法修改组队目的地，点击后添加按钮后，底图拖拽 | P2
APIMCIM-30686 | [U625MCA][100%]The simulated navigation page is inconsistent with the UI | P2
APIMCIM-30681 | [U625MCA][100%]The search page along the way in navigation is inconsistent with the UI | P2
APIMCIM-30667 | [U625MCA][100%]Favorites rename page is inconsistent with UI | P2
APIMCIM-30665 | [U625MCA][100%]The favorites editing state is inconsistent with the UI | P2
APIMCIM-30658 | [U625MCA][100%]The personal toolbox page is inconsistent with the UI | P2
APIMCIM-29543 | CLONE - 【必现】【widget】1117 重启车机或者杀掉地图，首次点击widget的回家按钮无反应，需要点击第二次才行 | P2
APIMCIM-29498 | Phase 5：【必现，FO签收发生】 导航态，终点连接线太粗（必现） | P2
APIMCIM-29119 | Phase 5：【必现】 模拟导航中，暂停按钮不正确 | P2
APIMCIM-29118 | Phase 5：【必现】副驾侧导航结束卡片上没有实景图 | P2
APIMCIM-29110 | Phase 5：【必现】队员收到队长更改目的地后确认，路况条超出TBT面板 | P2
APIMCIM-29108 | Phase 5：【必现】我的队伍界面，未设置终点时，定位icon过大 | P2
APIMCIM-29106 | Phase 5：【必现】系统设置中提示音量调节到最低，导航中不显示静音icon | P2
APIMCIM-29104 | Phase 5：【必现】合作模式下副驾侧音量值显示不清晰 | P2
APIMCIM-28999 | Phase 5：【必现】语音说“关闭导航声音”，进入导航音量查看之后，再退出音量页面，音量图标显示错误 | P2
APIMCIM-28998 | Phase 5：【必现】队长更换目的地后，车机端取消更换目的地，ETA面板显示异常 | P2
APIMCIM-28996 | Phase 5：【必现】合作模式下，组队出行页面的地址栏主副驾两边显示不一致 | P2
APIMCIM-28972 | Phase 5：【必现】我的队伍里调起输入框后，蒙层也可以继续点击并响应操作 | P2
APIMCIM-28941 | Phase 5：【必现】熟路导航到达目的地后，弹出toast”已抵达目的地，即将退出路线雷达” | P2
APIMCIM-28923 | Phase 5：【必现，FO签收发生】 巡航模式，固定按钮选项和边框间隔过大 | P2
APIMCIM-28922 | Phase 5：【必现，FO签收发生】 巡航模式，固定按钮选项和边框间隔过大 | P2
APIMCIM-28917 | Phase 5：【偶现，FO签收发生】结束卡片，副驾侧无图片（偶现） | P2
APIMCIM-28886 | Phase 5：【必现】导航设置中无隐私设置开关 | P2
APIMCIM-28883 | Phase 5：【必现】离线地图下载界面，进度条显示不正确 | P2
APIMCIM-28870 | Phase 5：【必现，FO签收发生】14-11 语音关闭导航播报，音量图标状态未同步 | P2
APIMCIM-28867 | Phase 5：【偶现】从算路界面返回，详情页显示错误 | P2
APIMCIM-28864 | Phase 5：【必现】周边搜4S店，搜索结果不显示福特logo | P2
APIMCIM-28857 | Phase 5：【必现】模拟导航里面，暂停/继续的图标没有转换 | P2
APIMCIM-28852 | Phase 5：【必现】地址检索页面，点击地址下面公里数的区域，则再去点击地址名，无法发起算路 | P2
APIMCIM-28849 | Phase 5：【必现】收藏夹中，长按删除收藏的地址，保存后退出再进入收藏夹页面，刚才删除的地址又恢复至收藏夹中 | P2
APIMCIM-28835 | Phase 5：【必现，FO签收发生】调整导航音量，音量数字显示位置错误 | P2
APIMCIM-28833 | Phase 5：【必现】在导航设置中调节音量，音量小部件依然显示静音 | P2
APIMCIM-28827 | Phase 5：【必现】地图卡片上的GPS信号显示不正确 | P2
APIMCIM-28810 | Phase 5：【必现】移除队友后，界面显示不正确 | P2
APIMCIM-28698 | Phase 5：【必现】合作模式下，副驾位置的音量值在框体外面，跟主驾不一致 | P2
APIMCIM-28697 | Phase 5：【偶发】合作模式下，设置里的小地图模式的框体变大 | P2
APIMCIM-28688 | Phase 5：【必现】事件上报页面，录音之后点击停止，会自动退出事件上报页面 | P2
APIMCIM-28687 | Phase 5：【必现】事件上报页面，点击输入框，不会直接调起输入法键盘 | P2
APIMCIM-28680 | Phase 5：【偶发】 POI详情页，信息显示不完整 | P2
APIMCIM-28860 | Phase 5：【必现】“先去这”按钮文字溢出 | P2
APIMCIM-28845 | Phase 5：【必现】无法语音切换至提示音播报模式 | P2
APIMCIM-30659 | [U625MCA][100%]History message page, delete successful toast box too small | P2
APIMCIM-25479 | [HMI WALK-THROUGH][U625MCA][100%]The message center icon and height display are inconsistent with the design | P2
APIMCIM-29124 | Phase 5：【必现】历史消息app，点击“设置”无任何反应 | P2
APIMCIM-31084 | [U625MCA][100%]QRcode payment page crash in splash screen when move it from main driving screen to co-pilot screen | P2
APIMCIM-31081 | [U625MCA][100%]Black screen when calling in movie ticket payment page | P2
APIMCIM-30908 | [U625MCA][100%]NO gas station information or display one first and display another one after clicking back button when clicking two gas stations together in select gas station page | P2
APIMCIM-30497 | 【U625】【必现】【服务生态】在电影购票点击搜索框，没有弹出输入键盘 | P2
APIMCIM-30375 | [U625MCA][100%]The co-pilot can seize the mini app opened by the main driver at any time, and prompts the toast text color to be dark | P2
APIMCIM-30109 | [U625MCA][100%]Mini app - movie, the payment page pops up to the main driver | P2
APIMCIM-30091 | [U625MCA][100%]The recently used/my favorites page has no return function, and the layout is inconsistent with the UI. | P2
APIMCIM-28820 | [U625MCA][25%]Smart parking click to authorize without response | P2
APIMCIM-31338 | 【phase5】【U625】【随心听】歌曲播放界面，点击音频设置，再点击左上角返回随心听，返回的是随心听首页不是播放页面 | P2
APIMCIM-30599 | [U625MCA][100%]QQ Music deletes songs missing Toast prompt | P2
APIMCIM-30594 | [U625MCA][100%]The font color should be white when songs are not checked in QQ music batch editing | P2
APIMCIM-30593 | [U625MCA][100%]There are currently no songs in the qq music playlist the prompt is inconsistent with the UI | P2
APIMCIM-30589 | [U625MCA][100%]The Himalayan double speed selection page lacks scroll bars | P2
APIMCIM-30588 | [U625MCA][100%]Himalayan unsubscribe Toast is inconsistent with UI | P2
APIMCIM-30582 | [U625MCA][100%]Ximalaya logout pop-up button is inconsistent with the UI | P2
APIMCIM-30581 | [U625MCA][100%]Ximalaya code scanning login page overlaps when there is no network | P2
APIMCIM-30580 | [U625MCA][100%]The light effect of Himalayan News should follow the movement of the progress bar | P2
APIMCIM-30498 | 【U625】随心听分屏边界处有字时异常高亮显示 | P2
APIMCIM-29873 | [U625MCA][100%]When playing music, the launcher card display is inconsistent with the UI | P2
APIMCIM-29628 | Phase 5：【必现】QQ音乐播放器进入声音设置页面，左上角返回，没有返回播放器 | P2
APIMCIM-28891 | Phase 5：【必现】喜马拉雅/QQ音乐无法播放，无任何toast提示 | P2
APIMCIM-26252 | Phase 5：【必现】QQ音乐刷新页面时，刷新成功/失败没有任何提示 | P2
APIMCIM-22433 | Phase 5：【必现】全局免唤醒：上一首/下一首。TTS错误 | P2
APIMCIM-28961 | Phase 5：【偶现】副驾语音唤醒“上一曲/下一曲”切换主驾的音乐 | P2
APIMCIM-30331 | [U625MCA][100%]Scanning the QR code to pay for Ximalaya membership purchases by the passenger driver should not appear in the main driver’s window | P2
APIMCIM-30330 | [U625MCA][100%]The main driver’s Himalayan payment page should be moved to the co-driver’s page and should not disappear | P2
APIMCIM-31062 | [U625MCA][smartscene]个人时光，进入随心看再返回个人时光，页面出现闪烁 | P2
APIMCIM-30625 | [U625MCA][100%]Personalized voice broadcast help page slider cannot be completed | P2
APIMCIM-30624 | [U625MCA][100%]The personalized voice broadcast page slider cannot be completed | P2
APIMCIM-30069 | [U625MCA][100%]Signed agreement page, incorrect title | P2
APIMCIM-30052 | [U625MCA][100%]Split screen, protocol content is not fully displayed | P2
APIMCIM-30696 | 【随心看】未登录车机账号的状态下，语音点播『我要看小猪佩奇』进入随心看首页一直显示加载状态 | P1
APIMCIM-30695 | 【U625】【随心看】【分屏语音】副驾搜索结果界面，主驾语音：我要看莲花楼，副驾播放视频，实际应该是主驾播放（另外，主驾搜索结果界面，副驾语音播放，主驾视频播放） | P1
APIMCIM-30694 | 【爱奇艺】登录VIP爱奇艺账号，点击个人中心的退出账号，提示退出失败（15：21左右） | P1
APIMCIM-30690 | 【爱奇艺】副驾侧连接蓝牙耳机，主驾侧播放爱奇艺后移屏到副驾侧，依旧功放播放 | P1
APIMCIM-30689 | 【爱奇艺】副驾驶有人，车速大于5KM，分屏副驾侧播放随心看时取消分屏，无法取消如视频（17：00左右） | P1
APIMCIM-31071 | Phase 5：【必现】随心看时，点击常驻栏的all app图标，闪屏 | P2
APIMCIM-30882 | [U625MCA][100%]When iQiyi plays a video, the progress bar should not be dragged when sliding with three fingers to move the screen | P2
APIMCIM-30867 | Phase 5：【必现】随心看点击个人中心，会员头像显示错误 | P2
APIMCIM-30855 | Phase 5：【必现】爱奇艺/小视频播放时，滑动亮度调节，不能到最大值 | P2
APIMCIM-30827 | Phase 5：【必现】播放爱奇艺视频，开始播放时视频右侧会闪一下 | P2
APIMCIM-30777 | Phase 5：【必现】随心看的提示应该显示错误“登录福特（派）帐号解锁在线视频” | P2
APIMCIM-30635 | [U625MCA][100%]Brightness volume adjustment light effect is wrong | P2
APIMCIM-30623 | [U625MCA][100%]Variety show playlist page lacks scroll bar | P2
APIMCIM-30618 | [U625MCA][100%]Immersive mode should not show the resident bar | P2
APIMCIM-30613 | [U625MCA][100%]The IQIYI trial end page is inconsistent with the UI | P2
APIMCIM-30605 | [U625MCA][100%]The title size of the IQIYI voice search results page is inconsistent with the UI | P2
APIMCIM-30604 | [U625MCA][100%]IQIYI did not find the relevant video page and the UI is inconsistent | P2
APIMCIM-30319 | [U625MCA][100%]iQiyi input content should not overlap with the search box | P2
APIMCIM-28774 | Phase 5：【必现】随心看中，倍速的提示语不正确 | P2
APIMCIM-28637 | Phase 5：【必现】点击首页随心听widget上的本地按钮，TTS会播报“好的” | P2
APIMCIM-26900 | Phase 5：【必现】爱奇艺播放时，切R档，视频未暂停 | P2
APIMCIM-26550 | Phase 5：【偶现】合作模式，点击随心听应用，不能进入 | P2
APIMCIM-26527 | Phase 5：【必现】实车挂入R档，爱奇艺视频仍在播放 | P2
APIMCIM-26524 | Phase 5：【偶现】爱奇艺收藏按钮偶现收藏不了 | P2
APIMCIM-26381 | Phase 5：【必现】独立模式，爱奇艺源，点击收藏toast提示位置不一致 | P2
APIMCIM-26371 | Phase 5：【必现】爱奇艺收藏按钮点击无反应 | P2
APIMCIM-26310 | Phase 5 【必现】挂倒挡，随心看爱奇艺视频未暂停播放 | P2
APIMCIM-22533 | Phase 5：【必现】独立模式，副驾唤醒语音：打开随心看，总是主驾侧打开随心看 | P2
APIMCIM-22528 | Phase 5：【必现】独立模式，副驾点击爱奇艺不显示连接耳机弹窗，点击USB视频播放时显示 | P2
APIMCIM-29165 | [Phase5][U625MCA][VPA][必现]主驾唤醒展示swan卡片，副驾立刻软按键立刻唤醒语音，VPA形象异常 | P2
APIMCIM-29162 | [Phase5][U625MCA][VPA][必现]车牌限行城市切换查询，TTS播报未及时切换 | P2
APIMCIM-28974 | [U625MCA][100%] Voice help center is opened on driver's side by voice on co-driver's side | P2
APIMCIM-28971 | [U625MCA][100%] Extending listening time is incorrect( should be set to 20 seconds) | P2
APIMCIM-26383 | [U625MCA][100%] The Movie application is opened on Driver's side when VPA query on co-pilot side | P2
APIMCIM-30953 | [Phase5][U625MCA][VPA][必现]语料“查看小狗的图片”指令不支持 | P2
APIMCIM-28750 | [U625MCA][100%] VPA image display abnormal when waking up again and TTS broadcast is still continued after VPA exits. | P2
APIMCIM-30809 | [U625MCA][100%] Any voice cannot be recognized after wake up VPA by pressing VPA icon | P1
APIMCIM-31052 | Phase 5：【偶现】VR:半开遮阳帘。播报错误 | P2
APIMCIM-30521 | 【U625-中配实车】【语音】10:20 语音：链接蓝牙；并未打开蓝牙开关 | P2
APIMCIM-29007 | Phase 5：【必现】副驾唤醒语音后，语音会识别到语音自己说的话 | P2
APIMCIM-28944 | Phase 5：【必现】小视频时，可见即可说有动效无效果 | P2
APIMCIM-28815 | Phase 5：【必现】免唤醒：上一首/下一首。播报错误 | P2
APIMCIM-28811 | Phase 5：【必现】所有应用界面，点击随心看-本地。播报：好的 | P2
APIMCIM-27585 | 【U625MCA】【100%】【VR】分屏，主驾或副驾打开电子手册后，另一个屏语音打开电子手册，无法打开，TTS无反应 | P2
APIMCIM-26539 | Phase 5：【必现】独立模式，主驾唤醒vr：我想看神探狄仁杰，响应在副驾播放视频 | P2
APIMCIM-26530 | Phase 5：【偶现】语音会一直播放“好，音量调到2了” | P2

## Open Bug List
CIA (Customer Impact Assessment)
Key | Supplier | Summery | Priority | Repeat step | Frequency | Affects Version | Issue Analysis |  |  | ICA | PCA | Planned Fix Version | Data Tagging Analysis | Customer Complain
[7 empty] | Risk assessment （Need FO Confirmation） | XCL Evaluation | Root cause
APIMCIM-31313 | Baidu | 【U625-中配实车】【语音】15:22 “音量减小500” 预期TTS：仅支持0-30的音量范围调节哦；实际TTS：已经是最小音量了 | P2 |  |  | FB_R04.1_ENG | [5 empty] | Request_Reject
APIMCIM-31208 | Baidu | 【U625实车】【语音】 12378979 14:44 空调关闭，语音：关闭吹足，实际播报吹面已关闭，预期播报空调已关闭 | P2 |  |  | FB_R04.1_ENG | [5 empty] | Request_Reject
APIMCIM-31207 | Baidu | 【U625实车】【语音】 12378974 14:34 空调关闭，语音：关闭吹面，实际播报吹面已关闭，预期播报空调已关闭 | P2 |  |  | FB_R04.1_ENG | [5 empty] | Request_Reject
APIMCIM-31201 | Baidu | 【U625实车】【语音】15:40 偶现一次，空调打开，语音：开启座舱新风：TTS：座舱新风已打开后，再次播报空调已打开 | P2 |  |  | FB_R04.1_ENG
APIMCIM-31190 | Baidu | [U625MCA][100%][App] VPA "Pause" cannot disappear after relax mode is running. | P2 |  |  | FB_R04.1_ENG
APIMCIM-31133 | Baidu | 【U625-中配实车】【语音】【高概率】10:23 语音：打开热点 TTS：当前状态不支持，但实际打开了车载热点 | P2 |  |  | FB_R04.1_ENG
APIMCIM-31082 | Baidu | [U625MCA][100%]Searched results dispear after swiping up at Mango TV searching page | P2 |  |  | FB_R04.1_ENG
APIMCIM-31064 | Baidu | Phase 5：【必现】唤醒说：云之羽。上屏错误 | P2 |  |  | FB_R04.1_ENG
APIMCIM-31053 | Baidu | Phase 5：【必现】免唤醒说：导航到新街口。播报：请先打开地图 | P2 |  |  | FB_R04.1_ENG
APIMCIM-30960 | Baidu | Phase 5: 【必现】比例尺50米时，未显示3D楼快 | P2 |  |  | FB_R04.1_ENG
APIMCIM-30945 | Baidu | [U625MCA][100%] The screen jump error after VPA query "Bluetooth setting" | P2 |  |  | FB_R04.1_ENG
APIMCIM-30938 | baidu | [U625MCA][100%]Failed to initiate home navigation after completing the off duty itinerary through IVI reboot. | P2 |  |  | FB_R04.1_ENG
APIMCIM-30911 | Baidu | Phase 5：【必现】打开地图时，logo先靠边缘截断显示 | P2 |  |  | FB_R04.1_ENG
APIMCIM-30883 | Baidu | Phase 5：【偶现】唤醒后，指令未被识别上屏 | P2 |  |  | FB_R04.1_ENG
APIMCIM-30871 | Baidu | Phase 5：【必现】VR:减小导航音量到0.播报错误 | P2 |  |  | FB_R04.1_ENG
APIMCIM-30859 | Baidu | [U625MCA][Once]Cannot invoke relax mode "The starry sky theme" after user says "Turn on starry sky" | P2 |  |  | FB_R04.1_ENG
APIMCIM-30682 | Baidu | [U625MCA][100%]The road error page is inconsistent with the UI | P2 |  |  | FB_R04_ENG
APIMCIM-30680 | Baidu | [U625MCA][100%]More pages in the navigation operation state are inconsistent with the UI | P2 |  |  | FB_R04_ENG
APIMCIM-30679 | Baidu | [U625MCA][100%]The offline map download page is inconsistent with the UI | P2 |  |  | FB_R04_ENG
APIMCIM-30678 | Baidu | [U625MCA][100%]Navigation setting height is inconsistent with UI | P2 |  |  | FB_R04_ENG
APIMCIM-30677 | Baidu | [U625MCA][100%]The navigation settings broadcast page is inconsistent with the UI | P2 |  |  | FB_R04_ENG
APIMCIM-30676 | Baidu | [U625MCA][100%]Restricted route avoidance is inconsistent with the UI | P2 |  |  | FB_R04_ENG
APIMCIM-30675 | Baidu | [U625MCA][100%]Navigation perspective is inconsistent with UI | P2 |  |  | FB_R04_ENG
APIMCIM-30670 | Baidu | [U625MCA][100%]The search result page is inconsistent with the UI | P2 |  |  | FB_R04_ENG
APIMCIM-30611 | Baidu | 【U625】【Caraudio（10ch）】【实车】【必现】播放视频，语音静音，回复已经是静音模式，但vr结束后自动解除了mute | P2 |  |  | FB_R04.1_ENG
APIMCIM-30586 | Baidu | [U625MCA][100%]Himalaya confirms that the purchase content is inconsistent with the UI | P2 |  |  | FB_R04_ENG
APIMCIM-30412 | Baidu | [U625MCA][100%]Smart Security Manager, privacy permission page icon style is not uniform | P2 |  |  | FB_R04_ENG
APIMCIM-30406 | Baidu | Clone Form PL24 XCL Issue U625MCA 地图白屏 | P2 |  |  | FB_R04_ENG
APIMCIM-30399 | Baidu | Clone Form PL24 XCL Issue U625MCA 导航到达目的地判断逻辑问题，已在POI 对应的AOI区域内，还提示前往外部位置，熄火重启后 ，仍提示是否恢复上次导航路线？ | P2 |  |  | FB_R04_ENG
APIMCIM-30392 | Baidu | Clone Form PL24 XCL Issue U625MCA 【偶现】【Maps】 在夹江隧道内发生偏航长时间未能触发偏航，且按错误道路导航 | P2 |  |  | FB_R04_ENG
APIMCIM-30384 | Baidu | Clone Form PL24 XCL Issue U625MCA [必现][map]车辆行驶在隧道中发起导航/偏航，惯导不生效，无法推送车辆当前位置 | P2 |  |  | FB_R04_ENG
APIMCIM-30378 | Baidu | Clone Form PL24 XCL Issue U625MCA 【偶现】隧道口主动偏航后导航蚯蚓线和小卡片不更新 | P2 |  |  | FB_R04_ENG
APIMCIM-30377 | Baidu | [U625MCA][100%]Mini app is full screen, unable to swipe left | P2 |  |  | FB_R04_ENG
APIMCIM-30372 | Baidu | Clone Form PL24 XCL Issue U625MCA 【偶现】【Maps】 在地下停车场发起导航驶出，GPS信号恢复慢，导航算路恢复慢 | P2 |  |  | FB_R04_ENG
APIMCIM-30368 | Baidu | Clone Form PL24 XCL Issue U625MCA 【偶现】【地图】车辆从地下停车场出来后地图定位不准确 | P2 |  |  | FB_R04_ENG
APIMCIM-30356 | Baidu | 【U625MCA】【性能】【CPU】Launcher显示到进入稳定运行阶段经过的时间过长 | P2 |  |  | FB_R04.1_ENG
APIMCIM-30317 | Baidu | [U625MCA][100%]The main driver should not exit the input method when operating the co-pilot | P2 |  |  | FB_R04_ENG
APIMCIM-30292 | Baidu | 【625】【语音】【必现】通过语音方式“自定义唤醒词”为“你好福特”，再关闭自定义唤醒词，默认唤醒词你好福特唤不醒了 | P2 |  |  | FB_R04_ENG
APIMCIM-30200 | Baidu | CLONE - Clone Form PL24 XCL Issue U611MCA 【偶现】【Maps】 在地下停车场行驶，地图车标方向与车辆实际行驶方向不一致 | P2 |  |  | LC_R04_ENG
APIMCIM-30198 | Baidu | Clone Form PL24 XCL Issue U625MCA 【偶现】【Maps】 在地下停车场行驶，地图车标方向与车辆实际行驶方向不一致 | P2 |  |  | FB_R04_ENG
APIMCIM-30182 | Baidu | Clone Form PL24 XCL Issue U625MCA 出地下停车场，重新发起导航，车标未绑定在路线上，恢复绑定时间大于3S | P2 |  |  | FB_R04_ENG
APIMCIM-30071 | Baidu | [U625MCA][100%]To cancel the agreement, click on the map in the split-screen state, the map logo will flash once | P2 |  |  | FB_R04_ENG
APIMCIM-29709 | Baidu | [U625MCA][100%]Launcher map card is inconsistent with UI | P2 |  |  | FB_R04_ENG
APIMCIM-29707 | Baidu | [U625MCA][100%]The logo position should not jump when the map is opened | P2 |  |  | FB_R04_ENG
APIMCIM-29643 | Baidu | 【U625】呼出VR，录入温度调高/低一点，会一直执行下去。（13：24） | P2 |  |  | FB_R04_ENG
APIMCIM-29587 | Baidu | [U625MCA][100%]Smart refueling coupons reduced after uses coupons to place orders and fail payments | P2 |  |  | FB_R04_ENG
APIMCIM-29517 | Baidu | Phase 5：【必现，FO签收发生】 导航中，点击组队设置，GPS图标闪烁红色（必现） | P2 |  |  | FB_R04_ENG
APIMCIM-29506 | Baidu | Phase 5：【偶现，FO签收发生】 结束卡片，主副驾图片不一致（偶现） | P2 |  |  | FB_R04_ENG
APIMCIM-29500 | Baidu | Phase 5：【偶现，FO签收发生】 主驾侧导航态，异常自动切换为副驾侧导航态 | P2 |  |  | FB_R04_ENG
APIMCIM-29496 | Baidu | Phase 5：【必现，FO签收发生】小地图模式，副驾异常出现侧边选项（必现） | P2 |  |  | FB_R04_ENG
APIMCIM-29493 | Baidu | Phase 5：【必现，FO签收发生】 分屏模式下，主驾地图卡片显示不全（必现） | P2 |  |  | FB_R04_ENG
APIMCIM-29491 | Baidu | Phase 5：【必现，FO签收发生】 导航中，全屏，分屏模式下，导航引导线位置不一致（必现） | P2 |  |  | FB_R04_ENG
APIMCIM-29476 | Baidu | Phase 5：【必现，FO签收发生】 滑动调节导航音量，主副驾音量数字显示位置不一致 | P2 |  |  | FB_R04_ENG
APIMCIM-29474 | Baidu | Phase 5：【必现，FO签收发生】 音量图标显示静音，点击查看，实际未静音（必现） | P2 |  |  | FB_R04_ENG
APIMCIM-29281 | Baidu | Phase 5：【必现，FO签收发生】 主驾侧导航态，车道线未居中 | P2 |  |  | FB_R04_ENG
APIMCIM-29156 | Baidu | Clone Form PL24 XCL Issue U625MCA 【偶现】进入地库，休眠重启后，发起导航驶出地库，车标长时间未绑路 | P2 |  |  | FB_R04_ENG
APIMCIM-29121 | Baidu | Phase 5：【必现】 断网时发送微信send2car位置消息，连网后收不到此消息 | P2 |  |  | FB_R04_ENG
APIMCIM-29117 | Baidu | Phase 5：【必现】算路界面无拥堵加剧或拥堵消散提醒 | P2 |  |  | FB_R04_ENG
APIMCIM-29115 | Baidu | Phase 5：【偶现】“到达目的地”播报不完整 | P2 |  |  | FB_R04_ENG
APIMCIM-29113 | Baidu | Phase 5：【必现】无网无数据3分钟算路失败后连接网络，点击刷新路线，定位错误 | P2 |  |  | FB_R04_ENG
APIMCIM-29109 | Baidu | Phase 5：【必现】队友排名面板上无“相对排名”文案 | P2 |  |  | FB_R04_ENG
APIMCIM-29105 | Baidu | Phase 5：【必现】发送剩余路线至福特派，发送失败 | P2 |  |  | FB_R04_ENG
APIMCIM-29093 | Baidu | Phase 5：【必现】个人中心和导航设置的车牌号不同步 | P2 |  |  | FB_R04_ENG | [5 empty] | Request_Reject
APIMCIM-29088 | Baidu | [U625MCA][100%]Not jump to CCS page when user click go to open button after switching from split screen to full screen with CCS OFF | P2 |  |  | FB_R04_ENG
APIMCIM-29069 | Baidu | Phase 5:【AutoTest】Monkey测试20h，出现1次包名为com.baidu.che.codriver的ANR异常 | P2 |  |  | FB_R04_ENG
APIMCIM-29068 | Baidu | Phase 5:【AutoTest】Monkey测试20h，出现2次包名为com.baidu.bodyguard的CRASH异常 | P2 |  |  | FB_R04_ENG
APIMCIM-28997 | Baidu | Phase 5：【偶发】队长更换目的地后，车机端收不到地址更新提示 | P2 |  |  | FB_R04_ENG
APIMCIM-28995 | Baidu | Phase 5：【必现】长途算路页面相同服务区可多次添加为途径点 | P2 |  |  | FB_R04_ENG | [5 empty] | Request_Reject
APIMCIM-28994 | Baidu | Phase 5：【必现】编辑车牌，点击保存时，提示需要重新登录账号 | P2 |  |  | FB_R04_ENG
APIMCIM-28991 | Baidu | Phase 5：【必现】开启队友排名，但是没有队员排名的页面出来 | P2 |  |  | FB_R04_ENG
APIMCIM-28990 | Baidu | Phase 5：【必现】巡航模式下的比例尺位置与其他模式不一致 | P2 |  |  | FB_R04_ENG
APIMCIM-28951 | Baidu | Phase 5：【必现】VR：下一个清明节。播报错误 | P2 |  |  | FB_R04_ENG | [5 empty] | Request_Reject
APIMCIM-28937 | Baidu | Phase 5：【必现】已是黑夜模式，VR:黑夜模式。播报错误 | P2 |  |  | FB_R04_ENG
APIMCIM-28933 | Baidu | Phase 5：【偶现，FO签收发生】 隧道内偏航，无“叮”提示音 | P2 |  |  | FB_R00_ENG
APIMCIM-28931 | Baidu | Phase 5：【必现，FO签收发生】 巡航态，超速无提示，车标不变红 | P2 |  |  | FB_R00_ENG
APIMCIM-28926 | Baidu | [U625MCA][100%]Microphone permission not recover to default not allow after brand reset/delete VIN in IVI keeper page | P2 |  |  | FB_R04_ENG
APIMCIM-28924 | Baidu | Phase 5：【必现，FO签收发生】 沿途搜 银行，主驾侧与副驾侧，图标底色不同步 | P2 |  |  | FB_R00_ENG
APIMCIM-28914 | Baidu | Phase 5：【必现】消息中心上下滑动查看时，还是能进入巡航模式 | P2 |  |  | FB_R04_ENG
APIMCIM-28904 | Baidu | Phase 5：【偶现，FO签收发生】主页导航图标一直保持正北向上，与地图内图标方向不一致（偶现） | P2 |  |  | FB_R00_ENG
APIMCIM-28894 | Baidu | Phase 5：【必现】车机收不到百度接人的位置信息 | P2 |  |  | FB_R04_ENG
APIMCIM-28888 | Baidu | Phase 5：【必现】导航结束卡片中点击美食，下拉加载下一页搜索结果后，自动开始路径规划 | P2 |  |  | FB_R04_ENG
APIMCIM-28879 | Baidu | Phase 5：【必现，FO签收发生】语音唤醒框，遮盖导航（必现） | P2 |  |  | FB_R00_ENG
APIMCIM-28877 | Baidu | Phase 5：【必现，FO签收发生】实际路况显示红色，TBT路况图未标红 | P2 |  |  | FB_R00_ENG
APIMCIM-28876 | Baidu | Phase 5：【必现】巡航模式下，Widget卡片不显示路况 | P2 |  |  | FB_R04_ENG
APIMCIM-28874 | Baidu | Phase 5：【必现，FO签收发生】静音状态下，语音增大导航音量，音量bar没有变更 | P2 |  |  | FB_R00_ENG
APIMCIM-28872 | Baidu | Phase 5：【必现】巡航模式下，比例尺不跟随视角切换而变化 | P2 |  |  | FB_R04_ENG | [5 empty] | Request_Reject
APIMCIM-28866 | Baidu | Phase 5：【必现】长按底图进入POI详情页，显示地图上的点 | P2 |  |  | FB_R04_ENG
APIMCIM-28863 | Baidu | Phase 5：【必现】长按底图进入POI详情页，收藏无动效 | P2 |  |  | FB_R04_ENG
APIMCIM-28862 | Baidu | Phase 5：【必现】长按底图进入POI详情页，点击收藏按钮，弹出toast“从收藏夹移出” | P2 |  |  | FB_R04_ENG
APIMCIM-28861 | Baidu | Phase 5：【偶现】导航设置中“导航”和“通用”同时高亮 | P2 |  |  | FB_R04_ENG
APIMCIM-28858 | Baidu | Phase 5：【必现】林肯之道账号没有登录时，导航可正常使用 | P2 |  |  | FB_R04_ENG | [5 empty] | Request_Reject
APIMCIM-28856 | Baidu | Phase 5：【必现】导航中打开服务条款，屏幕上多出一个回车位及+-按钮，点了无反应 | P2 |  |  | FB_R04_ENG
APIMCIM-28855 | Baidu | Phase 5：【必现】 熟路导航添加途径点后，终点ETA面板下面没有显示途径点的ETA信息 | P2 |  |  | FB_R04_ENG | [5 empty] | Request_Reject
APIMCIM-28854 | Baidu | Phase 5：【必现】导航中，语音说”顺路去福特研发中心“，语音回复”找到多个福特研发中心，请问去第几个“，实际放大底图看，就一个POI点 | P2 |  |  | FB_R04_ENG
APIMCIM-28851 | Baidu | Phase 5：【必现】继续下载离线地图时，还是存在全部开始的菜单 | P2 |  |  | FB_R04_ENG
APIMCIM-28846 | Baidu | Phase 5：【必现】部分沿途搜结果无绕行代价信息 | P2 |  |  | FB_R04_ENG
APIMCIM-28844 | Baidu | Phase 5：【必现】银行/加油站沿途搜中点击品牌，搜索结果的绕行代价标签闪烁 | P2 |  |  | FB_R04_ENG
APIMCIM-28840 | Baidu | Phase 5：【必现】首页和导航中，比例尺的位置不正确 | P2 |  |  | FB_R04_ENG
APIMCIM-28831 | Baidu | Phase 5：【偶现】VR:"不走高速”，TTS回复已使用不走高速方案，但偏好中不走高速选项不高亮 | P2 |  |  | FB_R04_ENG
APIMCIM-28809 | Baidu | Phase 5：【必现】VR:播放蓝牙音乐，无响应无播报 | P2 |  |  | FB_R04_ENG
APIMCIM-28762 | Baidu | Phase 5：【必现】导航惯导日志导出只有1kb | P2 |  |  | FB_R04_ENG
APIMCIM-28694 | Baidu | Phase 5：【必现】熟路模式下，首页widget中ETA面板会遮挡路线及车标 | P2 |  |  | FB_R04_ENG
APIMCIM-28692 | Baidu | Phase 5：【偶发】底图路线丢失，只有车标 | P2 |  |  | FB_R04_ENG
APIMCIM-28690 | Baidu | Phase 5：【偶发】无法进入巡航模式 | P2 |  |  | FB_R04_ENG | [5 empty] | Request_Reject
APIMCIM-28685 | Baidu | Phase 5：【必现】首页widget车标不会随设置而变化 | P2 |  |  | FB_R04_ENG
APIMCIM-28683 | Baidu | Phase 5：【必现】导航中的车标朝向，和全览下的车标朝向不一致 | P2 |  |  | FB_R04_ENG | [5 empty] | Request_Reject
APIMCIM-28682 | Baidu | Phase 5：【必现】算路页面没有路况预测 | P2 |  |  | FB_R04_ENG | [5 empty] | Request_Reject
APIMCIM-28681 | Baidu | Phase 5：【必现】设置中给语音授权，页面会卡住 | P2 |  |  | FB_R04_ENG
APIMCIM-28664 | Baidu | Phase 5：【偶发】交通路况手动关闭后，无法手动开启 | P2 |  |  | FB_R04_ENG
APIMCIM-28662 | Baidu | Phase 5：【必现】导航结束卡片开启时，导航结束后没有导航结束卡片 | P2 |  |  | FB_R04_ENG
APIMCIM-28661 | Baidu | Phase 5：【必现】widget中，右上角车速显示和实际车速不一致 | P2 |  |  | FB_R04_ENG
APIMCIM-28660 | Baidu | Phase 5：【必现】巡航模式下，首页widget的功能菜单点击无效 | P2 |  |  | FB_R04_ENG
APIMCIM-28659 | Baidu | Phase 5：【必现】添加途径点时，选择地图选点，无法添加途径点，一直提示“网络未连接，检查网络后重试” | P2 |  |  | FB_R04_ENG
APIMCIM-28230 | Baidu | [U625MCA][100%] VPA can be waked up during E-call event | P2 |  |  | FB_R00_ENG
APIMCIM-27044 | Baidu | Phase 5【AutoTest】Monkey测试13h，出现1次com.baidu.bodyguard包的anr异常 | P2 |  |  | FB_R00_ENG, FB_R04_ENG
APIMCIM-27015 | Baidu | Phase 5：【必现】导航语音输入添加途经点后，TTS回复异常 | P2 |  |  | FB_R00_ENG
APIMCIM-27010 | Baidu | Phase 5：【偶现】导航中，无法添加车牌 | P2 |  |  | FB_R00_ENG
APIMCIM-27005 | Baidu | Phase 5：【必现】地图里小地图出现比较慢 | P2 |  |  | FB_R00_ENG
APIMCIM-26980 | Baidu | Phase 5：【必现】车机端组队出行目的地添加途径点后途径点未同步给队友 | P2 |  |  | FB_R00_ENG | [5 empty] | Request_Reject
APIMCIM-26822 | Baidu | Phase 5：【必现】导航中，路况条未连接 | P2 |  |  | FB_R00_ENG
APIMCIM-26746 | Baidu | [U625MCA][3/3]power on VPA available takes 14.8s, way behind the target's 8s | P2 |  |  | FB_R00_ENG, FB_R04.1_ENG
APIMCIM-26706 | Baidu | [U625MCA][100%]Mango TV activation member QR code abnormality | P2 |  |  | FB_R00_ENG, FB_R04_ENG
APIMCIM-26682 | Baidu | Phase 5：【偶现】导航中VR:搜索附近的加油站。搜索结果非加油站 | P2 |  |  | FB_R00_ENG
APIMCIM-26671 | Baidu | Phase 5：【必现】独立模式，唤醒副驾VR:收藏视频，TTS：好的。但收藏了主驾的音频 | P2 |  |  | FB_R00_ENG | [5 empty] | Request_Reject
APIMCIM-26452 | Baidu | Phase 5：【偶现】【地图】离线导航过程中，车机首页车速车标车速与右上角车速不一致 | P2 |  |  | FB_R00_ENG
APIMCIM-26450 | Baidu | Phase 5：【必现】【地图】语音说导航到温度学派中医院，回复我还不清楚怎么控制它 | P2 |  |  | FB_R00_ENG
APIMCIM-26448 | Baidu | Phase 5：【必现】【地图】离线导航过程中，搜索温度学派中医院，显示未下载离线地图 | P2 |  |  | FB_R00_ENG
APIMCIM-26447 | Baidu | Phase 5：【必现】【地图】导航过程中，车速未超速的情况下，车标框显示为红色 | P2 |  |  | FB_R00_ENG
APIMCIM-26446 | Baidu | Phase 5：【必现】【地图】车机首页车速单位显示为大写的KM/H | P2 |  |  | FB_R00_ENG
APIMCIM-26445 | Baidu | Phase 5：【必现】【地图】导航设置中设置车标为经典车标，车机首页依旧显示为车速车标 | P2 |  |  | FB_R00_ENG
APIMCIM-26442 | Baidu | Phase 5：【偶现】挂R档进360后，退出360页面页面冻屏，点击地图无效 | P2 |  |  | FB_R00_ENG
APIMCIM-26425 | Baidu | [U625MCA][100%] No TTS broadcasts while playing the VIP program. | P2 |  |  | FB_R00_ENG
APIMCIM-26378 | Baidu | [U625MCA][100%] Wrong voice feedback when VPA query POI during navigation. | P2 |  |  | FB_R00_ENG
APIMCIM-26105 | Baidu | [U625MCA][100%]Incomplete display of smart parking fee rules | P2 |  |  | FB_R00_ENG
APIMCIM-24777 | Baidu | 【625】【语音】车机系统控制-语音“更换主题”/手动切换主题-TTS“已为你找到如下语音帮助***” | P2 |  |  | FB_R00_ENG
APIMCIM-22716 | Baidu | [U625MCA][100%] Voice feedback error when VPA exit Idiom Solitaire without game | P2 |  |  | FB_DCV4_ENG
APIMCIM-22513 | Baidu | Phase 5：【必现】子POI推荐框和限行提醒重叠显示 | P2 |  |  | FB_DCV4_ENG
APIMCIM-22471 | Baidu | Phase 5：【必现】导航页面提示语有些在页面上方，有些在页面下方，建议跟707一样统一在页面下方 | P2 |  |  | FB_DCV4_ENG
APIMCIM-22443 | Baidu | Phase 5：【必现】VR:增加导航音量。无TTS无响应 | P2 |  |  | FB_DCV4_ENG
APIMCIM-22419 | Baidu | Phase 5：【必现】恢复默认设置后，车标设置变成车速车标 | P2 |  |  | FB_DCV4_ENG | [5 empty] | Request_Reject
APIMCIM-22406 | Baidu | Phase 5：【必现】首次进入地图，提示“四指左滑或点击仪表可同步开启仪表地图显示”，但地图首页无仪表按钮 | P2 |  |  | FB_DCV4_ENG | [5 empty] | Request_Reject
APIMCIM-15766 | Baidu | [Phase5][U625MCA][VPA][必现]一语唤醒”打电话“，VPA形象显示正确，但无TTS”你要打给谁”语音播报 | P2 |  |  | LC_DCV3_ENG
APIMCIM-14316 | Baidu | Phase5_【U625MCA】【必现】【launcher】所有应用--小程序在分屏模式下，小程序推荐和分类界面显示不全且无法滑动 | P2 |  |  | FB_DCV2_ENG
APIMCIM-6939 | Baidu | Phase 5：【必现】Launcher页面导航卡片显示不正确 | P2 |  |  | FB_DCVBeta_ENG

## Metrics
Process | Proposed KPI | Target / Norm | Operational Definition | Archivement Time | Week/Month | Comments
SWE.1.Software Requirements Analysis | Software Requirements Reviewed Rate % | 100% | Number of approved(reviewed) Software Requirements/ Number of Software Requirements | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.2.Software Architectural Design | SW Architectural to SW Requirement Coverage Rate | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.3 Software Detailed Design and Unit Construction | Traceable Software requirements(Jira Story) to the code | 100% | All Jira requirements should have a corresponding software unit in GIT | SOP: All requirement Formal release scope : The requirements planned to be released in this version. |  | Using Traceability From Code to Requirement&Change_Template to show the evidence.
SWE.3 Software Detailed Design and Unit Construction | SW detail design to SW Architectural Coverage | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.4 Software Unit Verification | Unit test（Code） coverage | >= 80 % | (Conditions True + Conditions False + Covered Lines)/(2*Conditions + Executable Lines) | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.4 Software Unit Verification | Static Code Analysis Number of Critical Bugs | 0 | Static Code result in Sonar. | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Planned Integration Test cases vs. actual executed integration test cases | 100% | Percentage of SW integration Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Software Integration Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Software Integration Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Software Integration Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | SW architecture design test coverage (HLD with Ready State test cases) | 100% | (Number of HLD SQD have integraton test Case + Number of Interface have integration test case)/(Number of HLD SQD + Number of interface) | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software IntegrationTest | Count of Software Integration Test defects | 0 | Count of Integration Defects | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Planned Qualification test cases vs. actual executed Qualification test cases | 100% | Percentage of SW Qualification Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | SW requirement test coverage | 100% | Percentage of Requirements in Jira that has corresponding test cases in TestRail | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Count of Software Qualification test defects | 0 | Count of Defects raised in the SW Qualification Testing Phase | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.1 Quality Assurance | NC closure rate | 90% | Closed NC/Total NC | Monthly
SUP.1 Quality Assurance | Process Audit compliance | 100% | Percentage of audits completed on time | Monthly
SUP.8 Configuration Management | Nightly builds have a success rate | 100% | Percentage of compliance as defined in the process audit checklist | Every Sprint
SUP.8 Configuration Management | Ba'seline completed Rate | 100% | Count of of actually baseline CI Item number/ Count of Planned baseline CI item Number | Monthly
SUP.8 Configuration Management | CM Audit Passrate | 100% | Passrate of CM Audit Checklist: Count of passed Number in CM Audit Checklist/total planned CM Audit Checklist | Monthly
SUP.9 Problem Resolution Management | Immediate Gating/Gating （Critical） defects for release | 0 | All urgent defects actioned on high priority, | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.9 Problem Resolution Management | Problem closure adherence | 100% | No. of defects closed against no. of defects planned for closure in this release （Include Project deviation issue and Defect） | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.9 Problem Resolution Management | Defect fix time | <40 | Defect fix time | Every Sprint
SUP.9 Problem Resolution Management | Count of IG&G defect @current version | <1 | Count of IG&G defect @current version | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.10 Change Request Management | Change Request status closure % | 100% | No. of Change Requests completed / Total number of change requests raised in the version | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
MAN.3 Project Management | Requirement Completion Rate for sprint/Milestone | > 85% | No. of requirements delivered / No. of requirements committed for this sprint/Milestone | Every Sprint/Milestone
MAN.3 Project Management | Commitment Adherencen for All Requirement | 100% | No. of requirements delivered / No of requirements Committed for all requirement | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
Software Metrics Conlusion
Metrics Summary:

## Sign off Evidence
截图必须包含 ： 版本号 发起sign off 的名字 Approve 者的名字 Sign off的时间 Note： 1. Sign off的版本以供应商测试完的时间点; 2. Milestone release 副总签字,OKTB/OTA 要求总经理签字； Inhouse： Milestone release LL5, OKTB/OTA: LL4;