## 首页
|  |  |  | 文件No. | 页数
|  |  |  | ThunderSoft-QMS-18-JL17 | 5
<Ford Phase5>测试用例执行
历史记录
版本号 | 日期 | 作者/修订者 | 制订/修改内容 |  |  | 评审人/评审日期 | 评审要求
V1.0 | 2021-07-04 | 邓荣祥 | 创建
V1.1 | 2022-03-06 | 陈传勤 | 优化相关模块测试用例
V1.2 | 2022-11-26 | 李可可 | 优化首页内容展示

## Summary-DCV2
U718_DCV2测试报告
软件版本 | SOC：20230309_LB_DCV2_ENG00 MCU：20230310_LB_DCV2_ENG00 ECG: ECG2-milestone-2023-01-Bundle-Release_EH_maps-0.0.42.256 TCU: TCU2-milestone-2023-01-modem6-Bundle-Release-China-2.2.2.133 |  |  |  | 测试范围 | 1、所有Fetaure 2、只包含创达开发范围
测试硬件 | B&C |  |  |  | 测试人员 | 姜云腾&关满意&李可可&袁露&杨春明&肖文迪&徐成龙&黄钊敏&赵雅非
测试方法 | 手动 |  |  |  | 测试环境 | 台架
项目经理 | 余琦 |  |  |  | 项目总监 | 陈凯
总结 | 总体说明：本轮DCV2测试，Focus测试，涉及模块34个，整体Pass率为92.12%，执行率为93.58% 一、DCV2交付模块说明： 本轮新增的测试模块：Account、多功能座椅（CR）、MMOTA、STR 本轮未测试模块：①个性化设置档案（Enhance Memory）——FO已确认DCV3交付； ② 哨兵模式——DCV3交付 二、通过率详情： 1）Pass率<=70%的模块1个 ①FNV诊断：APIMCIM-18679：FNV诊断中上传日志到云端，有概率无法连接云端，报503，影响case【13】——ford分析中 2）70%<=Pass率<=90%的模块10个 ①Account：首轮测试有3个BUG，其中关键APIMCIM-18405：账号登录失效，无法出现弹窗：“账号登录，你的账号登录失效，请重新登录，影响case【5】——ford分析中 ②MMOTA：APIMCIM-19576 VI升级TCU，熄火后无法进入激活-点火查看更新详情无“立即激活”按钮，影响case【21】——YF分析中 APIMCIM-19574 USB升MCU，ECG打印S1007，IG=OFF，激活失败，IVI弹出更新失败弹窗，影响case【14】——YF分析中 ③拖车：APIMCIM-16233：点击想要激活的拖车，TX(45C)指令下发不对，影响case【4】、APIMCIM-15469点击待激活拖车，无法正确下发TX信号215，影响case【6】、APIMCIM-16298编辑宽度值后，没有下发TX信号0x288（拖车360设置编辑也未下发288信号），影响case【18】——信号相关问题，YF分析中 ④Audio 外置(24ch)：APIMCIM-17092：车随音速无效果，影响Case【31】——ford_dsp分析中 ⑤PAAK：APIMCIM-18570：创建个人车门解锁密码过程中途会弹出“原厂密码不匹配”且会更改界面标题。完成以后无法弹出“连接超时”弹窗，影响case【7】——对手键BCM问题，影响整体使用效果 ⑥Car Audio音源矩阵(24ch)：MDO和MDR环境未做好【18】——YF ⑦WIR：APIMCIM-15605：APN2 unable to be established，影响case【5】——IG问题，ford分析中；APIMCIM-18093：连接需要认证的wifi，会自动变为未连接，之后连接其他wifi会出现相同情况，影响case【1】_ford分析中 ⑧Car Power：718硬按键有问题，无法测试相关用例【11】 ⑨STR：APIMCIM-19560：进入STR模式后，无法正常退出STR模式（使用一段时间后出现的问题） ——YF分析中 ⑩车载热点，单点问题分布，暂无关键问题 3）Pass率>90%的模块7个 VCS、Vehicle Setting、AAR、蓝牙儿童座椅、Theme、DLNA，3D车模，BUG详情见列表 4）Pass率=100%的模块16个
问题列表
FeatureID | 模块 | DCV2通过率 | 影响Case数 | BugID | Bug标题 |  | 严重程度 | 状态 | 归属 | 分析
SYNC+_Z0037 | FNV诊断 | 48% | 13 | APIMCIM-18679 | Phase5_【U718】【偶现】【FNV】FNV诊断中上传日志到云端，有概率无法连接云端，报503 |  | Gating | TO DO | ford
SYNC+_0164 | Account | 70.97% | 5 | APIMCIM-18405 | Phase5_【U718】【黑盒】【必现】【Account】账号登录失效，无法出现弹窗：“账号登录，你的账号登录失效，请重新登录” |  | High | TODO | Ford | 分析中
|  |  | 3 | APIMCIM-18406 | Phase5_【U718】【黑盒】【必现】【Account】账号登录界面，新手引导界面无法进入 |  | High | TODO | Ford | 分析中
|  |  | 1 | APIMCIM-18411 | Phase5_【U718】【黑盒】【偶现】【1/20】【Account】登录账号的实际个数与账号管理中个数不一致 |  | High | TODO | Ford | 分析中
SYNC+_Z0127 | Audio 外置(24ch) | 74.74% | 10 | APIMCIM-18224 | Phase5_【U718】【黑盒】【必现】【CarAudio】【24ch】chime压制音Attenuation 6无压制效果 |  | high | TO DO | ford
|  |  | 8 | APIMCIM-15987 | Phase5_【U718】【黑盒】【必现】【Car-audio】音量设置中通话，语音，提示音不生效 |  | high | TO DO | YF
|  |  | 31 | APIMCIM-17092 | Phase5_【U718】【黑盒】【必现】【Car_Audio】【24ch】车随音速无效果 |  | Gating | TO DO | ford | DSP分析中
| STR | 75% | 1 | FCIVIOS-14322 | Phase5_【U718】【黑盒】【必现】【STR】车载热点开关打开状态，进入STR模式，再退出STR模式，车载热点开关却是关闭状态 |  | High | TO DO | TS | 分析中
|  |  | 1 | APIMCIM-19560 | Phase5_【U718】【黑盒】【Car Power】【必现】进入STR模式后，无法正常退出STR模式（使用一段时间后出现的问题） |  | IG | TO DO | YF
|  |  | 1 | APIMCIM-19326 | Phase5_【U718】【黑盒】【单机必现】【System】正常连接后，控制屏黑屏无法使用，使用投屏软件在电脑上投屏时，报错 |  | High | TO DO | YF | 分析中
SYNC+_0106 | PAAK | 80.56% | 7 | APIMCIM-18570 | Phase5_【U718】【黑盒】【必现】【PAAK】创建个人车门解锁密码过程中途会弹出“原厂密码不匹配”且会更改界面标题。完成以后无法弹出“连接超时”弹窗 |  | Gating | TO DO | BCM对手键 | 正在跟踪对手键解决
|  |  | 4 | FCIVIOS-14069 | Phase5_【U718】【黑盒】【必现】【PAAK】密码包含大写字母+小写字母+数字（存在不连续重复数字或字母时）满14位时，预期显示强，实际显示好 |  | High | In Progress | TS | 分析中
|  |  | 1 | FCIVIOS-14222 | Phase5_【U718】【黑盒】【必现】【PAAK】密码最多64位，目前未做密码长度限制 |  | High | Test | TS | DCV3合入
|  |  | 1 | FCIVIOS-12385 | Phase5_【U718】【黑盒】【必现】【paak】SPSS中要求密码包含xato-net-10-million-passwords-10000.txt里面字符串时，等级不得高于“一般” |  | High | In Progress | TS | 分析中
|  |  | 1 | FCIVIOS-12763 | Phase5_【U718】【黑盒】【必现】【PAAK】重置智能备用钥匙-密钥输入锁定，发送RX后，没有弹出预期弹窗 |  | High | TO DO | TS | 分析中
|  |  | 1 | FCIVIOS-14072 | Phase5_【U718】【黑盒】【偶现】【PAAK】偶现无故弹出”搜索中“，且无法取消弹窗 |  | High | TO DO | TS | 分析中
|  |  | 1 | FCIVIOS-14236 | Phase5_【U718】【黑盒】【必现】【paak】重置智能备用密钥->无法正确弹出车门解锁密码保存失败的弹窗 |  | High | TO DO | TS | 分析中
|  |  | 1 | FCIVIOS-14227 | Phase5_【U718】【黑盒】【偶现】【50%】【PAAK】重置智能密钥->请输入原密码界面，偶现密码输入框无法输入密码 |  | High | TO DO | TS | 分析中
|  |  | 1 | FCIVIOS-13989 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥时，输入车辆启动的密码时，弹窗会把密码输入框遮挡 |  | High | TO DO | TS | 分析中
|  |  | 1 | FCIVIOS-14082 | Phase5_【U718】【黑盒】【必现】【PAAK】输入车辆启动密码后，点击确定，加载过程中会有主菜单按扭出现，且可点击，从而跳出密码界面 |  | High | TO DO | TS | 分析中
|  |  | 3 | FCIVIOS-14084 | Phase5_【U718】【黑盒】【必现】【PAAK】”密码输入次数已经超过最大限制“无法弹出 |  | High | TO DO | TS | 分析中
|  |  | 1 | FCIVIOS-14086 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥启动车辆，输入正确密码后，无法弹出密码正确弹框 |  | High | TO DO | TS | 分析中
|  |  | 1 | FCIVIOS-14087 | Phase5_【U718】【黑盒】【必现】【PAAK】IG=off时，输入密码弹窗右上角存在关闭按扭，预期没有关闭按扭 |  | High | TO DO | TS | 分析中
|  |  | 3 | FCIVIOS-14088 | Phase5_【U718】【黑盒】【必现】【PAAK】密码界面未使用监听，未对这三个条件进行判断（启动状态、Delay accessory已启⽤、extended play已启⽤） |  | High | TO DO | TS | 分析中
|  |  | 1 | FCIVIOS-14089 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥时，密码输入框未收到信号后，无法弹出toast"系统错误，无法完成该请求" |  | High | TO DO | TS | 分析中
|  |  | 6 | FCIVIOS-14090 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥时，密码正确密码后，无法弹出”密码正确，车辆已成功解锁" |  | High | TO DO | TS | 分析中
|  |  | 1 | FCIVIOS-14091 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥时，密码连续输入五次错误，没有提示超过最大次数 |  | High | TO DO | TS | 分析中
SYNC+_Z0098/SYNC+_Z1029/SYNC+_Z1030/SYNC+_Z1033/SYNC+_Z1034/SYNC+_Z1036/SYNC+_Z1039/SYNC+_Z1050 | 拖车 | 81.11% | 1 | FCIVIOS-14096 | Phase5_【U718】【黑盒】【必现】【拖车】添加第10个拖车，是否继续建立选择否，在名称界面时，修改名称为另外的名称。保存会跳转到车机主界面，预期提示超过10个拖车 |  | high | TO DO | TS
|  |  | 4 | APIMCIM-16233 | Phase5_【U718】【黑盒】【必现】【拖车】点击想要激活的拖车，TX(45C)指令下发不对 |  | Gating | TO DO | YF
|  |  | 6 | APIMCIM-15469 | Phase5_【U718】【黑盒】【必现】【拖车】点击待激活拖车，无法正确下发TX信号215 |  | Gating | TO DO | YF
|  |  | 1 | FCIVIOS-14013 | Phase5_【U718】【黑盒】【偶现】【拖车】激活某个拖车后，偶现激活界面拖车的排序不正确 |  | high | TO DO | TS
|  |  | 1 | FCIVIOS-11169 | Phase5_【U718】【黑盒】【必现】【拖车】所有infobook文案未提供，当前只有图标无法点击查看 |  | high | TO DO | TS
|  |  | 5 | APIMCIM-15810 | Phase5_【U718】【黑盒】【必现】【拖车】满足拖车报警开关条件后，该按扭仍然是置灰状态，不可点击 |  | high | reopen | YF
|  |  | 18 | APIMCIM-16298 | Phase5_【U718】【黑盒】【必现】【拖车】编辑宽度值后，没有下发TX信号0x288（拖车360设置编辑也未下发288信号） |  | Gating | TO DO | YF
|  |  | 1 | APIMCIM-19295 | Phase5_【U718】【黑盒】【必现】【拖车】连接上BCM以后，拖车灯的弹窗会反复弹。查看其信号在跳变 |  | high | TO DO | BCM对手键 | 正在跟踪对手键解决
|  |  | 1 | FCIVIOS-14211 | Phase5_【U718】【黑盒】【必现】【拖车】通知=打开&有激活的拖车，选择弹窗“查看设置”，跳转到拖车设置界面后，会弹出重量设置弹窗 |  | Medium | TO DO | TS
|  |  | 1 | FCIVIOS-14017 | Phase5_【U718】【黑盒】【必现】【拖车】通知=打开&有激活的拖车，检测到拖车连接，选择弹窗的“添加拖车”预期跳转到拖车主界面并激活默认拖车，实际未跳转也未下发TX信号 |  | high | TO DO | TS
|  |  | 1 | FCIVIOS-14021 | Phase5_【U718】【黑盒】【必现】【拖车】界面停在选择激活拖车界面时，出现“检测到拖车连接”弹窗，点击添加拖车后，拖车名称输入异常 |  | high | TO DO | TS
|  |  | 1 | FCIVIOS-13991 | Phase5_【U718】【黑盒】【必现】【拖车】拖车里面有部分场景未适配主题（汇总） |  | high | test | TS | DCV3合入
SYNC+_0223 | MMOTA | 82.59% | 7 | APIMCIM-19463 | Phase5_【U718】【必现】【MMOTA】升级成功打印S1010，IG=RUN启动车机后会重启一次 |  | High | TODO | YF | 分析中
|  |  | 1 | FCIVIOS-14410 | Phase5_【U718】【必现】【MMOTA】切换主题后进行VI-OTA升级-未设定日程-待激活阶段点击系统日程未设定弹窗“立即激活”button显示不全 |  | High | test | TS | DCV3合入
|  |  | 21 | APIMCIM-19576 | Phase5_【U718】【必现】【MMOTA】VI升级TCU，熄火后无法进入激活-点火查看更新详情无“立即激活”按钮 |  | Gating | TODO | YF | 分析中
|  |  | 14 | APIMCIM-19574 | Phase5_【U718】【黑盒】【必现】【MMOTA】USB升MCU，ECG打印S1007，IG=OFF，激活失败，IVI弹出更新失败弹窗 |  | Gating | TODO | YF | 分析中
SYNC+_0126_Car Audio | Car Audio音源矩阵(24ch) | 82.96% | 2 | APIMCIM-18289 | Phase5_【U718】【黑盒】【偶现】【音源矩阵】【24ch】来电前点击播放蓝牙音乐，挂断电话后蓝牙音乐未进行播放 |  | high | TO DO | ford | 分析中
|  |  | 3 | APIMCIM-18444 | Phase5_【U718】【黑盒】【必现】【CarAudio】【24ch】百度地图导航时点按power键，导航声音会暂停 |  | high | TO DO | YF | 分析中
|  |  | 18 | NT | MDO和MDR环境未做好 |  |  |  | YF
SYNC+_Z0060 | Car Power | 85.14% | 11 | NT | 718硬按键有问题，无法测试相关用例
SYNC+_Z0043 | WIR | 86.96% | 1 | APIMCIM-18093 | Phase 5_【U718】【必现】【WiFi Setting】连接需要认证的wifi，会自动变为未连接，之后连接其他wifi会出现相同情况 |  | Gating | TO DO | Ford
|  |  | 5 | APIMCIM-15605 | Phase5:[U718][50%] APN2 unable to be established |  | IG | In Progress | Ford
SYNC+_Z0155 | 车载热点 | 89.47% | 1 | APIMCIM-16358 | Phase5_【U718】【必现】【Hotspot】连接车载热点，手机无法上网 |  | High | TO DO | Ford | 需要北美分析原因
|  |  | 1 | APIMCIM-18194 | Phase5_【U718】【黑盒】【必现】【WiFi Hotspot】调整里程数<16km后，复位wifi热点，车载热点没有变为默认关闭状态 |  | High | TO DO | Ford | 需要北美分析原因
SYNC+_0205 | Theme | 91.67% | 1 | FCIVIOS-14370 | Phase5_【U718】【黑盒】【必现】【VehicleSettings】切换主题后，车控车设的选择按扭和菜单显示异常 |  | High | TO DO | TS
SYNC+_0021 | DLNA | 93.33% | 1 | APIMCIM-18287 | Phase5_【U718】【黑盒】【必现】【DLNA】手机连接上DLNA车机热点，在线视频可以正常播放，第一次投屏加载不出内容，退出后，无法投屏 |  | High | TO DO | YFVE | 等待YF分析
SYNC+_0266 | 3D车模 | 95.15% | 3 | APIMCIM-16536 | Phase5_【U718】【黑盒】【必现】【3D车模】处于RVC界面，底部不会显示灯光按钮 |  | High | TODO | TS | 待分析
|  |  | 8 | FCIVIOS-14257 | Phase5_【U718】【黑盒】【必现】【3D车模】配置氛围灯DE01=varient 2，发送信号=64，点击亮度为20时，亮度条不在20的竖线上且TX会下发一个off的值 |  | High | TODO | TS | 待分析
|  |  | 1 | FCIVIOS-14364 | Phase5_【U718】【黑盒】【必现】【3D车模】发送位置灯信号，车模中间位置灯无亮度变化 |  | High | Test | TS | DCV3合入
|  |  | 1 | FCIVIOS-14270 | Phase5_【U718】【黑盒】【必现】【3D车模】进入车内点击故障 |  | High | TODO | TS | 待分析
|  |  | 1 | FCIVIOS-14053 | Phase5_【U718】【黑盒】【必现】【3D车模】进入3D车模音效点击更多按钮，音效图标位置与系统设置显示不一致 |  | High | TODO | TS | 待分析
|  |  | 9 | NT | 车模颜色未适配NT，等待UI/UE签收 |  |  |  | TS
|  |  | 2 | NT | 后备箱运动中双击暂停需实车测试 |  |  |  | TS
| VCS | 95.65% | 2 | FCIVIOS-14071 | Phase5_【U718】【黑盒】【必现】【HVAC】语音“增大/减小后排空调风量”，TTS反馈“后排空调风量已增大/减小” |  | Medium | TO DO | TS | 未分析
|  |  | 2 | FCIVIOS-14070 | Phase5_【U718】【黑盒】【必现】【HVAC】语音“增大/减小后排空调温度”，TTS反馈“空调温度已调高/调低” |  | Medium | TO DO | TS | 未分析
SYNC+_0132 | AAR | 97.06% | 1 | FCIVIOS-14278 | Phase5_【U718】【黑盒】【必现】【AAR】台架无法获取滤芯状态，一直报网络异常请稍后重试 |  | High | TO DO | TS
|  |  | 1 | APIMCIM-18407 | Phase5_【U718】【黑盒】【偶现】【50%】【AAR】AAR语音弹窗，偶现没有语音播报 |  | High | Test | TS | DCV3合入
SYNC+_Z0129 | 蓝牙儿童座椅 | 97.3% | 1 | FCIVIOS-14058 | Phase5_【U718】【黑盒】【必现】【Vehicle Settings】播放蓝牙音乐，连接儿童座椅TTS播报时，蓝牙音乐音量没有降低 |  | medium | TODO | TS | 待分析
SYNC+_Z0210/SYNC+_Z0204/SYNC+_Z0278/SYNC+_Z0281/SYNC+_Z0277/SYNC+_Z0197/SYNC+_Z0187/SYNC+_Z0180/SYNC+_Z0178/SYNC+_Z0183/SYNC+_Z0181/SYNC+_Z0182/SYNC+_Z0206/SYNC+_Z0215/SYNC+_Z0212/SYNC+_Z0217/SYNC+_Z0216/SYNC+_Z0213/SYNC+_Z0201/SYNC+_Z0214/SYNC+_Z0209/SYNC+_Z0211/SYNC+_0074 | Vehicle Setting | 98.34% | 1 | FCIVIOS-14041 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】当前未配置功能，依旧可以搜索出车控功能 |  | High | test | TS
|  |  | 1 | APIMCIM-18617 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】点击切换驾驶模式 切换主题后，自动跳转至灯光设置界面 |  | High | To do | YF
|  |  | 12 | NT | 座椅界面需实车验证查看【12】

## 模块详细数据-DCV2
模块详细数据
FeatureID | Moudle | Total | Pass | Fail | Block | NT | DCV2_Pass Rate （Pass/Total） | DCV2_Run Rate （Pass+Fail）/Total | 测试/开发 | DCV1_Pass Rate （Pass/Total） | 通过率是否下降 | 下降主要原因 | 车辆信息 | 测试时长 | Comments | 重点模块
SYNC+_0106 | PAAK手机钥匙 | 180 | 145 | 17 | 18 | 0 | 80.56% | 90% | 赵雅非/许超 | 67.24% | 否 |  | / | / |  | 否
SYNC+_Z0032 | CCS | 54 | 54 | 0 | 0 | 0 | 100% | 100% | 李可可/于凯凯 | 91.4% | 否 |  | / | / |  | 否
SYNC+_0266 | 3D车模 | 515 | 490 | 4 | 10 | 11 | 95.15% | 95.92% | 肖文迪/李行健 | 33.02% | 否 |  | / | / |  | 否
SYNC+_Z0081 | Car input | 44 | 44 | 0 | 0 | 0 | 100% | 100% | 袁露/贺金 | 89.38% | 否 |  | / | / |  | 是
SYNC+_0126 | 音源矩阵(Ecall)-(24ch) | 135 | 112 | 2 | 3 | 18 | 82.96% | 84.44% | 袁露/杨永恒 | 70.46% | 否 |  | / | / |  | 是
SYNC+_0073 | FAPA | 176 | 176 | 0 | 0 | 0 | 100% | 100% | 赵雅非/顾佳宁 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0098/SYNC+_Z1029/SYNC+_Z1030/SYNC+_Z1033/SYNC+_Z1034/SYNC+_Z1036/SYNC+_Z1039/SYNC+_Z1050 | 拖车 | 217 | 176 | 12 | 29 | 0 | 81.11% | 86.64% | 赵雅非/董昑禹 | 86.01% | 是 | 问题单数量没有新增，用例基数下降 | / | / |  | 是
SYNC+_Z0026 | Multi -display | 16 | 16 | 0 | 0 | 0 | 100% | 100% | 肖文迪/贺金 | 100% | 否 |  | / | / |  | 是
| VCS | 92 | 88 | 2 | 2 | 0 | 95.65% | 97.83% | 袁露&关满意&黄钊敏&肖文迪/张嘉 | 80.18% | 否 |  | / | / |  | 是
SYNC+_Z0127 | Audio 外置(24ch) | 194 | 145 | 3 | 46 | 0 | 74.74% | 76.29% | 袁露/杨永恒 | 84.41% | 是 | 新增APIMCIM-18224，影响整体通过率 | / | / |  | 是
SYNC+_Z0210/SYNC+_Z0204/SYNC+_Z0278/SYNC+_Z0281/SYNC+_Z0277/SYNC+_Z0197/SYNC+_Z0187/SYNC+_Z0180/SYNC+_Z0178/SYNC+_Z0183/SYNC+_Z0181/SYNC+_Z0182/SYNC+_Z0206/SYNC+_Z0215/SYNC+_Z0212/SYNC+_Z0217/SYNC+_Z0216/SYNC+_Z0213/SYNC+_Z0201/SYNC+_Z0214/SYNC+_Z0209/SYNC+_Z0211/SYNC+_0074 | Vehicle Setting | 842 | 828 | 2 | 0 | 12 | 98.34% | 98.57% | 关满意/王闯&许超&石松&董晗禹 | 95.38% | 否 |  | / | / |  | 是
SYNC+_Z0155 | 车载热点 | 19 | 17 | 2 | 0 | 0 | 89.47% | 100% | 李可可/于凯凯 | 100% | 是 | 新增2个BUG，依赖北美分析 | / | / |  | 否
SYNC+_Z0028 | Rear audio（24ch） | 28 | 28 | 0 | 0 | 0 | 100% | 100% | 袁露/李行健 | 69.32% | 否 |  | / | / |  | 是
SYNC+_Z0043 | WIR | 46 | 40 | 2 | 4 | 0 | 86.96% | 91.3% | 杨春明/张金海 | 100% | 是 | 新增一个外部BUG影响通过率 | / | / |  | 否
SYNC+_0132 | AAR | 68 | 66 | 2 | 0 | 0 | 97.06% | 100% | 赵雅非/杨永恒 | 95.74% | 否 |  | / | / |  | 否
SYNC+_Z0159--SYNC+_Z0177 | HVAC | 105 | 105 | 0 | 0 | 0 | 100% | 100% | 姜云腾/窦歆禹 | 100% | 否 |  | / | / |  | 是
SYNC+_0205 | Theme | 12 | 11 | 1 | 0 | 0 | 91.67% | 100% | 赵雅非/董晗禹 | 100% | 是 | 新增BUG | / | / |  | 是
SYNC+_0134 | 数字香氛 | 35 | 35 | 0 | 0 | 0 | 100% | 100% | 肖文迪/董晗禹 | 93.15% | 否 |  | / | / |  | 是
SYNC+_Z0050 | 无线充电 | 5 | 5 | 0 | 0 | 0 | 100% | 100% | 赵雅非/王跃鑫 | 100% | 否 |  | / | / |  | 是
SYNC+_Z1000 | Launcher | 128 | 128 | 0 | 0 | 0 | 100% | 100% | 袁露/肖梁 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0060 | Car Power | 74 | 63 | 0 | 0 | 11 | 85.14% | 85.14% | 李可可/秦诚 | 89.68% | 是 | 本轮foucs测试，用例基础数据不同了 | / | / |  | 是
SYNC+_Z0153 | GNSS | 32 | 32 | 0 | 0 | 0 | 100% | 100% | 李可可/卓明琼 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0036 | Bezel Diagnostics工程模式 | 47 | 47 | 0 | 0 | 0 | 100% | 100% | 李可可/于凯凯 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0129 | 蓝牙儿童座椅 | 37 | 36 | 1 | 0 | 0 | 97.3% | 100% | 黄钊敏/南东东 | 71.43% | 否 |  | / | / |  | 是
SYNC+_0264 | EMR | 46 | 46 | 0 | 0 | 0 | 100% | 100% | 姜云腾/窦歆禹 | 100% | 否 |  | / | / |  | 是
SYNC+_0021 | DLNA | 15 | 14 | 1 | 0 | 0 | 93.33% | 100% | 李可可/贺金 | 96.88% | 是 | 新增一个BUG影响通过率 | / | / |  | 是
SYNC+_0073 | 雷达 | 207 | 207 | 0 | 0 | 0 | 100% | 100% | 黄钊敏/蔡宇飞 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0037 | FNV诊断 | 25 | 12 | 1 | 12 | 0 | 48% | 52% | 李可可/于凯凯 | 96.43% | 是 | APIMCIM-18648，ford分析中 | / | / |  | 否
| V2I | 45 | 45 | 0 | 0 | 0 | 100% | 100% | 肖文迪/董晗禹 | 97.96% | 否 |  | / | / |  | 否
SYNC+_0122 | VHA | 85 | 85 | 0 | 0 | 0 | 100% | 100% | 肖文迪/胡远征 | 87.35% | 否 |  | / | / |  | 否
SYNC+_Z0033 | Provisioning | 4 | 4 | 0 | 0 | 0 | 100% | 100% | 李可可/于凯凯 | 100% | 否 |  | / | / |  | 否
SYNC+_0164 | Account | 31 | 22 | 3 | 6 | 0 | 70.97% | 80.65% | 赵雅非/ford | / | 否
| STR | 12 | 9 | 3 | 0 | 0 | 75% | 100% | 黄钊敏/秦诚 | / | 否
SYNC+_0223 | MMOTA | 247 | 204 | 4 | 39 | 0 | 82.59% | 84.21% | 李可可&黄钊敏/陈明瑶&刘畅 | / | 否
Total |  | 3818 | 3535 | 62 | 169 | 52 | 92.59% | 94.21%

## 重点模块列表 (hidden)
DLNA
Car Power
Car input
Theme
GNSS
Rear audio
Launcher
Audio 内置
Audio 外置（12ch）
Audio 外置（24ch）
音源矩阵(Ecall-12ch)
音源矩阵(Ecall-24ch)
音源矩阵(Ecall)
Vehicle Setting
数字香氛
无线充电
Multi -display
FCS(Account)
Bezel Diagnostics工程模式
个性化设置档案
HVAC
VCS
雷达
FAPA
powerflow能量流
EMR
蓝牙儿童座椅

## R06.1_Fix (hidden)
Issue key | Summary | Reporter | Status | Assignee | Component/s | Labels | Labels | Priority | Fix Version/s
APIMCIM-13801 | Phase 5：【必现】路试时，副驾有人，打开爱奇艺播放视频，卡顿并闪退 | jsun62 | Approval | jsun62 | Video | CDX707 | Inhouse_Platform | Immediate Gating | LA_R06.1_ENG
APIMCIM-9608 | [100%] MMOTA_China: Upgrade TCU by VI, the sync+ screen turns black when vehicle enters inhibit state | jzhan376 | Approval | jzhan376 | MMOTA | Inhouse_Platform | MigratingToCloud | Immediate Gating | LA_R06.1_ENG
APIMCIM-13273 | 【Phase V】【CDX707】【TOP】【DLNA】【5/5】TCU网环境下媒体投射开关异常，各模式也无法开启关闭 | lshi42 | Approval | zqiu12 | DLNA | CDX707 | Inhouse_Platform | Immediate Gating | LA_R06.1_ENG
APIMCIM-11765 | Phase5:[必现][CDX707]点击车模上的故障预警无法跳转到故障详情页 | xwang310 | Done | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | Immediate Gating | LA_R06_ENG
APIMCIM-13930 | Phase 5：【偶发】实车路试时，后台总是发生com.ford.sync.apa Crash | jsun62 | Approval | jsun62 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13540 | [100%] MMOTA_China: Entering into "preparing to update" page, ignition run, update failure has pop up, but updating progress still dominating the screen. | yli391 | Approval | yli391 | MMOTA | CDX707 | ECG | Gating | LA_R06.1_ENG
APIMCIM-13080 | 【Phase V】【CDX707】【R06.1-Production】【A】【2/20】移动widget card出现重叠或不显示 | zliu151 | Approval | zliu151 |  | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13745 | [10%] MMOTA_China: OTA updating SOC on vehicle, occasionally SOC installation failed. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13230 | Phase 5：【必发】H689272 13：59 在空调界面点击智能新风，提示“获取滤芯状态失败，联系客服 错误代码：-300” | hmo3 | Test | cchen244 | Auto Air Refresh | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12618 | Phase5:[必现][CDX707]发动机没启动IVI上显示车辆故障信息 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10295 | Phase5:[100%][CDX707] [CCS]After powercycle，no ccs sharing popup | qshi14 | Approval | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12602 | Phase5:[必现][CDX707]After Master reset, no ccs sharing popup | qshi14 | Approval | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13303 | [100%] MMOTA_China:Update TCU by VI and the activation conditions are not met, IVI does not pop up the corresponding pop-up according to the type of precondition | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12274 | Phase5:[偶现]DTC 0xE40100 | xhuang93 | In Progress | mzhuo1 | Diagnostic | EOL | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13402 | 【Phase V】【CDX707】【A】【儿童座椅】【5/5】车辆设置中儿童座椅功能无法进入，点击闪退 | zqiu12 | Approval | zqiu12 | BT Child Seat | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13276 | 【Phase V】【CDX707】【A】【TC】【5/5】睡眠唤醒、首次上电或切换两次驾驶模式后，瞬时油耗指示归零 | xdu22 | Approval | xdu22 |  | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13138 | 【Phase V】【CDX707】【A】【Audio】【5/5】24ch功放，播放音乐，触发关机动画，恢复Run状态后，音乐播放无声. | ywang535 | Approval | ywang535 | Audio | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13729 | Phase5_【CDX707】【黑盒】【必现】【MMOTA】VI-TCU，安装结束后，IG=off，车辆不进入激活状态，更新失败 | cyang114 | Closed with Accept | gyuan6 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12714 | [CDX707][Performance][ResponseaTime]Launcher显示到SDM可用响应时间过长，需要优化。 | ljia14 | Approval | ljia14 | System Performance | CDX707 | digitalee | Gating | LA_R06.1_ENG
APIMCIM-12893 | Phase 5：【偶发】断网后，发生com.ford.sync.fnvservice/com.yfve.report Crash | jsun62 | Approval | jsun62 | FNV | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12738 | Phase 5：【偶发】首页widget编辑页，重复快速拖动改变卡片和位置，launcher发生闪退 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12646 | Phase 5：【必现】Launcher主页3D车模不显示 | hzhan238 | Approval | hzhan238 | 3D Vehicle model | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12795 | Phase 5：【必现】唤醒语音：播放/上一首/下一首，USB音乐播放，但Audio off并未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12217 | Phase 5：【偶发】RACM端切源到随心听，随心听播放页显示错误的歌曲信息 | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-11450 | 【R05-回归测试】【广场】【必现】03:15 我的收藏编辑页面退出后会弹应用商店弹窗 | ntian2 | Approval | ntian2 | Launcher | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-11789 | Phase 5：【必现】首页，能把同一个卡片拖到四个widget位上 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12868 | Phase 5：【偶发】蓝牙音乐页面卡死，点击Home键，再次打开随心听显示黑屏 | jsun62 | Approval | jsun62 | BT Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12292 | Phase 5：【必现】播放蓝牙音乐时，RACM端点击Audio off按钮无法关闭媒体音频 | jsun62 | Approval | jsun62 | BT Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12892 | Phase 5：【偶发】爱奇艺播放时，发生四个APP Crash | jsun62 | Approval | jsun62 | Video | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12796 | Phase 5：【必现】唤醒语音：音量大一点/音量小一点，USB音乐未播放，Audio off也未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12864 | 【台架】【偶现】【CDX707】【widget卡片】widget卡片样式变小 | ntian2 | Approval | ntian2 | Map&Navigation | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12941 | 【Phase V】【CDX707】【A】【BT Phone】【5/5】oppo find X 通话车机无声，使用手机铃声来电去电，车机无声 | zqiu12 | Closed with Accept | zqiu12 | BT Phone | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12712 | Phase 5：【偶现】TCU有网的车，连接WiFi，一直显示正在加入网络.. | tshan3 | Approval | tshan3 | WiFi Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12317 | Phase 5：【高频】播放QQ音乐，RACM端点击音乐源按钮，音乐源页面显示空白 | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10872 | Phase 5：【偶现】3D车模位置不正确 | jxu148 | Approval | jxu148 | 3D Vehicle model | CDX707 | CDX707C_UAT_1st | Gating | LA_R06.1_ENG
APIMCIM-11832 | Phase 5：【偶发】爱奇艺播放时，发生com.baidu.iov.dueros.videos ANR | jsun62 | Approval | jsun62 | Video | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-9451 | Phase 5: 【偶发】【AutoTest】泊车相关功能信号接收有延迟，不响应现象 | yzhu104 | Approval | yzhu104 | Parking Assist | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12569 | Phase5:【必现】【CDX707】播放USB音乐->打开地图->导航路线->开始导航，导航播报结束后媒体音量变大，退出地图后恢复正常 | zsu13 | Approval | zsu13 | Audio | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13549 | 【Phase V】【CDX707】【A】【Audio】【1/10】播放音乐，挂断电话后，音乐的声音突然变大. | ywang535 | Approval | ywang535 | Audio | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-11862 | Phase 5：【必现】蓝牙歌曲在播放，但没有退出Audio off | jsun62 | Approval | jsun62 | Audio | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-11221 | Phase5：【偶现】在地图页面，旋转声音按钮调节媒体音量，将媒体音量调整为0后，QQ音乐依然有声音发出 | jchen384 | Approval | jchen384 | Audio | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12924 | Phase 5：【必现】蓝牙音乐播放时，RACM端高亮显示"循环模式"按钮 | jsun62 | Approval | jsun62 | BT Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12887 | Phase 5：【必现】唤醒语音：播放/上一首/下一首，QQ音乐播放，但Audio off并未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13614 | Phase 5：【必发】H689293 13：46 系统设置—音效设置—平衡 衰减—重置失败 必现 | hmo3 | Approval | hmo3 | System Setting | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12220 | Phase 5：【必现】插入U盘后，RACM端不会立即显示USB音乐入口 | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12197 | Phase 5：【偶发】快速连续点击第一个卡片的删除按钮，发生com.ford.sync.controllerlauncher Crash | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13647 | Phase 5：【偶发】【AutoTest】Monkey测试时，出现com.ford.sync.hvac的crash | jsun62 | Approval | jsun62 | BT Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10369 | Phase 5：【必现】无TCU环境下，视频投屏后一直加载中，无法投屏 | xwang314 | Approval | xwang314 | DLNA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12878 | Phase 5：【必现】唤醒语音：音量大一点/音量小一点，Audio off未解除，蓝牙音乐未播放 | jsun62 | Approval | jsun62 | BT Music | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13235 | Phase 5：【偶发】H689272 15：27 点击泊车辅助按键，选择泊车后进入无信息显示的界面，然后退出不了点击下方的菜单也无反应 | hmo3 | Approval | hmo3 | Vehicle Setting | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13016 | Phase 5：【偶发】倒档来车预警影像开关点击无法打开 | sliu141 | Approval | sliu141 | Vehicle Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12140 | Phase 5：【偶发】设置发生com.yfve.settings ANR | jsun62 | Approval | jsun62 | System Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13491 | [100%] MMOTA_China: Upgrade TCU by VI, precondition pop up exist all the time during activation. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-7895 | [100%] MMOTA_China:OTA升级SOC,下载过程中发Shed_Level_Req:3_SHED2_CONTIN或Shed_Level_Req=5_SHED_ENG_OFF,进入安装会报SIM_E1001,OTAM_E1008,OTAM_E1016 | jzhan376 | Approval | jzhan376 | MMOTA | Inhouse_Platform | MigratingToCloud | Gating | LA_R06.1_ENG
APIMCIM-12785 | Phase5:[10%][CDX707]登录账号后首页头像未同步更新 | lxue15 | Approval | lxue15 | Account | CDX707 | CDX707_CVPP | Gating | LA_R06.1_ENG
APIMCIM-12270 | [CDX707][Performance][Stability]monkey test ,vendor.ford.soa happens native crash | rhuang35 | Approval | rhuang35 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12363 | Phase 5：【必现】副驾随心听却支持添加到default卡片 | jsun62 | Approval | jsun62 | Music | CDX707 | CDX707C_UAT_2nd | Gating | LA_R06.1_ENG
APIMCIM-12264 | [CDX707][Performance][Stability]monkey test,com.ford.sync.controllerlauncher happens 1 times crash | rhuang35 | Approval | rhuang35 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12499 | Phase 5：【偶现】 模拟导航无声14:28 | rzhao22 | Approval | rzhao22 | Audio | R06_SIGN_OFF | R061_MUST_FIX | Gating | LA_R06.1_ENG
APIMCIM-12263 | [CDX707][Performance][Stability]monkey test,com.ford.sync.fnvservice happens 2 times crash | rhuang35 | Approval | rhuang35 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10984 | [100%] MMOTA_China: Upgrade TCU by VI, The time displayed in the "System Update Reminder" pop-up is inconsistent with the set time | jzhan376 | Approval | jzhan376 | MMOTA | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12314 | Phase 5：【高频】删除蓝牙设备，RACM端点击蓝牙音乐源按钮，发生多个Crash | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12110 | Phase5:[CDX707]No banner message pops up after filter saturation | cshengji | Approval | cshengji | Auto Air Refresh | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-10920 | [CDX707][Performance][Stability]monkey test,com.yfve.settings happens 3 times crash | sjie2 | Approval | sjie2 | System Stability | CDX707 | digitalee | Gating | LA_R06.1_ENG
APIMCIM-12021 | Phase5:[必现][CDX707]音效设置页面的部分设置项点击无效 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | IACC, | Gating | LA_R06.1_ENG
APIMCIM-10185 | [100%] MMOTA_China: USB plugged to upgrade MCU,during download/ installation/pending activation when upgrade SOC via OTA,the USB upgrade cannot continue after SOC upgrade is canceled. | jzhan376 | Closed with Accept | dliu79 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13050 | Phase5:[100%]CDX707 Authorization time popup text error | jgu37 | Approval | jgu37 | V2I | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13649 | Phase 5：【偶发】【AutoTest】Monkey测试时，出现com.ford.sync.controllerlauncher Crash | jsun62 | Test | zzhou68 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13807 | Phase 5：【偶发】路试时，后台发生com.ford.sync.fnvservice Crash | jsun62 | Approval | jsun62 | FNV | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10694 | Phase 5：【必现】后屏来源播放蓝牙或USB音乐，后屏音频关闭按键交互出错 | tshan3 | Approval | wxie15 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13079 | Phase5:[100%][CDX707]VPA status is about seat when query E-manual | lxue15 | Approval | lxue15 | Virtual Personal Assistant | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13338 | [100%] MMOTA_China: Upgrade TCU by VI,ADB log prints lots of error messages about the statusbar during upgrade process | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13482 | [100%] MMOTA_China: Upgrade TCU by VI, precondition pop up button not match with UI. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-5293 | Phase 5：【812】【必现】唤醒车机，语音:打开分屏。播报：操作失败 | tshan3 | Approval | tshan3 | VR | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13125 | Phase5:[CDX707][Performance][Roadtest]Roadtes test, in the background, the cpu usage rate of controller launcher is as high as 20%, without releasing | sjie2 | Approval | sjie2 | System Performance | digitalee | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13600 | Phase 5：【必发】H689286 1121 车辆启动时开着“安全开门预警”，熄火后再次启动车辆，“安全开门预警”按钮自动关闭后再次开启。必现 | hmo3 | Approval | hmo3 | Vehicle Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13678 | Phase5：【必现】在地图页面，按压中控台上的“¦P¦”按键进入自动泊车页面，自动泊车页面未占满整个页面，操作屏顶部为地图的画面 | jchen384 | Approval | jchen384 | Parking Assist | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13603 | Phase 5：【必发】689306 10：46 主界面点击车模，进入车内，点击林肯香氛按钮，打开林肯香氛，选择其他香氛时开关会有一个关闭开启的现象 必现 | hmo3 | Approval | hmo3 | Drive Mode | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13328 | Phase 5：【必发】H689281 18：53 每次按泊车辅助按键，中控屏都会显示泊车雷达按钮从关闭到打开的现象 | hmo3 | Approval | hmo3 | System Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12430 | Phase 5: 【必现】车钥匙检测提示没有主动get Can信号反馈状态 | xli318 | Approval | xli318 | Vehicle Setting | GIM | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13536 | Phase5:[必现][CDX707]Ambient light is still display opening in 3D car model when the light switch is turned off. | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11837 | phase5：【偶现】偶现点击车路协同闪退到主界面 | lshi42 | Approval | zqiu12 | Vehicle Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11824 | 【Phase V】【CDX707】【A】【RACM】【3/5】后屏source源信息，蓝牙图标显示为随心听，且切源时大概率不显示，插入U盘后，播放源和显示的源信息不同步 | lshi42 | Approval | zqiu12 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10427 | Phase5:[CDX707][偶现]共享位置关闭的情况下，需要定位授权的应用可以选择权限 | qshi14 | Done | qshi14 | User Privacy | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10429 | Phase5:[CDX707][偶现]共享位置打开的情况下，定位授权app提示“"无法开启定位”---请开启“共享车辆位置”后重试 | qshi14 | Done | qshi14 | User Privacy | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12157 | Phase5_【CDX707】【黑盒】【必现】【CarAudio外置】导航声音不在播报的情况下设置，再次导航音量不起效果 | tzhou37 | Closed with Accept | tzhou37 | Audio | CDC707 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13509 | Phase 5：【必发】H689270 1035 首次打开空调出现一条灰色残影。 | hmo3 | Approval | hmo3 | Climate | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12631 | Phase 5：【偶现】已保存的手机热点开启后，车机未自动连接上wifi | hzhan238 | Approval | hzhan238 | WiFi Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12886 | Phase 5：【必现】播放QQ音乐，快进快退时唤醒语音，语音结束后，歌曲播放，但audio off仍未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11124 | 【Phase V】【CDX707】【A】【System Setting】【5/5】音效设置界面进入音乐界面，在音乐界面点击“音效设置”按钮进入音效设置，无法进入音量设置/均衡器/平衡衰减界面. | zqiu12 | Done | zqiu12 | System Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12833 | Sensitive Data(VIN) Disclosure – AccountService | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse | High | LA_R06.1_ENG
APIMCIM-12583 | TLS not Verified – swuservice.apk | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10191 | Phase5:[偶现][CDX707]brandreset清掉授权后， CCS icon图标显示为授权状态图标 | qshi14 | Monitor | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12590 | [100%] MMOTA_China: USB update SOC with corrupt SW file, IVI pop up is wrong. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-8442 | [20%] MMOTA_China: VIL file is empty after USB upgrade ECG success | yli391 | Approval | yli391 | MMOTA | CDx707C | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10901 | Phase 5：【必现】插拔U盘，后排屏音源显示错误 | bliu94 | Approval | bliu94 | Multi-Screen Interaction | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-10896 | Phase 5：【必现】RACM切源，随心听/USB切到蓝牙音乐，RACM音源图标显示error | bliu94 | Approval | bliu94 | Multi-Screen Interaction | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-12931 | Phase 5：【必现】断电再上电，Audio off不被记忆 | jsun62 | Rejected | jsun62 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11801 | Phase 5：【必现】空调内循环按键点击打开与关闭，在按键左侧有动效 | tshan3 | Approval | tshan3 | Climate | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12202 | [100%] MMOTA_China: USB update ECG/TCU, updating progress jump from 0% to 100%. | yli391 | Approval | jwang373 | MMOTA | CDX707 | ECG | High | LA_R06.1_ENG
APIMCIM-10681 | Phase 5：【必现】后屏蓝牙音乐界面，记忆显示了USB的播放模式：随机与循环。 | tshan3 | Approval | tshan3 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12581 | Private keys are found on swuservice.apk | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12194 | Phase5:[100%][CDX707]New user guide screen displays after changing account | lxue15 | Approval | lxue15 | Account | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11813 | Phase5_[CDX707C][必现】【Enhanced Memory】 创建档案时，IVI下发信号CtrStkDsplyOp_D_Rq值错误 | nli52 | Approval | nli52 | Personalization | CDX707 | CDX707C | High | LA_R06.1_ENG
APIMCIM-12188 | Phase5:[100%][CDX707] The content layout of the shared pop-up window is not beautiful, and the text is truncated | qshi14 | Approval | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12040 | Phase5[CDX707][必现]:护航详情同级页面语音无法打开胎压监测页面 | xwang310 | Approval | xwang310 | Vehicle Health Alert | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12556 | Phase 5：【必现】+1屏，删除所有卡片，再添加7个卡片，第四个卡片size偏小 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12557 | Phase 5：【必现】+1屏，长按一个卡片时，点击"保存"按钮，选中的卡片仍显示编辑态 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12326 | [100%] MMOTA_China: Upgrade TCU by VI,"system update successful" pops up when the update progress bar reaches 11% | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12118 | Phase 5：【必现】语音切换声源定位时，tts播报错误 | tshan3 | Approval | tshan3 | VR | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11463 | Phase5：【偶现】退出 Revel@Experience 视频，闪现视频进度条 | jchen384 | Approval | jchen384 | System Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-11237 | 【语音】 【基础功能】 【CDX707】 关闭自动模式tts播报已关闭，但实车上屏幕图标没有变化，仍显示自动模式 | ntian2 | Approval | ntian2 | VR | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12644 | Phase 5：【必现】关闭林肯香氛后3D车模里仍显示香氛打开状态 | hzhan238 | Approval | hzhan238 | 3D Vehicle model | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12587 | Phase 5: 【必现】车辆控制界面，点击下方车辆控制按钮，车辆控制页面不应进行刷新。 | xli318 | Approval | xli318 | Vehicle Setting | GIM | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12130 | Phase 5: 【偶现】导航，Media和电话交互，挂断电话后Media会出现爆音 | jzeng28 | Closed with Accept | tzhou37 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10933 | Phase5_【CDX707】【黑盒】【偶现】【FAPA】在360摄像头环境下，自动泊车不可用偶现无播报 | tzhou37 | Closed with Accept | tzhou37 | Fapa | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-12201 | [100%] MMOTA_China: USB update ECG/TCU/SYNC+, the remaining file number increasing, not decreasing. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-7237 | Phase5：【必现】[CDX707][HMI走查] 3D车模_车辆（车模相关）快捷控制视觉布局问题 | fwang116 | Done | yliu404 | 3D Vehicle model | CDX707 | CDX707C_UAT_1st | High | LA_R06.1_ENG
APIMCIM-11877 | Phase5:[100%][CDX707]点击车身颜色tab会重置色环和车身颜色 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11436 | Phase5：【必现】[CDX707][HMI走查] 点击时的水波纹效果不同 | fwang116 | Done | fwang116 |  | CDX707 | CDX707_HMI | High | LA_R06.1_ENG
APIMCIM-11733 | Phase5_[CDX707C][必现】【Enhanced Memory】 删除个人账号下对应的个性化档案后，再次切换回该账号，会一直提示该账号下个性化档案已删除 | nli52 | Approval | nli52 | Personalization | Inhouse_Platform | TW43 | High | LA_R06.1_ENG
APIMCIM-11623 | Phase5-[CDX707C][必现】【Enhanced Memory】在D/R/L/N档时，IVI界面会弹出个性化保存弹框 | nli52 | Approval | nli52 | Personalization | CDX707 | CDX707C | High | LA_R06.1_ENG
APIMCIM-12351 | Phase5:[必现][CDX707]自定义模式下车门和地板灯光调至最低后返回显示异常 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12426 | Phase5：【必现】[CDX707][HMI走查]_info弹窗置于后台，再次打开后，弹窗重新弹出 | yqin24 | Done | yqin24 | System UI | CDX707 | CDX707_HMI | High | LA_R06.1_ENG
APIMCIM-12554 | Phase 5：【偶现】出风口滑动调节界面与空调主界面重叠 | tshan3 | Approval | tshan3 | Climate | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11439 | Phase5：【必现】[CDX707][HMI走查] 系统按钮动效问题 | fwang116 | Done | fwang116 |  | CDX707 | CDX707_HMI | High | LA_R06.1_ENG
APIMCIM-11874 | Phase5:[100%][CDX707]重置第五个车身颜色tab异常 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12195 | Phase 5：【必现】[CDX707]空调风量调节背景部分过亮，出风口整个偏上 | jyi23 | Approval | jyi23 | Climate | CDX707_HMI | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11988 | Phase5:[偶现][CDX707]车外页熄火需要有“发动车辆才可以使用全部车辆功能”提示 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12002 | Phase5:[必现][CDX707]3D车模页面的音效设置同步不到系统音效设置页面 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-9524 | [100%] MMOTA_China:Click the "Clear" button, the system update plan cannot be cleared | jzhan376 | Approval | jzhan376 | MMOTA | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-9092 | Phase5:【必现】[CDX707]快速滑动选择按摩方式，选中的按摩方式仍然会与其他按摩方式多次来回切换 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | CDX707C_UAT_1st | High | LA_R06.1_ENG
APIMCIM-9541 | [100%] MMOTA_China: Upgrade TCU by VI, the "System update schedule not set" popup does not pop up when pending activation | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12200 | Phase 5：【必现】+1屏的widget编辑状态，点击Home键，再向左滑动到+1屏，状态栏与右上角的按钮重叠，且卡片不晃动 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11790 | Phase 5：【必现】音效设置内的菜单点击时，没有白色背景的点击动效 | jsun62 | Approval | jsun62 | General Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12283 | Phase5：【必现】车模重置车身颜色，最后一个光圈一下重置到初始颜色，需要点击两次重置按钮才能重置到初始的颜色 | jchen384 | Approval | jchen384 | 3D Vehicle model | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12134 | Phase 5: 【必现】导航和QQ音乐交互时，导航播报时QQ音乐不会降音播放 | jzeng28 | Closed with Accept | yyang179 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10571 | Phase5：【必现】[CDX707][HMI走查] Climate空调电动出风口_页面视觉布局问题 | fwang116 | Done | xdou | Climate | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13216 | Phase 5：【必现】CDX707 允许车路协同infobook,授权时间的弹窗“年”字没适配主题，左上角关闭按钮和图标“取消”重复 | lzhan249 | Approval | lzhan249 | V2I | CDX707_HMI | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-12037 | Phase5：【必现】[CDX707][HMI走查]多模块空中升级 (MMOTA) _按钮动效问题 | fwang116 | Done | cyang114 | MMOTA | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-13215 | Phase 5：【必现】CDX707 系统设置进度条颜色没适配 | lzhan249 | Approval | lzhan249 | System Setting | CDX707_HMI | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-13317 | Test Page with Shortcuts – VoiceControlSevice | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-12629 | Phase5:【必现】【CDX707】车外天窗控制界面与主界面重叠 | swang218 | Closed with Accept | wxiao13 | 3D Vehicle model | FCPA | Inhouse_App | Medium | LA_R06.1_ENG
APIMCIM-12816 | Phase 5：【必现】3D车模车辆健康报警和各个故障显示点击没有按钮音效 | hzhan238 | Approval | hzhan238 | 3D Vehicle model | CDX707 | ICV | Medium | LA_R06.1_ENG
APIMCIM-12844 | Exportable Activity DoS – AccountService | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-11966 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_弹窗页面布局问题 | fwang116 | Done | wxiao13 | V2I | CDC_TS_HMI | CDX707 | Medium | LA_R06.1_ENG
APIMCIM-12410 | Phase5：【必现】3D车模顶部的动画和坐享净界主题的动画不一致 | jchen384 | Approval | jchen384 | 3D Vehicle model | CDC_Phase5 | CDX707 | Medium | LA_R06.1_ENG
APIMCIM-12208 | Phase5：【必现】[CDX707][HMI走查]快捷控制-动效问题 | fwang116 | Done | fwang116 | Drive Mode | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12205 | Phase5：【必现】[CDX707][HMI走查]手机无线充电-动效问题 | fwang116 | Done | fwang116 | Wireless Charging | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12206 | Phase5：【必现】[CDX707][HMI走查] _DAT Setting_动效问题 | fwang116 | Done | cxu63 | DAT Setting | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12144 | Phase5：【必现】[CDX707][HMI走查] DIDC-动效问题 | fwang116 | Done | cxu63 | Driver Info | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12039 | Phase5：【必现】[CDX707][HMI走查]遥控启动设置-弹窗动效问题 | fwang116 | Done | zlian2 | Remote Control | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12030 | Phase5：【必现】[CDX707][HMI走查] _launcher_toast动效问题 | fwang116 | Done | lxiao19 | Launcher | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11802 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_视觉布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11806 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_info页面布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11811 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_申请流程页面布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12043 | Phase5：【必现】[CDX707][HMI走查] 诊断分析-动效问题 | fwang116 | Done | cwang236 | FNV | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11807 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_toast布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-10094 | Phase5：【必现】[CDX707][HMI走查] _system UI & launcher_视觉布局问题 | fwang116 | Done | fwang116 | System UI | CDX707 | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-7935 | Phase5：【必现】[CDX707][HMI走查] Face ID_条款界面视觉布局问题 | fwang116 | Done | jzhu79 | FaceID | CDX707 | HMI | Medium | LA_R06.1_ENG
APIMCIM-12654 | Phase 5: 【必现】把主题从"自在航行"切换至“坐享净界”，车辆控制界面右侧的滑条未变蓝色。 | xli318 | Approval | xli318 | Vehicle Setting | GIM | Inhouse_Platform | Low | LA_R06.1_ENG
APIMCIM-10556 | Phase5_[CDX707C][必现】【Enhanced Memory】 After Paak was associated with Profile, the Paak name is wrong | nli52 | Approval | nli52 | Personalization | CDX707 | CDX707C | Low | LA_R06.1_ENG

## R06.1_Fix_TS (hidden)
Issue key | Summary | Reporter | Status | Created | Assignee | Component/s | Affects Version/s | Priority | Labels | Labels | Labels | Labels | Labels | Labels | Labels | Labels
APIMCIM-12874 | Phase 5：【偶现】625实车，连接WiFi后，自动会被关闭 | tshan3 | To Do | 2022-10-21 04:25 | tshan3 | WiFi Setting | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-12903 | Phase 5：【偶发】RACM端显示“音频关闭”，但是点击“关闭”按钮无响应 | jsun62 | In Progress | 2022-10-23 22:50 | bliu94 | Multi-Screen Interaction | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-13437 | Phase 5：【偶发】NTT 707 EPT02 684122 1435 驾驶辅助，开关倒档来车预警，屏幕跳动 | hmo3 | To Do | 2022-11-03 23:52 | hmo3 | Driver Assistance | LA_R06_ENG | High | CAF | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | IVI
APIMCIM-12815 | Phase 5：【必现】已连接wifi网络，下载导航语音包时，依然弹出“非wifi网络将消耗移动流量，是否继续下载"的弹框 | jxu148 | In Progress | 2022-10-20 11:31 | jzhan372 | Map&Navigation | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Plaform | Inhouse_Platform | R061_MUST_FIX
APIMCIM-13822 | Phase 5：【必现】空调开关无法开启 | xwang314 | To Do | 2022-11-12 04:57 | xwang314 | Climate | LA_R06_ENG | Gating | CDC_IVITst | CDC_phase5 | CDX707 | Inhouse_Platform
APIMCIM-12274 | Phase5:[偶现]DTC 0xE40100 | xhuang93 | In Progress | 2022-10-07 03:35 | mzhuo1 | Diagnostic | LA_R05_ENG | Gating | CDC_Phase5 | CDX707 | EOL | Inhouse_Platform | IVI | R061_MUST_FIX | W43 | W44
APIMCIM-13917 | Phase5_【CDX707】【黑盒】【必现】【Audio】进入静音模式后，播放音乐，依旧有声音 | cyang114 | To Do | 2022-11-14 05:01 | cyang114 | Audio | LA_R06_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform | W46
APIMCIM-14001 | Phase 5：【必现】调节座椅页面，未高亮的菜单的"<"按钮都是高亮 | jsun62 | To Do | 2022-11-15 09:02 | jsun62 | Seat | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13737 | 【PhaseV】【CDX707】【A】【RACM】【5/5】RACM无法调节音量 | zqiu12 | To Do | 2022-11-10 01:10 | zqiu12 |  | LA_R06.1_ENG | Gating | CDC_IVITst | CDC_Phase5 | CDC707 | CDX707 | Inhouse_Platform | W46 | YFVE
APIMCIM-13855 | Phase 5：【偶发】空调调出动效异常 | jxu148 | To Do | 2022-11-13 08:32 | xdou | Climate | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-14007 | Phase 5：【偶发】实车路试时，车机突然断网 | jsun62 | To Do | 2022-11-15 09:27 | jzhan372 | Carrier | LA_R06_ENG | Immediate Gating | CDC_IVITst | CDC_Phase5 | CDX707 | CVPPVOCF | Inhouse_Platform | VOCF
APIMCIM-14046 | Phase 5：【必现】历史消息页面，点击未接来电的"通话"按钮，无任何响应 | jsun62 | To Do | 2022-11-16 02:12 | lwang287 | Launcher | LA_R06_ENG | Gating | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-13815 | Phase 5：【必现】副驾随心听总是显示"加载失败"，完全不能用 | jsun62 | In Progress | 2022-11-12 03:08 | jzhan372 | Music | LA_R06_ENG | Gating | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | R07_MUST_FIX_YF | VOCF
APIMCIM-13989 | Phase 5：【偶现】媒体音调节无效，旋钮和音量设置均无效 | cyang114 | To Do | 2022-11-15 03:16 | yyang179 | Audio | LA_R06_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform | TS
APIMCIM-13316 | Exportable Component DoS – Inhouse APPs | xzhan221 | In Progress | 2022-11-02 01:53 | hzhu74 | Cybersecurity |  | Medium | APIM | CDX707 | Cybersecurity | Inhouse_APP | Inhouse_Platform | PenTest | Sync+3.0
APIMCIM-12845 | Lack of APP Hardening-Inhouse | xzhan221 | To Do | 2022-10-21 01:16 | ycai28 | Cybersecurity |  | Medium | APIM | CDX707 | Cybersecurity | Inhouse_Platform | PenTest | Sync+3.0
APIMCIM-13868 | Phase 5：【偶现】路试中Card2突然弹出香氛相关toast | jxu148 | To Do | 2022-11-13 10:40 | wxiao13 | Launcher | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13734 | 【Phase V】【CDX707】【A】【Audio】【5/5】实车LV606 104A 外置功放24CH,平衡/衰减位置不正确. | ywang535 | In Progress | 2022-11-10 00:55 | hzhu74 | Audio | LA_R06.1_ENG | Gating | CDC_IVITst | CDC_Phase5 | CDC707 | CDX707 | Inhouse_Platform | YFVE
APIMCIM-13586 | 【Phase V】【CDX707】【A】【Upgrade】【2/2】OTA整包升级，S1008激活成功后ign run，等待vil上传，等待超过10分钟，没有报S1010 | zqiu12 | To Do | 2022-11-07 02:18 | zqiu12 | MMOTA | LA_R06.1_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-14002 | Phase 5：【必现】调节座椅页面，点击"<"">"按钮，只是高亮其菜单 | jsun62 | To Do | 2022-11-15 09:03 | jsun62 | Seat | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13990 | Phase 5：【偶现】【外置功放】平衡衰减调节无效 | cyang114 | To Do | 2022-11-15 03:23 | yyang179 | Audio | LA_R06_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform | TS
APIMCIM-13863 | Phase 5：【偶发】移动widget，原来的卡片位置黑屏3s | jxu148 | To Do | 2022-11-13 09:33 | cxu63 | Launcher | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | YFVE
APIMCIM-13458 | Phase 5：【偶发】NTT707 EPT02 684122 1445 空调页面风量大小无显示 | hmo3 | To Do | 2022-11-04 02:29 | hmo3 | Climate | LA_R06_ENG | High | CAF | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | IVI | NTT
APIMCIM-14070 | Phase 5：【偶现】挂断蓝牙微信电话后，蓝牙音乐爆音 | jxu148 | To Do | 2022-11-16 03:42 | yyang179 | BT Music | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13688 | Phase 5：【必现】打开车窗后，3D车模的车窗依旧处于关闭关闭状态 | hzhan238 | To Do | 2022-11-08 19:59 | hzhan238 | 3D Vehicle model | LA_R06_ENG | High | CAF | CDC_Phase5 | CDX707 | ICV | Inhouse_Platform | notbug | phase5_launchTst
APIMCIM-13687 | Phase 5：【必现】在3D车模快捷控制页面停止操作15s，车模不会自动关闭 | hzhan238 | To Do | 2022-11-08 19:56 | hzhan238 | 3D Vehicle model | LA_R06_ENG | High | CAF | CDC_Phase5 | CDX707 | ICV | Inhouse_Platform | notbug | phase5_launchTst
APIMCIM-13793 | Phase 5：【必发】707H689274车辆设置中没有车钥匙检测提示选项 | hmo3 | To Do | 2022-11-11 04:28 | yzhan482 | Vehicle Setting | LA_R06_ENG | High | CAF | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | IVI | NTT

## Jira_issue
Issue key | Summary | Reporter | Priority | Status | Created | Assignee | 问题归属 | 修改计划 | Components
APIMCIM-19576 | Phase5_【U718】【必现】【MMOTA】VI升级TCU，熄火后无法进入激活-点火查看更新详情无“立即激活”按钮 | zhangjian zhou | Gating | To Do | 2023-03-17 17:14 | chang liu | YF
APIMCIM-19560 | Phase5_【U718】【黑盒】【Car Power】【必现】进入STR模式后，无法正常退出STR模式（使用一段时间后出现的问题） | chunming yang | Gating | To Do | 2023-03-17 17:14 | Chunwei Wang | YF
APIMCIM-18679 | Phase5_【U718】【偶现】【FNV】FNV诊断中上传日志到云端，有概率无法连接云端，报503 | chunming yang | Gating | To Do | 2023-03-01 22:14 | Xinming Xiao | ford
APIMCIM-18093 | Phase 5_【U718】【必现】【WiFi Setting】连接需要认证的wifi，会自动变为未连接，之后连接其他wifi会出现相同情况 | chunming yang | Gating | In Progress | 2023-02-16 06:23 | Hanghang Zhou | ford
APIMCIM-18570 | Phase5_【U718】【黑盒】【必现】【PAAK】创建个人车门解锁密码过程中途会弹出“原厂密码不匹配”且会更改界面标题。完成以后无法弹出“连接超时”弹窗 | Chuanqin Chen | Gating | To Do | 2023-02-13 05:02 | Kai Jie Zhang | bcm对手键
APIMCIM-17269 | Phase5_【U718】【黑盒】【必现】【DLNA】投放视频出现卡顿后关闭重新投放功能无法恢复 | wendi Xiao | Gating | Test | 2023-01-19 01:01 | Zihao Qiu | YF | DCV3合入
APIMCIM-16298 | Phase5_【U718】【黑盒】【必现】【拖车】编辑宽度值后，没有下发TX信号0x288（拖车360设置编辑也未下发288信号）（迁移PSTTT-933） | Chuanqin Chen | Gating | To Do | 2023-01-06 07:15 | Hongshuai Li | YF
APIMCIM-16233 | Phase5_【U718】【黑盒】【必现】【拖车】点击想要激活的拖车，TX(45C)指令下发不对（PSTTT-1094 迁移） | Chuanqin Chen | Gating | Test | 2023-01-05 08:12 | Zihao Qiu | YF
APIMCIM-17510 | Phase5_【U718】【黑盒】【必现】【Audio】【24ch】点击百度地图进行导航，无声音提示 | tianqi zhou | Gating | To Do | 2023-01-05 03:26 | Peng Wang | ford
APIMCIM-15469 | Phase5_【U718】【黑盒】【必现】【拖车】点击待激活拖车，无法正确下发TX信号215 | Chuanqin Chen | Gating | Test | 2022-11-18 01:31 | Chuanqin Chen | YF
APIMCIM-17092 | Phase5_【U718】【黑盒】【必现】【Car_Audio】【24ch】车随音速无效果 | tianqi zhou | Gating | To Do | 2022-11-10 22:17 | Peng Wang | ford
FCIVIOS-14414 | Phase5_【U718】【黑盒】【偶现】【Monkey】【settings】monkey 测试中com.yfve.settings发生crash（java.lang.IndexOutOfBoundsException) | Chuanqin Chen | High | To Do | 2023-03-16 22:29 | hao zhu | TS
FCIVIOS-14413 | Phase5_【U718】【黑盒】【偶现】【Monkey】【vha】monkey 测试中 com.ford.sync.vha 发生crash（java.lang.IllegalStateException）和anr( Input dispatching timed out) | Chuanqin Chen | High | Tested | 2023-03-16 22:23 | Chuanqin Chen | TS
FCIVIOS-14387 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号后备箱由P档变成非P档，发送熄火信号在发送点火信号，后备箱按钮高亮会闪一下 | wendi Xiao | High | To Do | 2023-03-14 22:41 | Xingjian Li | TS
FCIVIOS-14386 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号打开按摩开关，发送按摩模式，launcher显示按摩座椅动效 | wendi Xiao | High | To Do | 2023-03-14 22:33 | Xingjian Li | TS
APIMCIM-19326 | Phase5_【U718】【黑盒】【单机必现】【System】正常连接后，控制屏黑屏无法使用，使用投屏软件在电脑上投屏时，报错 | Chuanqin Chen | High | To Do | 2023-03-14 01:24 | Yang Hou
FCIVIOS-14370 | Phase5_【U718】【黑盒】【单机必现】【VehicleSettings】切换主题后，车控车设的选择按扭和菜单显示异常 | Chuanqin Chen | High | Monitor | 2023-03-13 05:17 | Chuanqin Chen | TS
APIMCIM-19295 | Phase5_【U718】【黑盒】【必现】【拖车】连接上BCM以后，拖车灯的弹窗会反复弹。查看其信号在跳变 | Chuanqin Chen | High | To Do | 2023-03-13 04:50 | Kai Jie Zhang
FCIVIOS-14365 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号：打开下尾门，车模不显示下尾门开启 | wendi Xiao | High | To Do | 2023-03-10 03:40 | Xingjian Li | TS
FCIVIOS-14364 | Phase5_【U718】【黑盒】【必现】【3D车模】发送位置灯信号，车模中间位置灯无亮度变化 | wendi Xiao | High | Tested | 2023-03-10 03:32 | wendi Xiao | TS
FCIVIOS-14363 | Phase5_【U718】【黑盒】【必现】【3D车模】设置后备箱为手动，双击按钮，点击home键，弹窗仍显示 | wendi Xiao | High | To Do | 2023-03-10 03:20 | Xingjian Li | TS
FCIVIOS-14322 | Phase5_【U718】【黑盒】【必现】【STR】车载热点开关打开状态，进入STR模式，再退出STR模式，车载热点开关却是关闭状态 | zhaomin huang | High | To Do | 2023-03-06 06:14 | Cheng Qin | TS
APIMCIM-19242 | Phase5_【U718】【黑盒】【必现】【AAR】台架无法获取滤芯状态，一直报网络异常请稍后重试 | Chuanqin Chen | High | To Do | 2023-03-02 06:40 | xiaoyan wan
FCIVIOS-14270 | Phase5_【U718】【黑盒】【必现】【3D车模】进入车内点击故障ICOM图标不会跳转vha界面 | wendi Xiao | High | To Do | 2023-03-02 04:57 | Xingjian Li | TS
FCIVIOS-14261 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】从车模入口进入多功能座椅，界面出现重叠 | manyi guan | High | Tested | 2023-03-02 01:55 | manyi guan | TS
FCIVIOS-14259 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】氛围灯RX信号模拟无效值时，切换界面后 氛围灯自动打开 | manyi guan | High | Tested | 2023-03-02 01:47 | manyi guan | TS
FCIVIOS-14257 | Phase5_【U718】【黑盒】【必现】【3D车模】配置氛围灯DE01=varient 2，发送信号=64，点击亮度为20时，亮度条不在20的竖线上且TX会下发一个off的值 | wendi Xiao | High | To Do | 2023-03-02 01:23 | Xingjian Li | TS
FCIVIOS-14256 | Phase5_【U718】【黑盒】【必现】【3D车模】配置氛围灯DE01=varient 2，发送信号亮度无效信号，点击空白区域再次点击氛围灯按钮，车模显示动效 | wendi Xiao | High | To Do | 2023-03-02 01:04 | Xingjian Li | TS
APIMCIM-18850 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】当前未配置灯光设置功能，依旧可以搜索出灯光功能 | manyi guan | High | In Progress | 2023-03-01 21:59 | Wang Qian
FCIVIOS-14236 | Phase5_【U718】【黑盒】【必现】【paak】重置智能备用密钥->无法正确弹出车门解锁密码保存失败的弹窗 | Chuanqin Chen | High | To Do | 2023-03-01 06:01 | chao Xu | TS
FCIVIOS-14227 | Phase5_【U718】【黑盒】【偶现】【50%】【PAAK】重置智能密钥->请输入原密码界面，偶现密码输入框无法输入密码 | Chuanqin Chen | High | To Do | 2023-03-01 03:24 | chao Xu | TS
FCIVIOS-14222 | Phase5_【U718】【黑盒】【必现】【PAAK】密码最多64位，目前未做密码长度限制 | Chuanqin Chen | High | Tested | 2023-03-01 02:12 | Chuanqin Chen | TS
APIMCIM-18691 | Phase5_【U718】【黑盒】【Monkey】【setting】com.yfve.settings内存泄漏 | Chuanqin Chen | High | Test | 2023-02-28 21:52 | Zihao Qiu
FCIVIOS-14216 | Phase5_【U718】【黑盒】【偶现】【Monkey】【launcher】controllerlauncher有内存超标 | Chuanqin Chen | High | Monitor | 2023-02-28 21:49 | Chuanqin Chen | TS
FCIVIOS-14215 | Phase5_【U718】【黑盒】【偶现】【Monkey】【launcher】controllerlauncher有crash(Short Msg: android.renderscript.RSRuntimeException) | Chuanqin Chen | High | Monitor | 2023-02-28 21:46 | Chuanqin Chen | TS
FCIVIOS-14214 | Phase5_【U718】【黑盒】【偶现】【Monkey】【vha】com.ford.sync.vha有anr（ANR in com.ford.sync.vha (com.ford.sync.vha/.vhacontrol.ui.VhaActivity)） | Chuanqin Chen | High | Monitor | 2023-02-28 21:42 | Chuanqin Chen | TS
APIMCIM-18411 | Phase5_【U718】【黑盒】【偶现】【1/20】【Account】登录账号的实际个数与账号管理中个数不一致 | Chuanqin Chen | High | To Do | 2023-02-24 00:09 | Li Sun
APIMCIM-18407 | Phase5_【U718】【黑盒】【偶现】【50%】【AAR】AAR语音弹窗，偶现没有语音播报 | Chuanqin Chen | High | Test | 2023-02-23 21:45 | Chuanqin Chen
APIMCIM-18406 | Phase5_【U718】【黑盒】【必现】【Account】账号登录界面，新手引导界面无法进入 | Chuanqin Chen | High | To Do | 2023-02-23 21:37 | Jian Yao
APIMCIM-18405 | Phase5_【U718】【黑盒】【必现】【Account】账号登录失效，无法出现弹窗：“账号登录，你的账号登录失效，请重新登录” | Chuanqin Chen | High | To Do | 2023-02-23 21:29 | Niu Tian
APIMCIM-18391 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】IOD拖车行程发送信号后，pano屏拖车行程无对应数据变化 | manyi guan | High | To Do | 2023-02-23 02:31 | Wang Qian
APIMCIM-18353 | Phase5_【U718】【偶现】【MMOTA】VI升级下载阶段切换5G-WIFI-5G无法恢复下载 | zhangjian zhou | High | To Do | 2023-02-22 07:58 | zhangjian zhou
FCIVIOS-14098 | Phase5_【U718】【黑盒】【必现】【3D车模】打开远近灯光，发送照明系统故障，车模仍显示远近灯光 | wendi Xiao | High | In Progress | 2023-02-22 06:23 | Xingjian Li | TS
FCIVIOS-14096 | Phase5_【U718】【黑盒】【必现】【拖车】添加第10个拖车，是否继续建立选择否，在名称界面时，修改名称为另外的名称。保存会跳转到车机主界面，预期提示超过10个拖车 | Chuanqin Chen | High | Tested | 2023-02-22 04:38 | Chuanqin Chen | TS
FCIVIOS-14091 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥时，密码连续输入五次错误，没有提示超过最大次数 | Chuanqin Chen | High | Tested | 2023-02-22 02:08 | Chuanqin Chen | TS
FCIVIOS-14090 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥时，密码正确密码后，无法弹出”密码正确，车辆已成功解锁" | Chuanqin Chen | High | Tested | 2023-02-22 02:02 | Chuanqin Chen | TS
FCIVIOS-14089 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥时，密码输入框未收到信号后，无法弹出toast"系统错误，无法完成该请求" | Chuanqin Chen | High | Tested | 2023-02-22 01:51 | Chuanqin Chen | TS
FCIVIOS-14088 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥 密码界面未使用监听，未对这三个条件进行判断（启动状态、Delay accessory已启⽤、extended play已启⽤） | Chuanqin Chen | High | Tested | 2023-02-22 01:45 | Chuanqin Chen | TS
FCIVIOS-14087 | Phase5_【U718】【黑盒】【必现】【PAAK】IG=off时，输入密码弹窗右上角存在关闭按扭，预期没有关闭按扭 | Chuanqin Chen | High | Tested | 2023-02-22 01:21 | Chuanqin Chen | TS
FCIVIOS-14086 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥启动车辆，输入正确密码后，无法弹出密码正确弹框 | Chuanqin Chen | High | To Do | 2023-02-22 01:12 | chao Xu | TS
FCIVIOS-14082 | Phase5_【U718】【黑盒】【必现】【PAAK】输入车辆启动密码后，点击确定，加载过程中会有主菜单按扭出现，且可点击，从而跳出密码界面 | Chuanqin Chen | High | Tested | 2023-02-22 00:51 | Chuanqin Chen | TS
FCIVIOS-14076 | Phase5_【U718】【黑盒】【必现】【3D车模】进入3d车模车内界面，发送未启动发动机信号，车内显示车模尾部 | wendi Xiao | High | Tested | 2023-02-21 21:49 | wendi Xiao | TS
FCIVIOS-14075 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号ig=off，acc=on，车模显示轮胎故障 | wendi Xiao | High | In Progress | 2023-02-21 21:36 | Xingjian Li | TS
FCIVIOS-14072 | Phase5_【U718】【黑盒】【偶现】【PAAK】偶现无故弹出”搜索中“，且无法取消弹窗 | Chuanqin Chen | High | Tested | 2023-02-21 08:38 | Chuanqin Chen | TS
APIMCIM-18289 | Phase5_【U718】【黑盒】【偶现】【音源矩阵】【24ch】通话中点击播放蓝牙音乐，挂断电话后蓝牙音乐未进行播放 | tianqi zhou | High | To Do | 2023-02-21 08:10 | Wang Qian
FCIVIOS-14069 | Phase5_【U718】【黑盒】【必现】【PAAK】密码包含大写字母+小写字母+数字（存在不连续重复数字或字母时）满14位时，预期显示强，实际显示好 | Chuanqin Chen | High | Tested | 2023-02-21 07:40 | Chuanqin Chen | TS
APIMCIM-18617 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】点击切换驾驶模式 切换主题后，自动跳转至灯光设置界面 | manyi guan | High | Test | 2023-02-21 05:46 | Zihao Qiu
APIMCIM-18287 | Phase5_【U718】【黑盒】【必现】【DLNA】手机连接上DLNA车机热点，在线视频可以正常播放，第一次投屏加载不出内容，退出后，无法投屏 | chunming yang | High | To Do | 2023-02-21 04:29 | Meng Wang
FCIVIOS-14053 | Phase5_【U718】【黑盒】【必现】【3D车模】进入3D车模音效点击更多按钮，音效图标位置与系统设置显示不一致 | wendi Xiao | High | In Progress | 2023-02-21 01:09 | Xingjian Li | TS
FCIVIOS-14050 | Phase5_【U718】【黑盒】【必现】【3D车模】重启机器快速进入车内界面，车内显示后备箱按钮且右侧车模显示氛围灯效果 | wendi Xiao | High | Tested | 2023-02-21 00:26 | wendi Xiao | TS
APIMCIM-18261 | Phase5_【U718】【黑盒】【偶现】【WiFi】林肯之道互联复位-全部复位后，点击wifi开关，wifi开关置灰（后续在原生设置中可以打开） | chunming yang | High | To Do | 2023-02-21 00:12 | Zhicheng Liu
FCIVIOS-14046 | Phase5_【U718】【黑盒】【必现】【3D车模】修改车模颜色 ，U盘升级，车模颜色未记忆 | wendi Xiao | High | Reopened | 2023-02-20 20:48 | Xingjian Li | TS
FCIVIOS-14041 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】当前未配置倒挡来车预警影像功能，依旧可以搜索出该功能 | manyi guan | High | Tested | 2023-02-20 06:17 | manyi guan | TS
FCIVIOS-14040 | Phase5_【U718】【黑盒】【偶现】【Vehicle Setting】monkey过程中com.yfve.settings发生crash（java.lang.IllegalStateException） | zhaomin huang | High | Awaiting implementation (migrated) | 2023-02-20 05:54 | zhaomin huang | TS
APIMCIM-18212 | Phase5_【U718】【黑盒】【必现】【Monkey】com.yfve.settings内存泄露 | Chuanqin Chen | High | Test | 2023-02-20 00:05 | Zihao Qiu
APIMCIM-18444 | Phase5_【U718】【黑盒】【必现】【CarAudio】【24ch】百度地图导航时点按power键，导航声音会暂停 | tianqi zhou | High | To Do | 2023-02-18 05:26 | Yankun Zhao
FCIVIOS-14021 | Phase5_【U718】【黑盒】【必现】【拖车】界面停在选择激活拖车界面时，出现“检测到拖车连接”弹窗，点击添加拖车后，拖车名称输入异常 | Chuanqin Chen | High | Tested | 2023-02-17 05:17 | Chuanqin Chen | TS
FCIVIOS-14017 | Phase5_【U718】【黑盒】【必现】【拖车】通知=打开&有激活的拖车，检测到拖车连接，选择弹窗的“添加拖车”预期跳转到拖车主界面并激活默认拖车，实际未跳转也未下发TX信号 | Chuanqin Chen | High | To Do | 2023-02-17 01:58 | hanyu dong | TS
APIMCIM-18109 | Phase5_【U718】【黑盒】【必现】【Monkey】【蓝牙电话】com.yfve.settings有crash（java.lang.RuntimeException: Unable to start activity ComponentInfo{com.yfve.settings/com.yfve.settings.activitys.InputActivity） | Chuanqin Chen | High | To Do | 2023-02-16 21:27 | Zhicheng Liu
FCIVIOS-14006 | Phase5_【U718】【黑盒】【FNV】【必现】插入exfat格式的U盘，抓取的日志大小为空 | chunming yang | High | Tested | 2023-02-16 03:42 | chunming yang | TS
FCIVIOS-13991 | Phase5_【U718】【黑盒】【必现】【拖车】拖车里面有部分场景未适配主题（汇总） | Chuanqin Chen | High | Tested | 2023-02-15 05:45 | Chuanqin Chen | TS
FCIVIOS-13989 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥时，输入车辆启动的密码时，弹窗会把密码输入框遮挡 | Chuanqin Chen | High | To Do | 2023-02-15 02:07 | chao Xu | TS
FCIVIOS-13689 | Phase5_【U718】【黑盒】【偶现】【FNV】soa出现crash | Chuanqin Chen | High | Monitor | 2023-02-10 07:27 | Chuanqin Chen | TS
FCIVIOS-12763 | Phase5_【U718】【黑盒】【必现】【PAAK】重置智能备用钥匙-密钥输入锁定，发送RX后，没有弹出预期弹窗 | Chuanqin Chen | High | Tested | 2023-01-16 08:04 | Chuanqin Chen | TS
APIMCIM-17520 | Phase5_【U718】【黑盒】【必现】【林肯香氛】模拟香氛过期，香氛界面会调起语音弹窗 | wendi Xiao | High | To Do | 2023-01-14 06:15 | Niu Tian
APIMCIM-16536 | Phase5_【U718】【黑盒】【必现】【3D车模】处于RVC界面，底部不会显示灯光按钮 | wendi Xiao | High | To Do | 2023-01-11 01:28 | Xingjian Li
APIMCIM-16722 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】搜索当前未配置的功能，可以搜索出来结果 | manyi guan | High | In Progress | 2023-01-10 02:09 | Zhicheng Liu
APIMCIM-16468 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】模拟发送驾驶模式异常状态弹窗信号时，界面跳转至上一次界面 再跳转回驾驶模式界面 | manyi guan | High | To Do | 2023-01-09 00:43 | Zhicheng Liu
APIMCIM-16358 | Phase5_【U718】【必现】【Hotspot】连接车载热点，手机无法上网 | zhangjian zhou | High | In Progress | 2023-01-07 06:48 | qipeng zhao
APIMCIM-16357 | Phase5_【U718】【必现】【Hotspot】热点设置界面插拔ECG和IVI的连接线束，界面会出现重叠 | zhangjian zhou | High | Test | 2023-01-07 06:25 | Wang Qian
APIMCIM-16934 | Phase5_【U718】【黑盒】【偶现】【音源矩阵】【24ch】播放蓝牙音乐时熄屏，再次亮屏后，蓝牙音乐未自动恢复播放 | tianqi zhou | High | Approval | 2023-01-07 05:29 | tianqi zhou
APIMCIM-17512 | Phase5_【U718】【黑盒】【偶现】【Audio】【24ch】蓝牙电话选择外置铃声，接听来电时喇叭无铃声输出 | tianqi zhou | High | To Do | 2023-01-07 03:35 | Yankun Zhao
APIMCIM-16274 | Phase5_【U718】【黑盒】【必现】【Theme】驾驶模式切换到低速爬坡，预期主题切换到山湖无界，实际无切换动作 | Chuanqin Chen | High | To Do | 2023-01-05 07:01 | Zhicheng Liu
APIMCIM-16417 | Phase5_【U718】【黑盒】【必现】【Audio】【24ch】电话通话中，前排喇叭无声音输出 | tianqi zhou | High | To Do | 2023-01-05 03:45 | Fisher Liu
FCIVIOS-12385 | Phase5_【U718】【黑盒】【必现】【paak】SPSS中要求密码包含xato-net-10-million-passwords-10000.txt里面字符串时，等级不得高于“一般” | Chuanqin Chen | High | Tested | 2023-01-05 01:42 | Chuanqin Chen | TS
APIMCIM-16047 | Phase5_【U718】【黑盒】【偶现】【V2I】多次退出使用计划，再次进入车路协同界面，偶现界面显示空白 | wendi Xiao | High | Awaiting implementation (migrated) | 2022-12-30 06:13 | bing xu
APIMCIM-15810 | Phase5_【U718】【黑盒】【必现】【拖车】满足拖车报警开关条件后，该按扭仍然是置灰状态，不可点击 | Chuanqin Chen | High | Reopened | 2022-12-17 05:53 | Chuanqin Chen
FCIVIOS-12067 | Phase5_【U718】【黑盒】【必现】【V2I】进入车辆协同界面，不显示使用计划文本 | wendi Xiao | High | To Do | 2022-12-11 21:04 | Heng DU | TS
APIMCIM-18198 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号后雾灯无反应 | wendi Xiao | High | Test | 2022-11-15 04:16 | Zihao Qiu
APIMCIM-15987 | Phase5_【U718】【黑盒】【必现】【Car-audio】音量设置中通话，语音，提示音不生效 | tianqi zhou | High | To Do | 2022-11-14 01:16 | Fisher Liu
FCIVIOS-11297 | Phase5_【U718】【黑盒】【必现】【VCS】语音调节后排风量，tts播报提示“你的爱车暂不支持该功能”，且无信号下发 | guangdong yuan | High | Tested | 2022-11-09 21:18 | Yunteng Jiang | TS
FCIVIOS-11181 | Phase5_【U718】【黑盒】【必现】【拖车】360设置成功以后，需要进入TAD calibration环节，目前保存完成后无其他信息，请与FO确认流程 | Chuanqin Chen | High | To Do | 2022-11-05 05:02 | hanyu dong | TS
FCIVIOS-11169 | Phase5_【U718】【黑盒】【必现】【拖车】所有infobook文案未提供，当前只有图标无法点击查看 | Chuanqin Chen | High | To Do | 2022-11-04 22:54 | qi yu | TS
APIMCIM-15867 | Phase5_【U718】【黑盒】【偶现】【Car_Audio】切换音源，蓝牙音乐偶现暂停不播放 | tianqi zhou | High | To Do | 2022-11-02 03:54 | Huanxin Fu
APIMCIM-15868 | Phase5_【U718】【黑盒】【偶现】【Car_Audio】QQ音乐偶现不播放 | tianqi zhou | High | Monitor | 2022-11-02 03:38 | guangdong yuan
APIMCIM-17573 | Phase5_【U718】【黑盒】【必现】【 Vehicle Settings】播放vr时，tts播报打断当前播放vr | Yunteng Jiang | High | Test | 2022-09-19 06:31 | Niu Tian
APIMCIM-19359 | Phase5_【U718】【必现】【VCS】在all app页面语音“打开小程序”，无TTS反馈 | Yunteng Jiang | Medium | In Progress | 2023-03-14 06:51 | Yunteng Jiang
FCIVIOS-14211 | Phase5_【U718】【黑盒】【必现】【拖车】通知=打开&有激活的拖车，选择弹窗“查看设置”，跳转到拖车设置界面后，会弹出重量设置弹窗 | Chuanqin Chen | Medium | To Do | 2023-02-28 08:16 | hanyu dong | TS
FCIVIOS-14071 | Phase5_【U718】【黑盒】【必现】【HVAC】语音“增大/减小后排空调风量”，TTS反馈“后排空调风量已增大/减小” | Yunteng Jiang | Medium | To Do | 2023-02-21 08:02 | Xinyu Dou | TS
FCIVIOS-14070 | Phase5_【U718】【黑盒】【必现】【HVAC】语音“增大/减小后排空调温度”，TTS反馈“空调温度已调高/调低” | Yunteng Jiang | Medium | To Do | 2023-02-21 07:57 | Xinyu Dou | TS
FCIVIOS-14058 | Phase5_【U718】【黑盒】【必现】【Vehicle Settings】播放蓝牙音乐，连接儿童座椅TTS播报时，蓝牙音乐音量没有降低 | zhaomin huang | Medium | To Do | 2023-02-21 02:31 | yongheng yang | TS
FCIVIOS-14057 | Phase5_【U718】【黑盒】【必现】【HVAC】前排auto full时按钮点击无动效，后排按钮disable状态与前排显示不一致 | Yunteng Jiang | Medium | Tested | 2023-02-21 02:07 | Yunteng Jiang | TS
FCIVIOS-14013 | Phase5_【U718】【黑盒】【偶现】【拖车】激活某个拖车后，偶现激活界面拖车的排序不正确 | Chuanqin Chen | Medium | To Do | 2023-02-16 22:37 | hanyu dong | TS
FCIVIOS-12657 | Phase5_【U718】【黑盒】【偶现】【monkey】monkey中，launcher模块出现ANR | zhaomin huang | Medium | Tested | 2023-01-12 21:01 | zhaomin huang | TS
APIMCIM-13692 | Phase5_【U611】【黑盒】【必现】【AAR】滤芯状态获取失败，网络异常 | Yunteng Jiang | Medium | To Do | 2022-11-04 04:11 | Stella Shi
APIMCIM-14129 | Phase5_【U718】【黑盒】【必现】【Rear Audio】处于电话/语音唤起，后屏不会全屏显示文字提示 | wendi Xiao | Medium | In Progress | 2022-10-31 06:41 | Bin Meng
APIMCIM-13339 | Phase5_【U718】【黑盒】【必现】【AAR】滤芯状态获取失败，网络异常 | Yunteng Jiang | Medium | To Do | 2022-10-31 06:11 | Stella Shi
APIMCIM-14128 | Phase5_【U718】【黑盒】【必现】【Rear Audio】当前播放蓝牙音乐，点击后屏来源切换随心听音乐，后屏仍显示蓝牙界面 | wendi Xiao | Medium | Test | 2022-08-25 07:19 | guangdong yuan