## 首页
|  |  |  | 文件No. | 页数
|  |  |  | ThunderSoft-QMS-18-JL17 | 5
<Ford Phase5>测试报告
历史记录
版本号 | 日期 | 作者/修订者 | 制订/修改内容 |  |  | 评审人/评审日期 | 评审要求
V1.0 | 2021-07-04 | 邓荣祥 | 创建
V1.1 | 2022-03-06 | 陈传勤 | 优化相关模块测试用例
V1.2 | 2022-11-26 | 李可可 | 优化首页内容展示

## Summary-DCV4
U718_DCV4测试报告
软件版本 | SOC：20230505_LB_DCV4_ENG00 MCU：20230505_LB_DCV4_ENG00 ECG: ECG2-milestone-2023-04-Bundle-Release_EH_maps-0.0.45.283 TCU: TCU2-milestone-2023-04-modem6-Bundle-Release-China-2.3.3.156 |  |  |  | 测试范围 | 1、所有Fetaure 2、只包含创达开发范围
测试硬件 | B&C |  |  |  | 测试人员 | 姜云腾&关满意&李可可&杨惟婧&杨春明&肖文迪&黄钊敏&赵雅非
测试方法 | 手动 |  |  |  | 测试环境 | 台架
项目经理 | 余琦 |  |  |  | 项目总监 | 陈凯
总结 | 总体说明：本轮DCV4测试，Focus测试，涉及模块32个，整体Pass率为88.94%执行率为90.75% 一、DCV4交付模块说明： 本轮未测试模块： ①Rear audio（24ch）、音源矩阵(Ecall)-(24ch)、Audio 外置(24ch)——DSP版本待升级，DCV4不交付 本轮新增模块： ①个性化设置档案（Enhance Memory） 二、通过率详情： 1）Pass率<=70%的模块4个 ①雷达：功能阻塞，APIMCIM-22000 发信Rx信号，雷达弹窗触发不出来，——R00版本修改合入 ②FNV诊断：APIMCIM-18679：FNV诊断中上传日志到云端，有概率无法连接云端，报503，影响case【13】——ford分析中 ③Theme：APIMCIM-16274：驶模式切换到低速爬坡，预期主题切换到山湖无界，实际无切换动作 ——YFVE，历史问题，较长时间未修复 ④Enhance Memory：APIMCIM-22109paak相关信号上报无效【19】，APIMCIM-22114keyfob无法关联【11】——首次交付，问题较多，ford分析中 2）70%<=Pass率<=90%的模块2个 ①Account：APIMCIM-18405：账号登录失效，无法出现弹窗：“账号登录，你的账号登录失效，请重新登录，影响case【3】——ford分析中 ②STR：无关键问题，影响单点场景 3）Pass率>90%的模块14个 ①PAAK：APIMCIM-18570：创建个人车门解锁密码过程中途会弹出“原厂密码不匹配，影响case【2】——对手键BCM问题，影响整体使用效果 ②3D车模：颜色未适配，影响case【8】——车模当前待review改进阶段，UI会等review签收后进行更新 ③拖车：APIMCIM-16233：点击想要激活的拖车，TX(45C)指令下发不对，影响case【4】——信号相关问题，YF分析中 ④MMOTA：APIMCIM-20366：Phase5:[U718][100%]VI update can't be triggered，影响case【14】——ECG分析中 其他暂无关键问题（Car input、Vehicle Setting、WIR、AAR、HVAC、数字香氛、Launcher、Car Power、蓝牙儿童座椅、V2I） 4）Pass率=100%的模块12个
问题列表
FeatureID | 模块 | 本轮通过率 | 影响Case数 | BugID | Bug标题 |  | 严重程度 | 状态 | 归属 | 分析
SYNC+_0073 | 雷达 | 0% | 208 | APIMCIM-22000 | Phase5_【U718】【黑盒】【必现】【雷达】发信Rx信号，雷达弹窗触发不出来 |  | P1 | TO DO | TS | R00合入
SYNC+_Z0037 | FNV诊断 | 48% | 13 | APIMCIM-18679 | Phase5_【U718】【偶现】【FNV】FNV诊断中上传日志到云端，有概率无法连接云端，报503 |  | P1 | TO DO | Ford | 需推动
SYNC+_0205 | THEME | 50% | 4 | APIMCIM-16274 | Phase5_【U718】【黑盒】【必现】【Theme】驾驶模式切换到低速爬坡，预期主题切换到山湖无界，实际无切换动作 |  | P2 | TODO | YFVE
|  |  | 1 | FCIVIOS-15182 | Phase5_【U718】【黑盒】【必现】【THEME】切换主题为第三种主题，点击车控，tab的>未适配主题 |  | P2 | TODO | ts
SYNC+_0165 | EnhanceMemory | 65.63% | 1 | APIMCIM-22288 | Phase5_【U718】【必现】【个性化档案】创建新的档案，档案头像页面未显示默认头像 |  | P3 | TO DO | FORD
|  |  | 11 | APIMCIM-22114 | Phase5_【U718】【必现】【个性化档案】keyfob无法关联 |  | P2 | TO DO | FORD
|  |  | 19 | APIMCIM-22109 | Phase5_【U718】【必现】【个性化档案】paak相关信号上报无效 |  | P2 | TO DO | FORD
|  |  | 1 | APIMCIM-22289 | Phase5_【U718】【必现】【个性化档案】连接档案页面，点击未连接的置灰paak，未提示paak未连接弹窗，且上报连接信号后入口仍置灰 |  | P2 | TO DO | FORD
|  |  | 1 | APIMCIM-22103 | Phase5_【U718】【必现】【个性化档案】连接档案页面未勾选且未关联钥匙，下一步按钮仍可点击 |  | P2 | TO DO | FORD
|  |  | 1 | APIMCIM-22067 | Phase5_【U718】【必现】【个性化档案】非当前档案无法删除 |  | P2 | TO DO | FORD
|  |  | 1 | APIMCIM-22104 | Phase5_【U718】【必现】【个性化档案】重置修改上报成功信号无效 |  | P2 | TO DO | FORD
|  |  | 1 | APIMCIM-22106 | Phase5_【U718】【必现】【个性化档案】上报26b PaakCnnct_D_Stat 1，点击智能手机钥匙入口仍弹出未连接弹窗 |  | P2 | TO DO | FORD
|  |  | 1 | APIMCIM-22004 | Phase5_【U718】【必现】【个性化档案】光速探境主题未与档案适配 |  | P2 | TO DO | FORD
|  |  | 1 | APIMCIM-22022 | Phase5_【U718】【必现】【个性化档案】进入STR前有一个用户档案1，进入str退出后，档案1消失 |  | P2 | TO DO | FORD
|  |  | 6 | NT | 自动保存未合入，相关用例无法测试
SYNC+_0164 | Account | 80.95% | 3 | APIMCIM-18405 | Phase5_【U718】【黑盒】【必现】【Account】账号登录失效，无法出现弹窗：“账号登录，你的账号登录失效，请重新登录” |  | P2 | TODO | Baidu | 分析中
|  |  | 1 | PSTT-544 | Phase5_【U718】【黑盒】【必现】【Account】账号登录成功和网络不佳等情况时，toast不符合UI设计 |  | P2 | TODO | Inhouse | 分析中
| STR | 82.14% | 2 | FCIVIOS-15243 | Phase5_【U718】【必现】【HVAC】进入str前后，空调按钮状态不一致 |  | P2 | TODO | TS
|  |  | 3 | FCIVIOS-15242 | Phase5_【U718】【黑盒】【必现】【CarPower】进出STR后，wifi开关没有保持打开状态 |  | P2 | TODO | TS
SYNC+_Z0159 /SYNC+_Z0177 | HVAC | 91.19% | 1 | FCIVIOS-15243 | Phase5_【U718】【必现】【HVAC】进入str前后，空调按钮状态不一致 |  | P2 | TO DO | TS
|  |  | 1 | FCIVIOS-15246 | Phase5_【U718】【必现】【HVAC】当前是吹脚模式，语音切换吹风模式，未下发吹脚关闭信号 |  | P2 | TO DO | TS
|  |  | 2 | FCIVIOS-15247 | Phase5_【U718】【必现】【HVAC】语音降低温度，TTS反馈“空调温度已调低两度” |  | P3 | TO DO | TS
|  |  | 13 | FCIVIOS-15249 | Phase5_【U718】【必现】【HVAC】语音调节后排温度，TTS反馈“空调温度已调到最低” |  | P1 | TO DO | TS
|  |  | 2 | FCIVIOS-15250 | Phase5_【U718】【必现】【HVAC】语音“后排风量减小/增大x档”，TTS反馈“空调风量已减小/增大x档” |  | P3 | TO DO | TS
|  |  | 1 | FCIVIOS-15251 | Phase5_【U718】【必现】【HVAC】语音“后排风量调到x档”，TTS反馈“前排空调风量已调到x” |  | P3 | TO DO | TS
SYNC+_0106 | PAAK | 92.16% | 1 | APIMCIM-18570 | Phase5_【U718】【黑盒】【必现】【PAAK】创建个人车门解锁密码过程中途会弹出“原厂密码不匹配” |  | P2 | TODO | BCM对手键
|  |  | 1 | APIMCIM-21825 | Phase 5: 【必现】输入错误车门解锁密码，点击"重试"按钮后弹窗出现重影 |  | P2 | TODO | TS
|  |  | 1 | FCIVIOS-15222 | Phase5_【U718】【黑盒】【必现】【BSP】创建智能备用密钥，进入到创建车门解锁密码时，第二个密码输入框提示内容显示不正确 |  | P3 | In Progress | TS
|  |  | 1 | FCIVIOS-15152 | Phase5_【U718】【黑盒】【必现】【BSP】五分钟锁定提示内容，与UI图的描述不一致，请更新 |  | P2 | Tested | TS
|  |  | 1 | PSTT-431 | Phase5_【U718】【黑盒】【必现】【PAAK】使用智能备用密钥时，输入车辆启动的密码时，弹窗会把密码输入框遮挡 |  | P1 | Analysis | Baidu
|  |  | 1 | FCIVIOS-15238 | Phase5_【U718】【黑盒】【必现】【BSP】“密码正确，车辆已成功解锁，请在20秒之内启动车辆”，提示语多了一个字 |  | P3 | TODO | TS
|  |  | 2 | FCIVIOS-15241 | Phase5_【U718】【黑盒】【必现】【BSP】使用密码阶段，delay accessory信号监听不正确 |  | P2 | TODO | TS
SYNC+_0265 | V2I | 92.86% | 1 | FCIVIOS-15194 | 【Phase5】【U718】【V2I】【黑盒】【必现】车路协同界面显示子菜单名称与UE不一致，“取消申请”的按钮未删除 |  | P2 | TODO | TS
|  |  | 1 | APIMCIM-22062 | 【Phase5】【U718】【V2I】【黑盒】【必现】默认设置页面-允许车路协同通知为开 |  | P2 | TODO | Ford
SYNC+_0266 | 3D车模 | 93.15% | 1 | FCIVIOS-15204 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号打开远光灯，车模可以点亮logo和中网贯穿灯 |  | P2 | 待办 | TS
|  |  | 1 | FCIVIOS-15204 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号打开远光灯，车模可以点亮logo和中网贯穿灯 |  | P2 | 待办 | TS
|  |  | 1 | FCIVIOS-15199 | Phase5_【U718】【黑盒】【必现】【3D车模】进入车内，点击通知栏灯光按钮，灯光弹窗与车内界面重叠 |  | P2 | 待办 | TS
|  |  | 1 | FCIVIOS-15211 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号打开后雾灯，发送信号选择位置灯，后雾灯置灰车模仍显示后雾灯效果 |  | P2 | 待办 | TS
|  |  | 1 | FCIVIOS-15226 | Phase5_【U718】【黑盒】【必现】【3D车模】发送等级无效信号，按摩按钮/按摩等级与车控状态显示不一致 |  | P2 | 待办 | TS
|  |  | 1 | FCIVIOS-15258 | Phase5_【U718】【黑盒】【必现】【3D车模】3D车内香氛界面点击多按钮，打开香氛，模拟异常再次打开香氛，退出车控，3D车内香氛未打开 |  | P2 | 待办 | TS
|  |  | 2 | FCIVIOS-15225 | Phase5_【U718】【黑盒】【必现】【3D车模】发送按摩等级为中，发送等级 信号=off，重启车机，进入3D车内，点击按摩按钮，tx信号记忆上次一次等级 |  | P2 | 待办 | TS
|  |  | 1 | FCIVIOS-14053 | Phase5_【U718】【黑盒】【必现】【3D车模】进入3D车模音效点击更多按钮，音效设备背景图与系统设置显示不一致 |  | P2 | 待办 | TS
|  |  | 3 | NT | 后备箱需实车测试（依赖实车） |  |  |  | TS | 6月份
|  |  | 9 | NT | 车模颜色未适配（车模当前待review改进阶段，UI会等review签收后进行更新） |  |  |  | TS
SYNC+_0132 | AAR | 93.06% | 3 | APIMCIM-22279 | Phase5_【U718】【黑盒】【必现】【AAR】环境正常的情况下，进入AAR获取滤芯时，一直报错码-300 |  | P2 | TO DO | Inhouse
|  |  | 1 | FCIVIOS-15260 | Phase5_【U718】【黑盒】【偶现】【AAR】历史记录界面，偶现横轴的时间点有重叠显示 |  | P3 | TO DO | TS
|  |  | 1 | FCIVIOS-15261 | Phase5_【U718】【黑盒】【必现】【AAR】历史记录界面，横坐标的时间显示与系统时间显示不统一，两者时间不一致 |  | P3 | TO DO | TS
SYNC+_0223 | MMOTA | 94.44% | 14 | APIMCIM-20366 | Phase5:[U718][100%]VI update can't be triggered |  | P1 | Inprogess | ECG | 需推动
SYNC+_Z0098/SYNC+_Z1029/SYNC+_Z1030/SYNC+_Z1033/SYNC+_Z1034/SYNC+_Z1036/SYNC+_Z1039/SYNC+_Z1050 | 拖车 | 95.56% | 4 | APIMCIM-16233 | Phase5_【U718】【黑盒】【必现】【拖车】点击想要激活的拖车，TX(45C)指令下发不对 |  | P1 | Reopened | YFVE
|  |  | 1 | FCIVIOS-15244 | Phase5_【U718】【黑盒】【必现】【拖车】拖车名称长度较长时，已激活的toast有截断 |  | P3 | In Progress | TS
|  |  | 1 | FCIVIOS-11169 | Phase5_【U718】【黑盒】【必现】【拖车】所有infobook文案未提供，当前只有图标无法点击查看 |  | P2 | TODO | TS | 需要跟踪infobook下发
|  |  | 1 | APIMCIM-19295 | Phase5_【U718】【黑盒】【必现】【拖车】连接上BCM以后，拖车灯的弹窗会反复弹。查看其信号在跳变 |  | P2 | TODO | BCM对手键
|  |  | 2 | FCIVIOS-14742 | Phase5_【U718】【黑盒】【必现】【拖车】通知=打开&激活拖车点火时提示拖车重量开关打开，选择弹窗“查看设置”，点击更改重量时跳转有抖动 |  | P3 | Reopen | TS
|  |  | 7 | FCIVIOS-14896 | Phase5_【U718】【黑盒】【必现】【拖车】通知=打开&激活默认拖车，选择弹窗“查看设置”和“添加拖车”，跳转界面异常，无激活拖车时“选择拖车”也有异常 |  | P2 | Tested | TS
SYNC+_Z0043 | WIR | 95.92% | 2 | FCIVIOS-15242 | Phase5_【U718】【黑盒】【必现】【CarPower】进出STR后，wifi开关没有保持打开状态 |  | P2 | TODO | TS
SYNC+0264 | CarInput | 96.83% | 2 | PSTT-563 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】模拟硬按键进入多功能座椅界面，向下滑动，界面出现重影 |  | P2 | TO DO | YFVE
SYNC+_0134 | 数字香氛 | 96.88% | 1 | FCIVIOS-15179 | Phase5_【U718】【必现】【林肯香氛】进入STR前香氛是打开状态，退出后香氛关闭 |  | P2 | TODO | YFVE
SYNC+_Z0129 | 蓝牙儿童座椅 | 97.44% | 1 | APIMCIM-22380 | Phase5_【U718】【CarAudio】【黑盒】【必现】当前prompt播放中，来电铃声，prompt未停止播放 |  | P2 | TODO | Baidu | 分析中
SYNC+_Z0060 | Car Power | 98.65% | 1 | NT | 缺少对应硬按件
SYNC+_Z0210/SYNC+_Z0204/SYNC+_Z0278/SYNC+_Z0281/SYNC+_Z0277/SYNC+_Z0197/SYNC+_Z0187/SYNC+_Z0180/SYNC+_Z0178/SYNC+_Z0183/SYNC+_Z0181/SYNC+_Z0182/SYNC+_Z0206/SYNC+_Z0215/SYNC+_Z0212/SYNC+_Z0217/SYNC+_Z0216/SYNC+_Z0213/SYNC+_Z0201/SYNC+_Z0214/SYNC+_Z0209/SYNC+_Z0211/SYNC+_0074 | Vehicle Setting | 99.18% | 1 | FCIVIOS-15193 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】倒挡来车预警影像在常用设置和驾驶辅助界面状态不一致 |  | P2 | TODO | TS
|  |  | 1 | FCIVIOS-15192 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】车速限制辅助 容限单位改变时，入口处值未同步 |  | P2 | TODO | TS
|  |  | 1 | FCIVIOS-15208 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】交通标志识别界面的超速警告 开关自动打开 |  | P2 | TODO | TS
|  |  | 1 | FCIVIOS-15236 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】防眩照明点击收藏图标后，常用设置中无此功能 |  | P2 | TODO | TS
|  |  | 1 | FCIVIOS-15239 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】信号配置出自动远光模式，切换界面后 功能消失 |  | P2 | TODO | TS
|  |  | 1 | FCIVIOS-15268 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】驾驶模式复杂路况vcs信号下发错误 |  | P2 | TODO | TS
|  |  | 1 | FCIVIOS-15266 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】氛围灯七色颜色和亮度刻度与UI不一致 |  | P2 | TODO | TS
SYNC+_Z0159 /SYNC+_Z0177 | Launcher | 99.26% | 1 | FCIVIOS-15245 | 【Phase5】【U718】【Launcher】【必现】限行和车牌号重叠 |  | P2 | TO DO | TS

## 模块详细数据-DCV4
模块详细数据
FeatureID | Moudle | Total | Pass | Fail | Block | NT | DCV4_Pass Rate （Pass/Total） | DCV4_Run Rate （Pass+Fail）/Total | 测试/开发 | DCV3_Pass Rate （Pass/Total） | 通过率是否下降 | 下降主要原因 | 车辆信息 | 测试时长 | Comments | 重点模块
SYNC+_0106 | PAAK手机钥匙 | 102 | 94 | 7 | 1 | 0 | 92.16% | 99.02% | 赵雅非/许超 | 90.43% | 否 |  | / | / |  | 否
SYNC+_Z0032 | CCS | 54 | 54 | 0 | 0 | 0 | 100% | 100% | 杨春明/于凯凯 | 100% | 否 |  | / | / |  | 否
SYNC+_0266 | 3D车模 | 292 | 272 | 8 | 1 | 12 | 93.15% | 95.89% | 肖文迪/李行健 | 92.69% | 否 |  | / | / |  | 否
SYNC+_Z0081 | Car input | 63 | 61 | 1 | 1 | 0 | 96.83% | 98.41% | 袁露/贺金 | 100% | 是 | 新增问题PSTT-563 | / | / |  | 是
SYNC+_0073 | FAPA | 179 | 179 | 0 | 0 | 0 | 100% | 100% | 黄钊敏/顾佳宁 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0098/SYNC+_Z1029/SYNC+_Z1030/SYNC+_Z1033/SYNC+_Z1034/SYNC+_Z1036/SYNC+_Z1039/SYNC+_Z1050 | 拖车 | 215 | 199 | 6 | 10 | 0 | 92.56% | 95.35% | 赵雅非/董昑禹 | 92.59% | 否 | 部分场景用例更新，导致总数有变化 | / | / |  | 是
SYNC+_Z0026 | Multi -display | 16 | 16 | 0 | 0 | 0 | 100% | 100% | 杨春明/贺金 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0210/SYNC+_Z0204/SYNC+_Z0278/SYNC+_Z0281/SYNC+_Z0277/SYNC+_Z0197/SYNC+_Z0187/SYNC+_Z0180/SYNC+_Z0178/SYNC+_Z0183/SYNC+_Z0181/SYNC+_Z0182/SYNC+_Z0206/SYNC+_Z0215/SYNC+_Z0212/SYNC+_Z0217/SYNC+_Z0216/SYNC+_Z0213/SYNC+_Z0201/SYNC+_Z0214/SYNC+_Z0209/SYNC+_Z0211/SYNC+_0074 | Vehicle Setting | 850 | 843 | 7 | 0 | 0 | 99.18% | 100% | 关满意/王闯&许超&石松&董晗禹 | 98.67% | 否 |  | / | / |  | 是
SYNC+_Z0155 | 车载热点 | 21 | 21 | 0 | 0 | 0 | 100% | 100% | 杨春明/于凯凯 | 100% | 否 |  | / | / |  | 否
SYNC+_Z0043 | WIR | 49 | 47 | 1 | 1 | 0 | 95.92% | 97.96% | 杨春明/张金海 | 100% | 是 | 新增STR的场景，验证存在新问题 | / | / |  | 否
SYNC+_0132 | AAR | 72 | 67 | 3 | 2 | 0 | 93.06% | 97.22% | 赵雅非/杨永恒 | 93.33% | 否 |  | / | / |  | 否
SYNC+_Z0159--SYNC+_Z0177 | HVAC | 227 | 207 | 6 | 14 | 0 | 91.19% | 93.83% | 姜云腾/窦歆禹 | 94.8% | 是 | 新增STR的场景，验证存在新问题 | / | / |  | 是
SYNC+_0205 | Theme | 10 | 5 | 2 | 3 | 0 | 50% | 70% | 杨春明/董晗禹 | 100% | 是 | 发散测试场景 | / | / |  | 是
SYNC+_0134 | 数字香氛 | 32 | 31 | 1 | 0 | 0 | 96.88% | 100% | 姜云腾/董晗禹 | 100% | 是 | 新增STR的场景，验证存在新问题 | / | / |  | 是
SYNC+_Z0050 | 无线充电 | 4 | 4 | 0 | 0 | 0 | 100% | 100% | 杨春明/王跃鑫 | 100% | 否 |  | / | / |  | 是
SYNC+_Z1000 | Launcher | 135 | 134 | 1 | 0 | 0 | 99.26% | 100% | 杨惟婧/肖梁 | 100% | 是 | 发散测试场景 | / | / |  | 是
SYNC+_Z0060 | Car Power | 89 | 88 | 0 | 0 | 1 | 98.88% | 98.88% | 杨春明/秦诚 | 98.65% | 否 |  | / | / |  | 是
SYNC+_Z0153 | GNSS | 35 | 35 | 0 | 0 | 0 | 100% | 100% | 赵雅非/徐俊 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0036 | Bezel Diagnostics工程模式 | 52 | 52 | 0 | 0 | 0 | 100% | 100% | 赵雅非/谢鑫 | 100% | 否 |  | / | / |  | 是
SYNC+_Z0129 | 蓝牙儿童座椅 | 45 | 44 | 1 | 0 | 0 | 97.78% | 100% | 黄钊敏/南东东 | 97.44% | 否 |  | / | / |  | 是
SYNC+_0264 | EMR | 52 | 52 | 0 | 0 | 0 | 100% | 100% | 姜云腾/徐欢 | 100% | 否 |  | / | / |  | 是
SYNC+_0021 | DLNA | 15 | 15 | 0 | 0 | 0 | 100% | 100% | 杨惟婧/贺金 | 100% | 否 |  | / | / |  | 是
SYNC+_0073 | 雷达 | 208 | 0 | 1 | 207 | 0 | 0% | 0.4808% | 黄钊敏/蔡宇飞 | 100% | 是 | 新引入阻塞BUG，APIMCIM-22000 | / | / |  | 是
SYNC+_Z0037 | FNV诊断 | 25 | 12 | 1 | 12 | 0 | 48% | 52% | 杨春明/于凯凯 | 48% | 否 |  | / | / |  | 否
SYNC+_0265 | V2I | 28 | 26 | 2 | 0 | 0 | 92.86% | 100% | 肖文迪/董晗禹 | 100% | 是 | 新增两个BUG | / | / |  | 否
SYNC+_0122 | VHA | 99 | 99 | 0 | 0 | 0 | 100% | 100% | 杨春明/胡远征 | 98.95% | 否 |  | / | / |  | 否
SYNC+_Z0033 | Provisioning | 4 | 4 | 0 | 0 | 0 | 100% | 100% | 杨惟婧/于凯凯 | 100% | 否 |  | / | / |  | 否
SYNC+_0164 | Account | 21 | 17 | 2 | 2 | 0 | 80.95% | 90.48% | 赵雅非/ford | 75% | 否
SYNC+_0165 | Enhance Memory | 128 | 84 | 10 | 28 | 6 | 65.62% | 73.44% | 姜云腾/李行键 | / | 否 | 首轮交付
| STR | 28 | 23 | 2 | 3 | 0 | 82.14% | 89.29% | 杨春明/秦诚 | 91.67% | 是 | 新增了测试场景
SYNC+_Z0023 | 流量统计 | 26 | 26 | 0 | 0 | 0 | 100% | 100% | 李可可/ | 100% | 否
SYNC+_0223 | MMOTA | 252 | 238 | 0 | 14 | 0 | 94.44% | 94.44% | 李可可&黄钊敏/陈明瑶&刘畅 | 66.8% | 否
Total |  | 3428 | 3049 | 62 | 299 | 19 | 88.94% | 90.75%
SYNC+_Z0127 | Audio 外置(24ch) | [7 empty] | 袁露/杨永恒 | 74.74% |  |  | / | / |  | 是
SYNC+_Z0028 | Rear audio（24ch） | [7 empty] | 袁露/李行健 | 100% |  |  | / | / |  | 是
SYNC+_0126 | 音源矩阵(Ecall)-(24ch) | [7 empty] | 袁露/杨永恒 | 82.96% |  |  | / | / |  | 是

## 重点模块列表 (hidden)
DLNA
Car Power
Car input
Theme
GNSS
Rear audio
Launcher
Audio 内置
Audio 外置（12ch）
Audio 外置（24ch）
音源矩阵(Ecall-12ch)
音源矩阵(Ecall-24ch)
音源矩阵(Ecall)
Vehicle Setting
数字香氛
无线充电
Multi -display
FCS(Account)
Bezel Diagnostics工程模式
个性化设置档案
HVAC
VCS
雷达
FAPA
powerflow能量流
EMR
蓝牙儿童座椅

## R06.1_Fix (hidden)
Issue key | Summary | Reporter | Status | Assignee | Component/s | Labels | Labels | Priority | Fix Version/s
APIMCIM-13801 | Phase 5：【必现】路试时，副驾有人，打开爱奇艺播放视频，卡顿并闪退 | jsun62 | Approval | jsun62 | Video | CDX707 | Inhouse_Platform | Immediate Gating | LA_R06.1_ENG
APIMCIM-9608 | [100%] MMOTA_China: Upgrade TCU by VI, the sync+ screen turns black when vehicle enters inhibit state | jzhan376 | Approval | jzhan376 | MMOTA | Inhouse_Platform | MigratingToCloud | Immediate Gating | LA_R06.1_ENG
APIMCIM-13273 | 【Phase V】【CDX707】【TOP】【DLNA】【5/5】TCU网环境下媒体投射开关异常，各模式也无法开启关闭 | lshi42 | Approval | zqiu12 | DLNA | CDX707 | Inhouse_Platform | Immediate Gating | LA_R06.1_ENG
APIMCIM-11765 | Phase5:[必现][CDX707]点击车模上的故障预警无法跳转到故障详情页 | xwang310 | Done | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | Immediate Gating | LA_R06_ENG
APIMCIM-13930 | Phase 5：【偶发】实车路试时，后台总是发生com.ford.sync.apa Crash | jsun62 | Approval | jsun62 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13540 | [100%] MMOTA_China: Entering into "preparing to update" page, ignition run, update failure has pop up, but updating progress still dominating the screen. | yli391 | Approval | yli391 | MMOTA | CDX707 | ECG | Gating | LA_R06.1_ENG
APIMCIM-13080 | 【Phase V】【CDX707】【R06.1-Production】【A】【2/20】移动widget card出现重叠或不显示 | zliu151 | Approval | zliu151 |  | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13745 | [10%] MMOTA_China: OTA updating SOC on vehicle, occasionally SOC installation failed. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13230 | Phase 5：【必发】H689272 13：59 在空调界面点击智能新风，提示“获取滤芯状态失败，联系客服 错误代码：-300” | hmo3 | Test | cchen244 | Auto Air Refresh | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12618 | Phase5:[必现][CDX707]发动机没启动IVI上显示车辆故障信息 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10295 | Phase5:[100%][CDX707] [CCS]After powercycle，no ccs sharing popup | qshi14 | Approval | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12602 | Phase5:[必现][CDX707]After Master reset, no ccs sharing popup | qshi14 | Approval | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13303 | [100%] MMOTA_China:Update TCU by VI and the activation conditions are not met, IVI does not pop up the corresponding pop-up according to the type of precondition | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12274 | Phase5:[偶现]DTC 0xE40100 | xhuang93 | In Progress | mzhuo1 | Diagnostic | EOL | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13402 | 【Phase V】【CDX707】【A】【儿童座椅】【5/5】车辆设置中儿童座椅功能无法进入，点击闪退 | zqiu12 | Approval | zqiu12 | BT Child Seat | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13276 | 【Phase V】【CDX707】【A】【TC】【5/5】睡眠唤醒、首次上电或切换两次驾驶模式后，瞬时油耗指示归零 | xdu22 | Approval | xdu22 |  | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13138 | 【Phase V】【CDX707】【A】【Audio】【5/5】24ch功放，播放音乐，触发关机动画，恢复Run状态后，音乐播放无声. | ywang535 | Approval | ywang535 | Audio | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13729 | Phase5_【CDX707】【黑盒】【必现】【MMOTA】VI-TCU，安装结束后，IG=off，车辆不进入激活状态，更新失败 | cyang114 | Closed with Accept | gyuan6 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12714 | [CDX707][Performance][ResponseaTime]Launcher显示到SDM可用响应时间过长，需要优化。 | ljia14 | Approval | ljia14 | System Performance | CDX707 | digitalee | Gating | LA_R06.1_ENG
APIMCIM-12893 | Phase 5：【偶发】断网后，发生com.ford.sync.fnvservice/com.yfve.report Crash | jsun62 | Approval | jsun62 | FNV | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12738 | Phase 5：【偶发】首页widget编辑页，重复快速拖动改变卡片和位置，launcher发生闪退 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12646 | Phase 5：【必现】Launcher主页3D车模不显示 | hzhan238 | Approval | hzhan238 | 3D Vehicle model | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12795 | Phase 5：【必现】唤醒语音：播放/上一首/下一首，USB音乐播放，但Audio off并未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12217 | Phase 5：【偶发】RACM端切源到随心听，随心听播放页显示错误的歌曲信息 | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-11450 | 【R05-回归测试】【广场】【必现】03:15 我的收藏编辑页面退出后会弹应用商店弹窗 | ntian2 | Approval | ntian2 | Launcher | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-11789 | Phase 5：【必现】首页，能把同一个卡片拖到四个widget位上 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12868 | Phase 5：【偶发】蓝牙音乐页面卡死，点击Home键，再次打开随心听显示黑屏 | jsun62 | Approval | jsun62 | BT Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12292 | Phase 5：【必现】播放蓝牙音乐时，RACM端点击Audio off按钮无法关闭媒体音频 | jsun62 | Approval | jsun62 | BT Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12892 | Phase 5：【偶发】爱奇艺播放时，发生四个APP Crash | jsun62 | Approval | jsun62 | Video | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12796 | Phase 5：【必现】唤醒语音：音量大一点/音量小一点，USB音乐未播放，Audio off也未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12864 | 【台架】【偶现】【CDX707】【widget卡片】widget卡片样式变小 | ntian2 | Approval | ntian2 | Map&Navigation | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12941 | 【Phase V】【CDX707】【A】【BT Phone】【5/5】oppo find X 通话车机无声，使用手机铃声来电去电，车机无声 | zqiu12 | Closed with Accept | zqiu12 | BT Phone | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12712 | Phase 5：【偶现】TCU有网的车，连接WiFi，一直显示正在加入网络.. | tshan3 | Approval | tshan3 | WiFi Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12317 | Phase 5：【高频】播放QQ音乐，RACM端点击音乐源按钮，音乐源页面显示空白 | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10872 | Phase 5：【偶现】3D车模位置不正确 | jxu148 | Approval | jxu148 | 3D Vehicle model | CDX707 | CDX707C_UAT_1st | Gating | LA_R06.1_ENG
APIMCIM-11832 | Phase 5：【偶发】爱奇艺播放时，发生com.baidu.iov.dueros.videos ANR | jsun62 | Approval | jsun62 | Video | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-9451 | Phase 5: 【偶发】【AutoTest】泊车相关功能信号接收有延迟，不响应现象 | yzhu104 | Approval | yzhu104 | Parking Assist | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12569 | Phase5:【必现】【CDX707】播放USB音乐->打开地图->导航路线->开始导航，导航播报结束后媒体音量变大，退出地图后恢复正常 | zsu13 | Approval | zsu13 | Audio | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13549 | 【Phase V】【CDX707】【A】【Audio】【1/10】播放音乐，挂断电话后，音乐的声音突然变大. | ywang535 | Approval | ywang535 | Audio | CDC707 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-11862 | Phase 5：【必现】蓝牙歌曲在播放，但没有退出Audio off | jsun62 | Approval | jsun62 | Audio | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-11221 | Phase5：【偶现】在地图页面，旋转声音按钮调节媒体音量，将媒体音量调整为0后，QQ音乐依然有声音发出 | jchen384 | Approval | jchen384 | Audio | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12924 | Phase 5：【必现】蓝牙音乐播放时，RACM端高亮显示"循环模式"按钮 | jsun62 | Approval | jsun62 | BT Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12887 | Phase 5：【必现】唤醒语音：播放/上一首/下一首，QQ音乐播放，但Audio off并未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13614 | Phase 5：【必发】H689293 13：46 系统设置—音效设置—平衡 衰减—重置失败 必现 | hmo3 | Approval | hmo3 | System Setting | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12220 | Phase 5：【必现】插入U盘后，RACM端不会立即显示USB音乐入口 | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12197 | Phase 5：【偶发】快速连续点击第一个卡片的删除按钮，发生com.ford.sync.controllerlauncher Crash | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13647 | Phase 5：【偶发】【AutoTest】Monkey测试时，出现com.ford.sync.hvac的crash | jsun62 | Approval | jsun62 | BT Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10369 | Phase 5：【必现】无TCU环境下，视频投屏后一直加载中，无法投屏 | xwang314 | Approval | xwang314 | DLNA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12878 | Phase 5：【必现】唤醒语音：音量大一点/音量小一点，Audio off未解除，蓝牙音乐未播放 | jsun62 | Approval | jsun62 | BT Music | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13235 | Phase 5：【偶发】H689272 15：27 点击泊车辅助按键，选择泊车后进入无信息显示的界面，然后退出不了点击下方的菜单也无反应 | hmo3 | Approval | hmo3 | Vehicle Setting | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-13016 | Phase 5：【偶发】倒档来车预警影像开关点击无法打开 | sliu141 | Approval | sliu141 | Vehicle Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12140 | Phase 5：【偶发】设置发生com.yfve.settings ANR | jsun62 | Approval | jsun62 | System Setting | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13491 | [100%] MMOTA_China: Upgrade TCU by VI, precondition pop up exist all the time during activation. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-7895 | [100%] MMOTA_China:OTA升级SOC,下载过程中发Shed_Level_Req:3_SHED2_CONTIN或Shed_Level_Req=5_SHED_ENG_OFF,进入安装会报SIM_E1001,OTAM_E1008,OTAM_E1016 | jzhan376 | Approval | jzhan376 | MMOTA | Inhouse_Platform | MigratingToCloud | Gating | LA_R06.1_ENG
APIMCIM-12785 | Phase5:[10%][CDX707]登录账号后首页头像未同步更新 | lxue15 | Approval | lxue15 | Account | CDX707 | CDX707_CVPP | Gating | LA_R06.1_ENG
APIMCIM-12270 | [CDX707][Performance][Stability]monkey test ,vendor.ford.soa happens native crash | rhuang35 | Approval | rhuang35 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12363 | Phase 5：【必现】副驾随心听却支持添加到default卡片 | jsun62 | Approval | jsun62 | Music | CDX707 | CDX707C_UAT_2nd | Gating | LA_R06.1_ENG
APIMCIM-12264 | [CDX707][Performance][Stability]monkey test,com.ford.sync.controllerlauncher happens 1 times crash | rhuang35 | Approval | rhuang35 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12499 | Phase 5：【偶现】 模拟导航无声14:28 | rzhao22 | Approval | rzhao22 | Audio | R06_SIGN_OFF | R061_MUST_FIX | Gating | LA_R06.1_ENG
APIMCIM-12263 | [CDX707][Performance][Stability]monkey test,com.ford.sync.fnvservice happens 2 times crash | rhuang35 | Approval | rhuang35 | System Stability | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-10984 | [100%] MMOTA_China: Upgrade TCU by VI, The time displayed in the "System Update Reminder" pop-up is inconsistent with the set time | jzhan376 | Approval | jzhan376 | MMOTA | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-12314 | Phase 5：【高频】删除蓝牙设备，RACM端点击蓝牙音乐源按钮，发生多个Crash | jsun62 | Approval | jsun62 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-12110 | Phase5:[CDX707]No banner message pops up after filter saturation | cshengji | Approval | cshengji | Auto Air Refresh | CDC_Phase5 | CDX707 | Gating | LA_R06.1_ENG
APIMCIM-10920 | [CDX707][Performance][Stability]monkey test,com.yfve.settings happens 3 times crash | sjie2 | Approval | sjie2 | System Stability | CDX707 | digitalee | Gating | LA_R06.1_ENG
APIMCIM-12021 | Phase5:[必现][CDX707]音效设置页面的部分设置项点击无效 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | IACC, | Gating | LA_R06.1_ENG
APIMCIM-10185 | [100%] MMOTA_China: USB plugged to upgrade MCU,during download/ installation/pending activation when upgrade SOC via OTA,the USB upgrade cannot continue after SOC upgrade is canceled. | jzhan376 | Closed with Accept | dliu79 | MMOTA | CDX707 | Inhouse_Platform | Gating | LA_R06.1_ENG
APIMCIM-13050 | Phase5:[100%]CDX707 Authorization time popup text error | jgu37 | Approval | jgu37 | V2I | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13649 | Phase 5：【偶发】【AutoTest】Monkey测试时，出现com.ford.sync.controllerlauncher Crash | jsun62 | Test | zzhou68 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13807 | Phase 5：【偶发】路试时，后台发生com.ford.sync.fnvservice Crash | jsun62 | Approval | jsun62 | FNV | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10694 | Phase 5：【必现】后屏来源播放蓝牙或USB音乐，后屏音频关闭按键交互出错 | tshan3 | Approval | wxie15 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13079 | Phase5:[100%][CDX707]VPA status is about seat when query E-manual | lxue15 | Approval | lxue15 | Virtual Personal Assistant | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13338 | [100%] MMOTA_China: Upgrade TCU by VI,ADB log prints lots of error messages about the statusbar during upgrade process | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13482 | [100%] MMOTA_China: Upgrade TCU by VI, precondition pop up button not match with UI. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-5293 | Phase 5：【812】【必现】唤醒车机，语音:打开分屏。播报：操作失败 | tshan3 | Approval | tshan3 | VR | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13125 | Phase5:[CDX707][Performance][Roadtest]Roadtes test, in the background, the cpu usage rate of controller launcher is as high as 20%, without releasing | sjie2 | Approval | sjie2 | System Performance | digitalee | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13600 | Phase 5：【必发】H689286 1121 车辆启动时开着“安全开门预警”，熄火后再次启动车辆，“安全开门预警”按钮自动关闭后再次开启。必现 | hmo3 | Approval | hmo3 | Vehicle Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13678 | Phase5：【必现】在地图页面，按压中控台上的“¦P¦”按键进入自动泊车页面，自动泊车页面未占满整个页面，操作屏顶部为地图的画面 | jchen384 | Approval | jchen384 | Parking Assist | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13603 | Phase 5：【必发】689306 10：46 主界面点击车模，进入车内，点击林肯香氛按钮，打开林肯香氛，选择其他香氛时开关会有一个关闭开启的现象 必现 | hmo3 | Approval | hmo3 | Drive Mode | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13328 | Phase 5：【必发】H689281 18：53 每次按泊车辅助按键，中控屏都会显示泊车雷达按钮从关闭到打开的现象 | hmo3 | Approval | hmo3 | System Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12430 | Phase 5: 【必现】车钥匙检测提示没有主动get Can信号反馈状态 | xli318 | Approval | xli318 | Vehicle Setting | GIM | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13536 | Phase5:[必现][CDX707]Ambient light is still display opening in 3D car model when the light switch is turned off. | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11837 | phase5：【偶现】偶现点击车路协同闪退到主界面 | lshi42 | Approval | zqiu12 | Vehicle Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11824 | 【Phase V】【CDX707】【A】【RACM】【3/5】后屏source源信息，蓝牙图标显示为随心听，且切源时大概率不显示，插入U盘后，播放源和显示的源信息不同步 | lshi42 | Approval | zqiu12 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10427 | Phase5:[CDX707][偶现]共享位置关闭的情况下，需要定位授权的应用可以选择权限 | qshi14 | Done | qshi14 | User Privacy | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10429 | Phase5:[CDX707][偶现]共享位置打开的情况下，定位授权app提示“"无法开启定位”---请开启“共享车辆位置”后重试 | qshi14 | Done | qshi14 | User Privacy | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12157 | Phase5_【CDX707】【黑盒】【必现】【CarAudio外置】导航声音不在播报的情况下设置，再次导航音量不起效果 | tzhou37 | Closed with Accept | tzhou37 | Audio | CDC707 | CDX707 | High | LA_R06.1_ENG
APIMCIM-13509 | Phase 5：【必发】H689270 1035 首次打开空调出现一条灰色残影。 | hmo3 | Approval | hmo3 | Climate | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12631 | Phase 5：【偶现】已保存的手机热点开启后，车机未自动连接上wifi | hzhan238 | Approval | hzhan238 | WiFi Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12886 | Phase 5：【必现】播放QQ音乐，快进快退时唤醒语音，语音结束后，歌曲播放，但audio off仍未解除 | jsun62 | Approval | jsun62 | Music | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11124 | 【Phase V】【CDX707】【A】【System Setting】【5/5】音效设置界面进入音乐界面，在音乐界面点击“音效设置”按钮进入音效设置，无法进入音量设置/均衡器/平衡衰减界面. | zqiu12 | Done | zqiu12 | System Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12833 | Sensitive Data(VIN) Disclosure – AccountService | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse | High | LA_R06.1_ENG
APIMCIM-12583 | TLS not Verified – swuservice.apk | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10191 | Phase5:[偶现][CDX707]brandreset清掉授权后， CCS icon图标显示为授权状态图标 | qshi14 | Monitor | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12590 | [100%] MMOTA_China: USB update SOC with corrupt SW file, IVI pop up is wrong. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-8442 | [20%] MMOTA_China: VIL file is empty after USB upgrade ECG success | yli391 | Approval | yli391 | MMOTA | CDx707C | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10901 | Phase 5：【必现】插拔U盘，后排屏音源显示错误 | bliu94 | Approval | bliu94 | Multi-Screen Interaction | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-10896 | Phase 5：【必现】RACM切源，随心听/USB切到蓝牙音乐，RACM音源图标显示error | bliu94 | Approval | bliu94 | Multi-Screen Interaction | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-12931 | Phase 5：【必现】断电再上电，Audio off不被记忆 | jsun62 | Rejected | jsun62 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11801 | Phase 5：【必现】空调内循环按键点击打开与关闭，在按键左侧有动效 | tshan3 | Approval | tshan3 | Climate | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12202 | [100%] MMOTA_China: USB update ECG/TCU, updating progress jump from 0% to 100%. | yli391 | Approval | jwang373 | MMOTA | CDX707 | ECG | High | LA_R06.1_ENG
APIMCIM-10681 | Phase 5：【必现】后屏蓝牙音乐界面，记忆显示了USB的播放模式：随机与循环。 | tshan3 | Approval | tshan3 | Multi-Screen Interaction | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12581 | Private keys are found on swuservice.apk | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12194 | Phase5:[100%][CDX707]New user guide screen displays after changing account | lxue15 | Approval | lxue15 | Account | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11813 | Phase5_[CDX707C][必现】【Enhanced Memory】 创建档案时，IVI下发信号CtrStkDsplyOp_D_Rq值错误 | nli52 | Approval | nli52 | Personalization | CDX707 | CDX707C | High | LA_R06.1_ENG
APIMCIM-12188 | Phase5:[100%][CDX707] The content layout of the shared pop-up window is not beautiful, and the text is truncated | qshi14 | Approval | qshi14 | Customer Connectivity Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12040 | Phase5[CDX707][必现]:护航详情同级页面语音无法打开胎压监测页面 | xwang310 | Approval | xwang310 | Vehicle Health Alert | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12556 | Phase 5：【必现】+1屏，删除所有卡片，再添加7个卡片，第四个卡片size偏小 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12557 | Phase 5：【必现】+1屏，长按一个卡片时，点击"保存"按钮，选中的卡片仍显示编辑态 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12326 | [100%] MMOTA_China: Upgrade TCU by VI,"system update successful" pops up when the update progress bar reaches 11% | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12118 | Phase 5：【必现】语音切换声源定位时，tts播报错误 | tshan3 | Approval | tshan3 | VR | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11463 | Phase5：【偶现】退出 Revel@Experience 视频，闪现视频进度条 | jchen384 | Approval | jchen384 | System Setting | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-11237 | 【语音】 【基础功能】 【CDX707】 关闭自动模式tts播报已关闭，但实车上屏幕图标没有变化，仍显示自动模式 | ntian2 | Approval | ntian2 | VR | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12644 | Phase 5：【必现】关闭林肯香氛后3D车模里仍显示香氛打开状态 | hzhan238 | Approval | hzhan238 | 3D Vehicle model | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12587 | Phase 5: 【必现】车辆控制界面，点击下方车辆控制按钮，车辆控制页面不应进行刷新。 | xli318 | Approval | xli318 | Vehicle Setting | GIM | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12130 | Phase 5: 【偶现】导航，Media和电话交互，挂断电话后Media会出现爆音 | jzeng28 | Closed with Accept | tzhou37 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10933 | Phase5_【CDX707】【黑盒】【偶现】【FAPA】在360摄像头环境下，自动泊车不可用偶现无播报 | tzhou37 | Closed with Accept | tzhou37 | Fapa | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-12201 | [100%] MMOTA_China: USB update ECG/TCU/SYNC+, the remaining file number increasing, not decreasing. | yli391 | Approval | yli391 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-7237 | Phase5：【必现】[CDX707][HMI走查] 3D车模_车辆（车模相关）快捷控制视觉布局问题 | fwang116 | Done | yliu404 | 3D Vehicle model | CDX707 | CDX707C_UAT_1st | High | LA_R06.1_ENG
APIMCIM-11877 | Phase5:[100%][CDX707]点击车身颜色tab会重置色环和车身颜色 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11436 | Phase5：【必现】[CDX707][HMI走查] 点击时的水波纹效果不同 | fwang116 | Done | fwang116 |  | CDX707 | CDX707_HMI | High | LA_R06.1_ENG
APIMCIM-11733 | Phase5_[CDX707C][必现】【Enhanced Memory】 删除个人账号下对应的个性化档案后，再次切换回该账号，会一直提示该账号下个性化档案已删除 | nli52 | Approval | nli52 | Personalization | Inhouse_Platform | TW43 | High | LA_R06.1_ENG
APIMCIM-11623 | Phase5-[CDX707C][必现】【Enhanced Memory】在D/R/L/N档时，IVI界面会弹出个性化保存弹框 | nli52 | Approval | nli52 | Personalization | CDX707 | CDX707C | High | LA_R06.1_ENG
APIMCIM-12351 | Phase5:[必现][CDX707]自定义模式下车门和地板灯光调至最低后返回显示异常 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12426 | Phase5：【必现】[CDX707][HMI走查]_info弹窗置于后台，再次打开后，弹窗重新弹出 | yqin24 | Done | yqin24 | System UI | CDX707 | CDX707_HMI | High | LA_R06.1_ENG
APIMCIM-12554 | Phase 5：【偶现】出风口滑动调节界面与空调主界面重叠 | tshan3 | Approval | tshan3 | Climate | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11439 | Phase5：【必现】[CDX707][HMI走查] 系统按钮动效问题 | fwang116 | Done | fwang116 |  | CDX707 | CDX707_HMI | High | LA_R06.1_ENG
APIMCIM-11874 | Phase5:[100%][CDX707]重置第五个车身颜色tab异常 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12195 | Phase 5：【必现】[CDX707]空调风量调节背景部分过亮，出风口整个偏上 | jyi23 | Approval | jyi23 | Climate | CDX707_HMI | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11988 | Phase5:[偶现][CDX707]车外页熄火需要有“发动车辆才可以使用全部车辆功能”提示 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12002 | Phase5:[必现][CDX707]3D车模页面的音效设置同步不到系统音效设置页面 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-9524 | [100%] MMOTA_China:Click the "Clear" button, the system update plan cannot be cleared | jzhan376 | Approval | jzhan376 | MMOTA | Inhouse_Platform | MigratingToCloud | High | LA_R06.1_ENG
APIMCIM-9092 | Phase5:【必现】[CDX707]快速滑动选择按摩方式，选中的按摩方式仍然会与其他按摩方式多次来回切换 | xwang310 | Approval | xwang310 | 3D Vehicle model | CDX707 | CDX707C_UAT_1st | High | LA_R06.1_ENG
APIMCIM-9541 | [100%] MMOTA_China: Upgrade TCU by VI, the "System update schedule not set" popup does not pop up when pending activation | jzhan376 | Approval | jzhan376 | MMOTA | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12200 | Phase 5：【必现】+1屏的widget编辑状态，点击Home键，再向左滑动到+1屏，状态栏与右上角的按钮重叠，且卡片不晃动 | jsun62 | Approval | jsun62 | Launcher | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-11790 | Phase 5：【必现】音效设置内的菜单点击时，没有白色背景的点击动效 | jsun62 | Approval | jsun62 | General Setting | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-12283 | Phase5：【必现】车模重置车身颜色，最后一个光圈一下重置到初始颜色，需要点击两次重置按钮才能重置到初始的颜色 | jchen384 | Approval | jchen384 | 3D Vehicle model | CDC_Phase5 | CDX707 | High | LA_R06.1_ENG
APIMCIM-12134 | Phase 5: 【必现】导航和QQ音乐交互时，导航播报时QQ音乐不会降音播放 | jzeng28 | Closed with Accept | yyang179 | Audio | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-10571 | Phase5：【必现】[CDX707][HMI走查] Climate空调电动出风口_页面视觉布局问题 | fwang116 | Done | xdou | Climate | CDX707 | Inhouse_Platform | High | LA_R06.1_ENG
APIMCIM-13216 | Phase 5：【必现】CDX707 允许车路协同infobook,授权时间的弹窗“年”字没适配主题，左上角关闭按钮和图标“取消”重复 | lzhan249 | Approval | lzhan249 | V2I | CDX707_HMI | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-12037 | Phase5：【必现】[CDX707][HMI走查]多模块空中升级 (MMOTA) _按钮动效问题 | fwang116 | Done | cyang114 | MMOTA | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-13215 | Phase 5：【必现】CDX707 系统设置进度条颜色没适配 | lzhan249 | Approval | lzhan249 | System Setting | CDX707_HMI | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-13317 | Test Page with Shortcuts – VoiceControlSevice | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-12629 | Phase5:【必现】【CDX707】车外天窗控制界面与主界面重叠 | swang218 | Closed with Accept | wxiao13 | 3D Vehicle model | FCPA | Inhouse_App | Medium | LA_R06.1_ENG
APIMCIM-12816 | Phase 5：【必现】3D车模车辆健康报警和各个故障显示点击没有按钮音效 | hzhan238 | Approval | hzhan238 | 3D Vehicle model | CDX707 | ICV | Medium | LA_R06.1_ENG
APIMCIM-12844 | Exportable Activity DoS – AccountService | xzhan221 | Test | xzhan221 | Cybersecurity | Cybersecurity | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-11966 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_弹窗页面布局问题 | fwang116 | Done | wxiao13 | V2I | CDC_TS_HMI | CDX707 | Medium | LA_R06.1_ENG
APIMCIM-12410 | Phase5：【必现】3D车模顶部的动画和坐享净界主题的动画不一致 | jchen384 | Approval | jchen384 | 3D Vehicle model | CDC_Phase5 | CDX707 | Medium | LA_R06.1_ENG
APIMCIM-12208 | Phase5：【必现】[CDX707][HMI走查]快捷控制-动效问题 | fwang116 | Done | fwang116 | Drive Mode | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12205 | Phase5：【必现】[CDX707][HMI走查]手机无线充电-动效问题 | fwang116 | Done | fwang116 | Wireless Charging | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12206 | Phase5：【必现】[CDX707][HMI走查] _DAT Setting_动效问题 | fwang116 | Done | cxu63 | DAT Setting | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12144 | Phase5：【必现】[CDX707][HMI走查] DIDC-动效问题 | fwang116 | Done | cxu63 | Driver Info | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12039 | Phase5：【必现】[CDX707][HMI走查]遥控启动设置-弹窗动效问题 | fwang116 | Done | zlian2 | Remote Control | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12030 | Phase5：【必现】[CDX707][HMI走查] _launcher_toast动效问题 | fwang116 | Done | lxiao19 | Launcher | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11802 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_视觉布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11806 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_info页面布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11811 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_申请流程页面布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-12043 | Phase5：【必现】[CDX707][HMI走查] 诊断分析-动效问题 | fwang116 | Done | cwang236 | FNV | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-11807 | Phase5：【必现】[CDX707][HMI走查] _车路协同_V2I设置_toast布局问题 | fwang116 | Done | dnan1 | V2I | CDX707 | CDX707_HMI | Medium | LA_R06.1_ENG
APIMCIM-10094 | Phase5：【必现】[CDX707][HMI走查] _system UI & launcher_视觉布局问题 | fwang116 | Done | fwang116 | System UI | CDX707 | Inhouse_Platform | Medium | LA_R06.1_ENG
APIMCIM-7935 | Phase5：【必现】[CDX707][HMI走查] Face ID_条款界面视觉布局问题 | fwang116 | Done | jzhu79 | FaceID | CDX707 | HMI | Medium | LA_R06.1_ENG
APIMCIM-12654 | Phase 5: 【必现】把主题从"自在航行"切换至“坐享净界”，车辆控制界面右侧的滑条未变蓝色。 | xli318 | Approval | xli318 | Vehicle Setting | GIM | Inhouse_Platform | Low | LA_R06.1_ENG
APIMCIM-10556 | Phase5_[CDX707C][必现】【Enhanced Memory】 After Paak was associated with Profile, the Paak name is wrong | nli52 | Approval | nli52 | Personalization | CDX707 | CDX707C | Low | LA_R06.1_ENG

## R06.1_Fix_TS (hidden)
Issue key | Summary | Reporter | Status | Created | Assignee | Component/s | Affects Version/s | Priority | Labels | Labels | Labels | Labels | Labels | Labels | Labels | Labels
APIMCIM-12874 | Phase 5：【偶现】625实车，连接WiFi后，自动会被关闭 | tshan3 | To Do | 2022-10-21 04:25 | tshan3 | WiFi Setting | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-12903 | Phase 5：【偶发】RACM端显示“音频关闭”，但是点击“关闭”按钮无响应 | jsun62 | In Progress | 2022-10-23 22:50 | bliu94 | Multi-Screen Interaction | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-13437 | Phase 5：【偶发】NTT 707 EPT02 684122 1435 驾驶辅助，开关倒档来车预警，屏幕跳动 | hmo3 | To Do | 2022-11-03 23:52 | hmo3 | Driver Assistance | LA_R06_ENG | High | CAF | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | IVI
APIMCIM-12815 | Phase 5：【必现】已连接wifi网络，下载导航语音包时，依然弹出“非wifi网络将消耗移动流量，是否继续下载"的弹框 | jxu148 | In Progress | 2022-10-20 11:31 | jzhan372 | Map&Navigation | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Plaform | Inhouse_Platform | R061_MUST_FIX
APIMCIM-13822 | Phase 5：【必现】空调开关无法开启 | xwang314 | To Do | 2022-11-12 04:57 | xwang314 | Climate | LA_R06_ENG | Gating | CDC_IVITst | CDC_phase5 | CDX707 | Inhouse_Platform
APIMCIM-12274 | Phase5:[偶现]DTC 0xE40100 | xhuang93 | In Progress | 2022-10-07 03:35 | mzhuo1 | Diagnostic | LA_R05_ENG | Gating | CDC_Phase5 | CDX707 | EOL | Inhouse_Platform | IVI | R061_MUST_FIX | W43 | W44
APIMCIM-13917 | Phase5_【CDX707】【黑盒】【必现】【Audio】进入静音模式后，播放音乐，依旧有声音 | cyang114 | To Do | 2022-11-14 05:01 | cyang114 | Audio | LA_R06_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform | W46
APIMCIM-14001 | Phase 5：【必现】调节座椅页面，未高亮的菜单的"<"按钮都是高亮 | jsun62 | To Do | 2022-11-15 09:02 | jsun62 | Seat | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13737 | 【PhaseV】【CDX707】【A】【RACM】【5/5】RACM无法调节音量 | zqiu12 | To Do | 2022-11-10 01:10 | zqiu12 |  | LA_R06.1_ENG | Gating | CDC_IVITst | CDC_Phase5 | CDC707 | CDX707 | Inhouse_Platform | W46 | YFVE
APIMCIM-13855 | Phase 5：【偶发】空调调出动效异常 | jxu148 | To Do | 2022-11-13 08:32 | xdou | Climate | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-14007 | Phase 5：【偶发】实车路试时，车机突然断网 | jsun62 | To Do | 2022-11-15 09:27 | jzhan372 | Carrier | LA_R06_ENG | Immediate Gating | CDC_IVITst | CDC_Phase5 | CDX707 | CVPPVOCF | Inhouse_Platform | VOCF
APIMCIM-14046 | Phase 5：【必现】历史消息页面，点击未接来电的"通话"按钮，无任何响应 | jsun62 | To Do | 2022-11-16 02:12 | lwang287 | Launcher | LA_R06_ENG | Gating | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-13815 | Phase 5：【必现】副驾随心听总是显示"加载失败"，完全不能用 | jsun62 | In Progress | 2022-11-12 03:08 | jzhan372 | Music | LA_R06_ENG | Gating | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | R07_MUST_FIX_YF | VOCF
APIMCIM-13989 | Phase 5：【偶现】媒体音调节无效，旋钮和音量设置均无效 | cyang114 | To Do | 2022-11-15 03:16 | yyang179 | Audio | LA_R06_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform | TS
APIMCIM-13316 | Exportable Component DoS – Inhouse APPs | xzhan221 | In Progress | 2022-11-02 01:53 | hzhu74 | Cybersecurity |  | Medium | APIM | CDX707 | Cybersecurity | Inhouse_APP | Inhouse_Platform | PenTest | Sync+3.0
APIMCIM-12845 | Lack of APP Hardening-Inhouse | xzhan221 | To Do | 2022-10-21 01:16 | ycai28 | Cybersecurity |  | Medium | APIM | CDX707 | Cybersecurity | Inhouse_Platform | PenTest | Sync+3.0
APIMCIM-13868 | Phase 5：【偶现】路试中Card2突然弹出香氛相关toast | jxu148 | To Do | 2022-11-13 10:40 | wxiao13 | Launcher | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13734 | 【Phase V】【CDX707】【A】【Audio】【5/5】实车LV606 104A 外置功放24CH,平衡/衰减位置不正确. | ywang535 | In Progress | 2022-11-10 00:55 | hzhu74 | Audio | LA_R06.1_ENG | Gating | CDC_IVITst | CDC_Phase5 | CDC707 | CDX707 | Inhouse_Platform | YFVE
APIMCIM-13586 | 【Phase V】【CDX707】【A】【Upgrade】【2/2】OTA整包升级，S1008激活成功后ign run，等待vil上传，等待超过10分钟，没有报S1010 | zqiu12 | To Do | 2022-11-07 02:18 | zqiu12 | MMOTA | LA_R06.1_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform
APIMCIM-14002 | Phase 5：【必现】调节座椅页面，点击"<"">"按钮，只是高亮其菜单 | jsun62 | To Do | 2022-11-15 09:03 | jsun62 | Seat | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13990 | Phase 5：【偶现】【外置功放】平衡衰减调节无效 | cyang114 | To Do | 2022-11-15 03:23 | yyang179 | Audio | LA_R06_ENG | Gating | CDC_IVITest | CDC_Phase5 | CDX707 | Inhouse_Platform | TS
APIMCIM-13863 | Phase 5：【偶发】移动widget，原来的卡片位置黑屏3s | jxu148 | To Do | 2022-11-13 09:33 | cxu63 | Launcher | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | YFVE
APIMCIM-13458 | Phase 5：【偶发】NTT707 EPT02 684122 1445 空调页面风量大小无显示 | hmo3 | To Do | 2022-11-04 02:29 | hmo3 | Climate | LA_R06_ENG | High | CAF | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | IVI | NTT
APIMCIM-14070 | Phase 5：【偶现】挂断蓝牙微信电话后，蓝牙音乐爆音 | jxu148 | To Do | 2022-11-16 03:42 | yyang179 | BT Music | LA_R06_ENG | High | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | VOCF
APIMCIM-13688 | Phase 5：【必现】打开车窗后，3D车模的车窗依旧处于关闭关闭状态 | hzhan238 | To Do | 2022-11-08 19:59 | hzhan238 | 3D Vehicle model | LA_R06_ENG | High | CAF | CDC_Phase5 | CDX707 | ICV | Inhouse_Platform | notbug | phase5_launchTst
APIMCIM-13687 | Phase 5：【必现】在3D车模快捷控制页面停止操作15s，车模不会自动关闭 | hzhan238 | To Do | 2022-11-08 19:56 | hzhan238 | 3D Vehicle model | LA_R06_ENG | High | CAF | CDC_Phase5 | CDX707 | ICV | Inhouse_Platform | notbug | phase5_launchTst
APIMCIM-13793 | Phase 5：【必发】707H689274车辆设置中没有车钥匙检测提示选项 | hmo3 | To Do | 2022-11-11 04:28 | yzhan482 | Vehicle Setting | LA_R06_ENG | High | CAF | CDC_IVITst | CDC_Phase5 | CDX707 | Inhouse_Platform | IVI | NTT

## Jira_issue
Issue key | Summary | Reporter | Priority | Status | Created | Assignee | 问题归属 | 修改计划 | Components
APIMCIM-21416 | Phase5_【U718】【MMOTA】【必现】VI升级TCU，S1003后报E1005 | zhangjian zhou | P0 | Test | 2023-04-22 20:43 | zhongjian fu | ECG
APIMCIM-22000 | Phase5_【U718】【黑盒】【必现】【雷达】发信Rx信号，雷达弹窗触发不出来 | zhaomin huang | P1 | Test | 2023-05-08 01:49 | zhaomin huang | TS | R00修复
APIMCIM-22540 | Phase5_【U718】【必现】【HVAC】改变后排空调温度单位为华氏度，调节条仍显示摄氏度 | Yunteng Jiang | P1 | To Do | 2023-04-05 23:08 | huan xu | TS | R00修复
APIMCIM-20366 | Phase5:[U718][100%]VI update can't be triggered | zhangjian zhou | P1 | In Progress | 2023-03-30 23:03 | zhangjian zhou | ECG
APIMCIM-19576 | Phase5_【U718】【偶现】【MMOTA】VI升级TCU，熄火后无法进入激活-点火查看更新详情无“立即激活”按钮 | zhangjian zhou | P1 | Monitor | 2023-03-17 07:12 | zhangjian zhou | TS | 已修复，但因VI升级阻塞，该BUG无法验证
APIMCIM-19574 | Phase5_【U718】【黑盒】【必现】【MMOTA】USB升MCU，ECG打印S1007，IG=OFF，激活失败，IVI弹出更新失败弹窗 | zhaomin huang | P1 | To Do | 2023-03-17 05:55 | liangzhen.chu | YFVE
APIMCIM-18679 | Phase5_【U718】【偶现】【FNV】FNV诊断中上传日志到云端，有概率无法连接云端，报503 | chunming yang | P1 | To Do | 2023-03-01 22:14 | Xinming Xiao | Ford
APIMCIM-18093 | Phase 5_【U718】【必现】【WiFi Setting】连接需要认证的wifi，会自动变为未连接，之后连接其他wifi会出现相同情况 | chunming yang | P1 | To Do | 2023-02-16 06:23 | Chenyang Zhu | Ford
PSTT-431 | Phase5_【U718】【黑盒】【必现】【PAAK】【智能备用密钥】使用智能备用密钥时，输入车辆启动的密码时，弹窗会把密码输入框遮挡 | Chuanqin Chen | P1 | Analysis | 2023-02-15 02:07 | Wenxiong Cai | Baidu
APIMCIM-16233 | Phase5_【U718】【黑盒】【必现】【拖车】点击想要激活的拖车，TX(45C)指令下发不对（PSTTT-1094 迁移） | Chuanqin Chen | P1 | Reopened | 2023-01-05 08:12 | Wang Qian | YFVE
APIMCIM-17510 | Phase5_【U718】【黑盒】【必现】【Audio】【24ch】点击百度地图进行导航，无声音提示 | tianqi zhou | P1 | To Do | 2023-01-05 03:26 | Peng Wang | Ford | 当前24ch的phoenix架构下的chime还没有通，依赖Harman侧chime通路 support
APIMCIM-17092 | Phase5_【U718】【黑盒】【必现】【Car_Audio】【24ch】车随音速无效果 | tianqi zhou | P1 | To Do | 2022-11-10 22:17 | Peng Wang | Ford
FCIVIOS-15288 | Phase5_【U718】【偶现】【Monkey】ANR in com.ford.sync.trailersettings (com.ford.sync.trailersettings/.TrailerSettingActivity) PID: 18858 Reason: Input dispatching timed out | zhangjian zhou | P2 | To Do | 2023-05-16 05:24 | Liang Xiao
FCIVIOS-15307 | Phase5_【U718】【必现】【FAPA】自动泊车界面，车头前方雷达黄色区域显示不全 | zhangjian zhou | P2 | To Do | 2023-05-16 23:23 | jianing gu
FCIVIOS-15287 | Phase5_【U718】【必现】【HVAC】当前后排温度最高/最低，语音增大/降低温度，有信号下发 | Yunteng Jiang | P2 | To Do | 2023-05-16 04:53 | huan xu
FCIVIOS-15274 | Phase5_【U718】【黑盒】【必现】【3D车模】进入3D车外快捷，点击车模颜色按钮，点击车模颜色弹窗退出颜色弹窗界面 | wendi Xiao | P2 | To Do | 2023-05-15 22:28 | Xingjian Li
FCIVIOS-15270 | Phase5_【U718】【偶现】【Monkey】com.yfve.settings ANR Reason: Input dispatching timed out | zhangjian zhou | P2 | To Do | 2023-05-15 22:01 | zhangjian zhou
FCIVIOS-15268 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】驾驶模式复杂路况vcs信号下发错误 | manyi guan | P2 | To Do | 2023-05-15 05:23 | Liang Xiao
FCIVIOS-15266 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】氛围灯七色颜色和亮度刻度与UI不一致 | manyi guan | P2 | To Do | 2023-05-15 04:39 | Liang Xiao
FCIVIOS-15262 | Phase5_【U718】【黑盒】【必现】【3D车模】进入3D车模氛围灯界面，发送无效信号，点击空白处再次点击氛围灯，氛围灯按钮开启 | wendi Xiao | P2 | To Do | 2023-05-15 03:24 | Xingjian Li
APIMCIM-22380 | Phase5_【U718】【CarAudio】【黑盒】【必现】当前prompt播放中，来电铃声，prompt未停止播放 | Yunteng Jiang | P2 | In Progress | 2023-05-15 02:13 | Niu Tian
FCIVIOS-15258 | Phase5_【U718】【黑盒】【必现】【3D车模】3D车内香氛界面点击多按钮，打开香氛，模拟异常再次打开香氛，退出车控，3D车内香氛未打开 | wendi Xiao | P2 | To Do | 2023-05-15 01:44 | Xingjian Li
FCIVIOS-15257 | Phase5_【U718】【黑盒】【必现】【3D车模】打开香氛，模拟异常，点击空白处再次点击香氛按钮，香氛按钮有一个打开关闭效果 | wendi Xiao | P2 | To Do | 2023-05-15 01:41 | Xingjian Li
FCIVIOS-15246 | Phase5_【U718】【必现】【HVAC】当前是吹脚模式，语音切换吹风模式，未下发吹脚关闭信号 | Yunteng Jiang | P2 | To Do | 2023-05-13 07:27 | huan xu
FCIVIOS-15245 | 【Phase5】【U718】【Launcher】【必现】限行和车牌号重叠 | tianqi zhou | P2 | Tested | 2023-05-12 07:07 | tianqi zhou
APIMCIM-22301 | Phase5_【U718】【黑盒】【偶现】【Launcher】开机第一次联wifi，状态栏wifi图标显示与wifi界面的不一致 | tianqi zhou | P2 | Test | 2023-05-12 05:28 | Zihao Qiu
FCIVIOS-15243 | Phase5_【U718】【必现】【HVAC】进入str前后，空调按钮状态不一致 | Yunteng Jiang | P2 | To Do | 2023-05-12 04:44 | huan xu
APIMCIM-22289 | Phase5_【U718】【必现】【个性化档案】连接档案页面，点击未连接的置灰paak，未提示paak未连接弹窗，且上报连接信号后入口仍置灰 | Yunteng Jiang | P2 | In Progress | 2023-05-12 04:09 | Xiaocheng Wang
FCIVIOS-15242 | Phase5_【U718】【黑盒】【必现】【CarPower】进出STR后，wifi开关没有保持打开状态 | chunming yang | P2 | To Do | 2023-05-12 03:52 | Cheng Qin
FCIVIOS-15241 | Phase5_【U718】【黑盒】【必现】【BSP】使用密码阶段，delay accessory信号监听不正确 | Chuanqin Chen | P2 | Tested | 2023-05-12 02:32 | Chuanqin Chen
FCIVIOS-15239 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】信号配置出自动远光模式，切换界面后 功能消失 | manyi guan | P2 | To Do | 2023-05-12 01:25 | zhewen lian
FCIVIOS-15237 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】防眩照明信号TX RX值错误 | manyi guan | P2 | To Do | 2023-05-11 23:15 | zhewen lian
FCIVIOS-15236 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】防眩照明点击收藏图标后，常用设置中无此功能 | manyi guan | P2 | To Do | 2023-05-11 23:07 | zhewen lian
FCIVIOS-15234 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】ign=off 驾驶模式界面置灰，切换tab界面再回来，驾驶模式界面变为高亮状态 | manyi guan | P2 | To Do | 2023-05-11 22:17 | chao Xu
APIMCIM-22279 | Phase5_【U718】【黑盒】【必现】【AAR】环境正常的情况下，进入AAR获取滤芯时，一直报错码-300 | Chuanqin Chen | P2 | To Do | 2023-05-11 05:58 | Jialin Zhu
APIMCIM-22247 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】搜索尾灯，点击后跳转至尾灯界面 | manyi guan | P2 | To Do | 2023-05-11 03:38 | Wang Qian
PSTT-563 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】模拟硬按键进入多功能座椅界面，向下滑动，界面出现重影 | chunming yang | P2 | Analysis | 2023-05-11 03:04 | Wang Qian
FCIVIOS-15226 | Phase5_【U718】【黑盒】【必现】【3D车模】发送等级无效信号，按摩按钮/按摩等级与车控状态显示不一致 | wendi Xiao | P2 | To Do | 2023-05-11 01:37 | Xingjian Li
FCIVIOS-15225 | Phase5_【U718】【黑盒】【必现】【3D车模】发送按摩等级为中，发送等级 信号=off，重启车机，进入3D车内，点击按摩按钮，tx信号记忆上次一次等级 | wendi Xiao | P2 | To Do | 2023-05-11 01:24 | Xingjian Li
FCIVIOS-15224 | Phase5_【U718】【黑盒】【必现】【3D车模】重启机器，进入3D车内，车模显示氛围灯效果 | wendi Xiao | P2 | To Do | 2023-05-11 01:16 | Xingjian Li
FCIVIOS-15220 | Phase5_【U718】【黑盒】【偶现】【Monkey】【BSP】com.ford.sync.vehiclecontrol.vehicle.ui.paak.fragment.PaaKBspFragment | Chuanqin Chen | P2 | Tested | 2023-05-10 23:06 | Chuanqin Chen
FCIVIOS-15219 | Phase5_【U718】【黑盒】【偶现】【Monkey】com.ford.sync.controllerlauncher内存超过620 | Chuanqin Chen | P2 | To Do | 2023-05-10 22:51 | Liang Xiao
PSTT-559 | Phase5_【U718】【monkey】【yfve.setting】monkey测试中yfve.setting出现crash | Yunteng Jiang | P2 | Analysis | 2023-05-10 22:39 | Wang Qian
FCIVIOS-15217 | CLONE - Phase5_【U718】【黑盒】【必现】【3D车模】进入3D车模副驾，点击更多按钮，发送氛围灯颜色，退出车控，3D车模显示氛围灯效果 | wendi Xiao | P2 | To Do | 2023-05-10 22:34 | Xingjian Li
FCIVIOS-15216 | Phase5_【U718】【黑盒】【必现】【3D车模】打开按摩按钮，选择按摩模式，按摩模式选中效果先由小变大 | wendi Xiao | P2 | To Do | 2023-05-10 22:15 | Xingjian Li
FCIVIOS-15215 | Phase5_【U718】【黑盒】【必现】【3D车模】切换主题，进入3D车模按摩，按摩等级进度条未适配主题 | wendi Xiao | P2 | To Do | 2023-05-10 22:08 | Xingjian Li
FCIVIOS-15214 | Phase5_【U718】【黑盒】【monkey】【Vehicle Setting】monkey过程中settings发生crash | manyi guan | P2 | To Do | 2023-05-10 22:01 | chao Xu
FCIVIOS-15212 | Phase5_【U718】【黑盒】【必现】【3D车模】模拟故障，发送熄火信号，3D车模旋转左前45度 | wendi Xiao | P2 | To Do | 2023-05-10 06:24 | Dongdong Nan
FCIVIOS-15211 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号打开后雾灯，发送信号选择位置灯，后雾灯置灰车模仍显示后雾灯效果 | wendi Xiao | P2 | To Do | 2023-05-10 06:18 | Dongdong Nan
FCIVIOS-15208 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】交通标志识别界面的超速警告 开关自动打开 | manyi guan | P2 | To Do | 2023-05-10 03:10 | chao Xu
APIMCIM-22114 | Phase5_【U718】【必现】【个性化档案】keyfob无法关联 | Yunteng Jiang | P2 | In Progress | 2023-05-10 02:38 | Xiaocheng Wang
FCIVIOS-15204 | Phase5_【U718】【黑盒】【必现】【3D车模】发送信号打开远光灯，车模可以点亮logo和中网贯穿灯 | wendi Xiao | P2 | To Do | 2023-05-10 02:29 | Dongdong Nan
APIMCIM-22109 | Phase5_【U718】【必现】【个性化档案】paak相关信号上报无效 | Yunteng Jiang | P2 | In Progress | 2023-05-10 02:26 | Xiaocheng Wang
APIMCIM-22106 | Phase5_【U718】【必现】【个性化档案】上报26b PaakCnnct_D_Stat 1，点击智能手机钥匙入口仍弹出未连接弹窗 | Yunteng Jiang | P2 | In Progress | 2023-05-10 02:14 | Xiaocheng Wang
APIMCIM-22104 | Phase5_【U718】【必现】【个性化档案】重置修改上报成功信号无效 | Yunteng Jiang | P2 | In Progress | 2023-05-10 02:08 | Xiaocheng Wang
APIMCIM-22103 | Phase5_【U718】【必现】【个性化档案】连接档案页面未勾选且未关联钥匙，下一步按钮仍可点击 | Yunteng Jiang | P2 | In Progress | 2023-05-10 02:02 | Xiaocheng Wang
APIMCIM-22098 | Phase5_【CDX707】【必现】【个性化档案】EnhancedMemoryApplication code security audit | Yunteng Jiang | P2 | Test | 2023-05-10 01:36 | Xiao Lei Zhang
FCIVIOS-15200 | Phase5_【U718】【黑盒】【必现】【3D车模】进入+1屏，点击车控再次点击home键，3D车模会消失一下 | wendi Xiao | P2 | To Do | 2023-05-10 01:28 | Xingjian Li
FCIVIOS-15199 | Phase5_【U718】【黑盒】【必现】【3D车模】进入车内，点击通知栏灯光按钮，灯光弹窗与车内界面重叠 | wendi Xiao | P2 | To Do | 2023-05-10 01:21 | Xingjian Li
FCIVIOS-15198 | Phase5_【U718】【黑盒】【必现】【3D车模】未配置后备箱，发送后备箱信号，后备箱按钮高亮显示 | wendi Xiao | P2 | To Do | 2023-05-09 23:14 | Xingjian Li
FCIVIOS-15196 | Phase5_【U718】【黑盒】【必现】【3D车模】进入车外修改车模颜色为第三个，重启机器，车模颜色会改变 | wendi Xiao | P2 | In Progress | 2023-05-09 22:27 | Xingjian Li
APIMCIM-22067 | Phase5_【U718】【必现】【个性化档案】非当前档案无法删除 | Yunteng Jiang | P2 | In Progress | 2023-05-09 07:05 | Xiaocheng Wang
APIMCIM-22062 | 【Phase5】【U718】【V2I】【黑盒】【必现】默认设置页面-允许车路协同通知为开 | tianqi zhou | P2 | To Do | 2023-05-09 04:23 | Yuan Yan Zhang
FCIVIOS-15194 | 【Phase5】【U718】【V2I】【黑盒】【必现】车路协同界面显示子菜单名称与UE不一致，“取消申请”的按钮未删除 | tianqi zhou | P2 | To Do | 2023-05-09 04:14 | Liang Xiao
FCIVIOS-15193 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】倒挡来车预警影像在常用设置和驾驶辅助界面状态不一致 | manyi guan | P2 | To Do | 2023-05-09 03:55 | chao Xu
FCIVIOS-15192 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】车速限制辅助 容限单位改变时，入口处值未同步 | manyi guan | P2 | To Do | 2023-05-09 03:10 | chao Xu
APIMCIM-22034 | Phase5_【U718】【黑盒】【必现】【STR】车载热点开关打开状态，进入STR模式，再退出STR模式，车载热点开关需要等待1m30s左右才会恢复打开状态 | chunming yang | P2 | To Do | 2023-05-08 23:28 | Jia Xian Li
APIMCIM-22030 | Phase5_【U718】【monkey】monkey测试com.ford.sync.enhancedmemory出现anr | Yunteng Jiang | P2 | In Progress | 2023-05-08 22:23 | Xiaocheng Wang
APIMCIM-22029 | Phase5_【U718】【monkey】monkey测试com.ford.sync.enhancedmemory出现crash | Yunteng Jiang | P2 | In Progress | 2023-05-08 22:21 | Xiaocheng Wang
APIMCIM-22031 | 【Phase5】【U718】【Monkey】CRASH: com.yfve.settings | tianqi zhou | P2 | To Do | 2023-05-08 22:19 | Zhicheng Liu
FCIVIOS-15182 | Phase5_【U718】【黑盒】【必现】【THEME】切换主题为第三种主题，点击车控，tab的>未适配主题 | wendi Xiao | P2 | To Do | 2023-05-08 07:13 | chao Xu
APIMCIM-22022 | Phase5_【U718】【必现】【个性化档案】进入STR前有一个用户档案1，进入str退出后，档案1消失 | Yunteng Jiang | P2 | In Progress | 2023-05-08 04:53 | Xiaocheng Wang
PSTT-558 | Phase5_【U718】【必现】【林肯香氛】进入STR前香氛是打开状态，退出后香氛关闭 | Yunteng Jiang | P2 | Analysis | 2023-05-08 04:48 | Wang Qian
APIMCIM-22004 | Phase5_【U718】【必现】【个性化档案】光速探境主题未与档案适配 | Yunteng Jiang | P2 | In Progress | 2023-05-08 02:49 | Xiaocheng Wang
PSTT-544 | Phase5_【U718】【黑盒】【必现】【Account】账号登录成功和网络不佳等情况时，toast不符合UI设计 | Chuanqin Chen | P2 | Analysis | 2023-05-06 03:46 | Li Sun
FCIVIOS-15152 | Phase5_【U718】【黑盒】【必现】【BSP】五分钟锁定提示内容，与UI图的描述不一致，请更新 | Chuanqin Chen | P2 | Tested | 2023-05-05 06:49 | Chuanqin Chen
APIMCIM-21595 | Phase5_【U718】【必现】【个性化档案】首页保存还原与浮窗保存还原点击后显示不一致 | Yunteng Jiang | P2 | To Do | 2023-04-25 09:35 | Hui Zhang
FCIVIOS-14992 | Phase5_【U718】【黑盒】【必现】【PAAK】重置智能备用密钥-新密码保存失败，启动密码和车门解锁密码可能已删除请联系经销商，弹窗无法构造 | Chuanqin Chen | P2 | To Do | 2023-04-23 03:10 | jianing gu
PSTT-555 | Phase5_【U718】【黑盒】【偶现】【Monkey】monkey 测试中 com.yfve.settings发生anr(ANR in com.yfve.settings (com.yfve.settings/.activitys.SettingsActivity)) | Chuanqin Chen | P2 | Analysis | 2023-04-20 00:13 | Wang Qian
FCIVIOS-14896 | Phase5_【U718】【黑盒】【必现】【拖车】通知=打开&激活默认拖车，选择弹窗“查看设置”和“添加拖车”，跳转界面异常，无激活拖车时“选择拖车”也有异常 | Chuanqin Chen | P2 | Tested | 2023-04-19 02:35 | Chuanqin Chen
APIMCIM-21211 | Phase5_【U718】【Monkey】【Account】Monkey测试，com.ford.sync.account (com.ford.sync.account/.activity.LoginActivity)出现ANR | chunming yang | P2 | To Do | 2023-04-17 22:19 | chunming yang
PSTT-493 | Phase5_【U718】【黑盒】【偶现】【Monkey】com.yfve.settings内存超标 | Chuanqin Chen | P2 | New | 2023-04-16 23:50 | Wang Qian
PSTT-475 | Phase5_【U718】【黑盒】【必现】【AAR】“自动开启空调状态栏通知”弹窗上的“切换”和“取消”按扭，点击不灵敏，要点击两次，用户体验差 | Chuanqin Chen | P2 | Analysis | 2023-04-08 07:16 | Wenxiong Cai
APIMCIM-20748 | Phase5_【U718】【黑盒】【偶现】【Account】登录帐号过程中，二维码会自动刷新，无法登录成功 | Chuanqin Chen | P2 | To Do | 2023-04-08 05:50 | Chuanqin Chen
FCIVIOS-14727 | Phase5_【U718】【黑盒】【必现】【V2I】点击车路协同续订弹窗文字无反应 | wendi Xiao | P2 | Reopened | 2023-04-07 05:58 | Liang Xiao
FCIVIOS-14709 | Phase5_【U718】【黑盒】【偶现】【Monkey】【拖车】monkey 测试中com.ford.sync.trailersettings出现crash（Long Msg: java.lang.NullPointerException: Attempt to invoke virtual method） | Chuanqin Chen | P2 | Reopened | 2023-04-06 01:20 | Liang Xiao
FCIVIOS-14704 | Phase5_【U718】【必现】【HVAC】语音调节后排风量，TTS反馈“前排风量已调到**” | Yunteng Jiang | P2 | To Do | 2023-04-04 07:05 | huan xu
FCIVIOS-14703 | Phase5_【U718】【必现】【HVAC】语音调节后排温度，TTS反馈错误 | Yunteng Jiang | P2 | To Do | 2023-04-04 06:58 | huan xu
FCIVIOS-14689 | Phase5_【U718】【必现】【林肯香氛】香氛未知状态下强度未变为关 | Yunteng Jiang | P2 | Reopened | 2023-04-04 03:11 | Liang Xiao
FCIVIOS-14677 | Phase5_【U718】【黑盒】【必现】【3D车模】打开氛围灯 ，设置亮度为50%，3D车模显示亮度与车控显示不一致 | wendi Xiao | P2 | To Do | 2023-04-03 23:14 | Xingjian Li
APIMCIM-20486 | Phase5_【U718】【偶现】【MMOTA】未设定更新计划-VI升级激活阶段，IG=OFF后偶现同时弹系统日程未设定消息和倒计时弹窗，并可点击系统日程未设定消息 | zhangjian zhou | P2 | Test | 2023-04-03 07:46 | zhangjian zhou
FCIVIOS-14663 | Phase5_【U718】【黑盒】【偶现】【3D车模】模拟故障进入车外快捷，双击故障，退出vha,车外显示空白 | wendi Xiao | P2 | To Do | 2023-04-03 05:25 | Xingjian Li
FCIVIOS-14649 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】配置交通标识识别功能，IVI界面不显示该功能 | manyi guan | P2 | To Do | 2023-04-03 01:29 | chao Xu
APIMCIM-20418 | Phase5_【U718】【黑盒】【Monkey】【Vehicle Setting】Settings内存泄漏 | manyi guan | P2 | In Progress | 2023-04-02 22:28 | Wang Qian
FCIVIOS-14635 | Phase5_【U718】【黑盒】【必现】【3D车模】模拟照明系统故障，发送远近灯光位置灯，车模会旋转角度 | wendi Xiao | P2 | To Do | 2023-03-31 04:49 | Dongdong Nan
FCIVIOS-14630 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】交通标志识别中的超速警告 切换界面后 开关自动打开 | manyi guan | P2 | To Do | 2023-03-31 03:00 | chao Xu
FCIVIOS-14469 | Phase5_【U718】【黑盒】【偶现】【Monkey】【settings】monkey 测试中com.yfve.settings 内存异常 | wendi Xiao | P2 | Tested | 2023-03-22 22:28 | wendi Xiao
APIMCIM-19831 | Phase5_【U718】【黑盒】【Car Power】【必现】进入STR模式预期1分半左右，实际3分钟以上 | Chuanqin Chen | P2 | To Do | 2023-03-22 01:48 | Wang Qian
APIMCIM-19830 | Phase5_【U718】【黑盒】【偶现】【Monkey】【settings】monkey 测试中com.yfve.settings发生crash（java.lang.IndexOutOfBoundsException) | Chuanqin Chen | P2 | Test | 2023-03-16 22:29 | Zihao Qiu
APIMCIM-19326 | Phase5_【U718】【黑盒】【单机必现】【System】正常连接后，控制屏黑屏无法使用，使用投屏软件在电脑上投屏时，报错 | Chuanqin Chen | P2 | To Do | 2023-03-14 01:24 | Yang Hou
FCIVIOS-14322 | Phase5_【U718】【黑盒】【偶现】【STR】车载热点开关打开状态，进入STR模式，再退出STR模式，车载热点开关却是关闭状态 | zhaomin huang | P2 | Tested | 2023-03-06 06:14 | chunming yang
APIMCIM-19242 | Phase5_【U718】【黑盒】【必现】【AAR】台架无法获取滤芯状态，一直报网络异常请稍后重试 | Chuanqin Chen | P2 | To Do | 2023-03-02 06:40 | xiaoyan wan
FCIVIOS-14256 | Phase5_【U718】【黑盒】【必现】【3D车模】配置氛围灯DE01=varient 2，发送信号亮度无效信号，点击空白区域再次点击氛围灯按钮，车模显示动效 | wendi Xiao | P2 | To Do | 2023-03-02 01:04 | Xingjian Li
APIMCIM-18850 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】当前未配置灯光设置功能，依旧可以搜索出灯光功能 | manyi guan | P2 | In Progress | 2023-03-01 21:59 | Wang Qian
APIMCIM-18691 | Phase5_【U718】【黑盒】【Monkey】【setting】com.yfve.settings内存泄漏 | Chuanqin Chen | P2 | Test | 2023-02-28 21:52 | Zihao Qiu
FCIVIOS-14214 | Phase5_【U718】【黑盒】【偶现】【Monkey】【vha】com.ford.sync.vha有anr（ANR in com.ford.sync.vha (com.ford.sync.vha/.vhacontrol.ui.VhaActivity)） | Chuanqin Chen | P2 | Reopened | 2023-02-28 21:42 | Liang Xiao
APIMCIM-18411 | Phase5_【U718】【黑盒】【偶现】【1/20】【Account】登录账号的实际个数与账号管理中个数不一致 | Chuanqin Chen | P2 | In Progress | 2023-02-24 00:09 | Niu Tian
APIMCIM-18405 | Phase5_【U718】【黑盒】【必现】【Account】账号登录失效，无法出现弹窗：“账号登录，你的账号登录失效，请重新登录” | Chuanqin Chen | P2 | Test | 2023-02-23 21:29 | Chuanqin Chen
APIMCIM-18353 | Phase5_【U718】【偶现】【MMOTA】VI升级下载阶段切换5G-WIFI-5G无法恢复下载 | zhangjian zhou | P2 | To Do | 2023-02-22 07:58 | zhangjian zhou
APIMCIM-18289 | Phase5_【U718】【黑盒】【偶现】【音源矩阵】【24ch】通话中点击播放蓝牙音乐，挂断电话后蓝牙音乐未进行播放 | tianqi zhou | P2 | To Do | 2023-02-21 08:10 | Wang Qian
APIMCIM-18617 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】点击切换驾驶模式 切换主题后，自动跳转至灯光设置界面 | manyi guan | P2 | Test | 2023-02-21 05:46 | Zihao Qiu
FCIVIOS-14053 | Phase5_【U718】【黑盒】【必现】【3D车模】进入3D车模音效点击更多按钮，音效设备背景图与系统设置显示不一致 | wendi Xiao | P2 | Reopened | 2023-02-21 01:09 | Liang Xiao
APIMCIM-18261 | Phase5_【U718】【黑盒】【偶现】【WiFi】林肯之道互联复位-全部复位后，点击wifi开关，wifi开关置灰（后续在原生设置中可以打开） | chunming yang | P2 | To Do | 2023-02-21 00:12 | Guanghui Liu
FCIVIOS-14046 | Phase5_【U718】【黑盒】【必现】【3D车模】修改车模颜色 ，U盘升级，车模颜色未记忆 | wendi Xiao | P2 | Reopened | 2023-02-20 20:48 | Xingjian Li
APIMCIM-19558 | Phase5_【U718】【黑盒】【偶现】【Vehicle Setting】monkey过程中com.yfve.settings发生crash（java.lang.IllegalStateException） | zhaomin huang | P2 | Awaiting implementation | 2023-02-20 05:54 | Zeming Mao
APIMCIM-18212 | Phase5_【U718】【黑盒】【必现】【Monkey】com.yfve.settings内存泄露 | Chuanqin Chen | P2 | Reopened | 2023-02-20 00:05 | Zhicheng Liu
APIMCIM-18444 | Phase5_【U718】【黑盒】【必现】【CarAudio】【24ch】百度地图导航时点按power键，导航声音会暂停 | tianqi zhou | P2 | To Do | 2023-02-18 05:26 | Yankun Zhao
APIMCIM-18109 | Phase5_【U718】【黑盒】【必现】【Monkey】【蓝牙电话】com.yfve.settings有crash（java.lang.RuntimeException: Unable to start activity ComponentInfo{com.yfve.settings/com.yfve.settings.activitys.InputActivity） | Chuanqin Chen | P2 | To Do | 2023-02-16 21:27 | Zhicheng Liu
APIMCIM-17520 | Phase5_【U718】【黑盒】【必现】【林肯香氛】模拟香氛过期，香氛界面会调起语音弹窗 | wendi Xiao | P2 | To Do | 2023-01-14 06:15 | Niu Tian
APIMCIM-16722 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】搜索当前未配置的功能，可以搜索出来结果 | manyi guan | P2 | In Progress | 2023-01-10 02:09 | Zhicheng Liu
APIMCIM-16468 | Phase5_【U718】【黑盒】【必现】【Vehicle Setting】模拟发送驾驶模式异常状态弹窗信号时，界面跳转至上一次界面 再跳转回驾驶模式界面 | manyi guan | P2 | Test | 2023-01-09 00:43 | Zihao Qiu
APIMCIM-16934 | Phase5_【U718】【黑盒】【偶现】【音源矩阵】【24ch】播放蓝牙音乐时熄屏，再次亮屏后，蓝牙音乐未自动恢复播放 | tianqi zhou | P2 | Approval | 2023-01-07 05:29 | tianqi zhou
APIMCIM-17512 | Phase5_【U718】【黑盒】【偶现】【Audio】【24ch】蓝牙电话选择外置铃声，接听来电时喇叭无铃声输出 | tianqi zhou | P2 | To Do | 2023-01-07 03:35 | Yankun Zhao
APIMCIM-16274 | Phase5_【U718】【黑盒】【必现】【Theme】驾驶模式切换到低速爬坡，预期主题切换到山湖无界，实际无切换动作 | Chuanqin Chen | P2 | To Do | 2023-01-05 07:01 | Lin Yuan
APIMCIM-16417 | Phase5_【U718】【黑盒】【必现】【Audio】【24ch】电话通话中，前排喇叭无声音输出 | tianqi zhou | P2 | To Do | 2023-01-05 03:45 | Fisher Liu
APIMCIM-16047 | Phase5_【U718】【黑盒】【偶现】【V2I】多次退出使用计划，再次进入车路协同界面，偶现界面显示空白 | wendi Xiao | P2 | Awaiting implementation | 2022-12-30 06:13 | wendi Xiao
APIMCIM-15987 | Phase5_【U718】【黑盒】【必现】【Car-audio】音量设置中通话，语音，提示音不生效 | tianqi zhou | P2 | To Do | 2022-11-14 01:16 | Fisher Liu
FCIVIOS-11169 | Phase5_【U718】【黑盒】【必现】【拖车】所有infobook文案未提供，当前只有图标无法点击查看 | Chuanqin Chen | P2 | To Do | 2022-11-04 22:54 | qi yu
APIMCIM-15867 | Phase5_【U718】【黑盒】【偶现】【Car_Audio】切换音源，蓝牙音乐偶现暂停不播放 | tianqi zhou | P2 | To Do | 2022-11-02 03:54 | Huanxin Fu
APIMCIM-15868 | Phase5_【U718】【黑盒】【偶现】【Car_Audio】QQ音乐偶现不播放 | tianqi zhou | P2 | Monitor | 2022-11-02 03:38 | tianqi zhou
APIMCIM-17573 | Phase5_【U718】【黑盒】【必现】【 Vehicle Settings】播放vr时，tts播报打断当前播放vr | Yunteng Jiang | P2 | Reopened | 2022-09-19 06:31 | Niu Tian
FCIVIOS-15309 | Phase5_【CDX707】【monkey】【yfve.setting】com.yfve.setting出现anr | Yunteng Jiang | P3 | To Do | 2023-05-17 01:12 | chao Xu
FCIVIOS-15272 | Phase5_【U718】【monkey】【yfve.setting】com.yfve.setting出现crash | Yunteng Jiang | P3 | To Do | 2023-05-15 22:02 | Yunteng Jiang
FCIVIOS-15261 | Phase5_【U718】【黑盒】【必现】【AAR】历史记录界面，横坐标的时间显示与系统时间显示不统一，两者时间不一致 | Chuanqin Chen | P3 | To Do | 2023-05-15 02:54 | huan xu
FCIVIOS-15260 | Phase5_【U718】【黑盒】【偶现】【AAR】历史记录界面，偶现横轴的时间点有重叠显示 | Chuanqin Chen | P3 | To Do | 2023-05-15 02:48 | huan xu
FCIVIOS-15252 | Phase5_【U718】【必现】【HVAC】语音后排风量调到8/0，TTS反馈“前排空调风量已调到最大/最小” | Yunteng Jiang | P3 | To Do | 2023-05-13 08:06 | huan xu
FCIVIOS-15251 | Phase5_【U718】【必现】【HVAC】语音“后排风量调到x档”，TTS反馈“前排空调风量已调到x” | Yunteng Jiang | P3 | To Do | 2023-05-13 08:04 | huan xu
FCIVIOS-15250 | Phase5_【U718】【必现】【HVAC】语音“后排风量减小/增大x档”，TTS反馈“空调风量已减小/增大x档” | Yunteng Jiang | P3 | To Do | 2023-05-13 08:00 | huan xu
FCIVIOS-15248 | Phase5_【U718】【必现】【HVAC】当前温度最高/最低，语音增大/降低温度，有信号下发 | Yunteng Jiang | P3 | To Do | 2023-05-13 07:39 | huan xu
FCIVIOS-15247 | Phase5_【U718】【必现】【HVAC】语音降低温度，TTS反馈“空调温度已调低两度” | Yunteng Jiang | P3 | To Do | 2023-05-13 07:35 | huan xu
FCIVIOS-15244 | Phase5_【U718】【黑盒】【必现】【拖车】拖车名称长度较长时，已激活的toast有截断 | Chuanqin Chen | P3 | Tested | 2023-05-12 05:50 | Chuanqin Chen
APIMCIM-22288 | Phase5_【U718】【必现】【个性化档案】创建新的档案，档案头像页面未显示默认头像 | Yunteng Jiang | P3 | In Progress | 2023-05-12 04:05 | Xiaocheng Wang
FCIVIOS-15238 | Phase5_【U718】【黑盒】【必现】【BSP】“密码正确，车辆已成功解锁，请在20秒之内启动车辆”，提示语多了一个字 | Chuanqin Chen | P3 | Tested | 2023-05-12 01:14 | Chuanqin Chen
FCIVIOS-15222 | Phase5_【U718】【黑盒】【必现】【BSP】创建智能备用密钥，进入到创建车门解锁密码时，第二个密码输入框提示内容显示不正确 | Chuanqin Chen | P3 | Tested | 2023-05-10 23:25 | Chuanqin Chen
PSTT-480 | Phase5_【U718】【黑盒】【必现】【Vehicle Settings】连接蓝牙儿童座椅时，唤醒语音，当弹出未锁定消息横幅时语音被打断 | zhaomin huang | P3 | Analysis | 2023-04-10 06:16 | Wenxiong Cai
FCIVIOS-14742 | Phase5_【U718】【黑盒】【必现】【拖车】通知=打开&激活拖车点火时提示拖车重量开关打开，选择弹窗“查看设置”，点击更改重量时跳转有抖动 | Chuanqin Chen | P3 | Reopened | 2023-04-09 23:10 | Liang Xiao
FCIVIOS-14582 | Phase5_【U718】【Monkey】【HVAC】HVAC出现crash | Yunteng Jiang | P3 | Tested | 2023-03-26 22:27 | Yunteng Jiang
FCIVIOS-14058 | Phase5_【U718】【黑盒】【必现】【Vehicle Settings】播放蓝牙音乐，连接儿童座椅TTS播报时，蓝牙音乐音量没有降低 | zhaomin huang | P3 | To Do | 2023-02-21 02:31 | yongheng yang
APIMCIM-13692 | Phase5_【U611】【黑盒】【必现】【AAR】滤芯状态获取失败，网络异常 | Yunteng Jiang | P3 | To Do | 2022-11-04 04:11 | Stella Shi
APIMCIM-14129 | Phase5_【U718】【黑盒】【必现】【Rear Audio】处于电话/语音唤起，后屏不会全屏显示文字提示 | wendi Xiao | P3 | In Progress | 2022-10-31 06:41 | Bin Meng
APIMCIM-13339 | Phase5_【U718】【黑盒】【必现】【AAR】滤芯状态获取失败，网络异常 | Yunteng Jiang | P3 | To Do | 2022-10-31 06:11 | Stella Shi