## BOF
| Global Feature Dictionary Name | Domain | Feature Initiator | Manager | DVP RequirementID | 1st round DV test status | Hil | BB | Issue | APIMCIM Jira Number | Jira Status | FDL | Fix Date | Next step | Comment from Jiajia/Deyin | Risk Level
PMT4 | Start / Stop (12v Internal Combustion) |  | Li, Yanzhi | Fang, Kevin (Zh.J.) | RQT-003100-019588 | 2022-07-05 | [6 empty] | 2022-07-05 | Leave one ACC related test case |  | Target to close before PEC | Close before PEC with car
PMT2 | Convenience Lighting |  | Wu, Xiaoxiao | Xu, Tom (Wei) | RQT-000600-717164 | Pass |  | Y | [7 empty] | Complete
PMT2 | Overhead Lighting |  | Wu, Xiaoxiao | Xu, Tom (Wei) | RQT-000600-719074 | Pass |  | Y | [7 empty] | Complete
PMT2 | Ambient Lighting | IVI | Sun, Qiming (Q.) | Xu, Tom (Wei) | RQT-000600-714651 | Done |  | Y | GIM-40691 GIM-40106 | GIM-40691 -> APIMCIM-7655 GIM-40106 -> APIMCIM-5607 | DONE APPROVAL | YFVE Inhouse | 18-Jul 18-Jul | IVI R04 fix 7/18, fixed with daily SW IVI R04 fix 7/18 |  | First pass with re-DV before FEC.
PMT4 | Automatic Engine Idle Shutdown (AEIS) | IVI | Zhang, Jian (Ben.) | Fang, Kevin (Zh.J.) | RQT-031400-714303 | Done |  |  | GIM-40856 |  |  |  | 2022-07-18 | Cluster R04 SW release on 7/18 |  | First pass with re-DV before FEC.
PMT4 | Vehicle Start |  | Zhang, Jian (Ben.) | Fang, Kevin (Zh.J.) |  | 2022-07-08 | [6 empty] | 2022-06-30 | Borrowed LV613 from VEV to test from 30-Jun -Done |  | Target to close before PEC | Close before PEC with car
PMT4 | Range Selection | Cluster | Gao, Jiliang (J.) | Fang, Kevin (Zh.J.) | RQT-000600-718503 | Done | Y | [8 empty] | Complete | Close before PEC with car
DAT | Clear Exit Assist | IVI | Liu, Hongxin (H.) | Wu, Barclay (Kai) | RQT-003600-708663 | Done | Y |  | GIM-40712 |  |  |  | 2022-06-20 | IVI R00 fix | IPC issue | Function test completed and pass, bug on-going fix, no impact on sign off.
PMT1 | Front Window Wiper/Washer |  | Wu, Bob | Wang, Koby (Y.W) | RQT-011600-019785 | Pass |  | Y | [7 empty] | Complete
PMT1 | Front Automatic Wiping |  | Wu, Bob | Wang, Koby (Y.W) | RQT-011600-019785 | Pass |  | Y | [7 empty] | Complete
PMT1 | Rear Window Wiper/Washer |  | Wu, Bob | Wang, Koby (Y.W) | RQT-011600-019785 | Pass |  | Y | [7 empty] | Complete
DAT | Cross Traffic Alert (CTA) with Braking (RCTB) | IVI | Liu, Hongxin (H.) | Wu, Barclay (Kai) | RTQ-190400-016283 | Done | Y |  | GIM-40723 GIM-40724 | GIM-40723 -> APIMCIM-7212 GIM-40724 -> APIMCIM-7216 | APPROVAL APPROVAL | YFVE Inhouse | 18-Jul 18-Jul | IVI R04 fix IVI R04 fix |  | Function test completed and pass, bug on-going fix, no impact on sign off. | Re-DV, deep dive.
Platform | Auto Vehicle Hold (AVH) |  | Baermann, Natalie (N.) | Bongarth, Wolfgang (W.P.) |  | 2022-07-14 | [6 empty] | 2022-07-07 |  |  | Target to close before PEC
Platform | Lane Keeping System (LKS) |  | Benak, Attila (A.B.) | Bongarth, Wolfgang (W.P.) |  | 2022-07-10 |  |  | GIM-41479 |  |  |  |  | Record can log on 6/30 morning - Done Reconnect on 6/30 afternoon |  | Target to close before PEC
DAT | Tire Pressure Monitoring System (TPMS) | IVI | Wang, Vincent (X.) | Wu, Barclay (Kai) | https://ford.webex.com/ford/j.php?MTID=m5d89580139b5eba50ebc9de35d3cf176 | Pass | [9 empty] | Complete
PMT1 | Heated Backlight | IVI | Shi, Song | Wang, Koby (Y.W) | RQT-011105-012074 RQT-011105-012064 RQT-011105-012082 | Pass | Y | [8 empty] | Complete
PMT2 | Heated Steering Wheel (HSW) | IVI | Sophie Yan |  | RQT-000600-716563(PMT) RQT-110601-714424（VEV） | Pass |  | Y | [7 empty] | Complete
EC | Outside Air Temperature (OAT) | Cluster | Xie, Will (W.) | Luo, Li (.) | RQT-120400-008414 | Pass | [9 empty] | Complete
PMT1 | Power Moonroof and Shade | IVI | Hu, Peter (P.H) | Yuan, Gloria (XQin) | RQT-011703-714965 | Pass |  | Y | [7 empty] | Complete
Platform | Evasive Steer Assist (ESA) |  | Wulff, Patrick (P.) | Bongarth, Wolfgang (W.P.) |  | Pass | [9 empty] | Complete
EE | Global Windows Open/Close (GWOC) | IVI | Xiang, Cici | Zhou, Silver (X.B.) | RQT-191000-013899 （EF-0166） | Done |  | Y | GIM-41283 |  |  |  | 2022-08-02 | DCU fix 1) No Anti-pinch 2)Function lost after several times before 2-Aug |  | First pass with re-DV before FEC.
PMT1 | Electrochromatic Automatic Day/Night Mirrors |  | Zhao, Emma | Wang, Koby (Y.W) | RQT-010901-013393 RQT-180100-009409 | Pass |  | Y | [7 empty] | Complete
PMT1 | Power Adjustable Mirrors |  | Zhao, Emma | Wang, Koby (Y.W) | RQT-010902-022279 | Pass |  | Y | [7 empty] | Complete
PMT1 | Power Folding Mirrors / Autofold |  | Zhao, Emma | Wang, Koby (Y.W) | RQT-010902-022279 | Pass |  | Y | [7 empty] | Complete
EE | Reverse Dip Exterior Mirrors |  | Chen, Vivi | Zhou, Silver (X.B.) | RQT-010902-022279 | Pass | Y | [8 empty] | Complete
EE | Daytime Running Light (DRL) | IVI | Chen, Julian | Zhou, Silver (X.B.) | RQT-170100-704122 | Pass | [9 empty] | Complete
PMT1 | Power Open/Close Liftgate | IVI | Hu, Peter (P.H) | Yuan, Gloria (XQin) | hbc | 2022-07-08 | [6 empty] | 2022-07-08 | Pending RGTM calibration complete on 7/8 |  | Target to close before PEC
EE | Enhanced Memory | IVI | Li, Ning | Zhou, Silver (X.B.) | RQT-000600-706383 | 18-Jul TBD |  | Y | DSM5 PAAK |  |  |  | 11-Jul TBD | DSM5 SW release - 7/11 PAAK Vehicle set up – X PAAK function verification – X + 5 Walk Away Lock verification – X + 6 |  | Potential PEC Un-contain
EE | Perimeter Anti-Theft Alarm | Cluster | Zhang, Zengguang | Zhou, Silver (X.B.) | RQT-190100-017601 ARMING THE ALARM RQT-190100-017602 DISARMING THE ALARM RQT-190100-017605 FLASHER OUTPUT RQT-190100-017607 ALARM STATE STORAGE RQT-190100-017614 ALARM ACTIVATION RQT-190100-017615 ALARM RQT-190100-017616 BATTERY DISCONNECTION RQT-190100-017621 TRUNK/LIFTGATE/ENGINE HOOD ALARM SWITCH | Pass | Y | [8 empty] | Complete
EE | Power Child Locking Doors (PCL) |  | Zhao, Jacky | Zhou, Silver (X.B.) | RQT-011411-013585 POWER CHILD LOCK | 2022-07-08 | Y |  | GIM-40432 |  |  |  | 2022-07-05 | DCU SW update on 6/30 7/5 |  | Target to close before PEC
EE | Digital Scent for China version | IVI | Liu, Peng | Zhou, Silver (X.B.) | RQT-000600-717523 | Done |  | Y | GIM-37504 GIM-39997 GIM-39999 | GIM-37504 -> APIMCIM-5500 GIM-39997 -> APIMCIM-5609 GIM-39999 -> APIMCIM-5552 | APPROVAL Test APPROVAL | YFVE Inhouse Inhouse | 18-Jul 17-Aug 18-Jul | IVI R04 IVI R05 IVI R04 | GIM-39997 is still under the DCR process（Target to fix this issue in R05） | Function test completed and pass, bug on-going fix, no impact on sign off.
DAT | Active Park Assist (APA) - Gen 8 | IVI | He, Michael (X.) | Wu, Barclay (Kai) | RQT-003601-722743 RQT-003601-722762 | 23-Jun 16-Jul | [9 empty] | Target to close before PEC
DAT | Driver Alert System (DAS) | IVI | Song, Amy (S.) | Wu, Barclay (Kai) | RQT-190402-019875 RQT-190402-019421 | 10-Jun 7-Jul | Y | [5 empty] | 2022-06-23 | IPC SW release on 6/23 - Done |  | Target to close before PEC
EE | Electro Mechanical Register | IVI | Wang, Wei (W.) | Zhou, Silver (X.B.) | RQT-000600-715744 | Done |  | Y | GIM-40530 GIM-40591 | GIM-40530 -> APIMCIM-6996 GIM-40591 -> APIMCIM-6993 | TODO APPROVAL | Ford-RCCM Inhouse | 18-Jul | IVI R04 fix | GIM-40530 is RCCM issue, please change the component to RCCM | First pass with re-DV before FEC.
EE | Passive Entry | Cluster | Duan, Zhengju (Z.) | Zhou, Silver (X.B.) | RQT-191200-014897 RQT-191200-014903 RQT-191200-014899 RQT-191200-014900 RQT-191200-014901 RQT-191200-014902 RQT-191200-014898 | Done | Y |  | IVI issue |  |  |  | 2022-08-07 | IVI R05 fix on 8/7 |  | First pass with re-DV before FEC.
PMT1 | Fuel Filler Lock (FFL) |  | Han, Amy (Y.) | Wang, Koby (Y.W) |  | Pass | Y | [8 empty] | Complete
DAT | Blind Spot Information System (BLIS) | IVI | Liu, Hongxin (H.) | Wu, Barclay (Kai) | RTQ-190400-016282 | Pass | Y | [8 empty] | Complete
DAT | Global Beltminder | IVI | Xu, Xi Hai (X.) | Wu, Barclay (Kai) | RQT-012006-016465 | Pass | Y |  | GIM-39965 GIM-39959 GIM-39993 GIM-39994 |  |  |  | 18-Jul 20-Jun 20-Jun 20-Jun | IVI R04 fix Cluster SW fix Fix on vehicle, pending clarification with tester Fix on vehicle, pending clarification with tester | GIM-39965 is IPC issue, please change the component to IPC. | Function test completed and pass, bug on-going fix, no impact on sign off.
DAT | SOS Post-Crash Alert |  | Xu, Xi Hai (X.) | Wu, Barclay (Kai) | RQT-012006-016486 | Pass |  | Y | [7 empty] | Complete
EC | Speedometer | Cluster | Cao, Helen (H.) | Wu WenZhong, Forrest (W.) | RQT-130000-012717 | Pass | Y | [8 empty] | Complete
DAT | Lane Centering Assist (LCA) | IVI | Ni, Anthony (H.A.) | Wu, Barclay (Kai) | RQT-190300-020345 | 2022-07-29 | Y |  | ACC |  |  |  | 2022-07-05 | ACC test completion – 7/5 ADA function debug / SW verification – 7/8 ECG SW update for ADA -7/8 LCA/ADA test completion – 7/29 |  | Potential PEC Un-contain
EE | Lincoln Embrace / Ford Welcome Farewell | IVI | Chen, Huizhen | Zhou, Silver (X.B.) | RQT-000600-022315 | Done without sound 7/19/2022 | Y | Y | GIM-37450 GIM-40598 | GIM-40598 -> APIMCIM-2183 | IN PROGRESS | YFVE | 3-Aug 17-Aug | Animation release on 7/1(Done), IVI R05 fix IVI R05 fix on 8/17 7/13 IVI release function of adding sound | GIM-37450 is pending on HMI input. Program is leading this issue. No release commitment from IVI | First pass without sound. Late change with sound target to close before 7/19. | First DV without done. Re-DV without sound on 17-Aug. First DV with sound by 19-Jul. Deep dive.
EC | Heated Mirrors | IVI | Xie, Will (W.) | Luo, Li (.) | RQT-000600-716584 | Pass | [9 empty] | Complete
DAT | Pre-Collision Assist (PCA) | IVI | Zhu, Jinpeng (J.) | Wu, Barclay (Kai) | RQT-190300-023553 RQT-190300-006427 | Pass | Y | [8 empty] | Complete
DAT | Adaptive Cruise Control (ACC) | IVI | Cui, Victor (M.) | Wu, Barclay (Kai) | RQT-190300-006251 | 2022-07-05 | Y |  | GIM-38552 GIM-40688 GIM-41335 | GIM-40688 -> APIMCIM-7215 GIM-41335 -> APIMCIM-8227 | TODO Approval | YFVE YFVE | 18-Jul 18-Jul | PCM and BCM congif issue, pending retest with correct config IVI R04 fix on 7/18, fixed with daily SW IVI R04 fix on 7/18, fixed with daily SW |  | Target to close before PEC
DAT | Intelligent Adaptive Cruise Control (iACC) | IVI | Cui, Victor (M.) | Wu, Barclay (Kai) | RQT-001402-020053 | 2022-07-05 | Y | [8 empty] | Target to close before PEC
DAT | Traffic Sign Recognition | IVI | Cui, Victor (M.) | Wu, Barclay (Kai) | RQT-001402-000008 | 2022-07-05 | Y | [8 empty] | Target to close before PEC
EE | Low Beam including Manual and Autolamps | Cluster | Chen, Julian | Zhou, Silver (X.B.) | RQT-170100-704063 | Pass | Y | [8 empty] | Complete
EE | Manual High Beam / Flash to Pass | Cluster | Chen, Julian | Zhou, Silver (X.B.) | RQT-170100-704064 | Pass | [9 empty] | Complete
EE | Multi-Contour Seat (MCS) | IVI | Du, Hao (H.) | Zhou, Silver (X.B.) | RQT-011013-711204 | Done |  | Y | GIM-39933 | GIM-39933 -> APIMCIM-5469 | Approval | Inhouse | 2022-08-03 | IVI R05 fix on 8/3 |  | Function test completed and pass, bug on-going fix, no impact on sign off.
EE | Turn Indicator Light | Cluster | Zhang, Yanos | Zhou, Silver (X.B.) | RQT-170100-704121 RQT-170100-704126 | Pass | [9 empty] | Complete
EE | Hazard Light | Cluster | Zhang, Yanos | Zhou, Silver (X.B.) | RQT-170000-710185 | Pass | [9 empty] | Complete
EE | Fog Lights |  | Zhang, Yanos | Zhou, Silver (X.B.) | RQT-170300-704129 | Pass | [9 empty] | Complete
EE | Stop Light |  | Zhang, Yanos | Zhou, Silver (X.B.) | RQT-170100-704124 | Pass | [9 empty] | Complete
EE | Position/Parking Light | Cluster | Zhang, Yanos | Zhou, Silver (X.B.) | RQT-170100-704125 | Pass | [9 empty] | Complete
EE | Auto Delay / Home Safe Light | IVI | Chen, Julian | Zhou, Silver (X.B.) | RQT-170000-714963 | Pass | [9 empty] | Complete
EE | Backup Light |  | Zhang, Yanos | Zhou, Silver (X.B.) | RQT-170300-704127 | Pass | [9 empty] | Complete
EE | Automatic Dynamic Leveling | Cluster | Chen, Julian | Zhou, Silver (X.B.) | RQT-170100-704068 | Pass | Y | [8 empty] | Complete
EE | Static Bending Light |  | Chen, Julian | Zhou, Silver (X.B.) | RQT-170101-022626 | Pass | Y | [8 empty] | Complete
EE | Dynamic Bending Light Predictive | IVI | Chen, Julian | Zhou, Silver (X.B.) | RQT-170100-704073 RQT-000600-707743 RQT-170100-704065 | 27-Jun 16-Jul | Y | [5 empty] | 2022-07-04 | IPMA 11DTC resolved |  | Target to close before PEC
EE | Speed Dependent Light Mode |  | Chen, Julian | Zhou, Silver (X.B.) | RQT-170100-704074 | Pass | Y | [8 empty] | Complete
EE | Sign Based Light Mode |  | Chen, Julian | Zhou, Silver (X.B.) | RQT-170100-704071 | 2022-07-08 | Y | [5 empty] | 2022-06-24 | DAT SW release on 6/24 - Done |  | Target to close before PEC
EE | Wireless Accessory Charging | IVI | Lyu, Qingtao (Q.) | Zhou, Silver (X.B.) | RQT-000600-022389 | Pass |  | Y | [7 empty] | Complete
PMT4 | AWD / 4WD: Torque Transfer for Handling & Traction (FWD or RWD) |  | Gao, Jiliang (J.) | Fang, Kevin (Zh.J.) | RQT-000600-718929 | Pass | [9 empty] | Complete
DAT | Reverse Brake Assist (RBA) | IVI | Li, Xin | Wu, Barclay (Kai) | RQT-001402-022381 | 2022-07-12 | Y | [6 empty] | Finish function test Calibration arranges between 7/11~7/12 |  | Target to close before PEC
EE | Power Central Lock Suite (PCLS) | IVI | Zhao Jacky | Zhou, Silver (X.B.) | RQT-011411-013547 VEHICLES WITH CENTRAL LOCKING FEATURE ONLY RQT-011411-013549 Drive Away Lock (DAL) RQT-011411-013550 UNLOCKING THE DRIVER'S DOOR WHILE CENTRAL LOCKED RQT-011411-013551 UNLOCKING ALL DOORS WHILE CENTRAL LOCKED RQT-011411-013553 SMART UNLOCKING RQT-011411-013554 UNLOCKING ALL OTHER DOORS WHILE DRIVER'S DOOR UNLOCKED RQT-011411-013559 SPECIAL LOCKING/UNLOCKING RQT-011411-013562 LOCKING WHILE IGNITION "ON" RQT-011411-013565 LOCKING SETTING INDICATION RQT-011411-013566 TAILGATE / DECKLID RELEASE RQT-011411-013567 Power Release of Liftgate or Hatchback RQT-011411-013569 REMOTE CONTROL RQT-011411-013570 PROGRAMMABLE SINGLE DOOR/2 STEP UNLOCKING RQT-011411-013575 UNLOCK FEEDBACK RQT-011411-013586 ELECTRONIC FUEL DOOR LOCK RQT-011411-013587 LED LOCKING INDICATION RQT-011411-013588 ELECTRONIC LOCKABLE STORAGE | 12-Jul TBD | Y |  | GIM-40557 Handsfree PAAK |  |  |  | 5-Jul 8-Jul TBD | DCU SW release on 6/30 7/5 Handsfree calibration on 7/8 PAAK Vehicle set up – X PAAK function verification – X + 5 Walk Away Lock verification – X + 7 |  | Potential PEC Un-contain
DAT | Blind Spot Assist (BSA) | IVI | Liu, Hongxin (H.) | Wu, Barclay (Kai) | RQT-190402-705850 | Pass | Y | [8 empty] | Complete
EE | Unlock Purge / Periodic Parking Purge |  | Du, Hao (H.) | Zhou, Silver (X.B.) | RQT-011200-715823 | Pass |  | Y | [7 empty] | Complete
EE | Key-in Reminder | Cluster | Xiang, Cici | Zhou, Silver (X.B.) | RQT-000600-022951 | Pass |  | Y | [7 empty] | Complete
DAT | Active Drive Assist 1.5 (Lane Biasing) | IVI | Song, Amy (S.) | Wu, Barclay (Kai) | RQT-190300-020345 | 2022-08-05 | Y |  | LCA |  |  |  | 2022-07-29 | LCA/ADA test completion – 7/29 LB/ALC test completion – 8/5 |  | Potential PEC Un-contain
EE | Remote Start (Key Fob) | IVI | Xu, Echo | Zhou, Silver (X.B.) | RQT-190201-015554 RQT-190201-015551 RQT-190201-015541 RQT-190201-015548 RQT-190201-015553 RQT-190201-015542 RQT-190201-015555 RQT-190201-015540 RQT-190201-015546 RQT-190201-015543 RQT-190201-015537 RQT-190201-015557 RQT-190201-015547 RQT-190201-015550 RQT-190201-015538 RQT-190201-704432 RQT-190201-015552 RQT-190201-015544 | Pass | Y | [8 empty] | Complete
EE | Flush Door Handle | IVI | Zhu, Jiawei | Zhou, Silver (X.B.) | RQT-999996-708094 | 10-Jun 22-Jun 12-Jul TBD |  | Y | GIM-37707 PAAK |  |  |  | 12-Jul TBD | DCU SW fix on 6/15 6/30 7/12 PAAK Vehicle set up – X PAAK function verification – X + 5 Walk Away Lock verification – X + 6 |  | Potential PEC Un-contain
EE | Walk Away Lock | IVI | Zhang, Zengguang | Zhou, Silver (X.B.) | RQT-000600-713203 | 10-Jun 21-Jun 1-Jul TBD |  | Y | PAAK |  |  |  | TBD | PAAK Vehicle set up – X PAAK function verification – X + 5 Walk Away Lock verification – X + 7 |  | Potential PEC Un-contain
PMT4 | Fuel Cut / Fuel Disablement |  | Zhang, Jian (Ben.) | Fang, Kevin (Zh.J.) | RQT-001401-000480(safety test REQ) | Pass | [9 empty] | Complete
EC | Indicate Fuel | Cluster | Cao, Helen (H.) | Wu WenZhong, Forrest (W.) | RQT-130000-012683 | Pass | Y | [8 empty] | Complete
DAT | Surround View Cameras | IVI | Li, Xin | Wu, Barclay (Kai) | RQT-131305-007774 RQT-011603-019113 RQT-131305-007778 RQT-131305-007780 RQT-131305-020606 RQT-131305-021422 RQT-131305-007776 RQT-002600-022945 RQT-003200-002906 RQT-131305-019075 | Pass |  | Y | [7 empty] | Complete
EE | First Row Seat Position Control | IVI | Du, Hao (H.) | Zhou, Silver (X.B.) | RQT-000600-716683 | Pass | [9 empty] | Complete
EE | Seat Temperature Control | IVI | Du, Hao (H.) | Zhou, Silver (X.B.) | RQT-000600-714783 | Pass | [9 empty] | Complete
EE | Second Row Seat Position Control |  | Du, Hao (H.) | Zhou, Silver (X.B.) | RQT-000600-716743 | Done |  |  | PFSM issue |  |  |  | 2022-06-30 | PFSM SW and calibration on 6/30 |  | Function test completed and pass, bug on-going fix, no impact on sign off.
DAT | Base Park Aid (BPA) | IVI | He, Michael (X.) | Wu, Barclay (Kai) | RQT-001402-019868 | Pass | [9 empty] | Complete
PMT3 | Selectable Drive Modes (SDM) | IVI | Yang, Yi | Ge, Wendy (Z. H.) | RQT-000600-710204 | Done | Y |  | GIM-40555 | GIM-40555 -> APIMCIM-7224 | Approval | Inhouse | 2022-08-03 | IVI R05 fix on 8/3 |  | Function test completed and pass, bug on-going fix, no impact on sign off.
EE | Automatic Lock Suite | IVI | Liu, Fangwei | Zhou, Silver (X.B.) | RQT-011411-013571 PROGRAMMABLE AUTOLOCK AND AUTOUNLOCK RQT-011411-013579 AUTOUNLOCK | Pass | Y | [8 empty] | Complete
EE | Passive Start | Cluster | Duan, Zhengju (Z.) | Zhou, Silver (X.B.) | RQT-011411-013579 AUTOUNLOCK（Vev） RQT-191200-014895 RQT-191200-014900 RQT-191200-014896 RQT-191200-019096 RQT-191200-014901 | Pass | [9 empty] | Complete
EC | Smooth Dimming | IVI | Li, Qiyang | Xu, Fisher (C.) | RQT-000600-022389 | Done |  | Y | IVI issue Cluster issue DCU issue |  |  |  | 7-Aug 18-Jul 5-Jul | IVI R05 fix on 8/7 Cluster R04 fix on 7/18 DCU SW release on 30-Jun 5-Jul |  | First pass with re-DV before FEC.
PMT4 | Oil Minder | Cluster | Pang, Larry (P.) | Fang, Kevin (Zh.J.) |  | 12-Jun 8-Jul | Y |  | GIM-37645 GIM-40779 |  |  |  | 18-Jul 18-Jul | IVI R04 IVI R04 |  | Target to close before PEC
DAT | Automatic High Beam (AHBC/GFHB/ADB) - FNV3 |  | Song, Amy (S.) | Wu, Barclay (Kai) | RQT-190402-019944 RQT-190402-019479 | 10-Jun 7-Jul | Y | [5 empty] | 2022-06-23 | IPC SW release on 6/23 -Done |  | Target to close before PEC
PMT3 | Steering Column Position Control |  | Wang, Peggy | Ge, Wendy (Z. H.) | RQT-191001-013625 | 31-May 28-Jun 12-Jul |  | Y | GIM-39053 |  |  |  | 2022-07-11 | DSM5 SW support jog mode and KOL on 6/27 7/11 |  | Target to close before PEC
PMT1 | Power Window Controls |  | Hu, Peter (P.H) | Yuan, Gloria (XQin) | RQT-011103-714666 | Done |  | Y | GIM-41283 |  |  |  | 2022-08-02 | DCU fix 1) No Anti-pinch before 2-Aug |  | First pass with re-DV before FEC.
EE | Steering Horizon Controller | IVI | Xi, Tian | Zhou, Silver (X.B.) |  | Done | Y |  | GIM-40688 | GIM-40688 -> APIMCIM-7215 | TODO | YFVE | 2022-07-18 | IVI R04 fix on 7/18 |  | First pass with re-DV before FEC.
| Driver Information Display Control (DIDC) |  | Pang, Larry (P.) | Fang, Kevin (Zh.J.) | RQT-003401-705266 | [8 empty] | FHEV only

## Basic Function
No | Feature | DVP Requirement ID | AFO/D&R/Interface | Supervisor | Manager | Supplier | Supplier DCV5 Pass rate | EE Integration Test Result(Y/N) | DCV5 Limitation | Supplier R00 Pass rate | Supplier R04 Pass rate | FO R00 PEC Sign off Result | R00 Limitation | R04 Sign off Result | R04 Limitation
1 | Lincoln Rear Audio Controls |  | Wang, Peng (P.) <pwang75@ford.com> | Xu, Roger (.) <pxu15@ford.com> | Xu, Fisher (C.) <cxu8@ford.com> | YFVE | 90% | N | 1.BT 通话状态同步功能未做。（新增功能） APIMCIM-3957 Risk for PEC WCHEN154: 此功能暂未测试，测试用例缺失 |  |  | Fail | APIMCIM-3957
2 | 后排娱乐空调控制面板 |  |  |  |  | YFVE | 90% | N/A | 1.BT 通话状态同步功能未做。（新增功能） APIMCIM-3957 Risk for PEC WCHEN154: 707无此功能 |  |  | Pass
3 | Audio Management |  | Xia, Meng (M.) <MXIA13@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | Ford_InHouse | 59% | N/A | 1，V2I涉及到的测试项（包含内外置）； 2，恢复出厂设置（包含内外置）； 3，OTA涉及到的测试项（包含内外置）； 4，bug。 5/13/2022: 将未测试的test case同步Xia Meng， 并确认PEC sign off 风险. （单独TDR） WCHEN154: 未进行测试 |  |  | Pass | With Condition: APIMCIM-7961 APIMCIM-7892 APIMCIM-7891 APIMCIM-7881 APIMCIM-7880 APIMCIM-7260
4 | Lincoln more speakers audio & ANC tuning |  |  |  |  | YFVE | NA | N | 计划R04实现功能。6/15完成标定。 |  |  | Pass
5 | Revel QIS 3D Audio (Audio System, settings) |  |  |  |  | YFVE | 100% | N |  |  |  | Pass
6 | Speakers Config |  |  |  |  | YFVE | NA | Y | 1. 12Channel : 开发进度100% 2. 24Channel ：暂无对手件联调 无法单独统计，分布在各个audio模块统计。以上已与F0 (XiangMeng)确认 |  |  | Pass
7 | Support Ford external DSP module by A2B |  |  |  |  | YFVE | NA | N | 12Channel : 开发进度100% 24Channel ：需要对手件联调。 无法单独统计，分布在各个audio模块统计。以上已与F0 (XiangMeng)确认 |  |  | Pass
8 | Speed compensated volume 根据车速调整音量 |  |  |  |  | Ford_InHouse | 30% | Y | 因YF的bug block 6个test case； bug单：PS-5 5/13/2022：将未测试的test case同步Xia Meng， 并确认PEC sign off 风险. |  |  | Pass | 10 speaker OK. Pending 13 Speaker Harman EQ tunning to double check.
9 | Chime |  |  |  |  | YFVE | 98.44% | Y | w4390/W4391/W4392/W4393报警功能缺失造成block 2022/0513: YF提供测试报告给到FO xia meng |  |  | Pass | Need re-test in R04
10 | 声音设置 sound setting |  |  |  |  | YFVE | 72% | Y | 1.音量提示场景错误 2.车速音量调整默认错误 如上问题需要是创达修复。 2022/05/13: xia meng 和TS确认issue 状态进度。 YF提供测试报告给到FO xia meng |  |  | Pass
11 | Location Service |  | Yao, Tristan (Lan) <LYAO17@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | Ford_InHouse | 53% | Y | 1,YF诊断数据没有显示全； 5/13/2022：待TS更新. |  |  | Pass | With Condition. Issue list详见Sheet1
12 | 系统设置-》单位设置 |  | Zhang, Yi Peng (Y.) <YZHAN482@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | YFVE | 93% | Y | 距离单位没有长度单位显示 计划R00修复 |  |  | Pass
13 | System Stability |  | Chen, Deyin (D.) | Xu, Roger (.) <pxu15@ford.com> |  | YFVE | 30% | Y | 显存溢出，ramdump等问题(单独TDR) |  |  | Fail | Pending On R04 HQX1.2.1 Baseline Switch
14 | Log system |  | Chen, Deyin (D.) | Xu, Roger (.) <pxu15@ford.com> |  | YFVE | NA | Y | 开发进度85%。 1.工程模式：LOG等级控制未做 2.FNV 的LOG诊断：已完成ANR，蓝牙异常状态上传，剩余类似黑屏死机卡死花屏等异常状态还未实现上报 SWV计划R00测试 2022/05//13: 惯导日志，需要Baidu提供具体开发需求 |  |  | Pass | with condition. APIMCIM-3886
15 | 系统设置-》时间设置 &关于本机 &免责申明 |  | Wang, Peng (P.) <pwang75@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | YFVE | 69.68% | Y | 1.设备名称在蓝牙关闭时修改无作用 2.系统设置中点击搜索按钮无输入法打开 计划R00解决 |  |  | Pass
16 | 百度输入法 Baidu Input |  |  |  |  | Baidu | 100% | Y |  |  |  | Pass
17 | 工程模式 bezel diagnostic |  |  |  |  | YFVE | 36.57% | Y | 1.工程模式下的speak walk-around test点击speaker_on无反应。 2,有bug 以上问题R00解决 jzhou101（05/17 TDR）: 工程模式语言显示对比Phase4 有无明显优势，特别针对BU项目. |  |  | Fail | APIMCIM-2166/APIMCIM-2170/APIMCIM-2191/APIMCIM-2194/APIMCIM-2195/APIMCIM-2199/APIMCIM-2203
18 | Ford Clock Strategy |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | YFVE | NA | Y | 时钟策略需求变更。需求文档5/9已完成。开发已实车联调暂未问题。 SWV计划R00测试 |  |  | Pass
19 | Fully Ford ECU Diagnostic&EOL |  |  |  |  | YFVE | 30% | Y | 1.主要诊断服务（10会话）出现No response等系统问题 2.Routine中，声音相关的历程功能未实现 3.DTC中，有部分逻辑存在问题，还有部分未实现（单独5D 追踪） 计划R04解决 |  |  | Fail | APIMCIM-8171/APIMCIM-8170/APIMCIM-7943/APIMCIM-8169/APIMCIM-8172/APIMCIM-3161/APIMCIM-3166/APIMCIM-3149/APIMCIM-3162/APIMCIM-3164/APIMCIM-3148/APIMCIM-3147/APIMCIM-3165/APIMCIM-3163/APIMCIM-3159/APIMCIM-3167
20 | MCU software download (via CAN) |  | Niu Chun | Xu, Roger (.) <pxu15@ford.com> |  | YFVE | 82.69% | N | 1.MCU升级当前只实现了DET升级方式 2.U盘DCV5降级到DCV4版本车机mcu版本显示null； 3.先升级4.22号MCU版本再Qfile刷写4.22 SOC版本必现串口掉线刷写失败 4.DET 刷写mcu过程中报两种Error 5.DET升级mcu 版本完成后，需要手动断电重启车机才能完成vbf升级 |  |  | Pass | Retest in R04->R05
21 | Power management |  | Gao, Ling (L.) <LGAO31@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | YFVE | 97.55% | Y | 1.ignition=run时，没有做信号丢失处理 2.EP phone倒计时结束进入standby，过一会车机会声音自动播放，此时是黑屏状态 3.sleep时，按Power键进EP，EP时间结束，再按Power键没有进入EP 暂无人力解决 2022/05/13: Gaoling 联系领导关于人力问题 YF 发送测试报告 给到FO Gaoling |  |  | Fail | APIMCIM-7861/APIMCIM-3176 Issue： Ep mode issue Phone mode issue Three screen strategy solution
22 | A2B Functional/EQ Tool |  | Qin Chuanxi<CQIN13@ford.com> | Liu, Leo |  | YFVE | NA | N | 12Channel : 1）.EQ Tool开发自测完成90%。剩余10% vbf 文件通过DET升级没有实现 2）.A2B Functional：无法单独统计，分布在各个audio模块统计。 24 Channel:暂无对手件联调。 |  |  | Pass
23 | Noise cancellation for Baidu VR |  | Zhang, Meijuan (M.) <MZHAN102@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | Baidu | NA | Y | 硬件底层链路开发自测100%。 |  |  | Pending Test
24 | Bluetooth Phone |  | Xu, Xin (X.) xxu91@ford.com | Yu, Diven (D.W.) <dyu12@ford.com> |  | YFVE | 92.02% | Y | 1.存在偶现通话无声的问题 2.进入蓝牙电话通讯录搜索页面，输入法未自动弹出.（计划R04解决（基线1.2.1）） |  |  | Fail | Refer to sheet3
25 | Bluetooth music |  | Xu, Xin (X.) xxu91@ford.com |  |  | YFVE | 79.41% | Y | 1.蓝牙音乐的封面和手机端不同步. 2.未知状态，widget上显示未在播放,且控件未置灰 3.Card2播放的蓝牙音乐不显示专辑封面 计划R00解决 |  |  | Fail | Refer to sheet3
26 | 蓝牙耳机 |  | Xu, Xin (X.) xxu91@ford.com |  |  | YFVE | NA | Y | 分别统计蓝牙设置与蓝牙音乐中统计 |  |  | Pass
27 | Bluetooth Setting 蓝牙设置 |  | Xu, Xin (X.) xxu91@ford.com |  |  | YFVE | 88.59% | Y | 1.蓝牙设备无正在等待过程 2.紧急救援开启时，第二个蓝牙设备连接时仍显示紧急救援开关. 计划R00解决 |  |  | Pass
28 | 语音设置 audio setting |  | Zhang, Meijuan (M.) <MZHAN102@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | YFVE | 82% | Y | 1.免唤醒命令词开启部分语音指令不可用 以上需要百度解决下。 |  |  | Pass | APIMCIM-8582 APIMCIM-5651
29 | Illumination |  | Li, Qiyang (Q.) <QLI111@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | YFVE | NA | N | 背光需求在DCV5刚刚确定。 SWV计划R00测试 |  |  | Pass | With Condition(Partial Pass): APIMCIM-7736 APIMCIM-8262
30 | System Performance |  | Qi Xuliang | Yu, Diven (D.W.) <dyu12@ford.com> |  | YFVE | NA | Y | 部分动效需求在开发确认中 |  |  | Pass | Should re-test in R04 with the HQX1.2.1
31 | wifi设置 wifi setting |  | Yu, Diven (D.W.) <dyu12@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | YFVE | 61% | Y | 1.wifi热点密码变更后没有弹出重新输入密码窗口 2.添加网络输入错误的密码，点击加入，显示错误提示后一直在正在加入网络且显示不全 以上问题计划R00解决 3.可用/无网网络通知状态栏图标与实际UI不符。此问题创达提供UI |  |  | Fail | APIMCIM-8579 APIMCIM-8581 APIMCIM-7047 APIMCIM-4453
32 | Consumer Behavior Data (IVI related)埋点 |  | Gu, Zhong Tian (Z.) <zgu10@ford.com> | Xu, Tony (C.) <cxu29@ford.com> |  | Baidu/YFVE/Inhouse | / | N | Baidu:未合入，计划R05 |  |  | Pending Test | Target R05-R06
34 | Autosar/ITV |  | Song, Robert (J.) <jsong30@ford.com> | Sun, Evan (Yi) | Zhou, Silver (X.B.) | YFVE | 60% |  | ITV包括(网络+诊断),见No19 汇总 |  |  | Fail | Follow by 5D, test in R04
37 | Active Noise Cancellation |  | Yao, Keita (Y.) <yyao21@ford.com> | Jiang, Sherry (S.Y.) <sjiang17@ford.com> | Tang, Xiaolin (VE DDE) | YFVE | NA |  | 计划R04实现功能。6/15完成标定。 |  |  | Fail | Joint Debug, Pending test in R05
38 | Display Funtion Safety |  | Wang Yu YWANG544@ford.com | Qiu, Nao (N.) nqiu2@ford.com | Wu WenZhong, Forrest (W.) | YFVE | NA |  | 计划R04测试 |  |  | Pending Test | Pending test in R04
备注： 非Fisher 组 basic Function 待Chen Jiaqiu,Chen Vincent补充
|  | Total | 35 |  | Fail Supplier | 9
|  | Pass | 21 |  | YFVE | 9
|  | Pending Test | 5 |  | Baidu | 0
|  | Fail | 9 |  | TS/Inhouse | 0

## Customer Facing
No | Feature | DVP Requirement ID | AFO/D&R/Interface | Supervisor | Manager | Supplier | Supplier DCV5 Pass rate | EE Integration Test Result(Y/N) | DCV5 Limitation | Supplier R00 Pass rate | Supplier R04 Pass rate | FO R00 PEC Sign off Result | R00 Limitation | R04 Sign off Result | R04 Limitation
1 | 地图基础版（见《IOV-地图功能list) Foundamental version of Map |  | Yao, Tristan (Lan) <LYAO17@ford.com> | Xu, Roger (.) <pxu15@ford.com> | Xu, Fisher (C.) <cxu8@ford.com> | Baidu | 89% | Y | 1. 未实车标定，不支持路测； 2. 部分地图语音指令未合入，R00已合入； 3. 无根据光感判断白天/黑夜模式切换，新接口，R04合入； 4. 无小程序融合，R04合入； jzhou101（05/17 TDR）: 细化地图实车标定准入指标. --FO Yao Lan |  |  | Pass | APIMCIM-8154 APIMCIM-8130 APIMCIM-8125 APIMCIM-8124 APIMCIM-8114 APIMCIM-8111 APIMCIM-8109 APIMCIM-8105 APIMCIM-8104 APIMCIM-8103 APIMCIM-8097 APIMCIM-8096 APIMCIM-8095 APIMCIM-8093 APIMCIM-8092 APIMCIM-8082 APIMCIM-8152 APIMCIM-8131 APIMCIM-8128 APIMCIM-8127 APIMCIM-8123 APIMCIM-8121 APIMCIM-8120 APIMCIM-8119 APIMCIM-8118 APIMCIM-8113 APIMCIM-8112 APIMCIM-8110 APIMCIM-8106 APIMCIM-8102 APIMCIM-8099 APIMCIM-8098 APIMCIM-8094 APIMCIM-8091 APIMCIM-8024 APIMCIM-8023 APIMCIM-8021 APIMCIM-8019 APIMCIM-8018 APIMCIM-7976 APIMCIM-7975 APIMCIM-7940 APIMCIM-7938 APIMCIM-7936 APIMCIM-7934 APIMCIM-7876 APIMCIM-7874 APIMCIM-7872 APIMCIM-7734
2 | 开始导航倒计时/导航结束卡片 Starting/Ending Count Down |  |  |  |  | Baidu | 100% | Y |  |  |  | Pass
3 | 个性化底图-4S店POI显示 4S Dealer POI on Map |  |  |  |  | Baidu | 100% | Y |  |  |  | Pass
4 | 组队出行 Team Travel |  |  |  |  | Baidu | 100% | Y |  |  |  | Pass
5 | 微信地址分享 WeChat Send To Car |  |  |  |  | Baidu | 100% | Y |  |  |  | Pass
6 | 最新版领先市场的地图导航能力 Leading Connected Map/Navi |  |  |  |  | Baidu | 89% | Y | 同1 |  |  | Pass
7 | 本地音乐-MTP音乐 MTP music/USB音乐 USB music/蓝牙音乐 BT music |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | YFVE | USB音乐79.55% BT music79.41% | Y | USB音乐： 1.副驾USB投屏后，主驾USB再投屏，无法投屏 蓝牙音乐： 1.半屏投屏关闭投屏后，Card2播放的蓝牙音乐不显示专辑封面. 如上问题R00解决 |  |  | Pass | APIMCIM-8494 APIMCIM-8493 APIMCIM-8519 APIMCIM-7816 APIMCIM-8306 APIMCIM-3087 APIMCIM-6692 APIMCIM-7709 APIMCIM-7162 APIMCIM-8489 APIMCIM-7720 APIMCIM-8087 APIMCIM-8009 APIMCIM-8406 APIMCIM-8484 APIMCIM-8486 APIMCIM-8490 APIMCIM-8491 APIMCIM-8492 APIMCIM-8518 APIMCIM-5409 APIMCIM-8317 APIMCIM-8324 APIMCIM-8325 APIMCIM-8326 APIMCIM-8327 APIMCIM-8329 APIMCIM-8402 APIMCIM-8410 APIMCIM-8323 APIMCIM-8328 APIMCIM-8408 APIMCIM-8405 APIMCIM-8407 APIMCIM-8320 APIMCIM-6713 APIMCIM-8485
8 | 随心听- 音乐/新闻/有声书 (QQ 音乐-支持QQ 音乐账号登陆；喜马拉雅免费资源集成） |  |  |  |  | Baidu | 98% | Y | 1.Ford Hub相关用例block |  |  | Pass
9 | USB视频播放 Video- USB video |  |  |  |  | YFVE | 52.71% | Y | 1.Launcher无法更改Widget（创达问题已提单），导致从Launcher进入视频界面的用例Block 2.视频快进/快退逻辑有问题 3.播放列表中的首个/最后一个视频切换视频逻辑错误 以上计划R00修复 |  |  | Pass
10 | 爱奇艺 (在线视频APP) Video - Streaming video Iqiyi |  |  |  |  | Baidu | 99% | Y | 3.副驾USB投屏后，主驾USB再投屏，无法投屏 |  |  | Pass
11 | 在线收音机/电台 Online Radio 资源提供方：蜻蜓FM |  |  |  |  | Baidu | 98% | Y | 云听(在线国家电台)相关无法支持PEC sign off, TDR booked. |  |  | Pass
12 | 舱内娱乐Cabin On-live 1.0 （Agile） |  |  |  |  | YFVE/唱吧 | NA | N | R00 开始集成KTV. Audio framework 层pending TS， 预计R04合入. jzhou101（05/17 TDR）: Involve FO 确认PEC->PP 交付基准. |  |  | Pending Test | Not J1 intent
13 | 蓝牙电话 Bluetooh Phone |  | Xu, Xin (X.) xxu91@ford.com | Yu, Diven (D.W.) <dyu12@ford.com> |  | YFVE | 92.2% | Y | 1.存在偶现通话无声的问题 2.进入蓝牙电话通讯录搜索页面，输入法未自动弹出.（计划R04解决（基线1.2.1）） |  |  | Fail | 蓝牙音乐播放切换音乐过程中，专辑界面会跳到一个不知来源的图片，过一会才同步到正常对应的专辑图片，使用oppo reno3 播放音乐全部显示该图片为专辑图片； 连接蓝牙播放蓝牙音乐，过一段时间发现蓝牙自动断开，过一会自动重连，但没有继续播放音乐 新设备首次配对失败，车机端没有任何反馈，配对状态突然消失
14 | 儿童座椅报警Child Restraint System (CRS) - ( e.g BT Child seat 蓝牙座椅) |  |  |  |  | YFVE | 93.08% | Y | 1.儿童座椅功能可正常连接，但在配对连接时存在无配对过程直接显示在配对列表且状态显示正在连接的现象 2.儿童座椅在连接未连接状态下自动切换 计划R00修复 |  |  | Pass
15 | 主副驾独立蓝牙系统 |  |  |  |  | YFVE | BT Phone92.02% BT setting88.59% | Y | 1.蓝牙电话模块基本功能已实现,但存在偶现通话无声的问题. 2.紧急救援开启时，第二个蓝牙设备连接时仍显示紧急救援开关. 以上R00解决 |  |  | Pass | 副驾随心听播放过程中的音效调节按钮，点击进入调整的是整车的参数，且当前副驾耳机音量无法调节
16 | DLNA投屏 |  | Jia, Elaine (T.) <tjia2@ford.com> |  |  | YFVE | 50.62% | Y | 1.DLNA投屏与车速安全交换策略未完善 2.媒体投射手机热点模式和车辆热点模式可以同时开关 3.图片投屏后未适配屏幕 计划R00解决 WCHEN154: DLNA可以FO介入测试。测试环境block了一些用例，主要原因是TCU联网问题导致 jzhou101（05/17 TDR）: 确认测试接口人，明确哪些具体的场景被Block. |  |  | Fail | APIMCIM-7650 APIMCIM-2148 APIMCIM-7690 APIMCIM-6799 APIMCIM-6924 APIMCIM-6750 APIMCIM-7139 APIMCIM-1211 APIMCIM-1204 APIMCIM-7896 APIMCIM-8380 APIMCIM-5881 APIMCIM-7927 APIMCIM-7136 APIMCIM-1208 APIMCIM-1230 | Pass | FEC前需要fix的Issue List: 详见Elaine测试报告.
17 | 人脸识别账户登录Face ID - Driver (DAT-DSMC) |  |  |  |  | Baidu | 78% | Y | 1、系统交互依赖倒挡的未执行 2、个人中心页面的语音无法识别；R00解决 3、账号登录页面二维码下面的人脸识别登录按钮的缺失；R00解决 5/12/2022： 与FO确认PEC sign off target 依然为钧捷方案. |  |  | Fail | Pending DSMC Bug fix.
18 | AR 导航 AR Navigation |  | Ding, Sunny (X.) <XDING13@ford.com> |  |  | Baidu | 实车环境0% 模拟环境70% | N | 未实车标定，模拟开发自测通过率70%，可通过模拟视频流验证（可验证功能前期已输出FO） jzhou101（05/17 TDR）: PEC（功能）/FEC（性能） 实现成熟度进一步确认. |  |  | Pending Test | Target test on 0706
19 | Voice Recognition Systems |  | Zhang, Meijuan (M.) <MZHAN102@ford.com> |  |  | Baidu | 89% | Y | 1. 未实车标定，降噪算法未合入，唤醒识别率差；（已明确标定计划） 2. 未包含离线指令，0303、0412新增语音指令；R00合入 3. setting中无语音帮助、自定义发音人入口（setting未开发，需要输入命令执行），R04合入 VCS 车控接口尚无明确合入计划，影响“新增”车控车设语音指令功能交付. PEC sign off potential risk（TDR Booked）. |  |  | Pending Test | Target test on 08/10
20 | 福特派/林肯之道地址分享 FordPass/LincolnWay Send to car |  | Shi, Stella (J.) <jshi32@ford.com> | Wang, Johnny (J.) <JWANG308@ford.com> | Fan, Henry (H.) <hfan11@ford.com> | Baidu | 100% |  | WCHEN154: 非我们测试内容
21 | 随心听- Ximalaya 2.0 |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Baidu | 99% |  | 无断点续播，R00已合入
22 | 语音助手1.5/2.0 VPA 1.5/2.0 (融合贯通生态的智能化的语音助手）Agile |  | Xie, Jie (J.) <JXIE49@ford.com> |  |  | Inhouse_APP | 80% |  | SmartRecommondation4类场景没有合入 节日场景+widget没有实现，PEC 无法sign off
23 | 车机端电子版用户手册 E-Manual 2.0 Agile |  | Peng, Ivan (F.) <FPENG6@ford.com> |  |  | Inhouse_APP | 70% |  | QA功能没有合入，PEC 无法sign off
24 | (百度小程序) 违章查询 Query traffic violations (IVI) |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  |  | 无此功能
25 | 车辆警示与车辆状态 Vehicle Health Alert and Status(VH) |  | Chen, Wei (W.) <WCHEN160@ford.com> |  |  | Ford_InHouse | 90.5% |  | 1，需要实车测试机油寿命； 2，未提供UI图片(异常状态图片待05/19输入)，VHA异常情况的UI图片。
26 | 用户反馈Customer Feedback 2.0 |  | Xie, Jie (J.) <JXIE49@ford.com> |  |  | Baidu | 80% |  | 遗留部分体验性bug未修复，R00修复合入 WCHEN154: 非我们测试内容
27 | 升级版紧急救援/服务 eCall |  | Ren, Siyuan (Alex.) <sren6@ford.com> | [5 empty] | WCHEN154: 非我们测试内容
28 | 道路救援Road Side Assitance (RSA) |  | Ren, Siyuan (Alex.) <sren6@ford.com> | [5 empty] | WCHEN154: 非我们测试内容
29 | 智能新风Auto Air Refresh (AAR) G2 (Blue Shield) |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Ford_InHouse | 73.4% |  | 1，未测试：滤芯更换,滤芯状态失败，车外PM未获取数据； 2，需要实车这些硬件满足测试要求。 WCHEN154: 当前测试环境不满足
30 | 舒享时分Relax/自由秘境At Ease |  | Zhou, Calvin (.) <QZHOU31@ford.com> |  |  | Inhouse_APP | 80% |  | 卡屏黑屏问题(R00切换16G DDR) DSM部分因没有软件所有没有调试 5/13/2022：Pending DSM5 SW readiness, PEC sign off potential risk. WCHEN154: 非我们测试内容
31 | 个人时光 Smart Scene - Personal Enjoyment |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Inhouse_APP | 81% |  | bug R00/R04 合入
32 | 客人模式Smart Scene - Guest Mode |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Inhouse_APP | 86.7% |  | Bug R00/R04合入
33 | 智能行程 Smart Scene - Intelligent Journey |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Inhouse_APP | 71% |  | 需要实车测试和车控关联大
34 | (百度小程序) 电影票预定 Movie Ticket Booking 美团外卖MeiTuanTake-away 鲜花预定Order flower delivery 机票查询 Flight search 火车票查询 Train ticket search 酒店预定 Hotel booking |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | Baidu | 小程序广场：100% 电影票垂类：/ |  | 小程序广场可显示小程序（热点网络可以）； 垂类未合入，R00合入电影票，其他需求无；
35 | 时空秘信Surprise/Secret message |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | Inhouse_APP | 90% |  | Bug R00/R04合入
36 | 车机应用商店Apps Anywhere(SYNC+) |  | Ren, Siyuan (Alex.) <sren6@ford.com>
37 | 车家互联 ( “小度家居”扫码) Vehicle to Home |  | Kan, Bing (B.) <BKAN@ford.com>
38 | 车机端福特账号和百度账号同时登录 (By 福特派 or 林肯之道App） Baidu and Ford/Lincoln Account dual Login |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | Baidu/TS | Baidu账号：82% |  | 无法解绑、换绑、退登，需要和福特账号同时切换线上环境，R04切线上
39 | 智慧停车 Smart Parking |  | Ren, Siyuan (Alex.) <sren6@ford.com>
40 | 小额免密支付Seamless Payment |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | Baidu | 88% |  | 涉及小程序垂类部分暂不可测试，R00合入小程序垂类
41 | 聚合支付 Aggregate payment +百度-我的钱包 Baidu Wallet |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | Baidu | 88% |  | 涉及小程序垂类部分暂不可测试，R00合入小程序垂类
42 | 消息&消息中心 notification & notification center |  | Zhang, Xu (X.) <XZHAN304@ford.com> |  |  | Baidu | 60% |  | 下拉列表不显示消息，需要延峰配合解决BCM时间问题，沟通中
43 | Lancher - 3D Car Model with vehicle controls |  | Zhang, Renye (R.) <RZHANG68@ford.com> |  |  | Ford_InHouse | 99.4% |  | 有bug；
44 | 天气 Weather |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Baidu | 95% |  | 语音需求未合入，R00合入
45 | Lidget 2.0 Agile |  | Zhou, Calvin (.) <QZHOU31@ford.com> |  |  | Inhouse_APP | 没有合入 |  | PEC 无法sign off
46 | FNOS |  | Chen, Wei (W.) <WCHEN160@ford.com>
47 | (百度小程序) 加油 - Oil Service |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | Baidu | 小程序广场：100% 加油垂类：/ |  | 小程序广场可显示小程序（热点网络可以）； 垂类未合入，R00合入加油/停车，其他需求无；
48 | (百度小程序) 洗车 - Car wash |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | Baidu | 无此功能
49 | 手机钥匙Phone as key(PaaK) |  | Zhang, Yan (Y.) <YZHAN481@ford.com> | Lu, Chao (C.) <CLU42@ford.com> |  | Ford_InHouse | 100%
50 | 远程解锁/启动 Remote Door Lock/Engine Start |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Ford_InHouse | 100%
51 | 远程鸣笛闪灯 Vehicle Announcement via FordPass |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Ford_InHouse | IVI侧无此功能
52 | 远程空调控制 Remote Climate Control (RCC) via FordPass/Lincoln Way |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Ford_InHouse | IVI侧无此功能
53 | 远程车门关闭状态显示/查看 Vehicle Locking Status Check; |  | Lin, Shawn (X.) <xlin17@ford.com>
54 | 4G/5G Entertainment Connectivity Subscription |  | Lin, Shawn (X.) <xlin17@ford.com>
55 | CCS (Customer Connectivity Setting) |  | Gu, Regina (Q.) <QGU12@ford.com> |  |  | Ford_InHouse | 100%
56 | 本地危险事件上报及播报 LHI (Local Hazard Information) |  | Zhang, Wei (W.) <WZHAN175@ford.com> | Li, Yifei (Y.) <nli26@ford.com>
57 | 4G/5G Uu车路协同 V2I Lite (Production) |  | Zhang, Wei (W.) <WZHAN175@ford.com>
58 | 多模块空中升级 Multi Module OTA (MMOTA) (including: USB Update for TCU and ECG; IVI VMCU, CCPU...) |  | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Ford_InHouse | 软件未交付 |  | YFVE 5D 跟进,且得到LL5 approval.
59 | Market Place |  | Chen, Joey (Jun.) | Ji, Kevin (ECDX) <qji4@ford.com> | Ji, Kevin (ECDX) <qji4@ford.com> |  | 软件未交付 |  | R04交付
60 | Muse |  | Shen, Chuangye (C.) <CSHEN21@ford.com> | Zhang, Qing (Q.) <qzhang90@ford.com> | Kou, Guoqiang (G.) <GKOU1@ford.com> | Inhouse_APP
61 | 爱车探索Demo Mode |  | Liu, Ying (Y.) <YLIU391@ford.com> | Lee, Grace (G.) <glee51@ford.com> |  | Inhouse_APP | 60% |  | 新增语音没有合入（打开爱车探索等语音指令pending DCR）， Ui的改动R00合入
62 | 动力流动画显示Power Flow |  | TBD(Gu, Alfred (Y.) <YGU37@ford.com>) | TBD(Zhang, Jim (RECEE.) <jzhan102@ford.com>) | TBD(Li, Charles (C.) <cli137@ford.com>) | Ford_InHouse | 89.3% |  | 1，动画组合信号未测试；

## Others
车控车设--Yipeng
APIMCIM-5435Phase 5：【必现】未显示Predictive Speed Assist设置项
APIMCIM-5427Phase 5：【必现】切换档案后，Query信号的PersIndex仍然发送PersonalityIndex = Vehicle
APIMCIM-5538Phase 5：【必现】点击驾驶模式切换主题，页面切换缓慢，滞留时间很长，且没有停留在驾驶模式界面
APIMCIM-3545Phase 5：【必现】尾灯动画没有pre-animation 显示
APIMCIM-1083Phase 5：【必现】Ignition=OFF，Vehicle setting应不可用
APIMCIM-6654Phase 5：【必现】音乐律动只能在红色和橙色之间切换
APIMCIM-6890Phase 5：【必现】车速限制容限请求信号IsaOffst_D_Rq下发后，不应置为0x0，导致容限无法设为0km/h
APIMCIM-6896Phase 5：【必现】车速限制，断电重启后，不应周期性下发SlMde_D_Rq =0x2，会自动且为手动模式
APIMCIM-6904Phase 5：【必现】RequestTimeOut后泊车位自动提醒请求信号没有back to “NoRequest”.
APIMCIM-6931Phase 5：【必现】机油寿命重置功能未完成
APIMCIM-7186Phase 5：【必现】车速限制辅助容限游标刻度与信号值对应错误
APIMCIM-7761Phase 5：【必现】QUERY缺少Feature ID: 405/807/80B/804/802
APIMCIM-7762Phase 5：【必现】后备箱盖软开关，Speed Restriction Configuration未实现
APIMCIM-8347Phase 5：【必发】只显示防眩照明时，点击请求打开，应下发0x2
APIMCIM-7254Phase5_【CDX707】【黑盒】【必现】【Vehicle Setting】【SYNC+_Z0075】巡航控制中的车道内动态避让开关点击无反应
Camera--Liu Shiwang
· 手动进入360界面或360延时显示时，要按两次Camera键才能退出360界面 APIMCIM-8055
· 需求变更超速时按Camera键进入360的提醒没有实现；
· 需求变更360延时显示切换到前视没有实现；
· 乌龟图没有白天黑夜区分 APIMCIM-7931
· 雷达PrkSns_D_Stat为Off时，乌龟图色块显示错误，应为透明 APIMCIM-7630

## BOF--Pre DV (hidden)
Filter by Program
No | Feature | DVP | AFO/D&R/Interface | Supervisor | Manager | Supplier | Supplier DCV5 Pass rate | EE Integration Test Result(Y/N) | DCV5 Limitation | Supplier R00 Pass rate | Supplier R04 Pass rate | FO Plan 1st round test completed date | Date to provide report | Test Pass Rate | Comments
|  | Requirement ID |  |  |  |  | Pass rate |  |  | Pass rate | Pass rate
| Heated Backlight |  | Shi, Song |  |  | Ford_InHouse | 100% | Y
| Power Moonroof and Shade |  | Hu, Peter |  |  | Ford_InHouse | 100% | Y | 语音控制天窗
| Power Open/Close Liftgate |  | Hu, Peter |  |  | Ford_InHouse | 100% | Y
| Low Beam including Manual and Autolamps |  | Chen, Julian |  |  | Cluster
| Daytime Running Light (DRL) |  | Chen, Julian |  |  | Ford_InHouse | 100% | N
| Manual High Beam / Flash to Pass |  | Chen, Julian |  |  | Cluster
| Turn Indicator Light |  | Zhang, Yanos |  |  | Cluster
| Hazard Light |  | Zhang, Yanos |  |  | Cluster
| Position/Parking Light |  | Zhang, Yanos |  |  | Cluster
| Auto Delay / Home Safe Light |  | Chen, Julian |  |  | Ford_InHouse | 93% | Y | Z0180：有1个fail项，有bug 2022/05/13: align with FO next week
| Automatic Dynamic Leveling |  | Chen, Julian |  |  | Cluster
| Dynamic Bending Light Predictive |  | Chen, Julian |  |  | Ford_InHouse | 100% | N | Z0178
| Ambient Lighting |  | Sun, Qiming |  |  | Ford_InHouse | 72% | Y | 1,需求有变更；新需求的UI未提供。 2,有41个NT项。 2022/05/13: no UI input.
| Heated Steering Wheel (HSW) |  | Yan, Sophie |  |  | Ford_InHouse | 100% | Y
| Multi-Contour Seat (MCS) |  | Du, Hao |  |  | Ford_InHouse | 100% | Y
| First Row Seat Position Control |  | Du, Hao |  |  | Ford_InHouse | 无此功能
| Seat Temperature Control |  | Du, Hao |  |  | Ford_InHouse | 100% | Y
| Electro Mechanical Register |  | Wang, Wei |  |  | Ford_InHouse | 87% | Y | 1，自动模式中手动切换的动效未实现； EMO新动效R00 HOTFIX合入；
| Digital Scent for China version |  | Ma, Shuhan |  |  | Ford_InHouse | 95% | Y | bug：香氛断连判断逻辑 2022/05:13: TS & YF R00 hot fix
| Selectable Drive Modes (SDM) |  | Yang, Yi |  |  | Ford_InHouse | 95.7% | Y | 有bug 2022/05:13: 1. 驾驶模式与氛围灯联动 2. 驾驶模式选择界面无动画 3. 仪表侧驾驶模式只有英文显示
| Smooth Dimming |  | Li, Qiyang |  |  | YFVE | NA | N | SWV计划R04测试
| Lincoln Embrace / Ford Welcome Farewell |  | Chen, Huizhen |  |  | YFVE | 67% | Y | 1.开车门主页车模无动画显示 ?? TS 2.新CR计划R06完成交付验收
| Tire Pressure Monitoring System (TPMS) |  | Wang, Vincent |  |  | Ford_InHouse | 100% | Y
| Outside Air Temperature (OAT) |  | Xie, Will |  |  | Cluster
| Global Windows Open/Close (GWOC) |  | Xiang, Cici |  |  | Ford_InHouse | 100% | Y | SYNC+_Z0216
| Enhanced Memory |  | Li, Niki |  |  | Ford_InHouse | 97% |  | 1,无法在个人中心里面取消个性化档案配置，需要百度解决； 2，有bug
| Perimeter Anti-Theft Alarm |  | Zhang, Zengguang |  |  | Cluster
| Active Park Assist (APA) |  | He, Michael |  |  | Ford_InHouse | 76% | N | 1，有94个NT项； 2，360影像没有调通； 3，需要实车上APA的对手件满足要求。 2022/05/13: TS 联系FO 对手件的软件做联调
| Driver Alert System (DAS) |  | Song, Amy |  |  | Ford_InHouse | 91.67% | Y | 1，UEUI暂未更新，无法测试。 2022/05:13: No HMI input
| Remote Start (Key Fob) |  | Xu, Echo |  |  | Ford_InHouse | 100% | Y
| Passive Start |  | Duan, Zhengju (Z.) |  |  | Cluster
| Passive Entry |  | Duan, Zhengju (Z.) |  |  | Cluster
| Blind Spot Information System (BLIS) |  | Liu, Hongxin |  |  | Ford_InHouse | 89% | Y | Z1002：1个fail项，bug 2022/05:13: Need FO to do pre-signoff
| Cross Traffic Alert (CTA) with Braking (RCTB) |  | Liu, Hongxin |  |  | YFVE | 94% | Y | 1.R档倒车影像卡住不动 2.雷达声音以及颜色提示反应迟钝 3.换R档先退回上一个页面在返回RVC界面 计划R00解决
| Speedometer |  | Cao, Helen |  |  | Cluster
| Lane Centering Assist (LCA) |  | Ni, Anthony |  |  | Ford_InHouse | 100% | Y
| Heated Mirrors |  | Xie, Will |  |  | Ford_InHouse | 100% | Y
| Pre-Collision Assist (PCA) |  | Zhu, Jessi |  |  | Ford_InHouse | 100% | Y
| Adaptive Cruise Control (ACC) |  | Cui, Victor |  |  | Ford_InHouse | 97% | Y | 一个NT项，UEUI未更新； 2022/05:13: need HMI input
| Intelligent Adaptive Cruise Control (iACC) |  | Cui, Victor |  |  | Ford_InHouse | 100% | Y
| Traffic Sign Recognition |  | Cui, Victor |  |  | Ford_InHouse | 100% | Y
| Wireless Accessory Charging |  | Lyu, Qingtao (Q.) |  |  | Ford_InHouse | 100% | Y
| Reverse Brake Assist (RBA) |  | Cai, Lingling |  |  | Ford_InHouse | 74% | Y | 1，1个NT：UEUI未更新； 2，YF侧的bug block4个测试项。 2022/05:13: TS 提供YF bug list
| Clear Exit Assist |  | Liu, Hongxin |  |  | Ford_InHouse | 77% | Y | 1.NT原因：需要实车上ECU件状态满足要求； 2.有Bug。 2022/05:13: need FO 更新对手件状态
| Blind Spot Assist (BSA) |  | Liu, Hongxin |  |  | Ford_InHouse | 100% | Y
| Key-in Reminder |  | Xiang, Cici |  |  | Cluster
| Active Drive Assist 1.5 |  | Song, Amy |  |  | Ford_InHouse | 88% | Y | NT原因： 三级菜单功能的搜索暂未开发；暂无法测试 2022/05:13:
| Global Beltminder |  | Xu, Xi Hai |  |  | Ford_InHouse | 无此功能
| Flush Door Handle |  | Zhu, Jiawei |  |  | Ford_InHouse |  |  | 非TS负责
| Remote Park Assist (REPA) |  | He, Michael |  |  | Ford_InHouse | / | N | 目前做的Fapa
| Walk Away Lock |  | Zhang, Zengguang |  |  | Ford_InHouse | 90% | Y | NT原因： 三级菜单功能的搜索暂未开发；暂无法测试 2022/05:13:
| Indicate Fuel |  | Cao, Helen |  |  | Cluster
| Surround View Cameras |  | Cai, Lingling |  |  | YFVE | 85% | Y | 1.360视角退出360后雷达区域一直黑色显示，断B+才能恢复 2.360配置不能正确显示，需多次重启才能正确显示 计划R00解决 3.多次点击放大缩小按钮倒车影像显示异常等 4.进入前视、card1、card2先黑一下，再显示影像 计划R04解决
| Base Park Aid (BPA) |  | He, Michael |  |  | YFVE | 100% | N
| Power Central Lock Suite (PCLS) |  | Zhao, Jacky |  |  | Ford_InHouse | 100% | Y
| Automatic Lock Suite |  | Zhao, Jacky |  |  | Ford_InHouse | 100% | Y
| Automatic High Beam (AHBC/GFHB) - FNV3 |  | Song, Amy |  |  | Ford_InHouse | 80% | Y | NT原因： 1.三级菜单功能的搜索暂未开发；暂无法测试 2.APIMCIM-2138 Block测试 3.Ignition!=4场景车控功能显示，UIUE未更新相关需求，无法测试 2022/05:13: Need HMI input for item3
| Steering Horizon Controller |  | Xi, Tian |  |  | YFVE | 45% | Y | DI：1.RES按键逻辑错误 2.切换CC/ACC状态，左侧按键焦点丢失，按键常显 3.通话时触发报警，报警触发有问题 计划R00修复 IVI:内部需求滞后未测试。 计划R00测试。
| Automatic Engine Idle Shutdown (AEIS) |  | Zhang, Jian |  |  | Ford_InHouse | 88% | Y | 1.有BUG 2022/05:13: TS update the JIRA ticket
| Range Selection |  | Gao, Jiliang |  |  | Cluster
| Oil Minder |  | Pang, Larry |  |  | Cluster

## DCV5 Refresh Plan (hidden)
DCV5 Refresh for IVI pre sign off
Team | Interface | Tel | Bench/BB/Vehicle | Location | Quantity | Refresh Date
IVI | Sun Jun @Sun, Jun (J.) |  | Bench | Makerspace | 5 | Done
IVI | Xia Xiaojin @Xia, Xiao Jin (X.) |  | Vehicle | 保密车库2 | 5 | Done
ECDX | Chen Vincent @Chen, Vincent (N.) |  | 18551732721 | EOB3 | 6 | Done
VEV | Zhou Xuguang |  | BB | EOB1 EE LAB |  | Done
Others | @Li, Daisy (Y.P.) @Ji, Lyra (L.) |  | LV610(15051888744) LV641(HCHEN188) FV32(18605697218) LV626(lzhao19) LV612(yyang130) |  | 5 | 预计05/11