## Sheet1
No | Feature | AFO/D&R/Interface | Supervisor | Manager | Supplier | Test Result
SYNC+_Z0247 | Heated Backlight | Shi, Song |  |  | Ford_InHouse | Inhouse：该功能在103A车子上，有遥控启动设置部分配置项，但页面置灰 APIMCIM-7009
SYNC+_Z1048 | Power Moonroof and Shade | Hu, Peter |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_Z0293/SYNC+_Z0212 | Power Open/Close Liftgate | Hu, Peter |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_Z0258 | Low Beam including Manual and Autolamps | Chen, Julian |  |  | Ford_InHouse | OK
SYNC+_Z0178 | Light Setting-Adaptive headlamps |  |  |  | Ford_InHouse | Inhouse：该功能在103A车子上，有自适应前照灯开关配置项，无自适应前照灯设置配置项, duplicated with Dynamic Bending Light Predictive
SYNC+_Z0181 | Daytime Running Light (DRL) | Chen, Julian |  |  | Ford_InHouse | OK
SYNC+_Z0231 | Manual High Beam / Flash to Pass | Chen, Julian |  |  | Ford_InHouse | OK
FIP中找不到Feature ID | Turn Indicator Light | Zhang, Yanos |  |  | Cluster | LV644, 103A: 当只拔掉左灯connector, 开左转向，仪表left telltale因故障有倍频，开右转向，仪表right telltale也有倍频，Nok, 应该正常频率；当只拔掉右灯connector, 开左转向，仪表left telltale闪烁频率正常，开右转向，仪表right telltale因故障有倍频，ok. Juduement: 跟IVI无关。
SYNC+_Z0244 | Hazard Light | Zhang, Yanos |  |  | Cluster | OK
SYNC+_Z0257 | Position/Parking Light | Zhang, Yanos |  |  | Cluster | OK
| Auto Delay / Home Safe Light | Chen, Julian |  |  | Ford_InHouse | OK
SYNC+_Z0241 | Automatic Dynamic Leveling | Chen, Julian |  |  | Ford_InHouse | jzhou101： FO 尚未测试
| Dynamic Bending Light Predictive | Chen, Julian |  |  | Ford_InHouse | jzhou101： FO 尚未测试（对手件软件pending）
SYNC+_Z0101 | Ambient Lighting | Sun, Qiming |  |  | Ford_InHouse | 1.动态模式背景色不变化（Jira Number TBD TS） 2.音乐律动只有红色和橙色变化，亮度有可能有延迟 APIMCIM-6654 3.氛围灯的文字描述，设置氛围灯的亮度与颜色，仅在黑夜模式下启用是不对的
SYNC+_Z0295 | Heated Steering Wheel (HSW) | Yan, Sophie |  |  | Ford_InHouse | Inhouse：该功能在103A车子上，有遥控启动设置部分配置项，但页面置灰
SYNC+_Z0047 | Multi-Contour Seat (MCS) | Du, Hao |  |  | Ford_InHouse | APIMCIM-6998 https://www.jira.ford.com/browse/GIM-40528
SYNC+_Z0287 | First Row Seat Position Control | Du, Hao |  |  | Ford_InHouse | 与IVI无关
SYNC+_Z0297 | Seat Temperature Control | Du, Hao |  |  | Ford_InHouse | 测试要到5.20左右才可以进行， Potential Risk for PEC sign off. Deviation Needed. ---Lyra Ji.
SYNC+_0264 | Electro Mechanical Register | Wang, Wei |  |  | Ford_InHouse | 1. GIM-40042 voice control no function ； R00修复. 2.GIM-40529 Auto register no order show ； R00修复. 3.GIM-40530 Airflow animation not smooth ； TS正在进行分析和方案优化, Target R04. 4.GIM-40531 CDX707 EM register incorrect working status on climate floor and windscreen mode； TS 会后确认原因与修复计划. 5.GIM-40534 CDX707 EM register no correct feedback position signals from RCCM when close register ； 6.GIM-40535 CDX707 EM register onbody/off button hard to seen for the dark color ； UI设计问题，非软件bug, 需要HMI优化. @Lyra Ji. 7.GIM-40591 CDX707 EM register manual mode -not support multiple operations TS 会后确认原因与修复计划.
SYNC+_0134 | Digital Scent for China version | Ma, Shuhan |  |  | Ford_InHouse | 打开香氛界面在香氛选型界面出现红色感叹号，且出现“为了保证你的健康与最佳体验，请避免使用过期或未获林肯中国认证的香氛产品”提示(Jira Issue Number TBD)
SYNC+_Z0045 | Selectable Drive Modes (SDM) | Yang, Yi |  |  | Ford_InHouse | 1. 驾驶模式和氛围灯关联后, 页面切换缓慢，滞留时间很长，且界面跳变 APIMCIM_5538 Jzhou101：Yang yi, Yipeng 会后拉上YFVE 同步优化方案，如果推进不下去，下周二上Fisher LL5 TDR。 2.驾驶模式控制界面动画特效不显示 GIM_40555 Jzhou101：动画资源不满足性能要求（序列帧，100M）,需要Studio/HMI 团队重新输出. @Lyra, Yang Yi. 3.驾驶模式仪表盘显示为英文 APIMCIM_6893 R00修复.
SYNC+_Z0044 | Smooth Dimming | Li, Qiyang |  |  | YFVE | IVI转发ignition_status 信号到ICP用来控制ICP 音量旋钮背光流水灯 和延锋aligned 5/26交付软件(R04) 11.1 Touch Screen 亮度补偿设置（ 用来调节11.1 Touch Screen 屏幕亮度的设置项） 和延锋aligned 5/26交付软件(R04)
| Lincoln Embrace / Ford Welcome Farewell | Chen, Huizhen |  |  | YFVE | 1. unlock/屏幕会亮一下再熄屏.GIM-40598 (APIMCIM-2183)
SYNC+_Z0289 | Tire Pressure Monitoring System (TPMS) | Wang, Vincent |  |  | Ford_InHouse | jzhou101： FO 尚未测试(HCM)
FIP中找不到Feature ID | Outside Air Temperature (OAT) | Xie, Will |  |  | Cluster | jzhou101： FO 尚未测试
FIP中找不到Feature ID | Global Windows Open/Close (GWOC) | Xiang, Cici |  |  | Ford_InHouse | jzhou101： FO 尚未测试(DCU calibration)
SYNC+_0165 | Enhanced Memory | Li, Niki |  |  | Ford_InHouse | jzhou101： FO 尚未测试(DSM 5 not ready)
SYNC+_Z0288 | Perimeter Anti-Theft Alarm | Zhang, Zengguang |  |  | Cluster | LV627,Cluster could not seeting menu
FIP中是否为FAPA功能？ | Active Park Assist (APA) | He, Michael |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_Z0229 | Driver Alert System (DAS) | Song, Amy |  |  | Ford_InHouse | jzhou101： FO 尚未测试
FIP中有多个功能 | Remote Start (Key Fob) | Xu, Echo |  |  | Ford_InHouse | jzhou101： FO 尚未测试
FIP中找不到Feature ID | Passive Start | Duan, Zhengju (Z.) |  |  | Cluster
FIP中找不到Feature ID | Passive Entry | Duan, Zhengju (Z.) |  |  | Cluster
SYNC+_Z0071 | Blind Spot Information System (BLIS) | Liu, Hongxin |  |  | Ford_InHouse | OK. 功能开关按钮可正常开启/关闭
SYNC+_0098 | Cross Traffic Alert (CTA) with Braking (RCTB) | Liu, Hongxin |  |  | YFVE | Not OK 1. CTA 报警箭头与UI不匹配(APIM CIM Jira Number) YFVE Liu Zike 2. CTA Chime， IPC与IVI握手失败--已跟Eureka反馈 3. CTA开启关闭时，倒挡来车预警影像 按钮在IVI屏幕出现/消失，导致整个开关菜单出现跳变(APIM CIM Jira Number) YFVE Liu Zike
| Speedometer | Cao, Helen |  |  | Cluster
SYNC+_Z0281 | Lane Centering Assist (LCA) | Ni, Anthony |  |  | Ford_InHouse | Inhouse：该功能在103A车子上没有车道居中保持配置项，需要FO确认在什么配置类型的车子上才有
SYNC+_Z1003 | Heated Mirrors | Xie, Will |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_Z0091 | Pre-Collision Assist (PCA) | Zhu, Jessi |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_Z0075 | Adaptive Cruise Control (ACC) | Cui, Victor |  |  | Ford_InHouse | jzhou101： FO 尚未测试 (PCM calibration)
SYNC+_Z0075 | Intelligent Adaptive Cruise Control (iACC) | Cui, Victor |  |  | Ford_InHouse | Cui Victor: 1. ADAS Map 信号没有发出. --Baidu侧确认. 2.IACC 菜单通过配置显示无效. ---Zhang Yipeng Double confirm.
SYNC+_Z0097 | Traffic Sign Recognition | Cui, Victor |  |  | Ford_InHouse | Inhouse：该功能在103A车子上没有交通标志识别配置项，需要FO确认在什么配置类型的车子上才有(speed limit assist 替代)
SYNC+_Z0050 | Wireless Accessory Charging | Lyu, Qingtao (Q.) |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_0074 | Reverse Brake Assist (RBA) | Cai, Lingling |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_0101 | Clear Exit Assist | Liu, Hongxin |  |  | Ford_InHouse | pending, test not completed.
SYNC+_Z0071 | Blind Spot Assist (BSA) | Liu, Hongxin |  |  | Ford_InHouse | OK.
FIP中找不到Feature ID | Key-in Reminder | Xiang, Cici |  |  | Cluster
SYNC+_Z0091 SYNC+_Z0093 SYNC+_Z0094 SYNC+_Z0096 SYNC+_Z0099 | Active Drive Assist 1.5 | Song, Amy |  |  | Ford_InHouse | Inhouse：该功能在103A车子上信息如下： SYNC+_Z0093 - 仅有车速限制辅助-超速警告配置项，可点击 SYNC+_Z0094 - 无车速限制配置项，需要FO确认在什么配置类型的车子上才有 SYNC+_Z0099 - 无逆行提醒配置项，需要FO确认在什么配置类型的车子上才有
SYNC+_Z1007 | Global Beltminder | Xu, Xi Hai |  |  | Ford_InHouse | jzhou101： FO 尚未测试
FIP中找不到Feature ID | Flush Door Handle | Zhu, Jiawei |  |  | Ford_InHouse | OK
FIP中是否为FAPA功能？ | Remote Park Assist (REPA) | He, Michael |  |  | Ford_InHouse | Michael, 影像调出速度缓慢（NTC 软件版本待确认）卡滞. 需要REC 实车（CDX707FV34-LV644）做ABA测试. Potential Risk for PEC.
SYNC+_Z0187/SYNC+_Z0286 | Walk Away Lock | Zhang, Zengguang |  |  | Ford_InHouse | LV627,PEPS not calibration yet, WAL couldn't test and may not confirm the IVI seeting is enable Jzhou101: Potential Risk for PEC sign off. Deviation Needed. ---Lyra Ji.
FIP中找不到Feature ID | Indicate Fuel | Cao, Helen |  |  | Cluster
FIP中找不到Feature ID | Surround View Cameras | Cai, Lingling |  |  | YFVE | ADAS ECU的分辨率已经更新到了1536*664（Late change）， YFVE分辨率适配计划R04.确认有无机会合入R00.
FIP中找不到Feature ID | Base Park Aid (BPA) | He, Michael |  |  | YFVE | Joint debug
SYNC+_Z0187 | Power Central Lock Suite (PCLS) | Zhao, Jacky |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_Z0187 | Automatic Lock Suite | Zhao, Jacky |  |  | Ford_InHouse | LV627,No temporary driving license. Drive Away Lock \ Auto Unlock to be tested.
SYNC+_Z0231 | Automatic High Beam (AHBC/GFHB) - FNV3 | Song, Amy |  |  | Ford_InHouse | Inhouse：该功能在103A车子上没有此配置项，需要FO确认在什么配置类型的车子上才有
SYNC+_Z0290 | Steering Horizon Controller | Xi, Tian |  |  | YFVE/Cluster | ACC相关的功能无法进入子级菜单(Cluster), 右侧多媒体控制已经完成.
SYNC+_Z0246 | Automatic Engine Idle Shutdown (AEIS) | Zhang, Jian |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_Z0286 | Range Selection | Gao, Jiliang |  |  | Cluster | OK.
SYNC+_Z1026 | Oil Minder | Pang, Larry |  |  | Cluster
FIP中找不到Feature ID | Static Bending Light | Chen, Julian |  |  | Ford_InHouse | jzhou101： FO 尚未测试
FIP中找不到Feature ID | Speed Dependent Light Mode | Chen, Julian |  |  | Ford_InHouse | jzhou101： FO 尚未测试
SYNC+_Z1053 | Sign Based Light Mode | Chen, Julian |  |  | Ford_InHouse | jzhou101： FO 尚未测试 (HCM / DAT)
SYNC+_Z0279 | 2# Help Me Drive 驾驶辅助_高速驾驶辅助Highway Assist - Lane Biasing(DAT2.1 new feature) | Song, Amy (S.) <ssong18@ford.com> |  |  | Ford_InHouse | Inhouse：该功能在103A车子上没有车道内动态避让配置项，需要FO确认在什么配置类型的车子上才有
SYNC+_Z1008 | Driver_Information_Display_Control |  |  |  | Ford_InHouse | Inhouse：该功能在103A车子上情况如下： 有驾驶信息显示部分功能配置项（行车电脑1/2配置里显示空白；重置数据里面只有3个重置选项）
SYNC+_Z0213 | Remote start (activate, climate, auto, last setting, seats and wheels, duration) |  |  |  | Ford_InHouse | Inhouse：该功能在103A车子上，有遥控启动设置部分配置项，但页面置灰
SYNC+_Z0070 | Auto Stop Start |  |  |  | Ford_InHouse | Inhouse：该功能在103A车子上没有自动启停配置项，需要FO确认在什么配置类型的车子上才有