## CDX707 overal test plan
| 2022年 | [47 empty] | 2023年 | [47 empty] | 2024年
| 1月 |  |  |  | 2月 |  |  |  | 3月 |  |  |  | 4月 |  |  |  | 5月 |  |  |  | 6月 |  |  |  | 7月 |  |  |  | 8月 |  |  |  | 9月 |  |  |  | 10月 |  |  |  | 11月 |  |  |  | 12月 |  |  |  | 1月 |  |  |  | 2月 |  |  |  | 3月 |  |  |  | 4月 |  |  |  | 5月 |  |  |  | 6月 |  |  |  | 7月 |  |  |  | 8月 |  |  |  | 9月 |  |  |  | 10月 |  |  |  | 11月 |  |  |  | 12月 |  |  |  | 1月 |  |  |  | 2月 |  |  |  | 3月 |  |  |  | 4月 |  |  |  | 5月 |  |  |  | 6月 |  |  |  | 7月 |  |  |  | 8月 |  |  |  | 9月 |  |  |  | 10月 |  |  |  | 11月 |  |  |  | 12月
| 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w
CDX707项目节点
软件发布
QA-NTT/FCPA测试
VE-R202/HMI
ICV测试
T&D-SW Fleet测试
T&D-VOCF- Duty cycle
DCV
1/28
8/29
FEC
TT
PP
MP1
MP2
9/7
11/23
2/1
3/1
7/19
PEC
TT
DCV0
11/03
DCV1
12/29
DCV2
01/26
DCV3
03/09
DCV5
05/04
R00
06/01
R04
06/29
R05
07/25
DCV4
04/06
R06
09/21
R07
12/04
R08 for OKTB
01/24
R09 for OTA
04/28 TBD
整车静态Lite Test
整车压力测试
整车静态Lite Test
整车静态Lite Test
整车静态Lite Test
整车静态Lite Test
压力测试回归
整车静态Lite Test
OTA 压力测试
车辆多/不固定/停留1-2天
2/13~
车辆固定/DCV*2/TT*4
ICV状态检查及功能签收
整车动态软件测试
台架压力测试
语音/多模交互/蓝牙/空调/人脸识别/Wifi/兼容性等专项测试
ICV全功能测试
OTA送签版本功能测试
ICV全功能测试
整车动态软件测试
整车动态软件测试
回归及探索性测试
回归及探索性测试
用户驾驶测试
用户驾驶测试
用户驾驶测试
车辆固定/TT*2
地图/IPC/HUD等专项测试
TT*4~8/PP*4~8
整车动态Lite Test
整车动态Lite Test
整车动态Lite Test
车辆固定/TT*6/PP*6
静态/动态UI检查
静态/动态UI检查
静态/动态UI检查
地图/IPC/HUD等专项测试
ICV功能文档收集、用例完善
Note on A15: 作者: 三高试验，在当地跑8000km，加上路上往返，会在13000+多

## CDX707 China Gas EPT TT
G23 CDX707 China GAS EPT/TT Build Plan
|  | B | Body | EOL | End Of Line
|  | P | Paint | EE | EESE
|  | T | Trim | R | Quality rework | [15 empty] | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
|  | S/O | Sign Off
|  | ATS | Available To Ship | time axis 2022-07-23 to 2022-11-19
| Seq No. | Number | Category | VIN | Catcode | Series | Engine | Trans | Seat | Wheel | Drive | Version Pkg ACC | REMOTE STARTER#2 | Ext Color | Int Color | Owner | Usage | Shiping Req. Date | Build Deliv. Date | Gap
V | 1 | EPT 01 | China GAS | LVSHNCAC5NH684120 | 88DAK | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | White Platinum Tri-Coat | Black Onyx/(Medium Light Space Gray | TD&VE-TD | PV-R343 Corrosion Test | 2022-09-19 | 2022-09-29 | -10 | 2022-08-20: B; 2022-08-21: B; 2022-08-22: B; 2022-08-23: B; 2022-08-24: B; 2022-08-26: P; 2022-08-27: P; 2022-08-28: P; 2022-08-30: T; 2022-08-31: T; 2022-09-01: R; 2022-09-02: R; 2022-09-05: EOL; 2022-09-06: EOL; 2022-09-07: EOL; 2022-09-08: EOL; 2022-09-09: EOL; 2022-09-12: EE; 2022-09-13: EE; 2022-09-14: Hunter & Headlamp; 2022-09-15: S&R; 2022-09-16: S&R; 2022-09-19: CAL&2.5MinsWL; 2022-09-20: 2H WL&Camo.; 2022-09-21: ES; 2022-09-22: FCPA dynamic; 2022-09-23: NTT; 2022-09-26: BH8; 2022-09-27: S/O; 2022-09-28: Shake down; 2022-09-29: ATS
V | 2 | EPT 02 | China GAS | LVSHNCAC9NH684122 | 88DBB | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK | REMOTE STARTER #2 | Blue Diamond | Black Onyx/Black Onyx | ICV-sun xiuling | ICV software test | 2022-09-01 | 2022-09-30 | -29 | 2022-08-20: B; 2022-08-21: B; 2022-08-22: B; 2022-08-23: B; 2022-08-24: B; 2022-08-26: P; 2022-08-27: P; 2022-08-28: P; 2022-08-29: P/BIP AL; 2022-08-30: T; 2022-08-31: T; 2022-09-01: R; 2022-09-02: R; 2022-09-05: EOL; 2022-09-06: EOL; 2022-09-07: EOL; 2022-09-08: EOL; 2022-09-09: EOL; 2022-09-12: EE; 2022-09-13: EE; 2022-09-14: Hunter & Headlamp; 2022-09-15: S&R; 2022-09-16: S&R; 2022-09-19: CAL&2.5MinsWL; 2022-09-20: 2H WL&Camo.; 2022-09-21: AL; 2022-09-22: AL; 2022-09-23: ES; 2022-09-26: NTT; 2022-09-27: BH8; 2022-09-28: S/O; 2022-09-29: Shake down; 2022-09-30: ATS
B | 55 | TT BIW 01 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | Bodyshop |  |  |  | 0 | 2022-08-29: B; 2022-08-30: B; 2022-08-31: B; 2022-09-01: B; 2022-09-02: P; 2022-09-03: TearDown
B | 56 | TT BIW 02 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | Bodyshop |  |  |  | 0 | bar: 2022-08-29 to 2022-09-01
B | 61 | TT BIW 07 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | AE QC |  |  |  | 0 | bar: 2022-08-29 to 2022-09-01
V | 3 | EPT 03 | China GAS | LVSHNCAC2NH684124 | 88DAG | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | White Platinum Tri-Coat | Black Onyx/Medium Light Space Gray | TD&VE-Homo | Homologation test-Crash | 2022-09-15 | 2022-10-08 | -23 | 2022-08-29: B; 2022-08-30: B; 2022-08-31: B; 2022-09-01: B; 2022-09-02: P; 2022-09-05: P; 2022-09-06: P; 2022-09-07: T; 2022-09-08: T; 2022-09-09: R; 2022-09-12: R; 2022-09-13: EOL; 2022-09-14: EOL; 2022-09-15: EOL; 2022-09-16: EOL; 2022-09-19: EE; 2022-09-20: EE; 2022-09-21: FCPA; 2022-09-22: FCPA; 2022-09-23: FCPA; 2022-09-26: FCPA; 2022-09-27: FCPA; 2022-09-28: Hunter & Headlamp; 2022-09-29: CAL&2.5MinsWL; 2022-09-30: 2H WL&Camo.; 2022-10-05: S&R; 2022-10-06: S&R; 2022-10-07: S/O; 2022-10-08: ATS
V | 5 | EPT 05 | China GAS | LVSHNCAC0NH684123 | 88DBA | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK | REMOTE STARTER #2 | White Platinum Tri-Coat | Black Onyx/Red Line (FR5) | TD&VE-Homo | Homologation test-Photo/ Crash | 2022-09-15 | 2022-10-08 | -23 | 2022-08-29: B; 2022-08-30: B; 2022-08-31: B; 2022-09-01: B; 2022-09-02: P; 2022-09-05: P; 2022-09-06: P; 2022-09-07: T; 2022-09-08: T; 2022-09-09: R; 2022-09-12: R; 2022-09-13: EOL; 2022-09-14: EOL; 2022-09-15: EOL; 2022-09-16: EOL; 2022-09-19: EE; 2022-09-20: EE; 2022-09-21: FCPA; 2022-09-22: FCPA; 2022-09-23: FCPA; 2022-09-26: FCPA; 2022-09-27: FCPA; 2022-09-28: Hunter & Headlamp; 2022-09-29: CAL&2.5MinsWL; 2022-09-30: 2H WL&Camo.; 2022-10-05: S&R; 2022-10-06: S&R; 2022-10-07: S/O; 2022-10-08: ATS
V | 4 | EPT 04 | China GAS | LVSHNCAC7NH684121 | 88DAL | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | White Platinum Tri-Coat | Black Onyx (19W)/Allura Blue | TD&VE-Homo | Homologation test-Crash | 2022-09-15 | 2022-10-08 | -23 | 2022-08-30: B; 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: P; 2022-09-06: P; 2022-09-07: P; 2022-09-08: T; 2022-09-09: T; 2022-09-12: R; 2022-09-13: R; 2022-09-14: EOL; 2022-09-15: EOL; 2022-09-16: EOL; 2022-09-17: EOL(TRON) Validation; 2022-09-28: EE; 2022-09-29: EE; 2022-09-30: Hunter & Headlamp; 2022-10-05: CAL&2.5MinsWL; 2022-10-06: 2H WL&Camo.; 2022-10-07: S/O; 2022-10-08: ATS
v | 40 | TT 35 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 8.0 X 20" ALLOY WHL | AWD | SPORT VERSION PACK |  | White Platinum Tri-Coat | Black Onyx/Black Onyx | REC-PT | PCM Cal development | 2022-10-09 | 2022-10-09 | 0 | 2022-08-30: B; 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: P; 2022-09-06: P; 2022-09-07: P; 2022-09-08: T; 2022-09-09: T; 2022-09-12: R; 2022-09-13: R; 2022-09-14: EOL; 2022-09-15: EOL; 2022-09-16: EOL; 2022-09-19: EE; 2022-09-20: EE; 2022-09-21: S&R; 2022-09-22: S&R; 2022-09-23: CAL&2.5MinsWL; 2022-09-26: 2H-WL; 2022-09-27: Camo.&Hunter & Headlamp; 2022-09-28: ES 90; 2022-09-29: AL; 2022-09-30: NTT; 2022-10-05: Deep track; 2022-10-06: KOL; 2022-10-07: BH8; 2022-10-08: S/O; 2022-10-09: ATS
V | 41 | TT 36 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | Blue Diamond | Black Onyx/(Medium Light Space Gray | REC-PMT4 | Trans calibration (AVL sign off + Final tuning) | 2022-10-09 | 2022-10-09 | 0 | 2022-08-30: B; 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: P; 2022-09-06: P; 2022-09-07: P; 2022-09-08: T; 2022-09-09: T; 2022-09-12: R; 2022-09-13: R; 2022-09-14: EOL; 2022-09-15: EOL; 2022-09-16: EOL; 2022-09-19: EE; 2022-09-20: EE; 2022-09-21: S&R; 2022-09-22: S&R; 2022-09-23: CAL&2.5MinsWL; 2022-09-26: 2H-WL; 2022-09-27: Camo.&Hunter & Headlamp; 2022-09-28: E-4P; 2022-09-29: E-4P; 2022-09-30: E-4P; 2022-10-05: ES; 2022-10-06: NTT; 2022-10-07: ES 90; 2022-10-08: S/O; 2022-10-09: ATS
V | 49 | TT 44 | China GAS |  |  | BASE (100A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | Diamond Red TC | Black Onyx/(Medium Light Space Gray | REC-PMT5 | Power Window Calibration/PEPS Calibration | 2022-10-14 | 2022-10-11 | 3 | 2022-08-30: B; 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: P; 2022-09-06: P; 2022-09-07: P; 2022-09-08: P; 2022-09-09: T; 2022-09-12: T; 2022-09-13: R; 2022-09-14: R; 2022-09-15: EOL; 2022-09-16: EOL; 2022-09-19: EE; 2022-09-20: EE; 2022-09-21: S&R; 2022-09-22: S&R; 2022-09-23: CAL&2.5MinsWL; 2022-09-26: 8H-WL; 2022-09-27: 8H-WL; 2022-09-28: Camo.&Hunter & Headlamp; 2022-09-29: FCPA dynamic; 2022-09-30: BH8; 2022-10-05: M/F; 2022-10-06: SG/DCE; 2022-10-07: FCPA dynamic; 2022-10-08: NTT; 2022-10-09: KOL; 2022-10-10: S/O; 2022-10-11: ATS
V | 20 | TT 15 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK | REMOTE STARTER #2 | Diamond Red TC | Black Onyx/Black Onyx | TDC&VE-VI | R202/ PVP/ Issue Investigation | 2022-10-06 | 2022-10-05 | 1 | 2022-08-30: B; 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: P; 2022-09-06: P; 2022-09-07: P; 2022-09-08: P; 2022-09-09: T; 2022-09-12: T; 2022-09-13: R; 2022-09-14: R; 2022-09-15: EOL; 2022-09-16: EOL; 2022-09-19: EE; 2022-09-20: EE; 2022-09-21: CAL&2.5MinsWL; 2022-09-22: 2H-WL; 2022-09-23: Camo.&Hunter & Headlamp; 2022-09-26: S&R; 2022-09-27: S&R; 2022-09-28: AL; 2022-09-29: SG/DCE; 2022-09-30: S/O; 2022-10-05: ATS
V | 15 | TT 10 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | Diamond Red TC | Black Onyx/(Medium Light Space Gray | TDC&VE-VI | R202/ PVP/ Issue Investigation/PV-Wind tunnel test | 2022-10-06 | 2022-10-05 | 1 | 2022-08-30: B; 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: P; 2022-09-06: P; 2022-09-07: P; 2022-09-08: BIP AL; 2022-09-09: T; 2022-09-12: T; 2022-09-13: R; 2022-09-14: R; 2022-09-15: EOL; 2022-09-16: EOL; 2022-09-19: EE; 2022-09-20: EE; 2022-09-21: CAL&2.5MinsWL; 2022-09-22: 2H-WL; 2022-09-23: Camo.&Hunter & Headlamp; 2022-09-26: S&R; 2022-09-27: S&R; 2022-09-28: AL; 2022-09-29: SG/DCE; 2022-09-30: S/O; 2022-10-05: ATS
V | 14 | TT 09 | China GAS |  |  | BASE (100A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | Lustrous Grey | Black Onyx/(Medium Light Space Gray | TDC&VE-VI | R202/ PVP/ Issue Investigation | 2022-10-06 | 2022-10-05 | 1 | 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: B; 2022-09-06: P; 2022-09-07: P; 2022-09-08: P; 2022-09-12: T; 2022-09-13: T; 2022-09-14: R; 2022-09-15: R; 2022-09-16: EOL; 2022-09-19: EOL; 2022-09-20: EE; 2022-09-21: CAL&2.5MinsWL; 2022-09-22: S&R; 2022-09-23: S&R; 2022-09-26: 2H-WL; 2022-09-27: Camo.&Hunter & Headlamp; 2022-09-28: M/F; 2022-09-29: BH8; 2022-09-30: S/O; 2022-10-05: ATS
V | 16 | TT 11 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | White Platinum Tri-Coat | Black Onyx/(Medium Light Space Gray | TDC&VE-VI | R202/ PVP/ Issue Investigation | 2022-10-06 | 2022-10-06 | 0 | 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: B; 2022-09-06: P; 2022-09-07: P; 2022-09-08: P; 2022-09-12: T; 2022-09-13: T; 2022-09-14: R; 2022-09-15: R; 2022-09-16: EOL; 2022-09-19: EOL; 2022-09-20: EE; 2022-09-21: CAL&2.5MinsWL; 2022-09-22: S&R; 2022-09-23: S&R; 2022-09-26: 2H-WL; 2022-09-27: Camo.&Hunter & Headlamp; 2022-09-28: AL; 2022-09-29: M/F; 2022-09-30: SG/DCE; 2022-10-05: S/O; 2022-10-06: ATS
V | 19 | TT 14 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 8.0 X 20" ALLOY WHL | AWD | SPORT VERSION PACK |  | Lustrous Grey | Black Onyx/Black Onyx | TDC&VE-VI | R202/ PVP/ Issue Investigation | 2022-10-06 | 2022-10-06 | 0 | 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: B; 2022-09-06: P; 2022-09-07: P; 2022-09-08: P; 2022-09-12: T; 2022-09-13: T; 2022-09-14: R; 2022-09-15: R; 2022-09-16: EOL; 2022-09-19: EOL; 2022-09-20: EE; 2022-09-21: CAL&2.5MinsWL; 2022-09-22: S&R; 2022-09-23: S&R; 2022-09-26: 2H-WL; 2022-09-27: Camo.&Hunter & Headlamp; 2022-09-28: ES 90; 2022-09-29: M/F; 2022-09-30: NTT; 2022-10-05: S/O; 2022-10-06: ATS
V | 42 | TT 37 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK |  | Agate Black Metalic#2 | Black Onyx/Black Onyx | REC-PMT5 | EQ Tunning,PEPS Clibration (+ 5 days) | 2022-10-14 | 2022-10-12 | 2 | 2022-08-31: B; 2022-09-01: B; 2022-09-02: B; 2022-09-05: B; 2022-09-06: P; 2022-09-07: P; 2022-09-08: P; 2022-09-12: T; 2022-09-13: T; 2022-09-14: R; 2022-09-15: R; 2022-09-16: EOL; 2022-09-19: EOL; 2022-09-20: EE; 2022-09-21: CAL&2.5MinsWL; 2022-09-22: 2H-WL; 2022-09-23: Camo.&Hunter & Headlamp; 2022-09-26: E-4P; 2022-09-27: E-4P; 2022-09-28: E-4P; 2022-09-29: S&R; 2022-09-30: S&R; 2022-10-05: FCPA dynamic; 2022-10-06: NTT; 2022-10-07: Deep track; 2022-10-08: ES; 2022-10-09: KOL; 2022-10-10: BH8; 2022-10-11: S/O; 2022-10-12: ATS
V | 21 | TT 16 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | White Platinum Tri-Coat | Black Onyx (19W)/Allura Blue | T&D VOCF | High mileage | 2022-10-12 | 2022-10-12 | 0 | 2022-09-01: B; 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: P; 2022-09-08: P; 2022-09-09: P; 2022-09-13: T; 2022-09-14: T; 2022-09-15: R; 2022-09-16: R; 2022-09-19: EOL; 2022-09-20: EOL; 2022-09-21: EE; 2022-09-22: CAL&2.5MinsWL; 2022-09-23: 2H-WL; 2022-09-26: Camo.&Hunter & Headlamp; 2022-09-27: S&R; 2022-09-28: S&R; 2022-09-29: E-4P; 2022-09-30: E-4P; 2022-10-05: E-4P; 2022-10-06: AL; 2022-10-07: M/F; 2022-10-08: SG/DCE; 2022-10-09: KOL; 2022-10-10: FCPA dynamic; 2022-10-11: S/O; 2022-10-12: ATS
V | 22 | TT 17 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | Blue Diamond | Black Onyx/(Medium Light Space Gray | T&D VOCF | High mileage | 2022-10-12 | 2022-10-12 | 0 | 2022-09-01: B; 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: P; 2022-09-08: P; 2022-09-09: P; 2022-09-13: T; 2022-09-14: T; 2022-09-15: R; 2022-09-16: R; 2022-09-19: EOL; 2022-09-20: EOL; 2022-09-21: EE; 2022-09-22: CAL&2.5MinsWL; 2022-09-23: 2H-WL; 2022-09-26: Camo.&Hunter & Headlamp; 2022-09-27: NTT; 2022-09-28: FER; 2022-09-29: FER; 2022-09-30: FER; 2022-10-05: FCPA dynamic; 2022-10-06: NTT; 2022-10-07: S&R; 2022-10-08: S&R; 2022-10-09: KOL; 2022-10-10: BH8; 2022-10-11: S/O; 2022-10-12: ATS
V | 29 | TT 24 | China GAS |  |  | BASE (100A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | Lustrous Grey | Black Onyx/(Medium Light Space Gray | T&D VOCF | Duty Cycle with Climate | 2022-10-12 | 2022-10-12 | 0 | 2022-09-01: B; 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: P; 2022-09-08: P; 2022-09-09: P; 2022-09-13: T; 2022-09-14: T; 2022-09-15: R; 2022-09-16: R; 2022-09-19: EOL; 2022-09-20: EOL; 2022-09-21: EE; 2022-09-22: CAL&2.5MinsWL; 2022-09-23: 2H-WL; 2022-09-26: Camo.&Hunter & Headlamp; 2022-09-27: ES; 2022-09-28: FER; 2022-09-29: FER; 2022-09-30: FER; 2022-10-05: S&R; 2022-10-06: S&R; 2022-10-07: KOL; 2022-10-08: NTT; 2022-10-09: FCPA dynamic; 2022-10-10: BH8; 2022-10-11: S/O; 2022-10-12: ATS
V | 30 | TT 25 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 8.0 X 20" ALLOY WHL | AWD | SPORT VERSION PACK |  | Diamond Red TC | Black Onyx/Black Onyx | T&D VOCF | Duty Cycle with Climate | 2022-10-12 | 2022-10-12 | 0 | 2022-09-01: B; 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: P; 2022-09-08: P; 2022-09-09: P; 2022-09-12: P; 2022-09-13: T; 2022-09-14: T; 2022-09-15: R; 2022-09-16: R; 2022-09-19: EOL; 2022-09-20: EOL; 2022-09-21: EE; 2022-09-22: CAL&2.5MinsWL; 2022-09-23: FCPA; 2022-09-26: FCPA; 2022-09-27: FCPA; 2022-09-28: FCPA; 2022-09-29: FCPA; 2022-09-30: 2H-WL; 2022-10-05: Camo.&Hunter & Headlamp; 2022-10-06: S&R; 2022-10-07: S&R; 2022-10-08: M/F; 2022-10-09: SG/DCE; 2022-10-10: ES 90; 2022-10-11: S/O; 2022-10-12: ATS
V | 31 | TT 26 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK | REMOTE STARTER #2 | White Platinum Tri-Coat | Black Onyx/Red Line (FR5) | T&D VOCF | Duty Cycle with Climate | 2022-10-12 | 2022-10-12 | 0 | 2022-09-01: B; 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: P; 2022-09-08: P; 2022-09-09: P; 2022-09-12: P; 2022-09-13: T; 2022-09-14: T; 2022-09-15: R; 2022-09-16: R; 2022-09-19: EOL; 2022-09-20: EOL; 2022-09-21: EE; 2022-09-22: CAL&2.5MinsWL; 2022-09-23: 2H-WL; 2022-09-26: Camo.&Hunter & Headlamp; 2022-09-27: S&R; 2022-09-28: S&R; 2022-09-29: FCPA dynamic; 2022-09-30: BH8; 2022-10-05: AL; 2022-10-06: AL; 2022-10-07: moving parts; 2022-10-08: ES; 2022-10-09: NTT; 2022-10-10: KOL; 2022-10-11: S/O; 2022-10-12: ATS
V | 32 | TT 27 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  | REMOTE STARTER #2 | Blue Diamond | Black Onyx/(Medium Light Space Gray | T&D VOCF | Duty Cycle with Climate | 2022-10-12 | 2022-10-11 | 1 | 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: P; 2022-09-09: P; 2022-09-12: P; 2022-09-14: T; 2022-09-15: T; 2022-09-16: R; 2022-09-19: R; 2022-09-20: EOL; 2022-09-21: EOL; 2022-09-22: EE; 2022-09-23: CAL&2.5MinsWL; 2022-09-26: 2H-WL; 2022-09-27: Camo.&Hunter & Headlamp; 2022-09-28: NTT; 2022-09-29: S&R; 2022-09-30: S&R; 2022-10-05: moving parts; 2022-10-06: FCPA dynamic; 2022-10-07: BH8; 2022-10-08: KOL; 2022-10-09: ES 90; 2022-10-10: S/O; 2022-10-11: ATS
V | 8 | TT 03 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | White Platinum Tri-Coat | Black Onyx (19W)/Allura Blue | TD&VE-TD | PV-PASCAR 1+2 | 2022-10-11 | 2022-10-11 | 0 | 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: P; 2022-09-09: P; 2022-09-12: P; 2022-09-14: T; 2022-09-15: T; 2022-09-16: R; 2022-09-19: R; 2022-09-20: EOL; 2022-09-21: EOL; 2022-09-22: EE; 2022-09-23: CAL&2.5MinsWL; 2022-09-26: 2H-WL; 2022-09-27: Camo.&Hunter & Headlamp; 2022-09-28: FER; 2022-09-29: FER; 2022-09-30: FER; 2022-10-05: ES; 2022-10-06: S&R; 2022-10-07: S&R; 2022-10-08: KOL; 2022-10-09: NTT; 2022-10-10: S/O; 2022-10-11: ATS
V | 39 | TT 34 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  | REMOTE STARTER #2 | Diamond Red TC | Black Onyx/(Medium Light Space Gray | REC-ECDX | Connected Features delivery test and validation | 2022-10-11 | 2022-10-11 | 0 | 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: P; 2022-09-09: P; 2022-09-12: P; 2022-09-14: T; 2022-09-15: T; 2022-09-16: R; 2022-09-19: R; 2022-09-20: EOL; 2022-09-21: EOL; 2022-09-22: EE; 2022-09-23: CAL&2.5MinsWL; 2022-09-26: 2H-WL; 2022-09-27: Camo.&Hunter & Headlamp; 2022-09-28: ES; 2022-09-29: S&R; 2022-09-30: S&R; 2022-10-05: Deep track; 2022-10-06: M/F; 2022-10-07: SG/DCE; 2022-10-08: KOL; 2022-10-09: NTT; 2022-10-10: S/O; 2022-10-11: ATS
V | 47 | TT 42 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | Blue Diamond | Black Onyx (19W)/Allura Blue | REC-MKT | Launch Support | 2022-10-10 | 2022-10-10 | 0 | 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: P; 2022-09-09: P; 2022-09-12: P; 2022-09-14: T; 2022-09-15: T; 2022-09-16: R; 2022-09-19: R; 2022-09-20: EOL; 2022-09-21: EOL; 2022-09-22: EE; 2022-09-23: FCPA; 2022-09-26: FCPA; 2022-09-27: FCPA; 2022-09-28: FCPA; 2022-09-29: FCPA; 2022-09-30: CAL&2.5MinsWL; 2022-10-05: 2H-WL; 2022-10-06: Camo.&Hunter & Headlamp; 2022-10-07: S&R; 2022-10-08: S&R; 2022-10-09: S/O; 2022-10-10: ATS
V | 48 | TT 43 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  | REMOTE STARTER #2 | Lustrous Grey | Black Onyx/(Medium Light Space Gray | REC-MKT | Launch Support | 2022-10-10 | 2022-10-10 | 0 | 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: P; 2022-09-09: P; 2022-09-12: P; 2022-09-14: T; 2022-09-15: T; 2022-09-16: R; 2022-09-19: R; 2022-09-20: EOL; 2022-09-21: EOL; 2022-09-22: EE; 2022-09-23: CAL&2.5MinsWL; 2022-09-26: 2H-WL; 2022-09-27: Camo.&Hunter & Headlamp; 2022-09-28: ES 90; 2022-09-29: S&R; 2022-09-30: S&R; 2022-10-05: NTT; 2022-10-06: ES; 2022-10-07: FCPA dynamic; 2022-10-08: KOL; 2022-10-09: S/O; 2022-10-10: ATS
V | 53 | TT 48 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK | REMOTE STARTER #2 | White Platinum | Black Onyx/Black Onyx | REC-MKT | Launch Support | 2022-10-10 | 2022-10-11 | -1 | 2022-09-02: B; 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: P; 2022-09-09: P; 2022-09-12: P; 2022-09-13: P; 2022-09-14: T; 2022-09-15: T; 2022-09-16: R; 2022-09-19: R; 2022-09-20: EOL; 2022-09-21: EOL; 2022-09-22: EE; 2022-09-23: CAL&2.5MinsWL; 2022-09-26: 8H-WL; 2022-09-27: 8H-WL; 2022-09-28: Camo.&Hunter & Headlamp; 2022-09-29: S&R; 2022-09-30: S&R; 2022-10-05: E-4P; 2022-10-06: E-4P; 2022-10-07: E-4P; 2022-10-08: FCPA dynamic; 2022-10-09: BH8; 2022-10-10: S/O; 2022-10-11: ATS
V | 45 | TT 40 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 8.0 X 20" ALLOY WHL | AWD | SPORT VERSION PACK |  | White Platinum Tri-Coat | Black Onyx/Red Line (FR5) | REC-ECDX | IVI SW validation | 2022-10-14 | 2022-10-11 | 3 | 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: P; 2022-09-12: P; 2022-09-13: P; 2022-09-14: P; 2022-09-15: T; 2022-09-16: T; 2022-09-19: R; 2022-09-20: R; 2022-09-21: EOL; 2022-09-22: EOL; 2022-09-23: EE; 2022-09-26: CAL&2.5MinsWL; 2022-09-27: 2H-WL; 2022-09-28: Camo.&Hunter & Headlamp; 2022-09-29: S&R; 2022-09-30: S&R; 2022-10-05: FCPA dynamic; 2022-10-06: BH8; 2022-10-07: ES 90; 2022-10-08: NTT; 2022-10-09: KOL; 2022-10-10: S/O; 2022-10-11: ATS
V | 46 | TT 41 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  | REMOTE STARTER #2 | Blue Diamond | Black Onyx/(Medium Light Space Gray | REC-ECDX | YFVE, Baidu Debug and Validation | 2022-10-14 | 2022-10-11 | 3 | 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: P; 2022-09-12: P; 2022-09-13: P; 2022-09-15: T; 2022-09-16: T; 2022-09-19: R; 2022-09-20: R; 2022-09-21: EOL; 2022-09-22: EOL; 2022-09-23: EE; 2022-09-26: CAL&2.5MinsWL; 2022-09-27: 2H-WL; 2022-09-28: Camo.&Hunter & Headlamp; 2022-09-29: S&R; 2022-09-30: S&R; 2022-10-05: FCPA dynamic; 2022-10-06: BH8; 2022-10-07: Deep track; 2022-10-08: M/F; 2022-10-09: SG/DCE; 2022-10-10: S/O; 2022-10-11: ATS
V | 34 | TT 29 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | Lustrous Grey | Black Onyx/(Medium Light Space Gray | ICV-sun xiuling | ICV software test | 2022-10-14 | 2022-10-10 | 4 | 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: P; 2022-09-12: P; 2022-09-13: P; 2022-09-15: T; 2022-09-16: T; 2022-09-19: R; 2022-09-20: R; 2022-09-21: EOL; 2022-09-22: EOL; 2022-09-23: EE; 2022-09-26: CAL&2.5MinsWL; 2022-09-27: 2H-WL; 2022-09-28: Camo.&Hunter & Headlamp; 2022-09-29: ES 90; 2022-09-30: NTT; 2022-10-05: S&R; 2022-10-06: S&R; 2022-10-07: ES 90; 2022-10-08: Shift Test; 2022-10-09: S/O; 2022-10-10: ATS
V | 35 | TT 30 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 8.0 X 20" ALLOY WHL | AWD | SPORT VERSION PACK |  | Diamond Red TC | Black Onyx/Red Line (FR5) | ICV-sun xiuling | ICV software test | 2022-10-14 | 2022-10-11 | 3 | 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: P; 2022-09-12: P; 2022-09-13: P; 2022-09-14: P; 2022-09-15: T; 2022-09-16: T; 2022-09-19: R; 2022-09-20: R; 2022-09-21: EOL; 2022-09-22: EOL; 2022-09-23: EE; 2022-09-26: CAL&2.5MinsWL; 2022-09-27: 2H-WL; 2022-09-28: Camo.&Hunter & Headlamp; 2022-09-29: ES; 2022-09-30: ES 90; 2022-10-05: S&R; 2022-10-06: Deep track; 2022-10-07: M/F; 2022-10-08: SG/DCE; 2022-10-09: KOL; 2022-10-10: S/O; 2022-10-11: ATS
V | 36 | TT 31 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | White Platinum Tri-Coat | Black Onyx (19W)/Allura Blue | CAF-EESE | ADAS test, issue investigation | 2022-10-14 | 2022-10-13 | 1 | 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: P; 2022-09-12: P; 2022-09-13: P; 2022-09-15: T; 2022-09-16: T; 2022-09-19: R; 2022-09-20: R; 2022-09-21: EOL; 2022-09-22: EOL; 2022-09-23: EE; 2022-09-26: CAL&2.5MinsWL; 2022-09-27: 2H-WL; 2022-09-28: Camo.&Hunter & Headlamp; 2022-09-29: S&R; 2022-09-30: S&R; 2022-10-05: E-4P; 2022-10-06: E-4P; 2022-10-07: E-4P; 2022-10-08: ES; 2022-10-09: KOL; 2022-10-10: NTT; 2022-10-11: ES 90; 2022-10-12: S/O; 2022-10-13: ATS
V | 37 | TT 32 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  | REMOTE STARTER #2 | Agate Black Metalic#2 | Black Onyx (19W)/Allura Blue | CAF-EESE | EESE module funtion sign-off | 2022-10-14 | 2022-10-12 | 2 | 2022-09-05: B; 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: P; 2022-09-12: P; 2022-09-13: P; 2022-09-15: T; 2022-09-16: T; 2022-09-19: R; 2022-09-20: R; 2022-09-21: EOL; 2022-09-22: EOL; 2022-09-23: EE; 2022-09-26: CAL&2.5MinsWL; 2022-09-27: 2H-WL; 2022-09-28: Camo.&Hunter & Headlamp; 2022-09-29: S&R; 2022-09-30: S&R; 2022-10-05: FCPA dynamic; 2022-10-06: BH8; 2022-10-07: moving parts; 2022-10-08: M/F; 2022-10-09: SG/DCE; 2022-10-10: ES 90; 2022-10-11: S/O; 2022-10-12: ATS
V | 43 | TT 38 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  | REMOTE STARTER #2 | Lustrous Grey | Black Onyx (19W)/Allura Blue | REC-PMT5 | ADAS ECU SW Validation; 360/RBA validation; iACC validation | 2022-10-14 | 2022-10-14 | 0 | 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: P; 2022-09-13: P; 2022-09-14: P; 2022-09-16: T; 2022-09-19: T; 2022-09-20: R; 2022-09-21: R; 2022-09-22: EOL; 2022-09-23: EOL; 2022-09-26: EE; 2022-09-27: CAL&2.5MinsWL; 2022-09-28: 2H-WL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: E-4P; 2022-10-05: E-4P; 2022-10-06: E-4P; 2022-10-07: S&R; 2022-10-08: S&R; 2022-10-09: ES; 2022-10-10: Deep track; 2022-10-11: Shift Test; 2022-10-12: KOL; 2022-10-13: S/O; 2022-10-14: ATS
V | 44 | TT 39 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK |  | Diamond Red TC | Black Onyx/Red Line (FR5) | REC-PMT5 | Relax feature validation;Vehicle KOL Test | 2022-10-14 | 2022-10-13 | 1 | 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: P; 2022-09-13: P; 2022-09-14: P; 2022-09-15: P; 2022-09-16: T; 2022-09-19: T; 2022-09-20: R; 2022-09-21: R; 2022-09-22: EOL; 2022-09-23: EOL; 2022-09-26: EE; 2022-09-27: CAL&2.5MinsWL; 2022-09-28: 2H-WL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: S&R; 2022-10-05: S&R; 2022-10-06: M/F; 2022-10-07: SG/DCE; 2022-10-08: ES 90; 2022-10-09: NTT; 2022-10-10: KOL; 2022-10-11: BH8; 2022-10-12: S/O; 2022-10-13: ATS
V | 50 | TT 45 | China GAS |  |  | RESERVE (102A) |  | 8F35 | 5 seat |  | AWD |  | REMOTE STARTER #2 | Agate Black Metalic#2 | Black Onyx (19W)/Allura Blue | REC-PMT5 | Feature Validation for MMOTA | 2022-10-14 | 2022-10-14 | 0 | 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: P; 2022-09-13: P; 2022-09-14: P; 2022-09-16: T; 2022-09-19: T; 2022-09-20: R; 2022-09-21: R; 2022-09-22: EOL; 2022-09-23: EOL; 2022-09-26: EE; 2022-09-27: CAL&2.5MinsWL; 2022-09-28: 2H-WL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: ES; 2022-10-05: S&R; 2022-10-06: S&R; 2022-10-07: E-4P; 2022-10-08: E-4P; 2022-10-09: E-4P; 2022-10-10: ES 90; 2022-10-11: FCPA dynamic; 2022-10-12: BH8; 2022-10-13: S/O; 2022-10-14: ATS
V | 51 | TT 46 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK |  | Lustrous Grey | Black Onyx/Red Line (FR5) | REC-PMT5 | Feature Validation for MMOTA | 2022-10-14 | 2022-10-13 | 1 | 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: P; 2022-09-13: P; 2022-09-14: P; 2022-09-15: P; 2022-09-16: T; 2022-09-19: T; 2022-09-20: R; 2022-09-21: R; 2022-09-22: EOL; 2022-09-23: EOL; 2022-09-26: EE; 2022-09-27: CAL&2.5MinsWL; 2022-09-28: 2H-WL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: ES; 2022-10-05: S&R; 2022-10-06: S&R; 2022-10-07: FCPA dynamic; 2022-10-08: BH8; 2022-10-09: M/F; 2022-10-10: SG/DCE; 2022-10-11: FCPA dynamic; 2022-10-12: S/O; 2022-10-13: ATS
V | 52 | TT 47 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  | REMOTE STARTER #2 | Diamond Red TC | Black Onyx/(Medium Light Space Gray | REC-PMT5 | Feature Validation for MMOTA | 2022-10-14 | 2022-10-13 | 1 | 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: P; 2022-09-13: P; 2022-09-14: P; 2022-09-16: T; 2022-09-19: T; 2022-09-20: R; 2022-09-21: R; 2022-09-22: EOL; 2022-09-23: EOL; 2022-09-26: EE; 2022-09-27: CAL&2.5MinsWL; 2022-09-28: 2H-WL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: ES; 2022-10-05: S&R; 2022-10-06: S&R; 2022-10-07: FCPA dynamic; 2022-10-08: BH8; 2022-10-09: Shift Test; 2022-10-10: NTT; 2022-10-11: KOL; 2022-10-12: S/O; 2022-10-13: ATS
V | 7 | TT 02 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK | REMOTE STARTER #2 | Lustrous Grey | Black Onyx/Black Onyx | TD&VE-TD | PV-CCSE/VD | 2022-10-14 | 2022-10-14 | 0 | 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: P; 2022-09-13: P; 2022-09-14: P; 2022-09-15: P; 2022-09-16: T; 2022-09-19: T; 2022-09-20: R; 2022-09-21: R; 2022-09-22: EOL; 2022-09-23: EOL; 2022-09-26: EE; 2022-09-27: CAL&2.5MinsWL; 2022-09-28: 2H-WL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: ES 90; 2022-10-05: S&R; 2022-10-06: S&R; 2022-10-07: Deep track; 2022-10-08: FCPA dynamic; 2022-10-09: ES; 2022-10-10: M/F; 2022-10-11: SG/DCE; 2022-10-12: KOL; 2022-10-13: S/O; 2022-10-14: ATS
B | 57 | TT BIW 03 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | Bodyshop |  |  |  | 0 | 2022-09-06: B; 2022-09-07: B; 2022-09-08: B; 2022-09-09: P; 2022-09-12: TearDown
V | 11 | TT 06 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 8.0 X 20" ALLOY WHL | AWD | SPORT VERSION PACK |  | Diamond Red TC | Black Onyx/Red Line (FR5) | TD&VE-TD | PV-Pre CNCAP | 2022-10-18 | 2022-10-13 | 5 | 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: P; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-19: T; 2022-09-20: T; 2022-09-21: R; 2022-09-22: R; 2022-09-23: EOL; 2022-09-26: EOL; 2022-09-27: EE; 2022-09-28: CAL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: ES; 2022-10-05: ES 90; 2022-10-06: NTT; 2022-10-07: M/F; 2022-10-08: SG/DCE; 2022-10-09: Deep track; 2022-10-10: BH8; 2022-10-11: KOL; 2022-10-12: S/O; 2022-10-13: ATS
V | 12 | TT 07 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | Blue Diamond | Black Onyx (19W)/Allura Blue | TD&VE-TD | PV-Pre CNCAP | 2022-10-17 | 2022-10-09 | 8 | 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: P; 2022-09-14: P; 2022-09-15: P; 2022-09-19: T; 2022-09-20: T; 2022-09-21: R; 2022-09-22: R; 2022-09-23: EOL; 2022-09-26: EOL; 2022-09-27: EE; 2022-09-28: CAL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: ES; 2022-10-05: NTT; 2022-10-06: ES 90; 2022-10-07: KOL; 2022-10-08: S/O; 2022-10-09: ATS
V | 13 | TT 08 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 8.0 X 20" ALLOY WHL | AWD | SPORT VERSION PACK |  | White Platinum Tri-Coat | Black Onyx/Black Onyx | TD&VE-TD | PV-Pre CNCAP | 2022-10-18 | 2022-10-10 | 8 | 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: P; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-19: T; 2022-09-20: T; 2022-09-21: R; 2022-09-22: R; 2022-09-23: EOL; 2022-09-26: EOL; 2022-09-27: EE; 2022-09-28: CAL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: ES; 2022-10-05: ES 90; 2022-10-06: FCPA dynamic; 2022-10-07: M/F; 2022-10-08: NTT; 2022-10-09: S/O; 2022-10-10: ATS
V | 17 | TT 12 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 8.0 X 20" ALLOY WHL | AWD | SPORT VERSION PACK |  | White Platinum Tri-Coat | Black Onyx/Red Line (FR5) | TD&VE-Homo | PV-Pre CIASI | 2022-10-19 | 2022-10-12 | 7 | 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: P; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-19: T; 2022-09-20: T; 2022-09-21: R; 2022-09-22: R; 2022-09-23: EOL; 2022-09-26: EOL; 2022-09-27: EE; 2022-09-28: CAL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: NTT; 2022-10-05: ES; 2022-10-06: ES 90; 2022-10-07: M/F; 2022-10-08: SG/DCE; 2022-10-09: KOL; 2022-10-10: NTT; 2022-10-11: S/O; 2022-10-12: ATS
V | 18 | TT 13 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | Agate Black Metalic#2 | Black Onyx (19W)/Allura Blue | TD&VE-Homo | PV-Pre CIASI | 2022-10-21 | 2022-10-10 | 11 | 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: P; 2022-09-14: P; 2022-09-15: P; 2022-09-19: T; 2022-09-20: T; 2022-09-21: R; 2022-09-22: R; 2022-09-23: EOL; 2022-09-26: EOL; 2022-09-27: EE; 2022-09-28: CAL; 2022-09-29: Camo.&Hunter & Headlamp; 2022-09-30: ES 90; 2022-10-05: ES; 2022-10-06: KOL; 2022-10-07: NTT; 2022-10-08: BH8; 2022-10-09: S/O; 2022-10-10: ATS
V | 38 | TT 33 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK |  | Lustrous Grey | Black Onyx/Red Line (FR5) | BEX - Xu Hangang | Moonroof dynamic calibration at Dianjiang, two days usage, test cost 32,000RMB | 2022-10-19 | 2022-10-17 | 2 | 2022-09-07: B; 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: P; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-19: T; 2022-09-20: T; 2022-09-21: R; 2022-09-22: R; 2022-09-23: EOL; 2022-09-26: EOL; 2022-09-27: EE; 2022-09-28: CAL&2.5MinsWL; 2022-09-29: 2H-WL; 2022-09-30: Camo.&Hunter & Headlamp; 2022-10-05: AL; 2022-10-06: S&R; 2022-10-07: S&R; 2022-10-08: E-4P; 2022-10-09: E-4P; 2022-10-10: E-4P; 2022-10-11: Shift Test; 2022-10-12: FCPA dynamic; 2022-10-13: BH8; 2022-10-14: S/O; 2022-10-17: ATS
V | 23 | TT 18 | China GAS |  |  | BASE (100A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | Blue Diamond | Black Onyx/(Medium Light Space Gray | T&D VOCF | Duty Cycle/VOC/PV-Emission&F.E Pre-COP | 2022-10-25 | 2022-10-18 | 7 | 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-20: T; 2022-09-21: T; 2022-09-22: R; 2022-09-23: R; 2022-09-26: EOL; 2022-09-27: EOL; 2022-09-28: EE; 2022-09-29: CAL&2.5MinsWL; 2022-09-30: FCPA; 2022-10-05: FCPA; 2022-10-06: FCPA; 2022-10-07: FCPA; 2022-10-08: FCPA; 2022-10-09: 2H-WL; 2022-10-10: Camo.&Hunter & Headlamp; 2022-10-11: S&R; 2022-10-12: S&R; 2022-10-13: Deep track; 2022-10-14: moving parts; 2022-10-17: S/O; 2022-10-18: ATS
V | 24 | TT 19 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 8.0 X 20" ALLOY WHL | AWD | SPORT VERSION PACK |  | Agate Black Metalic#2 | Black Onyx/Red Line (FR5) | T&D VOCF | Duty Cycle/ VOC/ PV-Emission&F.E Pre-COP | 2022-10-24 | 2022-10-18 | 6 | 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-20: T; 2022-09-21: T; 2022-09-22: R; 2022-09-23: R; 2022-09-26: EOL; 2022-09-27: EOL; 2022-09-28: EE; 2022-09-29: CAL&2.5MinsWL; 2022-09-30: 8H-WL; 2022-10-05: 8H-WL; 2022-10-06: Camo.&Hunter & Headlamp; 2022-10-07: AL; 2022-10-08: S&R; 2022-10-09: S&R; 2022-10-10: M/F; 2022-10-11: SG/DCE; 2022-10-12: ANC; 2022-10-13: FCPA dynamic; 2022-10-14: BH8; 2022-10-17: S/O; 2022-10-18: ATS
V | 25 | TT 20 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | Lustrous Grey | Black Onyx (19W)/Allura Blue | T&D VOCF | Duty Cycle | 2022-10-24 | 2022-10-18 | 6 | 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-20: T; 2022-09-21: T; 2022-09-22: R; 2022-09-23: R; 2022-09-26: EOL; 2022-09-27: EOL; 2022-09-28: EE; 2022-09-29: CAL&2.5MinsWL; 2022-09-30: 8H-WL; 2022-10-05: 8H-WL; 2022-10-06: Camo.&Hunter & Headlamp; 2022-10-07: S&R; 2022-10-08: S&R; 2022-10-09: ES 90; 2022-10-10: moving parts; 2022-10-11: FCPA dynamic; 2022-10-12: BH8; 2022-10-13: M/F; 2022-10-14: SG/DCE; 2022-10-17: S/O; 2022-10-18: ATS
V | 26 | TT 21 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK | REMOTE STARTER #2 | White Platinum Tri-Coat | Black Onyx/Red Line (FR5) | T&D VOCF | Duty Cycle/ VOC/ PV-Emission&F.E Pre-COP | 2022-10-24 | 2022-10-17 | 7 | 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-19: P; 2022-09-20: T; 2022-09-21: T; 2022-09-22: R; 2022-09-23: R; 2022-09-26: EOL; 2022-09-27: EOL; 2022-09-28: EE; 2022-09-29: CAL&2.5MinsWL; 2022-09-30: 2H-WL; 2022-10-05: Camo.&Hunter & Headlamp; 2022-10-06: AL; 2022-10-07: S&R; 2022-10-08: S&R; 2022-10-09: E-4P; 2022-10-10: E-4P; 2022-10-11: E-4P; 2022-10-12: ES; 2022-10-13: ES 90; 2022-10-14: S/O; 2022-10-17: ATS
V | 27 | TT 22 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | Blue Diamond | Black Onyx/(Medium Light Space Gray | T&D VOCF | Duty Cycle | 2022-10-24 | 2022-10-17 | 7 | 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-19: BIP AL; 2022-09-20: T; 2022-09-21: T; 2022-09-22: R; 2022-09-23: R; 2022-09-26: EOL; 2022-09-27: EOL; 2022-09-28: EE; 2022-09-29: CAL&2.5MinsWL; 2022-09-30: 2H-WL; 2022-10-05: Camo.&Hunter & Headlamp; 2022-10-06: AL; 2022-10-07: S&R; 2022-10-08: S&R; 2022-10-09: ES; 2022-10-10: FCPA dynamic; 2022-10-11: BH8; 2022-10-12: KOL; 2022-10-13: NTT; 2022-10-14: S/O; 2022-10-17: ATS
V | 28 | TT 23 | China GAS |  |  | BASE (100A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | Agate Black Metalic#2 | Black Onyx/(Medium Light Space Gray | T&D VOCF | Duty Cycle | 2022-10-24 | 2022-10-20 | 4 | 2022-09-08: B; 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: P; 2022-09-15: P; 2022-09-16: P; 2022-09-20: T; 2022-09-21: T; 2022-09-22: R; 2022-09-23: R; 2022-09-26: EOL; 2022-09-27: EOL; 2022-09-28: EE; 2022-09-29: CAL&2.5MinsWL; 2022-09-30: 2H-WL; 2022-10-05: Camo.&Hunter & Headlamp; 2022-10-06: S&R; 2022-10-07: S&R; 2022-10-08: E-4P; 2022-10-09: E-4P; 2022-10-10: E-4P; 2022-10-11: ES 90; 2022-10-12: FCPA dynamic; 2022-10-13: BH8; 2022-10-14: Shift Test; 2022-10-17: NTT; 2022-10-18: KOL; 2022-10-19: S/O; 2022-10-20: ATS
V | 33 | TT 28 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK |  | Agate Black Metalic#2 | Black Onyx/Black Onyx | PT (PCCN Chen Shi) | PV test/ PCCN verification/HCT/HAT/CCT | 2022-10-30 | 2022-10-20 | 10 | 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: B; 2022-09-15: P; 2022-09-16: P; 2022-09-19: P; 2022-09-21: T; 2022-09-22: T; 2022-09-23: R; 2022-09-26: R; 2022-09-27: EOL; 2022-09-28: EOL; 2022-09-29: EE; 2022-09-30: CAL&2.5MinsWL; 2022-10-05: 2H-WL; 2022-10-06: Camo.&Hunter & Headlamp; 2022-10-07: AL; 2022-10-08: ES 90; 2022-10-09: NTT; 2022-10-10: S&R; 2022-10-11: S&R; 2022-10-12: KOL; 2022-10-13: FCPA dynamic; 2022-10-14: Deep track; 2022-10-17: BH8; 2022-10-18: ANC; 2022-10-19: S/O; 2022-10-20: ATS
V | 9 | TT 04 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD | SPORT VERSION PACK | REMOTE STARTER #2 | White Platinum Tri-Coat | Black Onyx/Red Line (FR5) | TD&VE-TD | PV-KLT | 2022-10-30 | 2022-10-17 | 13 | 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: B; 2022-09-15: P; 2022-09-16: P; 2022-09-19: P; 2022-09-20: P; 2022-09-21: T; 2022-09-22: T; 2022-09-23: R; 2022-09-26: R; 2022-09-27: EOL; 2022-09-28: EOL; 2022-09-29: EE; 2022-09-30: CAL&2.5MinsWL; 2022-10-05: 2H-WL; 2022-10-06: Camo.&Hunter & Headlamp; 2022-10-07: AL; 2022-10-08: S&R; 2022-10-09: S&R; 2022-10-10: ES; 2022-10-11: NTT; 2022-10-12: KOL; 2022-10-13: moving parts; 2022-10-14: S/O; 2022-10-17: ATS
V | 54 | TT 49 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | Agate Black Metalic#2 | Black Onyx (19W)/Allura Blue | TD&VE-TD | PV-Sunload | 2022-10-30 | 2022-10-20 | 10 | 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: B; 2022-09-15: P; 2022-09-16: P; 2022-09-19: P; 2022-09-21: T; 2022-09-22: T; 2022-09-23: R; 2022-09-26: R; 2022-09-27: EOL; 2022-09-28: EOL; 2022-09-29: EE; 2022-09-30: FCPA; 2022-10-05: FCPA; 2022-10-06: FCPA; 2022-10-07: FCPA; 2022-10-08: FCPA; 2022-10-09: CAL&2.5MinsWL; 2022-10-10: 2H-WL; 2022-10-11: Camo.&Hunter & Headlamp; 2022-10-12: S&R; 2022-10-13: S&R; 2022-10-14: E-4P; 2022-10-17: E-4P; 2022-10-18: E-4P; 2022-10-19: S/O; 2022-10-20: ATS
V | 6 | TT 01 | China GAS |  |  | RESERVE (102A) | 2.0T GAS | 8F35 | 5 seat |  | AWD |  |  | Agate Black Metalic#2 | Black Onyx/(Medium Light Space Gray | TD&VE-TD | PV-SW Fleet test | 2022-10-30 | 2022-10-20 | 10 | 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: B; 2022-09-15: P; 2022-09-16: P; 2022-09-19: P; 2022-09-21: T; 2022-09-22: T; 2022-09-23: R; 2022-09-26: R; 2022-09-27: EOL; 2022-09-28: EOL; 2022-09-29: EE; 2022-09-30: CAL&2.5MinsWL; 2022-10-05: 2H-WL; 2022-10-06: Camo.&Hunter & Headlamp; 2022-10-07: ES; 2022-10-08: S&R; 2022-10-09: S&R; 2022-10-10: FCPA dynamic; 2022-10-11: BH8; 2022-10-12: NTT; 2022-10-13: ANC; 2022-10-14: ANC; 2022-10-17: ANC; 2022-10-18: KOL; 2022-10-19: S/O; 2022-10-20: ATS
V | 10 | TT 05 | China GAS |  |  | SELECT (101A) | 2.0T GAS | 8F35 | 5 seat | 20" STYLE 5 | AWD |  |  | Lustrous Grey | Black Onyx/(Medium Light Space Gray | TD&VE-TD | PV-Pre CNCAP | 2022-10-30 | 2022-10-19 | 11 | 2022-09-09: B; 2022-09-12: B; 2022-09-13: B; 2022-09-14: B; 2022-09-15: P; 2022-09-16: P; 2022-09-19: P; 2022-09-21: T; 2022-09-22: T; 2022-09-23: R; 2022-09-26: R; 2022-09-27: EOL; 2022-09-28: EOL; 2022-09-29: EE; 2022-09-30: CAL&2.5MinsWL; 2022-10-05: 2H-WL; 2022-10-06: Camo.&Hunter & Headlamp; 2022-10-07: ES 90; 2022-10-08: NTT; 2022-10-09: ANC; 2022-10-10: ANC; 2022-10-11: ANC; 2022-10-12: S&R; 2022-10-13: S&R; 2022-10-14: Deep track; 2022-10-17: KOL; 2022-10-18: S/O; 2022-10-19: ATS
B | 58 | TT BIW 04 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | Bodyshop |  |  |  | 0 | bar: 2022-09-12 to 2022-09-15
B | 59 | TT BIW 05 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | Bodyshop |  |  |  | 0 | bar: 2022-09-12 to 2022-09-15
B | 60 | TT BIW 06 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | Bodyshop |  |  |  | 0 | bar: 2022-09-12 to 2022-09-15
B | 62 | TT BIW 08 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | Paint |  |  |  | 0 | bar: 2022-09-12 to 2022-09-16
B | 63 | TT BIW 09 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | Paint |  |  |  | 0 | bar: 2022-09-12 to 2022-09-16
B | 64 | TT BIW 10 | China GAS |  |  |  |  | 8F35 | 5 seat |  | AWD |  |  |  |  | Paint |  |  |  | 0 | bar: 2022-09-12 to 2022-09-16
[21 empty] | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
 | time axis 2022-07-23 to 2022-11-19
Formulas:
Build Deliv. Date = HLOOKUP("ATS",[Fri]:FO168,ROW(V78)-ROW([Usage])+1,0)

## CDX707DCV On-Site Support Plan (hidden)
ChongQing CDX707 Gas&FHEV DCV Build Phase（176*DCV vehicles） On-site Team Roster- In Spet.
period | Details | [7 empty] | Contact Window
[9 empty] | IVI |  |  |  | CAF PD |  |  | Baidu |  |  | TS |  |  | inhouse |  |  | YFVE
| Task based on Gas L-DCV2.1 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | Lead | Support | Email | Tel | Lead | Email | Tel | Lead | Email | Tel | Lead | Email | Tel | Lead | Email | Tel | Lead | Email | Tel
01/24-01/28 | YB/P | 5 | 6 | 6 | 6 | 4 | Spring Festival |  | Xu, Roger Xiang, Zhengxi |  |  |  | Wang, Yuanpeng Qian, Yan |  |  | Tian, Niu | [8 empty] | Huo, Dongchen | dhuo2@yfve.com.cn | 13207572880
| EE |  | 1 |  |  | 1
Gas L-DCV2.1 update on 1/24
2/7--02/13 | Task based on L-DCV2.1 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | Zhou, Jiajia | Chen, Deyin | jzhou101@ford.com | 15105166366 |  |  |  | 燕辉 Tian, Niu | v_yanhui02@baidu.com | +86 15320659069 | Cai,Yucao Zhu, Hao |  | 15251743953 | Zheng,wei | Zheng, Wei (W.) <WZHENG27@ford.com> |  | HUANG FENG | fhuang9@yfve.com.cn | fhuang9@yfve.com.cn
| YB/P | 6 | 5 | 6 | 7 | 6
| EE | 1 | 2 | 3 | 2 | 2
| NTT | [6 empty] | 1
2/14-2/20 | Task based on Gas L-DCV2.1 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | Zhou, Jiajia Zhang, Yipeng | Li, Xuedong | jzhou101@ford.com YZHAN482@ford.com | Zhang, Yipeng: 15195990203 |  |  |  | 燕辉 | v_yanhui02@baidu.com | +86 15320659069 | Zhu,Hao |  | 13218062980 |  |  |  | Liu, Zike HuangFeng | ysong20@yfve.com.cn | Liu, Zike: 18655216230 HuangFeng: 13166210801
| YB/P | 7 | 6 | 7 | 8 | 8
| EE | 3 | 4 | 4 | 3 | 3
| NTT | [6 empty] | 1
| FCPA |  |  |  |  | 2 | 2 | 2
2/21-2/27 | Task based on Gas L-DCV3 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | Chen, Weidi | Xiang, Zhengxi | WCHEN154@ford.com |  |  |  |  | 燕辉 | v_yanhui02@baidu.com | +86 15320659069 |  |  |  | Meng,tao | Meng, Tao (T.) <TMENG1@ford.com> |  | Huo, Dongchen Zheng, Qingchao | ysong20@yfve.com.cn | 18505532210
| YB/P | 6 | 6 | 4 | 5 | 3
| EE | 3 | 3 | 2 | 3 | 2
| NTT |  |  | 1 | 1 | 1 |  | 3
| FCPA | 2 | 2
| FCPA Dynamic |  | 2 |  |  | 1 | 1
Gas L-DCV3 update on 2/21
2/28-3/6 | Task based on Gas L-DCV3 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 |  | Huang, Xue | SLIU141@ford.com | 18068814635 |  |  |  | 燕辉 | v_yanhui02@baidu.com | +86 15320659069 | Wu, Yu |  | 19852816098 |  |  |  |  | ysong20@yfve.com.cn | 18505532210
| YB/P | 4 | 6 | 8 | 9 | 8
| EE | 4 | 3 | 3 | 3 | 3 | 1
| NTT | 1 | 2 | 1 |  | 1 | 2
| FCPA Dynamic | 3 | 2 | 3 | 3 | 1 | 1
3/7-3/13 | Task based on Gas L-DCV3 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | Liu, Shiwang | Zhang, Ying | MXIA13@ford.com |  |  |  |  | 燕辉 | v_yanhui02@baidu.com | +86 15320659069 | Wu, Yu |  |  | Zhu,jialin | Zhu, Jialin (J.) <JZHU79@ford.com> |  | Jin, Guangcheng | ysong20@yfve.com.cn | 18505532210
| YB/P | 6 | 4 | 1 |  | 1
| EE | 2 | 3 | 2 | 2
NTT
| FCPA | [6 empty] | 1
| FCPA SG/DC | [6 empty] | 1
| FCPA Dynamic | 2 | 3 | 2 | 1 | 1
3/14-3/20 | Task based on Gas L-DCV3, FHEV DCV3 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 |  | Yang, Hanhan | MXIA13@ford.com |  |  |  |  | 燕辉 | v_yanhui02@baidu.com | +86 15320659069 | [6 empty] | SONG YANQING | ysong20@yfve.com.cn | 18505532210
| YB/P | 3 | 6 | 8 | 8 | 5
| EE |  | 3 | 3 | 3 | 3 | 3
| NTT | 1
| FCPA | 2 | 2 | 2 | 2
| FCPA Dynamic | 1 | 2 | 2 | 1 | 1 |  | 1
3/21-3/27 | Task based on Gas L-DCV3, FHEV DCV3 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 |  | Xia, Xiaojin | CNIU@ford.com |  |  |  |  | 燕辉 | v_yanhui02@baidu.com | +86 15320659069 |  |  |  |  | Xu, Min (M.) <MXU40@ford.com> |  | Jin, Guangcheng | fhuang9@yfve.com.cn | fhuang9@yfve.com.cn
| YB/P | 2
| EE | 1
| NTT | [6 empty] | 1
| FCPA Dynamic |  | 1 | 1 | 1 | 1 |  | 1
3/28-4/3 | Task based on Gas L-DCV4, FHEV DCV3 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | Sun, Jun | Wang, Xi | JSUN62@ford.com |  |  |  |  | 燕辉 | v_yanhui02@baidu.com | +86 15320659069 |  |  |  | Xu,min (TBC) |  | ` | Jin, Guangcheng | ysong20@yfve.com.cn | 18505532210
| YB/P | [6 empty] | Ching Ming Festival
| EE |  | 3 | 3 | 3
| NTT | 1
| FCPA Dynamic | 1
Gas L-DCV4 update on 3/28
4/4-4/10 | Task based on Gas L-DCV4 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | TBD | Wang, Peng | PWANG75@ford.com |  |  |  |  | 燕辉 | v_yanhui02@baidu.com | +86 15320659069 |  |  |  | chai,yi | Chai, Yi (Y.) <YCHAI2@ford.com> |  | SONG YANQING | ysong20@yfve.com.cn | 18505532210
| EE | Ching Ming Festival |  | 1
| EE/PT |  |  | 1
| FCPA |  |  | 2 | 2 | 2
| FCPA Dynamic |  |  |  |  | 1 |  | 1
4/11-4/17 | Task based on Gas L-DCV4 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | Gao, Ling | Niu, Chun | DCHEN96@ford.com |  |  |  |  | 燕辉 | v_yanhui02@baidu.com | +86 15320659069 | [6 empty] | SONG YANQING | ysong20@yfve.com.cn | 18505532210
| FCPA | 2 | 2
| FCPA Dynamic |  | 1 | 1 | 1

## CDX707 EPTTT OnSite SupportPlan
ChongQing CDX707 Gas&FHEV EPTTT Build Phase（176*DCV vehicles） On-site Team Roster- In Spet.
period | Details | [7 empty] | Contact Window
[9 empty] | IVI |  |  |  | CAF PD/ICV |  |  | Baidu |  |  | TS |  |  | Tech Operation(include inhouse App) |  |  | YFVE
| Task based on R05.1 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | Lead | Support/Validation | Email | Tel | Lead | Email | Tel | Lead | Email | Tel | Lead | Email | Tel | Lead | Email | Tel | Lead | Email | Tel
09/05-09/11 | EOL | 2 | 2 | 2 | 2 | 2 |  |  | Huang, Xue Qi, Ronggui |  | XHUANG93@ford.com |  | wang, yuanpeng |  | 18696670412 | \ |  |  | \ | [5 empty] | huo, dongcheng huang,feng
09/12--09/18 | Task based on R05.1 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 |  |  | RQI2@ford.com |  |  |  |  | \ |  |  | \ |  |  | Zhu Chenyang Zhang, Xiaojing | czhu38@ford.com
| EOL |  | 2 | 5 | 8 | 12 | 1 | 1
| EE | 2 | 2
09/19-09/25 | Task based on R05.1 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | Qi, Ronggui (till 28-Sep) Zhang, Yipeng | Su, Zhijun | ZSU13@ford.com | [7 empty] | yuchao | caiyc0619@thundersoft.com | 15251743953 | Zhu Chenyang | czhu38@ford.com |  | 1系统+1仪表+QA
| EOL | 10 | 12 | 13 | 13 | 13 | 1 | 1
| EE | 7 | 11 | 5 | 6 | 6
| FCPA |  |  | 2 | 2 | 4
| FCPA dynamic |  |  |  | 1
| NTT |  |  |  |  | 1
09/26-10/02 | Task based on R05.1/R06 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 |  | Chen, Deyin | DCHEN96@ford.com |  | Fiona | [5 empty] | yuchao | caiyc0619@thundersoft.com | 15251743953 | Zhu Chenyang | czhu38@ford.com
| EOL | 13 | 12 | 5
| EE | 6 | 6 | 7 | 6
| FCPA | 4 | 4 | 2 | 2 | 2
| FCPA dynamic |  |  |  | 2
| NTT | 1 | 1 | 1 |  | 4
R06 update on 09/30
10/3-10/09 | Task based on R06 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | Zhang, Yipeng (till 7-Oct) Su,Zhijun | Zhao Ruijiang | ZSU13@ford.com | 18670368610 | Fiona | [5 empty] | zhuhao | zhuhao0701@thundersoft.com | 13218062980 | Xu Luwei/Zhu Chenyang | lxu105@ford.com czhu38@ford.com |  | 1系统+1仪表+QA
| FCPA |  |  | 2 | 2 | 2 | 2
| FCPA dynamic |  |  | 5 | 2 | 4 | 2 | 1
| NTT |  |  | 2 | 4 | 1 | 5 | 5
10/10-10/16 | Task based on R06 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 |  | Wang Peng | ZSU13@ford.com | 18670368610 | Fiona | [5 empty] | zhuhao | zhuhao0701@thundersoft.com | 13218062980 | Xu Luwei | lxu105@ford.com |  | 1系统+1仪表+QA
| FCPA dynamic | 3 | 3 | 2 | 2
| NTT | 3 | 1 | 1 | 1
10/17-10/23 | Task based on R06 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | Su,Zhijun 出差杭州 | Liu Binze | ZSU13@ford.com | 18670368610 |  |  |  | 导航标定 | [5 empty] | Xu Luwei | lxu105@ford.com |  | 1系统+1QA
| NTT | 1
| VOCF (Test site:CQ/Lhasa/Hainan) |  |  |  |  | 2 -Lhasa 2 -Hainan | 2 -CQ 2 -Lhasa 2 -Hainan | 2 -CQ 2 -Lhasa 2 -Hainan
R202
10/24-11/10 | Task based on R06 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 29-Oct ~ 10-Nov |  |  | Liu Shiwang | ZSU13@ford.com | 18670368610 |  |  |  | 导航标定 | [8 empty] | 1系统+1QA
| VOCF (Test site:CQ/HZ/Lhasa/Hainan) | 2 -CQ 2 -Lhasa 2 -Hainan | 2 -CQ 2 -Lhasa 2 -Hainan | 2 -CQ 3 -HZ 2 -Lhasa 2 -Hainan | 2 -CQ 5 -HZ 2 -Lhasa 2 -Hainan | 2 -CQ 5 -HZ 2 -Lhasa 2 -Hainan | 2 -CQ 6 -HZ 2 -Lhasa 2 -Hainan
R202
11/11-1/29/2023 | Task based on R06 | 11-Nov ~1-Dec |  |  | 2-Dec ~ 3-Dec |  | 4-Dec ~ 29-Jan-2023 |  |  | Meng Bin | ZSU13@ford.com | 18670368610 |  |  |  | 导航标定 | [8 empty] | 1系统+1QA
| VOCF (Test site:CQ/HZ) | 2 -CQ |  |  | 2 -CQ 2 -HZ |  | 2 -CQ
R202
R06.1 update on 11/11

## CDX707 TT VOCF
|  |  | plan del | Recovery KM plan
|  |  | act del | 660
[7 empty] | Test site | HZ 8000 | CQ 60000 | Lhasa 12800 | Hainan 12800 | Yakeshi 12800
Tag | VIN | Series | Engine | Fleet Activity | Test site |  | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
 | time axis 2022-10-15 to 2023-01-29
TT 16 | 0 | CN 102A | 2.0T Gas |  | CQ 60000 | Target | [7 empty] | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Target Accu | [7 empty] | 660 | 1320 | 1980 | 2640 | 3300 | 3960 | 4620 | 5280 | 5940 | 6600 | 7260 | 7920 | 8580 | 9240 | 9900 | 10560 | 11220 | 11880 | 12540 | 13200 | 13860 | 14520 | 15180 | 15840 | 16500 | 17160 | 17820 | 18480 | 19140 | 19800 | 20460 | 21120 | 21780 | 22440 | 23100 | 23760 | 24420 | 25080 | 25740 | 26400 | 27060 | 27720 | 28380 | 29040 | 29700 | 30360 | 31020 | 31680 | 32340 | 33000 | 33660 | 34320 | 34980 | 35640 | 36300 | 36960 | 37620 | 38280 | 38940 | 39600 | 40260 | 40920 | 41580 | 42240 | 42900 | 43560 | 44220 | 44880 | 45540 | 46200 | 46860 | 47520 | 48180 | 48840 | 49500 | 50160 | 50820 | 51480 | 52140 | 52800 | 53460 | 54120 | 54780 | 55440 | 56100 | 56760 | 57420 | 58080 | 58740 | 59400 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
Actual Accu
Status
TT 17 | 0 | CN 101A | 2.0T Gas |  | CQ 60000 | Target | [7 empty] | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Target Accu | [7 empty] | 660 | 1320 | 1980 | 2640 | 3300 | 3960 | 4620 | 5280 | 5940 | 6600 | 7260 | 7920 | 8580 | 9240 | 9900 | 10560 | 11220 | 11880 | 12540 | 13200 | 13860 | 14520 | 15180 | 15840 | 16500 | 17160 | 17820 | 18480 | 19140 | 19800 | 20460 | 21120 | 21780 | 22440 | 23100 | 23760 | 24420 | 25080 | 25740 | 26400 | 27060 | 27720 | 28380 | 29040 | 29700 | 30360 | 31020 | 31680 | 32340 | 33000 | 33660 | 34320 | 34980 | 35640 | 36300 | 36960 | 37620 | 38280 | 38940 | 39600 | 40260 | 40920 | 41580 | 42240 | 42900 | 43560 | 44220 | 44880 | 45540 | 46200 | 46860 | 47520 | 48180 | 48840 | 49500 | 50160 | 50820 | 51480 | 52140 | 52800 | 53460 | 54120 | 54780 | 55440 | 56100 | 56760 | 57420 | 58080 | 58740 | 59400 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
Actual Accu
Status
[6 empty] | Plan | [7 empty] | 1320 | 2640 | 3960 | 5280 | 6600 | 7920 | 9240 | 10560 | 11880 | 13200 | 14520 | 15840 | 17160 | 18480 | 19800 | 21120 | 22440 | 23760 | 25080 | 26400 | 27720 | 29040 | 30360 | 31680 | 33000 | 34320 | 35640 | 36960 | 38280 | 39600 | 40920 | 42240 | 43560 | 44880 | 46200 | 47520 | 48840 | 50160 | 51480 | 52800 | 54120 | 55440 | 56760 | 58080 | 59400 | 60720 | 62040 | 63360 | 64680 | 66000 | 67320 | 68640 | 69960 | 71280 | 72600 | 73920 | 75240 | 76560 | 77880 | 79200 | 80520 | 81840 | 83160 | 84480 | 85800 | 87120 | 88440 | 89760 | 91080 | 92400 | 93720 | 95040 | 96360 | 97680 | 99000 | 100320 | 101640 | 102960 | 104280 | 105600 | 106920 | 108240 | 109560 | 110880 | 112200 | 113520 | 114840 | 116160 | 117480 | 118800 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000
[6 empty] | Actual | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Current Status | bar: 2022-10-22 to 2023-01-29
TT 18 | 0 | CN 100A | 2.0T Gas |  | HZ 8000 | Target | 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 660; 2022-11-09: 660; 2022-11-10: 660
[6 empty] | Actual | 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
[6 empty] | Target Accu | 2022-10-29: 660; 2022-10-30: 1320; 2022-10-31: 1980; 2022-11-01: 2640; 2022-11-02: 3300; 2022-11-03: 3960; 2022-11-04: 4620; 2022-11-05: 5280; 2022-11-06: 5940; 2022-11-07: 6600; 2022-11-08: 7260; 2022-11-09: 7920; 2022-11-10: 8000
Actual Accu | bar: 2022-10-15 to 2022-12-13
Status
TT 19 | 0 | CN 101A | 2.0T Gas |  | HZ 8000 | Target | 2022-10-26: 660; 2022-10-27: 660; 2022-10-28: 660; 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
[6 empty] | Actual | 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
[6 empty] | Target Accu | 2022-10-26: 660; 2022-10-27: 1320; 2022-10-28: 1980; 2022-10-29: 2640; 2022-10-30: 3300; 2022-10-31: 3960; 2022-11-01: 4620; 2022-11-02: 5280; 2022-11-03: 5940; 2022-11-04: 6600; 2022-11-05: 7260; 2022-11-06: 7920; 2022-11-07: 8000; 2022-11-08: 8000; 2022-11-09: 8000; 2022-11-10: 8000
Actual Accu | bar: 2022-10-15 to 2022-12-13
Status
TT 20 | 0 | CN 101A | 2.0T Gas |  | HZ 8000 | Target | 2022-10-26: 660; 2022-10-27: 660; 2022-10-28: 660; 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
[6 empty] | Actual | 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
[6 empty] | Target Accu | 2022-10-26: 660; 2022-10-27: 1320; 2022-10-28: 1980; 2022-10-29: 2640; 2022-10-30: 3300; 2022-10-31: 3960; 2022-11-01: 4620; 2022-11-02: 5280; 2022-11-03: 5940; 2022-11-04: 6600; 2022-11-05: 7260; 2022-11-06: 7920; 2022-11-07: 8000; 2022-11-08: 8000; 2022-11-09: 8000; 2022-11-10: 8000
Actual Accu | bar: 2022-10-15 to 2022-12-13
Status
TT 21 | 0 | CN 102A | 2.0T Gas |  | HZ 8000 | Target | 2022-10-26: 660; 2022-10-27: 660; 2022-10-28: 660; 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
[6 empty] | Actual | 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
[6 empty] | Target Accu | 2022-10-26: 660; 2022-10-27: 1320; 2022-10-28: 1980; 2022-10-29: 2640; 2022-10-30: 3300; 2022-10-31: 3960; 2022-11-01: 4620; 2022-11-02: 5280; 2022-11-03: 5940; 2022-11-04: 6600; 2022-11-05: 7260; 2022-11-06: 7920; 2022-11-07: 8000; 2022-11-08: 8000; 2022-11-09: 8000; 2022-11-10: 8000
Actual Accu | bar: 2022-10-15 to 2022-12-13
Status
TT 22 | 0 | CN 102A | 2.0T Gas |  | HZ 8000 | Target | 2022-10-27: 660; 2022-10-28: 660; 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 660; 2022-11-09: 0; 2022-11-10: 0; 2022-12-02: 660; 2022-12-03: 660
[6 empty] | Actual | 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-12-02: 0; 2022-12-03: 0
[6 empty] | Target Accu | 2022-10-27: 660; 2022-10-28: 1320; 2022-10-29: 1980; 2022-10-30: 2640; 2022-10-31: 3300; 2022-11-01: 3960; 2022-11-02: 4620; 2022-11-03: 5280; 2022-11-04: 5940; 2022-11-05: 6600; 2022-11-06: 7260; 2022-11-07: 7920; 2022-11-08: 8000; 2022-11-09: 8000; 2022-11-10: 8000; 2022-12-02: 660; 2022-12-03: 1320
Actual Accu | bar: 2022-10-15 to 2022-12-13
Status
TT 23 | 0 | CN 100A | 2.0T Gas |  | HZ 8000 | Target | 2022-10-27: 660; 2022-10-28: 660; 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 660; 2022-11-09: 0; 2022-11-10: 0; 2022-12-02: 660; 2022-12-03: 660
[6 empty] | Actual | 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-12-02: 0; 2022-12-03: 0
[6 empty] | Target Accu | 2022-10-27: 660; 2022-10-28: 1320; 2022-10-29: 1980; 2022-10-30: 2640; 2022-10-31: 3300; 2022-11-01: 3960; 2022-11-02: 4620; 2022-11-03: 5280; 2022-11-04: 5940; 2022-11-05: 6600; 2022-11-06: 7260; 2022-11-07: 7920; 2022-11-08: 8000; 2022-11-09: 8000; 2022-11-10: 8000; 2022-12-02: 660; 2022-12-03: 1320
Actual Accu | bar: 2022-10-15 to 2022-12-13
Status
TT 24 | 0 | CN 100A | 2.0T Gas |  | Lhasa 8000 | Target | 2022-10-21: 660; 2022-10-22: 660; 2022-10-23: 660; 2022-10-24: 660; 2022-10-25: 660; 2022-10-26: 660; 2022-10-27: 660; 2022-10-28: 660; 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 660; 2022-11-09: 660; 2022-11-10: 0; 2022-12-02: 0; 2022-12-03: 0; 2022-12-04: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-10: 0; 2022-12-11: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-17: 0; 2022-12-18: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-24: 0; 2022-12-25: 0; 2022-12-26: 0; 2022-12-27: 0; 2022-12-28: 0
[6 empty] | Actual | 2022-10-21: 0; 2022-10-22: 0; 2022-10-23: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-12-02: 0; 2022-12-03: 0; 2022-12-04: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-10: 0; 2022-12-11: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-17: 0; 2022-12-18: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-24: 0; 2022-12-25: 0; 2022-12-26: 0; 2022-12-27: 0; 2022-12-28: 0
[6 empty] | Target Accu | 2022-10-21: 660; 2022-10-22: 1320; 2022-10-23: 1980; 2022-10-24: 2640; 2022-10-25: 3300; 2022-10-26: 3960; 2022-10-27: 4620; 2022-10-28: 5280; 2022-10-29: 5940; 2022-10-30: 6600; 2022-10-31: 7260; 2022-11-01: 7920; 2022-11-02: 8580; 2022-11-03: 9240; 2022-11-04: 9900; 2022-11-05: 10560; 2022-11-06: 11220; 2022-11-07: 11880; 2022-11-08: 12540; 2022-11-09: 12800; 2022-11-10: 12800; 2022-12-02: 0; 2022-12-03: 0; 2022-12-04: 0; 2022-12-05: 0; 2022-12-06: 0; 2022-12-07: 0; 2022-12-08: 0; 2022-12-09: 0; 2022-12-10: 0; 2022-12-11: 0; 2022-12-12: 0; 2022-12-13: 0; 2022-12-14: 0; 2022-12-15: 0; 2022-12-16: 0; 2022-12-17: 0; 2022-12-18: 0; 2022-12-19: 0; 2022-12-20: 0; 2022-12-21: 0; 2022-12-22: 0; 2022-12-23: 0; 2022-12-24: 0; 2022-12-25: 0; 2022-12-26: 0; 2022-12-27: 0; 2022-12-28: 0
Actual Accu | bar: 2022-10-15 to 2022-12-28
Status
TT 26 | 0 | CN 102A | 2.0T Gas |  | Lhasa 8000 | Target | 2022-10-21: 660; 2022-10-22: 660; 2022-10-23: 660; 2022-10-24: 660; 2022-10-25: 660; 2022-10-26: 660; 2022-10-27: 660; 2022-10-28: 660; 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 660; 2022-11-09: 660; 2022-11-10: 0; 2022-12-02: 0; 2022-12-03: 0
[6 empty] | Actual | 2022-10-21: 0; 2022-10-22: 0; 2022-10-23: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0; 2022-12-02: 0; 2022-12-03: 0
[6 empty] | Target Accu | 2022-10-21: 660; 2022-10-22: 1320; 2022-10-23: 1980; 2022-10-24: 2640; 2022-10-25: 3300; 2022-10-26: 3960; 2022-10-27: 4620; 2022-10-28: 5280; 2022-10-29: 5940; 2022-10-30: 6600; 2022-10-31: 7260; 2022-11-01: 7920; 2022-11-02: 8580; 2022-11-03: 9240; 2022-11-04: 9900; 2022-11-05: 10560; 2022-11-06: 11220; 2022-11-07: 11880; 2022-11-08: 12540; 2022-11-09: 12800; 2022-11-10: 12800; 2022-12-02: 0; 2022-12-03: 0
Actual Accu | bar: 2022-10-15 to 2022-12-13
Status
TT 25 | 0 | CN 101A | 2.0T Gas |  | Hainan 8000 | Target | 2022-10-21: 660; 2022-10-22: 660; 2022-10-23: 660; 2022-10-24: 660; 2022-10-25: 660; 2022-10-26: 660; 2022-10-27: 660; 2022-10-28: 660; 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 660; 2022-11-09: 660; 2022-11-10: 0
[6 empty] | Actual | 2022-10-21: 0; 2022-10-22: 0; 2022-10-23: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
[6 empty] | Target Accu | 2022-10-21: 660; 2022-10-22: 1320; 2022-10-23: 1980; 2022-10-24: 2640; 2022-10-25: 3300; 2022-10-26: 3960; 2022-10-27: 4620; 2022-10-28: 5280; 2022-10-29: 5940; 2022-10-30: 6600; 2022-10-31: 7260; 2022-11-01: 7920; 2022-11-02: 8580; 2022-11-03: 9240; 2022-11-04: 9900; 2022-11-05: 10560; 2022-11-06: 11220; 2022-11-07: 11880; 2022-11-08: 12540; 2022-11-09: 12800; 2022-11-10: 12800
Actual Accu | bar: 2022-10-15 to 2022-12-13
Status
TT 27 | 0 | CN 102A | 2.0T Gas |  | Hainan 8000 | Target | 2022-10-21: 660; 2022-10-22: 660; 2022-10-23: 660; 2022-10-24: 660; 2022-10-25: 660; 2022-10-26: 660; 2022-10-27: 660; 2022-10-28: 660; 2022-10-29: 660; 2022-10-30: 660; 2022-10-31: 660; 2022-11-01: 660; 2022-11-02: 660; 2022-11-03: 660; 2022-11-04: 660; 2022-11-05: 660; 2022-11-06: 660; 2022-11-07: 660; 2022-11-08: 660; 2022-11-09: 660; 2022-11-10: 0
[6 empty] | Actual | 2022-10-21: 0; 2022-10-22: 0; 2022-10-23: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
[6 empty] | Target Accu | 2022-10-21: 660; 2022-10-22: 1320; 2022-10-23: 1980; 2022-10-24: 2640; 2022-10-25: 3300; 2022-10-26: 3960; 2022-10-27: 4620; 2022-10-28: 5280; 2022-10-29: 5940; 2022-10-30: 6600; 2022-10-31: 7260; 2022-11-01: 7920; 2022-11-02: 8580; 2022-11-03: 9240; 2022-11-04: 9900; 2022-11-05: 10560; 2022-11-06: 11220; 2022-11-07: 11880; 2022-11-08: 12540; 2022-11-09: 12800; 2022-11-10: 12800
Actual Accu | bar: 2022-10-15 to 2022-12-13
Status
[6 empty] | Plan | 2022-10-21: 2640; 2022-10-22: 5280; 2022-10-23: 7920; 2022-10-24: 10560; 2022-10-25: 13200; 2022-10-26: 17820; 2022-10-27: 23760; 2022-10-28: 29700; 2022-10-29: 36300; 2022-10-30: 42900; 2022-10-31: 49500; 2022-11-01: 56100; 2022-11-02: 62700; 2022-11-03: 69300; 2022-11-04: 75900; 2022-11-05: 82500; 2022-11-06: 89100; 2022-11-07: 93960; 2022-11-08: 97420; 2022-11-09: 99120; 2022-11-10: 99200
[6 empty] | Actual | 2022-10-21: 0; 2022-10-22: 0; 2022-10-23: 0; 2022-10-24: 0; 2022-10-25: 0; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-29: 0; 2022-10-30: 0; 2022-10-31: 0; 2022-11-01: 0; 2022-11-02: 0; 2022-11-03: 0; 2022-11-04: 0; 2022-11-05: 0; 2022-11-06: 0; 2022-11-07: 0; 2022-11-08: 0; 2022-11-09: 0; 2022-11-10: 0
Current Status | bar: 2022-10-21 to 2022-11-10

## R&R
Name | Role | Res.
Xiang Zhengxi, Chen Weidi | REC Leader | 1. Define issue collecting and distribution process; 2. Keep monitoring on whole program issues; 3. Review JIRA(GIM) for daily issues, and matching the necessary AIMS(S5/Gating Issue) in JIRA; 4. Cooperate with IVI SW/PMO team on the regular Issue review meeting; 5. Support finding solutions for some key issues; 6. Push supplier to give the root cause and fix plan for Jira issue.
REC On site engineer | TOS(Technical On site) | 1. Lead the issue collecting tasks on site; 2. Distribute daily tasks to Baidu/YFVE/Inhouse/TS; 3. Communicate with FCPA/NTT/R202/VOCF/Audit team and make all information clear; 4. Filter duplicate issues and find GIM number for some issues; 5. Pass daily issues document to REC leader and support REC Leader to know the latest issue analysis process in CAF, avoid duplicated discussion. 6. Make sure all vehicles issue log/videos/pic upload into REC share drive;
Huang Xiaoli, Wang Yuanpeng | CAF PD | 1.Working with REC leader and TOS to ensure all issues information are available; 2.Help to coordinate with plant team, such as find vehicles, find some key person; 3.Leader backup when both REC leader and TOS are not available; 4.Lead Vehicle SW upgrade.
BAIDU On site engineer | BAIDU | 1. Clarify questions from plant team, confirm design intent; 2. Have a clear concept on daily issues and pass key information to R&D team; 3. Lead to collect all the Baidu related USB/ADB LOGS to Baidu RD(Make sure all issues have logs); 4. Validate on some key issues and perform test on each new software versions;
YFVE On site engineer | Nanjing YFVE | 1. Clarify questions from plant team, confirm design intent; 2. Have a clear concept on daily issues and pass key information to R&D team; 3. Catch CAN logs for some Camere/IPC/SWC related issues; 4. Validate on some key issues and perform test on each new software versions; 5. Flash vehicle correctly if needed;
Inhouse/TS On site engineer | Inhouse/TS | 1. Clarify questions from plant team, confirm design intent; 2. Have a clear concept on daily issues and pass key information to R&D team; 3. Catch CAN logs for some vehicle control related issues; 4. Validate on some key issues and perform test on each new software versions;

## Management Review
Date | Event | Details | Remark
2022-02-15 | 下线仪式 | 管理层名单正在整理
3.7 | OOB看车 （out of box） | REC VE牵头 有可能在南京 也有可能在重庆 | OOB: Out Of Box High level Team's initial/first review of vehicle during a build phase