## Ford Jira Cloud (14)
Issue Type | Issue key | Summary | Custom field (Supplier.) | Fix versions | Assignee | Reporter | Priority | Status
Bug | APIMCIM-25331 | Phase 5：【偶现】百度地图，点击免责声明同意并继续后，闪退 | Baidu | LC_R00_ENG | Tiantian Shan | Tiantian Shan | P1 | Monitor
Bug | APIMCIM-27750 | 【实车】【U611】【地图】11-08 夹江隧道行驶中，发生偏航（偶现） | Baidu | LC_R04_ENG | Wenxiong Cai | Niu Tian | P1 | Monitor
Bug | APIMCIM-27670 | 【U611】【R04】【地图】【偶现】1154 车标不绑路 | Baidu | LC_R04_ENG | Wenxiong Cai | Niu Tian | P1 | Monitor
Bug | APIMCIM-24569 | 【Phase V】【U611】【A】【百度输入法】【once】输入法页面点击无反应 | Baidu | LC_R04_ENG | Niu Tian | Zihao Qiu | P1 | Monitor
Bug | APIMCIM-30118 | Phase 5：【高频】主驾播放爱奇艺视频，副驾打开个人中心，点击随心看时发生闪退 | Baidu | LC_R05_ENG | Wenxiong Cai | Jun Sun | P1 | Test
Bug | APIMCIM-29843 | 【611】【语音】唤醒后，语音点播视频，TTS回复正常，但实际不执行 | Baidu | LC_R05_ENG | Niu Tian | Dan Zhou | P1 | Test
Bug | APIMCIM-28803 | Phase 5：【必现】【U611MCA】【Performance】"Launcher显示到导航启动时间“耗时较长，不达标 | Baidu | LC_R05_ENG | Wenxiong Cai | Zhichao Zhang | P1 | Test
Bug | APIMCIM-28642 | 【必现】【widget】1117 重启车机或者杀掉地图，首次点击widget的回家按钮无反应，需要点击第二次才行 | Baidu | LC_R05_ENG | Niu Tian | Niu Tian | P1 | Test
Bug | APIMCIM-27893 | Phase 5：【偶现】巡航界面，VR:"调高语音音量到3”，TTS一直重复回复:"好，音量调到3了” | Baidu | LC_R05_ENG | Wenxiong Cai | Jie Xu | P1 | In Progress
Bug | APIMCIM-27335 | 【Phase V】【U611】【A】【Monkey】【偶现】com.baidu.car.input出现内存泄漏 | baidu | LC_R05_ENG | Niu Tian | Zihao Qiu | P1 | Test
Bug | APIMCIM-26573 | Phase 5：【偶现】巡航模式下，车辆行驶中车标不动，车辆静止的时候，车标在移动 | Baidu | LC_R05_ENG | Wenxiong Cai | Zhimin Cheng | P1 | Test
Bug | APIMCIM-26353 | Phase 5：【偶现】分屏模式下，Widget卡片和导航信息不同步 | Baidu | LC_R05_ENG | Wenxiong Cai | Zhimin Cheng | P1 | Test
Bug | APIMCIM-26010 | [U611MCA][15h]com.baidu.car.input happen memory leak, RAM ranking up to 3.5G at maximum during monkey test of 15h | Baidu | LC_R05_ENG | Niu Tian | shen jie | P1 | Test
Bug | APIMCIM-25770 | Phase 5：【必现】从个人时光里打开随心看，分屏后，副驾和主驾同时显示随心看页面 | Baidu | LC_R05_ENG | Wenxiong Cai | Jun Sun | P1 | Test
Bug | APIMCIM-25613 | Phase 5：【偶现】导航中底图一直在缩放 | Baidu | LC_R05_ENG | Wenxiong Cai | Jingjing Zhu | P1 | In Progress
Bug | APIMCIM-25597 | Phase 5：【必现】导航中，主页widget一直显示GPS信号弱 | Baidu | LC_R05_ENG | Niu Tian | Jingjing Zhu | P1 | Test
Bug | APIMCIM-25477 | [U611MCA][1/15h]monkey test, after 15-hour monkey test, system restart | Baidu | LC_R05_ENG | Niu Tian | shen jie | P1 | Test
Bug | APIMCIM-25341 | [U611MCA][3/3]response time test, after system restart account QR code display takes 6.8s, not satisfied with the target 3s | Baidu | LC_R05_ENG | Niu Tian | shen jie | P1 | Test
Bug | APIMCIM-26092 | phase5:【偶现】进行导航设置时，地图整体闪退 | Baidu | LC_R00_ENG | changjiang Jing | changjiang Jing | P1 | Monitor
Bug | APIMCIM-25397 | Phase 5：【偶现】离线导航时点击继续导航，出现底图未加载 | Baidu | LC_R00_ENG | Jingjing Zhu | Jingjing Zhu | P1 | Monitor
Bug | APIMCIM-27322 | 【Phase V】【U611】【A】【Monkey】【偶现】出现la_guestdump.gcore.gz | Ford_IDPS | LC_R05_ENG | Jinchi Xu | Zihao Qiu | P1 | In Progress
Bug | APIMCIM-29100 | [U611MCA][91/15h]com.cvss.client happen crash during monkey test of 15h | Ford_IDPS | LC_R05_ENG | Jinchi Xu | shen jie | P1 | In Progress
Bug | APIMCIM-30120 | Phase 5：【高频】从个人时光里打开随心看，发生com.ford.sync.surprisemessage Crash | Ford-Inhouse | LC_R05_ENG | Jun Sun | Jun Sun | P1 | Test
Bug | APIMCIM-24021 | 【611】【语音】随心听-独立模式-所见即可说-主驾唤醒语音“QQ音乐/喜马拉雅/新闻”-期待命中主驾屏所见即可说-实际命中副驾屏所见即可说 | Ford-Inhouse | LC_R05_ENG | Niu Tian | Niu Tian | P1 | Approval
Bug | APIMCIM-25810 | [U611MCA][100%]V2I: After triggering V2I broadcast, the media volume is abnormal. | Ford-inhouse-cvpp | LC_R05_ENG | hui zhou | hui zhou | P1 | Test
Bug | APIMCIM-30138 | Phase 5：【偶现】多次开启关闭媒体投射开关后，置灰无法点击 | TS | LC_R05_ENG | Xi Wang | Xi Wang | P1 | Test
Bug | APIMCIM-29681 | 【PhaseV】【U611】【A】【Setting】【3次】BCM台架，多次开关媒体投射开关后，媒体投射开关卡死 | TS | LC_R05_ENG | Zihao Qiu | Zihao Qiu | P1 | Test
Bug | APIMCIM-22852 | Phase5:[U611MCA] 主页进入点击3D车模，进入车内后对应音量等按键失效，且卡屏，不能退出，点击3D车模卡片外界面退出 | TS | LC_R00_ENG | wendi Xiao | Chao Wang | P1 | Monitor
Bug | APIMCIM-30522 | [U611MCA][100%]BSP cannot be used in LPR and DeepSleep modes | TS | LC_R05_ENG | Chuanqin Chen | Yuanyuan Yang | P1 | Test
Bug | APIMCIM-28626 | Phase 5：【必现】【U611MCA】【Performance】Launcher显示到空调设置界面打开耗时较长 | TS | LC_R05_ENG | zhangjian zhou | Zhichao Zhang | P1 | Test
Bug | APIMCIM-26773 | 【U611 MCA】【黑盒】【偶现】【Vehicle Setting】切换主题时，发生闪退 | TS | LC_R05_ENG | manyi guan | manyi guan | P1 | Test
Bug | APIMCIM-30528 | 【实车】【U611 】【地图】14-10 分屏副驾侧导航，主驾侧主页地图卡片异常死图，且无法点击（必现） | TS |  | Liang Xiao | 田程 | P1 | To Do
Bug | APIMCIM-22694 | 【Phase V】【U611】【A】【实车】偶现两屏全黑后自动重启 | YFVE | LC_R00_ENG | 严文正 | 严文正 | P1 | Monitor
Bug | APIMCIM-27631 | U611蓝牙来电，执行模拟导航，导航播报声音被压制的非常小且只有后门喇叭有声音，前门没声音，蓝牙铃声无声音（10：23） | YFVE | LC_R04_ENG | Zihao Qiu | Rui Jiang Zhao | P1 | Test
Bug | APIMCIM-27059 | 【Phase V】【U611】【A】【HMI】【ONCE】U611刷完机后导入104A配置 仪表端单位显示与IVI默认设置不匹配 | YFVE | LC_R04_ENG | 严文正 | 严文正 | P1 | Monitor
Bug | APIMCIM-27035 | Phase 5：【偶现】实车LV913 IVI使用过程中自动黑屏重启 | YFVE | LC_R04_ENG | Cang Dingxin | Xi Wang | P1 | Monitor
Bug | APIMCIM-25981 | Phase 5：【偶现】车机冻屏 | YFVE | LC_R04_ENG | Xiang Li | Xiang Li | P1 | Monitor
Bug | APIMCIM-25665 | Phase 5：【偶现】IVI使用过程中黑屏后自动重启 | YFVE | LC_R04_ENG | ying.lan | Xi Wang | P1 | Monitor
Bug | APIMCIM-25199 | Phase 5：【偶发】台架静置，出现IVI卡死的情况 | YFVE | LC_R04_ENG | Yanhui Gu | Yanhui Gu | P1 | Monitor
Bug | APIMCIM-24818 | Phase 5：【偶发】台架load shed后，整车无声 | YFVE | LC_R04_ENG | Yanhui Gu | Yanhui Gu | P1 | Monitor
Bug | APIMCIM-23147 | 【Phase 5】【U611MCA】611 HB10 999990 1535 大屏空调AUTO开启时大屏调节风扇无变化（中控调节有变化） | YFVE | LC_R04_ENG | Zihao Qiu | Chao Wang | P1 | Test
Bug | APIMCIM-18232 | 【Phase V】【U611】【A】【Chime】【5/5】外置功放chime无法发声 | YFVE | LC_R04_ENG | Zihao Qiu | Zeming Mao | P1 | Test
Bug | APIMCIM-30043 | U611C MCA&U625C MCA HIL SIGNOFF: Global Belt minder initial pops up display duration time error | YFVE | LC_R05_ENG | Changdong Wang | Kangkang Wang | P1 | Test
Bug | APIMCIM-29763 | 【611】【语音】唤醒语音后TTS会被收音，当成语音指令继续循环执行 | YFVE | LC_R05_ENG | Zihao Qiu | Dan Zhou | P1 | Test
Bug | APIMCIM-29761 | 【U611】无USB设备-首页点击USB TAB然后进入小视频播放，再退出到首页，顶部搜索按钮消失 | YFVE | LC_R05_ENG | Zihao Qiu | Ridong Jaing | P1 | Test
Bug | APIMCIM-29687 | 【U611 MCA】【黑盒】【偶现】【Vehicle Setting】ign=off，ACC=on，点击setting无法进入 | YFVE | LC_R05_ENG | Zihao Qiu | manyi guan | P1 | Test
Bug | APIMCIM-29621 | U611C MCA SIGNOFF HIL: Global Belt Minder seating layout display issue | YFVE | LC_R05_ENG | Kangkang Wang | Kangkang Wang | P1 | Test
Bug | APIMCIM-29173 | U611MCA Bluecruise： When activate BC， 'resume control' warning pop up directly but ADAS ECU does not send out warning request | YFVE | LC_R05_ENG | Changxing Zhu | Yongfei Chen | P1 | Test
Bug | APIMCIM-29021 | 【U611】【黑盒】【必现】【实车】使用过密码启动车辆以后，再熄火-开关车门后屏幕仍然处于亮屏状态经过约1分钟后IVI黑屏 | YFVE | LC_R05_ENG | Zihao Qiu | Chuanqin Chen | P1 | Test
Bug | APIMCIM-28908 | 【611】【爱奇艺】分屏状态下主驾侧播放莲花楼预集，点击中间栏的爱奇艺图标，副驾侧可以抢夺主驾侧随心看，如视频 | YFVE | LC_R05_ENG | Zihao Qiu | Niu Tian | P1 | Test
Bug | APIMCIM-28666 | 【611】【语音】【偶现】611语音偶现弹窗闪屏 | YFVE | LC_R05_ENG | Zihao Qiu | Niu Tian | P1 | Test
Bug | APIMCIM-28539 | [U611MCA][100%]DLNA has been consuming traffic in the background | YFVE | LC_R05_ENG | weijian.yang | hui zhou | P1 | In Progress
Bug | APIMCIM-27959 | Phase 5 【必现】缩小第一个蓝牙电话后，车机端无法接听第二个蓝牙来电 | YFVE | LC_R05_ENG | Zihao Qiu | Xi Wang | P1 | Test
Bug | APIMCIM-27833 | Press hard button and enter 360 menu, can't see front camera video | YFVE | LC_R05_ENG | Lei Shi | Fiona Zheng | P1 | Test
Bug | APIMCIM-27696 | [U611MCA][100%]Bluetooth phone is not connected, launcher clicks the phone card, no pop-up reminder appears | YFVE | LC_R05_ENG | Zihao Qiu | Hua Yan | P1 | Test
Bug | APIMCIM-27650 | [U611MCA][100%]When the main climate is turned off, click the air volume pop-up window to adjust the wind speed, and the pop-up window does not display the air volume value | YFVE | LC_R05_ENG | Zihao Qiu | Hua Yan | P1 | Test
Bug | APIMCIM-27642 | [U611MCA][100%]The main climate is turned on and off, and the status bar icon is not fixed, which will cause displacement | YFVE | LC_R05_ENG | Zihao Qiu | Hua Yan | P1 | Test
Bug | APIMCIM-27525 | [U611MCA][100%]a popup up window appeared when try to use the soft button to open the liftgate in manual mode | YFVE | LC_R05_ENG | Changxing Zhu | Jun Wei | P1 | Test
Bug | APIMCIM-27524 | U611MCA quick panel liftgate control button highlighting not match liftgate ajar status | YFVE | LC_R05_ENG | Zihao Qiu | Jun Wei | P1 | Test
Bug | APIMCIM-27480 | [U611MCA][100%]Co-op mode, settings have no menu items | YFVE | LC_R05_ENG | Zihao Qiu | Liqian Zhang | P1 | Test
Bug | APIMCIM-27121 | 【Phase V】【U611】【A】【HMI】【5/5】触发W3541或W3542等报警，把0X44E全部发31，出现相关报警闪烁 | YFVE | LC_R05_ENG | 严文正 | 严文正 | P1 | Test
Bug | APIMCIM-27053 | [U611MCA][100%]The Bluetooth pairing process is wrong and the confirmation button is missing | YFVE | LC_R05_ENG | Zihao Qiu | jiang yi | P1 | Test
Bug | APIMCIM-27032 | [U611MCA][100%]Bluetooth music Bluetooth is not connected page car model wrong | YFVE | LC_R05_ENG | Zihao Qiu | jiang yi | P1 | Test
Bug | APIMCIM-26850 | [U611MCA][100%]The vehicle control card cannot be absorbed after sliding | YFVE | LC_R05_ENG | Zihao Qiu | Liqian Zhang | P1 | Test
Bug | APIMCIM-26847 | [U611MCA][100%]Quick control/vehicle control/system settings, slide left/right to the bottom, the width of the slide is inconsistent | YFVE | LC_R05_ENG | Zihao Qiu | Liqian Zhang | P1 | Test
Bug | APIMCIM-24097 | 【611】【语音】车机系统控制-精简屏幕控制-语音“打开/关闭主驾精简屏幕”/“打开/关闭副驾精简屏幕”-执行失败 | YFVE | LC_R05_ENG | Zihao Qiu | Niu Tian | P1 | Test
Bug | APIMCIM-23954 | U611C MCA SIGNOFF HIL global belt minder number of seats does not match the real vehicle | YFVE | LC_R05_ENG | 严文正 | Kangkang Wang | P1 | Approval
Bug | APIMCIM-23858 | 【Phase V】【U611】【A】【Warning】【5/5】配置DE0D R2_Bench=0&R2C3_Seatbelt_Cfg=0时，安全带未系报警的第二排中间座椅仍然显示 | YFVE | LC_R05_ENG | 严文正 | 严文正 | P1 | Test
Bug | APIMCIM-27632 | U611导航过程中 蓝牙来电，来电铃声忽然变大（9：37） | YFVE | LC_R04.1_ENG | Rui Jiang Zhao | Rui Jiang Zhao | P1 | Monitor
Bug | APIMCIM-27432 | 【Phase5】【U611MCA】VID_20230802_165837高概率出现自动关闭蓝牙然后再打开蓝牙 | YFVE | LC_R04.1_ENG | Zihao Qiu | Amy Xu | P1 | Monitor
Bug | APIMCIM-27321 | 【Phase V】【U611】【A】【Upgrade】【once】USB OTA升级完成后激活过程中，车机黑屏，重启不可恢复 | YFVE | LC_R04.1_ENG | Zihao Qiu | Zihao Qiu | P1 | Monitor
Bug | APIMCIM-27317 | 【PhaseV】【U611】【A】【DLNA】【1/5】爱奇艺投屏有声音无画面 | YFVE | LC_R04.1_ENG | Zihao Qiu | Zihao Qiu | P1 | Monitor
Bug | APIMCIM-25794 | Phase 5：【必现】【Performance】”Power on到launcher界面可见“耗时不达标 | YFVE | LC_R04.1_ENG | Hu Jiajia | Zhichao Zhang | P1 | In Progress
Bug | APIMCIM-30590 | Phase 5：【 U611 MCA 】 DSP 12CH model, wake-up voice, high volume and loudness | YFVE |  | Liao wan | Rui Liu | P1 | To Do
Bug | APIMCIM-28474 | Phase 5：【单机必现】打开云听即闪退 | YunTing | LC_R05_ENG | Jun Sun | Jun Sun | P1 | Approval