## mooodification (hidden)
2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01
6/1
Pano
Wireframes
HMI Support Specification
Revisions as required
7/3
7/10
controller Wireframes
Wireframe Model
Usability Clinic
Internal evaluations as needed
Usability validation Clinic
Pano Production
Assets +4 wks
Group A
Aug 28
Group (A?) B
Oct 13
Group C
Dec 7
Group D
Feb 2
Group A+B
Oct 30
Group C
Dec 7
Group D
Feb 2
Controller Production
Assets +4 wks
Group A
Oct 13
Group B
Dec 18
Group C
Feb 15
Group D
Apr 29
Pano Hero Screens
Prelim Group A
Aug 1
Group A+B
Sept 15
Group C
Nov 8
Group D
Jan 5
Group E
Mar 1
Controller Hero Screens
Group A
Sept 15
Group B
Nov 20
Group C
Jan 18
Group D
Apr 1
Group E
Jun 10
China HMI timing
Concept study
Wireframes
Revisions as required
Controller Production assets
HMI Vendor onboard?
< Oct 30
localization(translation)
Group A
Nov 30
Group B
Jan 30
Group C
Mar 30
Group D
May 30
Pano Production assets
Group A
Dec 13
Group B
Jan 13
Group C
Feb 13
Group D
Mar 13
Internal evaluations as needed
Usability validation Clinic

## ChangLOG
Version | Change Content | Input from
CDX707 timing & feature grouping Jan.28,2021 | 1. Revise the Group A UE delivery plan to complete all Group A UE by Mar. 15 in IVI feature detail plan Jan28 | Sherry Xia
| 2. Updated Hero screen expected date in IVI feature detail plan Jan28 | Sherry Xia
| 3. Added the RACM UE and UI delivery plan into Timing update Jan28 | Sherry Xia
| 4. Added the draft hero screen delivery timing into Timing update Jan.28 | Nicolas Thetard
CDX707 timing & feature grouping Jan.29,2021 | 1. In Timing update Jan29, Merged the Pano & Controller Timing line since the UE and UI delivery will be per feature rather than component | Luisa Liu
| 2. In Timing update Jan29, Added the timeline for function spec clarification | Luisa Liu
CDX707 timing & feature grouping Feb.1,2021 | 1. Changed FO name of Climate to Will Xie in IVI feature detail plan Feb1 | Xie Will
| 2. Add "SW plan" to capture 707 software release plan | Jiajia Zhou
| 3. Added key software delivery date into Timing update Feb1 | Jiajia Zhou
| 4. Added the hero screen delivery timing confirmed with FNA Studio on Feb. 1 into Timing update Feb1 | Nicolas Thetard
| 5. Delayed Assets delivery plan according to feature list update and Hero Screen delivery timing, and also considering Ergo sign-off time required into Timing update Feb1 and IVI feature detail plan Feb1 | Luisa Liu
| 6.Added FO names for Group B features | Jiajia Zhou
| 7. Revised feature HMI leads for a few features | Luisa Liu
| 8. Added Group B YFVE feature expected dates | Huang Feng
| 9. Confirmed Message center HMI will be provied by Ford HMI | Luisa Liu
| 10. Added DLNA partial function into Group A | Elaine Jia

## Control Asset Grouping Deliver6 (hidden)
Group A |  |  | Group B |  |  |  | Group C |  |  |  | Group C
DashCard Area | Dashcards Title | Description / Comments | DashCard Area | Dashcards Title | Description / Comments | WireFrame Readiness | DashCard Area | Dashcards Title | Description / Comments | Wireframe Readiness | DashCard Area | Dashcards Title | Description / Comments | Wireframe Readiness
Launcher | Vehicle Card - normal |  | Control & Settings | Front Page |  | Signed off | System | Voice Assist (VPA) / Voice Control |  | Cross carline project, no need separate hero screen
Launcher | Vehicle Card - TPMS is ON |  | Control & Settings | Multi-contour seats |  | Signed off |  | Ambiente Lighting | 128 colors, CD764 unique, UE under development | End of Sep. 2020
Launcher | Navigation Cad |  | Control & Settings | Seat massage |  | Signed off |  | Digital scent | Rescale from CX483, under development | Oct. 2020
Launcher | Music Card |  | System | Keyboard Global | moved to Uikit | n/a |  | Rejuvenation mode | Rescale from CX483, under development | Oct. 2020
Launcher | Video Card |  | System | Keyboard Qwerty | don't have this feature | n/a |  | Calendar | CD764 new, under development | Nov. 2020
Launcher | Phone Card |  | System | A-Z Jump Keyboard | don't have this feature | n/a |  | Smart Scene | CD764 new, under development | Nov. 2020
Launcher | More Services (App Drawer/App Menu) |  | System | Voice Assist (VPA) / Voice Control | Moved to Group C |  | System Animations | Welcome / Farewell animation
Launcher | Quick Panel |  | System | Profile View | Captured in Profile Editor / Personalization | n/a | System Animations | Individual mode <-> co-pilot mode / solo mode
Launcher | Recent Apps |  | Online Video | Front Page |  | Signed off |  | Drive mode selection (knob on console)
Launcher | Status Bar |  | Online Video | Video Player |  | Signed off | System Animations | UI Build
Launcher | Message hint and Message Center |  | USB Video | Front Page |  | Signed off | System Animations | Screen Transitions
Navigation | Main - On Route |  | USB Video | Folder View |  | Signed off | System Animations | OTA updates
Navigation | Main - Off Route |  | Control & Settings | Front page for system setting - Display Setting, Bluetooth Setting and wifi setting |  | Signed off | System Animations | Auto Park
Radio | AM/FM View |  | Control & Settings | Settings List - Setup Clock |  | Signed off | System Animations | Digital Scent
Radio | Tuner | AM/FM Tuner | Control & Settings | Settings List - Sound / Audio Setting |  | Signed off | System Animations | Active Call
Radio | Direct Tune | AM/FM Direct Tune | Control & Settings | Settings List - Display |  | Signed off | System Animations | Process Flows : Phone paring, charge
Radio | Online Radio |  | Control & Settings | Process Flow - Phone as a Key (PAAK) |  | Signed off | System Animations | VPA Digital Assistant
Media | Online Music front page |  | Control & Settings | Vehicle Status (Vehicle health alert) |  | Signed off | System Animations | IOD cards flow & Behavior
Media | Online Music player |  | Control & Settings | Process Flow - Profile Editor / Personalization |  | SIgned off
Media | Bluetooth Audio Player |  | Control & Settings | Process Flow- Phone Pairing / Blue tooth Setting |  | Signed off | Owner's Manual | Digitial Owners Manual App | E - mannual
Media | USB Player |  | Control & Settings | Settings Item - Driver Assist Configuration |  | Signed off
Media | USB/Bluetooth Browser |  | Controls & Settings | Settings Item - Set Code Task | don' t have this feature | n/a | Settings Animations | Infobooks//Settings2Centerstack
Media | USB Media Info |  | Control & Settings | Ambient Lighting | Moved to Group C | CD764 new design, UE under discussion | Settings Animations | Supplemental Animation/Experiences (e.g. MCS)
Climate | Climate Menu - Front |  | Assist | Active park Assist (camera) / FAPA |  | Signed off
Climate | Climate Menu - Rear | Move to Group B | Popup | Drive Assist (hotkey) |  | Signed off | System | Digital Scent
Climate | Control Mirror - Fan Speed |  | Notifications | Info - Navigation Fault | Move to Uikit | n/a
Climate | Control Mirror - Temperature |  | Notifications | Progress - Acquiring Traffic Data | Move to Uikit | n/a | Notifications | Generic Notification Small
Climate | Climate Ribbon |  | Physical Key | MCS Seat App - Adjust | No physical button, this page captured in Control&Setting - Seats | n/a | Notifications | Generic Notification Large
Climate | Climate Menu | [5 empty] | Notifications | Generic Dialog Small
Climate | Heated Seats Slider | [5 empty] | Notifications | Information Popup Basic
Climate | Heated Seats Mirror | [5 empty] | Notifications | Information Popup Detailed
Climate | Fan Slider
Climate | Auto Air Refresh | [5 empty] | Settings | Seat App - Adjust
Climate | Temperature Slider | [5 empty] | Settings | Seat App - Massage
Phone | Active Call States
Phone | Recent Calls States (empty, single, full)
Phone | Contact View
Phone | Contact List (empty, single, full)
Phone | Dialog - Incoming Call
Phone | Phone Dialpad
Phone | Phone Number Pad
Phone | Phone Unconnected/Unpaired
Phone | Smart Search Layout
Phone | Phone Smart Search
Parking Camera | Full Screen Views Front
Parking Camera | Full Screen Views Rear

## Timing update Feb1
May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01
6/1
Pano
Wireframes
HMI Support Specification
Revisions as required
7/3
7/10
controller Wireframes
Wireframe Model
Usability Clinic
Internal evaluations as needed
Usability validation Clinic
Pano Production
Assets
Group A
Aug 28
Group (A?) B
Oct 13
Group C
Dec 7
Group D
Feb 2
Controller Production
Assets +4 wks
Group A
Oct 13
Group B
Dec 18
Group C
Feb 15
Group D
Apr 29
Pano Hero Screens
Prelim Group A
Aug 1
Group A+B
Sept 15
Group C
Nov 8
Group D
Jan 5
Group E
Mar 1
Controller Hero Screens
Group A
Sept 15
Group B
Nov 20
Group C
Jan 18
Group D
Apr 1
Group E
Jun 10
China IVI HMI
(Lead by HMI and Studio)
for 1 theme
Revisions as required
DCV
FDJ
China Software
(Lead by EESE)
Interaction spec / UE
Group A
Mar 15
Group B
Apr 30
Group C
May 31
Group D
Jul 15
Group B
Nov 20
Supplier onboard
Group A + B
Nov 20
Group C
Dec 18
Group D
Feb 5
Target timing unknown
Usability validation external Clinic
SystemUI Usability validation
Revisions as required
PA Experience review
Aug 18
China Rear Armrest Control Panel HMI
UE
English
Jan.28
Chinese
Feb.10
Assets
English
Mar. 30
R05 for pre-DV
Jul. 10
Hero Screeen
Revisions
TBD
TBD
Kick off
Jan. 28
Hero Screen & UIkit
Group A
Mar 30
UE Creation Start
Feb 2
Global 707
Theme & Interaction Reivew in GAR
Mar. 1
Function Spec Clarification
(Lead by EESE&CVPP Feature owners)
Function Spec Clarification
Revisions as required
Group A
Mar 1
Group C
May 15
Group D
Jul 1
Group B
Apr 15
R09 for DCV1
Nov.17
R05 for DCV2
Mar.23
Group B
May 15
Group D
Jul 31
Group C
Jun 31
Pano + Controller Production assets /UI
Group A
Jun 15
Group C
Sep 15
Group D
Oct 30
Group B
Jul 30
UI Creation Start
Apr 15
Revisions as required

## IVI feature detail plan Feb1
Group A -> DCV beta (pre-DV)
Group A -> DCV beta (pre-DV)
Feature ID | Feature Group | Feature Name | Feature Develop Leader | Feature Owner / D&R | HMI Feature Lead | Description / Comments | UE Delivery Expected by Software | Function Clarification Complete | UE Design Start | UE Delivery Plan Date (2 Weeks) | UE Sign-off Plan Date (1 Week) | Hero Screen expected by HMI | Studio Hero Screen Delivery Target Date | Ergo Sign-off on Hero Screens | UI Delivery expected by Software | UI Delivery Plan Date (2 Weeks) | UI Sign-off Plan Date (2 weeks) | Eng Release Version
| Launcher&system UI | Vehicle Card - normal | Ford In-house | n/a | Zhang, Yiwan (Y.) <yzhan435@ford.com> |  | Jan.20 | Feb.8 | Jan. 15 | Feb.25 | Mar. 4 | Mar. 18 | Mar.30 | Apr. 14 | Jan.25 | Apr. 28 | May 13 | R3(Apr.28 Integration)
Vehicle Card - TPMS is ON
Navigation Cad
Music Card
Video Card
Phone Card
|  | More Services (App Drawer/App Menu) | YFVE |  |  |  | Jan.20 | Feb.8 | Jan. 15 | Feb.25 | Mar. 4 | Mar. 18 | Mar.30 | Apr. 14 | Jan.25 | Apr. 28 | May 13 | R3(Apr.28 Integration)
Quick Panel
Recent Apps
Status Bar
Message hint and Message Center
| Climate | Climate Menu - Front | Ford In-house | Xie, Will (W.) <wxie15@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  | Feb.1 | Jan.29 -> Apr 3 | Feb.3 | Feb.20 -> Feb. 4 | Feb.26 -> Feb. 30 | Mar.5 | Mar.30 | Apr. 14 | Feb.8 | Apr. 28 | May 13 | R5(Jun.23 Integration)
Climate Menu - Rear
Climate Ribbon
Climate Menu
Heated Seats Slider
Heated Seats Mirror
Fan Slider
Temperature Slider
RACM (Rear Control Panel)
| Camera | 360 摄像头图像 2.0 360 Camera Image 2.0 | YFVE | Li, Xin (X.) <xli268@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Feb.1 | Feb.8 | Feb.18 | Mar.8 | Mar.15 | Mar.22 | Mar. 30 | Apr. 14 | Feb.8 | May 5 | May 19 | R5(Jun.23 Integration)
360 摄像头图像 360 Camera Image
|  | 360 泊车辅助 360 View Parking Assit |  | He, Michael (X.) <xhe22@ford.com>
|  | 前视摄像头 Off Road Front View Camera |  | Li, Xin (X.) <xli268@ford.com>
后视摄像头 Rear Camera On Demand
|  | 多种摄像头 Multi Camera - CHMSL/AUX Camera/Rock Crawl |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Apr. 14 | n/a | n/a | n/a | n/a
| Help Me Avoid Collisions 避免碰撞辅助 Move to Group B(2021/1/21) | 交通预警 Cross Traffic Alert |  | Zhou, Wu (W.) <wzhou44@ford.com> | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Apr. 14 | n/a | n/a | n/a | n/a
|  | 变道辅助 trail Turn Assist (Soft switch) |  | Li, Xuedong (X.)XLI244@ford.com | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Apr. 14 | n/a | n/a | n/a | n/a
| Radio | AM/FM View | YFVE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Wang, Wei Hua (Lisa) <wwang96@ford.com> |  | Jan.20 | Feb.8 | Feb.20 | Mar.8 | Mar.15 | Mar.22 | Mar. 30 | Apr. 14 | Jan.25 | May 5 | May 19 | R2(Mar.31 Integration)
Tuner
Direct Tune
| Music 音乐 | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) Moved to Group A | YFVE | Xu, Amy (X.) <xyafei@ford.com> | Chen, Yu (Y.) <ychen372@ford.com> |  | Mar.1 | Jan.29 | Feb.3 | Feb.20 | Feb.26 | Mar.5 | Mar. 30 | Apr. 14 | Mar.5 | Apr. 28 | May 13 | R5(Jun.23 Integration)
|  | 本地音乐-MTP音乐 MTP music/USB音乐 USB music/蓝牙音乐 BT music | YFVE | Amy Xu for BT Music Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Chen, Yu (Y.) <ychen372@ford.com> for Bluetooth Music, Wang, Wei Hua (Lisa) <wwang96@ford.com> for USB Music |  | Feb.1 | Jan.29 | Feb.3 | Feb.20 | Feb.26 | Mar.5 | Mar. 30 | Apr. 14 | Feb.8 | Apr. 28 | May 13 | R5(Jun.23 Integration)
|  | 随心听- Ximalaya 2.0 | Baidu |  | Wang, Wei Hua (Lisa) <wwang96@ford.com> |  | Apr.05 |  |  | Mar. 25 | Apr.05 | Apr.1 | Mar. 30 | Apr. 14 | Apr.30 | Apr.15 | Apr.30 | R5(Jun.23 Integration)
|  | 随心听- 音乐/新闻/有声书 (QQ 音乐-支持QQ 音乐账号登陆；喜马拉雅免费资源集成） | Baidu |  | Wang, Wei Hua (Lisa) <wwang96@ford.com> |  | Apr.05 |  |  | Mar. 25 | Apr.05 | Apr.1 | Mar. 30 | Apr. 14 | Apr.30 | Apr.15 | Apr.30 | R5(Jun.23 Integration)
|  | 随心听-QQ 音乐2.0 Suixinting: QQ Music 2.0 | Baidu |  | Wang, Wei Hua (Lisa) <wwang96@ford.com> |  | Apr.05 |  |  | Mar. 25 | Apr.05 | Apr.1 | Mar. 30 | Apr. 14 | Apr.30 | Apr.15 | Apr.30 | R5(Jun.23 Integration)
| Bluetooh Phone 蓝牙电话 | Active Call States | YFVE | Xu, Amy (X.) <xyafei@ford.com> | Chen, Yu (Y.) <ychen372@ford.com> |  | Feb.1 | Jan.29 | Feb.3 | Feb.20 | Feb.26 | Mar.5 | Mar. 30 | Apr. 14 | Feb.8 | Apr. 28 | May 13 | R5(Jun.23 Integration)
Recent Calls States (empty, single, full)
Contact View
Contact List (empty, single, full)
Dialog - Incoming Call
Phone Dialpad
Phone Number Pad
Phone Unconnected/Unpaired
Smart Search Layout
Phone Smart Search
| 1# Message Center | 消息&消息中心 notification & notification center | Baidu (Ford for HMI) | Wang, Johnny (J.) <jwang308@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  | Mar.30 |  |  | Mar. 15 | Mar. 30 | Mar. 22 | Mar. 30 | Apr. 14 | Apr.20 | Apr. 5 | Apr.20 | R5(Jun.23 Integration)
|  | 车机端消息管理 Project Aspire_Aspire Notificaitons | Baidu (Ford for HMI) |  |  |  | Mar.30 |  |  | Mar. 15 | Mar. 30 | Mar. 22 | Mar. 30 | Apr. 14 | Apr.20 | Apr. 5 | Apr.20 | R5(Jun.23 Integration)
| Navigation - Basic Function 基础导航功能 | 地图基础版（见《IOV-地图功能list) Foundamental version of Map | Baidu | Yao, Tristan (Lan) <LYAO17@ford.com> | Li, Jessie (J.) <jli316@ford.com> |  | Mar.30 |  |  | Mar. 15 | Mar. 30 | Mar. 22 | Mar. 30 | Apr. 14 | Apr.20 | Apr. 5 | Apr.20 | R5(Jun.23 Integration)
| Navigation - Basic Function 基础导航功能 | 开始导航倒计时/导航结束卡片 Starting/Ending Count Down | Baidu |  |  |  | Mar.30 |  |  | Mar. 15 | Mar. 30 | Mar. 22 | Mar. 30 | Apr. 14 | Apr.20 | Apr. 5 | Apr.20 | R5(Jun.23 Integration)
| Video 视频 | USB Video | YFVE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Feb.1 | Feb.8 | Feb.20 | Mar.8 | Mar.15 | Mar.22 | Mar. 30 | Apr. 14 | Feb.8 | May 5 | May 19 | R5(Jun.23 Integration)
| System Setting | 语音设置 audio setting | YFVE | Huang, Xue (X.) XHUANG93@ford.com | Pan, Jingjing (J.) <jpan35@ford.com> |  | Mar.1 | Feb.8 | Feb.9 | Mar.8 | Mar.15 | Mar.22 | Mar. 30 | Apr. 14 | Mar.5 | May 5 | May 19 | R5(Jun.23 Integration)
|  | 蓝牙连接 BT connection |  |  | Chen, Yu (Y.) <ychen372@ford.com> |  | Jan.20 | [7 empty] | Jan.25 |  |  | R3(Apr.28 Integration)
|  | 日期和时间设置 date&time setting |  |  | Wang, Wei Hua (Lisa) <wwang96@ford.com> |  | Mar.1 | [7 empty] | Mar.5 |  |  | R3(Apr.28 Integration)
|  | Brightness |  |  | Wang, Wei Hua (Lisa) <wwang97@ford.com> |  | Mar.1 | [7 empty] | Mar.5 |  |  | R5(Jun.23 Integration)
|  | Display off |  |  | Wang, Wei Hua (Lisa) <wwang98@ford.com> |  | Mar.1 | [7 empty] | Mar.5 |  |  | R5(Jun.23 Integration)
|  | 显示/亮度设置 display/brightness setting |  | Chen, James (J.) <jchen303@ford.com> | Wang, Wei Hua (Lisa) <wwang99@ford.com> |  | Mar.1 | [7 empty] | Mar.5 |  |  | R5(Jun.23 Integration)
|  | Support Ford external DSP module by A2B |  | Huang, Xue (X.) XHUANG93@ford.com | ?? |  | Mar.1 | [7 empty] | Mar.5 |  |  | R5(Jun.23 Integration)
|  | 关于本机 |  |  | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Mar.1 | [7 empty] | Mar.5 |  |  | R3(Apr.28 Integration)
|  | 声音设置 sound setting |  |  | Wang, Wei Hua (Lisa) <wwang99@ford.com> |  | Mar.1 | [7 empty] | Mar.5 |  |  | R5(Jun.23 Integration)
|  | Wifi 热点 Wifi Hot Spot |  |  | Wang, Wei Hua (Lisa) <wwang99@ford.com> |  | Mar.1 | [7 empty] | Mar.5 |  |  | R5(Jun.23 Integration)
|  | wifi设置 wifi setting |  |  | Wang, Wei Hua (Lisa) <wwang99@ford.com> |  | Jan.20 | [7 empty] | Jan.25 |  |  | R2(Mar.31 Integration)
|  | keyboard | Baidu | Yao, Tristan (Lan) <LYAO17@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Mar.30 |  |  | Mar. 15 | Mar. 30 | Mar. 22 | Mar. 30 | Apr. 14 | Apr.20 | Apr.5 | Apr.20 | R5(Jun.23 Integration)
| System Setting on IVI - Unit | Unit Setting-Measurement Units | YFVE | Li, Xuedong (X.) <XLI244@ford.com> | Wang, Wei Hua (Lisa) <wwang96@ford.com> |  | Mar.1 | Feb.8 | Feb.9 | Mar.8 | Mar.15 | Mar.22 | Mar. 30 | Apr. 14 | Mar.5 | May 5 | May 19 | R5(Jun.23 Integration)
Unit Setting-Temperature
Unit Setting-Tire Pressure Units;
| 1# Foundemental Voice Capability 基础语音功能 (new) | Quliang to confirm | Baidu | Qi, Xuliang <xqi14@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  | Apr.05 |  |  | Mar. 29 | Apr.05 | Apr. 1 | Mar. 30 | Apr. 14 | Apr.30 | Apr.15 | Apr.,30 | R5(Jun.23 Integration)
| DLNA (wants to add to Group A) |  | YFVE | Jia, Elaine (T.) <tjia2@ford.com> | Wang, Wei Hua (Lisa) <wwang96@ford.com> |  | Apr.05 | Feb.8 | Feb. 9 | Mar.8 | Mar.15 | Apr. 1 | Mar. 30 | Apr. 14 | Apr.30 | Apr.15 | Apr.,30 | R5(Jun.23 Integration)
Group B -> DCV 0 (DV)
Feature ID | Feature Group | Feature Name | Feature Develop Leader | Feature Owner / D&R | HMI Feature Lead | Description / Comments | UE Delivery expected by SW | Function Clarification | UE Design start | UE Delivery Plan Date | UE Sign-off Plan Date(1 Week) | Hero Screen expected by HMI | Hero Screen delivery target date | Ergo Sign-off on Hero Screens | UI Delivery expected by SW | UI Delivery Plan Date | UI Sign-off Plan Date(2 weeks) | Eng Release Version
| Navigation - Basic Function 基础导航功能 Moved to Group A | 地图基础版（见《IOV-地图功能list) Foundamental version of Map | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Navigation - Basic Function 基础导航功能 Moved to Group A | 开始导航倒计时/导航结束卡片 Starting/Ending Count Down | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Bluetooh Phone 蓝牙电话 Moved to Group A | Active Call States | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Recent Calls States (empty, single, full) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Contact View | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Contact List (empty, single, full) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Dialog - Incoming Call | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Phone Dialpad | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Phone Number Pad | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Phone Unconnected/Unpaired | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Smart Search Layout | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Phone Smart Search | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Music 音乐 Moved to Group A | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) Moved to Group A | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 本地音乐-MTP音乐 MTP music/USB音乐 USB music/蓝牙音乐 BT music | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 随心听- Ximalaya 2.0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 随心听- 音乐/新闻/有声书 (QQ 音乐-支持QQ 音乐账号登陆；喜马拉雅免费资源集成） | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 随心听-QQ 音乐2.0 Suixinting: QQ Music 2.0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Video 视频 | Online Video | Baidu | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com>
|  | USB Video moved to GroupA | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Radio | AM/FM View | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Tuner | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Direct Tune | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Online Radio | Baidu | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Wang, Wei Hua (Lisa) <wwang96@ford.com> | [7 empty] | May 15 | May 30
|  | 在线收音机/电台 Online Radio 资源提供方：蜻蜓FM | Baidu | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Wang, Wei Hua (Lisa) <wwang96@ford.com> | [7 empty] | May 15 | May 30
| System Setting Moved to Group A except Reset | 语音设置 audio setting | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 蓝牙连接 BT connection | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 日期和时间设置 date&time setting | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Brightness | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Display off | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 显示/亮度设置 display/brightness setting | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Support Ford external DSP module by A2B | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Infotainment Diagnostic Spec- Speaker walk around 挨个喇叭发出声音（工程模式下显示）- don't need HMI | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 关于本机 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 恢复出厂设置 reset（Master Reset） | YFVE | Ge, Haiqing (H.) <hge5@ford.com>HGE5@ford.com | Wang, Wei Hua (Lisa) <wwang96@ford.com> | - | Jun. 15 | [5 empty] | May 15 | May 30 | Jul.15 | Jun.15 |  | R8(Sept.15 Integration)
|  | 声音设置 sound setting | [10 empty] | May 15 | May 30
|  | Wifi 热点 Wifi Hot Spot | [10 empty] | May 15 | May 30
|  | wifi设置 wifi setting | [10 empty] | May 15 | May 30
|  | keyboard | [10 empty] | May 15 | May 30
| Vehicle Setting | Adaptive Steering |  | Li, Xuedong (X.) <XLI244@ford.com> | Wang, Wei Hua (Lisa) <wwang96@ford.com> | [7 empty] | May 15 | May 30
|  | Auto Hold |  |  | Wang, Wei Hua (Lisa) <wwang97@ford.com> | [7 empty] | May 15 | May 30
|  | Auto Stop Start |  |  | Wang, Wei Hua (Lisa) <wwang98@ford.com> | [7 empty] | May 15 | May 30
|  | BTT Light (Blind Spot Trailer Tow) |  |  | Wang, Wei Hua (Lisa) <wwang99@ford.com> | [7 empty] | May 15 | May 30
|  | Cruise control- Type (Adaptive, intelligent, normal), tolerance |  |  | Wang, Wei Hua (Lisa) <wwang100@ford.com> | [7 empty] | May 15 | May 30
|  | Driver alert |  |  | Wang, Wei Hua (Lisa) <wwang101@ford.com> | [7 empty] | May 15 | May 30
|  | Engine Stop Start threshold |  |  | Wang, Wei Hua (Lisa) <wwang102@ford.com> | [7 empty] | May 15 | May 30
|  | Grade Assits |  |  | Wang, Wei Hua (Lisa) <wwang103@ford.com> | [7 empty] | May 15 | May 30
|  | Hill Decent Control |  |  | Wang, Wei Hua (Lisa) <wwang104@ford.com> | [7 empty] | May 15 | May 30
|  | Hill start assist |  |  | Wang, Wei Hua (Lisa) <wwang105@ford.com> | [7 empty] | May 15 | May 30
|  | Lane keeping mode (alert, aid, alert + aid), alert intensity (high, medium, low), sensitvity (normal, increased), lane keeping aid (on, off), lane keeping alert (high, medium, low, on, off) |  |  | Wang, Wei Hua (Lisa) <wwang106@ford.com> | [7 empty] | May 15 | May 30
|  | Pre Collision Assist (pre collision assist, distance indication, active breaking, evasive steer assist, alert sensitivity (high medium low)) |  |  | Wang, Wei Hua (Lisa) <wwang107@ford.com> | [7 empty] | May 15 | May 30
|  | Speed Limit Information / Speed Sign Recognition |  |  | Wang, Wei Hua (Lisa) <wwang108@ford.com> | [7 empty] | May 15 | May 30
|  | Speed Limiter |  |  | Wang, Wei Hua (Lisa) <wwang109@ford.com> | [7 empty] | May 15 | May 30
|  | Tow Haul |  |  | Wang, Wei Hua (Lisa) <wwang110@ford.com> | [7 empty] | May 15 | May 30
|  | Traction Control |  |  | Wang, Wei Hua (Lisa) <wwang111@ford.com> | [7 empty] | May 15 | May 30
|  | Traffic Sign Recognition |  |  | Wang, Wei Hua (Lisa) <wwang112@ford.com> | [7 empty] | May 15 | May 30
|  | Trailer Sway |  |  | Wang, Wei Hua (Lisa) <wwang113@ford.com> | [7 empty] | May 15 | May 30
|  | Wrong Way alert |  |  | Wang, Wei Hua (Lisa) <wwang114@ford.com> | [7 empty] | May 15 | May 30
| Vehicle Setting on IVI - Light | Light Setting-Adaptive headlamps |  |  | Wang, Wei Hua (Lisa) <wwang96@ford.com> | [7 empty] | May 15 | May 30
|  | Light Setting-Auto highbeam |  |  | Wang, Wei Hua (Lisa) <wwang97@ford.com> | [7 empty] | May 15 | May 30
|  | Light Setting-Autolamp delay |  |  | Wang, Wei Hua (Lisa) <wwang98@ford.com> | [7 empty] | May 15 | May 30
|  | Light Setting-daytime lights |  |  | Wang, Wei Hua (Lisa) <wwang99@ford.com> | [7 empty] | May 15 | May 30
|  | Light Setting-Glare Free lighting |  |  | Wang, Wei Hua (Lisa) <wwang100@ford.com> | [7 empty] | May 15 | May 30
|  | Light Setting-welcome lights |  |  | Wang, Wei Hua (Lisa) <wwang101@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln colors |  |  | Wang, Wei Hua (Lisa) <wwang102@ford.com> | [7 empty] | May 15 | May 30
|  | 单色氛围灯 single color ambient lighting |  |  | Wang, Wei Hua (Lisa) <wwang103@ford.com> | [7 empty] | May 15 | May 30
|  | 多色氛围灯 multi color ambient lighting |  |  | Wang, Wei Hua (Lisa) <wwang104@ford.com> | [7 empty] | May 15 | May 30
| Vehicle Setting on IVI - Lock | Lock Setting-Audible feedback |  |  | Wang, Wei Hua (Lisa) <wwang105@ford.com> | [7 empty] | May 15 | May 30
|  | Lock Setting-auto unlock |  |  | Wang, Wei Hua (Lisa) <wwang106@ford.com> | [7 empty] | May 15 | May 30
|  | Lock Setting-autolock |  |  | Wang, Wei Hua (Lisa) <wwang107@ford.com> | [7 empty] | May 15 | May 30
|  | Lock Setting-Exterior light feedback |  |  | Wang, Wei Hua (Lisa) <wwang108@ford.com> | [7 empty] | May 15 | May 30
|  | Lock Setting-Global unlock |  |  | Wang, Wei Hua (Lisa) <wwang109@ford.com> | [7 empty] | May 15 | May 30
|  | Lock Setting-Intelligent access |  |  | Wang, Wei Hua (Lisa) <wwang110@ford.com> | [7 empty] | May 15 | May 30
|  | Lock Setting-Key free |  |  | Wang, Wei Hua (Lisa) <wwang111@ford.com> | [7 empty] | May 15 | May 30
|  | Lock Setting-mislock |  |  | Wang, Wei Hua (Lisa) <wwang112@ford.com> | [7 empty] | May 15 | May 30
|  | Lock Setting-Remote unlock |  |  | Wang, Wei Hua (Lisa) <wwang113@ford.com> | [7 empty] | May 15 | May 30
|  | Lock Setting-switch inhibit |  |  | Wang, Wei Hua (Lisa) <wwang114@ford.com> | [7 empty] | May 15 | May 30
| Vehicle Setting on IVI - Mirror | Mirror Setting-Autofold |  |  | Wang, Wei Hua (Lisa) <wwang115@ford.com> | [7 empty] | May 15 | May 30
|  | Mirror Setting-Reverse tilt |  |  | Wang, Wei Hua (Lisa) <wwang116@ford.com> | [7 empty] | May 15 | May 30
| Vehicle Setting on IVI - Others | Active Noise Cancellation |  |  | Wang, Wei Hua (Lisa) <wwang117@ford.com> | [7 empty] | May 15 | May 30
|  | Air suspension |  |  | Wang, Wei Hua (Lisa) <wwang118@ford.com> | [7 empty] | May 15 | May 30
|  | Alarm (ask on exit ,sensor set, perimeter, all sensors active) |  |  | Wang, Wei Hua (Lisa) <wwang119@ford.com> | [7 empty] | May 15 | May 30
|  | Aux Heater |  |  | Wang, Wei Hua (Lisa) <wwang120@ford.com> | [7 empty] | May 15 | May 30
|  | Cargo Loading |  |  | Wang, Wei Hua (Lisa) <wwang121@ford.com> | [7 empty] | May 15 | May 30
|  | Chimes |  |  | Wang, Wei Hua (Lisa) <wwang122@ford.com> | [7 empty] | May 15 | May 30
|  | Easy access height |  |  | Wang, Wei Hua (Lisa) <wwang123@ford.com> | [7 empty] | May 15 | May 30
|  | Easy Entry / Easy Exit (Seat Adjustment) |  |  | Wang, Wei Hua (Lisa) <wwang124@ford.com> | [7 empty] | May 15 | May 30
|  | Ford Vehicle Settings On IVI [include: AutoHold, AutoStartStop.] |  |  | Wang, Wei Hua (Lisa) <wwang125@ford.com> | [7 empty] | May 15 | May 30
|  | Park Heater |  |  | Wang, Wei Hua (Lisa) <wwang126@ford.com> | [7 empty] | May 15 | May 30
|  | Park Lock Control |  |  | Wang, Wei Hua (Lisa) <wwang127@ford.com> | [7 empty] | May 15 | May 30
|  | Passenger Airbag |  |  | Wang, Wei Hua (Lisa) <wwang128@ford.com> | [7 empty] | May 15 | May 30
|  | Power running boards (auto, on, off) |  |  | Wang, Wei Hua (Lisa) <wwang129@ford.com> | [7 empty] | May 15 | May 30
|  | Rear liftgate |  |  | Wang, Wei Hua (Lisa) <wwang130@ford.com> | [7 empty] | May 15 | May 30
|  | Remote start (activate, climate, auto, last setting, seats and wheels, duration) |  |  | Wang, Wei Hua (Lisa) <wwang131@ford.com> | [7 empty] | May 15 | May 30
|  | Silent Mode |  |  | Wang, Wei Hua (Lisa) <wwang132@ford.com> | [7 empty] | May 15 | May 30
|  | Tire Mobility Kit |  |  | Wang, Wei Hua (Lisa) <wwang133@ford.com> | [7 empty] | May 15 | May 30
|  | Windows (remote open/close) |  |  | Wang, Wei Hua (Lisa) <wwang134@ford.com> | [7 empty] | May 15 | May 30
|  | Wipers (courtesy, rain, reverse) |  |  | Wang, Wei Hua (Lisa) <wwang135@ford.com> | [7 empty] | May 15 | May 30
| 2# Help Me Drive 驾驶辅助 - Vehicle Setting | 巡航 ACC |  | DAT setting should be updated confirmed with FO, FO as below: Cui, Victor (M.) <mcui5@ford.com>/Song, Amy (S.) <ssong18@ford.com>/Wang, Lynn (X.) <xwang187@ford.com>/Ni, Anthony | Wang, Wei Hua (Lisa) <wwang136@ford.com> | [7 empty] | May 15 | May 30
|  | 智能车速辅助 Intelligent Speed Assistance |  |  | Wang, Wei Hua (Lisa) <wwang137@ford.com> | [7 empty] | May 15 | May 30
|  | 自适应巡航设置 iACC 1.0 |  |  | Wang, Wei Hua (Lisa) <wwang138@ford.com> | [7 empty] | May 15 | May 30
| Help Me Avoid Collisions 避免碰撞辅助 | 交通预警 Cross Traffic Alert |  | Zhou, Wu (W.) <wzhou44@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | [7 empty] | May 15 | May 30
|  | 变道辅助 trail Turn Assist (Soft switch) |  | Li, Xuedong (X.)XLI244@ford.com | Zou, Yujuan (Y.) <yzou32@ford.com> | [7 empty] | May 15 | May 30
| System Setting on IVI - Unit Moved to Group A | Unit Setting-Measurement Units | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Unit Setting-Temperature | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | Unit Setting-Tire Pressure Units; | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Shortcut Keys | Climate (menu and rear shortcut keys)-Auto Air Refresh (AAR) |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa | Zhang, Yiwan (Y.) <yzhan435@ford.com> | [7 empty] | May 15 | May 30
|  | Climate (menu and rear shortcut keys)-climate in rear display |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa | Zhang, Yiwan (Y.) <yzhan436@ford.com> | [7 empty] | May 15 | May 30
|  | Climate (menu and rear shortcut keys)-Rear- Tri or Quad Zone climate |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa | Zhang, Yiwan (Y.) <yzhan437@ford.com> | [7 empty] | May 15 | May 30
|  | IVI interface via press physical switch 实体键IVI交互 |  | Li, Xuedong (X.) <XLI244@ford.com> | Zhang, Yiwan (Y.) <yzhan438@ford.com> | [7 empty] | May 15 | May 30
|  | Climate (menu and rear shortcut keys)-climate in rear display |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa | Zhang, Yiwan (Y.) <yzhan439@ford.com> | [7 empty] | May 15 | May 30
|  | Climate (menu and rear shortcut keys)-Auto Air Refresh (AAR) |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa | Zhang, Yiwan (Y.) <yzhan440@ford.com> | [7 empty] | May 15 | May 30
|  | Climate (menu and rear shortcut keys)-Rear- Tri or Quad Zone climate |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa | Zhang, Yiwan (Y.) <yzhan441@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln Seats |  | Li, Xuedong (X.) <XLI244@ford.com> | Zhang, Yiwan (Y.) <yzhan442@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln Camera Shortcut key |  |  | Zhang, Yiwan (Y.) <yzhan443@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln Park Assist Shortcut key-Autoparking |  |  | Zhang, Yiwan (Y.) <yzhan444@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln Park Assist Shortcut key-Park aid on off |  |  | Zhang, Yiwan (Y.) <yzhan445@ford.com> | [7 empty] | May 15 | May 30
|  | Adaptive Steering |  |  | Zhang, Yiwan (Y.) <yzhan446@ford.com> | [7 empty] | May 15 | May 30
|  | BTT Light (Blind Spot Trailer Tow) |  |  | Zhang, Yiwan (Y.) <yzhan447@ford.com> | [7 empty] | May 15 | May 30
|  | Hill Decent Control |  |  | Zhang, Yiwan (Y.) <yzhan448@ford.com> | [7 empty] | May 15 | May 30
|  | Speed Limit Information / Speed Sign Recognition |  |  | Zhang, Yiwan (Y.) <yzhan449@ford.com> | [7 empty] | May 15 | May 30
|  | Traffic Sign Recognition |  |  | Zhang, Yiwan (Y.) <yzhan450@ford.com> | [7 empty] | May 15 | May 30
|  | Speed Limiter |  |  | Zhang, Yiwan (Y.) <yzhan451@ford.com> | [7 empty] | May 15 | May 30
|  | Rear Park Aid |  |  | Zhang, Yiwan (Y.) <yzhan452@ford.com> | [7 empty] | May 15 | May 30
|  | Tow Haul |  |  | Zhang, Yiwan (Y.) <yzhan453@ford.com> | [7 empty] | May 15 | May 30
|  | Engine Stop Start threshold |  |  | Zhang, Yiwan (Y.) <yzhan454@ford.com> | [7 empty] | May 15 | May 30
|  | PADI |  |  | Zhang, Yiwan (Y.) <yzhan455@ford.com> | [7 empty] | May 15 | May 30
|  | Grade Assits |  |  | Zhang, Yiwan (Y.) <yzhan456@ford.com> | [7 empty] | May 15 | May 30
|  | Trailer Sway |  |  | Zhang, Yiwan (Y.) <yzhan457@ford.com> | [7 empty] | May 15 | May 30
|  | Driver alert |  |  | Zhang, Yiwan (Y.) <yzhan458@ford.com> | [7 empty] | May 15 | May 30
|  | Hill start assist |  |  | Zhang, Yiwan (Y.) <yzhan459@ford.com> | [7 empty] | May 15 | May 30
|  | Wrong Way alert |  |  | Zhang, Yiwan (Y.) <yzhan460@ford.com> | [7 empty] | May 15 | May 30
|  | Cross Traffic Alert |  |  | Zhang, Yiwan (Y.) <yzhan461@ford.com> | [7 empty] | May 15 | May 30
|  | Blind Spot |  |  | Zhang, Yiwan (Y.) <yzhan462@ford.com> | [7 empty] | May 15 | May 30
|  | Pre Collision Assist (pre collision assist, distance indication, active breaking, evasive steer assist, alert sensitivity (high medium low)) |  |  | Zhang, Yiwan (Y.) <yzhan463@ford.com> | [7 empty] | May 15 | May 30
|  | Lane keeping mode (alert, aid, alert + aid), alert intensity (high, medium, low), sensitvity (normal, increased), lane keeping aid (on, off), lane keeping alert (high, medium, low, on, off) |  |  | Zhang, Yiwan (Y.) <yzhan464@ford.com> | [7 empty] | May 15 | May 30
|  | Cruise control- Type (Adaptive, intelligent, normal), tolerance |  |  | Zhang, Yiwan (Y.) <yzhan465@ford.com> | [7 empty] | May 15 | May 30
|  | Traction Control |  |  | Zhang, Yiwan (Y.) <yzhan466@ford.com> | [7 empty] | May 15 | May 30
|  | Auto Hold |  |  | Zhang, Yiwan (Y.) <yzhan467@ford.com> | [7 empty] | May 15 | May 30
|  | Auto Stop Start |  |  | Zhang, Yiwan (Y.) <yzhan468@ford.com> | [7 empty] | May 15 | May 30
|  | modified mini ICP |  |  | Zhang, Yiwan (Y.) <yzhan469@ford.com> | [7 empty] | May 15 | May 30
|  | Multi-Function Knob |  |  | Zhang, Yiwan (Y.) <yzhan470@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln Camera Shortcut key |  |  | Zhang, Yiwan (Y.) <yzhan471@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln Park Assist Shortcut key-Autoparking |  |  | Zhang, Yiwan (Y.) <yzhan472@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln Park Assist Shortcut key-Park aid on off |  |  | Zhang, Yiwan (Y.) <yzhan473@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln Seats shortcut |  |  | Zhang, Yiwan (Y.) <yzhan474@ford.com> | [7 empty] | May 15 | May 30
|  | Lincoln Seats shortcut key |  |  | Zhang, Yiwan (Y.) <yzhan475@ford.com> | [7 empty] | May 15 | May 30
|  | Multi-Contoured Seats (Massage Seats) |  |  | Zhang, Yiwan (Y.) <yzhan476@ford.com> | [7 empty] | May 15 | May 30
|  | Multi-Function Knob |  |  | Zhang, Yiwan (Y.) <yzhan477@ford.com> | [7 empty] | May 15 | May 30
|  | PADI |  |  | Zhang, Yiwan (Y.) <yzhan478@ford.com> | [7 empty] | May 15 | May 30
|  | Rear Park Aid |  |  | Zhang, Yiwan (Y.) <yzhan479@ford.com> | [7 empty] | May 15 | May 30
| Soft Button | Ambient Lighting - Breath Control (setting: on/off) |  | Fu, Theo (X.) <XFU7@ford.com> | Wang, Wei Hua (Lisa) <wwang96@ford.com> | [7 empty] | May 15 | May 30
|  | Ambient Lighting - Music Visualizer |  | Fu, Theo (X.) <XFU7@ford.com> | Wang, Wei Hua (Lisa) <wwang97@ford.com> | [7 empty] | May 15 | May 30
|  | Power Running Boards (PRB) |  | Li, Xuedong (X.) <xli244@ford.com>/Chen, Emma (J.) <jchen276@ford.com> | Wang, Wei Hua (Lisa) <wwang98@ford.com> | [7 empty] | May 15 | May 30
|  | Power Tailgate (FordPass/SYNC); |  | Li, Xuedong (X.) <xli244@ford.com>/Chen, Emma (J.) <jchen276@ford.com> | Wang, Wei Hua (Lisa) <wwang99@ford.com> | [7 empty] | May 15 | May 30
| Navigation - Intelligent Function 智能导航功能 | 个性化底图-4S店POI显示 4S Dealer POI on Map | Baidu | Yao, Tristan (Lan) <LYAO17@ford.com> | Li, Jessie (J.) <jli316@ford.com> | [7 empty] | May 15 | May 30
|  | 本地危险事件上报及播报 LHI (Local Hazard Information) | Baidu | Lin, Shawn (X.) <xlin17@ford.com> | Li, Jessie (J.) <jli317@ford.com> | [7 empty] | May 15 | May 30
|  | 电子地平线（电子视野）EH - Electronical Horizon | Baidu | Cui, Victor (M.) <mcui5@ford.com> | Li, Jessie (J.) <jli318@ford.com> | [7 empty] | May 15 | May 30
| 3# Navigation - Team Travel 组队出行 | 组队出行 Team Travel | Baidu | Yao, Tristan (Lan) <LYAO17@ford.com> | Li, Jessie (J.) <jli319@ford.com> | [7 empty] | May 15 | May 30
| 4# POI Sharing/Receiving 地址分享 地址分享 | 微信地址分享 WeChat Send To Car | Baidu | Yao, Tristan (Lan) <LYAO17@ford.com> | Li, Jessie (J.) <jli320@ford.com> | [7 empty] | May 15 | May 30
|  | 福特派/林肯之道地址分享 FordPass/LincolnWay Send to car | Baidu | Shi, Stella (J.) <jshi32@ford.com> | Li, Jessie (J.) <jli321@ford.com> | [7 empty] | May 15 | May 30
| 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | 车辆状态 Vehicle Status (Vehicle Locator车辆位置, Mileage总里程, DTE 续航里程， Tire Pressure 胎压）On IVI 或Fordpass/Lincoln Way， 同时支持智能音箱在家查询 | ？ | Lu, Chao (C.) <clu42@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | [7 empty] | May 15 | May 30
Group C - > DCV 1
Feature ID | Feature Group | Feature Name | Feature Develop Leader | Feature Owner / D&R | HMI Feature Lead | Description / Comments | UE Delivery expected by SW | Function Clarification | UE Design start | UE Delivery Plan Date | UE Sign-off Plan Date(1 Week) | Hero Screen expected by HMI | Hero Screen delivery target date | Ergo Sign-off on Hero Screens | UI Delivery expected by SW | UI Delivery Plan Date | UI Sign-off Plan Date(2 weeks) | Eng Release Version
| Navigation - Intelligent Function 智能导航功能 Moved to Group B | 个性化底图-4S店POI显示 4S Dealer POI on Map | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Moved to Group B | 本地危险事件上报及播报 LHI (Local Hazard Information) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Moved to Group B | 电子地平线（电子视野）EH - Electronical Horizon | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 3# Navigation - Team Travel 组队出行 Moved to Group B | 组队出行 Team Travel | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 4# POI Sharing/Receiving 地址分享 地址分享 Moved to Group B | 微信地址分享 WeChat Send To Car | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| Moved to Group B | 福特派/林肯之道地址分享 FordPass/LincolnWay Send to car | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 Moved to Group B | 车辆状态 Vehicle Status (Vehicle Locator车辆位置, Mileage总里程, DTE 续航里程， Tire Pressure 胎压）On IVI 或Fordpass/Lincoln Way， 同时支持智能音箱在家查询 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 1# Foundemental Voice Capability 基础语音功能 | 多种TTS播报语音 Multiple TTS |  |  | Pan, Jingjing (J.) <jpan35@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 所见即可说 All the soft bottons in touch screen support voice command, inlucding selecting listed options |  |  | Pan, Jingjing (J.) <jpan36@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 音乐域/导航 支持中英文混杂 Chinese/English mixed music/navigation recognition |  |  | Pan, Jingjing (J.) <jpan37@ford.com> | [7 empty] | Jun. 31 | Jul. 15
| 7# VPA 形象化语音助手 | 语音助手3.0 VPA 3.0 Project Aspire_Intelligent Digital Assistant _ CN |  |  | Wang, Alisa (Y.) <ywang329@ford.com> | [7 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 随心拍 Travel Shooting |  |  | Pan, Jingjing (J.) <jpan37@ford.com> | [7 empty] | Jun. 31 | Jul. 15
| 3# Voice Control - IVI Application 语音控制 - 信息娱乐系统 | 电子用户手册语音搜索 E-Manual Voice Search |  |  | Pan, Jingjing (J.) <jpan37@ford.com> | [7 empty] | Jun. 31 | Jul. 15
| 4# Voice Wakeup/Passenger Command Capability 语音唤醒和分区控制 | 自定义语音唤醒词 Customized Wake-up keyword 林肯的语音唤醒词“你好，林肯” Lincoln wake-up commands 福特的语音唤醒词“你好，福特” Ford wake-up commands 核心功能场景化免唤醒命令 Wake-up command is not mandatory to activate for key functions |  |  | Pan, Jingjing (J.) <jpan37@ford.com> | [7 empty] | Jun. 31 | Jul. 15
| 5# AI Q&A 智能问答 | 世界之最 Most ** of the world |  |  | Pan, Jingjing (J.) <jpan38@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 人物百科 Celebrity encyclopedia |  |  | Pan, Jingjing (J.) <jpan39@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 地理 Geography |  |  | Pan, Jingjing (J.) <jpan40@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 天气 Weather |  |  | Pan, Jingjing (J.) <jpan41@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 彩票 Lotery |  |  | Pan, Jingjing (J.) <jpan42@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 日历 Calendar |  |  | Pan, Jingjing (J.) <jpan43@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 机票/航班信息 air ticket/flight info |  |  | Pan, Jingjing (J.) <jpan44@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 汇率 Exchange rate |  |  | Pan, Jingjing (J.) <jpan45@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 火车票 train |  |  | Pan, Jingjing (J.) <jpan46@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 热映电影 Popular movie |  |  | Pan, Jingjing (J.) <jpan47@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 电影票/外卖 movie ticket/take away |  |  | Pan, Jingjing (J.) <jpan48@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 电视剧基础属性 Episodes |  |  | Pan, Jingjing (J.) <jpan49@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 笑话 Jokes |  |  | Pan, Jingjing (J.) <jpan50@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 股价 Share price |  |  | Pan, Jingjing (J.) <jpan51@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 诗词 Poem |  |  | Pan, Jingjing (J.) <jpan52@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 闲聊 Chat |  |  | Pan, Jingjing (J.) <jpan53@ford.com> | [7 empty] | Jun. 31 | Jul. 15
|  | 限行 Traffic control info - License plate restriction |  |  | Pan, Jingjing (J.) <jpan54@ford.com> | [7 empty] | Jun. 31 | Jul. 15
| 7# VPA 形象化语音助手 | 交互界面Interaction page |  |  | Wang, Alisa (Y.) <ywang329@ford.com> | [7 empty] | Jun. 31 | Jul. 15
| 7# VPA 形象化语音助手 | 语音助手形象VPA 1.0 (Avatar Only） |  |  | Wang, Alisa (Y.) <ywang329@ford.com> | [7 empty] | Jun. 31 | Jul. 15
| 2# Help Me Drive 驾驶辅助 Moved to Group B | 巡航 ACC | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 智能车速辅助 Intelligent Speed Assistance | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  | 自适应巡航设置 iACC 1.0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 1# Life Service 生活服务 | 车机相册 IVI Picture Gallery |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 客人模式Smart Scene - Guest Mode |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 智慧指令 Smart Scene - Smart Order |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 用户日程显示Project Aspire_Routines / Daily View_IVI Calendar |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 电影票预定 Movie Ticket Booking |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 福特/林肯金融 Ford Credit |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 美团外卖MeiTuanTake-away |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
| 2# Travel Service 出行服务 | 随心拍Traveling Shooting |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
| 1# Life Service 生活服务 | 鲜花预定Order flower delivery |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
| 2# Travel Service 出行服务 | 机票查询 Flight search |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 火车票查询 Train ticket search |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 路书 (App -去兜风) Project Aspire_Route 66 / Tourist Mode (Education and Historical POIs)_CN (Route 66/Travel Book) |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 酒店预定 Hotel booking |  |  | Mini program under study | [7 empty] | Jun. 31 | Jul. 15
|  | 随心拍Travel Shooting 2.0 Project Aspire_Photos (GPS Created Trip Summary) |  |  | Luisa Liu | [7 empty] | Jun. 31 | Jul. 15
| 1# Account 账号 | 车机端百度账号登陆(By 福特派/lincoln app) Baidu Login |  |  | Zou Yujuan | [7 empty] | Jun. 31 | Jul. 15
| 2# Personalized Profile 个人设置档案 | 个性化设置记忆 Enhanced Memory |  |  | Zou Yujuan | [7 empty] | Jun. 31 | Jul. 15
| 1# Message Center Moved to Group A | 消息&消息中心 notification & notification center | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 1# Message Center Moved To Group A | 车机端消息管理 Project Aspire_Aspire Notificaitons | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 1# Charging Setting | 充电冲突提醒Charge Conflict Notification Popups | [10 empty] | Jun. 31 | Jul. 15
|  | 充电接口灯设置Charge Port Light Settings | [10 empty] | Jun. 31 | Jul. 15
|  | 充电流动画显示Power Flow | [10 empty] | Jun. 31 | Jul. 15
|  | 充电状态Battery Status of Charge | [10 empty] | Jun. 31 | Jul. 15
|  | 出发时间设置Departure Time Settings | [10 empty] | Jun. 31 | Jul. 15
|  | 推荐充电时间Preferred Charge Time | [10 empty] | Jun. 31 | Jul. 15
| 2# Distance to Empty (DTE) | 剩余里程显示(云端)Cloud Enhanced Distance to Empty | [10 empty] | Jun. 31 | Jul. 15
| 2# Distance to Empty (DTE) | 剩余里程显示Range Ring-Nav Screen （DTE) | [10 empty] | Jun. 31 | Jul. 15
| 3# BEV Unique | 前备箱软按键 IVI Soft touch-frunk | [10 empty] | Jun. 31 | Jul. 15
| 3# BEV Unique | 单踏板驾驶One Pedal Drive | [10 empty] | Jun. 31 | Jul. 15
| 3# BEV Unique | 智慧充电Smart Charging | [10 empty] | Jun. 31 | Jul. 15
| 3# BEV Unique | 行程计划Trip Planner | [10 empty] | Jun. 31 | Jul. 15
| 4# Charing Station Finder | 充电桩查找Station Finder | [10 empty] | Jun. 31 | Jul. 15
| 1# CAN/USB 升级 | CAN/USB 升级 | [10 empty] | Jun. 31 | Jul. 15
| Audio System | Brand Audio Config (Lincoln/Ford) | [10 empty] | Jun. 31 | Jul. 15
| Audio System | Engine Sound Enhancement (ESE) | [10 empty] | Jun. 31 | Jul. 15
| Audio System | Lincoln more speakers audio & ANC tuning | [10 empty] | Jun. 31 | Jul. 15
| Connected Services | CCS (Connectivity Control Setting) | [10 empty] | Jun. 31 | Jul. 15
| Connected Services | Message Center | [10 empty] | Jun. 31 | Jul. 15
| General Connected Feature | Embedded Modem Reset/Master reset | [10 empty] | Jun. 31 | Jul. 15
| General Connected Feature | FNV2 - FCI Protocol | [10 empty] | Jun. 31 | Jul. 15
| General Connected Feature | IP Pass Through Client | [10 empty] | Jun. 31 | Jul. 15
| General Connected Feature | Peripheral Provisioning | [10 empty] | Jun. 31 | Jul. 15
| IVI Support Vehicle Function | Phone Wireless Charging notification | [10 empty] | Jun. 31 | Jul. 15
| MCU features | MCU software download (via CAN) | [10 empty] | Jun. 31 | Jul. 15
| Soft Button | 手机端福特派&账号互通 Fordpass & account connection | [10 empty] | Jun. 31 | Jul. 15
| 2# OTA | IVI空中升级SYNC+ OTA | [10 empty] | Jun. 31 | Jul. 15
| 2# OTA | 多模块空中升级 Multi Module OTA (MMOTA) (including: USB Update for TCU and ECG; IVI VMCU, CCPU...) | [10 empty] | Jun. 31 | Jul. 15
| TCU | Ford Clock Strategy | [10 empty] | Jun. 31 | Jul. 15
| TCU | TCU- 用户流量统计及购买/Cellular data purchase and management | [10 empty] | Jun. 31 | Jul. 15
| 6# AR Navigation AR 导航 | AR 导航 AR Navigation | [10 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | AR 导航 AR Navigation On Cluster (Driver Side) | [10 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 前备箱打开控制 Frunk Control -Open |  |  |  | CDX727 (BEV) _lead | [6 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 后备箱打开控制 Trunk Control-Open | [10 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 天窗/遮阳帘控制 Roof window control |  |  |  | 天窗和遮阳帘可以分开控制。但是都由一条CAN 总线实现 | [6 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 座椅加热/通风控制/按摩 Seat Heating&Cooling/Seat Vented/Seat Massage |  |  |  | 三个功能可分开并且强依赖硬件，需核对项目HW Book 情况，确定具体落地 | [6 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 数字香氛 Digital Scent | [10 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 方向盘加热 Heated Steering Wheels Control | [10 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 氛围灯开关 Ambient Lighting on/off |  |  |  | 打开/关闭 | [6 empty] | Jun. 31 | Jul. 15
| 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | "出风等级控制 Air volume-增加风量 出风等级控制 Air volume-风量大一点 出风等级控制 Air volume-减少风量 出风等级控制 Air volume-风量小一点 出风等级控制 Air volume-风量正常 出风等级控制 Air volume-调整风量到xx档" "空气系统控制 Climate system control-调整出风方向/下一个出风方向 Air flow direction 空气系统控制 Climate system control-打开/关闭自动除霜系统 defrost 空气系统控制 Climate system control-打开/关闭内循环 recirc 空气系统控制 Climate system control-打开/关闭空气清新系统 fresh air 空气系统控制 Climate system control-打开/关闭后挡风除霜 rear deforst 空气系统控制 Climate system control-打开/关闭自动模式 Auto mode" "打开/关闭空调 open/close AC 空调控制 AC control-设置空调温度到xx度 Temp setting 空调控制 AC control-提高温度 Temp up 空调控制 AC control-降低温度 Temp down 空调控制 AC control-温度最低/最低温度 LO 空调控制 AC control-温度最高/最高温度 HI" |  |  |  | "出风等级控制 Air volume-增加风量 出风等级控制 Air volume-风量大一点 出风等级控制 Air volume-减少风量 出风等级控制 Air volume-风量小一点 出风等级控制 Air volume-风量正常 出风等级控制 Air volume-调整风量到xx档" "空气系统控制 Climate system control-调整出风方向/下一个出风方向 Air flow direction 空气系统控制 Climate system control-打开/关闭自动除霜系统 defrost 空气系统控制 Climate system control-打开/关闭内循环 recirc 空气系统控制 Climate system control-打开/关闭空气清新系统 fresh air 空气系统控制 Climate system control-打开/关闭后挡风除霜 rear deforst 空气系统控制 Climate system control-打开/关闭自动模式 Auto mode" "打开/关闭空调 open/close AC 空调控制 AC control-设置空调温度到xx度 Temp setting 空调控制 AC control-提高温度 Temp up 空调控制 AC control-降低温度 Temp down 空调控制 AC control-温度最低/最低温度 LO 空调控制 AC control-温度最高/最高温度 HI" | [6 empty] | Jun. 31 | Jul. 15
| 4# Voice Wakeup/Passenger Command Capability 语音唤醒和分区控制 | 双音区语音控制 Dual Zone Voice Control |  |  |  | ast Volum;A /C Temperature;Seat Heating;Speaker volumn;Massage) | [6 empty] | Jun. 31 | Jul. 15
| 6# Vehicle Status Query | 油量 Fuel status;胎压 Tire pressure;车辆剩余里程 mileage; | [10 empty] | Jun. 31 | Jul. 15
| 1# Help Me Park 停车辅助 | FAPA硬/软按键 Fully automated park assist (FAPA) - hard short cut/HMI |  |  |  | Lincoln Fully automated park assist (hard shortcut keys/HMI) | [6 empty] | Jun. 31 | Jul. 15
| 1# Help Me Park 停车辅助 | FAPA语音推荐/指导 Fully automated park assist (FAPA) - Voice Recommend / Guidance | [10 empty] | Jun. 31 | Jul. 15
| 1# Help Me Park 停车辅助 | 全自动泊车 Fully Assisted Parking (FIPa, FIPe, FOPa) | [10 empty] | Jun. 31 | Jul. 15
| 1# Help Me Park 停车辅助 | 制动辅助 Reverse Brake Assist (RBA) | [10 empty] | Jun. 31 | Jul. 15
| 1# Help Me Park 停车辅助 | 泊车辅助 RPA-Reverse Parking Aid |  |  |  | 4 ultra sonic sense (USS) only; Example obstical warning e.g fiesta high series | [6 empty] | Jun. 31 | Jul. 15
| 2# Help Me Drive 驾驶辅助 | 车路协同 V2I Lite |  |  |  | 纯软件的基于IVI 的China Local Solution including 4 features •Traffic Light Information(TLI) •Green Light Notification (GLN) •Green Light Optimal Speed Advisory(GLOSA) •Red Light Violation Warning(RLVW) | [6 empty] | Jun. 31 | Jul. 15
| 1# Camera Related 摄像头相关 | 人脸识别账户登录Face ID - Driver (Registration, Recognition, Account, Personalization, Welcome) | [10 empty] | Jun. 31 | Jul. 15
| 1# Camera Related 摄像头相关 | IVI 驾驶员状态监控和报警 IVI Drive Status Monitor & Alert (Fatigue, Distraction, Dangers Behaviour) | [10 empty] | Jun. 31 | Jul. 15
| 2# Vehicle Streaming Platform | 车辆流媒体平台Vehicle Streaming Platform (VSP) | [10 empty] | Jun. 31 | Jul. 15
| 1# Emergency Services 紧急救援 | 升级版紧急救援/服务 eCall |  |  |  | CN-CAP Safety (5 stars) driven features. Dedicated TCU, Microphone， Speaker. Automatic trigger condition is the same as current EA design(Oil pump cut off or air bag deploy); leverage current EA call center Yesway(95智驾). CN Regulation on e-call to be expected in 2024 (TBC) | [6 empty] | Jun. 31 | Jul. 15
| 2# Safety Reminder 安全提醒 | 儿童座椅报警Child Restraint System (CRS) - ( e.g BT Child seat 蓝牙座椅) |  |  |  | BT Child seat 蓝牙座椅, 蓝牙通信反馈儿童座椅是否正确安装了。CNCAP 安全需求，车载需要支持与CRS 实现通信功能. 通信的具体形式是蓝牙传输 | [6 empty] | Jun. 31 | Jul. 15
| 3# Entertainment 娱乐 | 时空秘信Surprise/Secret message |  |  |  | customer can schedule supirse message such as "Happy Birthday" | [6 empty] | Jun. 31 | Jul. 15
| 4# Personal Productivity 工作效率 | 视频会议 Project Aspire_Video Phone Calling / Video Conferencing (Meeting Mode)_CN |  |  |  | Demonstrate a Video call capability using the center stack with a Web application. The Functionality provides a view for Video conferencing in stationary mode. Includes conference experience , voice or audio in call and document viewing and sharing capabilities. These are listed as two items on Project Aspire Master List | [6 empty] | Jun. 31 | Jul. 15
| 5# In Vehicle Gaming 车载游戏 | 车载游戏 Project Aspire_In-Vehcle Gaming (Gaming Mode) |  |  |  | Project Aspire: Doggy dash: UX/UI only. Is a video interactive experience that is started from the center stack. The user goes into the experience icon within the center stack, selects the icon labeled doggy dash and a video starts to play taking over the full horizon and the center stack. Controls are still avaiable in the center stack if they want to end the experience. In the horizon display there are several dogs sitting and using controls (i.e. steering wheel) the user can pick a dog. Once a dog is selected it will sit in the video on the horizon display until the user presses a button saying they want to play. The dog will run across the full screen and then the user can throw a play and the dog will fetch the ball and the experience will start over. | [6 empty] | Jun. 31 | Jul. 15
| 6# Marketplace / Apps Anywhere 应用商店 | 车机应用市场Project Aspire_Marketplace / Apps Anywhere |  |  |  | Market Place is a extension of Ford Pass where following options are available for a customer - Chosen experiences such as relax could be purchased and downloaded to the vehicle - Chosen dashboards ( Videos , Static wallpapers) can be purchased and downloaded to the vehicle . Marketplace today is only QSR (Quick Service Retail -coffee, gas, etc). Buying any application purchases is not contained. Apps Anywhere build a foundation to support the application purchases. All on hold | [6 empty] | Jun. 31 | Jul. 15
| 7# Web Browser & Browser Based Application 浏览器和网页版应用 | 车载游览器/浏览器应用Project Aspire_Streaming Web / Applications |  |  |  | IQIYI is the assumption (Carryover Feature) The feature discribed below from project aspire is optional Using Chromium with QT the team integrated the following websites in to the ASPIRE experience. Each web application has a icon in the center stack that starts in the center stack and then can be casted to the horizon display. The user can scroll, pan select, play, pause, etc. just as they can on any website. | [6 empty] | Jun. 31 | Jul. 15
| 8# Wallpaper 墙纸 | 壁纸 Project Aspire_Dash Backgrounds |  |  |  | like your wallpaper on your phone or PC. The customer can personalize their dashboard with images, videos and sound. Content can be placed on top of the dashboard like on your PC and phone wallpaper. A dashboard covers the entire horizon screen. Project Aspire planed wallpaper/background including Luxury/Doggy dash/Dolphin/Live aquarium/Bloom/Comb/Dots/Houston Skyline/Kids photos/New York Aerial | [6 empty] | Jun. 31 | Jul. 15
| 1# Account 账号 | 车机端福特账号和百度账号同时登陆 (By 福特派 or 林肯之道App） Baidu and Ford/Lincoln Account dual Login |  |  |  | 车机端用户显示二维码， 用户通过福特派/林肯之道APP扫描二维码实现林肯/福特和百度账号互通。车机端会同时登陆福特/林肯账号和百度账号。 目前支持8个。 | [6 empty] | Jun. 31 | Jul. 15
| 2# Personalized Profile 个人设置档案 | 基于云端的用户档案Project Aspire_Personal Portable Profiles |  |  |  | (ProgramMarketing）Personal Portable Profiles - Create a setup wizard on IVI/Fordpass for customer - Passenger account & profile (could be after J1 - OTA upgrade) - Portble profile. If user move to another vehicle , I can migration all my setting preference with this account/profile effortlessly. Project Aspire： Demostrated profile creation in the cnterstack for three driver profiles and one passenger profile. | [6 empty] | Jun. 31 | Jul. 15
| 2# Personalized Profile 个人设置档案 | 快捷设置Rocket setup |  |  |  | 4S交车前，工作人员会带着车主进行首次设置的界面 | [6 empty] | Jun. 31 | Jul. 15
| 1# Payment & Wallet 支付和钱包 | 停车查询 & 停车费支付 Parking Fee |  |  |  | -查看实时车位 -搜索附近的停车场 -停车场付费（含二维码支付） | [6 empty] | Jun. 31 | Jul. 15
| 1# Payment & Wallet 支付和钱包 | 小额免密支付Seamless Payment |  |  |  | 支付功能里电影票，鲜花，餐品/外卖预定以及酒店可以支持免密支付。 小额（200CNY) 免密支付 （二维码扫描， 支付宝账号绑定。免密支付不支持微信付款） | [6 empty] | Jun. 31 | Jul. 15
| 1# Payment & Wallet 支付和钱包 | 百度-我的钱包 Baidu Wallet |  |  |  | 我的钱包 支付设置 我的钱包 聚合收银台 我的钱包 账单 我的钱包 订单中心 order center | [6 empty] | Jun. 31 | Jul. 15
| 1# Payment & Wallet 支付和钱包 | 聚合支付 Aggregate payment |  |  |  | 扫码支付的时候车机只显示一个二维码 | [6 empty] | Jun. 31 | Jul. 15
| 1# Display | 后排娱乐空调控制面板 Rear entertainment control(Climate/Audio) - U611 |  |  |  | 扶手箱后面有个小屏。CAN互动，消息协议由Lincoln定义 | [6 empty] | Jun. 31 | Jul. 15
| 2# Passenger Experience | 27'副驾本地及在线音乐/Offline&Online Music Player & audio manager | [10 empty] | Jun. 31 | Jul. 15
| 2# Passenger Experience | 27'地图/including Passenger Map&Navigation; | [10 empty] | Jun. 31 | Jul. 15
| 2# Passenger Experience | 27'空调设置(climate control from passenger area) | [10 empty] | Jun. 31 | Jul. 15
| 2# Passenger Experience | 副驾在线视频Online Video-clarify | [10 empty] | Jun. 31 | Jul. 15
| 2# Passenger Experience | 副驾天气预报Weather forecast |  |  |  | 27" touch -CD542. 之前天气是以卡片形式展示。 CD542 上面天气信息融入到背景中。添加了暖心贴士 | [6 empty] | Jun. 31 | Jul. 15
| 2# Passenger Experience | 副驾视频播放(支持 DLNA)/Passenger Video Playback(Support DLNA | YFVE | Jia Elaine |  |  | Feb.1 | Mar.4 | Mar.9 |  |  | Apr.1 | Jun. 31 | Jul. 15 |  |  |  | R5(Jun.23 Integration)
| 3# Driver Exlusive Screen Use Experience | 27” 屏幕扩展显示/Extend center or passenger display content(like Navi, to show the whole path in two screens) to two display (地图独占模式） | [10 empty] | Jun. 31 | Jul. 15
| Audio System | Lincoln Rear Audio Controls |  |  |  | Touch screen U611 | [6 empty] | Jun. 31 | Jul. 15
| Audio System | Rear Audio Controls |  |  |  | Ford - Hard button/Touch screen U611 | [6 empty] | Jun. 31 | Jul. 15
| Big Data Analytics | 统计月度和年度激活量 Statistics monthly and annual system activation quantities | [10 empty] | Jun. 31 | Jul. 15
| Carrier | Carrier API integration with Baidu 与百度的接口集成- Carrier Backend Development 运营商后台开发 Carrier Feed API integration with FORD 与福特的接口集成 API integration with Baidu 与百度的接口集成 Carrier Backend Development 运营商后台开发 SIM Management SIM卡管理 |  |  |  | retail data plan API, data usage query API, order API, payment API, invoice API, usage notification API, etc. | [6 empty] | Jun. 31 | Jul. 15
| Carrier | Carrier Backend Development 运营商后台开发 |  |  |  | associate 1 VIN with 2 SIMs; RNR platform; Online Mall; Jasper/M2M portal; Per APP billing, etc. | [6 empty] | Jun. 31 | Jul. 15
| Carrier | RNR |  |  |  | 实名认证 | [6 empty] | Jun. 31 | Jul. 15
| Carrier | 流量套餐app端流量查询购买 data plan query & oder | [10 empty] | Jun. 31 | Jul. 15
| Diagnostics | Fully Ford ECU Diagnostic&EOL | [10 empty] | Jun. 31 | Jul. 15
| Diagnostics (TCU & ECG) | FNVx_Diagnostics_Analytics |  |  |  | log 小工具包含USB TCU Log， 以及上传云端。 | [6 empty] | Jun. 31 | Jul. 15
| Preset APP | 安装/运行福特指定的第三方软件/VP硬件对应的软件 |  |  |  | Baidu: 推荐PJ1用OTA方式推一个应用程序接口。 | [6 empty] | Jun. 31 | Jul. 15
| Security Device | 网络安全解决方案 | [10 empty] | Jun. 31 | Jul. 15
| Settings | V2I Lite Settings | [10 empty] | Jun. 31 | Jul. 15
| Settings | 流量管理 | [10 empty] | Jun. 31 | Jul. 15
| System Setting - Others | Disclaimer |  |  |  | Content to be aligned with CVPP and baidu | [6 empty] | Jun. 31 | Jul. 15
| System Setting - Others | First Mile Navigation/Last Mile Navigation/Vehicle locator |  |  |  | FindMyCar．First Mile Navigation/Last Mile Navigation/Vehicle locator | [6 empty] | Jun. 31 | Jul. 15
| 1# Help Me Park 停车辅助 | 远程泊车辅助 Remote Park Assist (RePA) | [10 empty] | Jun. 31 | Jul. 15
| 1# Interactive User Guide 车主指导 | 爱车探索Demo Mode |  |  |  | Including 重温欢迎仪式 Replay Welcome Approach 配置介绍 Features Walkthrough | [6 empty] | Jun. 31 | Jul. 15
| 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 2.0 |  |  |  | Online content （cloud storage) | [6 empty] | Jun. 31 | Jul. 15
| 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 3.0 |  |  |  | Current: *3D Interface Display *Full Text Search *Support voice search *History Record -Click spots to jump to introduction of the components and parts -3D-View Interface - allow drag/rotate to explore different part of the car Next Step: - get IVI intro merged - First Time User Guidance - Maintenance Record | [6 empty] | Jun. 31 | Jul. 15
| 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 1.0 |  |  |  | Paper user manual go digital on IVI | [6 empty] | Jun. 31 | Jul. 15
| 2# Traffic Violation Checking 违章查询 | 违章查询 Query traffic violations (IVI) |  |  |  | Baidu: 用户终端查询是需要收费的。 | [6 empty] | Jun. 31 | Jul. 15
| 2# FordPass Remote Control 福特派远程控制 | 车辆保养时间/保养项目/保养里程建议Prognostics (Gasoline Vehicle) |  |  |  | 根据VHA和TCU（FB2+） report 机油状况，建议保养时间/保养项目/里程 | [6 empty] | Jun. 31 | Jul. 15
| 4# Dealer Service Booking 经销商服务预定 | 保养及在线预约 OSB - Online Service Booking |  |  |  | Dearler Search. /Vehicle Maintenance and the service booking 保养在线预约 OSB-订单查询 order inquiry 保养在线预约 OSB-保养预约 Service booking， time and leave a note for maintenance items 保养在线预约 OSB-建议保养项目 Base on mile display user manual suggested maintenance item when user click on this . | [6 empty] | Jun. 31 | Jul. 15
| 5# User Feedback Channel 用户反馈 | 用户反馈Customer Feedback |  |  |  | QR code scan and submit via phone | [6 empty] | Jun. 31 | Jul. 15
| 5# User Feedback Channel 用户反馈 | 用户反馈Customer Feedback 2.0 |  |  |  | Improved version.车机上进行语音录入用户反馈 | [6 empty] | Jun. 31 | Jul. 15
Group D -> DCV 2
Feature ID | Feature Group | Feature Name | Feature Develop Leader | Feature Owner / D&R | HMI Feature Lead | Description / Comments | UE Delivery expected by SW | Function Clarification | UE Design start | UE Delivery Plan Date | UE Sign-off Plan Date(1 Week) | Hero Screen expected by HMI | Hero Screen delivery target date | Ergo Sign-off on Hero Screens | UI Delivery expected by SW | UI Delivery Plan Date | UI Sign-off Plan Date(2 weeks) | Eng Release Version
| System | Voice Assist (VPA) / Voice Control | [10 empty] | Jul. 31 | Aug. 15
|  | Ambiente Lighting | [10 empty] | Jul. 31 | Aug. 15
|  | Digital scent | [10 empty] | Jul. 31 | Aug. 15
|  | Rejuvenation mode | [10 empty] | Jul. 31 | Aug. 15
|  | Calendar | [10 empty] | Jul. 31 | Aug. 15
|  | Smart Scene | [10 empty] | Jul. 31 | Aug. 15
| System Animations | Welcome / Farewell animation | [10 empty] | Jul. 31 | Aug. 15
|  | Individual mode <-> co-pilot mode / solo mode | [10 empty] | Jul. 31 | Aug. 15
|  | Drive mode selection (knob on console) | [10 empty] | Jul. 31 | Aug. 15
|  | UI Build | [10 empty] | Jul. 31 | Aug. 15
|  | Screen Transitions | [10 empty] | Jul. 31 | Aug. 15
|  | OTA updates | [10 empty] | Jul. 31 | Aug. 15
|  | Auto Park | [10 empty] | Jul. 31 | Aug. 15
|  | Digital Scent | [10 empty] | Jul. 31 | Aug. 15
|  | Active Call | [10 empty] | Jul. 31 | Aug. 15
|  | Process Flows : Phone paring, charge | [10 empty] | Jul. 31 | Aug. 15
|  | VPA Digital Assistant | [10 empty] | Jul. 31 | Aug. 15
|  | IOD cards flow & Behavior | [10 empty] | Jul. 31 | Aug. 15
| Owner's Manual | Digitial Owners Manual App | [10 empty] | Jul. 31 | Aug. 15
| Settings Animations | Infobooks//Settings2Centerstack | [10 empty] | Jul. 31 | Aug. 15
|  | Supplemental Animation/Experiences (e.g. MCS) | [10 empty] | Jul. 31 | Aug. 15
| System | Digital Scent | [10 empty] | Jul. 31 | Aug. 15
| Notifications | Generic Notification Small | [10 empty] | Jul. 31 | Aug. 15
|  | Generic Notification Large | [10 empty] | Jul. 31 | Aug. 15
|  | Generic Dialog Small | [10 empty] | Jul. 31 | Aug. 15
|  | Information Popup Basic | [10 empty] | Jul. 31 | Aug. 15
|  | Information Popup Detailed | [10 empty] | Jul. 31 | Aug. 15
| Settings | Seat App - Adjust | [10 empty] | Jul. 31 | Aug. 15
|  | Seat App - Massage | [10 empty] | Jul. 31 | Aug. 15
| 1# Air Quality 空气质量 | 座舱空气质量检测CAQ(Cabin Air Quality) |  |  |  | 后装方案 | [6 empty] | Jul. 31 | Aug. 15
| 2# Rejuvenation 活力恢复 | 数字香氛 Digital scent |  |  |  | 4 scent | [6 empty] | Jul. 31 | Aug. 15
| 2# Rejuvenation 活力恢复 | 数字香氛 Digital Scent 2.0 (New Scents) |  |  |  | New scents can work with imersive experience, e.g rejuvenations for customer heath & wellness, as well as Purify. | [6 empty] | Jul. 31 | Aug. 15
| 2# Rejuvenation 活力恢复 | 活力恢复 Project Aspire_Rejuvenation |  |  |  | Project Aspire: Relax is a feature/capability that allows to provide a user specific experience to induce calming or relaxing experience. The feature is a combination of effects in a vehicle to including- Digital scent- Advanced welcome with complimentary light and sound scheme in various parts of vehicle such as ambient lighting , Horizon display , center stack etc- Relax moment can be initiated and controlled via HMI. This feature also uses FordPass to download calm app, install, set up calm experience (ambient color, cabin temo, length of experience, other HVAC controls), save and then start calm experience with chatbot and FB messenger. | [6 empty] | Jul. 31 | Aug. 15
| 2# Rejuvenation 活力恢复 | 自由秘境Relax/At Ease |  |  |  | Pre-Global Rejuvenation | [6 empty] | Jul. 31 | Aug. 15
| 1# Vehicle to Home | 提前开扫地机器人 Turn on cleaning robert 提前开灯 Turn on lights 提前开空调 Turn on AC(at home) in advance |  |  |  | 扫描车机端显示二维码关联 “小度家居”， 之后在该平台上面关联的设备都会显示在IVI 界面， 并且支持语音远程启动。“你好福特，打开我家里的扫地机器人” | [6 empty] | Jul. 31 | Aug. 15
| 1# Vehicle to Home | 车家互联Project Aspire_General IOT (Smart Home)_CN (UI grahic upgrade -IVI端） | [10 empty] | Jul. 31 | Aug. 15
| 2# Passenger Experience | 联合驾趣 Co-Driver |  |  |  | 副驾区域显示车辆/行驶状态/可以发起POI 搜索， 设置导航路线. Lead CD542 27'L touch screen | [6 empty] | Jul. 31 | Aug. 15
| 1# Air Quality 空气质量 | UFC Lite notification (空气净化状态提示) |  |  |  | 空气净化状态提示, function module. Part of AAR. | [6 empty] | Jul. 31 | Aug. 15
| Audio System | Radio reception test | [10 empty] | Jul. 31 | Aug. 15
| Audio System | Revel QIS 3D Audio (Audio System, settings) |  |  |  | Lincoln -only | [6 empty] | Jul. 31 | Aug. 15
| Log System (IVI) | Automatically logging and uploading to log server -IVI Module |  |  |  | IVI本地产生的log可以某种特定的机制来执行log的自动上传到后台log服务器（支持Wifi/4G）；该log服务器有权限设定，向OEM开发；log具备标签机制，便于后台人员快速查找log文件;该方式为CDC中第一log方式。 | [6 empty] | Jul. 31 | Aug. 15
| TCU | Location Service （仪表指南针，etc.） | [10 empty] | Jul. 31 | Aug. 15
| User Data Burying point | Consumer Behavior Data (IVI related)埋点 |  |  |  | 统计功能使用情况和用户偏好 Statistics feature usage and user preferences | [6 empty] | Jul. 31 | Aug. 15
| User Data Burying point | 用户使用数据埋点 Phase 1 |  |  |  | 统计功能使用情况和用户偏好 Statistics feature usage and user preferences | [6 empty] | Jul. 31 | Aug. 15
| User Data Burying point | 用户使用数据埋点 Phase 2 |  |  |  | 统计功能使用情况和用户偏好 Statistics feature usage and user preferences | [6 empty] | Jul. 31 | Aug. 15

## Timing Jan29
May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01
6/1
Pano
Wireframes
HMI Support Specification
Revisions as required
7/3
7/10
controller Wireframes
Wireframe Model
Usability Clinic
Internal evaluations as needed
Usability validation Clinic
Pano Production
Assets
Group A
Aug 28
Group (A?) B
Oct 13
Group C
Dec 7
Group D
Feb 2
Controller Production
Assets +4 wks
Group A
Oct 13
Group B
Dec 18
Group C
Feb 15
Group D
Apr 29
Pano Hero Screens
Prelim Group A
Aug 1
Group A+B
Sept 15
Group C
Nov 8
Group D
Jan 5
Group E
Mar 1
Controller Hero Screens
Group A
Sept 15
Group B
Nov 20
Group C
Jan 18
Group D
Apr 1
Group E
Jun 10
China IVI HMI (Pano+Controller)
Concept study
Revisions as required
Pano + Controller Production assets /UI -- 4mon
Group A
Apr 30
Group C
Jul 31
Group D
Aug 31
Group B
Jun 15
DCV
FDJ
China SYNC+ Software
SW Debug
DV Feature Coding
SW Coding with tooled display
Interaction spec / UE -- 4.5mon
Group A
Mar 15
Group B
Apr 30
Group C
May 31
Group D
Jul 15
clarification
Group B
Nov 20
Supplier onboard
Revisions as required
Group A + B
Nov 20
Group C
Dec 18
Group D
Feb 5
Target timing unknown
Usability validation external Clinic
FDJ
System-UI UE ready
Feb 9
SystemUI Usability validation
Revisions as required
PA Experience review
Jul 9
China Rear Armrest Control Panel HMI
UE
English
Jan.28
Chinese
Feb.10
Assets
English
TBD
Chinese
TBD
Hero Screeen
Revisions
TBD
TBD
Kick off
Jan. 28
Hero Screen & UI (under discussion)
Revisions as required
Group A&B Pano
Mar 15
Group A&B Controller
Apr 15
Group C
May 31
Group D
Jul 9
UE Delivery Start
Feb 2
Hero Screen Delivery Start
Feb 23
UI Delivery Start
Mar 1
China SYNC+ Function Spec Clarification
Function Spec clarification
Revisions as required
Group A
Mar 1
Group C
May 15
Group D
Jul 1
Group B
Apr 15

## Timing Jan17
May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01
6/1
Pano
Wireframes
HMI Support Specification
Revisions as required
7/3
7/10
controller Wireframes
Wireframe Model
Usability Clinic
Internal evaluations as needed
Usability validation Clinic
Pano Production
Assets
Group A
Aug 28
Group (A?) B
Oct 13
Group C
Dec 7
Group D
Feb 2
Controller Production
Assets +4 wks
Group A
Oct 13
Group B
Dec 18
Group C
Feb 15
Group D
Apr 29
Pano Hero Screens
Prelim Group A
Aug 1
Group A+B
Sept 15
Group C
Nov 8
Group D
Jan 5
Group E
Mar 1
Controller Hero Screens
Group A
Sept 15
Group B
Nov 20
Group C
Jan 18
Group D
Apr 1
Group E
Jun 10
China IVI HMI timing
Concept study
Revisions as required
Controller Production assets /UI -- 4mon
Group A
Apr 30
Group C
Jul 31
Group D
Aug 31
Pano(Zone 2/3/4) Production assets 3.5 mon
Group B
Jun 15
Group D
Aug 31
Group C
Jul 31
Group B
Jun 30
Group A
May 15
Today
DCV
FDJ
China SYNC+ Software
SW Debug
DV Feature Coding
SW Coding with tooled display
Interaction spec / UE -- 4.5mon
Group A
Mar 15
Group B
Apr 30
Group C
May 31
Group D
Jul 15
clarification
Group B
Nov 20
Supplier onboard
Revisions as required
Revisions as required
Group A + B
Nov 20
Group C
Dec 18
Group D
Feb 5
Target timing unknown
Today
Usability validation external Clinic
FDJ
System-UI UE ready
Feb 9
SystemUI Usability validation
Revisions as required
PA Experience review
Studio initiate IVI Hero screem design, timing TBD
HeroScreen
Jul 9