## Slide 1: Phase5 SW Release Plan
Think
Point of view
Plan to Implement
Implement
Roger Xu, Jiajia Zhou
Date: July 01, 2021
Desired Outcome
Awareness
Decision
Escalation Help

## Slide 2: Phase 5 Vehicles Timeline
CDX707
CX788
UPV1
02/19
CDX747
TT
12/29
12/21
FEC
11/23
PEC
10/14
PP
03/14
03/01
OK2B
06/27
MP1
05/03
04/29
DCV
06/13
FDJ
01/07
UPV0
05/10
UPV1
08/16
UPV2
11/08
PA
12/08
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
2021 | 2022 | 2023 | 2024
MP2
05/31
Phase5 Scope |  |  |  |  |  |  |  |  |  |  | 
Program | PMT5 | Nameplate | Manufacture | J1 | OKTB | EE Architecture | Centerstack Size | Cluster |  | TCU | ECG
CDX707 | Yang Youfei, Xu Fiona | Nautilus | CAF | 3/28/2023 | 3/28/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
CX788 | He Sylvia | Ford | CAF | 4/26/2023 | 6/21/2023 | FNV2 | 15.3 | NA, AR HUD | Landscape | Boundle5 | ECG2
CDX747 | Yang Frank | Lincoln | BU | 6/12/2023 | 11/6/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
U611 MCA | Yang Frank | Aviator | CAF | 12/6/2023 | 1/23/2024 | FNV3 | 27 | 12.3，Standalone HUD | Landscape | Boundle6 | ECG2
U625MCA | Yang Frank | Explorer | CAF | 12/6/2023 | 1/23/2024 | FNV3 | 27 | 12.3，Standalone HUD | Landscape | Boundle6 | ECG2
U718 | Yang Frank | Navigator | BU | 3/11/2024 | 4/22/2024 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
U611MCA
TT
FEC
PEC
PP
09/05
OKTB
01/23
MP1
12/06
DCV
FDJ
UPV0
03/12
UPV1
06/11
UPV2
09/24
PA
10/17
HB
12/03
06/13
10/07
11/04
02/28
06/13
UPV2
06/11
PEC
06/13
PA
07/14
FDJ
08/20
TT
08/24
PP
11/09
MP1
02/01
DCV
02/02
MP2
03/01
FEC
07/25
OKTB
03/28
OK2B
11/06
MP2
10/09
MP1
06/12
PP
03/13
FEC
11/29
TT
12/12
PEC
11/01
UPV1
07/13
UPV2
10/26
FDJ
01/11
DCV
07/11
U718
FEC
04/18
PEC
03/07
OK2B
04/22
DCV
10/24
FDJ
04/26
UPV0
08/03
UPV1
11/02
UPV2
02/15
PA
02/23
MP2
04/08
TT
08/07
PP
10/23
MP1
03/11
U625MCA
TT
FEC
PEC
PP
09/05
OKTB
01/23
MP1
12/06
DCV
FDJ
UPV0
03/12
UPV1
06/11
UPV2
09/24
PA
10/17
HB
12/03
06/13
10/07
11/04
02/28
06/13

## Slide 3: CDX707 SW Release Plan @06/15
CDX707 VPP
Display(23.6+23.6,11.1 touch)
Vendor Integration
SW Release for CAF/FO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
06/11
SW Release for REC
PEC
06/13
PA
07/14
FDJ
08/20
TT
08/24
PP
11/09
MP1
02/01
DCV
02/02
DCV Alpha
03/19
DCV Beta
08/02
ITV Test
A0 PCBA
01/25
CDC AHU HW
A1
06/15
B0
12/13
B1 DV2
05/10
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
DCV Alpha1
03/31
DCV Alpha2
04/28
DCV Alpha3
05/26
DCV Alpha4
06/23
DCV Beta
07/18
08/01
DCV Beta1
08/18
DCV Beta2
09/15
DCV0
10/20
DCV0.1
11/17
DCV1
12/15
DCV2
01/12
DCV3
02/23
R00
03/23
R01
04/20
R04
05/18
R05
06/15
R05.1
07/13
R05.2
08/10
R06
09/07
R06.1
10/19
R07
11/20
R08 for OKTB
01/15
DCV Alpha0
02/23
DCV Alpha1
03/03
DCV Alpha2
03/31
DCV Alpha3
04/28
DCV Alpha4
05/26
DCV Beta
06/20
07/02
DCV Beta1
07/21
DCV Beta2
08/18
DCV0
09/15
DCV0.1
10/20
DCV1
11/17
DCV2
12/15
DCV3
01/12
R00
02/23
R01
03/23
R04
04/20
R05
05/18
R05.1
06/15
R05.2
07/13
R06
08/10
R06.1
09/07
R07
10/19
R08 for OKTB
12/15
Group A
03/15 sign-off UE
05/05 Stagger UI
05/19 sign-off UI
Group B
04/30 UE
06/02 stagger UI
06/16 sign-off UI
Group C 05/21 UE
08/17 UI
Group D
06/15 UE
09/15 UI
TBD
2021 | 2022 | 2023
09/13-10/15
12/17-03/15
05/15-06/15
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
MP2
03/01
FEC
07/25
OKTB
03/28
UX Release
FNVx Release
DCV0
11/03
DCV1
12/29
DCV2
01/26
DCV3
03/09
R01
05/04
R04
06/01
R05
06/29
R05.1
07/27
R00
04/06
R05.2
08/24
R06
09/21
R06.1
11/02
R07
12/04
R08 for OKTB
01/24
SOA Gateway
Wireless Interface Router
IVI Provisioning
Bezel Diagnostics(SOA related)
Diagnostic_ Analytic
CCS –Authorization
CCS – UFM/PTE
IP Pass Through Client
USB Update of TCU/ECG
SYNC+ SOC USB Update
SYNC+ SOC OTA Update
SYNC+ MCU USB Update
SYNC+ MCU OTA Update
Cluster SOC USB Update
Cluster MCU OTA Update
Rocket Setup
Purchase process
03/23-07/30
Net/Diagnostic full function 12/15 for DCV2
ITV P2 complete 07/18
R09 for OTA
04/28 TBD
PEC1
07/26
FEC1
09/06
Net/Diag develop~4.5months
Bug fix ~1.5m
ITV P1 Release for R04
04/15
Net/Diag Bug fix
For R00
01/30
Report Review 07/25
Vendor P1 test ~2.5 m
P2 Log Prepare ~2m
We are here
A2
09-03
EMC
12/17--02/02

## Slide 4: CX788 SYNC+/AR-HUD/Display Plan @06/07(Based on 11/26 Group A UI)
Display(15.4)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
CDC AHU HW
B0 DV1
07/18
A Sample Pre-DV
12/15
09/15
B1 DV2
01/06
Pre-DV
04/05-05/05
DV1
07/25-11/02
DV2
01/13-03/20
Eng version released for REC, focus and lite test.
Pro version support GPDS key node, full test.
CX788 VPP
UPV1
08/16
PEC
10/14
FDJ
01/07
TT
12/21
PP
03/01
DCV
06/13
FEC
11/23
OKTB
06/27
UPV0
05/31
AR-HUD
05/31
MP2
PA
12/08
UPV2
11/08
PV
03/27-06/27
PPAP
06/28-07/12
TFT HUD
Group A UI
11/26->11/01
IVI UI Plan
Group C UI
01/26
Group D UI
03/27
Group B UI
12/17
Group A UE
07/23
EMC
07/25-09/15
EMC
01/13-02/20
Group C UI
~04/15
System UI and Launcher UE Sign-off 07/16
MP1
04/29
Group B UE
09/03
R4
12/14
Group C UE
10/15
Group A UI
~02/15
Group C UI
~03/15
GPDS SW Version for MRD
R00
12/30
DCV Beta
04/14
R04
02/05
R05
03/14
R06
05/14
DCV0
07/14
DCV1
08/14
Package 1-3-HW+Base SW
SW Release for REC
R07
06/14
DCV Beta1
04/30
DCVBeta2
05/30
DCV0
06/30
DCV1
07/30
DCV2
08/30
DCV3
09/30
DCV4
11/15
R00
12/15
R04
01/15
R05.1
03/30
R06
04/30
R07
05/30
R08
06/30
R5
02/28
R6
03/30
R7
04/30
R8
05/30
R9
06/30
R10
07/30
R11
08/30
R12
10/15
R13
11/15
R14
12/15
R15
01/15
R16
02/28
R17
03/30
R18
04/30
Spring Festival
National Day
Spring Festival
DCV Beta
03/30
MFL Release
04/15
FIP Draft Release
04/30
DCV Alpha
02/28
R19
05/30
R05
02/28
R08
07/14
TFT T0 Sample
10/30
TFT T1 Sample
12/30
Tier 1 T0 Sample
3/30
Tier 1 T1 sample for DCV 5/20
Pre DV-1
Critical DV
11/8-12/31
3/30~5/20
Ass tooling
T0 Sample
2/15
T1 Sample
6/1
EMC + DV
6/15-9/15
Pre-DV
2/15~5/15
B Sample Pre-DV
02/25
AR HUD UI Plan
We are here

## Slide 5: CX788 SYNC+/AR-HUD/Display Plan @07/05 (Based on 10/10 Group A UI)
Display(15.4)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
CDC AHU HW
CX788 VPP
UPV1
08/16
PEC
10/14
FDJ
01/07
TT
12/21
PP
03/01
DCV
06/13
FEC
11/23
OKTB
06/27
UPV0
05/31
AR-HUD
05/31
MP2
PA
12/08
UPV2
11/08
TFT HUD
Group A UI
11/01
Checkpoint 4
IVI UI Plan
Group C UI
01/07
Group D UI
03/27
Group B UI
12/17
Group A UE
07/23
Group C UI
~04/15
System UI and Launcher UE Sign-off 07/16
MP1
04/29
Group B UE
09/03
Group A UI Delivery
10/10
Checkpoint 3
Group A UI
~02/15
Group C UI
~03/15
GPDS SW Version for MRD
Package 1-3-HW+Base SW
SW Release for REC
Spring Festival
National Day
MFL Release
04/15
FIP Draft Release
04/30
TFT T0 Sample
10/30
TFT T1 Sample
12/30
Tier 1 T0 Sample
3/30
Tier 1 T1 sample for DCV 5/20
Pre DV-1
Critical DV
11/8-12/31
3/30~5/20
Ass tooling
T0 Sample
2/15
T1 Sample
6/1
EMC + DV
6/15-9/15
Pre-DV
2/15~5/15
AR HUD UI Plan
We are here
R4
12/13
R00
10/11
DCV Beta
02/27
R04
12/11
R05
01/14
R06
03/17
DCV0
06/03
DCV1
07/04
R07
04/17
DCV0
05/20
DCV1
06/20
R01
10/27
R04
11/27
R06
03/04
R07
04/04
R08
05/04
R5
01/13
R6
02/20
R7
03/20
R8
04/20
R9
05/20
R10
06/20
R11
07/20
R12
08/20
R13
09/20
R14
10/27
R15
11/27
R16
12/27
R17
02/04
R18
03/04
Spring Festival
DCV Beta
02/20
R19
04/04
R05
12/27
R08
06/17
Eng version released for REC, focus and lite test.
Pro version support GPDS key node, full test.
B0
06/10
C
01/06
A1 Sample
09/15
Pre-DV
03/14-04/14
DV
06/17-08/05
RE-DV
11/25-12/30
PV
01/13-3/10
03/13-03/27
PPAP
EMC
06/17-07/17
EMC
11/25-
12/25
A2 Sample
03/07
HW Improve
PCB fabricate
04/15-06/02
HW Improve
PCB fabricate
08/06-11/10
Vehicle level calibration
09/19-11/25
CDC AHU HW Proposed VPP
PEC
12/02
DCV
08/17
FEC
01/28
DCV MRD
07/25
B1
11/18
TT MRD
02/14
PP MRD
04/17
MP1 MRD
05/17
OKTB
07/27
TT
03/08
PP
05/08
MP1
06/09
R00
09/20
R01
11/11

## Slide 6: CDX747 SW Draft Release Plan @0705
Package 1-3-HW+Base SW
Display(23.6+23.6, 11.1 touch)
GPDS SW Version for CAF
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
DCV Beta
01/06
R00
9/15
R04
10/17
R05
11/18
R06
12/30
R07 04/06
DCV0
03/30
DCV1
04/30
CDC AHU HW
B DV1
3/28
A Sample
10/12
Inhouse Proposal 09/10(TBD)
C DV2
9/20
Pre-DV
DV1
DV2
2021 | 2022 | 2023
12/24—1/28
4/5-6/30
10/20-11/20
CDX747
OK2B
11/06
MP2
10/09
MP1
06/12
PP
03/13
FEC
11/29
TT
12/12
PEC
11/01
UPV0
04/06
UPV1
07/13
UPV2
10/26
FDJ
01/11
DCV
07/11
HW Request Frozen
7/13
Eng version released for REC, focus and lite test.
Pro version support GPDS key node, full test.
Group A UI
09/30
IVI UI Plan
Group C UI
12/30
Group D UI
1/11
Group B UI
11/15
Group A UE
08/01
System UI and Launcher UE Sign-off 07/16
Group B UE
09/03
SW Release for REC
DCV0
03/16
DCV1
04/15
R00
09/01
R04
09/30
R06
12/15
R07
03/22
R08
07/15
DCV Beta
12/23
MFL Release
06/25
FIP Draft Release
07/20
R05
11/04
DCV Beta
11/24
DCV0
02/18
DCV1
03/15
DCV3
07/11
DCV3
06/10
R00
08/01
R04
09/01
R05
10/08
R06
11/15
R07
02/22
R08
06/15
R09
09/15
R09
08/15
R06.1
02/27
R06.1
02/13
R06.1
01/06
DCV Beta1
02/14
DCV Beta1
01/07
R07.1
06/02
R07.1
05/19
R07.1
04/20
DCV2
05/30
DCV2
04/30
R08 07/30
R09 preserved for OKTB 09/30
DCV Alpha
11/23
ITV Test
FNVx Release
Display timing TBD
YFVE: Need 10/M T0 sample supporting Pre DV
Notes: 有功能增加；
音频架构有变化。

## Slide 7: U611MCA SW Release Plan @06/02
Display(12.3+27 TOUCH)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
DCV Beta
12/03
R00
8/15
R04
9/15
R05
4/13
R06
07/05
R07 9/30
DCV0
03/13
DCV1
04/13
CDC AHU HW
B0 DV1
3/10
A1 Pre-DV
11/15
B1 DV2
8/20
Pre-DV
DV1
DV2
DV
DCV Alpha1
10/19
DCV Beta
11/19
DCV Beta1
11/19
DCV Beta2
12/19
DCV0
02/26
DCV1
03/27
DCV2
03/27
DCV3
04/27
DCV4
05/27
R00
07/27
R04
09/01
R04.1
12/30
Group A UI
07/01
Group B UI
09/04
Group C for 11/01
Group D before FDJ
12/01
2021 | 2022 | 2023
12/10-02/21
03/21-05/21
9/20-11/01
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
EMC
National Day
National Day
Spring Festival
Spring Festival
U611MCA
OK2B
1/23
MP1
12/06
PP
09/5
FEC
11/04
TT
6/13
PEC
10/07
UPV0
03/16
UPV1
06/11
UPV2
9/24
FDJ
12/3
DCV
06/13
HB
2/28
HW Request Frozen
6/11
Group A UE
04/15
01/27
05/05
MFL Release
04/30
FIP Draft Release
05/30
SW Release for CAF/FO
Vendor Integration
ITV Test
UX Release
FNVx Release
DCV Alpha1
09/12
DCV Alpha
07/18
DCV Beta
10/19
DCV0
01/21
DCV1
02/23
R00
06/27
R04
07/27
R04.1
11/30
R05
03/30
R04.1
01/15
R06
06/20
R07
09/15
R08 12/30
R08
12/15
R04.1
02/20
R06
05/20
R07
08/15
R08
11/15
A0 08/01(TBC) for SW debug
SOA Gateway
Wireless Interface Router
IVI Provisioning
Bezel Diagnostics(SOA related)
Diagnostic_ Analytic
CCS –Authorization
CCS – UFM/PTE
IP Pass Through Client
USB Update of TCU/ECG
SYNC+ SOC USB Update
SYNC+ SOC OTA Update
SYNC+ MCU USB Update
SYNC+ MCU OTA Update
Cluster SOC USB Update
Cluster MCU OTA Update
Rocket Setup
Notes: 有功能增加；
音频架构有变化。

## Slide 8: Phase5 SYNC+ 3.0 Timeline Draft To Be Reviewed
Project VPP
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
UPV2
Hardware
UX Release
PEC
PA
FDJ
TT
PP
MP1
DCV
DCV Beta
R00
R04
R05
R06
R07
Key Checkpoint
DCV0
Group A UI
For Pre DV/FDJ
Group B UI
For Critical DV/DCV
Group C UI
For DCV
Group D UI
For DCV/PEC
MP2
FEC
OKTB
UPV0
PS/PSC
1.Bill of feature Initialized(MFL)
2.Feature Owner confirmation
3. Basic Level spec are available
1. Supplier Sourced (SOBD)
======
1.Bill of feature(MFL) Finalized
2.Platform feature spec complete and cascaded
3.Function Safety Concept updated and completed
4.Cybersecurity Requirements Identified
5.UX(UEUI) alignment confirmed
6.SW environment and baseline Design
1. Platform feature spec finalization and sign off
2.Simulate feature integration of interfaces, states and responses to requested behavior
3. Early test of new and C/O features with physical parts
1.DCV Beta verified supporting Pre-DV/EMC, critical function including Climate/Camera/Radio/Music/Video/Navigation/Speed meter/Driving Info etc.
2.Feature Software early system-level integration test start at <FDJ> breadboard
3. UX doc sign off by HMI/Studio team
1.DCV1 verified supporting DV/EMC/DCV MRD with full function code completed.
2.Feature Software early system-level integration test complete by <DCV> breadboard, verify feature functionality and performance requirements.
1All design verification testing completed by <PEC>
2.Feature Software system-level integration test complete and sign off by feature owner and HMI team
3.R00 release for <PEC> without critical blocker issue,
4.Diagnostics Part2 DV(iTV) test report shows 100% passed
1. Software OTA window preserved post Job1 and before OKTB.
R08
1. Agile feature full function Integration without critical bug.
Group A Features Coding based on UI
DCV Alpha
DCV Beta
test
A1
Pre DV
Debug
B0
Critical DV
DCV Critical Path * 45 weeks
DCV1
17 weeks(4 months)
6 weeks
DCV
DCV MRD
4 weeks
5 weeks
>=6 weeks
DCV0
test
Eng Version
>=6 weeks
9 weeks
9 weeks
9 weeks
A0 PCBA
A1 Sample
B0 Sample
B1 Sample
Features and HMI Design
Display light up
Platform Arch design
PIPELINE Design
Initial release for Pre DV
DCV Beta
30% Coding
Release Fundamental features for DCV vehicle testing
DCV1
60% Coding
Zero IG defects supporting PEC sign off
R00
95% Coding(Not including Agile features)
Delivery of all features with zero G issues
R05 100% Coding
AIMS Issue solve / Bug fix
R06 100% Coding
AIMS Issue solve / Bug fix
R07 100% Coding
17 weeks(4months)
17 weeks(4months)
13 weeks(3months)
8weeks(2months)
9 weeks(2months)
8weeks(2months)
10weeks(2.5months)
Hotfix for OKTB
Preserved
5 weeks
>=14 weeks
>=32 weeks

## Slide 9: SYNC+ 3.0 DCV/PEC/J1 Critical Path
China Accelerated SW Plan ---DCV Critical Path
FDJ
DCV
Group A UI Release
MRD
DCV Beta 30%
DCV0 50%
DCV1 60%
45 weeks
Group A Features Coding based on UI
DCV Alpha
DCV Beta
Test
A Sample
Pre DV
Debug
B Sample
Critical DV
China Accelerated SW Plan ---PEC/J1 Critical Path
R00
95%
R04
R05
100%
R06
R07
R08
DCV1 60%
DCV
DCV MRD
4 weeks
5 weeks
9 weeks
9 weeks
Zero IG defects supporting PEC sign off
R00 (4*SW iterated versions )
95% Coding(Not including Agile features)
Delivery of all features with zero G issues
R05 100% Coding for TT MRD
AIMS Issue solve / Bug fix
R06 100% Coding for PP MRD
17 weeks(4months)
13 weeks(3months)
8weeks(2months)
DCV
6 weeks
PEC
FEC
6 weeks
TT
PP
AIMS Issue solve / Bug fix
R07 100% Coding for J1
8 weeks(2months)
Hotfix for OKTB
R08 100% Coding
Preserved
9 weeks
J1
Initial release for Pre DV
DCV Beta
30% Coding
Release Fundamental features for DCV vehicle testing
DCV1
60% Coding
17 weeks(4months)
8weeks(2months)
Features and HMI Design
Display light up
Platform Arch design
PIPELINE Design
10weeks(2.5months)
OKTB

## Slide 10: CDX707/788 SW Release Requirement for MRD
CDX707 |  |  |  | 
R-Event | Software Maturity | Corresponding Milestone | Release Due Date*1) | Build Support
TPB | Fully verified on component level | TPV BB MRD - 1 week | 9/9/2019 | Support TPV BB and TPV T&C MRD
TP3 | Updates Release | TDC - 2weeks | 1/22/2021 | Support TDC
DCV beta | System test on engineering prototype | eBB MRD | 8/20/2021 | Support FDJ
DCV 0 | Fully verified on component level | DCV BB MRD - 4 weeks | 11/10/2021 | Support <DCV BB> MRD and HiL MRD
DCV 1 | Updates Release | T/C MRD - 4 weeks | 12/8/2021 | Support <T/C> MRD
DCV 2 | Updates Release | DCV - 2 weeks | 1/19/2022 | Breadboard update, DCV vehicles update
DCV 3 | Updates Release | DCV+ 4 weeks | 3/2/2022 | Breadboard update, DCV vehicles update
R00 | Feature DV complete. | PEC - 6 weeks | 5/2/2022 | DCV vehicles update for PEC Sign-off
R04 | Feature DV signed off | FEC - 6 weeks | 6/13/2022 | DCV vehicles update for FEC Sign-off
R05 | Fully Validated Release | TT MRD - 4 weeks | 7/13/2022 | Support <TT> MRD
R06 | Fully Validated Release | PP MRD - 4 weeks | 9/28/2022 | Support <PP> MRD
R07 | Fully Validated Release | MP1/J1 MRD - 4 weeks | 12/6/2022 | Support <MP1> MRD
R-Event | Software Maturity | Corresponding Milestone | Release Due Date*1) | Build Support
TPB | Fully verified on component level | TPV BB MRD - 1 week | NA | Support TPV BB and TPV T&C MRD
TP3 | Updates Release | TDC - 2weeks | 7/30/2021 | Support TDC
DCV beta | System test on engineering prototype | eBB MRD | 1/7/2022 | Support FDJ
DCV 0 | Fully verified on component level | DCV BB MRD - 4 weeks | 3/21/2022 | Support <DCV BB> MRD and HiL MRD
DCV 1 | Updates Release | T/C MRD - 4 weeks | 5/4/2022 | Support <T/C> MRD
DCV 2 | Updates Release | DCV - 2 weeks | 5/30/2022 | Breadboard update, DCV vehicles update
DCV 3 | Updates Release | DCV+ 4 weeks | 7/11/2022 | Breadboard update, DCV vehicles update
R00 | Feature DV complete. | PEC - 6 weeks | 9/2/2022 | DCV vehicles update for PEC Sign-off
R04 | Feature DV signed off | FEC - 6 weeks | 10/12/2022 | DCV vehicles update for FEC Sign-off
R05 | Fully Validated Release | TT MRD - 3 weeks | 11/24/2022 | Support <TT> MRD
R06 | Fully Validated Release | PP MRD - 4 weeks | 1/26/2023 | Support <PP> MRD
R07 | Fully Validated Release | MP1/J1 MRD - 4 weeks | 4/1/2023 | Support <MP1> MRD

## Slide 11: CDX707 SW Maturity Chart @0524

## Slide 12: Backup material

## Slide 13: Phase 5 Vehicles Timeline Between CX788 & Accelerated VPP
China Accelerated SW Plan
FDJ
DCV
Group A UI Release
MRD
DCV Beta 35%
DCV0 80%
DCV1 85%
45 weeks
Group A Features Coding based on UI
DCV Alpha
DCV Beta
Test
A Sample
Pre DV
Debug
B Sample
Critical DV
Phase5 CDX788
FDJ
DCV
Group A UI Release 7/06(Per Template)
06/13
01/07
45 weeks
Group A UI
08/15(SW Expected)
40 weeks
Group A UI
11/01(HMI Feedback)
10 weeks Gap
smart surface
8'' HUD
15.3''
DCV0 80% 06/24
07/13-08/31
02/15
03/30
04/07-06/07
03/15
07/13
Group A Features Coding based on UI
DCV Alpha
DCV Beta
Test
A Sample
Pre DV
Debug
B Sample
Critical DV
MRD
IP MRD 05/06
DCV1 85% 07/24
5 weeks Gap
DCV Beta 35% 03/30
10 WKS Gap
10+5 WKS Gap
EC Approval
6/30
TFT T0 Sample
10/30
TFT T1 Sample
12/30
Tier 1 T0 Sample
3/30
Tier 1 T1 sample for DCV 5/20
Pre DV-Round 1
EMC + Critical DV
11/8-12/31
3/30~5/20
Tier 1 assembly tooling KO
EC Approval
6/30
Pre-EMC + critical DV
2/15~5/15
15.4” Display
AR-HUD
T0 Sample
2/15
Tier 2 TFT Tooling KO
Included PCBA
Tooling KO
8/30
12/15-3/15
Windshield surface/HUD package frozen
9/15
11/15
EMC + DV
6/15-9/15
T1 Sample
6/1

## Slide 14: CDX707 HW and SW Design & Validation Plan
Proposed resolution:
< DCV>: Retrofit SYNC+ HW with R10 SW on 22-Feb-2022.
<PEC><FEC> ><PSW>: Stagger milestone for SYNC+& related features.
<TT>: Check point at PEC 08/01 for SYNC+ retrofit on vehicle.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5
DCV
02/02
2021 | 2022 | 2023
DCV Beta(R5 Eng)
09/10
DCV0(R8 Eng)
12/20
（Critical DV)
DCV1(R10 Eng)
R10 2/22
SW Release
DCV Beta(R5 Eng)
07/10
(Pre-DV)
DCV0(R8 Eng)
10/20
（Critical DV)
SYNC+ Build
&Validation
07/13-9/13
10/21-12/15
Critical DV
12/21-4/5
06/07–7/10
09/13-11/18
12/24-2/22
2/22 – 5/27
08/02-09/05
TT build & PV
Ver. 20210224
PEC
06/13
FEC
07/11
TT
08/10
11/02
DCV MRD
01/05
MP1
02/01
MP2
03/01
UPV1
UPV2
PA
07/14
FDJ
08/20
VPP
SYNC+ DEVELOPMENT
Current plan
HMI 8wks delay
Vehicle level test/sign off
Vehicle level test/sign off
SYNC+ Build
&Validation
PSW
1/19
12/22
3wks
05/30
07/25
08/24
6wks
6wks
11/09
Pre-DV:
Preliminary DV and debug for basic functions of platform.
Hand build prototype sample (w/ ~30% design completion)
Test setup trail run
Test at none Ford certified Lab.
Critical DV:
Safety function validation(Speed, PRND, Fuel, Telltale, RVC, Climate, ESP/ADAS setting), EMC/thermal/Key off load, High/Low temperature operation
DCV off-tool sample
Ford certified Lab.
07/12-10/21
10/29
12/29
09/12-12/21
Re-DV
7wks
DCV1
PEC1
FEC1
3/15
(HMI)
New plan
Critical DV can’t complete by DCV MRD. (7wks gap)
02/22
PP
07/26
09/06
PSW
5/19
TT Build & PV
TT Containment:
Aligned with NMP: SYNC+ HW & SW w/ PEC signed off to support TT build. Potential TT retrofit 2 wks post TT required to contain critical DV test failure
TT/PP VOCF 2 shift to support robust SW & HW delivery
03/05
06/16
3/30
Hero S
5/5
Group A
6/1
Group C
6/16
UPV2
7/1
VPP
Checkpoint
1
2
3
DCV1(R10 Eng)
12/20
R00(R13 Eng) 04/06
R04(R15 Eng) 06/01
（Re-DV）
12/15
(HMI)
HMI 12wks delayed
3/15
SW Release
Compress Development timing and stagger DCV software to 3 version (R10/11/12) to support PEC/FEC sign off to contain HMI 12wks delay
PSW
HMI
HMI
(DCV build and PEC sign off)
To ensure robust and quality delivery no timing opportunity could be further compressed, downstream engineering work postponed by 8wks
(DCV build and vehicle test/sign off)
DV Test Impact & Opp.:
By R10 Feb. 22, 20 DCVs built w/ 4 plan to be shipped out at Feb. 15 for US Calibration
Further discussion with Cal to align the containment plan if defer 4 Cal. DCVs 1wk with right level HW & SW
Study to build DCV in 2 lines or add more DCVs to reduce build time
DCV Opportunity:
R8 ilo R10 to support DCV build w/ downstream test hold till R10 ready
CDC module retrofit takes 44 minutes only with control screen, lower vent and floor console disassembled
DCV2(R11 Eng)
DCV3(R12 Eng)
(DCV reflash)
Root cause & Countermeasure
Sample Build
Debug & Build
Critical DV
Re-DV
Sample Build
12/29
Pre-DV
SYNC+ CDC DV
4/18-06/06
Root cause & Countermeasure
06/10-08/01
SYNC+ CDC DV
Debug & Build
Pre-DV
DCV2(R11 Eng)
DCV3(R12 Eng)
R00(R13 Eng) 06/06
R04(R15 Eng) 08/01
（Re-DV）

## Slide 15: CDX707 System Block Diagram
2021 | 2022 | 2023

## Slide 16: CDX707 Software and Autosar Release Plan
Autosar Package integration
CDX707 VPP
YF Package integration
SW Release for CAF/FO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
06/11
SW Release for REC
PEC
06/13
PA
07/14
FDJ
08/20
TT
08/24
PP
11/09
MP1
02/01
DCV
02/02
DCV Alpha
03/19
DCV Beta
08/02
08/20
A0 PCBA
01/25
CDC AHU HW
A1 PCBA
05/30
06/08
B0 DV1
11/30
B1 DV2
05/10
Pre-DV
DV1
DV2
DCV Alpha1
03/31
DCV Alpha2
04/28
DCV Alpha3
05/26
DCV Alpha4
06/23
DCV Beta
07/18
08/01
DCV Beta1
08/18
DCV Beta2
09/15
DCV0
10/20
DCV0.1
11/17
DCV1
12/15
12/07
DCV2
01/12
01/07
DCV3
02/23
02/11
R00
03/23
R01
04/20
R04
05/18
R05
06/15
R05.1
07/13
R05.2
08/10
R06
09/07
R06.1
10/19
R07
11/20
R08 for OKTB
01/15
2021 | 2022 | 2023
08/02-08/30
12/05-2/28
05/15-06/15
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
MP2
03/01
FEC
07/25
OKTB
03/28
DCV0
11/03
11/10
DCV1
12/29
12/15
DCV2
01/26
01/14
DCV3
03/09
02/25
R01
05/04
R04
06/01
06/13
R05
06/29
07/14
R05.1
07/27
R00
04/06
05/02
R05.2
08/24
R06
09/21
09/29
R06.1
11/02
R07
12/04
12/14
R08 for OKTB
01/24
R09 for OTA
04/28 TBD
PEC1
07/26
FEC1
09/06
DCV0.1
10/20
DCV1
11/17
DCV2
12/15
DCV3
01/12
R00
02/23
R01
03/23
R04
04/20
R05
05/18
R05.1
06/15
R05.2
07/13
R06
08/10
R06.1
09/07
R07
10/19
R07 for OKTB
12/15
完成调查表，2周
完成德国报价，2周
预估项目定点
YF内部流程PR&PO，签订采购合同
6周
Vector释放软件包，10周
网络诊断全功能，FBL并行开发
Bug Fix
ITV P2
ITV P1
网络诊断初版
T：07/30
完成ITV
移植完成之前CAN信号,实现30%的CAN信号添加
DCV0
09/15
实现60%的CAN信号的添加，30%的DID和30%的DTC的实现
DCV Alpha4
05/26
DCV Beta
06/20
07/04
DCV Beta1
07/18
DCV Beta2
08/18
DCV0
09/15
注：
DCV ALPHA4 – R06 详细释放计划见后页
YF CAN 网络信号分3个版本释放
- 10/20(DCV0.1集成时间)释放30%信号(即整体信号30%),包括移植先前开发的CAN信号(YF自研包开发的信息)。
- 11/17(DCV1集成时间)释放30%信号(即整体信号60%)
- 12/15(DCV2集成时间)释放40%信号(即整体信号100%)
此外还需考虑Package2调试和集成时间。
ITV认证周期： T(2021/07/30) +12月, 完成认证时间2022/07/25

## Slide 17: Phase5 SW Integration and Release Rule
2021 | 2022 | 2023
Checkpoint1:
Vendor Integration
Checkpoint2:
Eng SW Release for REC
Checkpoint3:
Pro SW Release for CAF/FO