## Slide 1: CX788 SYNC+/AR-HUD/Display Plan @08/10 (Based on 11/15 Group A Delivery UI)
Display(15.4)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
CDC AHU HW
CX788 VPP
UPV1
08/16
PEC
10/14
FDJ
01/07
TT
12/21
PP
03/01
DCV
06/13
FEC
11/23
OKTB
06/27
UPV0
05/31
AR-HUD
05/31
MP2
PA
12/08
UPV2
11/08
Cluster(9.0) HW TBD
Group A UI
12/12
IVI+Cluster UI Plan
Group C UI
02/13
Group D
UI
03/25
Group B UI
01/09
MP1
04/29
Unsigned Group A UI Delivery
11/15
SW Release for CAF/FO
Vendor Integration
SW Release for REC
Spring Festival
National Day
TFT T0 Sample
10/30
TFT T1 Sample
12/30
Tier 1 T0 Sample
3/30
Tier 1 T1 sample for DCV 5/20
Pre DV-1
Critical DV
11/8-12/31
3/30~5/20
Ass tooling
T0 Sample
2/15
T1 Sample
6/1
EMC + DV
6/15-9/15
Pre-DV
2/15~5/15
We are here
DCV Alpha
01/20
R00
10/31
DCV Beta
03/19
R04
12/31
R05
02/07
R06
04/07
DCV0
06/23
DCV1
07/24 (=>(07/17)
R07
05/07
DCV0
06/10
DCV1
07/10
R04
12/17
R06
03/24
R07
04/24
R08
06/24
DCV Beta
02/12
DCV0
05/10
DCV1
06/10
R00
09/10
R04
11/17
R05
12/17
R06
02/24
R07
03/24
Spring Festival
DCV Beta
03/12
R08
05/24
R05
01/17
R08
07/07
Eng version released for REC, focus and lite test.
Pro version support GPDS key node, full test.
B0
06/24
C
02/02
A1 Sample
09/15
Pre-DV
04/03-05/03
DV
06/27-08/16
RE-DV
12/05-01/10
PV
02/09-04/05
04/08-04/22
PPAP
EMC
06/27-07/28
EMC
12/05-
01/05
A2 Sample
03/26
HW Improve
PCB fabricate
05/04-06/22
HW Improve
PCB fabricate
08/17-11/21
B1
11/30
R00
10/17
Group A UE
08/15
Group B UE
09/25
Overall Enablers:
HMI Delivery(Group-A/B/C/D) Can’t Delay Any Further.
Program Offers IVI S/W Team 5 DCV Vehicles For System Level Debug. (3 for suppliers, 2 for IVI Software Team), TT Vehicle *3 Is Also Required. Add two test NSPS engineers till FEC2 declared
Each Sign-off Team Has Qualified DV vehicles With Great DV Vehicle Usage Schedules => Need Dedicated Person To Manage Closely.
Pending Input
FDJ
01/28
FEC2
R00
1/13
UPV0
07/02
DCV
07/11
PEC
11/11
PEC2
R00
12/02
FEC
12/23
CX788 Proposed VPP
UPV1
09/13
PA
UPV2
TT
2/01
IPD
OKTB
7/25
Pending Update
PP
03/22
IPD
MP1
05/24
IPD
1
2
4
3
Compress actions IVI team has taken/ considered:
[4wks compress, Done] Use Group A UI Unsigned version to kick off coding(12/12 to 11/15) Utilize Ckp. to track risk assessment.
[2wks compress, Done] Compress the Group A coding time from 10 wks to ~7.5wks.
[2wks further compress, Done] Compress further 2wks Development &Validation time between DCV Alpha and DCV Beta (origin 8wks to 6wks)
[1wks, further compress Pull ahead B0 Sample Build, Done] With above 1/2/3 compress, plus take further risks to pull ahead B0 sample build W/O REC validation by 14 days(6/10 to 06/23).
[1wks, Studying]Compress REC DCV1 validation time window from 2 wks to 1 wks by further OT shift and adding NSPS
[2wks, compress studying] R04 engineering version to support FEC2 sign off ilo. Publishing ver.(Enablers: OT and adding NSPS)
5
6

## Slide 2: CX788 Engineering Timing Further Compress Possibilities @0730
Display(15.4)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
CDC AHU HW
CX788 VPP
UPV1
08/16
PEC
10/14
FDJ
01/07
TT
12/21
PP
03/01
DCV
06/13
FEC
11/23
OKTB
06/27
UPV0
05/31
AR-HUD
05/31
MP2
PA
12/08
UPV2
11/08
Cluster(9.2) HW TBD
Group A UI
11/29
IVI+Cluster UI Plan
Group C UI
01/31
Group D UI
03/25
Group B UI
01/03
MP1
04/29
Unsigned Group A UI Delivery
10/30
SW Release for CAF/FO
Vendor Integration
SW Release for REC
Spring Festival
National Day
TFT T0 Sample
10/30
TFT T1 Sample
12/30
Tier 1 T0 Sample
3/30
Tier 1 T1 sample for DCV 5/20
Pre DV-1
Critical DV
11/8-12/31
3/30~5/20
Ass tooling
T0 Sample
2/15
T1 Sample
6/1
EMC + DV
6/15-9/15
Pre-DV
2/15~5/15
We are here
DCV Alpha
01/05
R00
10/31
DCV Beta
03/19=>03/05
R04
12/31
R05
02/07
R06
04/07
DCV0
06/23
DCV1
07/24=>07/10
R07
05/07
DCV0
06/10
DCV1
07/10=>06/26
R04
12/17
R06
03/24
R07
04/24
R08
06/24
DCV Beta
02/12
DCV0
05/10
DCV1
06/10
R00
09/10
R04
11/17
R05
12/17
R06
02/24
R07
03/24
Spring Festival
DCV Beta
03/12 =>02/26
R08
05/24
R05
01/17
R08
07/07
Eng version released for REC, focus and lite test.
Pro version support GPDS key node, full test.
B0
06/30
C
02/02
A1 Sample
09/15
Pre-DV
04/03-05/03
DV
07/03-08/22
(=>08/01)
RE-DV
12/10-01/15
PV
02/09-04/05
04/08-04/22
PPAP
EMC
07/03-08/03 (=>07/13)
EMC
12/10-
01/10
A2 Sample
03/26=>03/05
HW Improve
PCB fabricate
05/04-06/22
HW Improve
PCB fabricate
08/22-11/26
B1
12/07
R00
10/17
Group A UE
08/15
Group B UE
09/25
The difference between 10/30 delivery and 11/29 sign-off version should be minor. UI key elements size/coordinates/UE logic cannot be changed.
SW team will estimate the change level to further study if there’s any duplicated work or CR.
PEC2
12/02
DCV
07/11
FEC2
01/13
OKTB
07/25
TT
02/01
Compress actions IVI team has taken/ considered:
[4wks Compress, Done] Use Group A UI Unsigned version to kick off coding(11.29 to 10/30) =>Risk: Poor Software Delivery Quality, Coding Rework When UE/UI Unsigned Design Changes. Delay Or Fail to Start Pre-DV; Unknown DCR cost charged
[10days Compress, Done] Compress the Group A coding time from 10 wks to ~7.5wks =>Risk: Low Software Quality, Risk To Delay Or Fail To Start Pre-DV and downstream.
[2wks Compress, Studying] Compress further 2 wks Development&Validation time between DCV Alpha and DCV Beta(origin 8wks to 6 wks) => Risk: Low Software Quality, Risk To Delay Or Fail To Start Pre-DV and downstream.
[1wks Compress, Studying] Compress REC DCV Beta validation time window from 2 wks to 1 wks by further OT shift and adding NSPS.
[Pull ahead A2 Sample Build, Studying] With above 1/2/3/4 compress, plus take further risks to pull ahead A2 sample build W/O REC validation by 21 days(3 wks, 03/26 to 03/05).
1
2
3
4
5