## Slide 1: Phase5 SW Release Plan
Think
Point of view
Plan to Implement
Implement
Roger Xu, Jiajia Zhou, James Chen
Date: Dec 11, 2020
Desired Outcome
Awareness
Decision
Escalation Help

## Slide 2: Phase 5 Vehicles Timeline
CDX707
CX788（Study）
Ford Version
Lincoln Version
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
CDX747
2021 | 2022 | 2023
OK2B
11/06
TT
11/04
FEC
11/04
PEC
09/16
MP2
10/09
MP1
06/12
PP
01/24
OK2B
06/21
MP1
04/26
UPV2
05/28
PP
03/13
FEC
11/23
TT
12/12
PEC
10/26
HB/DCV
05/18
FDJ
12/07
Supplier Integration
Supplier Integration
Key New Feature
PEC
05/30
PA
06/30
FDJ
08/06
FEC
07/11
TT
08/09
PP
11/09
MP1
02/01
UPV0
03/12
UPV1
06/11
UPV2
09/24
UPV0
05/10
UPV1
07/26
UPV2
10/15
FDJ
01/07
DCV
01/19
DCV
07/11
PA
11/17

## Slide 3: CDX707 SW Release Plan
CDX707 VPP
Display(23.6+23.6,11.1 touch)
Package 1-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
05/28
SW Release for REC
Package 2-Ford core service
PEC
05/30
PA
06/30
FDJ
08/06
FEC
07/11
TT
08/09
PP
11/09
MP1
02/01
DCV
01/19
R0
02/07
DCV Beta
07/20
DCV2
12/19
R00
04/30
R04
06/15
R05
07/16
R06
10/09
R07 01/01
Package 3-Eco APPs
Package 4-HMI
DCV0
09/20
DCV1
11/05
DCV3
02/19
A0 PCBA
01/07
CDC AHU HW
A1 PCBA
04/30
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
Inhouse APPs
R1
03/08
R2
04/07
R3
05/07
R4
06/07
R5
07/07
R6
08/06
R7
09/07
R8
10/07
R9
11/08
R10
12/07
R11
01/07
R12
02/15
R13
03/15
R14
04/15
R15
05/16
R16
06/15
R17
07/15
R18
08/15
R19
09/15
R20
10/20
R21
12/20
R22 for OKTB
02/20
R0
01/14
R1
02/14
R2
03/14
R3
04/14
R4
05/14
R5
06/14
R6
07/14
R7
08/14
R8
09/14
R9
10/14
R10
11/14
R11
12/14
R12
01/14
R13
02/23
R14
03/23
R15
04/23
R16
05/23
R17
06/23
R18
07/23
R19
08/23
R20
09/28
R21
11/28
R22 for OKTB
01/14
R0
01/14
R1
02/14
R2
03/14
R3
04/14
R4
05/14
R5
06/14
R6
07/14
R7
08/14
R8
09/14
R9
10/14
R10
11/14
R11
12/14
R12
01/14
R13
02/23
R14
03/23
R15
04/23
R16
05/23
R17
06/23
R18
07/23
R19
08/23
R20
09/28
R21
11/28
R22 for OKTB
01/14
R0
01/14
R1
02/14
R2
03/14
R3
04/14
R4
05/14
R5
06/14
R6
07/14
R7
08/14
R8
09/14
R9
10/14
R10
11/14
R11
12/14
R12
01/14
R13
02/23
R14
03/23
R15
04/23
R16
05/23
R17
06/23
R18
07/23
R19
08/23
R20
09/28
R21
11/28
R22 for OKTB
01/14
R1
02/07
R2
03/07
R3
04/07
R4
05/07
R5
06/07
R6
07/07
R7
08/07
R8
09/07
R9
10/08
R10
11/07
R11
12/07
R12
01/07
R13
02/15
R14
03/15
R15
04/15
R16
05/15
R17
06/15
R18
07/15
R19
08/15
R20
09/21
R21
11/21
R22 for OKTB
01/07
R0
01/07
Group A for R2 12/20
Group B
Group C
Group D
2021 | 2022 | 2023
07/10-08/05
10/15-12/15
05/15-06/15
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11

## Slide 4: CDX707 R0-R5 FIP

## Slide 5: CDX707 R0-R5 FIP
1.Autosar License---RFQ
2.FNV3 Readiness---NA
3.HMI
4.FO Definition
5.Bench R&R

## Slide 6: CDX707 SW FIP—R2 Release Plan
System UI
SPSS/PRD Release and frozen from FO
12/17
MRD Sign off with FO 12/22
UI/UE Release
12/25
Code Release and integration
03/07
MRD Review with FO
12/18
Coding
12/26
收音机 Radio
SPSS/PRD Release and frozen from FO
12/30
MRD Sign off with FO 01/12
12/7 | 12/14 | 12/21 | 12/28 | 01/04 | 01/11 | 01/18 | 01/25 | 02/01 | 02/08 | 02/15 | 02/22 | 03/01 | 03/08 | 03/15 | 03/22
Test case Sign off with FO 01/07
MRD Review with FO
01/06
UI/UE Release
01/07
Coding
01/13
Test case Sign off with FO 01/26
Code Release and integration
03/07
Log system-串口
SPSS/PRD Release and frozen from FO
12/30
MRD Sign off with FO 01/12
MRD Review with FO
01/06
UI/UE Release
01/07
Coding
01/13
Test case Sign off with FO 01/26
Code Release and integration
03/07
FPD Link
SPSS/PRD Release and frozen from FO
12/30
MRD Sign off with FO 01/12
MRD Review with FO
01/06
UI/UE Release
01/07
Coding
01/13
Test case Sign off with FO 01/26
Code Release and integration
03/07

## Slide 7: CDX707 Open Issue list—12/18 update
No | Topic/Issue | Assignee | Due date | Status
1 | 12/11: Input the last MFL including FDL and Pre-DV Dependency list for Vendors(YF/Baidu/inhouse) to review and confirm. Set daily meeting to review MFL with vendors(Group,Pre-DV List， FDL, Release Version), target to freeze the MFL COB 12-20. 12/14 Jzhou101：The latest MFL has been confirmed and obtained from planning/program team today, Pre-DV SW release version and FDL will be imported before 12-16 by James, targeting to review with vendors again on this Thursday’s weekly meeting(10:00-11:00am). 12/18：Action Plan: 12/21 Define and confirm the pre-dv dependency list with D&R and vendors; 12/22 Follow up all the open issue of FIP; 12/24 Confirm FO; 12/25 Frozen and Release Master Feature List which with the Aligned FOs; 12/28 Define the UI/UE release plan with HMI team. | Chen James， Huang Feng, Zheng Wei | 12/18/2020 | Y
2 | 12/11: FO of different features has not confirmed yet, influencing SPSS release and the R0 release. Help Needed! 12/18：LL6 Check and align the FO (Lead by each LL6, coordinated by PMT) | Chang Cathy, Xu Fiona | 12/24/2020 | Y
3 | 12/11: High risk for No HMI vendors onboard, Need YFVE confirm the deadline dependence. HMI team escalate this risk. 12/16：Group A draft UE will be released to REC on 12-20, vendors will be on-board within this week. 12/18:HMI team plan to discuss with HMI vendors and define the UI/UE release plan for R0-R5. Supporting Pre-DV. | Sun Xiao | 12/18/2020 | Y
4 | Fnv3 risk, can not support pre-DV. 12/18: Inhouse has followed this issue and try to find ICA/PCA internally. | Zheng Wei | 21-Dec | R

## Slide 8: Phase5 SW Maturity Requirement
Phase5 SW Maturity Requirement |  |  | 
DCV beta | System test on engineering prototype/ Bench | eBB MRD | Support FDJ
DCV 0 | Fully verified on component level | DCV BB MRD - 2 weeks | support BB MRD
DCV 1 | Updates Release | T/C MRD - 4 weeks | support DCV MRD
DCV 2 | Updates Release | DCV - 2 weeks | sw improvement
DCV 3 | Updates Release | DCV+ 4 weeks | support DCV
R00 | Feature DV complete. | PEC - 3 weeks | support PEC
R04 | Feature DV signed off | FEC - 3 weeks | support FEC
R05 | Fully Validated Release | TT MRD -3 weeks | support TT
R06 | Fully Validated Release | PP MRD - 3 weeks | support PP
R07 | Fully Validated Release | MP1/J1 MRD - 3 weeks | support MP1