## Slide 1: Phase5 SW Release Plan
Think
Point of view
Plan to Implement
Implement
Roger Xu, Jiajia Zhou, James Chen
Date: Feb 05, 2021
Desired Outcome
Awareness
Decision
Escalation Help

## Slide 2: Phase 5 Vehicles Timeline
CDX707
CX788
Ford Version
Lincoln Version
UPV1
02/19
CDX747
OK2B
11/06
TT
11/04
FEC
10/28
PEC
09/16
MP2
10/09
MP1
06/12
PP
01/17
OK2B
06/21
MP1
04/26
UPV2
05/28
PP
03/13
FEC
11/23
TT
12/12
PEC
10/26
DCV
05/18
FDJ
03/29
Supplier Integration
Supplier Integration
Key New Feature
PEC
05/30
PA
06/30
FDJ
08/06
FEC
07/11
TT
07/26
PP
10/11
MP1
02/01
UPV0
03/12
UPV1
06/11
UPV2
09/24
UPV0
05/10
UPV1
07/26
UPV2
10/15
FDJ
01/07
DCV
01/19
DCV
07/11
PA
02/10
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2021 | 2022 | 2023
HB
08/29
MP2
05/24

## Slide 3: Phase5 FIP Tracking

## Slide 4: CDX707 SW Release Plan
CDX707 VPP
Display(23.6+23.6,11.1 touch)
Package 1-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
05/28
06/11
SW Release for REC
Package 2-Ford core service
PEC
05/30
06/13
PA
06/30
07/14
FDJ
08/06
08/20
TT
07/26
08/02
PP
10/11
10/18
MP1
02/01
DCV
01/19
02/02
R0
03/03
DCV Beta
07/20
DCV2
01/05
R00
04/18
R04
05/30
R05
07/06
R06
09/21
R07 12/06
Package 3-Eco APPs
Package 4-HMI
DCV0
10/27
DCV1
11/24
DCV3
02/16
A0 PCBA
01/07 01/25
CDC AHU HW
A1 PCBA
04/30
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
Inhouse APPs
R1
03/31
R2
04/28
R3
05/26
R4
06/23
R5
07/10，07/18
R6
08/18
R7
09/15
R8
10/20
R9
11/17
R10
12/15
R11
01/12
R12
02/23
R13
03/23
R14
04/20
R15
05/18
R16
06/15
R17
07/13
R18
08/10
R19
09/07
R20
10/19
R21
11/20
R22 for OKTB
01/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
Group A for DCV Beta(R0-R5)
12/15 Delayed to 03/15 UE,04/30 UI
Cluster Assets 03/05
Group B for DCV1(R6-R9)
06/15
Group C for DCV3(R10-R11)
07/30
Group D for DCV2(R12-R13)
08/31
2021 | 2022 | 2023
07/23-08/20
10/25-12/15
05/15-06/15
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
MP2
03/01
FEC
07/11
07/25
OKTB
03/28

## Slide 5: CDX707 SW Release Plan—HMI Risk
CDX707 VPP
Display(23.6+23.6,11.1 touch)
Package 1-3-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
05/28
SW Release for REC
PEC
05/30
PA
06/30
FDJ
08/06
FEC
07/11
TT
07/26
PP
10/11
MP1
02/01
DCV
01/19
R0
03/03
DCV Beta
07/20
DCV2
01/05
R00
04/18
R04
05/30
R05
07/06
R06
09/21
R07 12/06
IVI UE Plan- Jan.15 Update
DCV0
10/27
DCV1
11/24
DCV3
02/16
A0 PCBA
01/25
CDC AHU HW
A1 PCBA
04/30
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
R1
03/31
R2
04/28
R3
05/26
R4
06/23
R5
07/10，07/18
R6
08/18
R7
09/15
R8
10/20
R9
11/17
R10
12/15
R11
01/12
R12
02/23
R13
03/23
R14
04/20
R15
05/18
R16
06/15
R17
07/13
R18
08/10
R19
09/07
R20
10/19
R21
11/20
R22 for OKTB
01/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
Group A
04/30
Group B
06/15
Group C 07/30
Group D 08/31
2021 | 2022 | 2023
07/10-08/05
10/25-12/15
05/15-06/15
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
MP2
03/01
Issue1:
Uncertain Cluster UX release plan， Pipeline design can’t be frozen in R1.
Group A
03/15
Group B
04/30
Group C
05/31
Group D
06/30
Group A
12/15
Group B
02/15
IVI UI Plan- Jan.15 Update
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
Cluster UX Plan- Unclear
Issue3:
IVI UE release plan has been delayed by 3 months; R5 will be delayed, Pre-DV will be delayed by 3 months.
Issue2:
UI has been delayed by 4 months, Uncertain Hero-screen release plan may cause the further delay of UI.
Group A
12/15
Group B
02/15
CAN’T MEET Pre DV/DCV/PEC Requirement.

## Slide 6: CDX707 HMI Release Plan--IVI
Issue1: Uncertain Cluster UX release plan.
Issue2: Uncertain Hero-screen release plan may cause the further delay of UI.
Issue3: IVI UE release plan has been delayed by 3 months; R5/Pre-DV maybe be delayed, Pre-DV will be delayed by 3 months.
.

## Slide 7: CDX707 HMI Release Plan--Cluster
To Be Confirmed by YFVE Team.

## Slide 8: CDX747 SW Release Plan--TBD
Display(23.6+23.6,11.1 touch)
Package 1-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
Package 2-Ford core service
R0
03/03
DCV Beta
12/15
DCV2
07/05
R00
9/15
R04
10/17
R05
11/06
R06
02/13
R07 05/06
Package 3-Eco APPs
Package 4-HMI
DCV0
04/10
DCV1
05/10
DCV3
08/11
A0 PCBA
01/07 01/25
CDC AHU HW
A1 PCBA
04/30
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
Inhouse APPs
R1
03/31
R2
04/28
R3
05/26
R4
06/23
R5
07/10，07/18
R6
08/18
R7
09/15
R8
10/20
R9
11/17
R10
12/15
R11
01/12
R12
02/23
R13
03/23
R14
04/20
R15
05/18
R16
06/15
R17
07/13
R18
08/10
R19
09/07
R20
10/19
R21
11/20
R22
01/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
Group A for DCV Beta
12/15 Delayed to 03/15 UE,04/30 UI
Group B for DCV0
06/15
Group C for DCV1
07/30
Group D for DCV2
08/31
2021 | 2022 | 2023
07/23-08/20
10/25-12/15
05/15-06/15
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
CDX747
OK2B
11/06
MP2
10/09
MP1
06/12
PP
03/13
FEC
11/29
TT
12/12
PEC
11/01
UPV0
04/06
UPV1
07/13
UPV2
10/26
FDJ
01/11
DCV
07/11
R23
02/28
R24
03/28
R25
04/28
Suppose the same with CDX707
R26
05/28
R27
06/28
R28
07/28
R29
08/28
R30 for OKTB
09/28

## Slide 9: CX707 SW Release Requirement for MRD
R-Event | Software Maturity | Corresponding Milestone | Release Due Date*1) | Build Support
TPB | Fully verified on component level | TPV BB MRD - 1 week | 9/9/2019 | Support TPV BB and TPV T&C MRD
TP3 | Updates Release | TDC - 2weeks | 1/22/2021 | Support TDC
DCV beta | System test on engineering prototype | eBB MRD | 8/6/2021 | Support FDJ
DCV 0 | Fully verified on component level | DCV BB MRD - 4 weeks | 10/27/2021 | Support <DCV BB> MRD and HiL MRD
DCV 1 | Updates Release | T/C MRD - 4 weeks | 11/24/2021 | Support <T/C> MRD
DCV 2 | Updates Release | DCV - 2 weeks | 1/5/2022 | Breadboard update, DCV vehicles update
DCV 3 | Updates Release | DCV+ 4 weeks | 2/16/2022 | Breadboard update, DCV vehicles update
R00 | Feature DV complete. | PEC - 6 weeks | 4/18/2022 | DCV vehicles update for PEC Sign-off
R04 | Feature DV signed off | FEC - 6 weeks | 5/30/2022 | DCV vehicles update for FEC Sign-off
R05 | Fully Validated Release | TT MRD - 4 weeks | 7/6/2022 | Support <TT> MRD
R06 | Fully Validated Release | PP MRD - 4 weeks | 9/21/2022 | Support <PP> MRD
R07 | Fully Validated Release | MP1/J1 MRD - 4 weeks | 12/6/2022 | Support <MP1> MRD