## Slide 1: Phase5 SW Release Plan
Think
Point of view
Plan to Implement
Implement
Roger Xu, Jiajia Zhou, James Chen
Date: March 2, 2021
Desired Outcome
Awareness
Decision
Escalation Help

## Slide 2: Phase 5 Vehicles Timeline
CDX707
CX788
UPV1
02/19
CDX747
OK2B
11/06
TT
11/04
FEC
10/28
PEC
09/16
MP2
10/09
MP1
06/12
PP
01/17
OK2B
06/21
MP1
04/26
UPV2
05/28
PP
03/13
FEC
11/23
TT
12/12
PEC
10/26
DCV
05/18
FDJ
03/29
PEC
05/30
PA
06/30
FDJ
08/06
FEC
07/11
TT
07/26
PP
10/11
MP1
02/01
UPV0
03/12
UPV1
06/11
UPV2
09/24
UPV0
05/10
UPV1
07/26
UPV2
10/15
FDJ
01/07
DCV
01/19
DCV
07/11
PA
02/10
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2021 | 2022 | 2023
HB
08/29
MP2
05/24
Phase5 Scope |  |  |  |  |  |  |  |  |  |  | 
Program | PMT5 | Nameplate | Manufacture | J1 | OKTB | EE Architecture | Centerstack Size | Cluster |  | TCU | ECG
CDX707 | Yang Youfei, Xu Fiona | Nautilus | CAF | 3/28/2023 | 3/28/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
CX788 | He Sylvia | Ford | CAF | 4/26/2023 | 6/21/2023 | FNV2 | 13.2~15.5 TBD | NA, AR HUD | Landscape | Boundle5 | ECG2
CDX747 | Yang Frank | Lincoln | BU | 6/12/2023 | 11/6/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
U611 MCA | Yang Frank | Aviator | CAF | 12/6/2023 | 1/23/2024 | FNV3 | 27 | 12.3，Standalone HUD | Landscape | Boundle6 | ECG2
U718 | Yang Frank | Navigator | BU | 3/11/2024 | 4/22/2024 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
CDX804 | Johnny | Lincoln | IMF | TBD | TBD | TBD | TBD |  | TBD |  | 
U611MCA
TT
FEC
PEC
PP
09/05
OK2B
01/23
MP1
12/06
DCV
FDJ
UPV0
03/12
UPV1
06/11
UPV2
09/24
PA
10/17
HB
12/13
06/13
10/07
11/04
02/28
06/13
PA
10/27

## Slide 3: CDX707 SW Release Plan
CDX707 VPP
Display(23.6+23.6,11.1 touch)
Package 1-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
05/28
06/11
SW Release for REC
Package 2-Ford core service
PEC
05/30
06/13
PA
06/30
07/14
FDJ
08/06
08/20
TT
07/26
08/02
PP
10/11
10/18
MP1
02/01
DCV
01/19
02/02
R0
03/19
DCV Beta
07/20
DCV2
01/05
R00
04/18
R04
05/30
R05
07/06
R06
09/21
R07 12/06
Package 3-Eco APPs
Package 4-HMI
DCV0
10/27
DCV1
11/24
DCV3
02/16
A0 PCBA
01/07 01/25
CDC AHU HW
A1 PCBA
04/30
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
Inhouse APPs
R1
03/31
R2
04/28
R3
05/26
R4
06/23
R5
07/10，07/18
R6
08/18
R7
09/15
R8
10/20
R9
11/17
R10
12/15
R11
01/12
R12
02/23
R13
03/23
R14
04/20
R15
05/18
R16
06/15
R17
07/13
R18
08/10
R19
09/07
R20
10/19
R21
11/20
R22 for OKTB
01/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
Group A for DCV Beta(R0-R5)
12/15 Delayed to 03/15 UE,04/30 UI
Cluster Assets 03/05
Group B for DCV1(R6-R9)
06/15
Group C for DCV3(R10-R11)
07/30
Group D for DCV2(R12-R13)
08/31
2021 | 2022 | 2023
07/10-08/20
10/25-12/15
05/15-06/15
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
MP2
03/01
FEC
07/11
07/25
OKTB
03/28

## Slide 4: CX788 SYNC+/AR-HUD Plan Draft (10%Take Rate) @03/02
Display
Package 1-3-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
R0
05/25
DCV Beta
12/17
DCV2
05/04
R00
08/05
R04
09/16
R05
10/14
R06
11/29
R07 03/08
DCV0
02/16
DCV1
03/30
DCV3
06/15
CDC AHU HW
B0 DV1
04/15
A2 Pre-DV
09/15
B1 DV2
09/04
R1
06/25
R2
07/25
R3
08/25
R4
09/25
R5
10/25
R6
11/25
R7
12/25
R8
02/15
R9
03/15
R10
04/15
R11
05/15
R12
06/15
R13
07/15
R14
08/15
R15
09/15
R16
10/25
R17
11/25
R18
12/25
R19
02/10
R20
03/10
R21
05/10 for OKTB
R0
04/25
R1
05/25
R2
06/25
R3
07/25
R4
08/25
R5
09/25
R6
10/25
R7
11/25
R8
12/25
R9
02/15
R10
03/18
R11
04/15
R12
05/15
R13
06/15
R14
07/15
R15
08/15
R16
09/15
R17
10/25
R18
11/25
R19
12/25
R20
02/10
R21
04/10
Group A
04/17
Group B
07/01
Group C
11/10
Group D
12/10
2021 | 2022 | 2023
Pre-DV
11/01-12/01
EMC/DV1
05/04-07/04
DV2
09/11-10/11
Re-DV
03/16-05/15
Spring Festival
National Day
Spring Festival
IVI/LED Strip/HUD UI Plan
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
CX788 VPP
UPV1
08/16
PEC
09/16
FDJ
01/07
TT
12/29
PP
03/14
MP1
05/03
DCV
06/13
FEC
11/23
OKTB
06/28
UPV0
05/31
Tooling 6 months
06/01-11/30
3/1-5/31
EC Approval
DV 3.5 months
12/01-03/15
PV 3 months
04/16-07/15
PPAP 3 months
07/16-10/15
AR-HUD
3/1-4/31
EC Approval
POC Kick Off
03/01
POC Prototype Delivery
08/15
Tooling 6 months
12/15-06/15
DV 3 months
06/16-09/15
Re-DV
09/16-10/31
PV 3 months
11/01-01/31
PPAP
02/01-02/28
SW Sign Off
AR Navi, Traditional HUD Feature
11/20
UPV0
09/15
UPV1
11/15
FDJ
03/01
UPV2
01/31
DCV
08/04
MP1 SW
04/15
MP2 SW
05/31
OTA Debug SW
SW Sign Off
AR ADAS Related Feature
05/30
MP2
EMC
05/04-06/19
UPV0
010/15
UPV1
12/15
FDJ
03/15
UPV2
02/15
DCV
08/15
PEC
10/31
PEC
12/15
PEC
09/15
FEC
11/01
TT
02/28
TT
04/02
AR-HUD
Tooling 6 months
01/31-07/31
DV 3 months
08/01-10/30
Re-DV
11/01-12/15
PV 3 months
12/16-03/16
PPAP
03/17-04/02
SW Sign Off
AR Navi, Traditional HUD Feature
12/31
MP1 SW
04/15
MP2 SW
05/31
OTA Debug SW
SW Sign Off
AR ADAS Related Feature
EMC
06/15-07/31
ME Change Post PoC
No ME Change Post PoC
PA
12/08
UPV2
11/08
Substitute parts before DV test:
Display: Support 2700*1080 resolution display ; - Forrest
AR-HUD substitute: Discuss with Baidu;- Forrest
Risk:
1. HUD/Display:
1) Sourcing complete as request;
2) ME change after PoC and drive 2 wks late;
2. CDC HW:
1) Deliver parts to CAF after EMC complete;
2) Support proposed TT MRD w/ alert;
3. CDC SW:
1) Sourcing:
2) HMI provide all info as planned;
PV
11/25-02/22
PPAP
03/22-04/04

## Slide 5: CDX747 SW Release Plan—Draft TBC
Display(23.6+23.6,11.1 touch)
Package 1-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
Package 2-Ford core service
R0
03/03
DCV Beta
12/15
DCV2
07/05
R00
9/15
R04
10/17
R05
11/06
R06
02/13
R07 05/06
Package 3-Eco APPs
Package 4-HMI
DCV0
04/10
DCV1
05/10
DCV3
08/11
A0 PCBA
01/07 01/25
CDC AHU HW
A1 PCBA
04/30
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
Inhouse APPs
R1
03/31
R2
04/28
R3
05/26
R4
06/23
R5
07/10，07/18
R6
08/18
R7
09/15
R8
10/20
R9
11/17
R10
12/15
R11
01/12
R12
02/23
R13
03/23
R14
04/20
R15
05/18
R16
06/15
R17
07/13
R18
08/10
R19
09/07
R20
10/19
R21
11/20
R22
01/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
Group A for DCV Beta
12/15 Delayed to 03/15 UE,04/30 UI
Group B for DCV0
06/15
Group C for DCV1
07/30
Group D for DCV2
08/31
2021 | 2022 | 2023
07/23-08/20
10/25-12/15
05/15-06/15
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
CDX747
OK2B
11/06
MP2
10/09
MP1
06/12
PP
03/13
FEC
11/29
TT
12/12
PEC
11/01
UPV0
04/06
UPV1
07/13
UPV2
10/26
FDJ
01/11
DCV
07/11
R23
02/28
R24
03/28
R25
04/28
Suppose the same with CDX707
R26
05/28
R27
06/28
R28
07/28
R29
08/28
R30 for OKTB
09/28

## Slide 6: U611MCA SW Release Plan--Placeholder
Display(23.6+23.6,11.1 touch)
Package 1-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
Package 2-Ford core service
R0
03/03
DCV Beta
12/15
DCV2
07/05
R00
9/15
R04
10/17
R05
11/06
R06
02/13
R07 05/06
Package 3-Eco APPs
Package 4-HMI
DCV0
04/10
DCV1
05/10
DCV3
08/11
A0 PCBA
01/07 01/25
CDC AHU HW
A1 PCBA
04/30
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
Inhouse APPs
R1
03/31
R2
04/28
R3
05/26
R4
06/23
R5
07/10，07/18
R6
08/18
R7
09/15
R8
10/20
R9
11/17
R10
12/15
R11
01/12
R12
02/23
R13
03/23
R14
04/20
R15
05/18
R16
06/15
R17
07/13
R18
08/10
R19
09/07
R20
10/19
R21
11/20
R22
01/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
Group A for DCV Beta
12/15 Delayed to 03/15 UE,04/30 UI
Group B for DCV0
06/15
Group C for DCV1
07/30
Group D for DCV2
08/31
2021 | 2022 | 2023
07/23-08/20
10/25-12/15
05/15-06/15
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
CDX747
OK2B
11/06
MP2
10/09
MP1
06/12
PP
03/13
FEC
11/29
TT
12/12
PEC
11/01
UPV0
04/06
UPV1
07/13
UPV2
10/26
FDJ
01/11
DCV
07/11
R23
02/28
R24
03/28
R25
04/28
To be updated by 03/10
R26
05/28
R27
06/28
R28
07/28
R29
08/28
R30 for OKTB
09/28

## Slide 7: CDX707 SW Release Requirement for MRD
R-Event | Software Maturity | Corresponding Milestone | Release Due Date*1) | HMI UI Release Plan | Build Support
TPB | Fully verified on component level | TPV BB MRD - 1 week | 9/9/2019 |  | Support TPV BB and TPV T&C MRD
TP3 | Updates Release | TDC - 2weeks | 1/22/2021 |  | Support TDC
DCV beta | System test on engineering prototype | eBB MRD | 8/6/2021 | Group A: DCV beta-7months | Support FDJ
DCV 0 | Fully verified on component level | DCV BB MRD - 4 weeks | 10/27/2021 | Group B: DCV0-7months | Support <DCV BB> MRD and HiL MRD
DCV 1 | Updates Release | T/C MRD - 4 weeks | 11/24/2021 | Group C-E: Meet FDJ | Support <T/C> MRD
DCV 2 | Updates Release | DCV - 2 weeks | 1/5/2022 |  | Breadboard update, DCV vehicles update
DCV 3 | Updates Release | DCV+ 4 weeks | 2/16/2022 |  | Breadboard update, DCV vehicles update
R00 | Feature DV complete. | PEC - 6 weeks | 4/18/2022 |  | DCV vehicles update for PEC Sign-off
R04 | Feature DV signed off | FEC - 6 weeks | 5/30/2022 |  | DCV vehicles update for FEC Sign-off
R05 | Fully Validated Release | TT MRD - 4 weeks | 7/6/2022 |  | Support <TT> MRD
R06 | Fully Validated Release | PP MRD - 4 weeks | 9/21/2022 |  | Support <PP> MRD
R07 | Fully Validated Release | MP1/J1 MRD - 4 weeks | 12/6/2022 |  | Support <MP1> MRD

## Slide 8: Backup material

## Slide 9: SYNC+ Phase5 HMI UX Issue & Risk Update
Think
Point of view
Plan to Implement
Implement
Roger Xu, Julia Zhu, Jiajia Zhou
Date: Feb 25, 2021
Desired Outcome
Awareness
Decision
Escalation Help

## Slide 10: Background Introduction
PIPELINE
Hero Screen and UI
UE
HW/SW Timing
UE->Hero Screen->UI
Pipe Line -Coding
Timing Plan

## Slide 11: Pre-DV/EMC Validation Mode and FIP
Pre-EMC: Audio/Camera/BT/Ethernet
Pre-DV: Nav/Audio/Media/VR/BT/Bezel Diag/DLNA
FIP
EMC Mode
DV Mode

## Slide 12: CDX707 SW Release Plan—HMI Risk
Display(23.6+23.6,11.1 touch)
Package 1-3-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
R0
03/03
DCV Beta
07/20
DCV2
01/05
R00
04/18
R04
05/30
R05
07/06
R06
09/21
R07 12/06
IVI UE Plan- Jan.15 Update
DCV0
10/27
DCV1
11/24
DCV3
02/16
A0 PCBA
01/25
CDC AHU HW
A1 PCBA
04/30
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
R1
03/31
R2
04/28
R3
05/26
R4
06/23
R5
07/10，07/18
R6
08/18
R7
09/15
R8
10/20
R9
11/17
R10
12/15
R11
01/12
R12
02/23
R13
03/23
R14
04/20
R15
05/18
R16
06/15
R17
07/13
R18
08/10
R19
09/07
R20
10/19
R21
11/20
R22 for OKTB
01/15
R0
02/23
R1
03/03
R2
03/31
R3
04/28
R4
05/26
R5
06/20
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22 for OKTB
12/15
Group A
05/05
Group B
06/15->07/15(TBC)
Group C 07/30->09/01(TBC)
Group D
08/31->10/15(TBC)
2021 | 2022 | 2023
07/10-08/05
10/25-12/15
05/15-06/15
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
Issue1:
Cluster UX will be released by UPV2，Details including Animation concept/multi theme will be continued to refine, Risk under control.
Group A
03/15
Group B
04/30
Group C
05/31
Group D
06/15
Group A
12/15
Group B
02/15
IVI UI Plan- Jan.15 Update
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
Cluster UI Plan- Unclear
Issue2:
IVI signed-off UE release plan has been delayed by 3 months; HMI should release unsigned UE supporting SW coding (refer to aligned plan in Slide8),
Issue3:
UI release plan has been delayed by 4.5 months and not frozen yet. Unsigned Group A&B UI should be released in advance supporting SW release.
Group A
12/15
Group B
02/15
CAN’T MEET Pre DV/DCV/PEC Requirement.
J1 deferral.
Group A&B& UE
03/05
Group C
04/12
Group D
06/11
CDX707 VPP
UPV1
02/19
UPV2
05/28
06/11
PEC
05/30
06/13
PA
06/30
07/14
FDJ
08/06
08/20
TT
07/26
08/02
PP
10/11
10/18
MP1
02/01
DCV
02/02
MP2
03/01
FEC
07/11
07/25
OKTB
03/28

## Slide 13: CDX707 Cluster HMI Release Plan
Cluster Grouping Docs will be continued to refine, Risk under control.

## Slide 14: CDX707 Minimum IVI Group A Delivery
Launcher& System UI
Climate
Camera
(4) Radio
(5) Bluetooth/USB Music
(6) Video
(7) System setting
(8) Navi (SW_Tier1 Release UX)
(9) Fundamental voice function (SW_Tier1 Release UX)
(10) DLNA
(11) Bluetooth Phone
IVI SW vendors have increased headcount to compensate the delay caused by HMI, but still has risk.
ICA: Breakdown the UX release plan feature by feature. Need HMI team support deliver draft or preliminary UX for coding.
What can we do now to meet CDX707 J1?

## Slide 15: CDX707 Minimum IVI Group A Delivery---J1 deferral 6 weeks
Features | Feature Owner | HMI Lead | Function Clarification | UE Delivery (<1Week) | UE Sign-off (1 Week) | Hero Screen (1 month??) | UI Delivery (2 Weeks Ergo Signoff + 2 Weeks HMI Delivery) | UI Stagger Requested by EESE | Gap/Weeks | UI Sign-off (2 weeks) | Comments
(1) System UI | TBD | Zhang Yiwan | Feb.8 | Feb.9 | Feb.9 | Mar. 30->Mar. 15 | Apr. 28 -> Apr. 13 | Mar. 1 | 6 | May 13 -> Apr. 22 | UI Apr.1 deliver without Ergo sign off
(1) Launcher | TBD | Zhang Yiwan | Feb.20 | Feb. 23 | Feb.25 | Mar. 30->Mar. 15 | Apr. 28 -> Apr. 13 | Mar. 1 | 6 | May 13 -> Apr. 22 | UI Apr.1 deliver without Ergo sign off
(2) Climate | Xie Will | Pan Jingjing | Jan.29 -> Feb. 3 | Feb.20 -> Feb. 23 | Feb. 26 | Mar. 30->Mar. 15 | Apr. 28 -> Apr. 14 | Mar. 19 | 4 | May 13 -> Apr. 29 | 
(3) Camera – 360,RVC | Li Xin | Zou Yujuan | Feb.8 -> Feb. 22 | Mar.8 -> Feb.24 | Mar.15 -> Mar.5 | Mar. 30->Mar. 15 | May 5 -> Apr. 21 | Apr. 6 | 4 | May 19 -> May 5 | Feasibility under YFVE confirm
(4) Radio - AM/FM | Xiang, Zhengxi | Wang, Wei Hua | Feb.8 | Mar.8 -> Feb. 23 | Mar.15 -> Mar.1 | Mar. 30->Mar. 15 | May 5 -> Apr. 21 | Apr.6 | 4 | May 19 -> May 5 | 
(5) Bluetooth Music | Xu Amy | Chen Yu | Jan.29 | Feb. 9 | Feb.26 | Mar. 30->Mar. 15 | Apr. 28 -> Apr. 14 | Mar. 19 | 4 | May 13 -> Apr. 29 | 
(6) USB Video | Xiang, Zhengxi | Luisa Liu | Feb. 8 | Mar.8 -> Feb. 23 | Mar.15 -> Mar.1 | Mar. 30->Mar. 15 | May 5 -> Apr. 21 | Apr.6 | 2 | May 19 -> May 5 | 
(7) System Setting Details in next slide | In next slide | In next slide | Feb.8 | Mar.8 | Mar.15 | Mar. 30->Mar. 15 | May 5 -> Apr. 21 | Mar. 19 | 5 | May 19 -> May 5 | 
(8) DLNA | Jia, Elaine | Wang, Wei Hua | Feb.8 -> Feb.20 | Mar.8->Mar.3 | Mar.15 | Mar. 30->Mar. 15 | May 5 -> Apr. 14 | Apr.15 | 0 | Apr.30 -> Apr. 29 | 
（9）Bluetooth Phone | Xu Amy | Chen Yu | Jan.29 | Feb.20 -> Feb.8 | Feb.26 | Mar. 30->Mar. 15 | Apr. 28 -> Apr. 14 | Mar. 19 | 4 | May 13 -> Apr. 29 | 
(10) USB Music | Xiang, Zhengxi | Wang, Wei Hua | Jan.29 | Feb.9 | Feb.26 | Mar. 30->Mar. 15 | Apr. 28 -> Apr. 14 | Mar. 19 | 4 | May 13 -> Apr. 29 | 
1. Hero Screen 03/15 delivery should be promised and optimized.
2. UI Delivery time should be optimized based on feature complexity.

## Slide 16: CDX707 Minimum IVI Group A Delivery---J1 deferral 6 weeks
 | Features | Feature Owner | HMI Lead | Function Clarification | UE Delivery (<1Week) | UE Sign-off (1 Week) | Hero Screen (1 month??) | UI Delivery (2 Weeks Ergo Signoff + 2 Weeks HMI Delivery) | UI Sign-off (2 weeks)
System Setting | 一级菜单 1st level menu | Huang, Xue |  | Feb. 8 | Feb. 22->Feb.23 | Feb. 25 | Mar.30->Mar.15 | May. 5->Apr.21 | May 19->May.5
 | 语音设置 audio setting | Huang, Xue | Pan, Jingjing | Feb.8 -> TBD | Mar.8->TBD | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | 蓝牙连接 BT connection |  | Chen, Yu | Feb.8 | Mar.8 -> Feb. 9 | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | 日期和时间设置 date&time setting |  | Wang, Wei Hua | Feb.8 | Mar.8 | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | Brightness |  | Wang, Wei Hua | Feb.8 | Mar.8 | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | Display off |  | Wang, Wei Hua | Feb.8 | Mar.8 | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | 显示/亮度设置 display/brightness setting | Chen, James | Wang, Wei Hua | Feb.8 | Mar.8->Feb.23 | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | 关于本机 | Huang, Xue | Zou, Yujuan | Feb.8 | Mar.8->Feb.23 | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | 声音设置 sound setting |  | Wang, Wei Hua | Feb.8 | Mar.8->Feb.23 | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | Wifi 热点 Wifi Hot Spot |  | Wang, Wei Hua | Feb.8 | Mar.8->Feb.23 | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | wifi设置 wifi setting |  | Wang, Wei Hua | Feb.8 | Mar.8->Feb.23 | Mar.15 | Mar.30->Mar.15 | May 5->Apr.21 | May 19->May.5
 | Keyboard | Yao, Tristan | Liu, Luisa (Fan.) | Feb. 8 | Mar. 15->Feb.24 | Mar. 30-> Feb.26 | Mar.30->Mar.15 | Apr.5 | Apr.20

## Slide 17: CDX707 IVI Group B-D UI <Timing update Feb25> Should be Updated
Should be updated and pulled ahead.

## Slide 18: The Potential Risk of CDX707
Hardware Risk: Hardware design & validation not completed by DCV MRD/DCV if Pre-DV/DV software release delay 1.5 months.
Critical DV can not be completed by DCV MRD.
Risk of module with faulty functions to support DCV build.
Vehicle DV(EMC/thermal/audio attribute..etc) sign-off can not catch-up PEC/FEC milestone.
Component re-DV sign-off can not catch-up FEC milestone.
HMI Risk: Un-signed HMI UE and UI delivered to supplier for development and software integration. Low quality of software performance, interaction, experience can’t support plant launch/validation process(FCPA/R202/VOCF/Management evaluation etc.), Especially AIMS flow(Software team doesn't accept AIMS in for this level software w/ un-signed HMI UX). AIMS should not be reported until PEC.
SW stability: The HMI unsigned UE & UI delivers 3 suppliers for software development and integration in stagger way, this definitely would cause pretty much more frequent software integration/release/validation. This could cause high software delivery risk/cost(for example, regression bug, unexpected issue during re-release software, capability and stability issue).
Deviation for PEC/FEC should be needed: the PEC/FEC for IVI SW need to be postponed or the reduce the criteria .
People resource/Support should be added: More NSPS testing service/Test vehicle(5 vehicles) required to catch up the frequent software release and validation, and cover more issue reported from JV plant. Need program to coordinate and organize the enhanced test plan in plant(5 vehicles*10 tester*5days).

## Slide 19: CDX707 SW Release Plan---IVI HMI Plans
CDX707 VPP
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
05/28
#1:SW Release for REC
PEC
05/30
PA
06/30
FDJ
08/06
FEC
07/11
TT
07/26
PP
10/11
MP1
02/01
DCV
01/19
DCV Beta
07/20
DCV2
01/05
R00
04/18
R04
05/30
R05
07/06
R06
09/21
R07 12/06
DCV0
10/27
DCV1
11/24
DCV3
02/16
R5 07/10,07/18
R8 10/20
R9 11/17
R13 03/23
2021 | 2022 | 2023
MP2
03/01
A0 PCBA 01/25
#1:CDC AHU HW
A1 PCBA 04/30
B0 DV1 10/05
A2 Pre-DV 06/30
B1 DV2 04/15
Pre-DV
DV1
DV2
07/10-08/05
10/25-12/15
05/15-06/15
[HMI Plan Delivery Agreement@2020/11/25]: HMI release plan can meet SW release requirements.
UE: Group A-Dec 15, Group B-Feb 15
UI: Group A-Dec 15, Group B-Feb 15
#2: SW Release for REC
R5 09/24
R8 12/31
R9 1/29
R13 05/23
#2: CDC AHU HW
Pre-DV
DV1
09/30-10/31
01/05-03/05
07/15-08/15
[HMI Plan@2021/1/17]: The overall SW delay is about 2.5 months, Pre-DV and DV1(DCV) delay 2.5 months, J1 delay 2 months
UE: Group A-Mar 15, Group B-Apr 30
UI: Group A-Apr 30, Group B-Jun 15
#4： SW Release for REC
R5 08/10
R8 11/19
R9 12/17
R13 04/22
#4：CDC AHU HW
Pre-DV
DV1
08/15-09/15
11/25-01/15
06/15-07/15
[Engineering proposal @ 2021/02/24]: Minimize HMI delivery of features one by one to provide UE and UI supporting SW release. The overall SW delay is about 1.5 month, Pre-DV and DV1(DCV) delay 1.5 month, J1 delay 1.5 month
UE: Group A-Mar 15, Group B-Apr 20(TBC)
UI: Group A-May 5, Group B-May 20(TBC)
#3： SW Release for REC
R5 11/10
R8 02/21
R9 03/17
R13 06/23
#3：CDC AHU HW
Pre-DV
DV1
11/15-12/10
02/25-04/15
08/15-09/15
[HMI Plan@2021/02/01 Draft ]:The overall delay is about 4 months, Pre-DV and DV1(DCV) delay 4 months, J1 delay 3 months
UE: Group A-Mar 15, Group B-Apr 30
UI: Group A-Jun 15, Group B-Jul 30
DV2
DV2
DV2
J1 deferral 3 months
J1 deferral 1 month
J1 deferral 2 months

## Slide 20: HMI Enablers to Support Software Release Plan
Enablers (including Driver info, Pano, Controller) | Lead | Target Date
(1) UE Stagger Group A (2) Framework to be frozen (3) UE and Logic Flow Final Group A common features (4) UE and Logic Flow Final Group A China unique features | M Schneider M Schneider & Julia M Schneider Julia Zhu | On-going Feb 18 Feb 25 Mar 15
(5) Hero Screen Stagger Group A (6) Hero Screen Final Group A | P Ruthenberg P Ruthenberg | On-going Mar 1
(7) UI Stagger Group A (8) All Assets & Slicing Final Group A common feature (9) All Assets & Slicing Final Group A China unique features | M Schneider M Schneider Julia Zhu | On-going Mar 27 Apr 27
The Enablers above supports a Recovery to a 1 Month CDX707C J1 deferral 3 Months
Further enablers required to recover J1 Timing per Plan of Record; Feb 2023

## Slide 21: UE-Hero Screen-UI Introduction
UI: User Interface
Focus on visual design, responsible for product graphics, icons, color matching, creating beauty, style and temperament.
  UE: User Experience
Focus on user interaction, the jump logic between the different interfaces or buttons. But no detailed coordinates or size information.
  Hero Screen
Part of the UI design pages, If a product has a total of 8000 UI pictures, HMI team will design the main 200 pictures as hero screen for reference, and than design the other pictures.
  UE: User Experience
UI: User Interface
UI: User Interface