## Slide 1: Phase5 SW Release Plan
Think
Point of view
Plan to Implement
Implement
Roger Xu, Jiajia Zhou
Date: April 22, 2021
Desired Outcome
Awareness
Decision
Escalation Help

## Slide 2: Phase 5 Vehicles Timeline
CDX707
CX788
UPV1
02/19
CDX747
TT
12/29
12/21
FEC
11/23
PEC
10/14
PP
03/14
03/01
OK2B
06/27
MP1
05/03
04/29
DCV
06/13
FDJ
01/07
UPV0
05/10
UPV1
08/16
UPV2
11/08
PA
12/08
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
2021 | 2022 | 2023 | 2024
MP2
05/31
Phase5 Scope |  |  |  |  |  |  |  |  |  |  | 
Program | PMT5 | Nameplate | Manufacture | J1 | OKTB | EE Architecture | Centerstack Size | Cluster |  | TCU | ECG
CDX707 | Yang Youfei, Xu Fiona | Nautilus | CAF | 3/28/2023 | 3/28/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
CX788 | He Sylvia | Ford | CAF | 4/26/2023 | 6/21/2023 | FNV2 | 15.3 | NA, AR HUD | Landscape | Boundle5 | ECG2
CDX747 | Yang Frank | Lincoln | BU | 6/12/2023 | 11/6/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
U611 MCA | Yang Frank | Aviator | CAF | 12/6/2023 | 1/23/2024 | FNV3 | 27 | 12.3，Standalone HUD | Landscape | Boundle6 | ECG2
U718 | Yang Frank | Navigator | BU | 3/11/2024 | 4/22/2024 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
CDX804 | Johnny | Lincoln | IMF | TBD | TBD | TBD | TBD |  | TBD |  | 
U611MCA
TT
FEC
PEC
PP
09/05
OKTB
01/23
MP1
12/06
DCV
FDJ
UPV0
03/12
UPV1
06/11
UPV2
09/24
PA
10/17
HB
12/03
06/13
10/07
11/04
02/28
06/13
UPV2
06/11
PEC
06/13
PA
07/14
FDJ
08/20
TT
08/24
PP
11/09
MP1
02/01
DCV
02/02
MP2
03/01
FEC
07/25
OKTB
03/28
OK2B
11/06
MP2
10/09
MP1
06/12
PP
03/13
FEC
11/29
TT
12/12
PEC
11/01
UPV1
07/13
UPV2
10/26
FDJ
01/11
DCV
07/11
CX718
FEC
04/18
PEC
03/07
OK2B
04/22
DCV
10/24
FDJ
04/26
UPV0
08/03
UPV1
11/02
UPV2
02/15
PA
02/23
MP2
04/08
TT
08/07
PP
10/23
MP1
03/11

## Slide 3: CDX707 SW Release Plan @03/30
CDX707 VPP
Display(23.6+23.6,11.1 touch)
Vendor Integration
SW Release for CAF/FO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
06/11
SW Release for REC
PEC
06/13
PA
07/14
FDJ
08/20
TT
08/24
PP
11/09
MP1
02/01
DCV
02/02
DCV Alpha
03/19
DCV Beta
08/02
ITV Test
A0 PCBA
01/25
CDC AHU HW
A1 PCBA
05/25
B0 DV1
10/05
A2 Pre-DV
06/30
B1 DV2
04/15
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
DCV Alpha1
03/31
DCV Alpha2
04/28
DCV Alpha3
05/26
DCV Alpha4
06/23
DCV Beta
07/18
DCV Beta1
08/18
DCV Beta2
09/15
DCV0
10/20
DCV0.1
11/17
DCV1
12/15
DCV2
01/12
DCV3
02/23
R00
03/23
R01
04/20
R04
05/18
R05
06/15
R05.1
07/13
R05.2
08/10
R06
09/07
R06.1
10/19
R07
11/20
R08 for OKTB
01/15
DCV Alpha0
02/23
DCV Alpha1
03/03
DCV Alpha2
03/31
DCV Alpha3
04/28
DCV Alpha4
05/26
DCV Beta
06/20
DCV Beta1
07/21
DCV Beta2
08/18
DCV0
09/15
DCV0.1
10/20
DCV1
11/17
DCV2
12/15
DCV3
01/12
R00
02/23
R01
03/23
R04
04/20
R05
05/18
R05.1
06/15
R05.2
07/13
R06
08/10
R06.1
09/07
R07
10/19
R08 for OKTB
12/15
Group A
03/15 sign-off UE
05/05 Stagger UI
05/19 sign-off UI
Group B
04/30 UE
06/02 stagger UI
06/16 sign-off UI
Group C 05/21 UE
08/17 UI
Group D
06/15 UE
09/15 UI
TBD
2021 | 2022 | 2023
07/10-08/20
10/25-1/25
05/15-06/15
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
MP2
03/01
FEC
07/25
OKTB
03/28
UX Release
FNVx Release
DCV0
11/03
DCV1
12/29
DCV2
01/26
DCV3
03/09
R01
05/04
R04
06/01
R05
06/29
R05.1
07/27
R00
04/06
R05.2
08/24
R06
09/21
R06.1
11/02
R07
12/04
R08 for OKTB
01/24
SOA Gateway
Wireless Interface Router
IVI Provisioning
Bezel Diagnostics(SOA related)
Diagnostic_ Analytic
CCS –Authorization
CCS – UFM/PTE
IP Pass Through Client
USB Update of TCU/ECG
SYNC+ SOC USB Update
SYNC+ SOC OTA Update
SYNC+ MCU USB Update
SYNC+ MCU OTA Update
Cluster SOC USB Update
Cluster MCU OTA Update
Rocket Setup
Purchase process
03/23-07/08
Net/Diagnostic full function 11/17 for DCV1
ITV P2 complete 07/07
R09 for OTA
04/28 TBD
PEC1
07/26
FEC1
09/06
Net/Diag develop~4.5months
Bug fix ~1.5months
ITV P1 Release for R00
03/23
Net/Diag Bug fix
For DCV2
01/08
Report Review 07/25
Vendor P1 test ~2.5 months
P2 Log Prepare ~2months

## Slide 4: CX788 SYNC+/AR-HUD/Display Draft Plan A@03/10
New Display
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
DCV2
05/30
R00
09/02
CDC AHU HW
B0 DV1
04/15
A Sample Pre-DV
12/15
B1 DV2
09/04
2021 | 2022 | 2023
Pre-DV
01/01-02/01
DV1
05/04-08/04
DV2
09/11-11/16
Re-DV
03/16-05/15
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
CX788 VPP
UPV1
08/16
PEC
10/14
FDJ
01/07
TT
12/29
12/21
PP
03/14
03/01
DCV
06/13
FEC
11/23
OKTB
06/27
UPV0
05/31
Tooling 6 months
06/01-11/30
3/1-5/31
EC Approval
DV 3.5 months
12/01-03/15
PV 3 months
04/16-07/15
PPAP 3 months
07/16-10/15
AR-HUD-Plan A
3/1-4/31
EC Approval
POC Kick Off
03/01
POC Prototype Delivery
08/15
Tooling 6 months
12/15-06/15
DV 3 months
06/16-09/15
Re-DV
09/16-10/31
PV 3 months
11/01-01/31
PPAP
02/01-02/28
SW Sign Off
AR Navi, Traditional HUD Feature
11/20
UPV0
09/15
UPV1
11/15
FDJ
03/01
UPV2
01/31
DCV
08/04
MP1 SW
04/15
MP2 SW
05/31
OTA Debug SW
SW Sign Off
AR ADAS Related Feature
05/31
MP2
EMC
05/04-06/19
PEC
09/15
FEC
11/01
TT
02/28
No ME Change Post PoC
PA
12/08
UPV2
11/08
PV
11/25-02/22
PPAP
02/23-03/07
3/1-4/31
EC Approval
Tooling 5.5months
12/1-05/15
DV 3 months
05/16-08/15
Re-DV
08/16-9/31
PV 3 months
10/7-01/7
EMC
04/10-05/15
TFT HUD
DCV Beta
01/07
R04
10/12
R05
11/08
R06
01/17
DCV0
03/21
DCV1
04/18
DCV3
07/11
Package 1-3-HW+Base SW
SW Release for REC
R07 03/15
R4
11/25
R5
12/25
R9
04/30
R10
05/30
R11
06/30
R12
07/30
R13
08/30
R14
09/30
R15
11/15
R16
12/15
R17
01/15
R18
02/28
R19
03/30
R20
04/30
R21
05/30 for OKTB
R4
10/25
R5
11/25
R8
02/28
R9
03/30
R10
04/30
R11
05/30
R12
06/30
R13
07/30
R14
08/30
R15
10/15
R16
11/15
R17
12/15
R18
01/15
R19
02/28
R20
03/30
R21
04/30
Group A UI
10/15 TBD
Target 8/15
Spring Festival
National Day
Spring Festival
IVI UI Plan
R8
03/30
Group C UI
12/15
Group D UI
01/15
Group B UI
11/15
Group A UE
07/31
Target 05/15
Checkpoint Post T&P Research
Checkpoint C
EMC
05/04-06/24
EMC
09/11-10/16
Checkpoint A
Checkpoint B
AR-HUD UI Plan
PoC UI Assets
09/30
UI Production Assets
11/15
System UI Draft
05/30
Sign-off 06/30
Target 04/30
MP1
05/03
04/29
HW FROZEN
04/15
SOBD 06/01
MFL Release
04/15
FIP Draft Release
04/30
HMI System UI
04/30
Group 8 UE
08/31

## Slide 5: CX788 HUD Plan Draft A/B @03/03
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2021 | 2022 | 2023
CX788 VPP
UPV1
08/16
PEC
10/14
FDJ
01/07
TT
12/29
PP
03/14
MP1
05/03
DCV
06/13
FEC
11/23
OKTB
06/28
UPV0
05/31
AR-HUD- Plan A
3/1-4/31
EC Approval
POC Kick Off
03/01
POC Prototype Delivery
08/15
Tooling 6 months
12/15-06/15
DV 3 months
06/16-09/15
Re-DV
09/16-10/31
PV 3 months
11/01-01/31
PPAP
02/01-02/28
SW Sign Off
AR Navi, Traditional HUD Feature
11/20
UPV0
09/15
UPV1
11/15
FDJ
03/01
UPV2
01/31
DCV
08/04
MP1 SW
04/15
MP2 SW
05/31
OTA Debug SW
SW Sign Off
AR ADAS Related Feature
05/31
MP2
EMC
05/04-06/19
PEC
09/15
FEC
11/01
TT
02/28
No ME Change Post PoC
PA
12/08
UPV2
11/08
3/1-4/31
EC Approval
Tooling 5.5months
12/1-05/15
DV 3 months
05/16-08/15
Re-DV
08/16-9/31
PV 3 months
10/7-01/7
EMC
04/10-05/15
TFT HUD
AR-HUD- Plan B
3/1-4/31
EC Approval
POC Kick Off
03/01
MP1 SW
04/15
MP2 SW
05/31
OTA Debug SW
UPV0
10/15
UPV1
12/15
FDJ
03/15
UPV2
02/15
DCV
09/15
PEC
10/31
FEC
12/15
TT
04/02
ME Change Post PoC
Tooling 6 months
01/31-07/31
DV 3 months
08/01-10/30
Re-DV
11/01-12/15
PV 3 months
12/16-03/16
PPAP
03/17-04/02
SW Sign Off
AR Navi, Traditional HUD Feature
12/31
EMC
06/15-07/31

## Slide 6: CDX747 SW Draft Release Plan @03/12
Display(23.6+23.6,11.1 touch)
Package 1-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
Package 2-Ford core service
DCV Beta
12/15
DCV2
07/05
R00
9/15
R04
10/17
R05
11/06
R06
02/13
R07 05/06
Package 3-Eco APPs
Package 4-HMI
DCV0
04/10
DCV1
05/10
DCV3
08/11
CDC AHU HW
B0 DV1
3/10
A Pre-DV
11/10
B1 DV2
9/20
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
Inhouse APPs
R7
09/15
R8
10/20
R9
11/17
R10
12/15
R11
01/12
R12
02/23
R13
03/23
R14
04/20
R15
05/18
R16
06/15
R17
07/13
R18
08/10
R19
09/07
R20
10/19
R21
11/20
R22
01/15
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
Group A for DCV Beta
06/15 UI
Group B for DCV Beta
07/13
Group C for DCV0
08/30
Group D for DCV2
10/26
2021 | 2022 | 2023
12/01-1/05
4/1-6/1
10/20-11/20
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
CDX747
OK2B
11/06
MP2
10/09
MP1
06/12
PP
03/13
FEC
11/29
TT
12/12
PEC
11/01
UPV0
04/06
UPV1
07/13
UPV2
10/26
FDJ
01/11
DCV
07/11
R23
02/28
R24
03/28
R25
04/28
R26
05/28
R27
06/28
R28
07/28
R29
08/28
R30 for OKTB
09/28
HW Request Frozen
7/13
MFL Release
04/30
FIP Draft Release
05/30
Notes: 有功能增加；
音频架构有变化。

## Slide 7: U611MCA SW Release Plan @03/12
Display(12.3+27 TOUCH)
Package 1-HW+Base SW
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
Package 2-Ford core service
DCV Beta
12/13
DCV2
06/01
R00
8/19
R04
9/19
R05
4/13
R06
07/05
R07 9/30
Package 3-Eco APPs
Package 4-HMI
DCV0
03/13
DCV1
04/13
DCV3
07/13
CDC AHU HW
B0 DV1
3/10
A Pre-DV
10/15
B1 DV2
8/20
Pre-DV
DV1
DV2
DV
Inhouse APPs
R6
08/18
R7
09/15
R8
10/20
R9
11/17
R10
12/15
R11
01/12
R12
02/23
R13
03/23
R14
04/20
R15
05/18
R16
06/15
R17
07/13
R18
08/10
R19
09/07
R20
10/19
R21
11/20
R22
01/15
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R6
07/18
Group A for DCV Beta
05/16 UI
Group B for DCV Beta
06/11
Group C for DCV0
08/30
Group D
9/24
2021 | 2022 | 2023
11/01-12/1
4/1-6/1
9/20-11/01
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
EMC
National Day
National Day
Spring Festival
Spring Festival
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
R6
07/21
R7
08/18
R8
09/15
R9
10/20
R10
11/17
R11
12/15
R12
01/12
R13
02/23
R14
03/23
R15
04/20
R16
05/18
R17
06/15
R18
07/13
R19
08/10
R20
09/07
R21
10/19
R22
12/15
U611MCA
OK2B
1/23
MP1
12/06
PP
09/5
FEC
11/04
TT
6/13
PEC
10/07
UPV0
03/16
UPV1
06/11
UPV2
9/24
FDJ
12/3
DCV
06/13
R23
02/28
R24
03/28
R25
04/28
R26
05/28
R27
06/28
R28
07/28
R29
08/28
R30 for OKTB
09/28
HB
2/28
HW Request Frozen
6/11
Group A UE
04/15
01/27
05/05
MFL Release
04/30
FIP Draft Release
05/30
Notes: 有功能增加；
音频架构有变化。

## Slide 8: Phase5 SYNC+ Timeline Draft
Project VPP
Vendor Integration
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
UPV2
SW Release for REC
UX Release
PEC
PA
FDJ
TT
PP
MP1
DCV
DCV Beta
DCV2
R00
R04
R05
R06
R07
FNV Features Release
Key Point
DCV0
DCV1
DCV3
A0 SAMPLE
CDC AHU HW
A1 SAMPLE
B0 DV1
B1 DV2
Pre-DV
DV1
DV2
iTV Feature Release
Group A
Group B
Group C
Group D
9 wks.
Eng version for vendor’s internal release and test.
Eng version not necessary to release.
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
MP2
FEC
OKTB
UPV0
PS/PSC
Initial Platform Release
Critical feature complete
MVP Complete-Vehicle features
Full Feature Complete
Bug fixing
J1 Release
SOA Gateway
Wireless Interface Router
IVI Provisioning
Bezel Diagnostics(SOA related)
Diagnostic_ Analytic
CCS –Authorization
CCS – UFM/PTE
IP Pass Through Client
USB Update of TCU/ECG
SYNC+ SOC/MCU USB Update
SYNC+ SOC/MCU OTA Update
Cluster SOC USB Update
Cluster MCU OTA Update
Rocket Setup
4 months ~Autosar package purchase
6 months ~ITV test complete
1.Bill of feature Initialized(MFL)
2.Feature Owner confirmations
3. Basic Level spec are available
1. Supplier Sourced (SOBD)
======
1.Bill of feature Finalized
2.Platform feature spec complete and cascaded
3.Function Safety Concept updated and completed
4.Cybersecurity Requirements Identified
5.UX(UEUI) alignment confirmed
6.SW environment and baseline Design
1. Platform feature spec finalization and sign off
2.Simulate feature integration of interfaces, states and responses to requested behavior
3. Early test of new and C/O features with physical parts
1.DCV Beta verified supporting Pre-DV/EMC, critical function including Climate/Camera/Radio/Music/Video/Navigation/Speed meter/Driving Info etc.
2.Feature Software early system-level integration test start at <FDJ> breadboard
3. UX doc sign off by HMI/Studio team
1.DCV1 verified supporting DV/EMC/DCV MRD with full function code completed.
2.Feature Software early system-level integration test complete by <DCV> breadboard, verify feature functionality and performance requirements.
1All design verification testing completed by <PEC>
2.Feature Software system-level integration test complete and sign off by feature owner and HMI team
3.R00 release for <PEC> without
critical blocker issue, Diagnostics Part2 DV(iTV) test report shows 100% passed
1. Software OTA window preserved post Job1 and before OKTB.
2. Software OTA window preserved post OKTB
5 wks.
12 wks.
HW REQUIREMENT FROZEN
DCV Beta1
R05.1
R08

## Slide 9: CDX707 SW Release Requirement for MRD
CDX707 |  |  |  | 
R-Event | Software Maturity | Corresponding Milestone | Release Due Date*1) | Build Support
TPB | Fully verified on component level | TPV BB MRD - 1 week | 9/9/2019 | Support TPV BB and TPV T&C MRD
TP3 | Updates Release | TDC - 2weeks | 1/22/2021 | Support TDC
DCV beta | System test on engineering prototype | eBB MRD | 8/20/2021 | Support FDJ
DCV 0 | Fully verified on component level | DCV BB MRD - 4 weeks | 11/10/2021 | Support <DCV BB> MRD and HiL MRD
DCV 1 | Updates Release | T/C MRD - 4 weeks | 12/8/2021 | Support <T/C> MRD
DCV 2 | Updates Release | DCV - 2 weeks | 1/19/2022 | Breadboard update, DCV vehicles update
DCV 3 | Updates Release | DCV+ 4 weeks | 3/2/2022 | Breadboard update, DCV vehicles update
R00 | Feature DV complete. | PEC - 6 weeks | 5/2/2022 | DCV vehicles update for PEC Sign-off
R04 | Feature DV signed off | FEC - 6 weeks | 6/13/2022 | DCV vehicles update for FEC Sign-off
R05 | Fully Validated Release | TT MRD - 4 weeks | 7/13/2022 | Support <TT> MRD
R06 | Fully Validated Release | PP MRD - 4 weeks | 9/28/2022 | Support <PP> MRD
R07 | Fully Validated Release | MP1/J1 MRD - 4 weeks | 12/6/2022 | Support <MP1> MRD
CX788 |  |  |  | 
R-Event | Software Maturity | Corresponding Milestone | Release Due Date*1) | Build Support
TPB | Fully verified on component level | TPV BB MRD - 1 week | NA | Support TPV BB and TPV T&C MRD
TP3 | Updates Release | TDC - 2weeks | 7/30/2021 | Support TDC
DCV beta | System test on engineering prototype | eBB MRD | 1/7/2022 | Support FDJ
DCV 0 | Fully verified on component level | DCV BB MRD - 4 weeks | 3/21/2022 | Support <DCV BB> MRD and HiL MRD
DCV 1 | Updates Release | T/C MRD - 4 weeks | 4/18/2022 | Support <T/C> MRD
DCV 2 | Updates Release | DCV - 2 weeks | 5/30/2022 | Breadboard update, DCV vehicles update
DCV 3 | Updates Release | DCV+ 4 weeks | 7/11/2022 | Breadboard update, DCV vehicles update
R00 | Feature DV complete. | PEC - 6 weeks | 8/5/2022 | DCV vehicles update for PEC Sign-off
R04 | Feature DV signed off | FEC - 6 weeks | 10/12/2022 | DCV vehicles update for FEC Sign-off
R05 | Fully Validated Release | TT MRD - 3 weeks | 11/8/2022 | Support <TT> MRD
R06 | Fully Validated Release | PP MRD - 4 weeks | 1/17/2023 | Support <PP> MRD
R07 | Fully Validated Release | MP1/J1 MRD - 4 weeks | 3/15/2023 | Support <MP1> MRD

## Slide 10: Backup material

## Slide 11: CDX707 HW and SW Design & Validation Plan
Proposed resolution:
< DCV>: Retrofit SYNC+ HW with R10 SW on 22-Feb-2022.
<PEC><FEC> ><PSW>: Stagger milestone for SYNC+& related features.
<TT>: Check point at PEC 08/01 for SYNC+ retrofit on vehicle.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5
DCV
02/02
2021 | 2022 | 2023
DCV Beta(R5 Eng)
09/10
DCV0(R8 Eng)
12/20
（Critical DV)
DCV1(R10 Eng)
R10 2/22
SW Release
DCV Beta(R5 Eng)
07/10
(Pre-DV)
DCV0(R8 Eng)
10/20
（Critical DV)
SYNC+ Build
&Validation
07/13-9/13
10/21-12/15
Critical DV
12/21-4/5
06/07–7/10
09/13-11/18
12/24-2/22
2/22 – 5/27
08/02-09/05
TT build & PV
Ver. 20210224
PEC
06/13
FEC
07/11
TT
08/10
11/02
DCV MRD
01/05
MP1
02/01
MP2
03/01
UPV1
UPV2
PA
07/14
FDJ
08/20
VPP
SYNC+ DEVELOPMENT
Current plan
HMI 8wks delay
Vehicle level test/sign off
Vehicle level test/sign off
SYNC+ Build
&Validation
PSW
1/19
12/22
3wks
05/30
07/25
08/24
6wks
6wks
11/09
Pre-DV:
Preliminary DV and debug for basic functions of platform.
Hand build prototype sample (w/ ~30% design completion)
Test setup trail run
Test at none Ford certified Lab.
Critical DV:
Safety function validation(Speed, PRND, Fuel, Telltale, RVC, Climate, ESP/ADAS setting), EMC/thermal/Key off load, High/Low temperature operation
DCV off-tool sample
Ford certified Lab.
07/12-10/21
10/29
12/29
09/12-12/21
Re-DV
7wks
DCV1
PEC1
FEC1
3/15
(HMI)
New plan
Critical DV can’t complete by DCV MRD. (7wks gap)
02/22
PP
07/26
09/06
PSW
5/19
TT Build & PV
TT Containment:
Aligned with NMP: SYNC+ HW & SW w/ PEC signed off to support TT build. Potential TT retrofit 2 wks post TT required to contain critical DV test failure
TT/PP VOCF 2 shift to support robust SW & HW delivery
03/05
06/16
3/30
Hero S
5/5
Group A
6/1
Group C
6/16
UPV2
7/1
VPP
Checkpoint
1
2
3
DCV1(R10 Eng)
12/20
R00(R13 Eng) 04/06
R04(R15 Eng) 06/01
（Re-DV）
12/15
(HMI)
HMI 12wks delayed
3/15
SW Release
Compress Development timing and stagger DCV software to 3 version (R10/11/12) to support PEC/FEC sign off to contain HMI 12wks delay
PSW
HMI
HMI
(DCV build and PEC sign off)
To ensure robust and quality delivery no timing opportunity could be further compressed, downstream engineering work postponed by 8wks
(DCV build and vehicle test/sign off)
DV Test Impact & Opp.:
By R10 Feb. 22, 20 DCVs built w/ 4 plan to be shipped out at Feb. 15 for US Calibration
Further discussion with Cal to align the containment plan if defer 4 Cal. DCVs 1wk with right level HW & SW
Study to build DCV in 2 lines or add more DCVs to reduce build time
DCV Opportunity:
R8 ilo R10 to support DCV build w/ downstream test hold till R10 ready
CDC module retrofit takes 44 minutes only with control screen, lower vent and floor console disassembled
DCV2(R11 Eng)
DCV3(R12 Eng)
(DCV reflash)
Root cause & Countermeasure
Sample Build
Debug & Build
Critical DV
Re-DV
Sample Build
12/29
Pre-DV
SYNC+ CDC DV
4/18-06/06
Root cause & Countermeasure
06/10-08/01
SYNC+ CDC DV
Debug & Build
Pre-DV
DCV2(R11 Eng)
DCV3(R12 Eng)
R00(R13 Eng) 06/06
R04(R15 Eng) 08/01
（Re-DV）

## Slide 12: CDX707 System Block Diagram
2021 | 2022 | 2023