## Slide 1: Phase5 SW Release Plan
Think
Point of view
Plan to Implement
Implement
Jiajia Zhou, Hanhan Yang, Ying Zhang
Date:01.05 2022
Desired Outcome
Awareness
Decision
Escalation Help

## Slide 2: Phase 5 Vehicles Timeline
CDX707
CX788
UPV1
03/05
CDX747
TT
02/01
FEC
01/13
PEC
12/02
PP
04/06
OK2B
07/25
MP1
06/07
DCV
07/11
FDJ
02/11
UPV0
07/02
UPV1
09/13
UPV2
12/06
PA
01/12
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
2021 | 2022 | 2023 | 2024
MP2
07/05
U6XX MCA updated 11/07
TT
FEC
PEC
PP
09/18
OKTB
01/23
MP1
12/06
DCV
UPV0
03/30
UPV1
06/25
UPV2
10/25
PA
10/17
12/22
HB
12/07
06/13
U611N
U625C/U611C
Chicago
04/24
U6XX C
05/22
U6XX C
02/28
U6XX CAF 4
07/05
UPV2
07/30
PEC
07/19
PA
08/18
FDJ
09/10
TT
09/07
PP
11/23
MP1
02/01
DCV
02/02
01/28
MP2
03/01
FEC
08/29
OKTB
03/28
OK2B
07/15
MP2
06/16
MP1
02/19
PP
12/03
FEC
07/29
TT
09/10
PEC
07/08
UPV1
07/13
UPV2
06/30
FDJ
09/18
DCV
03/18
U718
FEC
07/25
PEC
05/16
OK2B
05/06
DCV
12/05
FDJ
06/07
UPV0
08/10
UPV1
12/14
UPV2
03/29
PA
05/25
MP2
04/01
TT
09/18
PP
12/11
MP1
03/04
P702 MCA
TT
PP
08/28
OKTB
01/15
MP1
11/27
DCV
FDJ
UPV0
06/16
UPV1
09/15
UPV2
12/22
PA
01/02
03/18
09/19
06/05
FEC
PEC
01/06
02/03
MP2
01/02
PA
10/27
CX771 Draft VPP
TT
PP
08/02
OKTB
TBD
MP1
09/27
DCV
FDJ
UPV0
12/03
UPV1
02/05
UPV2
05/06
PA
06/01
07/08
12/07
06/07
FEC
PEC
03/24
04/21
MP2
TBD
UPV2-OKTB Postpone 33wks Proposal
DCV
08/01
U625N
Chicago
FDJ
DCV
08/31 Retrofit
HB
09/30
TT
02/01
PP
04/19
MP1
06/21
MP2
07/19
OKTB
08/08
GAS
FHEV
FDJ
05/11
PEC
12/07
FEC
01/03

## Slide 3: Phase 5 Vehicles Timeline
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5
2022 | 2023 | 2024 | 2025
CDX748
LR/TT
LS/PP
06/05
OKTB
10/30 NCM Battery
MP1
08/28
DCV
FDJ
UPV0
06/10
UPV1
09/09
UPV2
12/16
PA
01/25
03/03
09/18
03/13
FEC
PEC
01/19
03/01
MP2
09/25
PSC
01/12
OKTB
01/29 LFP Battery

## Slide 4: Phase 5 Vehicles Info
SYNC+ 3.0 Phase5 Scope |  |  |  |  |  |  |  |  |  |  |  | 
Program | PMT5 | IVI SW PM | Nameplate | Manufacture | J1 | OKTB | EE Architecture | Centerstack Size | Cluster |  | TCU | ECG
CDX707 | Yang Youfei, Xu Fiona | Zhou Jiajia (XCL) | Nautilus | CAF | GAS: 3/28/2023 2/1/2023 FHEV: 6/21/2023 | GAS: 3/28/2023 FHEV: 8/8/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
CX788 | Vijay | Yang Hanhan | Ford | CAF | 4/26/2023 | 6/21/2023 | FNV2 | 15.3 | 9.2, AR HUD | Landscape | Boundle5 | ECG2
CDX747 | Yang Frank Leon Xuan | Zhang Ying | Lincoln | BU | 6/12/2023 | 11/6/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
U611 MCA | Yang Frank Julian Wang | Zhang Ying Xia Xiaojin | Aviator | CAF | 12/6/2023 | 1/23/2024 | FNV3 | 27 | 12.3，Standalone HUD | Landscape | Boundle6 | ECG2
U625MCA | Yang Frank Julian Wang | Zhang Ying Xia Xiaojin | Explorer | CAF | 12/6/2023 | 1/23/2024 | FNV3 | 27 | 12.3，Standalone HUD | Landscape | Boundle6 | ECG2
U718 | Yang Frank Leon Xuan | Zhang Ying | Navigator | BU | 3/04/2024 | 05/06/2024 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
P702 MCA | Yang Frank Chen Fengmin | Yang Hanhan | F-150 Raptor | BU | 11/27/2023 | 01/15/2024 | FNV3 | 12.0 | 12.4 | Landscape | Boundle6 | ECG2
CX771 | Zhang Wen | Yang Hanhan | Mustang SUV |  |  |  | FNV2 |  |  |  |  | 
CDX748 | He Sylvia/Xiao Yao/Li Rich | Zhang Ying | Lincoln | CAF | Diff. Battery: NCM: 8/28/2024 LFP:11/27/2024 | NCM: 10/30/2024 LFP:1/29/2025 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) | Landscape | Boundle6 | ECG2

## Slide 5: CDX707 SW Release Plan HQX1.2.1@12/27
2021 | 2022 | 2023
CDX707
UPV1
03/05
3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV2
07/30
PEC
07/19
PA
08/18
FDJ
09/10
TT
09/07
PP
11/23
MP1
02/01
DCV
02/02
01/28
MP2
03/01
FEC
08/29
OKTB
03/28
HB
09/30
TT
02/01
PP
04/19
MP1
06/21
MP2
07/19
OKTB
08/08
GAS
FHEV
FDJ
05/11
AHU HW
A3 16G DDR
11/21
B0
12/17
DV1
12/17-03/15
EMC
12/17--02/02
B1
04/19
Mini DV
04/26-06/01
C
07/06
DV2+PV
07/09-08/15
Audio(24 Channel Amplifier): 05/E Amplifier ready,06/10 retrofit with the latest SW.
DCV
08/31 Retrofit
SW Release for REC. CAF/FO
DCV0
10/20
11/03
DCV1
12/15
12/29
DCV2
01/12
01/26
DCV3
02/16
03/02
R01
04/20
05/04
R04
05/18
06/01
R05
06/15
06/29
R05.1
07/13
07/25
R00
03/23
04/06
R06
09/07
09/21
R07
11/20
12/04
R08 for OKTB
01/15
01/24
R09 for OTA
04/14
04/28 TBD
HQX1.0
SW INTEG.
HQX1.2.1
DCV0
09/15
DCV0.1
10/20
DCV1
11/17
DCV2
12/15
DCV3
01/12
R00
02/23
R01
03/23
R04
04/20
R05
05/18
R05.1
06/15
R06
08/10
R07
10/19
R08 for OKTB
12/15
Qualcomm
Patch 1
01/31
FC
03/31
Patch 2
04/30
CS
08/31
ZBB
11/30
4 vendors Coding switch
02/14-06/29
Patch1:Carry over HQX1.0 Feature base on HQX1.2.1 Engineering line
FC(Feature Complete): Initial Release
Patch2:Fix Critical Issue support CDX707 FEC
CS(Commercial Sample):
Support new feature/Performance/stability improvements/Boot KPIs (100%)/CTS/VTS/STS - Coverage (100%)
Post CS/ZBB: Bug Fixes, Security Fixes
PEC
12/07
FEC
01/03
CP1
CP2
CP3
CP4
DCV1.1
01/05 CP

## Slide 6: CDX707 DCR Control Process Proposal
2021 | 2022 | 2023
CDX707
UPV1
03/05
3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV2
07/30
PEC
07/19
PA
08/18
FDJ
09/10
TT
09/07
PP
11/23
MP1
02/01
DCV
02/02
01/28
MP2
03/01
FEC
08/29
OKTB
03/28
HB
09/30
TT
02/01
PP
04/19
MP1
06/21
MP2
07/19
OKTB
08/08
GAS
FHEV
FDJ
05/11
Audio(24 Channel Amplifier): 05/E Amplifier ready,06/10 retrofit with the latest SW.
DCV
08/31 Retrofit
SW Release for REC. CAF/FO
DCV0
10/20
11/03
DCV1
12/15
12/29
DCV2
01/12
01/26
DCV3
02/16
03/02
R01
04/20
05/04
R04
05/18
06/01
R05
06/15
06/29
R05.1
07/13
07/25
R00
03/23
04/06
R06
09/07
09/21
R07
11/20
12/04
R08 for OKTB
01/15
01/24
Patch1:Carry over HQX1.0 Feature base on HQX1.2.1 Engineering line
FC(Feature Complete): Initial Release
Patch2:Fix Critical Issue support CDX707 FEC
CS(Commercial Sample):
Support new feature/Performance/stability improvements/Boot KPIs (100%)/CTS/VTS/STS - Coverage (100%)
Post CS/ZBB: Bug Fixes, Security Fixes
PEC
12/07
FEC
01/03
CP1
CP2
CP3
CP4
阶段1[->DCV3]：主体功能交付完毕，不允许大的架构性变化
阶段2[R00->R06]：体验优化，接受部分Agile feature 合入（影响系统性能的，务必于R04之前完成支持PEC sign off, 其他due date为R05.1 for TT build）
阶段3[R07->R08]：AIMS issue bug fix, 非必要不进行任何新功能合入.

## Slide 7: CDX707 SW Release Plan @09/23
CDX707 VPP
Display(23.6+23.6,11.1 touch)
Vendor Integration
SW Release for CAF/FO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
03/05
UPV2
07/30
SW Release for REC
PEC1
06/13
PA
08/18
FDJ
08/20
09/10
TT
08/30
PP
10/24
MP1
02/01
DCV
02/02
01/28
ITV Test
A0 PCBA
01/25
CDC AHU HW
A1
06/15
B0
12/13
B1 DV2
05/10
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
DCV Alpha4
06/23
DCV Beta
07/18
08/01
DCV Beta1
09/03
DCV0
10/20
DCV0.1
11/17
DCV1
12/15
DCV2
01/12
DCV3
02/16
R00
03/23
R01
04/20
R04
05/18
R05
06/15
R05.1
07/13
R05.2
08/10
R06
09/07
R06.1
10/19
R07
11/20
R08 for OKTB
01/15
DCV Alpha3
04/28
DCV Alpha4
05/26
DCV Beta
06/20
07/02
DCV Beta1
08/01
DCV0
09/15
DCV0.1
10/20
DCV1
11/17
DCV2
12/15
DCV3
01/12
R00
02/23
R01
03/23
R04
04/20
R05
05/18
R05.1
06/15
R05.2
07/13
R06
08/10
R06.1
09/07
R07
10/19
R08 for OKTB
12/15
Group A
03/15 sign-off UE
05/05 Stagger UI
05/19 sign-off UI
Group B
04/30 UE
06/02 stagger UI
06/16 sign-off UI
Group C 05/21 UE
08/17 UI
Group D
06/15 UE
09/15 UI
TBD
2021 | 2022 | 2023
09/13-10/15
12/17-03/15
05/15-06/15
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
MP2
03/01
FEC1
07/25
OKTB
03/28
UX Release
FNVx Release
DCV0
11/03
DCV1
12/29
DCV2
01/26
DCV3
03/09
R01
05/04
R04
06/01
R05
06/29
R05.1
07/25
R00
04/06
R06
09/21
R07
12/04
R08 for OKTB
01/24
SOA Gateway
Wireless Interface Router
IVI Provisioning
Bezel Diagnostics(SOA related)
Diagnostic_ Analytic
CCS –Authorization
CCS – UFM/PTE
IP Pass Through Client
MMOTA –SYNC+
Purchase process
03/23-07/30
Net/Diagnostic full function 12/15 for DCV2
ITV P2 complete 07/18 07/11
R09 for OTA
04/28 TBD
PEC2
07/19
FEC2
08/29
Net/Diag develop~4.5months
Bug fix ~1.5m
ITV P1 Release for R04
04/15
Net/Diag Bug fix
For R00
01/30
Report Review 07/25 07/18
Vendor P1 test ~2.5 m
P2 Log Prepare ~2m
We are here
A2
09-03
EMC
12/17--02/02
OKTB
FHEV 08/08
HQX1.2.1 switch
2022/12-2022/05
Eng version internal release.

## Slide 8: CX788 SYNC+/AR-HUD/Display Plan @08/10 (Based on 11/15 Group A Delivery UI)
Display(15.3)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
CDC AHU HW
CX788 VPP
UPV1
08/16
PEC
10/14
FDJ
01/07
TT
12/21
PP
03/01
DCV
06/13
FEC
11/23
OKTB
06/27
UPV0
05/31
AR-HUD
05/31
MP2
PA
12/08
UPV2
11/08
Cluster(9.0) HW Sourcing TBD
Group A UI
12/12
IVI+Cluster UI Plan
Group C UI
02/13
Group D
UI
03/25
Group B UI
01/09
MP1
04/29
Unsigned Group A UI Delivery
11/15
SW Release for CAF/FO
Vendor Integration
SW Release for REC
Spring Festival
National Day
TFT T0 Sample
10/30
TFT T1 Sample
12/30
Tier 1 T0 Sample
3/30
Tier 1 T1 sample for DCV 5/20
Pre DV-1
Critical DV
12/06
3/30~5/20
Ass tooling
T0 Sample
01/30
T1 Sample
6/1
EMC + DV
6/15-9/15
Pre-DV
2/15~5/15
We are here
DCV Alpha
01/20
R00
10/31
DCV Beta
03/19
R04
12/31
R05
02/07
R06
04/07
DCV0
06/23
DCV1
07/24 (=>(07/17)
R07
05/07
DCV0
06/10
DCV1
07/10
R04
12/17
R06
03/24
R07
04/24
R08
06/24
DCV Beta
02/12
DCV0
05/10
DCV1
06/10
R00
09/10
R04
11/17
R05
12/17
R06
02/24
R07
03/24
Spring Festival
DCV Beta
03/12
R08
05/24
R05
01/17
R08
07/07
B0
06/24
C
02/02
A0 11/15
Pre-DV
04/03-05/03
DV
06/27-08/16
RE-DV
12/05-01/10
PV
02/09-04/05
04/08-04/22
PPAP
EMC
06/27-07/28
EMC
12/05-
01/05
A1 Sample
03/26
HW Improve
PCB fabricate
05/04-06/22
HW Improve
PCB fabricate
08/17-11/21
B1
11/30
R00
10/17
Group A UE
08/15
Group B UE
09/25
Overall Enablers:
HMI Delivery(Group-A/B/C/D) Can’t Delay Any Further. MFL w/ FO/Spec release COB 08/19.
Program Offers IVI S/W Team 5 DCV Vehicles For System Level Debug. (3 for suppliers, 2 for IVI Software Team), TT Vehicle *3 Is Also Required.
2 test NSPS engineers for CDC till FEC2 declared, 1 Display D&R, 1 Cluster D&R onboard on early of Sept.
Each Sign-off Team Has Qualified DV vehicles With Great DV Vehicle Usage Schedules => Need Dedicated Person To Manage Closely.
FDJ
02/11
FEC2
R00
1/13
UPV0
07/02
DCV
07/11
PEC
11/11
PEC2
R00
12/02
FEC
12/23
CX788 Proposed latest VPP
UPV1
09/13
PA
UPV2
TT
2/01
OKTB
7/25
PP
04/06
MP1
06/07
1
2
4
3
Compress actions IVI team has taken/ considered:
[4wks compress, Done] Use Group A UI Unsigned version to kick off coding(12/12 to 11/15) Utilize Ckp. to track risk assessment.
[2wks compress, Done] Compress the Group A coding time from 10 wks to ~8wks.
[2wks further compress, Done] Compress further 2wks Development &Validation time between DCV Alpha and DCV Beta (origin 8wks to 6wks)
[1wks, further compress Pull ahead B0 Sample Build, Done] With above 1/2/3 compress, plus take further risks to pull ahead B0 sample build W/O REC validation by 14 days(6/10 to 06/23).
[1wks, Studying]Compress REC DCV1 validation time window from 2 wks to 1 wks by further OT shift and adding NSPS
[2wks, compress studying] R04 engineering version to support FEC2 sign off ilo. Publishing ver.(Enablers: OT and adding NSPS)
5
6
TFT T1 Sample
12/30
Tier 1 T0 Sample
3/30
Tier 1 T1 sample for DCV 6/13
Critical DV + EMC
3/30~6/13
Ass tooling
01/12
DCV Beta1
03/30
DCV Beta1
04/30
DCV2
07/10
DCV3
08/10
DCV2
08/10
DCV3
09/10
R01
10/17
R01
11/17
R01
11/31
Cluster coding based on 13.2
SW coding based on virtual display

## Slide 9: U611 MCA SW Release Plan Proposal @1213
Display(27 TOUCH)
SW Release for REC
DCV Beta
04/17
DCV4
12/24
R00
02/24
R05
05/03
R06
07/18
R07 10/08
DCV0
06/15
DCV1
07/15
CDC AHU HW
B0 DV1
04/05
A1 Pre-DV
03/01
B1 DV
08/15
EMC 2
DCV Alpha
03/08
DCV Beta
04/08
DCV3
08/08
R00
02/10
Group A UI
Delivery 11/09
A
12/09
2021 | 2022 | 2023 | 2024
09/15-10/20
National Day
National Day
Spring Festival
Spring Festival
U611MCA
OK2B
1/23
MP1
12/06
PP
09/18
LS:09/04
FEC
05/22
U6XX C
TT
07/03
LR:06/12
PEC
04/24
U6XX C
UPV0
03/30
UPV1
06/25
UPV2
10/25
FDJ
12/7
DCV
06/13
HB
2/28
PDL Release
09/01
FIP 1EC 09/09
SW Release for CAF/FO
Vendor Integration
U611 27’ UX Release
DCV Beta
03/08
R05
04/18
R06
07/03
R07
09/15
Reserve R08 12/30
R08
12/15
R05
03/18
R06
06/03
R07
08/15
R08
11/15
A0 11/30,12/25
DCV Beta1
04/08
DCV Alpha
01/25
DCV0
05/08
DCV1
06/08
1
DCV2
07/08
DCV1
07/08
DCV0
06/08
R00
01/01
DCV4
11/10
DCV4
12/10
DCV2
08/08
DCV3
09/08
DCV Beta1
05/08
All the program distributed features(BOF) should be included in IVI Group A.---HMI Aligned.
No SYNC+ sample needed for FDJ Hil test, PMT5/Program study the opportunity for FDJ BB & DCV EBB.---High Risk/impossible because of no HW&SW&HMI readiness. –Program/PMT5
Team Proposal: Use DCV Beta support AHU build for DCV MRD(04/M Ship, 05/15 MRD), Update SW to DCV0/DCV1 by USB.
Need HW provide 27’’ display*30(TBC) before 01/10. AHU*30(TBC) before 11/30.---Xuan Leon, Zhang Bingqing
Cluster：Initialized Normal Theme(Group A-B-C-D) already released which can support DCV Beta maturity(40%), Study the opportunity to use Capable theme support DCV0(60%) ,DCV1(80%)integration. Latest change under study(Dash background, etc.) with DCR, the new themes target PEC milestone(TBC).
EMC 1
06/13-07/13
A0 02/10
2PCS
B0 7/10
U611 12.3’ UX Release(TBC)
2 months
SW coding based on virtual display: 12/2/2021-3/11/2022
Light-up
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2
Group A+B+C+D UI
Initialized released.
E
11/21
B
12/15
DCV YB MRD
05/13
DCV EBB MRD
04/01???
R04
02/10
R04
03/10
R00
03/24
2
3
Compress actions IVI team has taken/ considered:
<4 weeks compress, done>Using Group A delivery version starting Coding with risk of re-work. Control the change content within 20%.
<4 weeks compress, done> considering many features C/O CDX707, drop DCV Beta2 version, compress 4 weeks during DCV Beta to DCV0
<2 weeks compress, done> Compress REC DCV0,DCV1 validation time window from 2 wks to 1 wks by further OT.
4
C/D
12/30
E
1/24
Multi Theme
02/28
Normal/Sport/ZEN C/O CDX764
New added Capable pending release
HQX1.2.1
Theme Change Plan TBC (Helen, Alisa)
Total DCV vehicle*4 arrive in REC 08/20
Normal/Sport/ZEN updated based on CDX764
Slippery theme updated on Normal(0.5)
New added Capable target FDJ
Capable
12/07
DV
09/15-12/17
03/11
Notes: 有功能增加；
音频架构有变化。

## Slide 10: U625 MCA SW Release Plan Proposal @1213
Display(27 TOUCH)
SW Release for REC
DCV Beta
04/17
DCV4
12/24
R00
02/24
R05
05/03
R06
07/18
R07 10/08
DCV0
06/15
DCV1
07/15
CDC AHU HW
DCV Alpha
03/08
DCV Beta
04/08
DCV3
08/08
R00
02/10
2021 | 2022 | 2023 | 2024
National Day
National Day
Spring Festival
Spring Festival
U611MCA
OK2B
1/23
MP1
12/06
PP
09/18
LS:09/04
FEC
05/22
U6XX C
TT
07/03
LR:06/12
PEC
04/24
U6XX C
UPV0
03/30
UPV1
06/25
UPV2
10/25
FDJ
12/7
DCV
06/13
HB
2/28
PDL Release
09/01
FIP 1EC 09/09
SW Release for CAF/FO
Vendor Integration
U625 27’ UX Release
DCV Beta
03/08
R05
04/18
R06
07/03
R07
09/15
Reserve R08 12/30
R08
12/15
R05
03/18
R06
06/03
R07
08/15
R08
11/15
DCV Beta1
04/08
DCV Alpha
01/25
DCV0
05/08
DCV1
06/08
DCV2
07/08
DCV1
07/08
DCV0
06/08
R00
01/01
DCV4
11/10
DCV4
12/10
DCV2
08/08
DCV3
09/08
DCV Beta1
05/08
U625 12.3’ UX Release (TBC)
2 months
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2
Group A+B UI
Sign off 09/19
C
10/17
D
10/30
E
11/21
DCV YB MRD
05/13
DCV EBB MRD
04/01
R04
02/10
R04
03/10
R00
03/24
Compress actions IVI team has taken/ considered:
<4 weeks compress, done>Using Group A delivery version starting Coding with risk of re-work. Control the change content within 20%.
<4 weeks compress, done> considering many features C/O CDX707, drop DCV Beta2 version, compress 4 weeks during DCV Beta to DCV0
<2 weeks compress, done> Compress REC DCV0,DCV1 validation time window from 2 wks to 1 wks by further OT.
Following standard GPDS3.3 delivery process, DCV Beta S/W is for FDJ, DCV1 S/W is for DCV build. UE/UI Delivery by FDJ is already Very Late to Support FDJ & DCV Global Feature Maturity Requirement.
No SYNC+ sample needed for FDJ Hil test, PMT5/Program study the opportunity for FDJ BB & DCV EBB.---High Risk/impossible because of no HW&SW&HMI readiness. –Program/PMT5
Team Proposal: Use DCV Beta support AHU build for DCV MRD(04/M Ship, 05/15 MRD), Update SW to DCV0/DCV1 by USB.
Need HW provide 27’’ display*30(TBC) before 01/10. AHU*30(TBC) before 11/30.---Xuan Leon, Zhang Bingqing
1
2
3
4
Group A UI
Delivery 12/07
A
12/25
1
B
01/10
C/D
01/24
2* Multi Theme
03/20
E
02/10
Smart surface change from 1.5 to 2.0(compared with 706).
HQX1.2.1
B0 DV1
04/05
A1 Pre-DV
03/01
B1 DV
08/15
A0 11/30,12/25
EMC 1
6/13-7/13
A0 01/10
2PCS
B0 7/10
Light-up
EMC 2
DV
09/15-10/20
09/15-12/17
SW coding based on virtual display: 12/1/2021-3/4/2022
03/04
Notes: 有功能增加；
音频架构有变化。

## Slide 11: CDX747 SW Draft Release Plan @1110-postoned VPP 33 wks
Vendor Integration
Display(23.6+23.6, 11.1 touch)
GPDS SW Version for Build
4 | 5 | 6 | 7 | … | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
DCV Beta
08/14
R00
4/29
R04
5/29
R05
6/29
R06
10/20
R07
1/4
DCV0
12/7
DCV1
1/7
CDC AHU HW
B DV1
07/05
A1 Sample
11/15
C
09/30
Pre-DV
DV1
DV2
2021 | 2022 | 2023 | 2024
01/03-02/08
07/8-8/26
9/30-11/11
CDX747
UPV0
04/06
UPV1
07/13
HW Request Frozen
7/13
Eng version released for REC, focus and lite test.
Pro version support GPDS key node, full test.
Group A/B UI 2/19
IVI UI Plan
SW Release for REC
DCV0
11/24
DCV1
12/24
R00
4/15
R04
5/15
R06
9/31
R07
12/20
R08
03/15
DCV Beta1
8/31
R05
6/15
DCV Beta
6/30
DCV0
10/24
DCV1
11/24
DCV3
2/24
DCV3
1/24
R00
3/15
R04
4/15
R05
5/15
R06
8/31
R07
11/20
R08
02/15
R09
04/15
R09
03/15
DCV Beta1
07/31
R07.1
1/20
R07.1
12/20
DCV2
1/24
DCV2
12/24
R08 03/29
R09 preserved for OKTB 04/29
DCV Alpha
5/30
FNVx Release
SOA Gateway
Wireless Interface Router
IVI Provisioning
Bezel Diagnostics(SOA related)
Diagnostic_ Analytic
CCS –Authorization
CCS – UFM/PTE
IP Pass Through Client
MMOTA –SYNC+
DCV Alpha
4/30
DCV Sample with CS3.0 11/30
Group C UI 3/19
UPV2
6/30
FDJ
9/18
DCV
3/18
PEC
7/8
FEC
7/29
TT
9/10
MP1
2/19
MP2
6/16
OK2B
7/13
DCV Beta
7/31
DCV Beta2
08/31
DCV Beta2
9/30
Spring Festival
PP
12/3
HQX1.2.1
Apply FNV4, waiting official VPP, MP1 in 2024.8
Notes: 有功能增加；
音频架构有变化。

## Slide 12: P702 MCA SW Release Plan @12/07
Display(12.4+12TOUCH)
P702MCA
OK2B
5/13
MP1
1/29
PP
10/23
04/03
FEC
TT
07/31
PEC
03/06
UPV0
06/17
UPV1
09/15
UPV2
03/08
FDJ
5/09
DCV
11/09
PA
03/09
MP2
02/26
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
2021 | 2022 | 2023 | 2024
CDC AHU HW
A1 Sample
22/6/25
IVI+Cluster UI Plan
SW Release for CAF/FO
Vendor Integration
SW Release for REC
DCV Beta
05/27
DCV0
08/14
DCV1
09/14
R00
1/20
R04
2/25
DCV Beta
05/20
DCV0
07/30
DCV1
08/30
DCV2
10/10
DCV3
11/30
R04
2/10
R00
1/05
DCV Beta
04/20
DCV Alpha
3/20
DCV0
06/30
DCV1
07/30
R04
1/10
R00
12/05
DCV2
09/10
DCV3
10/30
DCV Beta1
05/30
TFT sample
22/1/15
EESE SW Timing Opportunities And Enablers:
All the FDL/Program distributed features should be included in HMI Group A.
Group A UI unsign off version should be released on 12/30 in order to catch up with timing.
AHU and 12 inch Display should be ready before 1/15(TBC).
Group A UI
1/30
Group B UI
3/15
Group C UI
04/15
Group D UI
05/30
DV/EMC
7/20-8/20
Illumination
Touch Cali
1/16-2/28
DCV Beta1
06/30
DCV EBB 08/19
Group A unsigned off UI
12/30
DCV T&C 09/30
1 month Gap for FDJ
R05
5/30
R05
5/15
R05
04/15
R06
8/30
R07
11/30
R08
12/30
R09
3/20
R06
8/15
R07
11/15
R08
12/15
R09
3/05
R06
07/15
R07
10/15
R08
11/15
R09
02/05
BOF related UI
Notes: 有功能增加；
音频架构有变化。

## Slide 13: U718 SW Release Plan @1227
Project VPP
GPDS SW Version for MRD
CDC AHU Hardware
R00
03/29
R04
04/29
R05
07/18
R06
9/30
R07
12/31
R08
Reserved
DCV Beta
7/5
DCV0
9/5
A1 Sample
TBD
SW Release for REC
Vendor Integration
PS/PSC
03/16
UPV0
08/10
OKTB
5/6
FIP 1rst version
12/2
PDL 1rst version 11/24
DCV Alpha
4/15
DCV Alpha
5/15
DCV Beta
5/21
DCV Beta
6/21
DCV0
7/21
DCV1
8/21
DCV1
9/21
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5
R00
3/15
R00
2/15
DCV2
10/10
DCV3
12/10
DCV2
11/10
DCV3
1/10
R04
03/15
R04
4/15
R05
07/03
R05
06/03
R06
09/16
R07
12/16
R06
8/16
DCV0
8/21
2021 | 2022 | 2023 | 2024
Display(23.6+23.6, 11.1 touch)
A1 Sample
TBD
EESE SW Timing Risk & Enabler
Based on HMI time there is 1 months gap for FDJ;
3/21 Group A sign off version need contain all BOF features that FNA team focus on.
R08
11/16
UPV1
12/14
PA
5/25
DCV
12/5
PEC
5/16
FEC
7/25
TT
9/18
PP
12/11
MP1
3/4
FDJ
6/7
UX Release
Group A UI
3/21
Group B UI
5/27
Group C
6/21
DCV Beta1
6/21
DCV1
10/10
03/29
UPV2
BoF 1rst cascade end 11/24
1 months
RFQ 1rst version
12/10
DCV EBB
9/23
DCV YB
10/14
Surrogate UI
1/30
DCV Beta1
7/21
Compress actions IVI team has taken/ considered:
<4 weeks compress, done> Using surrogate UI (CDX707/CDX747) develop DCV alpha version
<2 weeks compress, done> Considering Group A UI re-using possibility saving two weeks during DCV Bate build

## Slide 14: U718 SW Release Plan @1208
Project VPP
GPDS SW Version for MRD
CDC AHU Hardware
R00
03/29
R04
04/29
R05
07/18
R06
9/30
R07
12/31
R08
Reserved
DCV Beta
9/29
DCV0
11/29
A1 Sample
TBD
SW Release for REC
Vendor Integration
PS/PSC
03/16
UPV0
08/10
OKTB
5/6
FIP 1rst version
12/2
PDL 1rst version 11/24
DCV Alpha
7/15
DCV Alpha
8/15
DCV Beta
8/15
DCV Beta
9/15
DCV0
10/15
DCV1
11/15
DCV1
12/15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5
R00
3/15
R00
2/15
DCV2
12/15
DCV3
1/15
DCV2
1/15
DCV3
2/15
R04
03/15
R04
4/15
R05
07/03
R05
06/03
R06
09/16
R07
12/16
R06
8/16
DCV0
11/15
2021 | 2022 | 2023 | 2024
Display(23.6+23.6, 11.1 touch)
A1 Sample
TBD
EESE SW Timing Risk:
Based on HMI time there is 3.5 months gap for FDJ, 2 month gap for DCV EBB, 2.5 month gap for DCV YB.
R08
11/16
UPV1
12/14
PA
5/25
DCV
12/5
PEC
5/16
FEC
7/25
TT
9/18
PP
12/11
MP1
3/4
FDJ
6/7
UX Release
Group A UI
4/30
Group B UI
5/28
Group C
6/25
New Theme plan
10/31
DCV Beta1
9/15
DCV1
12/29
03/29
UPV2
BoF 1rst cascade end 11/24
3.5 months
2.5 months
RFQ 1rst version
12/10
DCV EBB
9/23
DCV YB
10/14
2 months

## Slide 15: CDX748 SW Release Plan @1025
Project VPP
GPDS SW Version for MRD
UX Release
Group A UI
9/30
Group B UI
11.21
Group C UI
12.30
Group D UI
1.31
DCV Beta
3/7
DCV1
7/14
SW Release for REC
Vendor Integration
PSC
01/12
UPV0
6/10
UPV1
9/9
2022 | 2023 | 2024 | 2025
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5
PA
1/25
FDJ
3/3
DCV
9/18
PEC
1/19
FEC
3/1
LR/TT
03/13
LS/PP
06/05
MP1
08/28
MP2
09/25
OKTB
10/30 NCM Battery
OKTB
01/29 LFP Battery
UPV2
12/16
CDC AHU Hardware
Display(23.6+23.6, 11.1 touch)
DCV2
6/30
DCV Alpha
1/15
DCV Beta
1/15
DCV Beta
2/22
DCV0
530
DCV0
430
DCV1
6/30
DCV1
5/30
DCV Alpha
12/15
DCV3
08/30
DCV2
08/15
DCV3
09/30
DCV0
6/14
R00
12/1
R00
10/15
R00
11/15
R04
01/15
R04
11/30
R04
12/30
R05
02/15
R05
01/01
R06
04/01
R06
4/15
R06
2/28
R05
02/01
R07
05/13
R07
5/28
R07
04/13
R08
07/11
R08
07/25
R08
06/11
A1 Sample
TBD
A1 Sample
TBD
Apply FNV4, following CDX747, VPP keep updating

## Slide 16: Phase5 SYNC+ 3.0 Timeline Draft To Be Reviewed
Project VPP
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
UPV2
Hardware
UX Release
PEC
PA
FDJ
TT
PP
MP1
DCV
DCV Beta
R00
R04
R05
R06
R07
Key Checkpoint
DCV0
Group A UI
For Pre DV/FDJ
Group B UI
For Critical DV/DCV
Group C UI
For DCV
Group D UI
For DCV/PEC
MP2
FEC
OKTB
UPV0
PS/PSC
1.Bill of feature Initialized(MFL)
2.Feature Owner confirmation
3. Basic Level spec are available
4.1EC
1. Supplier Sourced (SOBD)
======
1.Bill of feature(MFL) Finalized
2.Platform feature spec complete and cascaded
3.Function Safety Concept updated and completed
4.Cybersecurity Requirements Identified
5.UX(UEUI) alignment confirmed
6.SW environment and baseline Design
7.pre-2EC
1. Platform feature spec finalization and sign off
2.Simulate feature integration of interfaces, states and responses to requested behavior
3. Early test of new and C/O features with physical parts
4.2EC
1.DCV Beta verified supporting Pre-DV/EMC, critical function including Climate/Camera/Radio/Music/Video/Navigation/Speed meter/Driving Info etc.
2.Feature Software early system-level integration test start at <FDJ> breadboard
3. UX doc sign off by HMI/Studio team
1.DCV1 verified supporting DV/EMC/DCV MRD with full function code completed.
2.Feature Software early system-level integration test complete by <DCV> breadboard, verify feature functionality and performance requirements.
1All design verification testing completed by <PEC>
2.Feature Software system-level integration test complete and sign off by feature owner and HMI team
3.R00 release for <PEC> without critical blocker issue,
4.Diagnostics Part2 DV(iTV) test report shows 100% passed
1. Software OTA window preserved post Job1 and before OKTB.
R08
1. Agile feature full function Integration without critical bug.
Group A Features Coding based on UI
DCV Alpha
DCV Beta
test
A1
Pre DV
Debug
B0
Critical DV
DCV Critical Path * 45 weeks
DCV1
17 weeks(4 months)
6 weeks
DCV
DCV MRD
4 weeks
5 weeks
>=6 weeks
DCV0
test
Eng Version
>=6 weeks
9 weeks
9 weeks
9 weeks
A0 PCBA
A1 Sample
B0 Sample
B1 Sample
Features and HMI Design
Display light up
Platform Arch design
PIPELINE Design
Initial release for Pre DV
DCV Beta
30% Coding
Release Fundamental features for DCV vehicle testing
DCV1
60% Coding
Zero IG defects supporting PEC sign off
R00
95% Coding(Not including Agile features)
Delivery of all features with zero G issues
R05 100% Coding
AIMS Issue solve / Bug fix
R06 100% Coding
AIMS Issue solve / Bug fix
R07 100% Coding
17 weeks(4months)
17 weeks(4months)
13 weeks(3months)
8weeks(2months)
9 weeks(2months)
8weeks(2months)
10weeks(2.5months)
Hotfix for OKTB
Preserved
5 weeks
>=14 weeks
>=32 weeks
14W
13W
14W
10W
26W

## Slide 17: SYNC+ 3.0 DCV/PEC/J1 Critical Path
China Accelerated SW Plan ---DCV Critical Path
FDJ
DCV
Group A UI Release
MRD
DCV Beta 30%
DCV0 50%
DCV1 60%
45 weeks
Group A Features Coding based on UI
DCV Alpha
DCV Beta
Test
A Sample
Pre DV
Debug
B Sample
Critical DV
China Accelerated SW Plan ---PEC/J1 Critical Path
R00
95%
R04
R05
100%
R06
R07
R08
DCV1 60%
DCV
DCV MRD
4 weeks
5 weeks
9 weeks
9 weeks
Zero IG defects supporting PEC sign off
R00 (4*SW iterated versions )
95% Coding(Not including Agile features)
Delivery of all features with zero G issues
R05 100% Coding for TT MRD
AIMS Issue solve / Bug fix
R06 100% Coding for PP MRD
17 weeks(4months)
13 weeks(3months)
8weeks(2months)
DCV
6 weeks
PEC
FEC
6 weeks
TT
PP
AIMS Issue solve / Bug fix
R07 100% Coding for J1
8 weeks(2months)
Hotfix for OKTB
R08 100% Coding
Preserved
9 weeks
J1
Initial release for Pre DV
DCV Beta
30% Coding
Release Fundamental features for DCV vehicle testing
DCV1
60% Coding
17 weeks(4months)
8weeks(2months)
Features and HMI Design
Display light up
Platform Arch design
PIPELINE Design
10weeks(2.5months)
OKTB

## Slide 18: CDX707/788 SW Release Requirement for MRD
CX788 |  |  |  | 
R-Event | Software Maturity | Corresponding Milestone | Release Due Date*1) | Build Support
TPB | Fully verified on component level | TPV BB MRD - 1 week | NA | Support TPV BB and TPV T&C MRD
TP3 | Updates Release | TDC - 2weeks | 7/30/2021 | Support TDC
DCV beta | System test on engineering prototype | eBB MRD | 1/7/2022 | Support FDJ
DCV 0 | Fully verified on component level | DCV BB MRD - 4 weeks | 3/21/2022 | Support <DCV BB> MRD and HiL MRD
DCV 1 | Updates Release | T/C MRD - 4 weeks | 5/4/2022 | Support <T/C> MRD
DCV 2 | Updates Release | DCV - 2 weeks | 5/30/2022 | Breadboard update, DCV vehicles update
DCV 3 | Updates Release | DCV+ 4 weeks | 7/11/2022 | Breadboard update, DCV vehicles update
R00 | Feature DV complete. | PEC - 6 weeks | 9/2/2022 | DCV vehicles update for PEC Sign-off
R04 | Feature DV signed off | FEC - 6 weeks | 10/12/2022 | DCV vehicles update for FEC Sign-off
R05 | Fully Validated Release | TT MRD - 3 weeks | 11/24/2022 | Support <TT> MRD
R06 | Fully Validated Release | PP MRD - 4 weeks | 1/26/2023 | Support <PP> MRD
R07 | Fully Validated Release | MP1/J1 MRD - 4 weeks | 4/1/2023 | Support <MP1> MRD
CDX707 |  |  |  | 
R-Event | Software Maturity | Corresponding Milestone | Release Due Date*1) | Build Support
TPB | Fully verified on component level | TPV BB MRD - 1 week | 9/9/2019 | Support TPV BB and TPV T&C MRD
TP3 | Updates Release | TDC - 2weeks | 1/22/2021 | Support TDC
DCV beta | System test on engineering prototype | eBB MRD | 9/25/2021 | Support FDJ
DCV 0 | Fully verified on component level | DCV BB MRD - 4 weeks | 11/10/2021 | Support <DCV BB> MRD and HiL MRD
DCV 1 | Updates Release | T/C MRD - 4 weeks | 12/15/2021 | Support <T/C> MRD
DCV 2 | Updates Release | DCV - 2 weeks | 1/14/2022 | Breadboard update, DCV vehicles update
DCV 3 | Updates Release | DCV+ 4 weeks | 2/25/2022 | Breadboard update, DCV vehicles update
R00 | Feature DV complete. | PEC - 6 weeks | 5/2/2022 | DCV vehicles update for PEC Sign-off
R04 | Feature DV signed off | FEC - 6 weeks | 6/13/2022 | DCV vehicles update for FEC Sign-off
R05 | Fully Validated Release | TT MRD - 4 weeks | 8/2/2022 | Support <TT> MRD
R06 | Fully Validated Release | PP MRD - 4 weeks | 9/26/2022 | Support <PP> MRD
R07 | Fully Validated Release | MP1/J1 MRD - 4 weeks | 1/4/2023 | Support <MP1> MRD

## Slide 19: CDX747/U6 MCA/U718/P702 MCA SW release schedule

## Slide 20: Backup material

## Slide 21: What’s SYNC+ PDL & FIP
Tech
Planning
ECDX
Manager
Review
Marketing
IVI SW PDL
Forum
Feature
Delivery
Leader
EESE IVI
SW & SYS
Feature
Cascade
Feature
Owner
Basic(ECU) Functions
(EESE IVI SW maintain)
Customer Facing
Features
(ECDX PMO maintain)
BOF Cascade Features
(FDL maintain)
IVI SW PDL
(ECDX PMO maintain)
IVI SW FIP
(EESE IVI SW
maintain)
Supplier Workload Ratio
ECU Functional SPEC Information
Feature Integrate Schedule
HMI Design
(UE & UI)
(EESE IVI SW maintain)
A
A
A
B
C
D
B

## Slide 22: GPDS Delivery Health Chart VS U6XX Actual Delivery Status.
GPDS MCA Platform Timing
UPV0
14w
UPV1
13w
UPV2
14w
FDJ
10w
DCV
26w
PSC
GPDS Feature and SW Pocket Card
BOF Finalized
Feature List Aligned to PDL
SOBA
Feature/Function Spec Complete
HMI Health Chart Created
Group A UI
(K4+4W)
33w
Group B UI
(K5+4W)
26w
20w
Group C UI
(K6+4W)
3w-4w
Group D UI(FAA+4W)
Group E Animation (FAA-4W)
DCV Beta For FDJ BB
DCV1 For DCV MRD
China SYNC+ 3.0 Critical Path: New/Modified IVI Platform & New UE/UI
45w
Group A UI latest date
U6XX MCA Actual Story
UPV0
03/30
UPV1
06/25
UPV2
10/25
FDJ
12/7
DCV
06/13
DCV YB MRD
05/13
DCV EBB MRD
04/01
PSC
01/11
2021/05
Confirmed U6XX in Phase5 Scope
BOF Cascade started to involve China Team
2021/07/20
HMI KOTEI SOBA
2021/09/01
SYNC+ PDL Initialized Version released with continuously change
2021/0908 RFQ released to Package1/2/3
11/09
Group A UI
04/17
DCV Beta For FDJ BB
07/15
DCV1 For DCV MRD
China SYNC+ 3.0 Critical Path: New/Modified IVI Platform & New UE/UI
39w(6w has been compressed)
DCV
Proposed 08/16
Program Content/BOF cascade did not follow the GPDS3.3 Process.
HMI delivery plan did not follow the Global/Go Fast Health Chart.
How to guarantee SW maturity meet the Global Software Maturity Progression? ---Deviation needed.
SW Develop Team Compressed the initial over 4months delay to 2 months by OT work
Notes: 有功能增加；
音频架构有变化。

## Slide 23: Software Maturity Progression Request

## Slide 24: SYNC+ 3.0 Critical Path: New/Modified IVI Platform & New UE/UI
China Accelerated SW Plan ---DCV Critical Path
FDJ
DCV
Group A UI Release
MRD
DCV Beta 30%
DCV0
DCV1 60%
45 weeks
Group A Features Coding based on UI
DCV Alpha
DCV Beta
Test
A Sample
Pre DV
Debug
B Sample
Critical DV
China Accelerated SW Plan ---PEC/J1 Critical Path
R00
95%
R04
100%
R05
R06
R07
R08
DCV1 60%
DCV
DCV MRD
4 weeks
5 weeks
9 weeks
(4+5)
9 weeks
R00 (4* iterated versions ) support PEC sign-off
95% Coding
(*Not including Agile features/late added content
** Phase4 takes 5* iterations within 5 months )
Features Code Completed 100% on R04,
R05 Iteration for TT MRD
AIMS Issue solve / Bug fix
R06 Iteration for PP MRD
17 weeks(4months)
13 weeks(3months)
8weeks(2months)
DCV
6 weeks
1st full Validation & Sign-off
PEC
FEC
6 weeks
2nd full Validation/Re-Sign off
TT
PP
AIMS Issue solve / Bug fix
R07 Iteration for J1
8 weeks(2months)
R08 reserved for OKTB when needed
Preserved
9 weeks
J1
Initial release for Pre DV
DCV Beta
30% Coding
Release Fundamental features for DCV vehicle testing
DCV1
60% Coding
16 weeks(4months)
10weeks(2.5months)
Features and HMI Design
Display light up
Platform Arch design
PIPELINE Design
10weeks(2.5months)
OKTB
Platform Fundamental Functionalities(Wifi/Network/BT/Display etc BSP Drivers Coding)
2wks
REC Validation
1st round integration/test
Group B UI Release
Group C UI Release
Group D UI Release
2nd round integration/test
7 weeks
8 weeks
4 weeks
(3 PCB + 1 Assembly & Software)
4 weeks
5 weeks
What we are talking now!

## Slide 25: CDX707 CDC Timing Improvement Plan Details
Study Target - Pull Ahead FEC1 To Support TT TCF Readiness Review
- Engineering study to pull ahead FEC1/PEC1 by 1 week with enablers and higher risks.
- Enablers: Prioritize EE DCV vehicle resource and increase test engineer for PEC1/FEC1.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5
DCV
02/02
2021 | 2022 | 2023
DCV Beta
09/10
DCV0
12/20
（Critical DV)
DCV1
R10 2/22
09/13-11/18
12/24-2/22
2/22 – 5/27
08/02-08/28 09/05
Ver. 20210224
PEC
06/13
FEC
07/11
TT
08/10
11/02
DCV MRD
01/05
MP1
02/01
MP2
03/01
UPV1
UPV2
PA
07/14
FDJ
08/20
VPP
SYNC+ DEVELOPMENT
Vehicle level test/sign off
SYNC+ Development
&Validation
1/19
12/22
05/30
07/25
08/30
6wks
5wks
6wks
5wks
11/09
09/12-12/21
7wks
DCV1
PEC1
FEC1
Critical DV can’t complete by DCV MRD. (7wks gap)
02/22
PP
07/2607/19
09/06
08/29
5/19
(Group-A)
03/05
06/16
3/30
Hero S
5/5
Group A
6/1
Group C
6/16
UPV2
7/1
VPP
Checkpoint
3/15
(Group-A)
SW Release
HMI
(DCV build and vehicle test/sign off)
(DCV reflash)
12/29
06/10-08/01
DCV2
DCV3
R00
06/06
R04
07/25
（Re-DV)
Critical DV
Re-DV
TT Build & PV
PSW
Root cause & Countermeasure
Sample Build
Debug & Build
Pre-DV
SYNC+ CDC DV
……
07/25 07/18
iTV Certification Completed
06/15
iTV P2
05/10
iTV P1
Bug Fix Iteration
07/30
Vector AutoSAR Package Delivery
New Challenges
Chipset Shortage
(CDC A1 Sample 2 wks delay)
COVID-19
(23.6’’ Pana screen 4 wks delay)
Late Sourcing
(FNOS AutoSAR package delivery 3 wks shift)
12/15
FNOS Diag 100%,
FBL dev in parallel.
FNOS Maturity Iteration
TT TCF 09/07
Critical Paths for FEC1 Pull-ahead Layout as:
Re-DV (Initial: 08/02~09/05, New: 08/02~08/28) => Compressed Re-DV duration w/ higher risk, need enablers of more test resource.
FNOS iTV Certification (Initial: 07/25, New: 07/18) => Compressed software validation/fix duration w/ higher risk.
R00 Software Release On Time (06/06) => Closely track each key S/W releases ahead and add more test resource towards PEC1
New Checkpoints
Notes: Pre-DV: 66 days, 2.2 months ; Critical DV: 60 days, 2 months; Sync+ CDC DV: 94 days, 3.13months;
Sample build: 52 days, 1.7 month; Re-DV: 26 days.

## Slide 26: CDX707 Critical path & 2nd Round Checkpoints
Checkpoints | Date | Key Items | Lead
Checkpoint 5.1 (2nd round) | 2021/7/30 | Group B UI sign off (Vehicle Setting/Navi/AR Navi/On-line Music/On-line Video) QA list health status review. | HMI & EESE HMI & EESE & PM
Checkpoint 5.2 (2nd round) | 2021/8/15 | Group C – session1/2 UI sign off QA list health status review. DCV Beta bench healthy status review. | HMI & EESE & ECDX HMI & EESE & ECDX & PM EESE
Checkpoint 5.3-1 (2nd round) | 2021/9/15 2021/9/30 | Group C – session2/2 UI sign off Group D UI sign off QA list health status review. | HMI & EESE & ECDX HMI & EESE & ECDX HMI & EESE & ECDX & PM
Checkpoint 5.3-2 (2nd round) | 2021/10/30 | Group A/B/C/D multi-theme UI sign off QA list health status review. | HMI & EESE & ECDX HMI & EESE & ECDX & PM
Checkpoint 5.4 (2nd round) | 2021/10/20 | DCV0 sw health status review. Agile sw health status review. QA list health status review. Establish 3rd round checkpoint if necessary. | EESE & ECDX ECDX HMI & EESE & ECDX & PM All
Checkpoint 5.5 | 2021/12/19 | RePA UI sign off | EE AFO & HMI
CP1
CP2
CP3
CP4
CP5
IVI bench delay and AutoSAR package delay drive risk for IVI development.
CP6
DCV
DCV MRD
UPV1
UPV2
PA
FDJ
03/05
06/16
02/02
01/05
Back to main page
Checkpoint 6 (1st round) | 2021/12/20 | HW critical DV test plan check in Dec 24th 2021 R08 readiness check for DCV build start in Feb 1st 2022 Retrofit detail plan(material, timing, cost, resource) R10 progress check for DCV test start in Feb 22nd.2022 | EESE EESE PM&VEV EESE
CP5.1
CP5.2
07/14
08/18
08/20
09/10
CP5.3
CP5.4

## Slide 27: CDX707 FDJ Software Delivery Plan – DuerOS
Jul-10 |  |  |  | Aug-10 |  |  |  | Sep-10 |  |  |  | Oct-10 |  |  |  | Nov-10 |  |  |  | Dec-10 |  |  |  | Jan-10 |  |  |  | Feb-10 |  |  |  | Mar-10 to Jun-13 |  |  | 
PEC
13-Jun
FDJ BB Start
25-Sep
DCV Vehicle Testing
FDJ / Eng BB
DCV Beta
DCV0
DCV2
DCV3
DCV1
25-Feb
DCV T/C MRD
12-Jan
Eng BB Start
8-Dec
Display-941/984
Display-983/984
Local Radio-FM
Local Radio-AM
Local system
Audio-Path
Audio-Source switch
Audio-Chime
Audio-A2B
Power
Phone-Dal
Phone-Phone Book
Phone-Call log
Local Music
Local Video-USB Video
System UI-Status bar
System UI-Navi bar
Network Vehicle setting
Network Vehicle control
Generic Diagnostic
Audio-ANC/ESE
USB Update-SOC
USB Update-VIP
Camera-Digital RVC
Camera-Digtial 360
DLNA-Video
DLNA-Photo
System UI-Volume bar
System Setting
Engineer mode diagnostic
FNOS AUTOSAR
PART 2
Network configuration
Power mode & voltage mode
Dimming
Gauge-Engine Coolant Temperature
Gauge-Engine Coolant Temperature transfer
Gauge-Speedo Tolerance Analysis
Gauge-Speedo meter
Gauge-Speedo meter Digital
Gauge-Tachometer
Odo
TRIP Computer Outside Air temp
System UI-Common popup
System setting Theme settings
System setting Vehicle hot-spot
System setting System update
System setting Master reset
System setting Search function
Engineer mode-EEP/ICP Diagnostic
Engineer mode-TCU Diagnostics
EOL
Part 1
SWDL
Cluster Chime Arbitrator
Chime
RTT
Telltale
Warning
TRIP Computer
Setting
Control Mirror
Message center
Welcome Goodbye animation
ADAS-ACC
ADAS-PCA
ADAS-Highway assist
OTA
Cyber Security
ETM
ETM Text
Function safety
Finalized DuerOS S/W delivery plan pending completion of BoF alignment and features’ requirement cascade
As of 13rd Oct

## Slide 28: QUALCOMM HQX1.0 VS HQX1.2.1
No | New Feature | Description | HQX 1.0 | HQX 1.2.1 | Platform | Comment
1 | 蓝牙音乐Hi-Res格式 | Ford项目需要支持APTX, LDAC蓝牙音乐编解码（第一路蓝牙需要解码，第二路蓝牙需要编码）。无此功能，蓝牙音乐功能将无法支持Hi-Res格式。如果采用第三方方案，可能会涉及到BT Stack的方案整体替换，并且第三方方案会有NRE以及Royalty费用。 | *No | No | All | APTX decoder已在6595完成，LDAC encoder已在8311完成 高通可以在1.2.1支持开发，需要NRE费用 *NJTC咨询第三方方案支持
2 | USB Video Decoder | Ford项目Media功能支持FLV文件(解码格式S263)。影响FLV文件的播放功能。 | *No | No | All | 高通可以在1.2.1支持开发，需要NRE费用 *NJTC集成开源软解码方案
3 | Digital RVC/AR NAVI/哨兵模式 | Ford项目需要Android支持多路Camera。当前福特有8路摄像头输入，会影响到多个摄像头同时使用的场景。 | No | No | 747 | 高通可以在1.2.1支持开发，需要NRE费用
4 | 倒车画面显示 | CVBS摄像头需要支持奇场和偶场数据反交错（625MCA有CVBS摄像头）。无此功能将会使搭载CVBS摄像头的车型倒车画面显示异常。 | No | No | 625 | 高通可以在1.2.1支持开发，需要NRE费用
5 | AVAS/EVSE | 在Phoenix项目MBBM基于MDSP开发，Ford Phase5需评估是否可以支持同样方案。 | No | No | 747 | 高通反馈: HQX1.2.1仅支持QNX实现。 高通可以在1.2.1支持开发，需要NRE费用
6 | A2B Slave/eAVB | A2B Slave模式或eAVB功能依赖于ASRC功能，需要做异步时钟转换。需要高通支持ASRC功能。 | No | No | 747 | 高通可以在1.2.1支持开发，需要NRE费用
7 | 第二路蓝牙 | 支持5.2协议栈, BQB （AVRCP TG, A2DP source）认证YFV lead， 高通Support。 | No | No | All | 高通可以在1.2.1支持开发，需要NRE费用
8 | AR NAVI | 百度要求打开NPU功能辅助AR导航开(需要Android侧支持)，以节省CPU算力。 现阶段讨论后考虑在QNX上支持CDSP/HTA。 | No | Yes | 788 | 需要NRE费用
9 | 哨兵模式 | CDX747需要基于STR（Suspend To RAM）实现哨兵模式。 | *Yes | Yes | 747 | 高通反馈: HQX1.0基线STR功能不稳定，需要升级至HQX1.2.1才能支持Bug Fix。
10 | DDR | DDR需要支持 16G，HQX1.0 layout 优化未做过，可能引起Security功能不正常 | *No | No | All | 高通可以在1.2.1支持开发，需要NRE费用 *NJTC在study自己开发支持16G
11 | Relax | Ford项目需支持Relax功能，目前我们已经基于HQX1.0 DSI Split方式实现（7680 * 720） | *Yes | Yes | 707/747/718 | 分辨率超出了高通文档范围，但是我们已经实现，需要高通认可方案的可行性及支持后续的问题修复。

## Slide 29: QUALCOMM切基线计划(基于Solution1)
FC适配：
FC支持适配前提条件：需要高通支持QNX各节点过程patch释放
此方案YFVE会额外增加基线迭代次数及大量适配工作

## Slide 30: CDX707 Software and Autosar Release Plan
Autosar Package integration
CDX707 VPP
YF Package integration
SW Release for CAF/FO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
02/19
UPV2
06/11
SW Release for REC
PEC
06/13
PA
07/14
FDJ
08/20
TT
08/24
PP
11/09
MP1
02/01
DCV
02/02
DCV Alpha
03/19
DCV Beta
08/02
08/20
A0 PCBA
01/25
CDC AHU HW
A1 PCBA
05/30
06/08
B0 DV1
11/30
B1 DV2
05/10
Pre-DV
DV1
DV2
DCV Alpha1
03/31
DCV Alpha2
04/28
DCV Alpha3
05/26
DCV Alpha4
06/23
DCV Beta
07/18
08/01
DCV Beta1
08/18
DCV Beta2
09/15
DCV0
10/20
DCV0.1
11/17
DCV1
12/15
12/07
DCV2
01/12
01/07
DCV3
02/23
02/11
R00
03/23
R01
04/20
R04
05/18
R05
06/15
R05.1
07/13
R05.2
08/10
R06
09/07
R06.1
10/19
R07
11/20
R08 for OKTB
01/15
2021 | 2022 | 2023
08/02-08/30
12/05-2/28
05/15-06/15
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
MP2
03/01
FEC
07/25
OKTB
03/28
DCV0
11/03
11/10
DCV1
12/29
12/15
DCV2
01/26
01/14
DCV3
03/09
02/25
R01
05/04
R04
06/01
06/13
R05
06/29
07/14
R05.1
07/27
R00
04/06
05/02
R05.2
08/24
R06
09/21
09/29
R06.1
11/02
R07
12/04
12/14
R08 for OKTB
01/24
R09 for OTA
04/28 TBD
PEC1
07/26
FEC1
09/06
DCV0.1
10/20
DCV1
11/17
DCV2
12/15
DCV3
01/12
R00
02/23
R01
03/23
R04
04/20
R05
05/18
R05.1
06/15
R05.2
07/13
R06
08/10
R06.1
09/07
R07
10/19
R07 for OKTB
12/15
完成调查表，2周
完成德国报价，2周
预估项目定点
YF内部流程PR&PO，签订采购合同
6周
Vector释放软件包，10周
网络诊断全功能，FBL并行开发
Bug Fix
ITV P2
ITV P1
网络诊断初版
T：07/30
完成ITV
移植完成之前CAN信号,实现30%的CAN信号添加
DCV0
09/15
实现60%的CAN信号的添加，30%的DID和30%的DTC的实现
DCV Alpha4
05/26
DCV Beta
06/20
07/04
DCV Beta1
07/18
DCV Beta2
08/18
DCV0
09/15
注：
DCV ALPHA4 – R06 详细释放计划见后页
YF CAN 网络信号分3个版本释放
- 10/20(DCV0.1集成时间)释放30%信号(即整体信号30%),包括移植先前开发的CAN信号(YF自研包开发的信息)。
- 11/17(DCV1集成时间)释放30%信号(即整体信号60%)
- 12/15(DCV2集成时间)释放40%信号(即整体信号100%)
此外还需考虑Package2调试和集成时间。
ITV认证周期： T(2021/07/30) +12月, 完成认证时间2022/07/25

## Slide 31: CDX707 SHC Feature in SYNC+ 3.0 Development Plan
Pre-Condition： 1.For CDX707 China CDC only implement all LHS function and partly RHS function, not include Driver Adjustment part (exp. Mirror, Pedal and Steering Wheel adjust)
2.China CDC SW development start point is T, before that the following documents must be qualified released, if these document release is delayed, the T point will also be delayed day by day:
-SPSS & STSS document -> Sync+ 3.0 Core Team Release
-FuSa SRS document -> SHC FO release
-HMI UE document and UI resource -> HMI Team Release
-CAN signal defined in DBC file -> Netcom Team
-1 H/C required for Sync+ 3.0 SPSS/STSS implementation. -> PMT to drive
Dependencies Statement:
3.The SHC physical component must be ready for joint debugging with China CDC from T+9weeks.
4. China CDC will make sure all CAN signal will be sent out correctly by component test, the system level joint verification will depend on DAT component availability(Dynamic driving is also required for DAT).
5.China CDC will do stagger releases for SHC feature, 1st release(T+5 months) LHS DAT part to support DAT team in-vehicle test, 2nd release(T+7 months) RHS Infotainment prat.
CDX707
UPV1
02/19
2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  |  | 2023 |  |  |  |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
UPV2
06/11
PEC
06/13
PA
07/14
FDJ
08/20
TT
08/24
PP
11/09
MP1
02/01
DCV
02/02
MP2
03/01
FEC
07/25
OKTB
03/28
STSS&SPSS Release
FuSa SRS Release
12/31
DBC Release
11/30
China CDC SW
SHC Feature Development Plan
Feature Doc Release
9/31
Feature Function Doc Release
10/31
Totally need T+5+2 month
Design &Coding
14Weeks
Debug with SHC
Test &BugFix
6 Weeks
RHS Test & BugFix
8 Weeks
LHS DAT part Function Release
RHS Infotainment part Function Release
T
T+9
wks
Audio Management, All Media Related, Navigation Info/setting, Bluetooth

## Slide 32: CX788 Opportunities And Enablers
IVI Actions To Compress | Status | Action Description | Risks | Enablers
4wks Compress | Taken With Risks | Take Group A UI Unsigned Version To Kick Off Coding(11.29 To 10/30) *Normally IVI/supplier only take signed version to kick off coding. | Poor Software Delivery Quality, Coding Rework When UE/UI Unsigned Design Changes. Delay Or Fail to Start Pre-DV; Unknown DCR cost charged | 1.MFL w/ FO/Spec release COB 08/19. 2.HMI Delivery(Group-A/B/C/D) Can’t Delay Any Further. Set Checkpoints and regular HMI PAT meeting to guarantee the HMI qualified release.---Program, VI
2wks Compress | Taken With Risks | Compress The Group A Coding Time From 10 Wks To ~8wks | Low Software Quality, Risk To Delay Or Fail To Start Pre-DV and downstream. | 3.IVI Counterparty/Bench Bom Release COB 08/30. IVI related key counterparty including AHU/15.4 display/9 cluster/AR HUD and the related harness should be ready COB 09/30(High Risk). Each Sign-off Team Has Qualified DV vehicles With Great DV Vehicle Usage Schedules => Need Dedicated Person To Manage Closely. ---Program, EESE
2wks Compress | Taken With Risks | Compress further 2wks Development &Validation time between DCV Alpha and DCV Beta (origin 8wks to 6wks) | Low Software Quality, Risk To Delay Or Fail To Start Pre-DV and downstream. | 
1wks Compress | HW token with Risk | With above 1/2/3 compress, plus take further risks to pull ahead B0 sample build W/O REC validation by 14 days(6/10 to 06/23). | If there is any critical bug of the Eng version released on 06/10, SW should be upgraded on 06/23. Delay for DV test start. | 4.Vendors must ensure sufficient development/test resources for CX788.---Vendor 5.OT shift will be needed for SW PM/Test leader to control the daily version quality and issue tracker efficiency. 2 test NSPS engineers for CDC till FEC2 declared.---Program, EESE 6.Vendors should complete the SW upgraded by USB and FBL, backup for any update request in NA. ---EESE
1wks Compress | In Studying | Compress REC DCV1 Validation Time Window From 2 Wks To 1 Wks By Further OT Shift. | If there is any critical bug of the Eng version released on 07/10, SW should be upgraded on 07/24. Delay for vehicle shippment. | 
2wks Compress | In Studying | Only 2 wks lead time for R04 FO sign off supporting FEC2(6wks per system team request) . Study using End version W/O REC validation supporting FO sign off. | Need FO confirm the sign-off lead time within 4 wks. High risk for delay FEC2 sign off if there is any critical issue on Eng version. | 7.Program Offers IVI S/W Team 5 DCV Vehicles For System Level Debug. (3 for suppliers, 2 for IVI Software Team), TT Vehicle *3 Is Also Required to guarantee the qualified release. ---Program
New 9’ Cluster added | Program token | Given cluster team need to kick off new 9’ display and split cluster application, additional people resource is required. | Risk….. | 8.Put 1 cluster D&R/1 display D&R(Ford head, onboard in Sep) ---Program, EESE
In Order To Support Program, Total 6 Actions Are Taken And Studied By EE IVI Team With Huge Risks(Unsigned UI to kick off coding).
Hardware B0 Complete Date (06/30 => 06/24, 1wks)
Software DCV1 Complete Date( Target 07/17 release to support SW update. 4+2+2+1=9 wks compressed with enablers)
Eventually FEC2 Sign off Date Still Has High Risks and Need Further Study.
1
2
3
4
5
6

## Slide 33: SYNC+3.0 SW Integration and Release Rule
2021 | 2022 | 2023
Checkpoint1:
Vendor Integration
Checkpoint2:
Eng SW Release for REC
Checkpoint3:
Pro SW Release for CAF/FO

## Slide 34: CDX707 System Block Diagram
2021 | 2022 | 2023

## Slide 35: CDX707 Minimum IVI Group A Delivery
Launcher& System UI (Basic function)
Climate (BOF)
Camera (BOF)
(4) Radio (Customer Facing, Pre DV test mode)
(5) Bluetooth Music(Customer Facing, Pre DV test mode)
(6) USB Video (Customer Facing, Pre DV test mode)
(7) System setting (Basic function)
(8) DLNA (Customer Facing, Pre DV test mode)
(9) Bluetooth Phone (Basic function)
(10)USB Music(Customer Facing, Pre DV test mode)
(11) Program Distributed Feature(BOF)
(DCV Alpha, DCV Beta)  Group A, DCV0 Group B, (DCV1, DCV3)  Group C-E
What can we do now to meet CDX707 J1?