## Slide 1: SYNC+3.0 SW Release Plan
Think
Point of view
Plan to Implement
Implement
Jiajia Zhou, Deyin Chen, Jiajian Wang, Zhijun Su, Kaijie Zhang
Date:11.13 2023
Desired Outcome
Awareness
Decision
Escalation Help

## Slide 2: SYNC+3.0 Vehicles Timeline
OK2B
9/23
U611MCA
PEC
8/11
FEC
OK
TB
Pre-TT
IPD: 11/21
TCF: 12/06
PP
IPD: 04/2
TCF: 04/16
MP1
IPD: 06/04
TCF: 06/19
MP2
IPD: 07/02
TCF: 07/17
08/20
TT
IPD: 1/02
TCF: 1/16
U625 MCA
10/19
6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
2023 | 2024 | 2025
09/05
OK
TB
Pre-TT
IPD: 11/21
TCF: 12/06
PP
IPD: 04/2
TCF: 04/16
MP1
IPD: 06/04
TCF: 06/19
MP2
IPD: 07/02
TCF: 07/17
08/20
TT
IPD: 1/02
TCF: 1/16
U625 MY24
10/20
PEC
9/21
FEC
PEC
9/28
FEC
U718
PEC
11/30
FEC
OK
TB
EPT2
IPD: 12/01
TCF: 12/11
PP
IPD: 06/28
TCF: 07/15
MP1
IPD: 09/16
TCF: 09/30
MP2
TCF: 10/28
11/18
TT
IPD: 03/29
TCF: 04/08
HW:12/15
SW:01/24

## Slide 3: SYNC+ 3.0 Vehicles Info
SYNC+ 3.0 Phase5 Scope |  |  |  |  |  |  |  |  |  |  |  | 
Program | PMO | IVI SW PM | Nameplate | Manufacture | J1 | OKTB | EE Architecture | Centerstack Size | Cluster |  | TCU | ECG
CDX707 | Li Daisy | Zhou Jiajia (XCL) | Nautilus | CAF | GAS: 2/1/2023 FHEV: 6/21/2023 | GAS: 3/28/2023 FHEV: 8/8/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
U611 MCA | Chen Fengmin | Wang Jiajian | Aviator | CAF | 06/19/2024 | 08/20/2024 | FNV3 | 27 | 12.3 | Landscape | Boundle6 | ECG2
U625MCA | Chen Deyin | Su Zhijun | Explorer | CAF | 06/19/2024 | 08/20/2024 | FNV3 | 27 | 12.3，HUD | Landscape | Boundle6 | ECG2
U718 | Chen Fengmin | Zhang Kaijie | Navigator | BU | 09/30/2024 | 11/18/2024 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2

## Slide 4: U718 SW Release Plan @ 23/11/13
Project VPP
SW Release for FNA Team
R00
07/8
R04
9/5
R05
11/06 Test Report
11/10 GNG
11/13 IVS
R06
5/24 Test Report
5/31 GNG
6/7 IVS
R07
8/9 Test Report
8/16 GNG
8/23 IVS
R07.1
9/11 Test Report
9/23 GNG
9/30 IVS
SW Release for REC
Vendor Integration
OKTB
11/18
4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
R00
6/26
R00
5/23
R04
7/31
R04
8/28
R05
10/18
R05
9/18
R06
5/10
R07
7/26
R06
3/28
2023 | 2024
R07
6/27
PEC
11/30
TT
IPD: 3/29
TCF:4/8
PP
IPD : 6/28
TCF : 7/15
MP1
IPD : 9/16
TCF : 9/30
R07.1
8.13
R07.1
9/3
R05.1
12/5
R05.1
12/29
R05.1
1/10 Test Report
MP2
TCF : 10/28
EPT2
IPD : 12/1
TCF: 12/11
FEC
HW:12/15
SW:1/24
R05.2
3/4 Test Report
3/11 GNG
3/18 IVS
R05.2
2/19
R05.2
1/15
Calibration
ANC/ESE
10/23
BT
12/4
1st VR
1/5
2nd VR
2/29
3rd VR
6/25
Spring Festival
2.10-2.17
Chime
11/30
Carplay
Carplay (Disable)
Carplay (Enable)
TBC

## Slide 5: U611MCA SW Release Plan @ 23/11/14
R00
7/17
R05
11/19
R07
4/16 test done
GNG:5/7
R00
7/3
2023 | 2024
U611MCA VPP proposal
PEC
8/11
SW Release for CAF
Vendor Integration
R07
4/1
R05
09/20
R07
3/1
R00
5/30
5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
R04
7/7
R04
8/14
R04
8/25
OK
TB
2.10~2.17
Spring Festival
R04.1
8/15
R04.1
9/06
SW Release for REC
R04.1 final eng
8/30 for redv
R05
10/23
R05HF
12/05
IVS RELEASE
IVS release
R06
3/1
IVS RELEASE
R06
2/2 TEST DONE
GNG:2/23
R06
1/12
R06
12/11
R07
5/16
IVS RELEASE
R04.1
9/11
R07.1
06/03
R07.1
06/24
R07.1
6/28 test done
GNG:7/05
MRD
R07.1
7/12
IVS RELEASE
Pre-TT
IPD: 11/21
TCF: 12/06
FEC
PP
IPD: 04/2
TCF: 04/16
MP1
IPD: 06/4
TCF: 06/19
MP2
IPD: 07/2
TCF: 07/17
08/20
TT
IPD: 1/2
TCF: 1/16
R07.1 only book for carplay
R05 HF for EX2.5 Lib 12/01
R05
11/17
R05
11/23
Notes: 有功能增加；
音频架构有变化。

## Slide 6: U625 MY24 SW Release Plan @ 23/11/14
R00
7/26
R05
11/19
R007
4/24 TEST DONE
GNG: 5/07
R00
7/12
2023 | 2024
U625 MY24 VPP proposal
PEC
9/21
SW Release for CAF
Vendor Integration
R07
4/08
R05
10/12
R07
3/08
R00
6/08
6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
R04
7/21
R04
8/21
R04
9/15
ANC vbf check
FEC
2.10~2.17
Spring Festival
R04.1
8/30
R04.1
9/15
SW Release for REC
R05
11/06
IVS release
R06
3/01 IVS release
R06
2/08 TEST DONE
GNG: 2/23
R06
1/19
R06
12/18
R07
5/16 IVS release
R04.1
10/08
OTA
DCV
8/08
10/19
R07.1
6/28 TEST DONE
GNG 7/05
MRD
R07.1
6/24
R07.1
6/03
R07.1
7/12 IVS release
OK
TB
Pre TT
IPD: 11/21
TCF: 12/06
TT
PP
IPD: 4/02
TCF: 4/16
MP1
IPD: 6/04
TCF: 6/19
MP2
IPD: 7/02
TCF: 7//17
8/20
IPD: 1/02
TCF: 1/16
R07.1 only for carplay
R05 HF
12/05
IVS RELEASE
R05 HF for EX2.5 Lib 12/01
R05
11/17
R05
11/23
Notes: 有功能增加；
音频架构有变化。

## Slide 7: U625 MY24 & U611MCAJ1 with CarPlay Plan
U625 MY24 &U611MCA Build Plan
9 | 10 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
IVI Integration Plan
R06
12/11 INT
U611
03/01 INT
U611
06/03 INT
U611
CarPlay Development Plan
09/06
Full Function
12/29
1st FO signoff(checkpoint)
04/15
Apple
Approval
Dependency
U611/U625
U611: 01/15 – 01/19 Supplier Tunning
01/22 – 01/26 Rec Road Test with R06, bug fix in R07
02/19 – 03/01 TT VOCF with R06, bug fix in R07
05/13 – 05/24 PP VOCF with R07, bug fix in R07.1
U625: 01/22 – 01/26 Supplier Tunning
01/29 - 02/02 Rec Road Test with R06, bug fix in R07
02/26 – 03/08 TT VOCF with R06, bug fix in R07
05/20 – 05/31 PP VOCF with R07, bug fix in R07.1
Spring Festival
New Year
Holiday
IPD: 02/20 03/26
TCF: 03/06 04/16
PP
R06
12/18 INT
U625
03/08 INT
U625
MP1
IPD: 04/30
06/04
TCF: 05/15 06/19
TBD
TBD
OTA
R07.1
06/03
INT
U625
IPD: 05/29 07/02
TCF: 06/12 07/17
MP2
07/05
08/20
OK
TB
Tomb
Sweeping
05/232nd FO signoff
Vehicles
IPD: 11/21
12/26
TCF: 12/06
01/16
TT
1st VR
The CarPlay VSCS is open from PP MP2 build
Besides VSCS, the CarPlay should also have compile option to enable/disable
R07
R07.1
R08
TBD
R08
R07
R06/R07/R07.1 REC Test Plan
U611:
  R06: 01/12 – 02/02
  R07: 04/01 – 04/16
  R07.1: 06/24 – 06/28
U625:
  R06: 01/19 – 02/09
  R07: 04/08 – 04/24
  R07.1: 06/24 – 06/28
Notes: Dekang: R07 集成CarPlay，需要delay 到3.15集成 –- 不用
Jiajia: IVI SW integration & release workflow -- done
Emma: R06.1 for CarPlay signoff bug fix –- 不需要R06.1， 所有carplay 改动，按照IVI 正常的软件集成做即可
Emma: VR is the pre-condition of CarPlay -- done
Jiajia: PP FCPA/NTT -- done
Dekang: TT VOCF/FCPA/NTT long mileage – Done
TT 不用delay
Plan special SW to support PP VOCF
MP1 打开 CarPlay
MP2 要么disable carplay，要么出版本fix issue
02/19 – 06/01(U611/U625，可分段，需要和VOCF 对齐跑车计划
期间跑两个版本，每个版本两周)
元旦：12/30 – 01/01
春节：02/10 – 02/17
清明：04/04 – 04/06
劳动节： 05/01 – 05/05
端午节： 06/08 – 06/10

## Slide 8: Enablers
Enablers | Date | Comments | DRI
Vehicle | 2024/01/05 | The vehicles(U611 9/14/28 speakers, U625 6/12/14 speakers) must be ready to support REC road test Pre-TT/TT Test plan align with Susan Team | 
VSCS | 2023/11/05 - 2024/06/25 | The CarPlay which is disabled as default and can only be enabled before testing | 
REC Road Test & TT VOCF/NTT & Bug Fix | 2024/01/05 - 2024/02/27 | The tester resources need to be ensured Ensure the TT VOCF/NTT starts at least on 5th/Jan, including long mileage - ensured Suppliers have 1 week to fix the bugs Lite test我们目前在准备，但是有部分case需要基于比较稳定的软件版本做截图，所以预计12月份可以提供。 Vocf/NTT样本量我们期望是至少2台车（1台低配 和1台中or高配），测试时间是从2月份持续到4月份。 Check point: NTT/VOCF 车辆部署状态，test case 传递状态： date – to be checked 期望在TT（1月16号TCF）赶NTT/VOCF TCF 之后 1周，开始NTT TCU 之后3周，开始VOCF 对齐CarPlay SW maturity status timeline 12月20号check TT build plan，选几台车用作NTT/VOCF 专项测试 | 
PP VOCF/NTT & Bug Fix | 2024/03/17 - 2024/04/15 | Ensure the PP VOCF/NTT starts at least on 17th/March, including long mileage Suppliers have 1 week to fix the bugs 同TT， 待check，比如build plan，SW status， test case coverage， etc. | 
MP1 VOCF/NTT | TBD | Ensure the MP1 VOCF/NTT test starts in time to check if there is critical issues to block the CarPlay delivery If critical issues are identified, assess if CarPlay could keep going forward with J1, or fix the issues in OTA 同TT，待check，比如build plan，SW status， test case coverage， etc. | 
Apple Certification | 2024/04/15 | Ensure pass the Apple Certification | 
Iphone | 2024/01/05 | OS should be upper than IOS13 HW should be upper than Ipone7 The Iphone should be ready before TT VOCF/NTT | 
VR | 2023/09/21 | The 1st VR calibration should complete on 21th/Sep as plan | 
Test Cases | 2024/01/05 | The test cases should be ready before 2024/01/05 to support REC road test/TT VOCF & NTT/PP VOCF & NTT | 
Notes: VOCF//NTT: 每个配置一台车
VOCF 专项测试，由REC/Supplier 派人跟车
VOCF 长里程，提供测试用例
NTT 测试用例由谁提供？？？？？？？？？？
UAT team to be involved？？？？？？？？？？？？？？
TT VOCF/FCPA/NTT
VR

## Slide 9: Risks
Risks | Due date | Comments | DRI
Apple Certification | 2024/04/15 | Fail to pass the Apple Certification will result to the J1 CAN NOT include CarPlay The containment plan is unclear | Su Zhijun Geng Dekang
Vehicles | 2024/01/02 | No Vehicles(U611 9/14/28 speakers, U625 6/12/14 speakers) to support CarPlay REC road test | Zhang Edward Liu Andrew Wu Yu Su Zhijun

## Slide 10: Backup material

## Slide 11: Phase5 SYNC+ 3.0 Timeline Draft To Be Reviewed
Project VPP
GPDS SW Version for MRD
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
UPV2
Hardware
UX Release
PEC
PA
FDJ
TT
PP
MP1
DCV
DCV Beta
R00
R04
R05
R06
R07
Key Checkpoint
DCV0
Group A UI
For Pre DV/FDJ
Group B UI
For Critical DV/DCV
Group C UI
For DCV
Group D UI
For DCV/PEC
MP2
FEC
OKTB
UPV0
PS/PSC
1.Bill of feature Initialized(MFL)
2.Feature Owner confirmation
3. Basic Level spec are available
4.1EC
1. Supplier Sourced (SOBD)
======
1.Bill of feature(MFL) Finalized
2.Platform feature spec complete and cascaded
3.Function Safety Concept updated and completed
4.Cybersecurity Requirements Identified
5.UX(UEUI) alignment confirmed
6.SW environment and baseline Design
7.pre-2EC
1. Platform feature spec finalization and sign off
2.Simulate feature integration of interfaces, states and responses to requested behavior
3. Early test of new and C/O features with physical parts
4.2EC
1.DCV Beta verified supporting Pre-DV/EMC, critical function including Climate/Camera/Radio/Music/Video/Navigation/Speed meter/Driving Info etc.
2.Feature Software early system-level integration test start at <FDJ> breadboard
3. UX doc sign off by HMI/Studio team
1.DCV1 verified supporting DV/EMC/DCV MRD with full function code completed.
2.Feature Software early system-level integration test complete by <DCV> breadboard, verify feature functionality and performance requirements.
1All design verification testing completed by <PEC>
2.Feature Software system-level integration test complete and sign off by feature owner and HMI team
3.R00 release for <PEC> without critical blocker issue,
4.Diagnostics Part2 DV(iTV) test report shows 100% passed
1. Software OTA window preserved post Job1 and before OKTB.
R08
1. Agile feature full function Integration without critical bug.
Group A Features Coding based on UI
DCV Alpha
DCV Beta
test
A1
Pre DV
Debug
B0
Critical DV
DCV Critical Path * 45 weeks
DCV1
17 weeks(4 months)
6 weeks
DCV
DCV MRD
4 weeks
5 weeks
>=6 weeks
DCV0
test
Eng Version
>=6 weeks
9 weeks
9 weeks
9 weeks
A0 PCBA
A1 Sample
B0 Sample
B1 Sample
Features and HMI Design
Display light up
Platform Arch design
PIPELINE Design
Initial release for Pre DV
DCV Beta
30% Coding
Release Fundamental features for DCV vehicle testing
DCV1
60% Coding
Zero IG defects supporting PEC sign off
R00
95% Coding(Not including Agile features)
Delivery of all features with zero G issues
R05 100% Coding
AIMS Issue solve / Bug fix
R06 100% Coding
AIMS Issue solve / Bug fix
R07 100% Coding
17 weeks(4months)
17 weeks(4months)
13 weeks(3months)
8weeks(2months)
9 weeks(2months)
8weeks(2months)
10weeks(2.5months)
Hotfix for OKTB
Preserved
5 weeks
>=14 weeks
>=32 weeks
14W
13W
14W
10W
26W

## Slide 12: SYNC+ 3.0 DCV/PEC/J1 Critical Path
China Accelerated SW Plan ---DCV Critical Path
FDJ
DCV
Group A UI Release
MRD
DCV Beta 30%
DCV0 50%
DCV1 60%
45 weeks
Group A Features Coding based on UI
DCV Alpha
DCV Beta
Test
A Sample
Pre DV
Debug
B Sample
Critical DV
China Accelerated SW Plan ---PEC/J1 Critical Path
R00
95%
R04
R05
100%
R06
R07
R08
DCV1 60%
DCV
DCV MRD
4 weeks
5 weeks
9 weeks
9 weeks
Zero IG defects supporting PEC sign off
R00 (4*SW iterated versions )
95% Coding(Not including Agile features)
Delivery of all features with zero G issues
R05 100% Coding for TT MRD
AIMS Issue solve / Bug fix
R06 100% Coding for PP MRD
17 weeks(4months)
13 weeks(3months)
8weeks(2months)
DCV
6 weeks
PEC
FEC
6 weeks
TT
PP
AIMS Issue solve / Bug fix
R07 100% Coding for J1
8 weeks(2months)
Hotfix for OKTB
R08 100% Coding
Preserved
9 weeks
J1
Initial release for Pre DV
DCV Beta
30% Coding
Release Fundamental features for DCV vehicle testing
DCV1
60% Coding
17 weeks(4months)
8weeks(2months)
Features and HMI Design
Display light up
Platform Arch design
PIPELINE Design
10weeks(2.5months)
OKTB

## Slide 13: What’s SYNC+ PDL & FIP
Tech
Planning
ECDX
Manager
Review
Marketing
IVI SW PDL
Forum
Feature
Delivery
Leader
EESE IVI
SW & SYS
Feature
Cascade
Feature
Owner
Basic(ECU) Functions
(EESE IVI SW maintain)
Customer Facing
Features
(ECDX PMO maintain)
BOF Cascade Features
(FDL maintain)
IVI SW PDL
(ECDX PMO maintain)
IVI SW FIP
(EESE IVI SW
maintain)
Supplier Workload Ratio
ECU Functional SPEC Information
Feature Integrate Schedule
HMI Design
(UE & UI)
(EESE IVI SW maintain)
A
A
A
B
C
D
B

## Slide 14: GPDS Delivery Health Chart VS U6XX Actual Delivery Status.
GPDS MCA Platform Timing
UPV0
14w
UPV1
13w
UPV2
14w
FDJ
10w
DCV
26w
PSC
GPDS Feature and SW Pocket Card
BOF Finalized
Feature List Aligned to PDL
SOBA
Feature/Function Spec Complete
HMI Health Chart Created
Group A UI
(K4+4W)
33w
Group B UI
(K5+4W)
26w
20w
Group C UI
(K6+4W)
3w-4w
Group D UI(FAA+4W)
Group E Animation (FAA-4W)
DCV Beta For FDJ BB
DCV1 For DCV MRD
China SYNC+ 3.0 Critical Path: New/Modified IVI Platform & New UE/UI
45w
Group A UI latest date
U6XX MCA Actual Story
UPV0
03/30
UPV1
06/25
UPV2
10/25
FDJ
12/7
DCV
06/13
DCV YB MRD
05/13
DCV EBB MRD
04/01
PSC
01/11
2021/05
Confirmed U6XX in Phase5 Scope
BOF Cascade started to involve China Team
2021/07/20
HMI KOTEI SOBA
2021/09/01
SYNC+ PDL Initialized Version released with continuously change
2021/0908 RFQ released to Package1/2/3
11/09
Group A UI
04/17
DCV Beta For FDJ BB
07/15
DCV1 For DCV MRD
China SYNC+ 3.0 Critical Path: New/Modified IVI Platform & New UE/UI
39w(6w has been compressed)
DCV
Proposed 08/16
Program Content/BOF cascade did not follow the GPDS3.3 Process.
HMI delivery plan did not follow the Global/Go Fast Health Chart.
How to guarantee SW maturity meet the Global Software Maturity Progression? ---Deviation needed.
SW Develop Team Compressed the initial over 4months delay to 2 months by OT work
Notes: 有功能增加；
音频架构有变化。

## Slide 15: Software Maturity Progression Request

## Slide 16: SYNC+3.0 SW Integration and Release Rule
2021 | 2022 | 2023
Checkpoint1:
Vendor Integration
Checkpoint2:
Eng SW Release for REC
Checkpoint3:
Pro SW Release for CAF/FO
Checkpoint4:
R1, R2 Must fix issue List Release

## Slide 17: CDX707 System Block Diagram
2021 | 2022 | 2023

## Slide 18: CDX707 DCR Control Process Proposal
2021 | 2022 | 2023
CDX707
UPV1
03/05
3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV2
07/30
PEC
07/19
PA
08/18
FDJ
09/10
TT
09/07
PP
11/23
MP1
02/01
DCV
02/02
01/28
MP2
03/01
FEC
08/29
OKTB
03/28
HB
09/30
TT
02/01
PP
04/19
MP1
06/21
MP2
07/19
OKTB
08/08
GAS
FHEV
FDJ
05/11
Audio(24 Channel Amplifier): 05/E Amplifier ready,06/10 retrofit with the latest SW.
DCV
08/31 Retrofit
SW Release for REC. CAF/FO
DCV0
10/20
11/03
DCV1
12/15
12/29
DCV2
01/12
01/26
DCV3
02/16
03/02
DCV5
04/20
05/04
R00
05/18
06/01
R04
06/15
06/29
R05
07/13
07/25
DCV4
03/23
04/06
R06
09/07
09/21
R07
11/20
12/04
R08 for OKTB
01/15
01/24
Patch1:Carry over HQX1.0 Feature base on HQX1.2.1 Engineering line
FC(Feature Complete): Initial Release
Patch2:Fix Critical Issue support CDX707 FEC
CS(Commercial Sample):
Support new feature/Performance/stability improvements/Boot KPIs (100%)/CTS/VTS/STS - Coverage (100%)
Post CS/ZBB: Bug Fixes, Security Fixes
PEC
12/07
FEC
01/03
CP1
CP2
CP3
CP4
阶段1[->DCV3]：主体功能交付完毕，不允许大的架构性变化
阶段2[DCV4->R06]：体验优化，接受部分Agile feature 合入（影响系统性能的，务必于R00之前完成支持PEC sign off）其他due date为R05.
阶段3[R07->R08]：AIMS issue bug fix, 非必要不进行任何新功能合入.

## Slide 19: SYNC+3.0 Vehicles Timeline
CDX707
UPV1
03/05
3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
2021 | 2022 | 2023 | 2024
U611 MCA
FEC
PEC
DCV
UPV0
03/30
UPV1
06/25
UPV2
10/25
PA
1/12
HB
2/21
2/8
8/11
9/5
02/28
UPV2
07/30
PEC
07/19
PA
08/18
FDJ
09/10
TT
09/26
PP
12/06
MP1
02/07
02/28
DCV
02/02
01/28
MP2
03/07
03/28
FEC
08/29
OKTB
04/04
04/25
05/15
U718
PEC/FEC
11/8
OK2B
9/23
DCV
3/20
FDJ
10/13
UPV0
08/10
UPV1
12/17
UPV2
06/21
PA
8/3
TT
2/12
PP
5/6
MP1
7/22
FDJ
DCV
08/31
10/17
Retrofit
HB
09/30
TT
02/01
02/15
PP
04/19
MP1
06/21
MP2
07/19
OKTB
08/08
GAS
FHEV
FDJ
05/11
07/01
PEC
12/07
FEC
01/03
VOCF
11/03
1st OTA
06/23 FCS
2nd OTA
TBD
U625MCA
FEC
10/19
PEC
9/21
DCV
2/8
FDJ
12/7
UPV0
03/30
UPV1
6/25
UPV2
10/25
U625 MY24
FEC
10/19
PEC
9/28
DCV
8/8
FDJ
5/26
PA
5/12
HB
02/28
MP2
07/17
OKTB
08/20
Pre TT
12/06
TT
01/16
MP1
06/19
EPT2
11/13
MP2
8/19
PP
04/16
MP2
07/17
OKTB
08/20
Pre TT
12/06
TT
01/16
MP1
06/19
PP
04/16