## Slide 1: SYNC+ 3.0 Critical Path: New/Modified IVI Platform & New UE/UI
China Accelerated SW Plan ---DCV Critical Path
FDJ
DCV
Group A UI Release
MRD
DCV Beta 30%
DCV0
DCV1 60%
45 weeks
Group A Features Coding based on UI
DCV Alpha
DCV Beta
Test
A Sample
Pre DV
Debug
B Sample
Critical DV
China Accelerated SW Plan ---PEC/J1 Critical Path
R00
95%
R04
100%
R05
R06
R07
R08
DCV1 60%
DCV
DCV MRD
4 weeks
5 weeks
9 weeks
(4+5)
9 weeks
R00 (4* iterated versions ) support PEC sign-off
95% Coding
(*Not including Agile features/late added content
** Phase4 takes 5* iterations within 5 months )
Features Code Completed 100% on R04,
R05 Iteration for TT MRD
AIMS Issue solve / Bug fix
R06 Iteration for PP MRD
17 weeks(4months)
13 weeks(3months)
8weeks(2months)
DCV
6 weeks
1st full Validation & Sign-off
PEC
FEC
6 weeks
2nd full Validation/Re-Sign off
TT
PP
AIMS Issue solve / Bug fix
R07 Iteration for J1
8 weeks(2months)
R08 reserved for OKTB when needed
Preserved
9 weeks
J1
Initial release for Pre DV
DCV Beta
30% Coding
Release Fundamental features for DCV vehicle testing
DCV1
60% Coding
16 weeks(4months)
10weeks(2.5months)
Group A Features Design
Display light up
Platform Arch design
PIPELINE Design
10weeks(2.5months)
OKTB
Platform Fundamental Functionalities(Wifi/Network/BT/Display etc BSP Drivers Coding)
2wks
REC Validation
1st round integration/test
Group B UI Release
Group C UI Release
Group D UI Release
2nd round integration/test
7 weeks
8 weeks
4 weeks
(3 PCB + 1 Assembly & Software)
4 weeks
5 weeks
What we are talking now!

## Slide 2: Phase 5 Vehicles Timeline
CDX707
CX788
UPV1
03/05
CDX747
TT
02/01
FEC
11/23
01/13
PEC
10/14
12/02
PP
04/06
OK2B
07/25
MP1
06/07
DCV
06/13
07/11
FDJ
01/07
02/11
UPV0
05/10
07/02
UPV1
08/16
09/13
UPV2
11/08
12/06
PA
12/08
01/12
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
2021 | 2022 | 2023 | 2024
MP2
07/05
U6XX MCA updated 11/07
TT
FEC
PEC
PP
09/18
OKTB
01/23
MP1
12/06
DCV
UPV0
03/30
UPV1
06/25
UPV2
09/24
10/25
PA
10/17
12/22
HB
12/07
06/13
U611N
U625C/U611C
Chicago
04/24
U6XX C
05/22
U6XX C
02/28
U6XX CAF 4
07/05
UPV2
07/30
PEC
06/13
PA
08/18
FDJ
09/10
TT
08/30
PP
10/24
MP1
02/01
DCV
02/02
01/28
MP2
03/01
FEC
07/25
OKTB
03/28
OK2B
11/06
MP2
10/09
MP1
06/12
PP
03/13
FEC
11/29
TT
12/12
PEC
11/01
UPV1
07/13
UPV2
10/26
FDJ
01/11
DCV
07/11
U718
FEC
04/18
PEC
03/07
OK2B
04/22
DCV
10/24
FDJ
04/26
UPV0
08/03
UPV1
11/02
UPV2
02/15
PA
02/23
MP2
04/08
TT
08/07
PP
10/23
MP1
03/11
P702 MCA
TT
PP
08/28
OKTB
01/15
MP1
11/27
DCV
FDJ
UPV0
06/16
UPV1
09/15
UPV2
12/22
PA
01/02
03/18
09/19
06/05
OKTB
FHEV 08/08
FEC
PEC
01/06
02/03
MP2
01/02
PA
10/27
CX771 Draft VPP
TT
PP
08/02
OKTB
TBD
MP1
09/27
DCV
FDJ
UPV0
12/03
UPV1
02/05
UPV2
05/06
PA
06/01
07/08
12/07
06/07
FEC
PEC
03/24
04/21
MP2
TBD
Timing to be adjusted
DCV
08/01
U625N
Chicago
FDJ

## Slide 3: U6XX Background & Recap
Program Late Content and Feature Cascaded with continuous change(not frozen yet), SYNC+ 3.0 IVI PDL initialized version cascaded until 09/01(near UPV2 09/28, process aligned until 08/E) with continuous change， ½ EC has been missed, 3rd EC started on 09-10(near UPV2 09/28). Global SIM Request IVI SW maturity follow < Software Maturity Progression >process(FDJ DCV Beta 2021/12/07 DI, DCV0 2022/04/01 PI).
Purpose of today’s meeting
Review key challenges and seek agreement
Key challenges
Due to the late PDL/requirement cascade and hero screen late released, HMI Group A UI sign off version release date can’t meet the critical 45wks per< SYNC+ 3.0 Critical Path > required, Need HMI bring this risk to program and set Checkpoints/regular meeting to track the HMI health chart. ---HMI/VI *DTG:10/28(Potential Delay Again)
Central stack & Display Chip shortage impact for DCV Alpha coding start and FDJ BB SW maturity --- PMT5 HW *DTG:10/30 Fisher TDR  YFVE will use PC as virtual screen supporting Android HMI coding until 27’ display ready on 2022/03/05. Done
Key Enablers to Make PEC/FEC Happen:
IVI test Bench Including BOM setup should be kicked off COB 10/14 --- PMT5/PM *DTG: 10/14, in process Done
EESE Dedicated 3 DCV vehicles requested for system level debug and calibration --- PM *DTG: 10/14 Frozen Request, Done
Set Checkpoint to regular review HMI Health Chart.---Program, VI, 11/05
ICA: Set up China unique FDJ and DCV milestone or Deviation for FDJ DCV Beta and DCV0. ---PM, in progress
PCA: Build SYNC+ PDL and Bom of Feature Cascade Process, to better follow GPDS3.3 Delivery Process. ---PMO,FDL, Done

## Slide 4: GPDS Delivery Health Chart VS U6XX Actual Delivery Status.
GPDS MCA Platform Timing
UPV0
14w
UPV1
13w
UPV2
14w
FDJ
10w
DCV
26w
PSC
GPDS Feature and SW Pocket Card
BOF Finalized
Feature List Aligned to PDL
SOBA
Feature/Function Spec Complete
HMI Health Chart Created
Group A UI
(K4+4W)
33w
Group B UI
(K5+4W)
26w
20w
Group C UI
(K6+4W)
3w-4w
Group D UI(FAA+4W)
Group E Animation (FAA-4W)
DCV Beta For FDJ BB
DCV1 For DCV MRD
China SYNC+ 3.0 Critical Path: New/Modified IVI Platform & New UE/UI
45w
Group A UI latest date
U6XX MCA Actual Story
UPV0
03/30
UPV1
06/25
UPV2
10/25
FDJ
12/7
DCV
06/13
DCV YB MRD
05/13
DCV EBB MRD
04/01
PSC
01/11
2021/05
Confirmed U6XX in Phase5 Scope
BOF Cascade started to involve China Team
2021/07/20
HMI KOTEI SOBA
2021/09/01
SYNC+ PDL Initialized Version released with continuously change
2021/0908 RFQ released to Package1/2/3
11/09
Group A UI
04/17
DCV Beta For FDJ BB
07/15
DCV1 For DCV MRD
China SYNC+ 3.0 Critical Path: New/Modified IVI Platform & New UE/UI
39w(6w has been compressed)
DCV
Proposed 08/16
Program Content/BOF cascade did not follow the GPDS3.3 Process.
HMI delivery plan did not follow the Global/Go Fast Health Chart.
How to guarantee SW maturity meet the Global Software Maturity Progression? ---Deviation needed.
SW Develop Team Compressed the initial over 4months delay to 2 months by OT work
Notes: 有功能增加；
音频架构有变化。

## Slide 5: Phase 5 Vehicles Info
SYNC+ 3.0 Phase5 Scope |  |  |  |  |  |  |  |  |  | 
Program | Nameplate | Manufacture | J1 | OKTB | EE Architecture | Centerstack Size | Cluster |  | TCU | ECG
CDX707 | Nautilus | CAF | GAS: 3/28/2023 2/1/2023 FHEV: 6/21/2023 | GAS: 3/28/2023 FHEV: 8/8/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
CX788 | Ford | CAF | 4/26/2023 | 6/21/2023 | FNV2 | 15.3 | 9.2, AR HUD | Landscape | Boundle5 | ECG2
CDX747 | Lincoln | BU | 6/12/2023 | 11/6/2023 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
U611 MCA | Aviator | CAF | 12/6/2023 | 1/23/2024 | FNV3 | 27 | 12.3，Standalone HUD | Landscape | Boundle6 | ECG2
U625MCA | Explorer | CAF | 12/6/2023 | 1/23/2024 | FNV3 | 27 | 12.3，Standalone HUD | Landscape | Boundle6 | ECG2
U718 | Navigator | BU | 3/11/2024 | 4/22/2024 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) |  | Landscape | Boundle6 | ECG2
P702 MCA | F-150 Raptor | BU | 11/27/2023 | 01/15/2024 | FNV3 | 12.0 | 12.4 | Landscape | Boundle6 | ECG2
CX771 | Mustang SUV |  |  |  | FNV2 |  |  |  |  | 
CDX748 | Lincoln | CAF | Diff. Battery: NCM: 8/28/2024 LFP:11/27/2024 | NCM: 10/30/2024 LFP:1/29/2025 | FNV3 | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) | 23.6(Pano-Non touch)*2&11.1(Controller-Touch) | Landscape | Boundle6 | ECG2

## Slide 6: U611 MCA SW Release Plan Proposal @1109
Display(27 TOUCH)
SW Release for REC
DCV Beta
04/17
DCV4
12/24
R00
02/24
R05
05/03
R06
07/18
R07 10/08
DCV0
06/15
DCV1
07/15
CDC AHU HW
B0 DV1
8/20
A1 Pre-DV
6/25
B1 DV2
11/20
Pre-DV
DV1
DV2
DCV Alpha
03/08
DCV Beta
04/08
DCV3
08/08
R00
02/10
Group A UI
Delivery 11/09
A
12/09
2021 | 2022 | 2023 | 2024
7/10-8/10
8/28-10/30
11/30-1/15
National Day
National Day
Spring Festival
Spring Festival
U611MCA
OK2B
1/23
MP1
12/06
PP
09/18
LS:09/04
FEC
05/22
U6XX C
TT
07/03
LR:06/12
PEC
04/24
U6XX C
UPV0
03/30
UPV1
06/25
UPV2
10/25
FDJ
12/7
DCV
06/13
HB
2/28
PDL Release
09/01
FIP 1EC 09/09
SW Release for CAF/FO
Vendor Integration
U611 27’ UX Release
DCV Beta
03/08
R05
04/18
R06
07/03
R07
09/15
Reserve R08 12/30
R08
12/15
R05
03/18
R06
06/03
R07
08/15
R08
11/15
A0 01/30
DCV Beta1
04/08
DCV Alpha
01/25
DCV0
05/08
DCV1
06/08
1
DCV2
07/08
DCV1
07/08
DCV0
06/08
R00
01/01
DCV4
11/10
DCV4
12/10
DCV2
08/08
DCV3
09/08
DCV Beta1
05/08
Following standard GPDS3.3 delivery process, DCV Beta S/W is for FDJ, DCV1 S/W is for DCV build. UE/UI Delivery by FDJ is already Very Late to Support FDJ & DCV Global Feature Maturity Requirement.
No SYNC+ sample needed for FDJ Hil test, PMT5/Program study the opportunity for FDJ BB & DCV EBB.---High Risk/impossible because of no HW&SW&HMI readiness. –Program/PMT5
Team Proposal: Use DCV Beta support AHU build for DCV MRD(04/M Ship, 05/15 MRD), Update SW to DCV1 by USB.
Need HW provide 27’’ display*30(TBC) before 01/10. AHU*30(TBC) before 11/30.---Xuan Leon, Zhang Bingqing
EMC
8/28-9/30
A0 3/20
Target 01/10
B0 7/10
U611 12.3’ UX Release(TBC)
4 months
2 months
SW coding based on virtual display
Light-up
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2
Group A+B UI
Sign off 09/19
C
10/17
D
10/30
E
11/21
B
12/15
DCV YB MRD
05/13
DCV EBB MRD
04/01
R04
02/10
R04
03/10
R00
03/24
2
3
Compress actions IVI team has taken/ considered:
<4 weeks compress, done>Using Group A delivery version starting Coding with risk of re-work. Control the change content within 20%.
<4 weeks compress, done> considering many features C/O CDX707, drop DCV Beta2 version, compress 4 weeks during DCV Beta to DCV0
<2 weeks compress, done> Compress REC DCV0,DCV1 validation time window from 2 wks to 1 wks by further OT.
To Be Updated
4
C/D
12/30
E
1/24
Multi Theme
02/28
Normal/Sport/ZEN C/O CDX764
New added Capable pending release
Notes: 有功能增加；
音频架构有变化。

## Slide 7: U625 MCA SW Release Plan Proposal @1109
Display(27 TOUCH)
SW Release for REC
DCV Beta
04/17
DCV4
12/24
R00
02/24
R05
05/03
R06
07/18
R07 10/08
DCV0
06/15
DCV1
07/15
CDC AHU HW
B0 DV1
8/20
A1 Pre-DV
6/25
B1 DV2
11/20
Pre-DV
DV1
DV2
DCV Alpha
03/08
DCV Beta
04/08
DCV3
08/08
R00
02/10
2021 | 2022 | 2023 | 2024
7/10-8/10
8/28-10/30
11/30-1/15
National Day
National Day
Spring Festival
Spring Festival
U611MCA
OK2B
1/23
MP1
12/06
PP
09/18
LS:09/04
FEC
05/22
U6XX C
TT
07/03
LR:06/12
PEC
04/24
U6XX C
UPV0
03/30
UPV1
06/25
UPV2
10/25
FDJ
12/7
DCV
06/13
HB
2/28
PDL Release
09/01
FIP 1EC 09/09
SW Release for CAF/FO
Vendor Integration
U625 27’ UX Release
DCV Beta
03/08
R05
04/18
R06
07/03
R07
09/15
Reserve R08 12/30
R08
12/15
R05
03/18
R06
06/03
R07
08/15
R08
11/15
A0 01/30
DCV Beta1
04/08
DCV Alpha
01/25
DCV0
05/08
DCV1
06/08
DCV2
07/08
DCV1
07/08
DCV0
06/08
R00
01/01
DCV4
11/10
DCV4
12/10
DCV2
08/08
DCV3
09/08
DCV Beta1
05/08
EMC
8/28-9/30
A0 3/20
Target 01/10
B0 7/10
U625 12.3’ UX Release (TBC)
4 months
2 months
SW coding based on virtual display
Light-up
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2
Group A+B UI
Sign off 09/19
C
10/17
D
10/30
E
11/21
DCV YB MRD
05/13
DCV EBB MRD
04/01
R04
02/10
R04
03/10
R00
03/24
Compress actions IVI team has taken/ considered:
<4 weeks compress, done>Using Group A delivery version starting Coding with risk of re-work. Control the change content within 20%.
<4 weeks compress, done> considering many features C/O CDX707, drop DCV Beta2 version, compress 4 weeks during DCV Beta to DCV0
<2 weeks compress, done> Compress REC DCV0,DCV1 validation time window from 2 wks to 1 wks by further OT.
To Be Updated
Following standard GPDS3.3 delivery process, DCV Beta S/W is for FDJ, DCV1 S/W is for DCV build. UE/UI Delivery by FDJ is already Very Late to Support FDJ & DCV Global Feature Maturity Requirement.
No SYNC+ sample needed for FDJ Hil test, PMT5/Program study the opportunity for FDJ BB & DCV EBB.---High Risk/impossible because of no HW&SW&HMI readiness. –Program/PMT5
Team Proposal: Use DCV Beta support AHU build for DCV MRD(04/M Ship, 05/15 MRD), Update SW to DCV1 by USB.
Need HW provide 27’’ display*30(TBC) before 01/10. AHU*30(TBC) before 11/30.---Xuan Leon, Zhang Bingqing
1
2
3
4
Group A UI
Delivery 12/07
A
12/25
1
B
01/10
C/D
01/24
2* Multi Theme
03/20
E
02/10
Smart surface change from 1.5 to 2.0(compared with 706).
Notes: 有功能增加；
音频架构有变化。

## Slide 8
Backup Materials

## Slide 9: U6XX Background & Recap
Program Late Content and Feature Cascaded with continuous change(not frozen yet), SYNC+ 3.0 IVI PDL initialized version cascaded until 09/01(near UPV2 09/28, process aligned until 08/E) with continuous change， ½ EC has been missed, 3rd EC started on 09-10(near UPV2 09/28). Global SIM Request IVI SW maturity follow < Software Maturity Progression >process(FDJ DCV Beta 2021/12/07 DI, DCV0 2022/04/01 PI).
Purpose of today’s meeting
Review key challenges and seek agreement
Key challenges
Due to the late PDL/requirement cascade and hero screen late released, HMI Group A UI sign off version release date can’t meet the critical 45wks per< SYNC+ 3.0 Critical Path > required, Need HMI bring this risk to program and set Checkpoints/regular meeting to track the HMI health chart. ---HMI/VI *DTG:10/28(Potential Delay Again)
Central stack & Display Chip shortage impact for DCV Alpha coding start and FDJ BB SW maturity --- PMT5 HW *DTG:10/30 Fisher TDR  YFVE will use PC as virtual screen supporting Android HMI coding until 27’ display ready on 2022/03/05. Done
Key Enablers to Make PEC/FEC Happen:
IVI test Bench Including BOM setup should be kicked off COB 10/14 --- PMT5/PM *DTG: 10/14, in process Done
EESE Dedicated 3 DCV vehicles requested for system level debug and calibration --- PM *DTG: 10/14 Frozen Request, Done
Set Checkpoint to regular review HMI Health Chart.---Program, VI, 11/05
ICA: Set up China unique FDJ and DCV milestone or Deviation for FDJ DCV Beta and DCV0. ---PM, in progress
PCA: Build SYNC+ PDL and Bom of Feature Cascade Process, to better follow GPDS3.3 Delivery Process. ---PMO,FDL, Done

## Slide 10: U6XX Handshake History
2021/05/01:SYNC+ System was involved in Feature Jira cascade process, got the first Jira sub-task on 05/07(UPV0 was missed). Continuously change and not frozen yet.
2021/06/02:< Phase5 SW Release Milestone_V2.8 0602> was released to team, 07/01 sign off Group A UI is the key enabler for SW coding start.
2021/06/09: HMI vendor onboard(Kotei), HMI asked the help for program team, request the MFL release ASAP.
2021/06/10: Based on the initialized Feature List, HMI handed up there would be large risk for FDJ and DCV.
2021/06/25: Draft HMI Grouping Plan released meeting the requirement by EESE. The pre-condition to deliver UE&UI assets before July 2nd is that these features will totally carryover from CD764 w/o UE&UI change.
2021/06/29-07/05: Baidu HMI Design blocked by RFQ release and Business strategy. All the HMI release plan would be updated based on frozen IVI SYNC+ MFL/PDL.
2021/09/01: SYNC+ PDL Initialized Version released.
2021/09/08: SYNC+ 3EC(1/2EC missed)RFQ released.
2021/09/17: EESE team asked again for the latest HMI plan.
2021/09/23: 4 months gap detected, EESE lead the meeting for HMI timing plan negotiation and concept clarification.
2021/09/30: HMI supported Baidu QA, aligned with Baidu about the UX strategy.
2021/10/15: YFVE feedback the draft SW integration timing based on HMI Group plan and FIP.
2021/10/19: IVI bring to Fisher TDR reviewing 6XX HMI timing and Chip shortage related issue.
2021/10/27: Baidu/YFVE feedbacked the EDT officially.
Program Content/BOF cascade did not follow the GPDS3.3 Process.
HMI delivery plan did not follow the Global/Go Fast Health Chart.
How to guarantee SW maturity meet the Global Software Maturity Progression? ---Deviation needed.

## Slide 11: U6XX MCA SW Release Plan @10/25
Display(12.3+27 TOUCH)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
DCV Beta
06/7
R00
12/24
R04
1/24
R05
04/19
R06
07/05
R07 9/30
DCV0
08/14
DCV1
9/14
CDC AHU HW
B0 DV1
8/20
A1 Pre-DV
6/25
B1 DV2
11/20
Pre-DV
DV1
DV2
DCV Alpha
4/30
DCV Beta
5/31
DCV3
10/10
R04
1/10
Group A UI
Sign off 1/10
Group B+C UI
Sign off 1/24
2021 | 2022 | 2023
7/10-8/10
8/28-10/30
11/30-1/15
National Day
National Day
Spring Festival
Spring Festival
U611MCA
OK2B
1/23
MP1
12/06
PP
09/18
LS:09/04
FEC
02/14
TT
07/03
LR:06/12
PEC
01/17
UPV0
03/16
UPV1
06/11
UPV2
9/28->10/25
FDJ
12/7
DCV
06/13
HB
2/28
PDL Release
09/01
FIP 1EC 09/09
SW Release for CAF/FO
Vendor Integration
U611 UX Release
DCV Beta
4/30
R05
04/05
R06
06/20
R07
09/15
Reserve R08 12/30
R08
12/15
R05
03/03
R06
05/20
R07
08/15
R08
11/15
A0 01/30
DCV Beta1
5/30
DCV Alpha
3/30
DCV0
6/30
DCV1
7/30
1
DCV2
08/30
DCV1
8/30
DCV0
7/30
R04
12/10
R00
11/10
R00
12/10
DCV2
9/30
DCV3
11/10
DCV Beta1
6/30
R04.1
1/10
R04
02/10
R04.1
02/24
Both U625MCA and U611MCA UE/UI Delivery (Group-A only) Timing Can’t Meet the Feature Software Maturity Requirement for FDJ and DCV(consider software design, coding and validation time).
Following standard GPDS3.3 delivery process, DCV Beta S/W is for FDJ, DCV1 S/W is for DCV build. UE/UI Delivery by FDJ is already Very Late to Support FDJ & DCV Global Feature Maturity Requirement.
Compress actions IVI team has taken/ considered:
<4 weeks compress, done> considering many features C/O CDX707 drop DCV Beta2 version, compress 4 weeks during DCV Beta to DCV0
Group A UI
Sign off 12/10
Group A UI
Sign off 12/30
EMC
8/28-9/30
A0 3/20
B0 7/10
U625 UX Release
6 months
4 months
SW coding based on virtual display
Light-up
Notes: 有功能增加；
音频架构有变化。

## Slide 12: CDX707 SW Release Plan @09/23
CDX707 VPP
Display(23.6+23.6,11.1 touch)
Vendor Integration
SW Release for CAF/FO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UPV1
03/05
UPV2
07/30
SW Release for REC
PEC1
06/13
PA
08/18
FDJ
08/20
09/10
TT
08/30
PP
10/24
MP1
02/01
DCV
02/02
01/28
ITV Test
A0 PCBA
01/25
CDC AHU HW
A1
06/15
B0
12/13
B1 DV2
05/10
Pre-DV
DV1
DV2
23.6 Pre-DV
03/22-06/09
23.6 DV
DCV Alpha4
06/23
DCV Beta
07/18
08/01
DCV Beta1
09/03
DCV0
10/20
DCV0.1
11/17
DCV1
12/15
DCV2
01/12
DCV3
02/23
R00
03/23
R01
04/20
R04
05/18
R05
06/15
R05.1
07/13
R05.2
08/10
R06
09/07
R06.1
10/19
R07
11/20
R08 for OKTB
01/15
DCV Alpha3
04/28
DCV Alpha4
05/26
DCV Beta
06/20
07/02
DCV Beta1
08/01
DCV0
09/15
DCV0.1
10/20
DCV1
11/17
DCV2
12/15
DCV3
01/12
R00
02/23
R01
03/23
R04
04/20
R05
05/18
R05.1
06/15
R05.2
07/13
R06
08/10
R06.1
09/07
R07
10/19
R08 for OKTB
12/15
Group A
03/15 sign-off UE
05/05 Stagger UI
05/19 sign-off UI
Group B
04/30 UE
06/02 stagger UI
06/16 sign-off UI
Group C 05/21 UE
08/17 UI
Group D
06/15 UE
09/15 UI
TBD
2021 | 2022 | 2023
09/13-10/15
12/17-03/15
05/15-06/15
Pro version released for REC, focus and lite test.
Pro version released for REC, full test.
11.1 EMC
09/30-10/30
12/05-12/11
National Day
National Day
Spring Festival
Spring Festival
Spring Festival
MP2
03/01
FEC1
07/25
OKTB
03/28
UX Release
FNVx Release
DCV0
11/03
DCV1
12/29
DCV2
01/26
DCV3
03/09
R01
05/04
R04
06/01
R05
06/29
R05.1
07/25
R00
04/06
R06
09/21
R07
12/04
R08 for OKTB
01/24
SOA Gateway
Wireless Interface Router
IVI Provisioning
Bezel Diagnostics(SOA related)
Diagnostic_ Analytic
CCS –Authorization
CCS – UFM/PTE
IP Pass Through Client
MMOTA –SYNC+
Purchase process
03/23-07/30
Net/Diagnostic full function 12/15 for DCV2
ITV P2 complete 07/18 07/11
R09 for OTA
04/28 TBD
PEC2
07/19
FEC2
08/29
Net/Diag develop~4.5months
Bug fix ~1.5m
ITV P1 Release for R04
04/15
Net/Diag Bug fix
For R00
01/30
Report Review 07/25 07/18
Vendor P1 test ~2.5 m
P2 Log Prepare ~2m
We are here
A2
09-03
EMC
12/17--02/02
OKTB
FHEV 08/08
HQX1.2.1 switch
2021/12-2022/05
Eng version internal release.

## Slide 13: Feature Clarification Source Complexity
Tech
Planning
ECDX
Manager
Review
Marketing
IVI SW PDL
Forum
Feature
Delivery
Leader
EESE IVI
SW & SYS
Feature
Cascade
Feature
Owner
Basic(ECU) Functions
(EESE IVI SW maintain)
Customer Facing
Features
(ECDX PMO maintain)
BOF Cascade Features
(FDL maintain)
IVI SW PDL
(ECDX PMO maintain)
IVI SW FIP
(EESE IVI SW
maintain)
Supplier Workload Ratio
ECU Functional SPEC Information
Feature Integrate Schedule
HMI Design
(UE & UI)
(EESE IVI SW maintain)
A
A
A
B
C
D
B

## Slide 14: U611 SW Draft Release Plan History
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2021 | 2022 | 2023
U611MCA
OK2B
1/23
MP1
12/06
FEC
02/24
TT
07/03
LR:06/12
PEC
01/17
UPV0
03/16
UPV1
06/11
UPV2
9/28->10/25
FDJ
12/3
DCV
06/13
HB
2/28
Display(12.3+27 TOUCH)
CDC AHU HW
B0 DV1
3/10
A1 Pre-DV
11/15
B1 DV2
8/20
Pre-DV
DV1
DV2
DV
12/10-02/21
03/21-05/21
9/20-11/01
EMC
HW Request Frozen
6/11
01/27
05/05
A0 08/01(TBC) for SW debug
DCV Beta
12/03
R00
8/15
R04
9/15
R05
4/13
R06
07/05
DCV0
03/13
DCV1
04/13
SW Release for Build
R07 9/30
IVI SW Proposal 0602 initial version according to 45wks critical path.
Display(12.3+27 TOUCH)
R04
12/30
R05
4/13
R06
07/05
R07 9/30
CDC AHU HW
B0 DV1
3/10
A1 Pre-DV
11/15
B1 DV2
8/20
Pre-DV
DV1
DV2
DV
12/10-02/21
03/21-05/21
9/20-11/01
EMC
HW Request Frozen
6/11
01/27
05/05
SW Release for Build
A0 08/01(TBC) for SW debug
Group A UI
07/01
Group B UI
09/04
Group C for 11/01
UX Release
Group D before FDJ
12/01
Group A UE
04/15
Group A UI
11/9
Group B/C UI
11/30
UX Release
IVI SW Proposal 0918 version: 4 months Gap for HMI Group A UI.
DCV Beta 4 months Gap for FDJ,
DCV1 3 months Gap for DCV.
Display(27 TOUCH)
CDC AHU HW
B0 DV1
8/20
A1 Pre-DV
6/25
B1 DV2
11/20
Pre-DV
7/10-08/10
DV1
08/28-10/30
DV2
11/30-1/15
DV
9/30
A0 1/30 for SW DEV.
EMC
08/28-09/30
A0 3/20
B0 7/10
SW Release for Build
UX Release
Group A UI
Sign off 1/10
Group B+C UI
Sign off 1/24
DCV Beta
06/7
R00
12/14
DCV0
08/14
DCV1
9/14
R04
1/24
R05
4/13
R06
07/05
R07 9/30
SW coding based on virtual display
DCV Beta
04/10
R00
11/24
DCV0
07/10
DCV1
8/10
IVI SW Proposal 1025 version: HMI schedule further delay 2 months, YFVE use virtual screen as development method
<Compress 4 weeks coding during DCV Beta to DCV0>
DCV Beta 6 months Gap for FDJ,
DCV1 4 months Gap for DCV.
Notes: 有功能增加；
音频架构有变化。

## Slide 15: U625 SW Draft Release Plan History
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2021 | 2022 | 2023
U611MCA
OK2B
1/23
MP1
12/06
FEC
02/24
TT
07/03
LR:06/12
PEC
01/17
UPV0
03/16
UPV1
06/11
UPV2
9/28->10/25
FDJ
12/3
DCV
06/13
HB
2/28
Display(12.3+27 TOUCH)
CDC AHU HW
B0 DV1
3/10
A1 Pre-DV
11/15
B1 DV2
8/20
Pre-DV
DV1
DV2
DV
12/10-02/21
03/21-05/21
9/20-11/01
EMC
HW Request Frozen
6/11
01/27
05/05
A0 08/01(TBC) for SW debug
DCV Beta
12/03
R00
8/15
R04
9/15
R05
4/13
R06
07/05
DCV0
03/13
DCV1
04/13
SW Release for Build
R07 9/30
Display(12.3+27 TOUCH)
R04
12/30
R05
4/13
R06
07/05
CDC AHU HW
B0 DV1
3/10
A1 Pre-DV
11/15
B1 DV2
8/20
Pre-DV
DV1
DV2
DV
12/10-02/21
03/21-05/21
9/20-11/01
EMC
HW Request Frozen
6/11
01/27
05/05
SW Release for Build
A0 08/01(TBC) for SW debug
Group A UI
07/01
Group B UI
09/04
Group C for 11/01
UX Release
Group D before FDJ
12/01
Group A UE
04/15
Group A UI
11/25
Group B /C UI
12/14
UX Release
IVI SW Proposal 0918 version: 5 months Gap for HMI Group A UI.
Compress actions IVI team has taken/consider:
<4 weeks compress> considering U611 lead, build DCV Beta version directly, DCV Alpha waived
DCV Beta
03/15
R00
11/24
DCV0
06/10
DCV1
7/10
UX Release
Display(27 TOUCH)
CDC AHU HW
B0 DV1
8/20
A1 Pre-DV
6/25
B1 DV2
11/20
Pre-DV
7/10-08/10
DV1
08/28-10/30
DV2
11/30-1/15
DV
9/30
A0 1/30 for SW DEV.
EMC
08/28-09/30
A0 3/20
B0 7/10
SW Release for Build
Group A UI
Sign off 12/10
Group B+C UI
Sign off 12/30
DCV Beta
06/7
R00
12/14
DCV0
08/14
DCV1
9/14
R04
1/24
R05
4/13
R06
07/05
R07 9/30
SW coding based on virtual display
IVI SW Proposal 1025 version: HMI schedule further delay 2 weeks, YFVE take virtual screen development method
Because of physical screen issue U611 and U625 share the same IVI SW schedule
IVI SW Proposal 0602 initial version according to 45wks critical path.
Notes: 有功能增加；
音频架构有变化。

## Slide 16: Software Maturity Progression Request