## Slide 1: U6XX IVI Timing and Enablers
Sept 29th , 2021

## Slide 2: U6XX Background & Recap
Program IVI PDL initialized version cascade delayed from UPV0(03/16) to 09/01(nearby UPV2 09/28)
Purpose of today’s meeting
Review key challenges and seek agreement
Key challenges
Due to the late PDL/requirement cascade, HMI Group A UI sign off version release date can’t meet the critical 45wks per< SYNC+ 3.0 Critical Path > required, Need HMI set Checkpoints/regular meeting to track the HMI health chart. ---HMI/VI *DTG:10/14
Central stack & Display Chip shortage impact for DCV Alpha coding start and FDJ BB SW maturity --- PMT5 HW *DTG:10/30
Key Enablers to Make PEC/FEC Happen:
IVI test Bench Including BOM setup should be kicked off COB 10/14 --- PMT5/PM *DTG: 10/14
Dedicated 3 DCV vehicles requested for system level debug and calibration --- PM *DTG: 10/14 Frozen Request
Set up China unique FDJ and DCV milestone. ---PM

## Slide 3: U611 MCA SW Release Plan @09/28
Display(12.3+27 TOUCH)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
DCV Beta
02/15
R00
11/24
R04
12/30
R05
04/19
R06
07/05
R07 9/30
DCV0
05/10
DCV1
6/10
CDC AHU HW
B0 DV1
3/10
A1 Pre-DV
11/15
B1 DV2
8/20
Pre-DV
DV1
DV2
DV
DCV Alpha
12/31
DCV Beta
1/31
DCV3
07/15
R04
12/15
Group A UI
Delivery 09/30
Sign off 11/09
Group B+C UI
Delivery 10/30
Sign off 11/30
2021 | 2022 | 2023
12/10-02/21
03/21-05/21
9/20-11/01
EMC
National Day
National Day
Spring Festival
Spring Festival
U611MCA
OK2B
1/23
MP1
12/06
PP
09/18
LS:09/04
FEC
02/24
TT
07/03
LR:06/12
PEC
01/17
UPV0
03/16
UPV1
06/11
UPV2
9/28
FDJ
12/3
DCV
06/13
HB
2/28
01/27
05/05
PDL Release
09/01
FIP 1EC 09/09
SW Release for CAF/FO
Vendor Integration
UX Release
DCV Beta
1/4
R05
04/05
R06
06/20
R07
09/15
Reserve R08 12/30
R08
12/15
R05
03/03
R06
05/20
R07
08/15
R08
11/15
A0 08/01(TBC) for SW debug
FDJ
TBD
DCV
TBD
DCV Beta1
1/31
DCV Alpha
11/30
DCV0
3//28
DCV1
4/25
1
DCV
Beta2
2//28
DCV2
06/05
DCV4
8/26
DCV1
5/23
DCV0
4/25
DCV4
9/26
R04
11/15
R00
09/30
R00
11/07
DCV2
07/05
DCV3
08/20
DCV Beta1
03/15
R04.1
12/15
R04
01/15
R04.1
01/30
EESE SW Timing Opportunities And Enablers:
HMI Delivery(Group-A/B/C/D) Can’t Delay Any Further. Set Checkpoints and regular HMI PAT meeting to guarantee the HMI qualified release.---Program, VI
IVI Counterparty/Bench Bom Release COB 10/14. IVI related key counterparty including AHU/27inch display and the related harness should be ready COB 10/30(High Risk!!). ---Program, EESE
Program Offers IVI S/W Team 3 DCV Vehicles For System Level Debug and calibration to make the PEC/FEC sign off happen. ---Program
To be Updated by HW Team
Compress actions IVI team has taken/ considered:
[4wks compress, Done] Use Group A UI Unsigned version to kick off coding(11/09 to 10/08) Utilize Ckp. to track risk assessment.
[2.5wks compress, Done] Compress the Group A coding time from 10 wks to ~7.5wks.
2
Notes: 有功能增加；
音频架构有变化。

## Slide 4: U625 MCA SW Release Plan @09/28
Display(12.3+27 TOUCH)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SW Release for REC
DCV Beta
5/30
R00
11/31
R04
12/31
R05
04/19
R06
07/05
R07 9/30
DCV0
8/24
DCV1
9/24
CDC AHU HW
B0 DV1
3/10
A1 Pre-DV
11/15
B1 DV2
8/20
Pre-DV
DV1
DV2
DCV Alpha
Waived
DCV Beta
05/15
DCV3
9/15
R04
1215
Group A UI
Sign off 12/20
Group B UI
Sign off 1/10
Group C for
Sign off 2/13
2021 | 2022 | 2023
12/10-02/21
03/21-05/21
9/20-11/01
National Day
National Day
Spring Festival
Spring Festival
U611MCA
OK2B
1/23
MP1
12/06
PP
09/18
LS:09/04
FEC
02/24
TT
07/03
LR:06/12
PEC
01/17
UPV0
03/16
UPV1
06/11
UPV2
9/28
FDJ
12/3
DCV
06/13
HB
2/28
HW Request Frozen
6/11
PDL Release
09/01
FIP 1EC 09/09
SW Release for CAF/FO
Vendor Integration
UX Release
DCV Beta
04/15
R05
04/05
R06
06/20
R07
09/15
Reserve R08 12/30
R08
12/15
R05
03/03
R06
05/20
R07
08/15
R08
11/15
A0 08/01(TBC) for SW debug
FDJ
TBD
DCV
TBD
DCV Beta1
5/15
DCV Alpha
Waived
DCV0
6//15
DCV1
7/15
DCV2
08/15
DCV1
8/15
DCV0
7/15
R04
11/15
R00
10/15
R00
11/15
DCV2
9/15
DCV3
10/15
DCV Beta1
6/15
To be Updated by HW Team
EESE SW Timing Opportunities And Enablers:
HMI Delivery(Group-A/B/C/D) Can’t Delay Any Further. Set Checkpoints and regular HMI PAT meeting to guarantee the HMI qualified release.---Program, VI
Program Offers IVI S/W Team 3 DCV Vehicles For System Level Debug and calibration to make the PEC/FEC sign off happen. ---Program
A
01/30
Light up
Compress actions IVI team has taken/ considered:
[4wks compress, Done] DCV Alpha waived suppose the SW dev environment can be C/O from U611.
1
Notes: 有功能增加；
音频架构有变化。

## Slide 5: SYNC+ 3.0 Critical Path: New/Modified IVI Platform & New UE/UI
China Accelerated SW Plan ---DCV Critical Path
FDJ
DCV
Group A UI Release
MRD
DCV Beta 30%
DCV0
DCV1 60%
45 weeks
Group A Features Coding based on UI
DCV Alpha
DCV Beta
Test
A Sample
Pre DV
Debug
B Sample
Critical DV
China Accelerated SW Plan ---PEC/J1 Critical Path
R00
95%
R04
100%
R05
R06
R07
R08
DCV1 60%
DCV
DCV MRD
4 weeks
5 weeks
9 weeks
(4+5)
9 weeks
R00 (4* iterated versions ) support PEC sign-off
95% Coding
(*Not including Agile features/late added content
** Phase4 takes 5* iterations within 5 months )
Features Code Completed 100% on R04,
R05 Iteration for TT MRD
AIMS Issue solve / Bug fix
R06 Iteration for PP MRD
17 weeks(4months)
13 weeks(3months)
8weeks(2months)
DCV
6 weeks
1st full Validation & Sign-off
PEC
FEC
6 weeks
2nd full Validation/Re-Sign off
TT
PP
AIMS Issue solve / Bug fix
R07 Iteration for J1
8 weeks(2months)
R08 reserved for OKTB when needed
Preserved
9 weeks
J1
Initial release for Pre DV
DCV Beta
30% Coding
Release Fundamental features for DCV vehicle testing
DCV1
60% Coding
16 weeks(4months)
10weeks(2.5months)
Features and HMI Design
Display light up
Platform Arch design
PIPELINE Design
10weeks(2.5months)
OKTB
Platform Fundamental Functionalities(Wifi/Network/BT/Display etc BSP Drivers Coding)
2wks
REC Validation
1st round integration/test
Group B UI Release
Group C UI Release
Group D UI Release
2nd round integration/test
7 weeks
8 weeks
4 weeks
(3 PCB + 1 Assembly & Software)
4 weeks
5 weeks
What we are talking now!