## FIP History
Version | Date | Contact | Change List
V0 | 2020-12-16 | James Chen | Provide the V0 version for vendors to input the SW release version.
V0 | 2020-12-16 | Huang Feng | Add a / b version information
V1.0 | 2020-12-17 | Huang Feng | Huang Feng Update FDL information based on FIP round1 meeting during 10:00-11:45 am.
V1.1 | 2020-12-21 | Zhou Jiajia | Update Pre-DV Req(Column AC) after discussion with Sherry Shang, James Chen.
V1.2 | 2020-12-22 | Huang Feng | Huang Feng Update FDL information based on FIP round3 meeting during 16:00-17:00 pm.
V1.3 | 2021-01-07 | Zhou Jiajia | Zhou Jiajia update FDL information and add comment based on FIP round3 meeting during 10:00-11:30 am.
V1.4 | 2021-01-11 | Huang Feng | Huang Feng Update FDL information based on FIP round5 meeting during 13:30-14:30 pm.
V1.5 | 2021-01-14 | Zhou Jiajia | Zhou Jiajia Update FDL information based on FIP round6 meeting during 10:00-11:00 am.
V1.6 | 2021-01-18 | Zhou Jiajia | Zhou Jiajia Update FDL information and release version(Parts of R10 plan ahead) based on FIP round7 meeting during 13:30-14:30 pm.
V1.7 | 2021-01-21 | Zhou Jiajia | Zhou Jiajia Update FDL information and release version(Parts of R12 plan ahead) based on FIP round8 meeting during 10:00-11:00 am.
V1.8 | 2021-01-25 | Zhou Jiajia | Zhou Jiajia Update FDL information and release version(Parts of R13/TBD plan ahead，Del column AF/AG) based on FIP round9 meeting during 10:00-11:00 am.
V1.9 | 2021-01-30 | Zhou Jiajia | Zhou Jiajia add the sheet“Summary” to show the feature distribution curve.
V2.0 | 2021-02-01 | Huang Feng | Huang Feng Update release version based on FIP V1.9 meeting during 16:00-17:30 pm.
V2.1 | 2021-02-03 | Zhou Jiajia | Update the FDL information for SYNC+_Z0020/SYNC+_Z0023/SYNC+_0128/SYNC+_0020/SYNC+_0068/SYNC+_0117/SYNC+_0118/SYNC+_0135/SYNC+_0136 based on CVPP regular meeting during 14:00-15:00.
V2.2 | 2021-03-09 | Chen Jiazu | Update the following features' FO, SYNC+_0010/SYNC+_0135/SYNC+_0152/SYNC+_0175/SYNC+_0134/SYNC+_0136/SYNC+_0145/SYNC+_0170/SYNC+_0194/SYNC+_0204/SYNC+_0205/SYNC+_0183/SYNC+_0159/SYNC+_0166/SYNC+_0203/SYNC+_0184/SYNC+_0206/SYNC+_0226/SYNC+_0240/SYNC+_Z0100/SYNC+_Z0101/SYNC+_Z0204/SYNC+_Z0059/SYNC+_Z0126/SYNC+_Z0002/SYNC+_Z0199/SYNC+_Z0007/SYNC+_Z0111/SYNC+_Z0017/SYNC+_0004/SYNC+_0008/SYNC+_0009/SYNC+_0016/SYNC+_0082/SYNC+_0247/SYNC+_Z0227/SYNC+_0120/SYNC+_0124/SYNC+_0125/SYNC+_0123/SYNC+_0131/SYNC+_0142/SYNC+_0141/SYNC+_0143/SYNC+_0149/SYNC+_0158/SYNC+_0160/SYNC+_0161/SYNC+_0162/SYNC+_0163/SYNC+_0164/SYNC+_0122/SYNC+_0171/SYNC+_0172/SYNC+_0173/SYNC+_0132/SYNC+_0165/SYNC+_0231/SYNC+_0234/SYNC+_0236/SYNC+_0238/SYNC+_0223/SYNC+_Z0128/SYNC+_Z0033/SYNC+_Z0038/SYNC+_Z0155/SYNC+_Z0020/SYNC+_Z0024/SYNC+_Z0023/SYNC+_Z0030/SYNC+_Z0041/SYNC+_Z0032
V2.3 | 2021-03-29 | Zhou Jiajia | Add column V/W/X for SW release version and plan Update FDL for "SYNC+_0159","SYNC+_0070"(Change from inhouse to Core service),"SYNC+_0077"(Change from inhouse to YFVE) Update comment for "SYNC+_0154","SYNC+_0156"
V2.4 | 2021-03-21 | Chen Jiazu | Update with 0324 Master Feature List. Update Porduct Suite: SYNC+_Z0227,SYNC+_Z0229,SYNC+_Z0230,SYNC+_Z0231,SYNC+_Z0232,SYNC+_Z0277,SYNC+_Z0278,SYNC+_Z0279,SYNC+_Z0280,SYNC+_Z0281,SYNC+_0223,SYNC+_0221,SYNC+_0222 Update Feature Group: SYNC+_0025，SYNC+_0027，SYNC+_0028，SYNC+_0029，SYNC+_0030，SYNC+_0032，SYNC+_0031，SYNC+_0241，SYNC+_0034，SYNC+_0035，SYNC+_0036，SYNC+_0037，SYNC+_0039，SYNC+_0040，SYNC+_0041，SYNC+_0042，SYNC+_0047，SYNC+_0048，SYNC+_0050，SYNC+_0049，SYNC+_0068，SYNC+_0070，SYNC+_0051，SYNC+_0074，SYNC+_0112，SYNC+_0141，SYNC+_0113，SYNC+_0114，SYNC+_0204，SYNC+_0154，SYNC+_0238，SYNC+_0115，SYNC+_0223，SYNC+_0221，SYNC+_0222，SYNC+_0227 Update Feature Name: SYNC+_0025，SYNC+_0028，SYNC+_0030，SYNC+_0032，SYNC+_0241，SYNC+_0034，SYNC+_0042，SYNC+_0047，SYNC+_0048，SYNC+_0050，SYNC+_0049，SYNC+_0068，SYNC+_0070，SYNC+_0082，SYNC+_0051，SYNC+_0095，SYNC+_0101，SYNC+_0098，SYNC+_0074，SYNC+_0110，SYNC+_0117，SYNC+_0118，SYNC+_0112，SYNC+_0141，SYNC+_0152，SYNC+_0113，SYNC+_0114，SYNC+_0203，SYNC+_0091，SYNC+_0240，SYNC+_Z0187，SYNC+_Z0197，SYNC+_0228 Update Feature Description: SYNC+_0025，SYNC+_0028，SYNC+_0029，SYNC+_0047，SYNC+_0049，SYNC+_0068，SYNC+_0082，SYNC+_0247，SYNC+_0051，SYNC+_0093，SYNC+_0089，SYNC+_0092，SYNC+_0098，SYNC+_0117，SYNC+_0119，SYNC+_0118，SYNC+_0124，SYNC+_0125，SYNC+_0129，SYNC+_0113，SYNC+_0114，SYNC+_0172 Update CDX707 column: SYNC+_0247，SYNC+_0118，SYNC+_0151，SYNC+_0158，SYNC+_0162，SYNC+_0156，SYNC+_0157，SYNC+_0153 Update CDX747 column: SYNC+_0247，SYNC+_0237，SYNC+_0110，SYNC+_0118，SYNC+_0141，SYNC+_0151，SYNC+_0158，SYNC+_0162，SYNC+_Z0240，SYNC+_0154，SYNC+_0156，SYNC+_0157，SYNC+_0153，SYNC+_Z0236，SYNC+_Z0238，SYNC+_Z0255，SYNC+_Z0055，SYNC+_Z0054 Delete: SYNC+_0024，SYNC+_0026，SYNC+_0243，SYNC+_0033，SYNC+_0038，SYNC+_0043，SYNC+_0244，SYNC+_0245，SYNC+_0246，SYNC+_0044，SYNC+_0242，SYNC+_0045，SYNC+_0046，SYNC+_0072，SYNC+_Z0082，SYNC+_Z0233，SYNC+_Z0184，SYNC+_Z0048，SYNC+_Z0049，SYNC+_Z0188，SYNC+_Z0189，SYNC+_Z0190，SYNC+_Z0191，SYNC+_Z0192，SYNC+_Z0193，SYNC+_Z0194，SYNC+_Z0195，SYNC+_Z0196，SYNC+_Z0198，SYNC+_Z0207 Add CX788 column. Add: SYNC+_0248，SYNC+_0249，SYNC+_0250，SYNC+_0251，SYNC+_0252，SYNC+_0253，SYNC+_0254，SYNC+_0255，SYNC+_0256，SYNC+_0257，SYNC+_0258，SYNC+_0259，SYNC+_0260，SYNC+_0263
V2.5 | 2021-04-14 | Zhou Jiajia | CX707 Release Plan update: Change SYNC+_0129（Child Restraint System） from R12(DCV3) to R10(DCV1). CX788 Feature scope update: "Y-study" for the feature ID: SYNC+_0156/SYNC+_0157/SYNC+_0115/SYNC+_0110/SYNC+_0135, "Y" for SYNC+_0196 “N” for SYNC+_Z0012 Add column "Z" to "AC" for CX788 release plan
V2.6 | 2021-04-14 | Chen Jiazu | Add SYNC+_0261 二排座椅控制 for U611 Add SYNC+_0265 V2I Lite for788
V2.7 | 2021-04-29 | Zhou Jiajia | Update CX788 FIP and HMI Dependency Plan.
V2.8 | 2021-05-08 | Zhou Jiajia | Update CX788 FIP(Column AC/AD will be updated accroding to the approved VPP)， change SYNC+_Z0028 intergration plan from R5 to R7 in CDX707/CX788, because of no HMI UX requirement about this feature.
V2.9 | 2021-05-10 | Chen Jiazu | Add Dev Spec for followin feature: SYNC+_0022,SYNC+_0256,SYNC+_0260,SYNC+_0253,SYNC+_0012,SYNC+_0015,SYNC+_0017,SYNC+_0018,SYNC+_0134,SYNC+_0095,SYNC+_0255,SYNC+_0165,SYNC+_Z0159~SYNC+_Z0177,SYNC+_0259,SYNC+_0248~SYNC+_0251，SYNC+_0020，SYNC+_0090，SYNC+_0091,SYNC+_0093,SYNC+_0252,SYNC+_0257,SYNC+_0258,SYNC+_0263,SYNC+_Z0056
v2.10 | 2021-05-18 | Chen Jiazu | Add Dev Spec for followin feature: SYNC+_Z0126,SYNC+_Z0038,SYNC+_Z0032,SYNC+_0221,SYNC+_0126,SYNC+_0127,SYNC+_0128,SYNC+_0163,SYNC+_0164
v2.11 | 2021-05-24 | Chen Jiazu | Add Dev Spec for following feature: SYNC+_0112,SYNC+_Z0092,SYNC+_0074
v2.12 | 2021-06-11 | Chen Jiazu | Add SYNC+_0266 Lancher - 3D Car Model with vehicle controls Update following features' FO: SYNC+_0139,SYNC+_0140,SYNC+_0153,SYNC+_Z0052,SYNC+_Z0069,SYNC+_Z0070,SYNC+_Z0077,SYNC+_Z0088 Delete the following feature from CDX707: SYNC+_Z0068 Adaptive Steering SYNC+_Z0078 Grade Assits SYNC+_Z0079 Hill Decent Control SYNC+_Z0080 Hill start assist SYNC+_Z0083 Lincoln Camera Shortcut key SYNC+_Z0084 Lincoln Drive Assist Shortcut key SYNC+_Z0095 Tow Haul SYNC+_Z0098 Trailer Sway SYNC+_0115 座舱内手机遥控 Project Aspire_Ultimate Remote Control SYNC+_0153 娱乐座舱Cabin On-Live （曾用名音乐派 Music Boom. Former name: JukeBox） SYNC+_0149 路书 (App -去兜风) Project Aspire_Route 66 / Tourist Mode (Education and Historical POIs)_CN (Route 66/Travel Book)
v2.13 | 2021-06-22 | Chen Jiazu | Update SYNC+_Z0101 Feature Name to ‘Ambient Lighting 128 Color’ Delete SYNC+_Z0100 Ambient Lighting - Breath Control (setting: on/off)
v2.14 | 2021-06-23 | Chen Jiazu
v2.15 | 2021-07-02 | Zhou Jiajia | CDX707 Change list: SYNC+_0123 保养及在线预约: On Hold SYNC+_0156 车载游戏:Y-OTA Updated CDX707 sw release plan: SYNC+_Z0032 SYNC+_Z0033 SYNC+_Z0039 SYNC+_Z0041 SYNC+_Z0043 SYNC+_Z0054 SYNC+_Z0101 SYNC+_0138 SYNC+_0145 SYNC+_0151 SYNC+_0157 SYNC+_0266 Add CX747 SW Integration Plan in Column AD-AF.
v2.16 | 2021-07-05 | Zhou Jiajia | Updated CDX707 Autosar related feature integration plan with Zheng Wei, Huang Feng. Align CDX747 Plan with vendors and HMI team.
v2.17 | 2021-07-13 | Chen Jiazu | Add Dev Spec for: SYNC+_0122 SYNC+_Z0045 Fob Free Entry and Ignition (NFC) Update Dev Spec for: SYNC+_0098，SYNC+_Z0068，SYNC+_Z0075,SYNC+_Z0076,SYNC+_Z0077,SYNC+_Z0091,SYNC+_Z0093,SYNC+_Z0094,SYNC+_Z0096,SYNC+_Z0097,SYNC+_Z0078,SYNC+_Z0079,SYNC+_Z0080,SYNC+_Z0095,SYNC+_Z0098,SYNC+_Z0178,SYNC+_Z0180，SYNC+_Z0181，SYNC+_Z0182，SYNC+_Z0183，SYNC+_Z0185，SYNC+_Z0186，SYNC+_Z0187，SYNC+_Z0197，SYNC+_Z0200，SYNC+_Z0201，SYNC+_Z0202，SYNC+_Z0203，SYNC+_Z0204，SYNC+_Z0205，SYNC+_Z0206，SYNC+_Z0208，SYNC+_Z0209，SYNC+_Z0210，SYNC+_Z0211，SYNC+_Z0212，SYNC+_Z0213，SYNC+_Z0214，SYNC+_Z0215，SYNC+_Z0216，SYNC+_Z0217，SYNC+_Z0227,SYNC+_Z0229,SYNC+_Z0231,Blind Spot Information System (BLIS) (CDX746/7),Perimeter Anti-Theft Alarm (CDX746/7) Add Heated Steering Wheel (CDX746/7) Passenger Airbag Deactivation (CDX746/7) Seat Temperature Control (CDX746/7) Power Liftgate (CDX746/7)
v2.18 | 2021-07-15 | Chen Jiazu | SYNC+_0042 update FDL to Ford_InHouse Delete SYNC+_0113,SYNC+_0114,SYNC+_0167,SYNC+_Z0027,SYNC+_Z0025,SYNC+_Z0046,SYNC+_Z0071,SYNC+_Z0072,SYNC+_Z0073,SYNC+_Z0074,SYNC+_Z0087,SYNC+_Z0200,SYNC+_Z0203,SYNC+_Z0205
V2.19 | 2021-08-04 | Chen Jiazu | Remove SYNC+_Z0057 FNOS (Phase5 use AutoSar) Add VSEM ID for following item:SYNC+_0073,SYNC+_0090,SYNC+_0106,SYNC+_0112,SYNC+_0132,SYNC+_0134,SYNC+_Z0075,SYNC+_Z0114,SYNC+_Z0281 Remove VSEM ID for following items:SYNC+_Z0212 Add following feature:SYNC+_0267,SYNC+_0269,SYNC+_0270,SYNC+_0271,SYNC+_0272,SYNC+_0273,SYNC+_0275,SYNC+_0276,SYNC+_0277,SYNC+_0278,SYNC+_0279,SYNC+_0280,SYNC+_0281,SYNC+_0282,SYNC+_0283,SYNC+_0284,SYNC+_Z0282,SYNC+_Z0283,SYNC+_Z0284,SYNC+_Z0285,SYNC+_Z0286,SYNC+_Z0287,SYNC+_Z0288,SYNC+_Z0289,SYNC+_Z0290,SYNC+_Z0291,SYNC+_Z0292,SYNC+_Z0293,SYNC+_Z0294,SYNC+_Z0295,SYNC+_Z0296,SYNC+_Z0297 Update Following items' Product Suite:SYNC+_0234,SYNC+_Z0240,SYNC+_Z0244 Update Following items' Feature Group:SYNC+_0221 Update Following items' feature name: -SYNC+_0221 'CAN/USB 升级' --> 'CAN 升级' -SYNC+_0011 'FM/AM收音机 AM/FM Radio' --> ' FM/AM收音机 AM/FM Radio （Anteena Based天线接收）' -SYNC+_0042 '语音助手2.0 VPA 2.0 (融合贯通生态的智能化的语音助手）' --> '语音助手1.5/2.0 VPA 1.5/2.0 (融合贯通生态的智能化的语音助手）' -SYNC+_0110 '后排乘客数字体验 2nd Row Digital Experiences including Cabin On-live (Jukebox)' --> '舱内娱乐Cabin On-live 1.0 ' -SYNC+_0156 '车载游戏 Project Aspire_In-Vehcle Gaming (Gaming Mode)' --> '舱内娱乐Carbin on live 2.0' -SYNC+_0157 '车机应用市场Project Aspire_Marketplace / Apps Anywhere' --> '车机应用商店Apps Anywhere(SYNC+)' -SYNC+_0158 'Lidget 2.0' --> '车载游览器/浏览器应用Project Aspire_Streaming Web / Applications' -SYNC+_0159 '壁纸 Project Aspire_Dash Backgrounds (Dual 23.6+11.1)' --> '壁纸 Project Aspire_Dash Backgrounds (Dual 23.6+11.1/or 27")' -SYNC+_0166 '基于云端的用户档案Project Aspire_Personal Portable Profiles' --> '基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP)' -SYNC+_0249 '两字拒识 (降低误识率采取的策略)' --> '取消两字拒识 (降低误识率采取的策略)' -SYNC+_0265 '车路协同 V2I Lite (Production)' --> '车路协同 4G V2I Lite (Production)' -SYNC+_0090 '360 摄像头图像 360 Camera Image' --> ’360 摄像头图像 360 Camera Image 1.0‘ Update Project Info for CX788
V2.19 | 2021-08-06 | Zhou Jiajia | Update CDX707 SYNC+_0269 天气,SYNC+_Z0282 车机管家 SW delivery plan. Update 747 SW release plan for the features with confirmed feature develop leader
v2.20 | 2021-08-14 | Chen Jiazu | Check with BOF and review with AFO to do the following modification: Add following feature for CDX707: SYNC+_Z0247,SYNC+_Z0289，F002216/A Add following feature for CDX707 TBD: SYNC+_Z0258,SYNC+_Z0244,SYNC+_Z0257,SYNC+_Z0241,SYNC+_Z0295,SYNC+_Z0287,SYNC+_Z0292,SYNC+_Z0297,SYNC+_Z0097，SYNC+_Z0246，F000810 Add VSEM ID F000903 to SYNC+_Z0227 F000064 to SYNC+_0170 F000908 to SYNC+_Z0091 F001430 to SYNC+_0101
v2.21 | 2021-08-15 | Zhou Jiajia | Update the SW release plan for the following Feature in CDX707. SYNC+_0073,SYNC+_0089,SYNC+_0091,SYNC+_0098,SYNC+_0134,SYNC+_Z0246,SYNC+_Z0097 Book the SW release version for the following feature: VESM ID F002216/A VESM ID F000564 FIP ID SYNC+_Z0289
v2.22 | 2021-08-18 | Chen Jiazu | Check with BOF and review with AFO to do the following modification: Update SYNC+_0170 description Update SYNC+_0170 develop rating (Baidu 100%->80, Core Service 0% ->20%) Add Dev Spec Lincoln Embrace_v2.2.2_CDX707_updated.pdf to SYNC+_0170 Update SYNC+_0170 FO Wu, Bella (Y.) <YWU150@ford.com> -> Chen, Huizhen (H.) <hchen188@ford.com> Add FO to SYNC+_Z0289 Wang, Vincent (X.) <xwang151@ford.com> Add description for SYNC+_Z0289 Add new feature F000800 Heated Mirror Add VSEM ID F000910\F000911 to SYNC+_Z0075 Cruise Control Type Update SYNC+_Z0075 feature name 'Cruise control- Type (Adaptive, intelligent, normal), tolerance' -->'Cruise Control Setting' Change SYNC+_Z0097 TSR CDX707 project into 'N' -->'Y' Add description for SYNC+Z0097 Add FO Xu, Xi Hai (X.) <xxu61@ford.com> to F002216/A Add Feature Description to F002216/A Add Feature Developer Leader information for F002216/A (Core_Service 90%, HW_Tier1 10%) Add FO Zhou, Travis (C.X.) <czhou17@ford.com> to SYNC+_Z0241 Update SYNC+_0134 Dev Spec Digital Scent PRD - for CDX707C 20210318.doc --> Digital Scent PRD - for CDX707C 20210714.doc Update SYNC+_Z0058 Dev Spec ES-H1BT-1A278-AA-V6.5_DRAFT.docx --> ES-H1BT-1A278-AA-V7.0.pdf Update SYNC+_0165 Enhanced_Memory_With_Soft_Button_Feature_Level_Specification_v1.2_Sep_27, 2020.docx -->Enhanced_Memory_With_Soft_Button_Feature_Level_Specification_v1.3_Aug_13, 2021.docx Add FO for Liu, Hongxin (H.) <HLIU162@ford.com> for F000564 Add description for F000564 Update SYNC+_0098 FO info Zhou, Wu (W.) <wzhou44@ford.com> -->Liu, Hongxin (H.) <HLIU162@ford.com> Add description for SYNC+_Z0281 Lane Centering Assist Add Dev Spec for SYNC+_Z0281 Lane Centering Assist Add description for SYNC+_Z0091 Pre Collision Assist Update SYNC+_0074 Li, Xin (X.) <xli268@ford.com> --> Update SYNC+_0101 FO Zhou, Wu (W.) <wzhou44@ford.com> -->Liu, Hongxin (H.) <HLIU162@ford.com> Update SYNC+_0101 Feature Description, add Dev Spec Add VSEM ID F002054 for SYNC+_Z0279 Add description for SYNC+_Z0279
v2.23 | 2021-08-19 | Chen Jiazu | Check with BOF and review with AFO to do the following modification: Add VSEM ID F000016/E to SYNC+_Z0070 Add VSEM ID F000123 to SYNC+_Z0176 Add VSEM ID F000162 to SYNC+_Z0212 Add SYNC+_Z0293 Power Liftgate Soft switch to CDX707 project scope Add VSEM ID F00158 to SYNC+_Z0047 Multi contour seat Add SYNC+_Z0287 First Row Seat Position Control to CDX707 project scope Add description & FO for SYNC+_Z0287 First Row Seat Position Control Update FO for SYNC+_Z0047 Li, Xuedong (X.) <XLI244@ford.com> -->Du, Hao (H.) <HDU9@ford.com> Add FO for SYNC+_Z0297 Add VSEM ID F003518 for SYNC+_Z0167 Front Row Seat Heated Add VSEM ID F003518 for SYNC+_Z0168 Front Seat Vent Update FO for SYNC+_Z0047 Yao, Frank (F.) <FYAO2@ford.com>/DongYa --> Du, Hao (H.) <HDU9@ford.com> Update FO for SYNC+_Z0176 Yan Yao, Frank (F.) <FYAO2@ford.com>/DongYa -->Yan, Sophie (C.) <cyan10@ford.com> Add Product Suite name 'Vehicle Control 车辆控制' to SYNC+_Z0247 Add Feature Group name 'Climate Control 空调控制' to SYNC+_Z0247 Add FO and Description for SYNC+_Z0247 Heated Backlight (climate) Add VSEM ID F001006 to SYNC+_Z0181 Light Setting-daytime lights Update FO for SYNC+_Z0181,SYNC+_Z0180 ,SYNC+_Z0178 Li, Xuedong (X.) <XLI244@ford.com> --> Zhou, Travis (C.X.) <czhou17@ford.com> Add VSEM ID F001027 to SYNC+_Z0178 Light Setting-Adaptive headlamps Add VSEM ID F000139 to SYNC+_Z0216 Windows (remote open/close) Update FO for SYNC+_Z0216 Li, Xuedong (X.) <XLI244@ford.com> -->Li, Shiyuan (S.) <sli163@ford.com> Add VSEM ID F000400 to SYNC+_Z0213 Remote start Update FO for SYNC+_Z0216 Lin, Shawn (X.) <xlin17@ford.com> --> Li, Shiyuan (S.) <sli163@ford.com> Delet the following feature from CDX707 project scope SYNC+_Z0244,SYNC+_Z0258,SYNC+_Z0257
v2.23 | 2021-08-20 | Zhou Jiajia | Update the SW plan for the 707 feature item: SYNC+_Z0247 SYNC+_Z0047 SYNC+_Z0297
v2.24 | 2021-08-26 | Zhou Jiajia | Update F000171,change 707 to Yes Update F000810 CDX707 update to Yes,and CX747 update to C/O Update SYNC+_Z0293，Update F0000162->F0000165 Add F003074/F000121/F000189/F000864/F000604/F003413/F003414/F003370/F003415/F001047 Add F000178 for U611 Update F000810 time plan&Fo JJin17 Update the SW plan for the 707 feature item: 1. Map related feature full function ready with UI COB DCV1. SYNC+_0002,SYNC+_0003,SYNC+_0006,SYNC+_0007,SYNC+_0239 2.Suixinting, Aqiyi full function ready with UI COB DCV1. SYNC+_0018,SYNC+_0020 3. Welcome/Farewell Animation should be ready COB DCV0.1. SYNC+_0194 4. Multi theme release plan change to DCV3(pending Studio/UI plan). SYNC+_0205 5. Update the customer feedback/Vehicle to home/Account etc. to DCV1(aligned with Baidu, YFVE). SYNC+_0125，SYNC+_0160/SYNC+_0161,SYNC+_0164，SYNC+_0172，SYNC+_0173，SYNC+_0106，SYNC+_0128,SYNC+_0010
v2.25 | 2021-08-31 | Chen Jiazu | Update SYNC+_Z0240 project info add CDX707,747 & U611 Add following feature for CDX747: F000818,F005350,F003410,F003411,F000864,F003074 Update SYNC+_Z0289 TPMS CDX747 project scope New-->C/O Change N to C/O for CDX747 about F002216/A F000122 change New to C/O for CDX747 F000913/C change N to C/O for CDX747 F000800 change idle to C/O for CDX747 F000760 change new to CO for CDX747 F000171 change new to CO for CDX747 Add U625 MCA project info

## Feature Implementation Plan
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 34 | 35 | 36 | 37 | 38
New Feature ID | VSEM ID | FNA JIRA Summary | Feature_Product_Suite | Feature_Group | Feature_Name | Feature_Description | Lead Team | Local Feature Owner | Global Feature Owner | UX Lead | Dev_Spec | Feature Development Leader | HW_Tier 1 | SW_Tier 1 | Ford IVI In-House | Core Service Provider | Phase5 | CDX707 | CDX747 | CX788 | U611MCA_RFQ | Change Level | Change Description | Local Feature Owner | Global Feature Owner |  | U625 MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner |  | 1st - phase # | Pre-DV Req | CDX707 HW-Tier1 Engineering Release | Release Version in GPDS | Original Release Date to REC(03/15 Ux Release) | Original Release Date to FO/CAF(2weeks) | CDX747 Release Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | HMI Group | CX788 HW-Tier1 Engineering Release | Release Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks)
SYNC+_Z0283 |  |  | System Function 系统功能 | Basic Feature 基础功能 | 部分界面中英文显示 | 提供部分页面的英文显示用于支持北美工厂生产的下线测试。 | EESE | James, Chen |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y-1st | Y-1st | C/O | N | C/O |  |  | James, Chen |  |  | Y | C/O |  | James, Chen |  |  | Phase5 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_Z0284 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Funtion Safety | 需要支持功能安全相关的实现（包含仪表部分） | EESE | Ding,Dean |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y-1st | Y-1st | C/O | Y | C/O |  |  | Ding,Dean |  |  | Y | C/O |  | Ding,Dean |  |  | Phase5 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R10 | DCV2 | 2022-05-30 | 2022-06-15
NewAdd3 |  |  | A# Navigation 地图导航 | Advance Map Function高级地图功能 | ADAS Map |  | EESE | Victor Cui |  |  |  | SW_Tier1 | 0% | 90% | 0% | 10% | Y | Y | C/O | Y | C/O |  |  | Victor Cui |  |  | Y | C/O |  | Victor Cui |  |  | Phase 2 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
NewAdd4 | F000781/F | CarPlay_via_Wi-Fi: 03 UPV0: MY24 CDX746/747 | System Function 系统功能 | Basic Feature 基础功能 | Carplay | 需要支持无线Carplay | EESE |  |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | N | N | N | N | N | [5 empty] | N | N |  |  |  |  | Phase5 | No | - | - | - | - | - | - | - |  | - | - | - | -
NewAdd5 |  |  | System Function 系统功能 | HMI人机交互 | Launcher UI 主页UI |  | HMI |  |  |  |  | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y | C/O | Y | Major | [5 empty] | Y | Major | New HMI layout and UE for 12.3'+27' Display |  |  |  | Phase 1 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R4 | DCV Alpha | 2021-11-25 | -
NewAdd6 |  |  | System Function 系统功能 | HMI人机交互 | System UI 系统UI |  | HMI | Luisa, Liu |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | Major |  |  | Luisa, Liu |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | Luisa, Liu |  |  | Phase 1 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R4 | DCV Alpha | 2021-11-25 | -
SYNC+_0001 | F000218/Q | Navigation Systems (CDX746/7) | A# Navigation 地图导航 | 1# Navigation - Basic Function 基础导航功能 | 地图基础版（见《IOV-地图功能list) Foundamental version of Map | 见《IOV-地图功能list)。 支持地图包更新MOTA。 POI检索、地点收藏 POI search & store destinations 3D地图 3D Map 首页地图 Launcher Map 地图显示的夜间/白天模式 Night/Day Mode 实时交通播报 Real-time Traffic Broadcast 惯性导航 Inertial Navigation 超速提醒 Reminder of over speed 路线雷达 radar detection in routes 限行提醒 Reminder of traffic control rules | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> | Deaibes, William (W.) |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 20% | 80% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0002 |  |  | A# Navigation 地图导航 | 1# Navigation - Basic Function 基础导航功能 | 开始导航倒计时/导航结束卡片 Starting/Ending Count Down |  | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0003 |  |  | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 个性化底图-4S店POI显示 4S Dealer POI on Map | 福特品牌显示福特标，林肯品牌显示林肯标，野马显示野马标 | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0004 |  |  | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 本地危险事件上报及播报 LHI (Local Hazard Information) | 危险事件上报及播报 | ECDX | Lin, Shawn (X.) <xlin17@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Phase 2 | No | R7 | R7(DCV Beta2) | 2021-09-15 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0005 |  |  | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 电子地平线（电子视野）EH - Electronical Horizon | TSR Fusion/ADAS MAP | EESE | Li, Cindy (Y.) <yli316@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | N | N | N | N | N |  |  | Li, Cindy (Y.) <yli316@ford.com> |  |  | N | N |  | Li, Cindy (Y.) <yli316@ford.com> |  |  | Phase 2 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0006 |  |  | A# Navigation 地图导航 | 3# Navigation - Team Travel 组队出行 | 组队出行 Team Travel | 分享地址，支持Ford/Lincoln 车型间 语音对讲 | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase 1 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0007 |  |  | A# Navigation 地图导航 | 4# POI Sharing/Receiving 地址分享 地址分享 | 微信地址分享 WeChat Send To Car | 微信中收到的地址可以长按选择百度地图，地址会同步给相同百度地图账号的车机端。首次需微信扫描车机二维码，关联账号 （又被叫做：微信互联） | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0008 |  |  | A# Navigation 地图导航 | 4# POI Sharing/Receiving 地址分享 地址分享 | 福特派/林肯之道地址分享 FordPass/LincolnWay Send to car | Send to car--把用户在FordPass 内置的地图查询的POI发送到车机 Send POI from smartphone APP to vehicle | ECDX | Shi, Stella (J.) <jshi32@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  |  | Phase 1 | No | R7 | R7(DCV Beta2) | 2021-09-15 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0010 |  |  | A# Navigation 地图导航 | 5# AR Navigation AR 导航 | AR 导航 AR Navigation | AR/专业地图切换AR/2D/Normal View Switch 终点目的地Destination Hint 道路吸附指引（主动）Road Guidance Arrow AR导航自动切换路线Road Guidance Arrow 语音指令Road Guidance Arrow 车道线偏离提醒Road Guidance Arrow 全览小地图Minimap overview 交通标志物识别TSR（Traffic Sign Recognition） | EESE | Ding, Sunny (X.) <XDING13@ford.com> |  |  |  | SW_Tier1 | 30% | 70% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Ding, Sunny (X.) <XDING13@ford.com> |  |  | N | N |  | Ding, Sunny (X.) <XDING13@ford.com> |  |  | Phase 4 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | R00 | 2022-09-01 | 2022-09-15 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0011 | F000349 | Tuner AM/FM/HD (CDX746/7) | B# Multimedia 多媒体 | 1# Radio 电台/收音机 | FM/AM收音机 AM/FM Radio （Anteena Based天线接收） | 收音机 radio-基本控制(上一个/下一个) foundamental control 收音机 radio-输入频段 channel input 收音机 radio-启动/停止收音机 turn on/off 收音机 radio-手动调台 manual tuning 收音机 radio-收藏列表 collections； Baidu: 自带的随声听App音乐是具有收藏列表的。Baidu需要design 收藏列表的HMI，配合Tier1实现该功能。 收音机 radio-更新电台列表(扫描及更新）update channels 收音机 radio-FM2 相关的菜单及功能 | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Murry, Tyrone (T.D.) |  | AMFM Tuner of Standalone AHU SPSS v1.8.pdf Auto Store_AM FM SPSS.pdf CD539C519D568_HMI_收音机_V1.0_20180912.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Phase 1 | Yes | R4 | R4(DCV Alpha4) | 2021-06-23 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R4 | DCV Alpha | 2021-11-25 | -
SYNC+_0012 |  |  | B# Multimedia 多媒体 | 1# Radio 电台/收音机 | 在线收音机/电台 Online Radio 资源提供方：蜻蜓FM | 资源能力提升. 资源涵盖不受传统radio 的地域限制。支持节目名称搜索，和收藏。 资源提供方：蜻蜓FM。 取决于电台是否做了online radio (有单独的license, 涵盖在phase 4 license 里面) Enhanced Online Radio (resource: 蜻蜓FM - 公版). with more radio programs without geograph constrains. Support voice command of "open online Radio" " Previouse one" " Next one" " Save". Availible for Phase 4 programs. Currently booked on CD542;U554;U725:P702;CX727. Other programs will need to book application cost if have display size differences. Attention: Keep pay attention to customer feedback and see opportunity of replace Traditional FM/AM using it. Things been called out by team - Data Consumption & Support 流量影响 - Online Radio's Resources & UE Improvement | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Online Radio APIM PRD v1.0 Feb 8, 2021.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Phase 4 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0109 |  |  | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | IVI 驾驶员状态监控和报警 IVI Driver Status Monitor & Alert (Fatigue, Distraction, Dangers Behaviour) |  | EESE | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  |  | FaceID with DSMC Function Specification_V8 _20201215.pdf | SW_Tier1 | 20% | 80% | 0% | 0% | Y | N | New | Y | N |  |  | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  |  | N | N |  | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0013 | F000345/K | Handsfree Phone (CDX746/7) | B# Multimedia 多媒体 | 2# Bluetooh Phone 蓝牙电话 | 蓝牙电话 Bluetooh Phone | 接听挂断；通话记录 records；拨号 dial；通讯录搜索；通讯录 contacts；同步通讯录和通话记录 sync contacts& records；请勿打扰 DO NOT IDSTURB | EESE | Xu, Amy (X.) <xyafei@ford.com> | Balakrishnan, Sabarish (S.) |  | BT Connectivity APIM SPSS v3.0 Feb 14, 2019.pdf BT Connectivity APIM Imp Guide v3.0 Feb 14, 2019.xlsx Phase5 Bt多路电话--PRD.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | Y |  |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0014 |  |  | B# Multimedia 多媒体 | 3# Music 音乐 | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) | 增加一个蓝牙模块，用来链接蓝牙耳机。 场景： 主驾听音乐（vehicle speaker); 副驾可连接自己的蓝牙耳机， 在双开模式下选择不同音乐资源来听 （支持在线音乐合本地音乐；不支持FM/AM;和蓝牙音乐） | EESE | Xu, Amy (X.) <xyafei@ford.com> |  |  | Phase5 副屏蓝牙--PRD.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | N | C/O |  |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | Phase 4 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_0015 | F000379/G | Core Media Player (CDX746/7) | B# Multimedia 多媒体 | 3# Music 音乐 | 本地音乐-MTP音乐 MTP music/USB音乐 USB music/蓝牙音乐 BT music | MTP (Media Tranfer Protocol)，可以本地外接音乐设备如iPod, 手机 | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Ahmed, Basheer (B.) |  | Media Player APIM SPSS v1.15 Jul 1, 2017.pdf Media Player APIM Imp Guide v1.15.1 Jul 1, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Y |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0016 |  |  | B# Multimedia 多媒体 | 3# Music 音乐 | 随心听- Ximalaya 2.0 | 允许用户登录自己账户 Suixinting: Ximalaya allow user login and enjoy more paid audio resources | ECDX | Shi, Stella (J.) <jshi32@ford.com> |  |  | SW | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  |  | Phase 4 | No | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0017 |  |  | B# Multimedia 多媒体 | 3# Music 音乐 | 随心听- 音乐/新闻/有声书 (QQ 音乐-支持QQ 音乐账号登陆；喜马拉雅免费资源集成） | 可以基于账号及喜好记忆进行主动推荐 Audio book/News/Music recommended according to account & preference | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Online Music APIM PRD v1.0 Feb 8, 2021.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0018 |  |  | B# Multimedia 多媒体 | 3# Music 音乐 | 随心听-QQ 音乐2.0 Suixinting: QQ Music 2.0 | 1.随心听VIP试听功能。 2.随心听歌曲切换音质。 3.同步手机端QQ音乐的歌单数据（默认自带歌单、自创建歌单、收藏的歌单）。 4.随心听增加歌手入口以及歌手搜索功能。 5. 登录页toast提示使用VIP账号登录，登录后显示账号是否是绿钻账号。 | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Online Music APIM PRD v1.0 Feb 8, 2021.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Phase 2 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0019 | F000379/G | Core Media Player (CDX746/7) | B# Multimedia 多媒体 | 4# Video 视频 | USB视频播放 Video- USB video | 需要支持主流视频格式 | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Media Player APIM SPSS v1.15 Jul 1, 2017.pdf Media Player APIM Imp Guide v1.15.1 Jul 1, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Y |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0020 |  |  | B# Multimedia 多媒体 | 4# Video 视频 | 爱奇艺 (在线视频APP) Video - Streaming video Iqiyi |  | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Video Player APIM PRD v1.0 Feb 8, 2021.pdf Video Player APIM PRD v1.0 Feb 8, 2021.pdf | SW_Tier1 | 20% | 80% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Phase 1 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0021 |  |  | B# Multimedia 多媒体 | 4# Video 视频 | 视频、音乐、图片DLNA投屏到车机显示器区分主副驾/Video Playback and Video and Photo project to Display(Driver and Passenger) via DLNA |  | EESE | Jia, Elaine (T.) <tjia2@ford.com> |  |  | DLNA投屏V0.2--PRD.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | N | C/O |  |  | Jia, Elaine (T.) <tjia2@ford.com> |  |  | Y | C/O |  | Jia, Elaine (T.) <tjia2@ford.com> |  |  | Phase 4 | Yes | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_0022 |  |  | B# Multimedia 多媒体 | 5# Sound & Effect 音效 | 底特律之音 Detroit Symphony Orchestra chimes | Detroit Symphony Orchestra chimes (林肯飞行家上面的底特律交响乐团打造的提示音） | EESE | Li Alvin (LLI156@ford.com) |  |  | Alerts v3 APIM SPSS v1.1 Mar 17, 2020.pdf Alerts v3 APIM_4.2 Imp Guide v1.1 Mar 17, 2020.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | N | C/O |  |  | Li Alvin (LLI156@ford.com) |  |  | N | N |  | Li Alvin (LLI156@ford.com) |  |  | Phase 4 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_0023 |  |  | B# Multimedia 多媒体 | 5# Sound & Effect 音效 | 电动车独有音效 EV Unique Chime (CDX727 lead) | Lead by CD727. Details need to be updated | EESE | Li Alvin (LLI156@ford.com) |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | N | N | N | N |  |  | Li Alvin (LLI156@ford.com) |  |  | N | N |  | Li Alvin (LLI156@ford.com) |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0025 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 播报能力+语音包 Multiple TTS (可切换） | 交互信息、提示信息、百度百科、电子说明书等语音播报， 并支持多种TTS 台湾女声（金莎语音PhaseII）、情感女声、标准女声，标准男声。 地图场景下有更丰富的语音包下载使用。 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0027 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 所见即可说 Voice command on IVI displayed touch elements | 系统界面可看见的文字，均可语音控制，部分APP包括爱奇艺的播放控制、外卖、酒店、智慧停车场、电影票、也支持。 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0028 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 打断式交互 全双工语音 Barge-in | 在语音助理进行播报时，用户可随时进行进一步的交互或说出新的命令，让助理执行相关操作，而无需等待播报结束； 支持双方同时说，互不干扰 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0029 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Natual Language Recognition 自然语音识别 | 普通话识别 Mandarin Rocognition | 本地/在线语音识别，将用户语音识别为文字. 识别率，根据背景噪声的大小高噪85%、中噪90%、低噪92%。 方言识别率低，取消了。 方言识别率目前较低 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0030 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Natual Language Recognition 自然语音识别 | 中英文混杂识别-电话域 Chinese/English mixed phone book recognition | 2000 英文词识别率74%， 不支持其他域 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 3 | No | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0031 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Natual Language Recognition 自然语音识别 | 离线指令 Offline Command | >500+ Offline comands | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0032 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Natual Language Recognition 自然语音识别 | 中英文混杂 - 音乐域/导航 Mandarin/English mixed language recognition - music/navigation | 识别率74% | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0034 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 前舱盖打开控制 Frunk Control -Open | CDX727 (BEV) _lead | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | Y | N | New | N | N |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | N | N |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0035 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 后备箱打开控制 Trunk Control-Open |  | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0036 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 天窗/遮阳帘控制 Roof window control | 天窗和遮阳帘可以分开控制。但是都由一条CAN 总线实现 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0037 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 座椅加热/通风控制/按摩 Seat Heating&Cooling/Seat Vented/Seat Massage | 三个功能可分开并且强依赖硬件，需核对项目HW Book 情况，确定具体落地 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0039 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 方向盘加热 Heated Steering Wheels Control |  | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | Y | Y | C/O | N | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0196 |  |  | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 电车实时车况界面 IOD Information On Demand/Display | 常规cluster 上面显示的信息 (车辆状况，油耗，胎压，里程， 我的驾驶怎么样？等等）输出至IVI界面，利用IVI Display 大屏的优势做了更直观的见面显示和相应的人机交互（例如下拉菜单）等更新。 Lead:CDX707 | EESE | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Fuel Economy SPSS v1.1 January 31, 2019 Fuel Economy APIM Imp Guide v1.1 January 31, 2019 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New | Y | N |  |  | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | N | N |  | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Phase 4 | No | - | - | - | - | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R7 | DCV Beta2 | 2021-12-25 | -
SYNC+_0040 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 氛围灯开关 Ambient Lighting on/off | 打开/关闭 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0115 | F003071 | Ultimate Remote Control (CDX746/7) | G# Remote Control 远程控制 | 2# In Cabin Remote Controller (Phone) 座舱内手机遥控器 | 座舱内手机遥控 Project Aspire_Ultimate Remote Control | Allow customer to use a mobile app (FordPass) to control all features that enhance the linger longer experience from a single touchpoint (audio with sharing, VSP, lighting, windows, PPOB, Power Tailgate, Power Running Boards, Seat Configuration, tbd accessories). Benfit: - Provides a space which a passenger feels in control and can enjoy their time in the vehicle - Provide a centralized way for a passenger to make their space confortable for them without disturbing others in the vehicle - Provide freedom for the driver/1R passenger of being the constant caretaker for the rest of the vehicle - alternative to myseatspace or multi-zone voice control or second row screen which are not in 707's assumption | ECDX | Shawn, Lin | Reed, Gregory (G.D.) |  |  | SW_Tier1 | 20% | 80% | 0% | 0% | Y-1st | N | New | Y-Study | New |  |  | Shawn, Lin |  |  | N | N |  | Shawn, Lin |  |  | Phase 5 | No | - | - | - | - | DCV2 | 2022-05-30 | 2022-06-14 | Group C | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0041 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 空调;风量和风向 A/C | "出风等级控制 Air volume-增加风量 出风等级控制 Air volume-风量大一点 出风等级控制 Air volume-减少风量 出风等级控制 Air volume-风量小一点 出风等级控制 Air volume-风量正常 出风等级控制 Air volume-调整风量到xx档" "空气系统控制 Climate system control-调整出风方向/下一个出风方向 Air flow direction 空气系统控制 Climate system control-打开/关闭自动除霜系统 defrost 空气系统控制 Climate system control-打开/关闭内循环 recirc 空气系统控制 Climate system control-打开/关闭空气清新系统 fresh air 空气系统控制 Climate system control-打开/关闭后挡风除霜 rear deforst 空气系统控制 Climate system control-打开/关闭自动模式 Auto mode" "打开/关闭空调 open/close AC 空调控制 AC control-设置空调温度到xx度 Temp setting 空调控制 AC control-提高温度 Temp up 空调控制 AC control-降低温度 Temp down 空调控制 AC control-温度最低/最低温度 LO 空调控制 AC control-温度最高/最高温度 HI" | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0042 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 5# VPA 形象化语音助手 | 语音助手1.5/2.0 VPA 1.5/2.0 (融合贯通生态的智能化的语音助手） | .Leading Intelligent skills ( 小度助手/百度语音最新版能力- 具体内容规划参照Product Owner-20201204 add. Plus VPA2.0 or 3.0 leading by Product Owner Chiu, Lulu Support in cabin vehicle control (ideally all), and all IVI software contents e.g navigation, open an app, user manual inquiry, search & play multimedia contents (music, audio book, video, etc). .facilitate conversation for relaxzation (joking, wikipidia, story, lite games) .Have visual character to express emotional elements (thinking, happy, listening) | ECDX | Suo, Feifei (F.) <FSUO@ford.com> |  |  |  | Ford_InHouse | 0% | 25% | 75% | 0% | Y-1st | Y-1st | C/O | Y | C/O |  |  | Suo, Feifei (F.) <FSUO@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Suo, Feifei (F.) <FSUO@ford.com> |  |  | Phase 5 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_0124 |  |  | H# Service & Maintenance 车主服务 | 5# User Feedback Channel 用户反馈 | 用户反馈Customer Feedback1.0 | QR code scan and submit via phone. 2021-02: 对于提交反馈的用户， 车机端会有个消息提醒：”感谢你的反馈。“ | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | N | N | N | Y | N |  |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Phase 1 | No | - | - | - | - | - | - | - |  | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0047 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 8# Multizone Voice Control 分区语音控制 | Dual Zone Voice Control 主副驾双音区分区控制 | 声源定位. 抢麦功能，判定用户方位，排除车内其他干扰、显示定位方向双音区分区语音控制 Dual Zone Voice Control. 支持主副驾分区控制。 目前双音区， 支持(空调, 方向盘加热, 座椅加热/按摩, 主副驾多媒体内容) 分区控制。 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0153 |  |  | K# Social & Operation 社交及运营服务 | 3# Entertainment 娱乐 | 娱乐座舱Cabin On-Live （曾用名音乐派 Music Boom. Former name: JukeBox） | Cabin On-live enables multi-users‘ real time interaction that initiated from the IVI when the car is on the road, ultimately enables a cross-OS light-weight social platform which can increase brand net promotor score. Inspired by music boom/jukebox and evolve into a platform hosting multiple low frequency but delightful experiencece. Expect to see growing, more and more exciting/engaging/lite offering from time to time | ECDX | Yu, Yaxing (Y.) <yyu55@ford.com> (PO) |  | Meng, Sheena (M.) <MXIA10@ford.com> |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-TBD | N | N | Y | N |  |  | Yu, Yaxing (Y.) <yyu55@ford.com> (PO) |  |  | N | N |  | Yu, Yaxing (Y.) <yyu55@ford.com> (PO) |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0048 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 唤醒词 - 品牌唤醒词 Brand wake-up commands | “你好，福特/林肯”默认唤醒词。Contain one-shot feature | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 2 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0049 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 免唤醒 - 全局/情景免唤醒 Wake-up Free | 全局免唤醒 - 包含包含QQ音乐/有声/新闻/在线电台/本地电台/本地音乐/蓝牙音乐/爱奇艺等应用运行时（包含后台运行）都可识别指令 （暂停/播放/上一首/下一首). 情景免唤醒 - 电话;随心看;导航;系统控制应用界面打开的情况下， 无需唤醒， 可以识别相关的指令 （接听/拒听电话；地图控制；第几个;上一页/下一页等） | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0050 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 唤醒词 - 自定义 Customized Wake-up keyword 林肯的语音唤醒词“你好，林肯” Lincoln wake-up commands 福特的语音唤醒词“你好，福特” Ford wake-up commands 核心功能场景化免唤醒命令 Wake-up command is not mandatory to activate for key functions |  | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 2 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0051 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 4# Life Services 生活服务 | 语音查询服务 | 语音查询服务（资讯/百科/游戏，笑话）-天气、股票、汇率、火车票、机票、航班信息、限号、百度百科、成语接龙、笑话等。 世界之最 Most ** of the world 支持查询世界上之最、中国之最 Support searching the most ** of the world/China 人物百科 Celebrity encyclopedia 支持娱乐明星、体育明星、历史人物等名人的重要信息（身高、体重、家乡、星座）、婚姻状况、亲属（如老婆、老公、女朋友）Support searching celebrity info 地理 Geography "支持查询某物的面积、长度、高度、食物的热量 Support searching something's dimension & food calorie" 天气 Weather "支持国内2560个城市和海外主要城市的6天内天气查询和当日生活指数查询。 Support weather info & related index search of 2560 domestic cities & main oversea cities." 彩票 Lotery 支持查询博彩类开奖结果(大乐透、七星彩、体彩、排列五、福彩、双色球）Support searching loteray info 日历 Calendar 支持查询节假日、节气时间 Support searching holiday date & China traditional solarterm dates 机票/航班信息 air ticket/flight info """支持查询机票/航班信息 support air ticket/flight info searching""" 汇率 Exchange rate "支持世界主要货币之间的兑换换算。 Support mainstreen currency exchange calculation" 火车票 train "支持查询火车票 support train ticket searching" 热映电影 Popular movie 支持电影实体查找（包括电影名、演员、类型等）Support movie searching 电影票/外卖 movie ticket/take away "支持购买电影票/外卖 support paying moive ticket" 电视剧基础属性 Episodes 支持查询电视剧的播出时间、电影的上映时间 Episodes'airtime 笑话 Jokes 支持文字笑话的询问与播报 Support reading literal jokes 股价 Share price 支持美股、港股、沪深股市的公司市值股价和大盘指数查询 Support US/HK/Shanghai/Shenzhen share price & stock index searching 诗词 Poem "支持唐诗宋词的完整篇章或上下句、作者、出处查询。 Support China acient poem searching & related info, i.e. writer" 闲聊 Chat 自由聊天，每句话都能有回应 Responding to every voice command/message 限行 Traffic control info - License plate restriction 查询6个主要限行城市（北京、杭州、兰州、成都、天津、武汉）的限行信息。 Support searching 6 main cities which implemented traffic control rules | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0068 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 6# Voice Command - IVI System Control 系统控制 | 音乐、收音机、在线电台、新闻、有声、爱奇艺、随心拍 等 | 本地媒体 收音机 打开 打开/播放/我想听收音机 切换到/收听/请打开/听/我要听… 关闭 关闭/退出收音机 停止/关掉… 把…关掉/关上 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 调台/搜索 上一台/下一台/上一个台/上一个频道/上一个频点/前一个/下一个台/后一个/ 播放/我要听104.3/FM88.8/AM538.0中国之声 扫描/更新/刷新/搜索电台 电台收藏 收藏 取消收藏 "USB音乐 （双开，声源定位）" 打开 打开/播放/我想听USB音乐/U盘音乐 "打开/播放/我想听主驾USB音乐/U盘音乐 打开/播放/我想听副驾USB音乐/U盘音乐" 关闭 关闭/退出USB音乐/U盘音乐 "关闭/退出主驾USB音乐/U盘音乐 关闭/退出副驾USB音乐/U盘音乐" 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 模式切换 随机播放/单曲循环/顺序播放/歌曲列表循环/列表循环音乐 "蓝牙音乐 " 打开 打开/播放/我想听蓝牙音乐 关闭 关闭/退出蓝牙音乐 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 在线媒体 "在线电台 " 打开 打开/播放/我想听/我要听（在线电台/在线收音机） 关闭 关闭/退出（在线电台/在线收音机） 播放控制 暂停 播放 调台/搜索 上一台/下一台 播放/我要听中国之声 切换播放路径 播放 切换 电台收藏 收藏 取消收藏 泛需求 打开随心听 打开（播放/我想听）在线音乐/随心听 "打开主驾（在线音乐/随心听） 播放主驾（在线音乐/随心听） 我想听主驾（在线音乐/随心听） 打开副驾（在线音乐/随心听） 播放副驾（在线音乐/随心听） 我想听副驾（在线音乐/随心听） " 关闭随心听 "关闭（在线音乐/随心听） 退出（在线音乐/随心听）" "关闭主驾（在线音乐/随心听） 退出主驾（在线音乐/随心听） 关闭副驾（在线音乐/随心听） 退出副驾（在线音乐/随心听）" "QQ音乐 （双开，声源定位）" 打开 （打开/播放/我想听）QQ音乐 "（打开/播放/我想听）主驾QQ音乐 （打开/播放/我想听）副驾QQ音乐" 关闭 "关闭（QQ音乐/在线音乐） 退出（QQ音乐/在线音乐）" "关闭主驾QQ音乐 退出主驾QQ音乐 关闭副驾QQ音乐 退出副驾QQ音乐" 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 模式切换 随机播放/单曲循环/顺序播放/歌曲列表循环/列表循环音乐 音乐点播 听歌意图，例：我想听歌/随便来首歌 听听音乐/放个歌/来点音乐/给我放首歌/有音乐么 播放/我想听/放一首/我要听/放/听/来首+ 歌曲名称 播放/我想听/放一首/我要听/放/听/来首+ 歌手名称的歌 播放/我想听/放一首/我要听/放/听/来首+歌手名称的歌曲名称 播放/我想听+歌曲类型的歌 歌曲收藏 收藏/加入收藏/帮我收藏 取消收藏/给我取消收藏 播放歌曲信息查询 歌手名称：这首歌是谁唱的 歌曲名称：现在播放的是什么歌 专辑：这首歌是什么专辑 泛问答（现在放的是什么） "有声 （双开，声源定位）" 打开 "打开（有声/有声读物） 播放（有声/有声读物） 我想听（有声/有声读物）" "打开主驾（有声/有声读物） 打开副驾（有声/有声读物） 播放主驾（有声/有声读物） 播放副驾有声/有声读物 我想听主驾（有声/有声读物） 我想听副驾（有声/有声读物）" 关闭 "关闭（有声/有声读物） 退出（有声/有声读物）" "关闭主驾（有声/有声读物） 退出主驾（有声/有声读物） 关闭副驾（有声/有声读物） 退出副驾（有声/有声读物）" 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 模式切换 随机播放/顺序播放/歌曲列表循环/列表循环音乐 有声点播 播放/我想听+ 有声名称 播放/我想听+有声类型（小说/有声书/相声/脱口秀/评书/故事/公开课等） 播放/我想听/我要听/播一段+专辑名 播放/我想听/我要听/播一段+主讲人的节目/作品 播放/我想听/我要听/播一段+主讲人的+分类 播放/我想听/我要听/播一段+专辑名的+节目名 播放/我想听/我要听/播一段+主讲人+专辑名 有声收藏 收藏/加入收藏/帮我收藏 取消收藏/给我取消收藏 播放有声信息查询 有声名称：现在播放的是什么节目 作者名称：这个节目是谁播讲的 专辑：这个节目是哪张专辑里的 泛问答（现在放的是什么） "新闻 （双开，声源定位）" 打开 打开/播放/我想听新闻 "（打开/播放/我想听）主驾新闻 （打开/播放/我想听）副驾新闻" 关闭 关闭/退出新闻 关闭/退出主/副驾新闻 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 模式切换 顺序播放/歌曲列表循环/列表循环音乐 新闻搜索 播放意图，例：今日新闻/有什么头条新闻 播放/我想听/今天的/最近的+新闻名称的新闻 播放/我想听/今天的/最近的+地域的新闻 播放/我想听/今天的/最近的/搜索+人物/事件的新闻 "爱奇艺 (支持可见即可说)" 打开 打开/我想看爱奇艺/随心看 关闭 关闭/退出爱奇艺/随心看 播放控制 暂停/播放 上一集/下一集 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 影片搜索 播放/我想看+ 视频名称 播放/我想看+影视类别 可见即可说 随心拍 打开/关闭随心拍 打开随心拍 关闭随心拍 拍照控制 拍照 视频控制 录制视频 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 60% | 0% | 40% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0073 | F000280 F000789 | Active Park Assist (CDX746/7) Active Park Assist (U6XX) | D# Co-Pilot360 驾驶辅助 | 1# Help Me Park 停车辅助 | 全自动泊车 Fully Automated Parking (FAPA) also called APA | Gen1 - Gen X 不停升级中。具体参照Feature Owner Cascade 信息. FAPA starts from 2018 C519. Enhanced Active Park Assist (EAPA) added perpendicular parking maneuvers to Ford's Active Park Assist (APA) feature. Active Park Assist 2.0 (APA2.0 makes the entire process a one-touch operation by automating the throttle and brake; the user is not required to give any input to get the vehicle into the space. | EESE | He, Michael (X.) <xhe22@ford.com> | Rashidzadeh, Hejir (H.) |  | Active Park Assist V2 APIM SPSS v1.11 Mar 23, 2020.pdf Active Park Assist V2 APIM Imp Guide v1.11 Mar 23, 2020.xlsx | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y | C/O | Y | Major |  |  | He, Michael (X.) <xhe22@ford.com> |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | He, Michael (X.) <xhe22@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0265 |  |  | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 车路协同 4G V2I Lite (Production) | V2I Lite (Production) For FNV2: 支持更多城市； | ECDX | Fan Henry | [8 empty] | Y | N | N | Y | N |  |  | Fan Henry |  |  | Y | New |  | Fan Henry |  |  | Phase4 | No |  |  |  |  | - | - | - |  | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0074 | F001330 | Reverse Brake Assist (CDX746/7) | D# Co-Pilot360 驾驶辅助 | 4# Help Me Avoid Collisions 避免碰撞辅助 | 倒车制动辅助 Reverse Brake Assist (RBA) | (倒车时识别静态物体依托radar，超声波雷达和rear camera) | EESE | Li, Yifan (Y.) <YLI381@ford.com> | Cheng, Samuel (S.) |  | Reverse Brake Assist SPSS v1.2 May 17, 2021.pdf Reverse Brake Assist APIM Imp Guide v1.2 May 17, 2021.xlsx | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y | C/O | Y | C/O |  |  | Li, Yifan (Y.) <YLI381@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Yifan (Y.) <YLI381@ford.com> |  |  | Phase 2 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0076 | F002930 | Remote Park Assist (RePA) 2024 CDX746/7 Remote Park Assist (REPA) (U611) | D# Co-Pilot360 驾驶辅助 | 1# Help Me Park 停车辅助 | 远程泊车辅助 Remote Park Assist (RePA) |  | EESE | He, Michael (X.) <xhe22@ford.com> | Rashidzadeh, Hejir (H.) |  | Remote Active Park Assist SPSS v1.0 Feb 4, 2020 | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y-1st | C/O | N | C/O |  |  | He, Michael (X.) <xhe22@ford.com> |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | He, Michael (X.) <xhe22@ford.com> |  |  | Phase 5 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | R00 | 2022-09-01 | 2022-09-15 | Group B | - | - | - | -
SYNC+_0077 |  |  | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 5G 车路协同 5G V2V | Global V2V including 1- Intersection Movement Assist(IMA) 2-Left Turn Assist(LTA); 3- Emergency Electronic Brake Light(EEBL).V2X including V2I and V2V and further more. | EESE | Shan, Susan |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y-1st | Y-1st | C/O | N | C/O |  |  | Shan, Susan |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shan, Susan |  |  | Phase 5 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | R00 | 2022-09-01 | 2022-09-15 | Group C | - | - | - | -
SYNC+_0082 |  |  | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 车路协同 V2I Lite (Beta) | 纯软件的基于IVI 的China Local Solution including 4 features •Traffic Light Information(TLI) •Green Light Notification (GLN) •Green Light Optimal Speed Advisory(GLOSA) •Red Light Violation Warning(RLVW) | EESE | Li, Yifei (Y.) <nli26@ford.com> |  |  |  | Ford_InHouse | 0% | 20% | 60% | 20% | Y | Y | C/O | Y | C/O |  |  | Li, Yifei (Y.) <nli26@ford.com> |  |  | N | N |  | Li, Yifei (Y.) <nli26@ford.com> |  |  | Phase 3 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0089 | F003515 | Surround View Cameras (CDX746/7) Surround View Cameras (U6XX) | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 360 摄像头图像 2.0 360 Camera Image 2.0 | 增加点:offset views+软按键 driving tube in front/rear offset views offset views==front left/front right/rear left/rear right | EESE | Li, Xin (X.) <xli268@ford.com> | Salcido-zarco, Alejandro (A.) |  | Multi-Camera Client APIM SPSS v1.14 Mar 31, 2021.pdf Multi-Camera Client APIM Imp Guide v1.14 Mar 31, 2021.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | Major |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2021-12-25 | -
SYNC+_0094 |  |  | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 多种摄像头 Multi Camera - CHMSL/AUX Camera/Rock Crawl | ional item的，重卡unique，但是中国基本用不到 [Susan FIP:360camera基础上再增加一些摄像头] | EESE | Li, Xin (X.) <xli268@ford.com> |  |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | N | N | N | N |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | N | N |  | Li, Xin (X.) <xli268@ford.com> |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0090 | F003515 F000292 | Surround View Cameras (CDX746/7) Surround View Cameras (U6XX) | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 360 摄像头图像 360 Camera Image 1.0 | IVI 界面用户可以自行打开。使用场景例如 出停车位，变道. 360°全景影像设置 setting "Front/Rear view (Front/Side/Rear Zoom 前/后的四拼图，后路放大视图)" 2D模式 "视角切换图 split view (Rear/Front wideangle view,单路广角视图)" "俯视图 plan view (Rear/Front+ Plan View 全景加前或后的单路视图)" | EESE | Li, Xin (X.) <xli268@ford.com> | Salcido-zarco, Alejandro (A.) |  | Multi-Camera Client APIM SPSS v1.14 Mar 31, 2021.pdf Multi-Camera Client APIM Imp Guide v1.14 Mar 31, 2021.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | Major |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  |  | Phase 1 | No | R7 | R7(DCV Beta2) | 2021-09-15 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2021-12-25 | -
SYNC+_0091 | F003631 | Base Park Aid (CDX746/7) | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 泊车辅助显示 Rear/Front/Side Visual Parking Aid | 障碍物距离显示 display distance to blocks (乌龟图);Park aid visual display (incl front rear and side) | EESE | Li, Xin (X.) <xli268@ford.com> | Al-Zaher, Sarya (S.) |  | Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.pdf Visual Park Assist Graphic Client V2 APIM Imp Guide v1.6 Dec 8, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  |  | Phase 1 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0092 |  |  | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 前视摄像头 Off Road Front View Camera | 前视影像可以延时一段时间 | EESE | Li, Xin (X.) <xli268@ford.com> |  |  | Off-road Front View Camera APIM Implementation Guide ver1_0 May 31 2013.xls Off-road Front View Camera APIM SPSS ver1_0 May 31 2013.doc Off-road Front View Camera APIM SPSS ver1_0 May 31 2013.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | N | C/O |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  |  | Phase 4 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_0103 |  |  | E# Access & Authorization 车钥匙 | 1# Keyfob 传统车钥匙 | 我的钥匙MyKey | XCL decision to stop this implementation from P702/MY21U554MCA Settings-Clear my keys Settings-Create my key Settings-My key status Settings-Volume limiter | EESE | Xu, Andy (X.) <xxu71@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | N | N | N | N | N |  |  | Xu, Andy (X.) <xxu71@ford.com> |  |  | N | N |  | Xu, Andy (X.) <xxu71@ford.com> |  |  | Phase 2 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0093 |  |  | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 后视摄像头 Rear Camera On Demand | 后视影像在R挡切换时可以延时一段时间，车速高于10km/h终止 | EESE | Li, Xin (X.) <xli268@ford.com> |  |  | Rear Camera On Demand APIM SPSS v1.1 June 21, 2019 Rear Camera On Demand APIM Imp Guide v1.1 June 21, 2019 | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  |  | Phase 4 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2021-12-25 | -
SYNC+_0095 |  |  | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 数字倒车影像 Rearview Camera - RVC (Digital) | Camera on demand;Rear view camera； IVI 绘制动态辅助线； RVC 叠加AR BPA | EESE | Li, Xin (X.) <xli268@ford.com> |  |  | Digital RVC SPSS v1.4 April 26, 2019.pdf Digital RVC APIM Imp Guide v1.4 April 26, 2019.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  |  | Phase 2 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0098 | F000565 | Cross Traffic Alert with Braking (CDX746/7) | D# Co-Pilot360 驾驶辅助 | 4# Help Me Avoid Collisions 避免碰撞辅助 | 倒挡来车预警 Cross Traffic Alert (CTA) | 倒挡来车预警, 大屏上面HMI显示左右两侧动态箭头; Phase 2 增加倒档来车预警- 软按键功能 on/off | EESE | Liu, Hongxin (H.) <HLIU162@ford.com> | Rossi, Antonio (A. R.) |  | Cross Traffic Alert APIM SPSS v1.5 Apr 1, 2021.pdf Cross Traffic Alert APIM Imp Guide v1.5 Apr 1, 2021.xlsx | HW_Tier1 | 80% | 0% | 0% | 20% | Y | Y | C/O | Y | C/O |  |  | Liu, Hongxin (H.) <HLIU162@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Liu, Hongxin (H.) <HLIU162@ford.com> |  |  | Phase 1 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0101 | F001430 |  | D# Co-Pilot360 驾驶辅助 | 4# Help Me Avoid Collisions 避免碰撞辅助 | 开车门路况辅助 Exit Warning （DAT2.1） | IVI need implement Clear Exit Assist Setting and Pop-Up Warning | EESE | Liu, Hongxin (H.) <HLIU162@ford.com> |  |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Liu, Hongxin (H.) <HLIU162@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Liu, Hongxin (H.) <HLIU162@ford.com> |  |  | Phase 4 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0106 | F001670/A F001372 | Phone as a Key (PaaK) "BUN" w/o Keyfob 2024 CDX746/7 Backup Start Passcode BSP (U611) | E# Access & Authorization 车钥匙 | 2# Phone As A Key (PaaK) 手机钥匙 | 手机钥匙Phone as key(PaaK) | Regular PAAK. 4 doors 天线1+ 6 或1+x， Backup Startup Passcode (BSP) 选配，refer to feature owner cascade。 | ECDX | Chen, chiefer | Hamel, Jeffrey (J.) |  |  | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y | C/O | Y | Major |  |  | Chen, chiefer |  |  | N | N |  | Chen, chiefer |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta1 | 2022-02-16 | - | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_0108 |  |  | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | 人脸识别账户登录Face ID - Driver (Registration, Recognition, Account, Personalization, Welcome) |  | EESE | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  |  | FaceID with DSMC Function Specification_V8 _20201215.pdf | SW_Tier1 | 20% | 80% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  |  | N | N |  | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0110 |  |  | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 2# Vehicle Streaming Platform | 舱内娱乐Cabin On-live 1.0 | First deploy to CDX707 with in car KTV and in car passenger DLNA | ECDX |  |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-1st | C/O | Y-Study | C/O | [5 empty] | N | N |  |  |  |  | Phase 5 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | R00 | 2022-09-01 | 2022-09-15 | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_0112 | F003415,F001047 | Cellular Remote Door Lock/Unlock (U6XX) | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程解锁/启动 Remote Door Lock/Engine Start | Remote Door unlock/start engine. 空调/座椅/方向盘加热 也会自动上一次熄火前的设置 | ECDX | Lin, Shawn (X.) <xlin17@ford.com> | Syed, Imtiaz (I.S.) |  | Cellular Remote Start, Extend Remote Start & Cancel Remote Start Feature Document v1.1.pdf Cellular Remote Start, Extend Remote Start & Cancel Remote Start Function Specification v1.0.pdf FNV2 Remote Start and Schedule Remote Start PRD v3.2.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Y |  |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0113 |  |  | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程鸣笛闪灯 Vehicle Announcement via FordPass | [Shawn] Non IVI seting provides additional Command & Control ability to customer that customer can remotely active the light （转向灯） and horn to locate their vehicle. Lead: CX482PHEV.FordPass have two solutions to meet different program architecture with additional testing cost. Currently planned on Fordpass. Additional LincolnWay UI will be required if need. FordPass远程控制灯光/鸣笛 Remote control lighting/horn.4G 信号 支持。Customer benefit 场景： 找车。 现有的keyfob 蓝牙模块有~40米。 (Lead phase 2: CX482/Lincoln Way (Not Ready) | ECDX | Lin, Shawn (X.) <xlin17@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | N |  |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Y | New |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Phase 2 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | - | - | - |  | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0114 |  |  | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程空调控制 Remote Climate Control (RCC) via FordPass/Lincoln Way | [Shawn] Need IVI setting Will allow customer’s to select their personal settings for cabin temperature, max defrost and heated/cooled seats. Customer can view the current vehicle cabin temperature and the last HVAC settings through the mobile app. 空调， 通风除霜，座椅加热，油车跟remote start 联动 （~10分钟后， 用户可以选择延时，否则engine stop)。新增项：实时显示，分开各项分开设置。支持FNV2架构。Gasoline and EV。 Lead：CD764. Feasible for programs with FNV2 architecture | ECDX | Lin, Shawn (X.) <xlin17@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | N |  |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Y | New |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | - | - | - |  | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0116 |  |  | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 爱车探索Demo Mode | Including 重温欢迎仪式 Replay Welcome Approach 配置介绍 Features Walkthrough | EESE | Lee, Grace (G.) <glee51@ford.com>/Liu, Luisa |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | C/O | Y | C/O |  |  | Lee, Grace (G.) <glee51@ford.com>/Liu, Luisa |  |  | N | N |  | Lee, Grace (G.) <glee51@ford.com>/Liu, Luisa |  |  | Phase 4 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV Beta1 | 2022-02-16 | - | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_0119 |  |  | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 1.0 | Paper "Owners' manual" go digital on IVI. OTA to support any contents updates/changes. | ECDX | Zhang, Xiaojing (X.) <xzhan247@ford.com> |  |  |  | Ford_InHouse | 0% | 10% | 90% | 0% | N | N | N | N | N |  |  | Zhang, Xiaojing (X.) <xzhan247@ford.com> |  |  | N | N |  | Zhang, Xiaojing (X.) <xzhan247@ford.com> |  |  | Phase 2 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0117 | F002370 | Digital Owner's Manual (CDX746/7) | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 1.5 | 1. Online content update（cloud storage) 支持内容通过云端更新（静默升级，无需OTA, 用户无感知) - Phase 4 全系 planned， phase 3 in progress; 2. 支持全量纸质手册 . 福特车型（5本); 林肯车型（6本); V1.0 只支持Owner's manual 3. 多媒体手册内容 (video形式本地存储， 具备流媒体形式，但目前没有内容对接）。支持后备箱踢脚 (CDX482/483 only)。 需Program/feature owner drive content design. 4. Voice Command open E-manual; Voice search content (20 keywords voice search) | EESE | Jiang, Wei (W.) |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | C/O | Y | Minor |  |  | Jiang, Wei (W.) |  |  | N | N |  | Jiang, Wei (W.) |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0118 | F002370 | Digital Owner's Manual (CDX746/7) | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 2.0 | 1. AI Voice Search. 云端支持 inhouse MPP 合作开发. POC 开发完成， waiting for approve. | EESE | Jiang, Wei (W.) |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-TBD | C/O | Y | C/O |  |  | Jiang, Wei (W.) |  |  | Y |  |  | Jiang, Wei (W.) |  |  | Phase 5 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0120 |  |  | H# Service & Maintenance 车主服务 | 2# Traffic Violation Checking 违章查询 | 违章查询 Query traffic violations (IVI) | Baidu: 用户终端查询是需要收费的。 | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | C/O |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 2 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0122 | F001048/F | Vehicle Health Alert and Status, and Vehicle Location (CDX746/7) | H# Service & Maintenance 车主服务 | 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | 车辆警示 Vehicle Health Alerts (VHA) | 传统显示再Cluster 上的各种故障报警(40多项), ECG 将信号传统到IVI及Fordpass/Lincoln Way 显示.建议保养时间/保养项目/里程 2021 Q1 手机端上线. | ECDX | Lu, Chao (C.) <clu42@ford.com> | McKinstry, Roy (R.S.) |  | ECPI_VSHA_Feature_Requirement_Document_v1_1.docx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 2 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0123 |  |  | H# Service & Maintenance 车主服务 | 4# Dealer Service Booking 经销商服务预定 | 保养及在线预约 OSB - Online Service Booking | Dearler Search. /Vehicle Maintenance and the service booking 保养在线预约 OSB-订单查询 order inquiry 保养在线预约 OSB-保养预约 Service booking， time and leave a note for maintenance items 保养在线预约 OSB-建议保养项目 Base on mile display user manual suggested maintenance item when user click on this . | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | MRD OSB MRD.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | On Hold | C/O | Y | Y |  |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | On Hold | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Phase 4 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0125 |  |  | H# Service & Maintenance 车主服务 | 5# User Feedback Channel 用户反馈 | 用户反馈Customer Feedback 2.0 | Improved version.车机上进行语音录入用户反馈。增加手机上的交互xx. target timing 是CX727 第一个OTA cadence | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0126 | F000997 | Pan-Euorpean eCall (CDX746/7) | I# Safety & Security 安全 | 1# Emergency Services 紧急救援 | 升级版紧急救援/服务 eCall | CN-CAP Safety (5 stars) driven features. Dedicated TCU, Microphone， Speaker. Automatic trigger condition is the same as current EA design(Oil pump cut off or air bag deploy); leverage current EA call center Yesway(95智驾). CN Regulation on e-call to be expected in 2024 (TBC) | ECDX | Ren, Siyuan (Alex.) | Berro, Hussein (H.) |  | eCall-PRD v1.2.pdf EECS Audio Client SPSS v1.1 November 1, 2018.pdf EECS Display Client (eCall) SPSS v1.0 March 16, 2018.pdf | HW_Tier1 | 60% | 0% | 0% | 40% | Y | Y | C/O | Y | C/O |  |  | Ren, Siyuan (Alex.) |  |  | Y |  |  | Ren, Siyuan (Alex.) |  |  | Phase 4 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0128 |  |  | I# Safety & Security 安全 | 1# Emergency Services 紧急救援 | 道路救援Road Side Assitance (RSA) | 道路救援， 用户IVI端一键触发(蓝牙电话）（安联） - 拨打道路救援电话，获取道路救援服务 - 入口：车机端"道路救援"应用，其存储着固定的道路救援电话号码 - 通过蓝牙连接的手机拨打道路救援电话 | ECDX | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | DUEROS_CVPP_RSA_PRD v1.2.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | Y | C/O |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | Phase 1 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta1 | 2022-02-16 | - | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_0129 |  |  | I# Safety & Security 安全 | 2# Safety Reminder 安全提醒 | 儿童座椅报警Child Restraint System (CRS) - ( e.g BT Child seat 蓝牙座椅) | BT Child seat 蓝牙座椅, 蓝牙通信反馈儿童座椅是否正确安装了。CNCAP 安全需求，车载需要支持与CRS 实现通信功能. 通信的具体形式是蓝牙传输. 目前仅支持环球娃娃品牌下的部分型号. CNCAP 5星要求。 | EESE | Xu, Amy (X.) <xyafei@ford.com> |  |  | 基于BT检测儿童安全座椅状态功能--PRD.docx | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | C/O | Y | C/O |  |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Amy (X.) <xyafei@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0130 |  |  | J# Health & Wellness | 1# Air Quality 空气质量 | 座舱空气质量检测CAQ(Cabin Air Quality) | 后装方案 | ECDX | Tong Tian |  |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | N | N | N | N | N |  |  | Tong Tian |  |  | N | N |  | Tong Tian |  |  | Phase 1 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0131 |  |  | J# Health & Wellness | 1# Air Quality 空气质量 | 智能新风Auto Air Refresh (AAR) G1 | 显示车内PM2.5, 提醒是否内外循环切换 | ECDX | Shi, Stella |  |  | DUEROS_CVPP_AAR v1.3.1_ChinaMarket_Sync+_20210225.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | N | N | N | N | N |  |  | Shi, Stella |  |  | N | N |  | Shi, Stella |  |  | Phase 2 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0132 | F001211 | Auto Air Refresh (AAR) for CHINA Markets (CDX746/7) | J# Health & Wellness | 1# Air Quality 空气质量 | 智能新风Auto Air Refresh (AAR) G2 (Blue Shield) | Blue Shield. 增加了主动干预，自行切换；点火后， 自动打开空调；行驶中， 提醒是否开空调 （不主动干预，因为会引起driver 紧张，安全影响） | ECDX | Shi, Stella (J.) <jshi32@ford.com> |  |  | DUEROS_CVPP_AAR v1.3.1_ChinaMarket_Sync+_20210225.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Y |  |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-01-27 | -
SYNC+_0133 |  | Digital Scent (China) (CDX746/7) | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 数字香氛 Digital scent 1.0 | 4 scents | BI | Chen, Minghui (M.) <MCHEN122@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0 | 0% | 90 | N | N | N | N | N |  |  | Chen, Minghui (M.) <MCHEN122@ford.com> |  |  | N | N |  | Chen, Minghui (M.) <MCHEN122@ford.com> |  |  | Phase 3 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0134 | F004410 F003130 | Digital Scent (China) (CDX746/7) Digital Scent (China) (U611) | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 数字香氛 Digital Scent 2.0 (New Scents) | New scents can work with imersive experience, e.g rejuvenations for customer heath & wellness, as well as Purify. | BI | Chen, Minghui (M.) <MCHEN122@ford.com> |  |  | Digital Scent PRD - for CDX707C 20210714.doc | Core_Service_Supplier | 10% | 0 | 0% | 90 | Y-1st | Y-1st | C/O | N | C/O |  |  | Chen, Minghui (M.) <MCHEN122@ford.com> |  |  | N | N |  | Chen, Minghui (M.) <MCHEN122@ford.com> |  |  | Phase 5 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_0135 | F003072 | Rejuvenate Mode (CDX747) | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 活力恢复 Project Aspire_Rejuvenation | Project Aspire: Relax is a feature/capability that allows to provide a user specific experience to induce calming or relaxing experience. The feature is a combination of effects in a vehicle to including- Digital scent- Advanced welcome with complimentary light and sound scheme in various parts of vehicle such as ambient lighting , Horizon display , center stack etc- Relax moment can be initiated and controlled via HMI. This feature also uses FordPass to download calm app, install, set up calm experience (ambient color, cabin temo, length of experience, other HVAC controls), save and then start calm experience with chatbot and FB messenger. | EESE | Liu, Kai (K.) <kliu63@ford.com> | Shetty, Sohan (S.R.) |  |  | Ford_InHouse | 0% | 0% | 90% | 10% | Y-1st | Y-OTA | New | Y-Study | C/O |  |  | Liu, Kai (K.) <kliu63@ford.com> |  |  | N | N |  | Liu, Kai (K.) <kliu63@ford.com> |  |  | Phase 5 | No | R26 | R26(R09) | 2023-04-28 | 2023-05-12 | DCV3 | 2022-07-11 | 2022-07-26 | Group C | R13 | R00 | 2022-08-30 | 2022-09-15
SYNC+_0136 |  |  | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 舒享时分Relax/自由秘境At Ease | Pre-Global Rejuvenation. China Local solution. 林肯车型正式名称 - 舒享时分Relax/ 车型f福特正式名称 - 自由秘境At Ease | EESE | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  |  |  | Ford_InHouse | 0% | 0% | 90% | 10% | Y | Y | N | Y | C/O |  |  | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | - | - | - |  | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0137 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 个人时光 Smart Scene - Personal Enjoyment | Personal Enjoyment 个人时光 Lead: CDx764 CD764 Implantation -Buddle setting to provide wonderful movie watch experiences in the copilot seat. Target Parking experience when customer watch movie for more than 30 minutes. Drive side is not considered in this design as long movie watching experience is not encouraged as for bad HMI or blocked sight. Buddle setting including Digital Scent, lighting , massage seat setting, enhanced co-pilot seat audio effect. Driver are expected to move to co-pilot seat to use this feature. Research shows that this movement won’t be a boundary as long as the experience is good. Moving forward, more enjoyment like game and other leisure enjoyment will be add. Developpment in progress. Smart Scene is part of phase 4 discussion with Desay. Product/Feature owner to provide details. Feature OTA Capability depends on Vehicle HW and display set e.g whether screen covers co-pilot seat). | ECDX | Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  | Meng, Sheena (M.) <MXIA10@ford.com> |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | C/O | Y | C/O |  |  | Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  |  |  | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV Beta1 | 2022-02-16 | - | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_0138 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 车机相册 IVI Picture Gallery | 支持车机本地/USB 图片和视频资源浏览/播放。 具体功参考技术文档。可参照现有手机相册的实现 | ECDX |  |  |  |  | SW_Tier1 | 20% | 80% | 0% | 0% | Y | Y-OTA | C/O | Y | C/O | [5 empty] | Y | Minor | New HMI layout and UE for 12.3'+27' Display |  |  |  | Phase 4 | No | R26 | R26(R09) | 2023-04-28 | 2023-05-12 | DCV3 | 2022-07-11 | 2022-07-26 | Group C | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0139 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 客人模式Smart Scene - Guest Mode | could be triggered by copilot seat door or seat sensor，or activate by voice command by customer. Guide guest to IVI contents (e.g music) in the meanwhile protect car owners privacy by removing owners' search records. Co-drive mode (lead by Grace lee) is more for onboard a family member or friends. -Challenges: part of the design is to give privacy to driver. requires removal of driver's or other users search records. require baidu implementation. currently dont have Baidu responses. -OTA Feasibility: designed for 27Inch Touch Screen. consider HMI changes for other programs. | ECDX | Sun, Zheng (Z.) <ZSUN6@ford.com>(PO) Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); |  | Meng, Sheena (M.) <MXIA10@ford.com> |  | Ford_InHouse | 10% | 0% | 90% | 0% | Y | Y | C/O | N | C/O |  |  | Sun, Zheng (Z.) <ZSUN6@ford.com>(PO) Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Sun, Zheng (Z.) <ZSUN6@ford.com>(PO) Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); |  |  | Phase 4 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV Beta1 | 2022-02-16 | - | Group B | - | - | - | -
SYNC+_0140 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 智慧指令 Smart Scene - Smart Order | Buddled setting for (CD764 MVP - 4 orders including 客人模式；通勤模式；冬日模式；夏日模式 。根据设定条件,IVI 屏幕主动推荐“智能指令”or activate by voice command. Allow customization on IVI/Fordpass。 - Challenges：1-limited modules in the vehicle is controllable. 2-Not a high priority for Ford global. Therefore setting on FordPass and send to car is not feasible even in 2021 . | ECDX | Sun, Zheng (Z.) <ZSUN6@ford.com>(PO) Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); |  | Meng, Sheena (M.) <MXIA10@ford.com> |  | Ford_InHouse | 10% | 0% | 90% | 0% | Y | Y | C/O | N | C/O |  |  | Sun, Zheng (Z.) <ZSUN6@ford.com>(PO) Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Sun, Zheng (Z.) <ZSUN6@ford.com>(PO) Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); |  |  | Phase 4 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV Beta1 | 2022-02-16 | - | Group B | - | - | - | -
SYNC+_0207 |  |  | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | HUD信息显示EESE/IVI info showed in HUD | CAN互动，消息协议由Ford定义。 导航，里程，多媒体，电话等信息在HUD上的显示。 (IVI 提供信号， HUD owner 决定显示信息） 仪表控制导航的功能：同步目的地收藏，设置目的地途经点Cluster control EESE/IVI Navigation。 来电号码及名称显示，接听，挂电话 incoming caller ID display，answer call， hang-up call 广播，专辑信息、歌名、歌手 Album info,song & singer and Radio 导航服务，转向、ETA等信息 turn lane,radar detector & ETA | EESE | Chen, James (J.) <jchen303@ford.com> |  |  |  | HW_Tier1 |  |  |  |  | Y | N | N | Y | N |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | Y | New | TP协议传输导航和来电信息给外部独立的HUD | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 2 | No | - | - | - | - | - | - | - |  | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0141 |  |  | K# Social & Operation 社交及运营服务 | 4# Personal Productivity 工作效率 | 车机日历Project Aspire_Routines / Daily View_IVI Calendar 2.0 | This experience provides capability to Ford / Lincoln user to access personalized calendar or day to day schedule while in the vehicle and different aspects influencing the customers daily life. The Experience covers different aspects such as Integrating into calendar, reminders appointments etc. Integrating into traffic (ETA , Traffic) Integrating into routine destinations or accessing customers locations per calendar Integrating into vehicle data such as Fuel/charge level and ability to predict fueling/charging time in the busy day. This is the day view that margaret has once she hoped in her vehicle. - From Project Aspire User calendar is an enabler to this function. For reference 764 have IVI Calendar (Local Design), need to work with global core team understandingthe global design. | ECDX | Shi, Stella (J.) <jshi32@ford.com> |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-1st | C/O | Y | C/O |  |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | N | N |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Phase 5 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0142 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 电影票预定 Movie Ticket Booking 美团外卖MeiTuanTake-away 鲜花预定Order flower delivery 机票查询 Flight search 火车票查询 Train ticket search 酒店预定 Hotel booking | 资源来自爱奇艺。查看热映电影;选座购票;付款;"鲜花预定（含二维码支付） Order flower delivery" 机票查询 Flight search 火车票查询 Train ticket search 酒店预定 Hotel booking | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 1 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0143 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 福特/林肯金融 Ford Credit | 账务记录 | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0145 |  |  | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 随心拍Traveling Shooting | Need AR Navigation Camera | ECDX |  |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y-OTA | C/O | Y | C/O | [5 empty] | N | N |  |  |  |  | Phase 4 | No | R26 | R26(R09) | 2023-04-28 | 2023-05-12 | DCV3 | 2022-07-11 | 2022-07-26 | Group C | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0151 |  |  | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 随心拍Travel Shooting 2.0 Project Aspire_Photos (GPS Created Trip Summary) | Share picutres & trip highlights (ex. Wechat or Facebook story report out). Ideas of things to share: selfie if taken with interior facial camera, personal photos taken during the trip, locations visited/passed, number of miles traveled, etc. | ECDX |  |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y-OTA | C/O | Y | C/O | [5 empty] | N | N |  |  |  |  | Phase 5 | No | R26 | R26(R09) | 2023-04-28 | 2023-05-12 | DCV3 | 2022-07-11 | 2022-07-26 | Group C | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0152 |  |  | K# Social & Operation 社交及运营服务 | 3# Entertainment 娱乐 | 时空秘信Surprise/Secret message | customer can schedule supirse message such as "Happy Birthday" | EESE | Lee, Grace (G.) <glee51@ford.com> |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | C/O | Y | C/O |  |  | Lee, Grace (G.) <glee51@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Lee, Grace (G.) <glee51@ford.com> |  |  | Phase 4 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV Beta1 | 2022-02-16 | - | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_0154 |  |  | K# Social & Operation 社交及运营服务 | 4# Personal Productivity 工作效率 | 视频会议 Project Aspire_Video Phone Calling / Video Conferencing (Meeting Mode)_CN | Demonstrate a Video call capability using the center stack with a Web application. The Functionality provides a view for Video conferencing in stationary mode. Includes conference experience , voice or audio in call and document viewing and sharing capabilities. These are listed as two items on Project Aspire Master List | ECDX | Wang, Johnny |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-1st | C/O | N | C/O |  |  | Wang, Johnny |  |  | N | N |  | Wang, Johnny |  |  | Phase 5 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0156 |  |  | K# Social & Operation 社交及运营服务 | 5# In Vehicle Gaming 车载游戏 | 舱内娱乐Carbin on live 2.0 | Cabin on live will include in car gaming(3rd party) | ECDX | Fan Henry |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-OTA | N | Y-Study | C/O |  |  | Fan Henry |  |  | TBD |  |  | Fan Henry |  |  | Phase 5 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | TBD |  |  |  | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0155 |  |  | K# Social & Operation 社交及运营服务 | 4# Personal Productivity 工作效率 | 车机日历IVI Calendar 1.0 | Generic calendar with Chinese traditional calendar/Holidays/Customer personal Events-Event Management (Add;Edit/Delete). IVI system will remind customer these recorded events on screen with voice broadcaste. Roadmap with more features to be implemented in upcoming phases. |  | Liu, Hailan (H.) <hliu142@ford.com> |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | N | N | New | N | N |  |  | Liu, Hailan (H.) <hliu142@ford.com> |  |  | TBD |  |  | Liu, Hailan (H.) <hliu142@ford.com> |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0157 |  |  | K# Social & Operation 社交及运营服务 | 6# Marketplace / Apps Anywhere 应用商店 | 车机应用商店Apps Anywhere(SYNC+) | Market Place is a extension of Ford Pass where following options are available for a customer - Chosen experiences such as relax could be purchased and downloaded to the vehicle - Chosen dashboards ( Videos , Static wallpapers) can be purchased and downloaded to the vehicle . Marketplace today is only QSR (Quick Service Retail -coffee, gas, etc). Buying any application purchases is not contained. Apps Anywhere build a foundation to support the application purchases. All on hold | ECDX | Fan Henry |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-OTA | C/O | Y-Study | C/O |  |  | Fan Henry |  |  | Y-Study |  |  | Fan Henry |  |  | Phase 5 | No | R26 | R26(R09) | 2023-04-28 | 2023-05-12 | DCV3 | 2022-07-11 | 2022-07-26 | Group C | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0158 |  |  | K# Social & Operation 社交及运营服务 | 7# Web Browser & Browser Based Application 浏览器和网页版应用 | 车载游览器/浏览器应用Project Aspire_Streaming Web / Applications | Previous name is 车载游览器/浏览器应用Project Aspire_Streaming Web / Applications IQIYI is the assumption (Carryover Feature) The feature discribed below from project aspire is optional Using Chromium with QT the team integrated the following websites in to the ASPIRE experience. Each web application has a icon in the center stack that starts in the center stack and then can be casted to the horizon display. The user can scroll, pan select, play, pause, etc. just as they can on any website. | ECDX | Fan Henry (TBD) |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-Study | N | Y | C/O |  |  | Fan Henry (TBD) |  |  | N | N |  | Fan Henry (TBD) |  |  | Phase 5 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | TBD |  |  |  | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0159 |  |  | K# Social & Operation 社交及运营服务 | 8# Wallpaper 墙纸 | 壁纸 Project Aspire_Dash Backgrounds (Dual 23.6+11.1/or 27") | like your wallpaper on your phone or PC. The customer can personalize their dashboard with images, videos and sound. Content can be placed on top of the dashboard like on your PC and phone wallpaper. A dashboard covers the entire horizon screen. Project Aspire planed wallpaper/background including Luxury/Doggy dash/Dolphin/Live aquarium/Bloom/Comb/Dots/Houston Skyline/Kids photos/New York Aerial | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y-1st | Y-1st | C/O | N | C/O |  |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Y | C/O |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Phase 5 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0149 |  |  | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 路书 (App -去兜风) Project Aspire_Route 66 / Tourist Mode (Education and Historical POIs)_CN (Route 66/Travel Book) | Route 66 can be different from Tourist mode. Route 66 is that we recommend a fabulous/fun trip and highlight preview of the best spot along the journey, where you can stay, best spot for pictures. Tourist Mode is customer decide where to go, whereever they go, we collect all location, pictures taken along the road and create a trip summary. Sweet to have. Like what most app or phone have today. On a trip with his/her family, for example, live in SH, Passing a town with historym, approaching a musesum/art gallery etc. - Lunch hour - Yelp for resturant recommendation. - From Program Marketing. Project Aspire - Route 66: UX only: Starts by downloading the route 66 experience from the marketplace. Once downloaded the user starts the experience by clicking on the Route 66 icon. This video and audio experience takes over the center stack, horizon display and audio to offer a curated experience as the user travels down route 66. It shows the entire route they will take before they start driving. When they come to the first stop on route 66 the video will talk about the stop, what they will see and allow them to take a photo inside the vehicle and outside of the vehicle using the vehicle cameras. These photos will be collected in the photo album located in the vehicles center stack and can be share with friends and social media at a later time. The curated experience will continue as the car travels through route 66. This experience can be stopped at started at anytime within the center stack. This experience uses features and technology like marketplace, web apps, photo album, vehicle position, vehicle cameras, connectivity, vehicle speakers and screens. | ECDX | Yu, Yaxing (Y.) <yyu55@ford.com> (Feature Owner);Shang, Vivian (Product Owner) |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | N | N | Y | Y |  |  | Yu, Yaxing (Y.) <yyu55@ford.com> (Feature Owner);Shang, Vivian (Product Owner) |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yu, Yaxing (Y.) <yyu55@ford.com> (Feature Owner);Shang, Vivian (Product Owner) |  |  | Phase 5 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | - |  | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_0160 |  |  | L# IoT(Internet of Things) 车家互联 | 1# Vehicle to Home | 车家互联 ( “小度家居”扫码) Vehicle to Home | 扫描车机端显示二维码关联 “小度家居”， 之后在该平台上面关联的设备都会显示在IVI 界面， 并且支持语音远程启动。“你好福特，打开我家里的扫地机器人”，提前开扫地机器人 Turn on cleaning robert/提前开灯 Turn on lights/提前开空调 Turn on AC(at home) an others in advance | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | C/O |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 1 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV1 | 2022-04-15 | 2022-04-30 | Group B | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0161 |  |  | L# IoT(Internet of Things) 车家互联 | 1# Vehicle to Home | 车家互联Project Aspire_General IOT (Smart Home)_CN (UI grahic upgrade -IVI端） |  | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y-1st | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | C/O |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 5 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV1 | 2022-04-15 | 2022-04-30 | Group B | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0162 |  |  | L# IoT(Internet of Things) 车家互联 | 2# Home to Vehicle | 家车互联Project Aspire_General IOT (Smart Home)_CN ( Home to Vehicle) | (UI grahic upgrade + Home to Vehicle Home (XiaoDu Smart Speaker) to vehicle platform | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | On Hold | C/O | Y | Y |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | On Hold |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 5 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | DCV1 | 2022-04-15 | 2022-04-30 | Group B | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0164 |  |  | M# Personalization & Account 账号和个人设置 | 1# Account 账号 | 车机端福特账号和百度账号同时登陆 (By 福特派 or 林肯之道App） Baidu and Ford/Lincoln Account dual Login | 车机端用户显示二维码， 用户通过福特派/林肯之道APP扫描二维码实现林肯/福特和百度账号互通。车机端会同时登陆福特/林肯账号和百度账号。 目前支持8个。 | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | 【福特phase5】MRD_账号模块个人中心 ID0164_林肯CDX707CDX747福特CDX788_V1.2_2021_05_14.docx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_0165 | F000172 | Enhanced Memory - FNV3 (CDX746/7) | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | 个性化设置记忆 Enhanced Memory | Seat settings, HMI Theme setting etc recorded in Enhanced Memory; 座椅，HMI 主题等多个性化设置选项profile记录在Enhanced Memory 里面. Normally support 3 profiles with hard switch. Some program go switchless. | ECDX | Xu, Andy (X.) <XXU71@ford.com> | Rahman, Naomee (N.) |  | Enhanced Memory APIM SPSS v1.11 October 18, 2019.pdf Enhanced Memory APIM Imp Guide v1.11 October 18, 2019.xlsx Enhanced Memory APIM SPSS With Soft Button v1.91 Feb 10, 2020.docx Enhanced_Memory_With_Soft_Button_Feature_Level_Specification_v1.2_Sep_27, 2020.docx | Core_Service_Supplier | 10% | 10% | 0% | 80% | Y | Y | C/O | N | C/O |  |  | Xu, Andy (X.) <XXU71@ford.com> |  |  | Y |  |  | Xu, Andy (X.) <XXU71@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_0166 | F002032 Rocket Setup - F002470 BLE Autopair - F002491 Autosave - F002830" | Personalized and Portable User Profile (PPP) (CDX746/7) | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | 基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP) | (ProgramMarketing）Personal Portable Profiles - Create a setup wizard on IVI/Fordpass for customer - Passenger account & profile (could be after J1 - OTA upgrade) - Portble profile. If user move to another vehicle , I can migration all my setting preference with this account/profile effortlessly. Project Aspire： Demostrated profile creation in the cnterstack for three driver profiles and one passenger profile. | EESE | Xu, Andy (X.) <xxu71@ford.com> |  |  |  | Core_Service_Supplier | 10% | 10% | 0% | 80% | Y-1st | Y-OTA | C/O | N | C/O |  |  | Xu, Andy (X.) <xxu71@ford.com> |  |  | Y |  |  | Xu, Andy (X.) <xxu71@ford.com> |  |  | Phase 5 | No | R26 | R26(R09) | 2023-04-28 | 2023-05-12 | DCV3 | 2022-07-11 | 2022-07-26 | Group C | - | - | - | -
SYNC+_0167 |  |  | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | 快捷设置Rocket setup | 4S交车前，工作人员会带着车主进行首次设置的界面 | ECDX | Gu, Xiaosheng (X.) <xgu14@ford.com> |  |  | Spec draft available Dec. 19th | Core_Service_Supplier | 10% | 10% | 0% | 80% | Y | N | N | Y | Y-TBD |  |  | Gu, Xiaosheng (X.) <xgu14@ford.com> |  |  | N | N |  | Gu, Xiaosheng (X.) <xgu14@ford.com> |  |  | Phase 2 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | - | - | - |  | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0170 | F004174 F000064 | Lincoln Embrace (Modified) (CDX746/7) | N# Engagement | 1# Appreciation | 车辆迎宾模式 Lincoln Embrace / Ford Welcome &Farewell | 福特品牌叫做 welcome & Farewell. 林肯品牌叫做 Lincoln Embrace 包含开关机动画，尾灯动画设置项 | EESE | Chen, Huizhen (H.) <hchen188@ford.com> | Fuller, Darnell (D.) |  | Lincoln Embrace_v2.2.2_CDX707_updated.pdf Welcome Farewell_Messages_Signals_V2.xlsx | HW_Tier1 | 80% | 0% | 0% | 20% | Y | Y | C/O | Y | C/O |  |  | Chen, Huizhen (H.) <hchen188@ford.com> |  |  | Y |  |  | Chen, Huizhen (H.) <hchen188@ford.com> |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0171 |  |  | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 智慧停车 Smart Parking | -查看实时车位；-搜索附近的停车场；-停车场付费（含二维码支付） | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R10 | DCV2 | 2022-05-30 | 2022-06-15
SYNC+_0172 |  |  | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 小额免密支付Seamless Payment | 百度带进来的部分生态，电影票，酒店，喜马拉雅 （不含美团外卖） 可以支持免密支付。 小额（单次不超过200CNY) 免密支付 （二维码扫描， 支付宝账号绑定。免密支付不支持微信付款） | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Lu, Chao (C.) <clu42@ford.com> |  |  |  | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R10 | DCV2 | 2022-05-30 | 2022-06-15
SYNC+_0173 |  |  | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 聚合支付 Aggregate payment +百度-我的钱包 Baidu Wallet | 我的钱包 支付设置 我的钱包 聚合收银台 我的钱包 账单 我的钱包 订单中心 order center； | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 1 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R10 | DCV2 | 2022-05-30 | 2022-06-15
SYNC+_0175 |  |  | P# Messaging & Alerts 消息和提醒 | 1# Message Center | 消息&消息中心 notification & notification center | Ford/Baidu both have the capability to push message. Phase 1- 30 text/Phase 4- H5,and more. Different "消息： - 消息展示方式：消息体、消息中心、状态栏的消息状态提醒 - 样式定义：消息体、状态提醒的样式 - 消息展示规则、优先级与冲突机制处理 消息中心： - 各种消息的接收、存储、查看" | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Phase 1 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R10 | DCV2 | 2022-05-30 | 2022-06-15
SYNC+_0184 |  |  | Q# Seamless Interface | 1# IVI Display & HMI | 双23.6寸全景屏+11.1寸横屏（可触摸）23.6'x2 (Pano -Non Touch) +11.1 Touch |  | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y-1st | Y-1st | C/O | N | C/O |  |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Phase 5 | Yes | R0 | R0(DCV Alpha) | 2021-03-19 | - | DCV Alpha | 2021-11-23 | - | Group A | - | - | - | -
SYNC+_0177 |  |  | Q# Seamless Interface | 1# IVI Display & HMI | 12.3寸横屏12.3' Landscape |  | HMI | [9 empty] | N | N | N | N | N | [5 empty] | N | N |  |  |  |  | Phase 1 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0178 |  |  | Q# Seamless Interface | 1# IVI Display & HMI | 12.8寸横屏12.8' Landscape | Xiao, Yun (Y.) | HMI | [9 empty] | N | N | N | N | N | [5 empty] | N | N |  |  |  |  | Phase 2 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0179 |  |  | Q# Seamless Interface | 1# IVI Display & HMI | 12.8寸竖屏12.8' Partrait |  | HMI | [9 empty] | N | N | N | N | N | [5 empty] | N | N |  |  |  |  | Phase 1 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0180 |  |  | Q# Seamless Interface | 1# IVI Display & HMI | 12寸横屏12' Landscape |  | HMI | [9 empty] | N | N | N | N | N | [5 empty] | N | N |  |  |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0181 |  |  | Q# Seamless Interface | 1# IVI Display & HMI | 13.2寸横屏13.2' Landscape |  | HMI | [9 empty] | Y | N | N | N | N | [5 empty] | N | N |  |  |  |  | Phase 3 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0182 |  |  | Q# Seamless Interface | 1# IVI Display & HMI | 15.5寸竖屏15.5' Portrait |  | HMI | [9 empty] | N | N | N | N | N | [5 empty] | N | N |  |  |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0183 |  |  | Q# Seamless Interface | 1# IVI Display & HMI | 27寸横屏 (可触摸）27' Landscape |  | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> | [8 empty] | Y | N | N | N | New |  |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | New | New |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0194 |  |  | Q# Seamless Interface | 3# Welcome/Farewell Animation | 开机/关机动画 IVI Display Welcome & Farewelll Animation (Display Visual Elements) | 目前分为Ford/Lincoln/Muatang BEV (CX727C) | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | Minor |  |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Y | New | New HMI layout and UE for 12.3'+27' Display | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0192 |  |  | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 联合驾趣 Co-Driver | 副驾区域显示车辆/行驶状态/可以发起POI 搜索， 设置导航路线. Lead CD542 27'L touch screen | HMI | Lee, Grace (G.) <glee51@ford.com>Liu, Luisa |  |  |  | Ford_InHouse | 0% | 0% | 90% | 10% | Y | N | N | N | New |  |  | Lee, Grace (G.) <glee51@ford.com>Liu, Luisa |  |  | Y | New |  | Lee, Grace (G.) <glee51@ford.com>Liu, Luisa |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0204 |  |  | Q# Seamless Interface | 4# HMI Theme | 精简（屏幕）模式 Calm Screen | 精简屏幕 - 提供预置背景图片供用户选择 | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | Minor |  |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Y | Minor |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV1 | 2022-04-15 | 2022-04-30 | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_0205 |  |  | Q# Seamless Interface | 4# HMI Theme | 多界面主题Multi-Theme | 3套主题每个主题都有白天/夜晚模式 | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  | HW_Tier1 | 70% | 10% | 10% | 10% | Y | Y | C/O | Y | Major |  |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R13 | R00 | 2022-08-30 | 2022-09-15
SYNC+_0203 |  |  | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 27寸主副驾屏幕区域交互模式 27" HMI 3 Modes 独自 (Solo)；合作驾驶 （Co-pilot)；独立（individual) Provide Enhaned Passenger Experience. | 独占 (Solo)；合作驾驶 （Co-pilot)；分屏（individual） | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | N | N | N | New |  |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Y | New |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0206 |  |  | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 界面个性化设置，和屏与屏之间内容分发HMI Screen Mirroring/Casting + HMI Personalization （再launcher，允许用户自定义）For Dual 23.6+11.1 | 从11.1 touch screen 投射到pano屏幕的不同区域 | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  | HW_Tier1 | 40% | 40% | 20% | 0% | Y-1st | Y-1st | C/O | N | C/O |  |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Phase 5 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_0221 | F001192/C | In-Vehicle Software Update (CDX746/7) | S# 系统升级 | 1# CAN 升级 | CAN 升级 |  | EESE | Wang, Jennifer (J.) <jwang373@ford.com> | Gudemaranahalli, Rohini Pr (R.) |  | In Vehicle Software Update (IVSU) APIM SPSS v2.8 May 30, 2019.pdf In Vehicle Software Update (IVSU) APIM Imp Guide v2.8 May 30, 2019.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Wang, Jennifer (J.) <jwang373@ford.com> |  |  | Y |  |  | Wang, Jennifer (J.) <jwang373@ford.com> |  |  | Phase 1 | No | R4 | R4(DCV Alpha4) | 2021-06-23 | - | DCV0 | 2022-03-16 | 2022-03-30 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_0223 | F001192/C | In-Vehicle Software Update (CDX746/7) | S# 系统升级 | 2# OTA | 多模块空中升级 Multi Module OTA (MMOTA) (including: USB Update for TCU and ECG; IVI VMCU, CCPU...) | Multi Module including sync+ | ECDX | Wang, Jennifer (J.) <jwang373@ford.com> | Gudemaranahalli, Rohini Pr (R.) |  | 547914_D_001_IVSU_Vehicle_Function_USB_Updates v3.0.pdf 547918_F_001_In Vehicle Software Update Vehicle FIS_v6.0.pdf 547923_A_001_IVSU Vehicle Function Download Manager v1.0.pdf 548171_H_001_IVSU_Vehicle_Function_HMI v4.0.docx 583758_B_001_IVSU_Vehicle_Function_Diff Updater_v2.0.pdf | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y | Y | C/O | Y | C/O |  |  | Wang, Jennifer (J.) <jwang373@ford.com> |  |  | Y |  |  | Wang, Jennifer (J.) <jwang373@ford.com> |  |  | Phase 4 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R10 | DCV2 | 2022-05-30 | 2022-06-15
SYNC+_0239 |  |  | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 最新版领先市场的地图导航能力 Leading Connected Map/Navi | 参照持续更新的Baidu Mainline 内容。Baseline 参照 Baidu Mainline 2020-11-30 版本feature 清单，同时应包含 落地前供应商能提供的最新版 | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y-1st | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase 5 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0208 | F001065 | Charge Status Indicator (CDX746/7) Programmable Electric Proconditioning and Charging (PEPC) | R# EV Features 新能源汽车功能 | 1# Charging | BEV Unique Charging | 充电状态Battery Status of Charge 充电冲突提醒Charge Conflict Notification Popups 出发时间设置Departure Time Settings 推荐充电时间Preferred Charge Time 剩余里程显示(云端)Cloud Enhanced Distance to Empty | ECDX | Yang, Jessica (Yu.) <yyang158@ford.com> | Rela, Pedro (P.R.) |  | Cloud Enhanced DTE APIM SPSS v1.2 Nov 19, 2020.docx EV Charge Programming v1 APIM SPSS v1.7 Aug 20, 2019_new.pdf | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | N | New | N | N |  |  | Yang, Jessica (Yu.) <yyang158@ford.com> |  |  | N | N |  | Yang, Jessica (Yu.) <yyang158@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0209 |  |  | R# EV Features 新能源汽车功能 | 1# Charging | 充电接口灯设置Charge Port Light Settings | On：Illuminates when plugging in，opening doors， pressing the unlock button on your remote and while charging. Off：Does not illuminate. Limited：Illuminates only when plugging in，opening doors，or pressing the unlock button on your remote. CD391PHEV 有三个选项 : “ on, off & Limited” U6xx只有两个选项“on，off” | EPE | Wu, Dean (D.) <dwu44@ford.com> |  |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | N | New | N | N |  |  | Wu, Dean (D.) <dwu44@ford.com> |  |  | N | N |  | Wu, Dean (D.) <dwu44@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0210 |  |  | R# EV Features 新能源汽车功能 | 3# EV Powertrain Related | 动力流动画显示Power Flow | Power Flow | EPE | Wu, Dean (D.) <dwu44@ford.com> |  |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | N | N | N | N |  |  | Wu, Dean (D.) <dwu44@ford.com> |  |  | N | N |  | Wu, Dean (D.) <dwu44@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | - |  | - | - | - | -
SYNC+_0215 |  |  | R# EV Features 新能源汽车功能 | 2# Distance to Empty (DTE) | 剩余里程显示Range Ring-Nav Screen (DTE) | Range Ring-Nav Screen 可续航里程在导航界面的显示 | EPE | Wu, Dean (D.) <dwu44@ford.com> |  |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | N | New | N | N |  |  | Wu, Dean (D.) <dwu44@ford.com> |  |  | N | N |  | Wu, Dean (D.) <dwu44@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0241 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | One-Shot 唤醒词加命令一起处理 | “你好福特， 帮我打开空调” Insead of " 你好福特“”在" "帮我打开空调“ | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  | Phase3 | No | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0222 |  |  | S# 系统升级 | 2# OTA | IVI空中升级SYNC+ OTA | SYNC+ OTA only. Housed under MMOTA from Phase 4 | ECDX | Pan, Yuan (Y.) <ypan23@ford.com> |  |  |  | Core_Service_Supplier | 40% | 0% | 0% | 60% | N | N | N | N | N |  |  | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | N | N |  | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Phase 1 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0247 |  |  | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 5G 车路协同 5G V2I | Global V2I: 4 feature offerings including 1-Traffic Light Information(TLI) 2-Green Light Notification (GLN) 3-Green Light Optimal Speed Advisory(GLOSA) 4-Red Light Violation Warning(RLVW). | ECDX | Li, Yifei (Y.) <nli26@ford.com> |  |  |  | Ford_InHouse | 0% | 10% | 60% | 30% | Y-1st | Y-1st | N | N | C/O |  |  | Li, Yifei (Y.) <nli26@ford.com> |  |  | Y | C/O |  | Li, Yifei (Y.) <nli26@ford.com> |  |  | Phase5 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | TBD |  |  |  | - | - | - | -
SYNC+_0224 |  |  | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | Special Memory | Like "Memory" on Apple Photo, send reminders to Lincoln way app or appear in Driver side screen about the memorable moments capture by 360 camera / internal camera/ dash camera (e.g. a memorable family trip, the longest driving date last year, a car accident, the biggest laugh/ yelling in car, the lowest energy consumption) - can be presented as a message or a short video (refer to Photo Memories function from iPhone) | [10 empty] | Y-1st | N | N | N | N | [5 empty] | N | N | [5 empty] | No | R19 | R19(R06) | 2022-09-07 | 2022-09-21 | - | - | - |  | - | - | - | -
SYNC+_0225 |  |  | B# Multimedia 多媒体 | 3# Music 音乐 | Kid Media Content/Game_CN | Integrate Kid education content into rear IVI system. Integrate some lite games for kids via voice recognition, such as 剪刀石头布 China Regional solution - integrate local app such as 少年得到, 凯叔讲故事, etc. | [5 empty] | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | N | N | N | N | [5 empty] | N | N | [5 empty] | No | R19 | R19(R06) | 2022-09-07 | 2022-09-21 | - | - | - |  | - | - | - | -
SYNC+_0226 |  |  | B# Multimedia 多媒体 | 3# Music 音乐 | Project Aspire _14C. (New) Karaoke – RED _CN |  | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  |  | SW_Tier1 | 10% | 80% | 0% | 10% | Y-1st | N | New | N | N |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | N | N |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  |  | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0227 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 8# Multizone Voice Control 分区语音控制 | Multi-zone voice control (1&2 Rows) | 4 Zones | EESE |  |  |  |  | HW_Tier1 | 60% | 40% | 0% | 0% | Y-1st | N | N | N | N | [5 empty] | N | N | [5 empty] | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | - | - | - |  | - | - | - | -
SYNC+_0228 | F003519 | My Seat Space (MSS) (CDX746/7) | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 3# MySeatSpace | MySeatSpace | The vision of MySeatSpace is to give customers an isolated immersive audio experience, enabling each occupant to listen to their own audio without disturbing others in the vehicle. This feature further enables in-car communication, private phone calls, media stream sharing and audio enhancements | EESE |  | Cintron, Austin (A.) |  |  | HW_Tier1 | 60% | 0% | 0% | 40% | Y-1st | N | New | N | N | [5 empty] | N | N | [5 empty] | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0229 |  |  | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | Video Interface Throughout Cabin (Rear Seat Monitor, w/ expanded request: allow 2R see 1R) | Driver can see the rear row situation on the screen by leveraging full cabin camera, to ease the worry on taking care of kid. (in-cabin baby monitoring) Kid(s) can see driver via 2nd row display and communicate w/ their parent, to avoid unsafe actions. (via 2nd row screen) | [5 empty] | SW_Tier1 | 20% | 80% | 0% | 0% | Y-1st | N | New | N | N | [5 empty] | N | N | [5 empty] | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0230 | "PPP - F002032 Rocket Setup - F002470 BLE Autopair - F002491 Autosave - F002830" | Personalized and Portable User Profile (PPP) (CDX746/7) | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | PPP with Stowable Steering Wheel position |  | ECDX |  | Stephens, Walter (W. L.) |  |  | Core_Service_Supplier | 0% | 10% | 0% | 90% | Y-1st | N | New | N | N | [5 empty] | N | N | [5 empty] | No | R26 | R26(R09) | 2023-04-28 | 2023-05-12 | DCV3 | 2022-07-11 | 2022-07-26 | Group C | - | - | - | -
SYNC+_0231 | F002812 | Mobile Device Viewer for Vehicle Cameras (CDX746/7) | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | Mobile Device Viewer | C/O global content Remote 360 view (exterior + full cabin camera) | ECDX | Shi, Stella (J.) <jshi32@ford.com> | Moreno Bautista, Ariana (A.) | [7 empty] | Y-1st | N | New | N | N |  |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | N | N |  | Shi, Stella (J.) <jshi32@ford.com> |  |  |  | No | - | - | - | - | TBD |  |  |  | - | - | - | -
SYNC+_0232 |  |  | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | Night Vision | from 747 prioritized global OTA concepts Act as a guardian by providing a sense of safety and security in dark areas by highlighting animals, pedestrians and objects in the field of view when the customer is away from or inside their vehicle | [5 empty] | HW_Tier1 | 100% | 0% | 0% | 0% | Y-1st | N | New | N | N | [5 empty] | N | N | [5 empty] | No | R14 | R14(R01) | 2022-04-20 | 2022-05-04 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0234 |  |  | R# EV Features 新能源汽车功能 | 4# Dealer Service Booking 经销商服务预定 | Valet Charging | - Valet Mode - Auto authorization (Preliminary access to vehicle) - Remote tracking of valet charging status - Remote monitoring of cabin | ECDX | Chen, Kiefer (Y.) <ychen290@ford.com> | [8 empty] | Y-1st | N | N | N | N |  |  | Chen, Kiefer (Y.) <ychen290@ford.com> |  |  | N | N |  | Chen, Kiefer (Y.) <ychen290@ford.com> |  |  |  | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0236 | F000812 | Cloud_Enhanced_DTE: 03 UPV0: MY24 CDX746/747 | R# EV Features 新能源汽车功能 | 2# Distance to Empty (DTE) | Cloud Based Battery Management System | Including： - Battery lifetime extension 电池寿命延长 - Range optimization 里程优化 - Battery health monitor 电池健康监测 - Real time driving recommendation based on DTC 基于DTC的实时驾驶建议 - Battery performance digital certificate | ECDX | Yang, Jessica (Yu.) <yyang158@ford.com> |  |  | Cloud Enhanced DTE APIM SPSS v1.2 Nov 19, 2020.docx | [5 empty] | Y-1st | N | New | N | N |  |  | Yang, Jessica (Yu.) <yyang158@ford.com> |  |  | N | N |  | Yang, Jessica (Yu.) <yyang158@ford.com> |  |  |  | No | - | - | - | - | TBD |  |  |  | - | - | - | -
SYNC+_0237 |  |  | J# Health & Wellness | 1# Air Quality 空气质量 | Smart Warm-up | System learns the departure time from calendar or daily use and pre-setup A/C and AAR before customer entering the vehicle. Enhanced experience on the current remote start. Suggest to leverage Lincoln Way for authorization of customer's calendar. | ECDX | [9 empty] | Y-1st | N | N | N | N | [5 empty] | N | N | [5 empty] | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0238 |  |  | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | Remote control of Frunk | Customer can remotely control frunk via Lincoln Way for express delivery. | ECDX | Lin, Shawn (X.) <xlin17@ford.com> | [8 empty] | Y-1st | N | N | N | N |  |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | N | N |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  |  | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0248 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 多轮交互/上下文交互 | 支持多轮交互和上下文理解 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0240 |  |  | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | 多模交互 Image recognition - Multi-Mode (Hand Gusture / Head / Emotion) | 基于手势(hand guesture)，点头/摇头（head)，作为指令识别。 具体逻辑见feature Document | EESE | Jia, Elaine (T.) <tjia2@ford.com> | [8 empty] | Y | N | N | N | N |  |  | Jia, Elaine (T.) <tjia2@ford.com> |  |  | N | N |  | Jia, Elaine (T.) <tjia2@ford.com> |  |  |  | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0249 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 取消两字拒识 (降低误识率采取的策略) | 取消两字拒识从phase 4开始：不执行两个字的语音指令，主要体现在可见即可说的语音能力. 针对可以在两个字的指令前增加“打开”或“点击”以执行语音指令，比如界面有“电话”，可说“打开电话”执行可见即可说指令 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0250 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 语音退出 | 可通过语音“退出”等，暂停语音服务 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0251 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 闲聊 | 没被其它垂类召回 最后才会走到闲聊，闲聊没有固定的策略，是算法模型，通过自己学习网上的聊天，系统自己生成聊天 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | No | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0252 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 3# Vehicle Services 车辆服务 | 车辆状态查询 | 胎压、油量、电量、违章 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0253 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 3# Vehicle Services 车辆服务 | 车主手册 | 车辆电子说明书 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | Ford_InHouse | 0% | 25% | 75% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | DCV1 | 2022-04-15 | 2022-04-30 | Group B | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_0255 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 6# Voice Command - IVI System Control 系统控制 | 专业导航 | 导航APP 打开导航/地图 退出导航/地图 继续导航 POI搜索 我要去<POI> 导航到<POI> 周边搜索 附近<POI> 附近的<POI> 添加途径点 中途去一下··· 半路去一下··· 添加途径点··· 导航+路线偏好 导航到<POI>不走高速 想去<POI>走省钱路线 导航去<POI>高速优先 导航去<POI>少收费 路线切换 推荐路线 高速优先 躲避拥堵 省钱路线 智能推荐 重新规划路线 地图缩放 放大地图 地图放到最大 缩小地图 地图缩到最小 路况开关 打开路况 关闭路况 昼夜模式切换 白天模式 黑夜模式 导航模式切换 查看全程 继续导航 巡航模式开关 打开巡航模式 关闭巡航模式 视图切换 车头朝上 正北模式 2D视图 3D模式 切换视图 路况查询 a点附近 具体道路 a点到b点 收藏当前点 收藏当前定位地点 收藏当前地址 常用地址 我要修改家庭地址 设置公司的地址 导航回家/回公司 我要回家/公司 导航回家/公司 我的位置查询 我的位置 我现在在哪儿 我在哪里 我现在在哪里 路况上报 上报路况 上报事故 上报施工 上报封路 上报事故 上报危险 导航音量 增加导航音量 导航音量小一点 打开导航声音 关闭导航声音 播报模式 打开新手模式 打开专家模式 行程中问答 如何行驶 红绿灯数量 驾车时长 前方限速 前方路况 酒店 电影院 美食 天气 限号 AR与2D map切换 打开AR导航 切换到AR导航 切换到专业导航 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0256 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 6# Voice Command - IVI System Control 系统控制 | AR导航 | AR与2D map切换 打开AR导航 切换到AR导航 切换到专业导航 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | N | N |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0257 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 6# Voice Command - IVI System Control 系统控制 | 系统控制(IVI模块系统级别） | 界面通用-返回主界面、界面导航、翻页、选择 BT电话-接听、挂断、拨打电话、搜索、更新通讯录、切换设备 音量控制 -增大音量、减小音量、系统静音 系统设置-蓝牙设置、WiFi设置、车载热点设置、更换主题、屏幕控制、精简屏幕控制、显示屏幕控制、驾驶模式控制 账户管理 -人脸识别 Launcher卡片-Launcher上可见即可说的支持说明 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | SW_Tier1 | 30% | 50% | 0% | 20% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0254 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 3# Vehicle Services 车辆服务 | EV/PHEV 充电功能 | 出发时间控制、充电计划控制、查找充电桩 "phase4： 1、周边搜：语音指令语义解析后根据AK来判断直接从服务端拉数据，还是把语义结果返回给语音客户端，再走地图搜索，在语音POI列表页显示，同时tts播报""为您找到了x个充电的地方，您要去第几个""，后续流程同语音搜索POI导航流程； 2、沿途搜：走目前默认逻辑" " CX482&CX483ICA： 1、周边搜：语音指令语义解析后根据AK来判断直接从服务端拉数据，还是把语义结果返回给语音客户端，再走地图搜索，在语音POI列表页显示，同时tts播报""为您找到了x个充电的地方，您要去第几个""，后续流程同语音搜索POI导航流程； 2、沿途搜：走目前默认逻辑" | EESE | Qi, Xuliang <xqi14@ford.com> | [9 empty] | N | N | N | N |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | N | N |  | Qi, Xuliang <xqi14@ford.com> | [5 empty] | - | - | - | - | - | - |  | - | - | - | -
SYNC+_0258 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 4# Life Services 生活服务 | 在线应用 | 在线应用-外卖、酒店、智慧停车场 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Qi, Xuliang <xqi14@ford.com> |  |  |  | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0259 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 香氛Digital Scent | 打开 打开香氛 关闭 关闭香氛 设置香味 换一种味道 打开第一/二/三种香味 调高浓度 浓度调高（步进为1） 浓度调到具体值（共3个等级，高中低） 调低浓度 浓度调低（步进为1） | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | SW_Tier1 | 10% | 60% | 0% | 30% | Y | Y | C/O | N | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | N | N |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_0260 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | Relax | relax模式调节 "打开森林模式/森林绮镜 进入森林模式/森林绮镜" "打开（大海模式/海屿之恋） 进入（大海模式/海屿之恋）" "打开馥郁暖心 进入馥郁暖心" "打开放松模式 进入放松模式" "关闭（森林模式/森林绮境） 退出（森林模式/森林绮境）" "关闭（大海模式/海屿之恋） 退出（大海模式/海屿之恋）" "关闭馥郁暖心 退出馥郁暖心" "关闭放松模式 退出放松模式" 换一(种/个)+放松模式 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 60% | 0% | 40% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  |  | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0263 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 驾驶辅助功能问答及播报 DAT - Voice Support | Wave I: FAPA - Lead by CX727/CD542; Wav II: b.Wave II: ADA1.0; Lane Biasing; Exit Warning; 逐步上车。 支持OTA. 具体见FO Spec 文档。 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf 01 Voice recognition feature list v2.4-20210416 - Phase 5.xlsx Phase VR new requirement-example for CAN.xlsx VR new requirement.xlsx | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  |  |  | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_0264 | F003951 | Electro Mechanical (EM) Register (CDX746/7) | J# Health & Wellness | 1# Air Quality 空气质量 | EM(Electro-Mechanical) Register | 新增电动马达，可以提供循环扫风模式（上下扫/左右扫）， 崭新的HMI 更加Iintuitive 直观的展现风向，用户可以直接touch 来改变风向；自动循环扫风模式设计有风向变化动效直观展示变化；有预设模式，并记忆用户设置； 支持单个出风口控制， 和驾驶员/副驾乘客侧 多个出风口捆绑设置； - China Lead: 707 会配合语音控制一起打造 | BI | Wang, Wei (W.) <wwang199@ford.com> | Smith, George (G.) |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st | Y-1st | Minor | TBD | C/O |  |  | Wang, Wei (W.) <wwang199@ford.com> |  |  | N | N |  | Wang, Wei (W.) <wwang199@ford.com> |  |  | Phase5 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_0261 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 2排座椅控制 2nd row Seat Control （7座车） | 3R Vehicle. Having this button to allow driver return the 2R Power seat easily without park & get off & return the seat. Return the 2R seat will give the way to the 3R. - Lead by U611ICA | EESE |  |  |  |  | Core_Service_Supplier |  |  |  |  | Y | N | N | N | N | [5 empty] | Y | New | [10 empty] | - | - | - |  | - | - | - | -
SYNC+_0266 |  |  | Q# Seamless Interface | 4# Intuitive Vehicle Control | Lancher - 3D Car Model with vehicle controls | This is a replacement of the format of the Launcher Car model with added functionality. Number of vehicle controls / functionalities will be added into this model. Need Kanzi rendering engine. the 3D object can be references in term of the structure for other programs, however it will still be a unique model for each program since each vehicle looks different. | HMI |  |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-1st | Major | Y | C/O | [5 empty] | Y | Major | New HMI layout and UE for 12.3'+27' Display |  |  |  | Phase 5 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0002 |  |  | System Function 系统功能 | Audio System 音频系统 | A2B Functional | A2B 音频数据总线高低音质衔接功能 | EESE | Liu, Yang (Y.) <YLIU307@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | Major | Y | C/O |  |  | Liu, Yang (Y.) <YLIU307@ford.com> |  |  | Y | C/O |  | Liu, Yang (Y.) <YLIU307@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0003 |  |  | System Function 系统功能 | Audio System 音频系统 | Active Noise Cancellationg (ANC) Tuning | ANC/ESE Tuning | VE | Yao, Keita (Y.) <yyao21@ford.com> |  |  | Electrical Sound Enhancement SPSS_Diagnostics.pdf Electrical Sound Enhancement SPSS V1.2 Oct 27, 2017.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | N | N | C/O |  |  | Yao, Keita (Y.) <yyao21@ford.com> |  |  | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  |  | Phase 2 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | - | - | - |  | - | - | - | -
SYNC+_Z0004 |  |  | System Function 系统功能 | Audio System 音频系统 | Audio Management |  | EESE | Li Alvin (LLI156@ford.com) |  |  | Audio Management APIM Imp Guide v1.5.1 Sep 26, 2018.xlsx Audio Management Logical to Physical CAN signal mapping Sep 7, 2018.docx Audio Management SPSS v1.5 Sep 7, 2018.pdf Audio Management Supplement SYNC 4.1 July 13th, 2018.docx Audio Settings Deployment May 9th, 2019.docx Audio Settings Logical to Physical CAN signal mapping Sep 6, 2018.docx Audio Settings v2 APIM Imp Guide v1.1 May 23, 2019.xlsx Audio Settings v2 APIM SPSS v1.1 May 23, 2019.pdf | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y | Y | Major | Y | C/O |  |  | Li Alvin (LLI156@ford.com) |  |  | Y | C/O |  | Li Alvin (LLI156@ford.com) |  |  | Phase 4 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2021-12-25 | -
SYNC+_Z0005 |  |  | System Function 系统功能 | Audio System 音频系统 | Brand Audio Config (Lincoln/Ford) | 品牌音箱调校 | EESE | Tian, Chen (C.) <CTIAN3@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | Major | Y | C/O |  |  | Tian, Chen (C.) <CTIAN3@ford.com> |  |  | Y | C/O |  | Tian, Chen (C.) <CTIAN3@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta1 | 2022-02-16 | - | Group B | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0006 |  |  | System Function 系统功能 | Audio System 音频系统 | Engine Sound Enhancement (ESE) | ESE Tuning 引擎音增强 | VE | Yao, Keita (Y.) <yyao21@ford.com> |  |  | Electrical Sound Enhancement SPSS_Diagnostics.pdf Electrical Sound Enhancement SPSS V1.2 Oct 27, 2017.pdf Electrical Sound Enhancement Sub-SYNC Imp Guide V1.0 Oct 27, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | N | N | C/O |  |  | Yao, Keita (Y.) <yyao21@ford.com> |  |  | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | - | - | - |  | - | - | - | -
SYNC+_Z0221 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting | CHUD (TFT HUD) - setting |  | EESE | Li, Jianxin (J.) <jli294@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | Y |  |  | Li, Jianxin (J.) <jli294@ford.com> |  |  | N | N |  | Li, Jianxin (J.) <jli294@ford.com> |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | R7 | DCV Beta2 | 2021-12-25 | -
SYNC+_Z0007 |  |  | System Function 系统功能 | Audio System 音频系统 | EQ tool |  | EESE | Liu, Yang (Y.) <yliu307@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | Major | Y | C/O |  |  | Liu, Yang (Y.) <yliu307@ford.com> |  |  | Y | C/O |  | Liu, Yang (Y.) <yliu307@ford.com> |  |  | Phase 2 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0008 |  |  | System Function 系统功能 | Audio System 音频系统 | Lincoln more speakers audio & ANC tuning | Lincoln more speakers audio & ANC tuning. Revel QLI | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | Major | N | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_Z0009 |  |  | System Function 系统功能 | Audio System 音频系统 | Lincoln Rear Audio Controls | Touch screen U611 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | Rear Audio Control APIM SPSS v1.4 Jul 1, 2017.pdf Rear Audio Control APIM Imp Guide v1.4 Jul 1, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | New | N | C/O |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 2 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_Z0010 |  |  | System Function 系统功能 | Audio System 音频系统 | Noise cancellation for Baidu VR |  | EESE | Qi Xuliang/Alvin Li |  |  | Voice recognition spec - 20191121.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi Xuliang/Alvin Li |  |  | Y | C/O |  | Qi Xuliang/Alvin Li |  |  | Phase 1 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0011 |  |  | System Function 系统功能 | Audio System 音频系统 | Radio reception test |  | EESE | Wu, Andy (Z.J.) <zwu21@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Wu, Andy (Z.J.) <zwu21@ford.com> |  |  | Y | C/O |  | Wu, Andy (Z.J.) <zwu21@ford.com> |  |  | Phase 1 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | DCV2 | 2022-05-30 | 2022-06-14 | Group C | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_Z0012 |  |  | System Function 系统功能 | Audio System 音频系统 | Rear Audio Controls | Ford - Hard button/Touch screen U611 | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Rear Audio Control APIM SPSS v1.4 Jul 1, 2017 Rear Audio Control APIM Imp Guide v1.4 Jul 1, 2017 | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | N | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | - | - | - | -
SYNC+_Z0013 |  |  | System Function 系统功能 | Audio System 音频系统 | Revel QIS 3D Audio (Audio System, settings) | Lincoln -only | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Audio Settings APIM SPSS v1.4 Nov 6, 2019 Audio Settings APIM Imp Guide v1.4 Nov 6, 2019 | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | N | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_Z0014 |  |  | System Function 系统功能 | Audio System 音频系统 | Speakers Config | Ford - up to 14 speakers. Lincoln - Up to 28 speakers （U611). Revel with QLI | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | Major | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0015 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Log system |  | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase5 CDC Log System Specification.docx | HW_Tier1 | 60% | 10% | 10% | 20% | Y | Y | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase 4 | Yes | R2 | R2(DCV Alpha2) | 2021-04-28 | - | DCV Alpha | 2021-11-23 | - | Group A | R4 | DCV Alpha | 2021-11-25 | -
SYNC+_Z0017 |  |  | ZZ# Foundemental Function 基础功能 | Basic Function | Implement/Integrate Ford SOA Structure |  | EESE | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | pending by Dapeng's input | Core_Service_Supplier | 25% | 0% | 0% | 75% | Y | Y | C/O | Y | C/O |  |  | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | Phase 1 | Yes | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0019 |  |  | System Function 系统功能 | Bluetooth Phone | 通话功能界面 请勿打扰 DO NOT IDSTURB 同步通讯录和通话记录 sync contacts& records 通讯录 contacts 通讯录搜索 拨号 dial 通话记录 records |  | EESE | Xu, Amy (X.) <xyafei@ford.com> |  |  | BT Connectivity APIM SPSS v3.0 Feb 14, 2019.pdf BT Connectivity APIM Imp Guide v3.0 Feb 14, 2019.xlsx Phase5 Bt多路电话--PRD.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Amy (X.) <xyafei@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0020 |  |  | ZZ# Foundemental Function 基础功能 | Carrier | Carrier | Carrier API integration with Baidu 与百度的接口集成- Carrier Backend Development 运营商后台开发 Carrier Feed API integration with FORD 与福特的接口集成 API integration with Baidu 与百度的接口集成 Carrier Backend Development 运营商后台开发 SIM Management SIM卡管理 retail data plan API, data usage query API, order API, payment API, invoice API, usage notification API, etc. RNR Carrier Feed associate 1 VIN with 2 SIMs; RNR platform; Online Mall; Jasper/M2M portal; Per APP billing, etc. | ECDX | Wang, Yuran<ywang422@ford.com> |  |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | C/O | Y | C/O |  |  | Wang, Yuran<ywang422@ford.com> |  |  | Y | C/O |  | Wang, Yuran<ywang422@ford.com> |  |  | Phase 1 | No | R11 | R11(DCV2) | 2022-01-12 | 2022-01-26 | DCV Beta1 | 2022-02-16 | - | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_Z0023 |  |  | ZZ# Foundemental Function 基础功能 | Carrier | 流量套餐app端流量查询购买 data plan query & oder | 流量套餐app端流量查询购买 data plan query & oder TCU- 用户流量统计及购买/Cellular data purchase and management Setting 流量管理 | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  |  | Ford_InHouse | 0% | 10% | 90% | 0% | Y | Y | C/O | Y | C/O |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | C/O |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R11 | DCV3 | 2022-06-30 | 2022-07-15
SYNC+_Z0024 |  |  | System Function 系统功能 | 信息多屏互动 | 2D Map in Cluster (study) |  | EESE | Ding, Sunny (X.) <XDING13@ford.com> |  |  |  | SW_Tier1 | 40% | 60% | 0% | 0% | Y | Y | C/O | N | C/O |  |  | Ding, Sunny (X.) <XDING13@ford.com> |  |  | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> |  |  | Phase 4 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_Z0025 |  |  | System Function 系统功能 | 信息多屏互动 | 导航服务，转向、ETA等信息 turn lane,radar detector & ETA | CAN互动，消息协议由Ford定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  |  | Core_Service_Supplier | 20% | 20% | 0% | 60% | Y | N | N | Y | N |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | - | - | - |  | R9 | DCV1 | 2021-12-25 | -
SYNC+_Z0026 |  |  | System Function 系统功能 | 信息多屏互动 | 来电号码及名称显示，接听，挂电话 incoming caller ID display，answer call， hang-up call | CAN互动，消息协议由Ford定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  |  | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y | Y | C/O | Y | C/O |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | - | - | - |  | R9 | DCV1 | 2021-12-25 | -
SYNC+_Z0027 |  |  | System Function 系统功能 | 信息多屏互动 | 仪表控制导航的功能：同步目的地收藏，设置目的地途经点Cluster control IVI Navigation。 | CAN互动，消息协议由Ford定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  |  | Core_Service_Supplier | 20% | 20% | 0% | 60% | Y | N | N | Y | N |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 2 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | - | - | - |  | R9 | DCV1 | 2021-12-25 | -
SYNC+_Z0028 |  |  | System Function 系统功能 | 信息多屏互动 | 广播，专辑信息、歌名、歌手 Album info,song & singer and Radio | CAN互动，消息协议由Ford定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  |  | Core_Service_Supplier | 60% | 20% | 0% | 20% | Y | N | N | Y | N |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 1 | Yes | R7 | R7(DCV Beta2) | 2021-09-15 | - | - | - | - |  | R7 | DCV Beta2 | 2021-12-25 | -
SYNC+_Z0030 |  |  | ZZ# Foundemental Function 基础功能 | Connected Services | Baidu数据平台 |  | ECDX | Fan, Henry (H.) <hfan11@ford.com> |  |  | PRD DUEROS_CVPP_Ford and Baidu Accoun_Phase 2_PRD_v1.4.pdf | SW_Tier1 | 0% | 90% | 10% | 0% | Y | Y | C/O | Y | C/O |  |  | Fan, Henry (H.) <hfan11@ford.com> |  |  | Y | C/O |  | Fan, Henry (H.) <hfan11@ford.com> |  |  | Phase 1 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0032 | F001040/E | Customer Connectivity Settings (CDX746/7) | ZZ# Foundemental Function 基础功能 | Connected Services | CCS (Connectivity Connectivity Setting) | 中国SYNC+ IVI端没有专门固定的设置界面。(global 版是一直有的）。中国采用用户授权 (手机端触发），允许后台获取用户数据（TCU） | ECDX | Gu, Regina (Q.) <qgu12@ford.com> | Pechlivanidis, Savvas (S.) |  | Customer Connectivity Settings Client APIM SPSS v1.5 Apr 22, 2020.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Gu, Regina (Q.) <qgu12@ford.com> |  |  | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  |  | Phase 4 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0033 |  |  | ZZ# Foundemental Function 基础功能 | Connected Services | Provisioning | 1. IVI TCU Provisioning - Baidu cloud, Ford cloud 2. TCU/ECG/BLEM provisioning - Baidu cloud, Ford cloud | ECDX | Cui, Rebecca (H.) <hcui2@ford.com> |  |  | Peripheral Module Provisioning SPSS v1.3 Apr 10, 2019.pdf | SW_Tier1 | 10% | 80% | 0% | 10% | Y | Y | C/O | Y | C/O |  |  | Cui, Rebecca (H.) <hcui2@ford.com> |  |  | Y | C/O |  | Cui, Rebecca (H.) <hcui2@ford.com> |  |  | Phase 4 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0035 |  |  | System Function 系统功能 | Diagnostic 诊断功能 | Fully Ford ECU Diagnostic&EOL |  | EESE | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 4 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_Z0036 |  |  | System Function 系统功能 | Diagnostic 诊断功能 | bezel diagnostic |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Bezel Diagnostics APIM SPSS v1.8 Sep 3, 2020.pdf Bezel Diagnostics APIM Imp Guide v1.8 Sep 3, 2020.xlsx Bezel Diagnostics Logical to Physical CAN signal mapping Sep 7, 2018.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | Minor | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  |  | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0037 |  |  | System Function 系统功能 | Diagnostic 诊断功能 | FNVx_Diagnostics_Analytics | log 小工具包含USB TCU Log， 以及上传云端。 | EESE | Liu, Dapeng (D.) <DLIU79@ford.com> |  |  |  | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y | Y | C/O | Y | C/O |  |  | Liu, Dapeng (D.) <DLIU79@ford.com> |  |  | Y | C/O |  | Liu, Dapeng (D.) <DLIU79@ford.com> |  |  |  | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_Z0038 |  |  | ZZ# Foundemental Function 基础功能 | General Connected Feature | Embedded Modem Reset/Master reset |  | ECDX | Gu, Regina (Q.) <qgu12@ford.com> |  |  | Embedded Modem Reset OnBoardClient v2 SPSS v1.4 May 9, 2019.pdf MasterReset-Diagram.vsdx | HW_Tier1 | 70% | 0% | 0% | 30% | Y | Y | C/O | Y | C/O |  |  | Gu, Regina (Q.) <qgu12@ford.com> |  |  | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0039 |  |  | ZZ# Foundemental Function 基础功能 | General Connected Feature | FNV2 - FCI Protocol | Ford Cloud Interface. 每个feature如需数据上传必须和云端签署的通信协议（安全相关）。用户感知不到 | ECDX | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | FNV2-FCI Protocol SPSS v1.1 August 17, 2018 | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y | C/O | Y | C/O |  |  | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | Phase 4 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0041 |  |  | ZZ# Foundemental Function 基础功能 | General Connected Feature | IP Pass Through Client |  | ECDX | Lin, Shawn (X.) <xlin17@ford.com> |  |  | SPSS/PRD IP Pass Through Client Imp Guide v1.1 September 4, 2018.xlsx IP Pass Through Client SPSS v1.1 September 4, 2018.pdf | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y | C/O | Y | C/O |  |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Phase 4 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0043 |  |  | ZZ# Foundemental Function 基础功能 | General Connected Feature | Wireless Interface Router(WIR) |  | ECDX | Lin, Shawn (X.) <xlin17@ford.com> |  |  | SPSS/PRD | Core_Service_Supplier | 20% | 0% | 0% | 70% | Y | Y | C/O | Y | C/O |  |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Phase 4 | Yes | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0044 |  |  | Vehicle Setting 车辆设置 | IVI Support Vehicle Function | Auto Dim | 自动灯光变暗 | EESE | Chen, James (J.) <JCHEN303@ford.com> |  |  |  | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | C/O | Y | C/O |  |  | Chen, James (J.) <JCHEN303@ford.com> |  |  | Y | C/O |  | Chen, James (J.) <JCHEN303@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0045 | F000549 | Selectable Drive Mode (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Drive Modes | 正常驾驶 运动驾驶 经济驾驶 | CED |  | Meza morales, Luis Enrique (L.) |  | Selectable Drive Mode SPSS v1.4 Aug 17, 2020.pdf Selectable Drive Mode APIM Imp Guide v1.4 Aug 17, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O | [5 empty] | Y | C/O |  |  |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0046 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Drive Modes |  | CED | Luis Meza |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | N | N | N | N | N |  |  | Luis Meza |  |  | N | N |  | Luis Meza |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0047 | F00158 F0003516 |  | Vehicle Control 车辆控制 | Seat Control 座椅控制 | Multi contour seat -Seat adjust -Custom Massage Patterns HMI for Multi-Contour Seats (U611) -Seat massage | 座椅调节 | EESE | Du, Hao (H.) <HDU9@ford.com> |  |  | Multi Contoured Seats Client V2 SPSS v1.5 June 9, 2020.pdf Multi Contoured Seats Client V2 Imp Guide v1.5 June 9, 2020.xlsx Power Lumbar Seat Client APIM SPSS v1.1 Apr 5, 2017.pdf Power Lumbar Seat Client APIM Imp Guide v1.1 Apr 5, 2017.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Du, Hao (H.) <HDU9@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> |  |  | Phase 1 | Yes | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_Z0050 | F001046/C | Wireless Accessory Charging (CDX746/7) | Vehicle Setting 车辆设置 | IVI Support Vehicle Function | Phone Wireless Charging notification | 无线充电提示 | EESE | Lyu, Qingtao (Q.) <qlyu@ford.com> | Grifka, Brian (B.M.) |  | Wireless Charging APIM SPSS v1.0 Oct 8, 2015.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Lyu, Qingtao (Q.) <qlyu@ford.com> |  |  | Y | C/O |  | Lyu, Qingtao (Q.) <qlyu@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0051 |  |  | System Setting 系统设置 | Sound Setting 音效设置 | Speed compensated volume 根据车速调整音量 |  | EESE | Li Alvin (LLI156@ford.com) |  |  | Audio Settings APIM SPSS v1.6 Sep 29, 2020.pdf Audio Settings APIM Imp Guide v1.6 Sep 29, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li Alvin (LLI156@ford.com) |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li Alvin (LLI156@ford.com) |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2021-12-25 | -
SYNC+_Z0052 |  |  | Vehicle Setting 车辆设置 | IVI Support Vehicle Function | TCS off | Soft button design（设计成软按键） | EESE | Goldbach, Michael (M.) <mgoldba3@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Goldbach, Michael (M.) <mgoldba3@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Goldbach, Michael (M.) <mgoldba3@ford.com> |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0054 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Automatically logging and uploading to log server -IVI Module | IVI本地产生的log可以某种特定的机制来执行log的自动上传到后台log服务器（支持Wifi/4G）；该log服务器有权限设定，向OEM开发；log具备标签机制，便于后台人员快速查找log文件;该方式为CDC中第一log方式。 | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase5 CDC Log System Specification.docx | HW_Tier1 | 80% | 10% | 10% | 10% | Y-1st | Y-1st | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase 5 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_Z0055 |  |  | System Function 系统功能 | Basic Feature 基础功能 | USB Log (secondary method) -IVI Module | 常规的利用外设U盘，通过某个特殊按键组合或者进入特定工程菜单，导入log数据到U盘中，中间需要有相应必要的UI交互。 Log菜单中支持对log开关和不同等级log的选择。该Log要包含Driving Info 和 Infotainment 两个Domain log日志 | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase5 CDC Log System Specification.docx | HW_Tier1 | 60% | 20% | 20% | 20% | Y-1st | Y-1st | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  |  | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0056 |  |  | System Function 系统功能 | Basic Feature 基础功能 | CAN signals （contain carry over signals） |  | EESE | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  |  | Y2021_FNV3_CMDB_v21.02_HS3_V2.DBC | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  |  | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  |  |  | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0057 |  |  | System Function 系统功能 | Basic Feature 基础功能 | FNOS |  | EESE | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | N | N | N | N | N |  |  | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  |  | N | N |  | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  |  | Phase 1 | Yes | - | - | - | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - |  | -
SYNC+_Z0058 | F000061 | Smooth Dimming (CDX746/7) | System Function 系统功能 | Basic Feature 基础功能 | Illumination |  | EESE | Chen, James (J.) <jchen303@ford.com> | Reis, Pedro (P.A.) |  | ES-H1BT-1A278-AA-V7.0.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | Minor |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0059 |  |  | System Function 系统功能 | System Upgrade 系统升级 | MCU software download (via CAN) |  | EESE | Xu, Tao (T.) <txu15@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xu, Tao (T.) <txu15@ford.com> |  |  | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  |  | Phase 1 | Yes | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV0 | 2022-03-16 | 2022-03-30 | Group B | R9 | DCV1 | 2022-04-30 | 2022-05-15
SYNC+_Z0060 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Power management |  | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | Power Management APIM SPSS v1.13 Sep 23, 2020.pdf Power Management APIM Imp Guide v1.13 Sep 23, 2020.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2021-12-25 | -
SYNC+_Z0069 | F000097/E | Auto Hold (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Auto Hold |  | EESE | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com> | James, Alex (J.A.) |  | Auto Hold APIM SPSS v1.1 Feb 20, 2017.pdf Auto Hold APIM Imp Guide v1.1 Feb 20, 2017.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0070 | F000016/E |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Auto Stop Start |  | EESE | Bush, Duane (D.R.) <dbush@ford.com> |  |  | Auto Start Stop SPSS v1.1 Oct 25, 2018.pdf Auto Start Stop APIM Imp Guide v1.1 Oct 25, 2018.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | N | Y | C/O |  |  | Bush, Duane (D.R.) <dbush@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Bush, Duane (D.R.) <dbush@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | - |  | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0064 |  |  | ZZ# Foundemental Function 基础功能 | Preset APP | 安装/运行福特指定的第三方软件/VP硬件对应的软件 | Baidu: 推荐PJ1用OTA方式推一个应用程序接口。 | EESE | Li,Justin |  |  |  | TBD |  |  |  |  | N | N | N | N |  |  |  | Li,Justin |  |  | N | N |  | Li,Justin |  |  | Phase 4 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_Z0071 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | BTT Light (Blind Spot Trailer Tow) |  | EESE | Shan, Susan (D.) <DSHAN@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | N |  |  | Shan, Susan (D.) <DSHAN@ford.com> |  |  | N | N |  | Shan, Susan (D.) <DSHAN@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0072 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Climate Menu | 按下此快捷键后IVI弹出空调控制页面，显示额外的空调控制软按键 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | Y |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | - |  | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0073 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Climate Mode Selection | 按下此快捷键后IVI弹出吹风模式弹窗，提供额外的三种吹风模式选择软按键 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | Y |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | - |  | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0074 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Climate Rear Control | 按下此快捷键后IVI弹出后排空调控制页面，提供额外的后排空调控制软按键 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | Y |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | - |  | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0068 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Adaptive Steering |  | EESE | Zhang, Isaac (S.) <szhang42@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | N |  |  | Zhang, Isaac (S.) <szhang42@ford.com> |  |  | N | N |  | Zhang, Isaac (S.) <szhang42@ford.com> |  |  | Phase 2 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0075 | VF004044 F000910 F000911 F000912 | Intelligent Adaptive Cruise Control (iACC) (CDX746/7) Intelligent Adaptive Cruise Control iACC (U6XX) | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Cruise Control Setting | Include following setting item: -Cruise control- Type (Adaptive, intelligent, normal), -tolerance | EESE | Cui, Victor (M.) <mcui5@ford.com> | Sarkar, Animesh (A.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | Major |  |  | Cui, Victor (M.) <mcui5@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0076 |  |  | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Driver alert |  | EESE | Song, Amy (S.) <ssong18@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Song, Amy (S.) <ssong18@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0077 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Engine Stop Start threshold |  | EESE | Bush, Duane (D.R.) <dbush@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | N | Y | C/O |  |  | Bush, Duane (D.R.) <dbush@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Bush, Duane (D.R.) <dbush@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | - |  | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0081 |  |  | System Function 系统功能 | Hardbutton Behavior | IVI interface via press physical switch 实体键IVI交互 Climate (menu and rear shortcut keys)-climate in rear display Climate (menu and rear shortcut keys)-Auto Air Refresh (AAR) Climate (menu and rear shortcut keys)-Rear- Tri or Quad Zone climate Lincoln Seats Lincoln Camera Shortcut key Lincoln Park Assist Shortcut key-Autoparking Lincoln Park Assist Shortcut key-Park aid on off Adaptive Steering BTT Light (Blind Spot Trailer Tow) Hill Decent Control Speed Limit Information / Speed Sign Recognition Traffic Sign Recognition Speed Limiter Rear Park Aid Tow Haul Engine Stop Start threshold PADI Grade Assits Trailer Sway Driver alert Hill start assist Wrong Way alert Cross Traffic Alert Blind Spot Pre Collision Assist (pre collision assist, distance indication, active breaking, evasive steer assist, alert sensitivity (high medium low)) Lane keeping mode (alert, aid, alert + aid), alert intensity (high, medium, low), sensitvity (normal, increased), lane keeping aid (on, off), lane keeping alert (high, medium, low, on, off) Cruise control- Type (Adaptive, intelligent, normal), tolerance Traction Control Auto Hold Auto Stop Start modified mini ICP Multi-Function Knob | climate in rear display；Auto Air Refresh (AAR)；Rear- Tri or Quad Zone climate Lincoln Seats shortcut key-Lincoln unique MCS seats and seat adjustment；4 or 2 way lumbar Lincoln Seats shortcut key-4 or 2 way lumbar Lincoln Camera Shortcut key-360, standard rear, etc, Includes all HMI views & Park aid on off；hard button trigger LPA screen hard button trigger LPA screen | HMI | Yao, Jeffery (J.) <jyao12@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Jeffery (J.) <jyao12@ford.com> |  |  | Y | C/O |  | Yao, Jeffery (J.) <jyao12@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0085 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Lincoln Park Assist Shortcut key | hard button trigger LPA screen | EESE | He, Michael (X.) <xhe22@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | He, Michael (X.) <xhe22@ford.com> |  |  | Y | C/O |  | He, Michael (X.) <xhe22@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0087 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Lincoln Seats shortcut key | Lincoln Seats shortcut key-4 or 2 way lumbar | EESE | Zhou, Weifu (W.) <wzhou43@ford.com> |  |  | Power Lumbar Seat Client APIM SPSS v1.1 Apr 5, 2017.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | N |  |  | Zhou, Weifu (W.) <wzhou43@ford.com> |  |  | N | N |  | Zhou, Weifu (W.) <wzhou43@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0088 | F000158 | Multi-Contour Seat (CDX746/7) | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Multi-Contoured Seats (Massage Seats) |  | EESE | Du, Hao (H.) <hdu9@ford.com> | Santos, Roger (R.M.) |  | Multi Contoured Seats Client V2 SPSS v1.5 June 9, 2020.pdf Multi Contoured Seats Client V2 Imp Guide v1.5 June 9, 2020.xlsx Power Lumbar Seat Client APIM SPSS v1.1 Apr 5, 2017.pdf Power Lumbar Seat Client APIM Imp Guide v1.1 Apr 5, 2017.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Du, Hao (H.) <hdu9@ford.com> |  |  | Y | C/O |  | Du, Hao (H.) <hdu9@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0091 | F000513 F004999 F000908 | Evasive Steer Assist (CDX746/7) Pre-Collision Assist (CDX746/7) | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Pre Collision Assist | PSA setting menu, refer setting SPSS VS-FUN-REQ-233569/B-Pre-Collision Assist (pre collision assist, distance indication, active breaking, evasive steer assist, alert sensitivity (high medium low)) | EESE | Zhu, Jinpeng (J.) <jzhu85@ford.com> | Wang, Haisu (H. Gelan, Ibrahim (I.S.)) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Zhu, Jinpeng (J.) <jzhu85@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhu, Jinpeng (J.) <jzhu85@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0092 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Rear Park Aid |  | EESE | He, Michael (X.) <xhe22@ford.com> |  |  | Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | He, Michael (X.) <xhe22@ford.com> |  |  | Y | C/O |  | He, Michael (X.) <xhe22@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0093 |  |  | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Speed Limit Information / Speed Sign Recognition |  | EESE | Cui, Victor (M.) <mcui5@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Cui, Victor (M.) <mcui5@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0094 |  |  | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Speed Limiter |  | EESE | Cui, Victor (M.) <mcui5@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Cui, Victor (M.) <mcui5@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0096 |  |  | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Traction Control |  | EESE |  |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O | [5 empty] | Y | Minor | New HMI layout and UE for 12.3'+27' Display |  |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0099 |  |  | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Wrong Way alert |  | EESE | Cui, Victor (M.) <mcui5@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Cui, Victor (M.) <mcui5@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0100 |  |  | Vehicle Setting 车辆设置 | Soft Button | Ambient Lighting - Breath Control (setting: on/off) |  | BI | Sun, Qiming (Q.) <qsun31@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | N |  |  | Sun, Qiming (Q.) <qsun31@ford.com> |  |  | N | N |  | Sun, Qiming (Q.) <qsun31@ford.com> |  |  | Phase 4 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-02-28 | 2022-03-14
SYNC+_Z0101 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Ambient Lighting 128 Color |  | BI | Sun, Qiming (Q.) <qsun31@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Sun, Qiming (Q.) <qsun31@ford.com> |  |  | Y | C/O |  | Sun, Qiming (Q.) <qsun31@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-02-28 | 2022-03-14
SYNC+_0070 |  |  | C# Intelligent Digital Assitant 智能数字助手 | 5# VPA 形象化语音助手 | 语音助手VPA 1.0 (形象化的语音助手） | Avatar Only. 语音助手形象化。 |  | Suo, Feifei (F.) <FSUO@ford.com> |  |  |  | Core_Service_Supplier | 0% | 0% | 0% | 100% | N | N | N | Y | N |  |  | Suo, Feifei (F.) <FSUO@ford.com> |  |  | N | N |  | Suo, Feifei (F.) <FSUO@ford.com> |  |  | Phase 3 | No | - | - | - | - | - | - | - |  | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0103 |  |  | Vehicle Setting 车辆设置 | Soft Button | Power Running Boards (PRB) |  | EESE | Wang Yan jing |  |  | Power Running Boards Softswitch InterfaceClient SPSS v1.0 October 5, 2018.pdf Power Running Boards Softswitch InterfaceClient Imp Guide v1.0 October 5, 2018.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | N | C/O |  |  | Wang Yan jing |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang Yan jing |  |  | Phase 4 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | - | - | - | -
SYNC+_Z0104 |  |  | Vehicle Setting 车辆设置 | Soft Button | Power Tailgate (FordPass/SYNC); |  | EESE | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  |  | TailGate Softswitch InterfaceClient Imp Guide v1.3 June 25, 2019.xlsx TailGate Softswitch InterfaceClient SPSS v1.3 June 25, 2019.pdf | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y | C/O | Y | C/O |  |  | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  |  | Phase 4 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-02-28 | 2022-03-14
SYNC+_Z0107 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Autosar |  | EESE | Song, Robert (J.) <jsong30@ford.com> |  |  | AUTOSAR SOW_2019.0-WGC1NJ5520MQ2-2.zip AUTOSAR\AUTOSAR SOW_2019.0-WGC1NJ5520MQ2.zip AUTOSAR\AUTOSAR SOW_2019.0.zip | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Song, Robert (J.) <jsong30@ford.com> |  |  | Y | C/O |  | Song, Robert (J.) <jsong30@ford.com> |  |  | Phase 4 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0083 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Lincoln Camera Shortcut key | Lincoln Camera Shortcut key-360, standard rear, etc, Includes all HMI views | EESE |  |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | N | Y | Y | [5 empty] | Y | C/O |  |  |  |  | Phase 2 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0084 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Lincoln Drive Assist Shortcut key | & Park aid on off；hard button trigger LPA screen | EESE | He, Michael (X.) <xhe22@ford.com> |  |  | Shortcut Key Driver Assist SPSS v1.2 Nov 26, 2019.pdf Shortcut Key Driver Assist APIM Imp Guide v1.2.1 Jan 24, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | Y |  |  | He, Michael (X.) <xhe22@ford.com> |  |  | Y | C/O |  | He, Michael (X.) <xhe22@ford.com> |  |  | Phase 2 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0108 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Ford Cyber Security Requirements |  | ECDX | Shao, Jian (J.) <JSHAO13@ford.com> |  |  | App_signing_requirements_ver 1.3.pdf Bluetooth_Security_Spec_1.0.docx C.13 Ford_CyberAssurance-SOW_ReleaseV1.3(EE).doc FESN Generation Spec_V0.6.pdf IVI Security Requirements v7.docx Key Material Requirements.docx Key Packaging Spec_V0.72.pdf Operating_Systems_Security_Requirements_RC3.docx Phase4 Security RR_20191024 .xlsx S26_Secure_Channel_v1_04_Release.doc Vehicle and Mobility Security Data Logging Standard.pdf Vehicle-Mobility-Security-Data-Logging_Standard_v06-04Apr18.pdf Vehicle_HotSpot_and_AP_Client_Specification_v.2_final.pdf Vehicle_to_Cloud_Security_Spec_1.1.pdf | HW_Tier1 | 30% | 40% | 20% | 10% | Y | Y | C/O | Y | C/O |  |  | Shao, Jian (J.) <JSHAO13@ford.com> |  |  | Y | C/O |  | Shao, Jian (J.) <JSHAO13@ford.com> |  |  | Phase 4 | No | R16 | R16(R05) | 2022-06-15 | 2022-06-29 | R05 | 2022-11-04 | 2022-11-18 | Group C | R13 | R00 | 2022-08-30 | 2022-09-15
SYNC+_Z0097 | F000913/C | Traffic Sign Recognition (CDX746/7) | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Traffic Sign Recognition | TSR setting item | EESE | Cui, Victor (M.) <mcui5@ford.com> | Sarkar, Animesh (A.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | N | Y | C/O | N | C/O |  |  | Cui, Victor (M.) <mcui5@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | - |  | - | - | - | -
SYNC+_Z0109 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Ford Ethernet |  | EESE | Xu, Tao (T.) <txu15@ford.com> |  |  | AutomotiveEthernetHardwareReviewTestMethod-00.06.03.400-AB.docx AutomotiveEthernetLinkImplementationSpecification-00.06.01.001-AC.docx AutomotiveEthernetModuleLevelDesignVerificationMethod-00.06.01.301-AB.docx AutomotiveEthernetPhysicalLayerSpecification-00.06.03.003-AB.docx AutomotiveEthernetSoftwareReviewChecklist-00.06.01.402-AB.docx AutomotiveEthernetSwitchChecklist-00.06.01.403-AA.docx AutomotiveEthernetSwitchImplementationSpecification-00.06.01.002-AA.docx AutomotiveEthernetSystemLevelDesignVerificationMethod-00.06.01.313-AB.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xu, Tao (T.) <txu15@ford.com> |  |  | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  |  | Phase 4 | Yes | R2 | R2(DCV Alpha2) | 2021-04-28 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R4 | DCV Alpha | 2021-11-25 | -
SYNC+_Z0110 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Ford Software development Requirements |  | EESE | Jian, Ashley (Yao.) <yjian@ford.com> |  |  | 2019_0 Release of Generic eSOW SW Attachment.zip | HW_Tier1 | 40% | 20% | 20% | 20% | Y | Y | C/O | Y | C/O |  |  | Jian, Ashley (Yao.) <yjian@ford.com> |  |  | Y | C/O |  | Jian, Ashley (Yao.) <yjian@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0089 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Multi-Function Knob |  | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | N |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 2 | No | - | - | - | - | - | - | - |  | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0090 |  |  | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | PADI |  | EESE | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | N | N |  |  | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | N | N |  | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | Phase 2 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | - | - | - |  | R6 | DCV Beta1 | 2022-02-28 | 2022-03-14
SYNC+_Z0111 |  |  | System Function 系统功能 | Basic Feature 基础功能 | FPD LINK III |  | EESE | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  |  | FPDLinkIIICableandConnectorAssemblyDesignVerficationChecklist-00.06.01.306-AA.docx FPDLinkIIICableandConnectorAssemblySpecification-00.06.01.005-AA.docx FPDLinkIIIImplementationReviewChecklist-00.06.01.405-AA.docx FPDLinkIIILinkImplementationSpecification-00.0 | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  |  | Y | C/O |  | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  |  | Phase 4 | Yes | R0 | R0(DCV Alpha) | 2021-03-19 | - | DCV Alpha | 2021-11-23 | - | Group A | R4 | DCV Alpha | 2021-11-25 | -
SYNC+_Z0112 |  |  | System Setting 系统设置 | Voice Setting 语音设置 | 语音设置 audio setting |  | EESE | Qi, Xuliang <xqi14@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Qi, Xuliang <xqi14@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0113 |  |  | System Setting 系统设置 | Bluetooth Setting 蓝牙设置 | 蓝牙连接 BT connection |  | EESE | Xu, Amy (X.) <xyafei@ford.com> |  |  | BT Connectivity APIM SPSS v3.0 Feb 14, 2019.pdf BT Connectivity APIM Imp Guide v3.0 Feb 14, 2019.xlsx Phase5 Bt多路电话--PRD.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Amy (X.) <xyafei@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0114 | F001050 | Clock (U6XX) | System Setting 系统设置 | General Setting 常规设置 | 日期和时间设置 date&time setting | 详情请参考Ford的HMI Spec | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Global Clock Strategy Specification Ver 1.8.pdf APIM Clock Strategy v1.4 Feb 6 2014.pdf APIM Clock Strategy ImplGuide v1.4 Oct 9, 2020.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0078 |  |  | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Grade Assits |  | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | N |  |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Phase 2 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0079 | F000090/C | Hill Descent Control (CDX746/7) | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Hill Decent Control |  | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> | Brown, Andrew (A.A.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | New |  |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  |  | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0080 |  |  | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Hill start assist | Aways On, on need IVI implement a soft switch | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | Y |  |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Phase 2 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0115 |  |  | System Setting 系统设置 | Display Setting 显示设置 | Brightness |  | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | ES-H1BT-1A278-AA-V6.5_DRAFT.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0116 |  |  | System Setting 系统设置 | Display Setting 显示设置 | Display off |  | EESE | Chen, James (J.) <jchen303@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 4 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0117 |  |  | System Setting 系统设置 | Display Setting 显示设置 | 显示/亮度设置 display/brightness setting | 详情请参考Ford的HMI Spec | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | ES-H1BT-1A278-AA-V6.5_DRAFT.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0095 |  |  | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Tow Haul |  | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | N |  |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Phase 2 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0120 |  |  | System Function 系统功能 | Audio System 音频系统 | Support Ford external DSP module by A2B |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Analog Devices A2B Hardware Review 000603.512 AD.doc Analog Devices A2B link Data Link and Physical Layer 000603 501 AD.doc Analog Devices A2B Link Implementation Specification V1_1.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | Major | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 4 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0098 |  |  | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Trailer Sway |  | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | N |  |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | N | N |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | Phase 2 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-02-28 | 2022-03-14
SYNC+_Z0121 |  |  | System Setting 系统设置 | General Setting 常规设置 | Disclaimer | Content to be aligned with CVPP and baidu | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0122 |  |  | System Setting 系统设置 | Other 其他 | Driving restriction | To Stop/cancel video playing when condition not correct. | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Driver Restrictions APIM SPSS v1.3 October 26 2018.pdf Driver Restrictions APIM Imp Guide v1.3.1 September 10 2020.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Phase 1 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0125 |  |  | System Setting 系统设置 | General Setting 常规设置 | 关于本机 | IVI sw version, VIN IVI ESN, TCU ESN… | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0126 |  |  | System Setting 系统设置 | General Setting 常规设置 | 恢复出厂设置 reset（Master Reset） | 详情请参考Ford的HMI Spec | ECDX | Gu, Regina (Q.) <qgu12@ford.com> |  |  | Embedded Modem Reset OnBoardClient v2 SPSS v1.4 May 9, 2019.pdf MasterReset-Diagram.vsdx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Gu, Regina (Q.) <qgu12@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Gu, Regina (Q.) <qgu12@ford.com> |  |  | Phase 1 | Yes | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2021-12-25 | -
SYNC+_Z0127 |  |  | System Setting 系统设置 | Sound Setting 音效设置 | 声音设置 sound setting | 详情请参考Ford的HMI Spec Mixed Mode Presets Autoset Preset Sound Settings - Treble/Mid/Bass Sound Settings - Balance/Fade Sound Settings - Speed Compensated Volume Sound Settings - Occupancy Mode | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Audio Settings APIM SPSS v1.6 Sep 29, 2020.pdf Audio Settings APIM Imp Guide v1.6 Sep 29, 2020.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0128 |  |  | System Setting 系统设置 | Wi-Fi Setting Wi-Fi 设置 | Wifi 热点 Wifi Hot Spot | Wifi hot spot (WHS)- SSID or password. Refer to current sync 3 | ECDX | Pan, Yuan (Y.) <ypan23@ford.com> |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Phase 2 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0129 |  |  | System Setting 系统设置 | Wi-Fi Setting Wi-Fi 设置 | wifi设置 wifi setting | 详情请参考Ford的HMI Spec | EESE | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | WiFi Configuration APIM SPSS v1.5 Sep 7, 2017.pdf WiFi Configuration APIM Imp Guide v1.5 Sep 7, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0130 |  |  | System Function 系统功能 | Others 其他 | 百度输入法 Baidu Input | 拼音+手写+数字、符号、英文键盘 和其它 且支持联想、记忆、当前热词功能等。 | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Phase 1 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0152 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Ford Clock Strategy |  | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | APIM Clock Strategy v1.4 Feb 6 2014.pdf APIM Clock Strategy ImplGuide v1.4 Oct 9, 2020.xlsx Global Clock Strategy Specification Ver 1.8.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | Phase 4 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0009 |  |  | H# Service & Maintenance 车主服务 | 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | 车辆状态 Vehicle Status (Vehicle Locator车辆位置, Mileage总里程, DTE 续航里程， Tire Pressure 胎压）On IVI 或Fordpass/Lincoln Way， 同时支持智能音箱在家查询. | (Vehicle Locator车辆位置, Mileage总里程, DTE 续航里程， Tire Pressure 胎压。 车辆位置-熄火时最后的位置同步到FordPass/Lincoln Way.位置准确度有限， 更多用来标准大概区域。 IVI 端显示内容取决于项目仪表(大小，其他影响), 具体项目落地情况需与项目确认. Phase 1- 信息来源不同Cluster/TCU/ Phase 2- 全部TCU 提供信息 | EESE | Lu, Chao (C.) <clu42@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | N | N | N | N | N |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | N | N |  | Lu, Chao (C.) <clu42@ford.com> |  |  | Phase 1 | No | - | - | - | - | - | - | - |  | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0153 |  |  | System Function 系统功能 | Basic Feature 基础功能 | Location Service （仪表指南针，etc.） |  | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Location Service APIM SPSS v1.10 July 10, 2019.pdf Location Service APIM Imp Guide v1.10 July 10, 2019.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | Phase 4 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0155 | F000974/E | WiFi Hotspot (CDX746/7) | ZZ# Foundemental Function 基础功能 | General Connected Feature | 车载热点 WifiHotspot | Ford TCU Related features (Modem Reset, WiFi, WiFi Hotspot)- TCU transfer CAN data to IVI Wifi hot spot (WHS)- SSID or password. Refer to current sync 3 Wi-Fi hotspot - TCU as WIFI Server (IVI provide HMI) | ECDX | Pan, Yuan (Y.) <ypan23@ford.com> | Nahle, Wassim (W.) |  | WiFi Hotspot OnBoardClient v2 SPSS v1.4 September 22, 2020.pdf WiFi Hotspot OnBoardClient v2 Imp Guide v1.4 September 22, 2020.xlsx | HW_Tier1 | 80% | 0% | 0% | 20% | Y | Y | C/O | Y | C/O |  |  | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Phase 4 | No | R9 | R9(DCV0.1) | 2021-11-17 | 2021-12-01 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0156 |  |  | System Function 系统功能 | Others 其他 | Consumer Behavior Data (IVI related)埋点 | 统计功能使用情况和用户偏好 Statistics feature usage and user preferences | EESE | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | C/O | Y | C/O |  |  | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  |  | Y | C/O |  | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  |  | Phase 1 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | DCV2 | 2022-05-30 | 2022-06-14 | Group C | R12 | DCV4 | 2022-07-30 | 2022-08-15
SYNC+_Z0159 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | AC - face | 空调吹脸 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0160 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | AC - feet | 空调吹脚 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0161 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | AC on/off | AC开关 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0162 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Auto AC | 自动 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0163 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Demist | 除雾 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0164 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Driver temp | 主驾温度 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0165 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Dual AC | 双区空调 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0166 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Fan | 风速 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0167 | F003518 |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Front Row Seat Heated | 前排座椅加热 | EESE | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Du, Hao (H.) <HDU9@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0168 | F003518 |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Front Seat Vent | 前排座椅吹风 | EESE | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Du, Hao (H.) <HDU9@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0127 |  |  | I# Safety & Security 安全 | 1# Emergency Services 紧急救援 | 紧急救援Emergency Assistance (EA) | 紧急救援，被动触发。 Emergency Assistance will be triggered when airbag pump out or oil pipe line cut off. An emergency call will be placed to China call center (95智驾 by customer's phone connected with Sync+ by bluetooth, and after line open, call center will provide corresponding services per customer's needs. | ECDX | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | Draft Emergency Assistance APIM_DuerOS SPSS.pdf | Ford_InHouse | 25% | 0% | 75% | 0% | Y | N | N | Y | N |  |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | N | N |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | Phase 3 | No | - | - | - | - | - | - | - |  | R8 | DCV0 | 2022-03-30 | 2022-04-14
SYNC+_Z0169 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Max AC | 空调最大 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0170 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Max windshield | 挡风除霜 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0171 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Passenger temp | 副驾温度 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0172 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Rear climate fan | 后排空调风速 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0173 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Rear climate mode | 后排空调模式 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0174 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Rear climate temp | 后排空调温度 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0175 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Recirc. | 车内循环 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0176 | F000123 |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Steering wheel heated | 方向盘加热 | EESE | Yan, Sophie (C.) <cyan10@ford.com> |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yan, Sophie (C.) <cyan10@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yan, Sophie (C.) <cyan10@ford.com> |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_0163 |  |  | M# Personalization & Account 账号和个人设置 | 1# Account 账号 | 车机端百度账号登陆(By 福特派/lincoln app) Baidu Login | 车机端用户显示二维码， 用户通过福特派APP扫描二维码实现福特账号和百度账号互通。 二维码车机端扫码 手机端福特派&百度账号互通 Fordpass & Baidu account connection 与福特账号打通 connected with Ford account 车机百度账号登录 Baidu account login | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | 【福特phase5】MRD_账号模块个人中心 ID0164_林肯CDX707CDX747福特CDX788_V1.2_2021_05_14.docx | SW_Tier1 | 0% | 100% | 0% | 0% | N | N | N | Y | N |  |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Phase 1 | No | - | - | - | - | - | - | - |  | - | - | - | -
SYNC+_Z0177 |  |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Windshield | 挡风玻璃 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 1 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0178 | F001027 |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-Adaptive headlamps |  | EESE | Zhou, Travis (C.X.) <czhou17@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Zhou, Travis (C.X.) <czhou17@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhou, Travis (C.X.) <czhou17@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2021-12-25 | -
SYNC+_Z0180 | F001014 | Home Safe Light (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-Autolamp delay |  | EESE | Zhou, Travis (C.X.) <czhou17@ford.com> | D'Agostino, Antonio (A.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Zhou, Travis (C.X.) <czhou17@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhou, Travis (C.X.) <czhou17@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2021-12-25 | -
SYNC+_Z0181 | F001006 |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-daytime lights |  | EESE | Zhou, Travis (C.X.) <czhou17@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Zhou, Travis (C.X.) <czhou17@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhou, Travis (C.X.) <czhou17@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2021-12-25 | -
SYNC+_Z0182 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-Glare Free lighting |  | EESE | Song, Amy (S.) <ssong18@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Song, Amy (S.) <ssong18@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_Z0183 | F000052/C | Courtesy_Lighting: 03 UPV0: MY24 CDX746/747 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-welcome lights |  | EESE | Wu, Bella (Y.) <ywu150@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Wu, Bella (Y.) <ywu150@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wu, Bella (Y.) <ywu150@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_Z0185 | F000063/C | Ambient Lighting (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | 单色氛围灯 single color ambient lighting | 车型只支持单色氛围灯 | EESE | Li, Xuedong (X.) <XLI244@ford.com> | Gemade, Ralph (R.) |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | New |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 1 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_Z0186 | F000063/C | Ambient Lighting (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | 多色氛围灯 multi color ambient lighting | 车型支持多色氛围灯 | EESE | Li, Xuedong (X.) <XLI244@ford.com> | Gemade, Ralph (R.) |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | New |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 1 | No | R8 | R8(DCV0) | 2021-10-20 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_Z0187 | F004256 F002951 F004255 | Automatic Lock Suite (CDX746/7) Walk Away Lock (CDX746/7) Power Central Lock Suite (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> | SOUZA, GABRIELLE DESIREE (G.C.) Griffin, Zachary (Z. D.) Silva, Nivea (N.B.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_Z0197 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Mirror Setting |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> | Strzelczyk, Anthony (A.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_Z0199 |  |  | System Function 系统功能 | Audio System 音频系统 | Active Noise Cancellation |  | EESE | Ding, Jack (F.) <fding@ford.com> |  |  | ANC SPSS v1.4 Oct 7 2013.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | Minor | Y | C/O |  |  | Ding, Jack (F.) <fding@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Ding, Jack (F.) <fding@ford.com> |  |  | Phase 2 | Yes | R5 | R5(DCV Beta) | 2021-07-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R10 | DCV2 | 2022-05-30 | 2022-06-15
SYNC+_Z0200 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Air suspension |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | Y |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_Z0201 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Alarm (ask on exit ,sensor set, perimeter, all sensors active) |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0202 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Aux Heater |  | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | N |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0203 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Cargo Loading |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | N |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0204 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Chimes |  | EESE | Cao,Helen |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Cao,Helen |  |  | Y | C/O |  | Cao,Helen |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0205 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Easy access height |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | C/O | Y | Y |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0206 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Easy Entry / Easy Exit (Seat Adjustment) |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0208 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Park Heater |  | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | Y | N |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0209 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Park Lock Control |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0210 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Passenger Airbag |  | EESE | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0211 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Power running boards (auto, on, off) |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0212 | F000162 |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Rear liftgate |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0213 | F000400 |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Remote start (activate, climate, auto, last setting, seats and wheels, duration) |  | EESE | Li, Shiyuan (S.) <sli163@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Shiyuan (S.) <sli163@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Shiyuan (S.) <sli163@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R8 | DCV0 | 2022-01-27 | -
SYNC+_Z0214 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Silent Mode |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0215 |  |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Tire Mobility Kit |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0216 | F000139 |  | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Windows (remote open/close) |  | EESE | Li, Shiyuan (S.) <sli163@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Shiyuan (S.) <sli163@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Shiyuan (S.) <sli163@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0217 | F000066 | Front Automatic Wiping (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Wipers (courtesy, rain, reverse) |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> | Johnson, Geoffrey (G.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R6 | DCV Beta1 | 2022-01-27 | -
SYNC+_Z0218 |  |  | System Setting 系统设置 | General Setting 常规设置 | Unit Setting-Measurement Units | Same as ford settings | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020.pdf Vehicle Settings APIM Imp Guide v1.24 Nov 2, 2020.xlsx Vehicle Settings Logical to Physical CAN signal mapping Oct 30, 2019.docx | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R7 | R7(DCV Beta2) | 2021-09-15 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0219 |  |  | System Setting 系统设置 | General Setting 常规设置 | Unit Setting-Temperature | Same as ford settings | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020.pdf Vehicle Settings APIM Imp Guide v1.24 Nov 2, 2020.xlsx Vehicle Settings Logical to Physical CAN signal mapping Oct 30, 2019.docx | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R7 | R7(DCV Beta2) | 2021-09-15 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0222 |  |  | Vehicle Setting 车辆设置 | Soft Button | SoftButton - Chauffeur Seat Control |  | EESE | TBD | [8 empty] | N | N | N | N | N |  |  | TBD |  |  | N | N |  | TBD |  |  |  | No | - | - | - | - | - | - | - |  | R5 | DCV Beta | 2021-12-25
SYNC+_Z0220 |  |  | System Setting 系统设置 | General Setting 常规设置 | Unit Setting-Tire Pressure Units; | Feature owners are from related functions | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020.pdf Vehicle Settings APIM Imp Guide v1.24 Nov 2, 2020.xlsx Vehicle Settings Logical to Physical CAN signal mapping Oct 30, 2019.docx | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | C/O | Y | C/O |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Phase 2 | No | R7 | R7(DCV Beta2) | 2021-09-15 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R5 | DCV Beta | 2021-12-25 | -
SYNC+_Z0227 | vFG000456/ vFG000284/ vFG000668/ vFG002069/ F000903 | Lane Keeping System (CDX746/7) | Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 车道偏离预警 Lane Keeping System(LKA+LDW） |  | EESE | Zhang, Wayne (W.R.) <wzhan114@ford.com> | Patil, Pranav (P.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Zhang, Wayne (W.R.) <wzhan114@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhang, Wayne (W.R.) <wzhan114@ford.com> |  |  | Phase 4 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0229 | F000285/B | Driver Alert System (CDX746/7) | Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 驾驶员警告系统 Driver Alert System (DAS) | 利用车外front camera，检测车道线和行车轨迹来判断驾驶员状态（疲劳+酒家+不清醒） | EESE | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Song, Amy (S.) <ssong18@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  |  | Phase 4 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0230 | FO to confirm VSEM ID | Active Drive Assist 1.2 (CDX746/7) | Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 高速主动辅助 Active Driver Assist or ADA (DAT2.0) | high way assit 由两种模式， 其中hands free 的就是ADA. Active Driver Assist will control steering, throttle, and braking of the vehicle with only driver supervision. The feature is only availible on prequalified sections of divided highways called "Blue Zones: while the drivers' attention is on the road. The driver's attention will be monitored with a driver facing camera. ADA buids upon ACC with lane centerin to offer hands free mode on highways while in the blue zone. | EESE | Ni, Anthony (H.A.) <hni1@ford.com> | Gotadki, Shruti (S. P.) |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Ni, Anthony (H.A.) <hni1@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Ni, Anthony (H.A.) <hni1@ford.com> |  |  | Phase 4 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0231 | F004650 | Auto High Beam Controller (CDX746/7) | Vehicle Setting 车辆设置 | DAT Setting | 3# Help Me See 视觉辅助 - 自适应远光灯 Auto High beam | uses the forward looking camera to identify leading or oncoming vehicles. If the vehicle in front is determined to be too close, the headlamps automatically switch from the high beam setting to the low beam setting. Once an on-coming vehicles passes, or th leading vehicle is out of range, the vehicle will automacticakky switch back to the high beam setting. | EESE | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Song, Amy (S.) <ssong18@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  |  | Phase 4 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0236 |  |  | Vehicle Control 车辆控制 | Seat Control 座椅控制 | Third Row Seat Position Control | To be confirm |  | TBD |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st(TBD) | N | N | N | N |  |  | TBD |  |  | N | N |  | TBD |  |  | Phase5 | No | R14 | R14(R01) | 2022-04-20 | 2022-05-04 | - | - | - |  | - | - | - | -
SYNC+_Z0238 |  |  | Vehicle Control 车辆控制 | Seat Control 座椅控制 | Driver Information Display Control (DIDC) | To be confirm |  | TBD |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st(TBD) | N | N | N | N |  |  | TBD |  |  | N | N |  | TBD |  |  | Phase5 | No | R14 | R14(R01) | 2022-04-20 | 2022-05-04 | - | - | - |  | - | - | - | -
SYNC+_Z0240 |  |  | ZZ# Foundemental Function 基础功能 | 1# Display | 后排娱乐空调控制面板 Rear entertainment control(Climate/Audio) - U611 | 扶手箱后面有个小屏。CAN互动，消息协议由Lincoln定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | Rear Audio Control APIM SPSS v1.4 Jul 1, 2017.pdf Rear Audio Control APIM Imp Guide v1.4 Jul 1, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | C/O | N | C/O |  |  | Chen, James (J.) <jchen303@ford.com> |  |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  |  | Phase 1 | No | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | - | - | - |  | - | - | - | -
SYNC+_Z0255 | F003110 | Rear Seat Controls Lockout (Modified) (CDX746/7) | Vehicle Control 车辆控制 | Seat Control 座椅控制 | Rear Seat Controls Lockout: - Window - Door - Audio - Climate | To be confirm | EESE | TBD | Ganna, Spurthi Varma (S.) |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st(TBD if impact IVI) | N | New | N | N |  |  | TBD |  |  | N | N |  | TBD |  |  | Phase5 | No | R14 | R14(R01) | 2022-04-20 | 2022-05-04 | - | - | - |  | - | - | - | -
SYNC+_Z0232 |  |  | Vehicle Setting 车辆设置 | DAT Setting | 4# Help Me Avoid Collisions 避免碰撞辅助 - 十字路口碰撞预警 Intersection Assist | 有不同版本 1.0/2.0/2.2 | EESE | Wang, Lynn (X.) <xwang187@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Wang, Lynn (X.) <xwang187@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Lynn (X.) <xwang187@ford.com> |  |  | Phase 4 | Yes | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0277 |  |  | Vehicle Setting 车辆设置 | DAT Setting | 4# Help Me Avoid Collisions 避免碰撞辅助_COLLISION MITIGATION SYS(FBFAB) |  | EESE | Wang, Lynn (X.) <xwang187@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Wang, Lynn (X.) <xwang187@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Lynn (X.) <xwang187@ford.com> |  |  | Phase2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0278 |  |  | Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助_车距提示 DADI(Distance Alert, Distance Indicator) |  | EESE | Cui, Victor (M.) <mcui5@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Cui, Victor (M.) <mcui5@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  |  | Phase2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0279 | F002054 |  | Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助_高速驾驶辅助Highway Assist - Lane Biasing(DAT2.1 new feature) | IVI need implement Lan Biasing Setting menu | EESE | Song, Amy (S.) <ssong18@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Song, Amy (S.) <ssong18@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  |  | Phase2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0280 |  |  | Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助_Assisted Lane Change |  | EESE | Song, Amy (S.) <ssong18@ford.com> |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Song, Amy (S.) <ssong18@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  |  | Phase2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_Z0281 | F000742 | Lane Centering Assist LCA (U6XX) | Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助_Lane Centering Assist | 在中控侧需要实现带有车道保持居中的CC设置项，具体参考Setting文档VS-SR-REQ-333005/C-with Lane Centering | EESE | Ni, Anthony (H.A.) <hni1@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O | Y | C/O |  |  | Ni, Anthony (H.A.) <hni1@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Ni, Anthony (H.A.) <hni1@ford.com> |  |  | Phase2 | No | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A | R7 | DCV Beta2 | 2022-01-27 | -
SYNC+_0268 |  |  | R# EV Features 新能源汽车功能 | 1# Charging | BEV Unique Charging | 行程计划Trip Planner 充电桩查找Station Finder 在地图上寻找充电地方 | ECDX | Yang, Jessica (Yu.) <yyang158@ford.com> |  |  | Cloud Enhanced DTE APIM SPSS v1.2 Nov 19, 2020.docx EV Charge Programming v1 APIM SPSS v1.7 Aug 20, 2019_new.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | N | New | N | N |  |  | Yang, Jessica (Yu.) <yyang158@ford.com> |  |  | N | N |  | Yang, Jessica (Yu.) <yyang158@ford.com> |  |  | Phase2 | No |  |  |  |  | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0246 | F000760 | Auto Engine Idle Shutdown (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting | AEIS (Auto Engine Idle Shutdown) for BEV | For CDX747 project this feature called DSI | EESE |  | Engelbrecht, CP (C.) |  | AEIS Feature Document_V2.2.docx AEIS Feature Implementation Spec_V1.docx DSI Feature Document_V1.docx DSI Feature Implementation Spec_V1.docx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O |  | C/O | [5 empty] | Y | Minor | New HMI layout and UE for 12.3'+27' Display | [5 empty] | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0244 | F001009 | Hazard Light (CDX746/7) | Vehicle Control 车辆控制 | Light Control 灯光控制 | Hazard Light |  | EESE |  |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0276 | F002710 | One_Pedal_Drive: 03 UPV0: MY24 CDX746/747 | Vehicle Setting 车辆设置 | Foundemental | 单踏板驾驶One Pedal Drive |  | EPE | Wu, Dean (D.) <dwu44@ford.com> |  |  | One-Pedal Drive APIM SPSS v1.0 May 14, 2019.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N |  |  | Wu, Dean (D.) <dwu44@ford.com> |  |  | N | N |  | Wu, Dean (D.) <dwu44@ford.com> | [8 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0258 | F000998 | Low Beam (CDX746/7) | Vehicle Control 车辆控制 | Light Control 灯光控制 | Low Beam Switch | RSD - Headlamp switch - Low Beam Includes Auto Lamps and Manual Low Beam | EESE |  |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0259 | F000058/C | Overhead Lighting (CDX746/7) | Vehicle Control 车辆控制 | Light Control 灯光控制 | Map/Dome Lights (RSD - Manual Interior Lighting) |  | EESE |  |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0257 | F001012/B | Parking Light / Position Light (CDX746/7) | Vehicle Control 车辆控制 | Light Control 灯光控制 | Parking Light (North America) Position Light (EU & China) (RSD - Headlamp switch - Park Lamps) – Includes license plate |  | EESE |  |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0253 | F003090 | Cabin & Battery Overheat Management (old name TMOS) (CDX746/7) | Vehicle Setting 车辆设置 |  | Cabin & Battery Overheat Management |  | SE-->EESE |  | Collins, Lynn (L.) |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0241 | F001023 | Automatic Dynamic Leveling (CDX746/7) | ZZ# Foundemental Function 基础功能 |  | Automatic Dynamic Leveling | NO impact for IVI | EESE | Zhou, Travis (C.X.) <czhou17@ford.com> | Gajjar, Jayneel Asutosh (J.) | [7 empty] | N | N | N |  | N |  |  | Zhou, Travis (C.X.) <czhou17@ford.com> |  |  | N | N |  | Zhou, Travis (C.X.) <czhou17@ford.com> | [8 empty] | TBD
SYNC+_Z0261 | F001149/E | Considerate Prompts (CDX746/7) | ZZ# Foundemental Function 基础功能 |  | Considerate Prompts |  | ECDX | Lu, Chao (C.) <clu42@ford.com> | Gonzalez, Cesar (C.) |  | ECPI_VSHA_Feature_Requirement_Document_v1_1.docx | [5 empty] | Y | N | N |  | N |  |  | Lu, Chao (C.) <clu42@ford.com> |  |  | N | N |  | Lu, Chao (C.) <clu42@ford.com> | [8 empty] | TBD
SYNC+_Z0256 | F000148/D | Power Folding Mirrors (CDX746/7) | ZZ# Foundemental Function 基础功能 |  | Power Folding Mirrors w & w/o autofold (RSD - Mirror Fold) |  | EESE |  | Strzelczyk, Anthony (A.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | N | New |  | New | [5 empty] | Y | New | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0235 | F004130 | Rear Seat Occupant Alert (CDX746/7) | ZZ# Foundemental Function 基础功能 |  | Rear Seat Occupant Alert |  | SE-->EESE |  | Nunes, Liandro (L. F.) |  | Rear Seat Occupant Alert APIM SPSS v1.3 Jun 4, 2021.pdf Rear Seat Occupant Alert APIM Imp Guide v1.3 Jun 4, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0247 | F000122/B | Heated Backlight (CDX746/7) | Vehicle Control 车辆控制 | Climate Control 空调控制 | Heated Backlight (climate) | Rear Derfost soft button后挡风玻璃加热 Hardbutton Indicator 硬按键指示灯（如果有） Pop-Up message Status Bar | EESE | Shi, Song (S.S.) <sshi24@ford.com> | Hossain, Mohammed (M.A.) |  | Climate Control APIM SPSS v1.0 May 28, 2021.pdf Climate Control APIM Imp Guide v1.0 May 28, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O |  | C/O |  |  | Shi, Song (S.S.) <sshi24@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Song (S.S.) <sshi24@ford.com> |  |  |  |  | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0263 | F003751 | Integrated Dash Camera (CDX746/7) | ZZ# Foundemental Function 基础功能 |  | Enhanced Dash Camera |  | EESE |  | Eteer, Malik (M.) | [7 empty] | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | TBD
SYNC+_Z0249 | F000146/B | Electrochromatic_Automatic_Day/Night_Mirrors: 03 UPV0: MY24 CDX746/747 | ZZ# Foundemental Function 基础功能 | Vehicle Setting | Electrochromatic Automatic Day/Night Mirrors |  | EESE |  |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0250 | F003170 | PDLC SkyLite Digital Shade (CDX746/7) | ZZ# Foundemental Function 基础功能 |  | PDLC SkyLite Digital Shade |  | SE-->EESE |  | Vandenbrink, Terry (T.) |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0262 | F003417 | Sentinel Experience Phase 3(CDX746/7) | ZZ# Foundemental Function 基础功能 |  | Integrated Sentinel(Video-Based Vehicle Monitoring) |  | SE-->EESE |  | Luken, Richard (R.) | [7 empty] | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | TBD
SYNC+_Z0251 | F002870 | Stowable Steering Column with Deployable Tray (CDX746/7) | ZZ# Foundemental Function 基础功能 |  | Stowable Steering Column w/ Deploying Tray |  | SE-->EESE |  | Lau, Tok (T. W.) | [7 empty] | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | TBD
SYNC+_Z0285 | F001212/A | Driver Focused Mode (CDX746/7) |  |  | Driver Focused Mode |  | EESE |  | Wijaya, Halim (H.) |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf 04_06_00 Driver Focused Mode vA.docx DFM FD 3.9.21 del.docx DFM FIS 3.26.21e.docx DFM FS 3.9.21 nd.docx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0286 | F004530/A | Drive Control Optimization (CDX746/7) （contain Buttonless） |  |  | Drive Control Optimization | Include the following feature: Buttonless Push to Start Feature Document AEIS (DSIS) Feature Document PPO (Pro Power Onboard) Feature Document(not for CDX747) RePA (Remote Park Assist) Feature Document Global Belt Minder Feature Document Multi-Contour Seat Feature Document Power Center Lock Suite Feature Document Classic Memory (EE/EE) Feature Document Welcome / Farewell Feature Document Lincoln Embrace Feature Document NFC (Near Field Communication) Feature Document Perimeter Anti-Theft Alarm Feature Document Range Selection Feature Document RSOA (Rear Seat Occupant Alert) Feature Document Walk Away Locking Feature Document | SE-->EESE |  |  |  | Buttonless Push to Start Feature Document AEIS (DSIS) Feature Document PPO (Pro Power Onboard) Feature Document(not for CDX747) RePA (Remote Park Assist) Feature Document Global Belt Minder Feature Document Multi-Contour Seat Feature Document Power Center Lock Suite Feature Document Classic Memory (EE/EE) Feature Document Welcome / Farewell Feature Document Lincoln Embrace Feature Document NFC (Near Field Communication) Feature Document Perimeter Anti-Theft Alarm Feature Document Range Selection Feature Document RSOA (Rear Seat Occupant Alert) Feature Document Walk Away Locking Feature Document | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
| F000171 | Classic Memory - FNV3 (CDX746/7) |  | Classic Memory |  |  | SE-->EESE |  | Brasileiro, Matheus (M.B.) |  | Enhanced_Memory_With_Soft_Button_Feature_Level_Specification_v1.3_Aug_13, 2021 | [5 empty] | Y | Y | C/O |  | C/O | [5 empty] | Y | C/O | [10 empty] | TBD
| F002216/A | Global Beltminder (CDX746/7) |  |  | Global Beltminder | IOD页面一个子项，仪表侧做逻辑处理，IVI侧只需要做显示逻辑 | EESE | Xu, Xi Hai (X.) <xxu61@ford.com> | Dsouza, Aston (.) |  |  | Core_Service | 10% | 0% | 0% | 90% | Y | Y | C/O |  | C/O |  |  | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  |  |  | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | -
| F000810 | Driver Information Display Control (CDX746/7) |  |  | Driver_Information_Display_Control | IOD：Fuel Economy Other：Trip Summary at key off “FHEV not ready to drive” | EPE | Jin Flora< JJIN17@ford.com> | Sousa, Filipe (F.B.) |  |  | Core_Service | 10% | 0% | 0% | 90% | Y | Y | C/O |  | N |  |  | Jin Flora< JJIN17@ford.com> |  |  | Y | Major | New HMI layout and UE for 12.3'+27' Display | Jin Flora< JJIN17@ford.com> |  |  |  |  | R12 | R12(DCV3) | 2022-02-23 | 2022-03-09 | TBD
SYNC+_Z0287 | F003516 | First Row Seat Position Control (CDX746/7) | Vehicle Control 车辆控制 | Seat Control 座椅控制 | First Row Seat Position Control | IVI need add Cushion Extension in Multi contour seat view | SE-->EESE | Du, Hao (H.) <HDU9@ford.com> | Aguilar, Diana (D.S.) |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | New |  | C/O |  |  | Du, Hao (H.) <HDU9@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> | [8 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
| F001790 | Key in Reminder (CDX746/7) |  |  | Key in Reminder |  | SE-->EESE |  | Silva, Diego (D.M.) | [7 empty] | Y | N | N |  | N | [5 empty] | N | N | [10 empty] | - | - | -
| F000564 | Blind Spot Information System (BLIS) (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting | Blindspot Detection | Menu Setting for BLS | EESE | Liu, Hongxin (H.) <HLIU162@ford.com> | Crosby, Michael (M.C.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O |  | C/O |  |  | Liu, Hongxin (H.) <HLIU162@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Liu, Hongxin (H.) <HLIU162@ford.com> |  |  |  |  | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV Beta | 2021-12-23 | 2022-01-06 | Group A
SYNC+_Z0288 | F000178/D | Perimeter Anti-Theft Alarm (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting | Perimeter Anti-Theft Alarm |  | EESE |  | Talaga, Joshua (J.) |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N |  |  |  | Mortarotti, Mariano (M.) |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | [9 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
| F002070 | Fob Free Entry and Ignition (NFC) (CDX746/7 (GE2)) |  |  | Fob Free Entry and Ignition (NFC) |  | SE-->EESE |  | Ehsan, Farhan (F.) |  | NFC Entry & Start InterfaceClient SPSS v1.1 July 9, 2021.pdf NFC Entry & Start InterfaceClient Imp Guide v1.1 July 9, 2021.xlsx | [5 empty] | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | TBD
SYNC+_Z0289 | F000109/D FNG000760 | TPMS (CDX746/7) Tire Pressure Monitoring System TPMS (U6XX) |  |  | TPMS | IOD页面显示胎压监控信息,IVI不做任何胎压检测逻辑处理，只负责做对应人机交互界面的显示 | EESE | Wang, Vincent (X.) <xwang151@ford.com> | Dave, Brijesh (B.) |  | 2016 TPM Sensor ES-9L2T-1A150-AF.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O |  | Major |  |  | Wang, Vincent (X.) <xwang151@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Vincent (X.) <xwang151@ford.com> |  |  |  |  | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | - | - | -
SYNC+_Z0290 | F004711 | Steering Horizon Control (CDX746/7) |  |  | Steering Horizon Control | 方向盘多功能按键 | SE-->EESE | Zhu, Jing Yuan (J.) <JZHU65@ford.com> | Li, Richard (R.Y.) |  |  | HW_Tier1 | 70% | 10% | 10% | 10% | Y | Y | Minor |  | N |  |  | Zhu, Jing Yuan (J.) <JZHU65@ford.com> |  |  | N | N |  | Zhu, Jing Yuan (J.) <JZHU65@ford.com> | [8 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0291 | F001010/B | Rear Fog Lights (CDX746/7) |  |  | Rear Fog Lights |  | EESE |  | D'Agostino, Antonio (A.) |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
| F001451/C | Blind Spot Assist (CDX746/7) |  |  | Blind_Spot_Assist | This is a IPC feature,no impact in IVI | EESE |  | McWilliams, John (J.S.) |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N |  | N | [5 empty] | N | N | [10 empty] | TBD
| F002430 | Plug and Charge (24 CDX746/7) |  |  | Plug and Charge |  | ECDX | Wang, Yixuan (Vovo) <ywang219@ford.com> | Jujavarapu, Sandeep (S.) | Liu, Hao (H.) <HLIU158@ford.com> | Plug and Charge SPSS v1.7 Jun 28, 2021.pdf Plug and Charge APIM Imp Guide v1.7 Jun 28, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N |  |  | Wang, Yixuan (Vovo) <ywang219@ford.com> |  |  | N | N |  | Wang, Yixuan (Vovo) <ywang219@ford.com> | [8 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0292 | F003517 | Second Row Seat Position Control (CDX746/7) | Vehicle Control 车辆控制 | Seat Control 座椅控制 | Second Row Seat Position Control | [5 empty] | Aguilar, Diana (D.S.) | [5 empty] | Y | TBD | New |  | N | [5 empty] | N | N | [10 empty] | TBD
SYNC+_Z0294 | F002010/B | Frunk (CDX746/7) | Vehicle Control 车辆控制 | Soft Button | Frunk Soft Switch |  |  |  | Butler, Jordan (J.) |  | Frunk Softswitch Interface Client SPSS v1.2 July 15, 2020 Frunk Softswitch Interface Client v2 SPSS v1.0 July 15, 2020 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0295 | F000123/C | Heated Steering Wheel (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Heated Steering Wheel Setting for Remote Start |  |  | Yan, Sophie (C.) <cyan10@ford.com> | Shirazawa, Diogo (D.H.) |  | Settings In Infotainment CenterStack SPSS v1.21 Mar 31, 2021（Seats and Steering Wheel - Remote Start） | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | New |  | C/O |  |  | Yan, Sophie (C.) <cyan10@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yan, Sophie (C.) <cyan10@ford.com> | [8 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0296 | F002214/A | Passenger Airbag Deactivation (CDX746/7) |  |  | Passenger Airbag Disable Indicate Telltale |  |  |  | Dsouza, Aston (.) |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | New |  | N | [5 empty] | N | N | [10 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0297 | F003518 | Seat Temperature Control (CDX746/7) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Seat Temperature Control Setting for Remote Start |  |  | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  | Settings In Infotainment CenterStack SPSS v1.21 Mar 31, 2021 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | New |  | C/O |  |  | Du, Hao (H.) <HDU9@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> |  |  |  |  | R10 | R10(DCV1) | 2021-12-15 | 2021-12-29 | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_Z0293 | F000165/D | Power Liftgate (CDX746/7) | Vehicle Control 车辆控制 | Soft Button | Power Liftgate Soft switch |  |  |  | Gunaratnam, Raj (M.) |  | LiftGate Softswitch Interface Client SPSS v1.2 June 21 2019.pdf LiftGate Softswitch Interface Client Imp Guide v1.2 June 21 2019.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | New |  | C/O | [5 empty] | Y | Minor | New HMI layout and UE for 12.3'+27' Display | [9 empty] | DCV0 | 2022-03-16 | 2022-03-30 | Group B
SYNC+_0267 |  |  |  |  | AR HUD |  | EESE | Zhang, Yong (Y.) <YZHAN468@ford.com> | [8 empty] | Y-1st | N |  | Y-1st | N |  |  | Zhang, Yong (Y.) <YZHAN468@ford.com> |  |  | N | N |  | Zhang, Yong (Y.) <YZHAN468@ford.com>
SYNC+_0269 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 天气 Weather | phase1-4是launcher 一部分。 Phase 5 作为独立App。显示天气， PM2.5 (点击进入AAR 界面）等。目前只显示当天的。资源方：百度. |  | Shi, Stella (J.) <jshi32@ford.com> |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y-1st | Y | Y | C/O |  |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  |  | Phase5 | No | R6 | R6(DCV Beta1) | 2021-08-18 | - | DCV Beta | 2021-12-23 | 2022-01-06 | Group A
SYNC+_0270 |  |  | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 1.0 | CNECDMPORT-136，CNECDMPORT-135(CX727) | [11 empty] | N | N | N | N | [5 empty] | N | N
SYNC+_0271 |  |  | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 1.5 | CNECDMPORT-343 | [11 empty] | N | N | N | N | [5 empty] | N | N
SYNC+_0272 |  |  | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 2.0 | CNECDMPORT-440 Personalized content | [11 empty] | Y-first | Y | Y- OTA | C/O | [5 empty] | Y | Minor | New HMI layout and UE for 12.3'+27' Display
SYNC+_0273 |  |  | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | Remote Window Control / Window Status (China) | CNECDMPORT-413 | [11 empty] | Y | Y | Y | C/O | [5 empty] | Y | Minor | New HMI layout and UE for 12.3'+27' Display
SYNC+_0275 |  |  | J# Health & Wellness | Ford_Signature Experience_Welcoming & Empathetic | SenseMyMood 1.0 | [12 empty] | N | N | Y-TBD | N | [5 empty] | N | N
SYNC+_0276 |  |  | J# Health & Wellness | Ford_Signature Experience_Welcoming & Empathetic | SenseMyMood 2.0 | [12 empty] | N | N | N | N | [5 empty] | N | N
SYNC+_0277 |  |  | J# Health & Wellness | Ford_Signature Experience_Welcoming & Empathetic | SenseMyMood 3.0 | [12 empty] | N | N | N | N | [5 empty] | N | N
SYNC+_0278 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Embrace | Digital Embrace 1.0 | [12 empty] | N | N | N | N | [5 empty] | N | N
SYNC+_0279 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Embrace | Digital Embrace 2.0 | [12 empty] | Y | Y | N | C/O | [5 empty] | N | N
SYNC+_0280 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Embrace | Digital Embrace 3.0 | [12 empty] | N | N | N | N | [5 empty] | N | N
SYNC+_0281 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Rejuvenate | Smart Wellness 1.0 | [12 empty] | Y | Y | N | C/O | [5 empty] | N | N
SYNC+_0282 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Rejuvenate | Smart Wellness 2.0 | [12 empty] | N | N | N | N | [5 empty] | N | N
SYNC+_0283 |  |  | H# Service & Maintenance 车主服务 | 6# Customer Care 客户关怀 | FNOC 1.0 | FNOC－First Notification of Care - Weather related | [11 empty] | Y | Y | Y | C/O | [5 empty] | Y | Minor | New HMI layout and UE for 12.3'+27' Display
SYNC+_0284 |  |  | H# Service & Maintenance 车主服务 | 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | FNOS | CNECDMPORT-114 - Oil Life Prediction / China SYNC+ IVI | [11 empty] | Y | Y | Y | C/O | [5 empty] | Y | Minor | New HMI layout and UE for 12.3'+27' Display
SYNC+_Z0282 |  |  | ZZ# Foundemental Function 基础功能 |  | 车机管家 | 百度主线用于管理主线内功能的隐私权限设置 |  | gu,regina |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | Y | Y | C/O |  |  | gu,regina |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | gu,regina |  |  | Phase2 | No | R13 | R13(R00) | 2022-03-23 | 2022-04-06 | DCV2 | 2022-05-30 | 2022-06-14 | Group C
| F000800 |  | Vehicle Control 车辆控制 | Climate Control 空调控制 | Heated Mirrors | 包含前除霜、后除霜、最大除霜 包含Remote Start Setting项 |  | Xie, Will (W.) <wxie15@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Climate Control APIM SPSS v1.0 May 28, 2021.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | C/O |  | C/O |  |  | Xie, Will (W.) <wxie15@ford.com> |  |  | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xie, Will (W.) <wxie15@ford.com>
| F003074 F000121 | Heated Wiper Blade (U611) | Vehicle Control 车辆控制 | Climate Control 空调控制 | Heated Wiper Blade Heated Windshield |  | EESE |  | Lima, Dorivaldo (.) |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ Climate Control APIM SPSS v1.0 May 28, 2021 | [5 empty] | Y | N | New |  | New | [5 empty] | Y | New
| F000189 | Keypad (U6XX) | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Keypad |  | EESE |  | Ferreira, Eliane (E.C.) |  | Vehicle Settings APIM SPSS v1.23 Mar 19, 2020 | [6 empty] | N | N |  | New | [5 empty] | Y | New
| F000864 |  |  |  | Power Release/Cinch Doors |  | EESE |  | Weiler, Jonathan (J.P.) | [8 empty] | N | New |  | New | [5 empty] | Y | New
| F000604 |  |  |  | Engine Starting Stationary |  | EESE |  | Hall, Jonathan (J.) | [8 empty] | N | N |  | New | [5 empty] | Y | New
| F003413,F003414,F003370 |  |  |  | Cellular Remote Start / Stop (U6XX) |  | ECDX |  | Syed, Imtiaz (I.S.) | [8 empty] | N | N |  | New | [5 empty] | Y | New
| F000818 |  |  |  | Plug In Charging (PIC) | [12 empty] | N | New |  | N
| F005350 |  |  |  | EV Charge Programming | [12 empty] | N | New |  | N
| F005310 |  |  |  | Buttonless Push To Start – BEV | [12 empty] | N | New |  | N
| F003410 |  |  |  | Cellular Remote Start w/Extend Remote Start FNV3 | [12 empty] | N | New |  | N
| F003411 |  |  |  | Cellular Scheduled Remote Start | [12 empty] | N | New |  | N
| F003774 |  |  |  | Augmented Reality | [12 empty] | N | New |  | N
Note on T2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline is CDX707
Note on AB2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline is CDX707
Note on AJ9: Huang, Feng (F.): 1. Baidu评估YF基础定位功能最迟R2版本释放 2.YF评估定位功能在R3版本释放。 YF和Baidu需再次评估确认依赖项风险
Note on AN18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm with Program with the stragety of AM/FM. --Frank
Note on AJ23: Huang, Feng (F.): R5:实现USB music 1. 基础功能满足，但格式可以支持MP3/AAC/WAV，更多格式支持及工作量取决于需求（考虑新的格式APE）。 2.文件扫描优化后延3个版本，即R8 R7:实现MTP music
Note on AJ25: Huang, Feng (F.): 依赖网络： 1. FNVX 无法支持R5版本 2. YF R2版本释放IVI芯片WIFI功能用于满足其他应用联网需求
Note on AJ27: Huang, Feng (F.): 1. 基础功能满足，但格式可以支持MP4/MKV，更多格式支持及工作量取决于需求。 2.文件扫描优化后延3个版本，即R8
Note on AJ29: Huang, Feng (F.): 1/14/2021 Pre DV R5 支持Mpeg-2， R8全功能释放.
Note on AN39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Qiyang Comment: 747 need soft button control Frunk.
Note on AJ44: Huang, Feng (F.): 电车实时车况界面IOD需求（是否适用于707）需要进一步和Xuedong/HMI team一起讨论
Note on AJ57: Huang, Feng (F.): 依赖360盒子，如R8释放功能，则R4版本需要360盒子支持
Note on AQ61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requirement and Road map should be confirmed by tech planning and program. --Frank.
Note on AJ63: Huang, Feng (F.): 依赖360盒子，如R8释放功能，则R4版本需要360盒子支持
Note on AJ65: Huang, Feng (F.): 依赖360盒子，如R8释放功能，则R4版本需要360盒子支持
Note on AJ69: Huang, Feng (F.): 12/21：参考SYNC+_0095， YF评估可在R5实现该功能. 需要提前4个月拿到原厂摄像头进行调试. IVI 协调FO支持提供对手件联系方式.
Note on AJ70: Huang, Feng (F.): 此功能依赖摄像头提供时间，YFV评估需要提前4个月拿到摄像头
Note on F72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feature Name is Clear Exit
Note on F98: Zhou, Jiajia (J.): 车机相册FDL有哪一方承担（SW_Tier1 or Inhouse），需要FO进一步确认
Note on T106: Ma, Jian (J.): CDX707 Study TIB12
Note on T109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cheier:会打包到Second Row的Online Cabin里
Note on AN119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check if the PPP replace Enhance memory. --Frank.
Note on AJ122: Huang, Feng (F.): 依赖HMI assets释放计划
Note on AN138: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI confirm with studio if the multi theme same with CDX707.---Lisa Gao.
Note on AJ141: Huang, Feng (F.) 指USB升级
Note on T160: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Still on study，not in BoF
Note on AJ182: Huang, Feng (F.): 1. 依赖Ford外置功放Ready时间。 2. 依赖CAN Bus依赖，YF预计R3提供基本网络功能。 3. 1和2依赖项OK后YF预计调试时间2个月，A2B释放需要1和2依赖项在R3版本时Ready。
Note on AJ183: Huang, Feng (F.): 1. Pre-DV需求参考SYNC+_Z0199 2. ANC Tuning不在Pre-DV节点实现，具体实现可参考SYNC+_Z0008
Note on AJ185: Huang, Feng (F.): 1. 依赖外置功放Ready时间，需要提前2个月Ready（即R8）
Note on AJ186: Huang, Feng (F.): 1. 依赖需项目定点后MBBM重新发包 2. 发包后预计6个月完成调试
Note on AJ188: Huang, Feng (F.): CDC使用外置DSP方案，EQ Tool由Ford提供。 1. 依赖Ford提供EQ Tool Ready时间。 2. YF使用此工具预计1-2周完成联调
Note on AJ191: Huang, Feng (F.): 1. 依赖项目定点后ECNR采购及发包，后续调试集成预计1.5-2月
Note on AJ196: Huang, Feng (F.): 1. 此版本支持Android logcat串口输出，无UI界面支持
Note on AJ198: Huang, Feng (F.): 与SYNC+_0013重复
Note on AJ205: Huang, Feng (F.): 为满足此特定的仪表交互需求，YF特别投入资源在R5版本实现多屏互动中音乐功能。 2021/05/07: HMI Group A-B UX 暂无该需求.
Note on AJ210: Huang, Feng (F.): 1. 工程模式R5版本提供部分功能支持，具体支持功能请参考12/22 Huang Feng发出的Round2 MM。
Note on AJ224: Huang, Feng (F.): 1. 工程模式中支持Android、QNX、MCU、HCI日志管理及导出功能
Note on AN225: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Follow CDX707, 12/15 Full CAN Release
Note on AJ226: Huang, Feng (F.): CDC项目不使用FNOS包，请参考SYNC+_Z0107中Autosar包评估
Note on AR226: Huang, Feng (F.): CDC项目不使用FNOS包，请参考SYNC+_Z0107中Autosar包评估
Note on AJ228: Huang, Feng (F.): 1. 因FBL包采购原因无法在R5支持VBF升级，VBF升级计划在R10实现 2. 替代方案：R4版本实现在工程模式界面支持USB升级MCU功能。
Note on AN229: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Power management may be minor/major change.
Note on AJ237: Huang, Feng (F.): 完成台架信号调试完成，包含MCU到SOC链路。假设DCV节点有实车提供，YFV可以在2个月内完成实车功能调试及功能释放。
Note on AJ256: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 释放计划详见5D.
Note on AJ261: Huang, Feng (F.): 特指以太网接口及底层驱动
Note on F263: Huang, Feng (F.): Will Xie 回复707项目只有MINI ICP, 无该功能
Note on AJ286: Huang, Feng (F.): 1. 实现本地时钟同步策略
Note on AJ321: Huang, Feng (F.): 此功能特指： R5版本实现4路ANC MIC路由到4路Speaker输出，同时在工程模式增加对应的诊断功能入口。
Note on F345: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BOF没有这条，只有ADA1.5 （Lane Biasing）
Note on T366: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This feature alaready included by VHA in CDX747 project
Note on AJ369: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feature requirement not clear, wait FO clarify

## Summary (hidden)
Feature_Product_Suite Feature Release Plan
| CDX707 |  |  |  |  | DCV beta |  |  | DCV0 | DCV1 | DCV2 |  | DCV3 | R00 | R04 | R05 |  |  |  | R06 |  | R07
| CDX747 | [8 empty] | DCV beta |  |  |  | DCV0 | DCV1 |  | DCV2 | DCV3 |  | R00 | R05 |  | R06 |  |  | R07
| R0 | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 | R12 | R13 | R14 | R15 | R16 | R17 | R18 | R19 | R20 | R21 | R22 | R23 | R24 | R25 | R26 | R27 | R28 | R29 | R30
Delivery Feature Number | 2 | 0 | 2 | 0 | 2 | 47 | 12 | 7 | 14 | 30 | 124 | 12 | 39 | 10 | 4 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 1
A# Navigation 地图导航 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
H# Service & Maintenance 车主服务 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
B# Multimedia 多媒体 | 0 | 0 | 0 | 0 | 1 | 6 | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
C# Intelligent Digital Assitant 智能数字助手 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 1 | 6 | 4 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
D# Co-Pilot360 驾驶辅助 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 2 | 3 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
E# Access & Authorization 车钥匙 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F# ISP (Intelligent Sensing Platform) 智能感应平台 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G# Remote Control 远程控制 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I# Safety & Security 安全 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J# Health & Wellness | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
K# Social & Operation 社交及运营服务 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
L# IoT(Internet of Things) 车家互联 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M# Personalization & Account 账号和个人设置 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
N# Engagement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O# Payment Services 支付服务 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P# Messaging & Alerts 消息和提醒 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Q# Seamless Interface | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ZZ# Foundemental | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R# EV Features 新能源汽车功能 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vehicle Control 车辆控制 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 27 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vehicle Setting 车辆设置 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 0 | 2 | 1 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System Setting 系统设置 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System Function 系统功能 | 1 | 0 | 2 | 0 | 0 | 13 | 0 | 1 | 5 | 7 | 5 | 0 | 7 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ZZ# Foundemental Function 基础功能 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
累计Consumption | 2 | 2 | 4 | 4 | 6 | 53 | 65 | 72 | 86 | 116 | 240 | 252 | 291 | 301 | 305 | 305 | 306 | 306 | 306 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 315 | 315 | 315 | 315 | 315

## Delete
New Feature ID | Summary | Feature_Product_Suite | Feature_Group | Feature_Name | Feature_Description | FInfo10 Lead_Team | Feature_Owner | UX Lead | FImp04 Dev_Spec | Feature Development Leader | HW_Tier 1 | SW_Tier 1 | Ford IVI In-House | Core Service Provider | FPrgm07 Phase5 | P5_CDX707 | P5_CX788 | P5_CDX804 | P5_CDX747 | P5_U611MCA | P5_U718 | P5_CDX847 | P5_CD542MCA | P5_CX788MCA | P5_CD764MCA | 1st - phase # | Pre-DV Req | Release A/B Version | Date
SYNC+_0052 | SYNC+_0027 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 人物百科 Celebrity encyclopedia | 支持娱乐明星、体育明星、历史人物等名人的重要信息（身高、体重、家乡、星座）、婚姻状况、亲属（如老婆、老公、女朋友）Support searching celebrity info | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0053 | SYNC+_0035 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 地理 Geography | 支持查询某物的面积、长度、高度、食物的热量 Support searching something's dimension & food calorie | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0054 | SYNC+_0025 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 天气 Weather | 支持国内2560个城市和海外主要城市的6天内天气查询和当日生活指数查询。 Support weather info & related index search of 2560 domestic cities & main oversea cities. | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0055 | SYNC+_0031 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 彩票 Lotery | 支持查询博彩类开奖结果(大乐透、七星彩、体彩、排列五、福彩、双色球）Support searching loteray info | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0056 | SYNC+_0038 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 日历 Calendar | 支持查询节假日、节气时间 Support searching holiday date & China traditional solarterm dates | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Phase 1 | No | R5 | 2021-07-10
SYNC+_0057 | SYNC+_0041 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 机票/航班信息 air ticket/flight info | "支持查询机票/航班信息 support air ticket/flight info searching" | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0058 | SYNC+_0034 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 汇率 Exchange rate | 支持世界主要货币之间的兑换换算。 Support mainstreen currency exchange calculation | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0059 | SYNC+_0040 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 火车票 train | 支持查询火车票 support train ticket searching | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0060 | SYNC+_0036 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 热映电影 Popular movie | 支持电影实体查找（包括电影名、演员、类型等）Support movie searching | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0061 | SYNC+_0039 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 电影票/外卖 movie ticket/take away | 支持购买电影票/外卖 support paying moive ticket | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0062 | SYNC+_0037 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 电视剧基础属性 Episodes | 支持查询电视剧的播出时间、电影的上映时间 Episodes'airtime | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0063 | SYNC+_0029 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 笑话 Jokes | 支持文字笑话的询问与播报 Support reading literal jokes | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0064 | SYNC+_0028 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 股价 Share price | 支持美股、港股、沪深股市的公司市值股价和大盘指数查询 Support US/HK/Shanghai/Shenzhen share price & stock index searching | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0065 | SYNC+_0033 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 诗词 Poem | 支持唐诗宋词的完整篇章或上下句、作者、出处查询。 Support China acient poem searching & related info, i.e. writer | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0066 | SYNC+_0032 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 闲聊 Chat | 自由聊天，每句话都能有回应 Responding to every voice command/message | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0067 | SYNC+_0026 | C# Intelligent Digital Assitant 智能数字助手 | 5# AI Q&A 智能问答 | 限行 Traffic control info - License plate restriction | 查询6个主要限行城市（北京、杭州、兰州、成都、天津、武汉）的限行信息。 Support searching 6 main cities which implemented traffic control rules | EESE/IVI | Qi XuLiang |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R5 | 2021-07-10
SYNC+_0069 | SYNC+_0415 | C# Intelligent Digital Assitant 智能数字助手 | 7# VPA 形象化语音助手 | 交互界面Interaction page |  |  | Suo, Feifei (F.) |  |  | Ford_InHouse | 0 | 0 | 100 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 3 | No | R10 | 2021-12-15
SYNC+_0104 | SYNC+_0497 | E# Access & Authorization 车钥匙 | 2# Phone As A Key (PaaK) 手机钥匙 | 智能备用密钥 Backup Startup Passcode (BSP) | Use same blem as PAAK. Backup of PAAK. How it work: work together with Key Pad on the door (exterior). customer use Key Pad on the door to unlock car; key in passcode on IVI to engine start. 密码要求8位 数字加字母 | CVPP | Wang, Cindy (X.J.) <xwang216@ford.com> |  | PRD 【更新】【Phase2林肯】LBI智能备用密钥_MRD_2019_7_11-v2.0.pdf | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 2 | No | TBD
SYNC+_0105 | SYNC+_0382 | E# Access & Authorization 车钥匙 | 2# Phone As A Key (PaaK) 手机钥匙 | 手机钥匙（经济版）Phone as key(PaaK) Lite | Lite Version for CD539ICA, 2 Door/1R | CVPP-Distribute System | Wang, Cindy (X.J.) /Joey Chen |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 3 | No | TBD
SYNC+_0121 | SYNC+_0098 | G# Remote Control 远程控制 | 2# FordPass Remote Control 福特派远程控制 | 车辆保养时间/保养项目/保养里程建议Prognostics (Gasoline Vehicle) | 根据VHA和TCU（FB2+） report 机油状况，建议保养时间/保养项目/里程 | CVPP | Lu, Chao (C.) |  |  | Ford_InHouse | 0 | 10 | 90 | 0 | Y | Y |  |  | Y | [7 empty] | No | R13 | 2022-03-15
SYNC+_0144 | SYNC+_0511 | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 美团外卖MeiTuanTake-away |  | CVPP | Lu, Chao (C.) <clu42@ford.com> |  | MRD | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R10 | 2021-12-15
SYNC+_0146 | SYNC+_0094 | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 鲜花预定Order flower delivery | 鲜花预定（含二维码支付） Order flower delivery | CVPP | Lu, Chao (C.) |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R10 | 2021-12-15
SYNC+_0147 | SYNC+_0095 | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 机票查询 Flight search | 机票查询 Flight search | CVPP | Lu, Chao (C.) |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R10 | 2021-12-15
SYNC+_0148 | SYNC+_0096 | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 火车票查询 Train ticket search | 火车票查询 Train ticket search | CVPP | Lu, Chao (C.) |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R10 | 2021-12-15
SYNC+_0150 | SYNC+_0097 | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 酒店预定 Hotel booking | 酒店预定 Hotel booking | CVPP | Lu, Chao (C.) |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R10 | 2021-12-15
SYNC+_0168 | SYNC+_0539 | N# Engagement | 1# Appreciation | 林肯迎宾模式Lincoln Embrace (vehicle setting: 3-mode selection) | 福特品牌叫做 welcome & Farewell. 林肯品牌叫做Lincoln Embrance | EESE/System | Wu, Bella (Y.) <YWU150@ford.com> |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y | N | Y | Y | Y | Y |  | N | N | Y | Phase 4 | No | R8 | 2021-10-20
SYNC+_0169 |  | N# Engagement | 1# Appreciation | 林肯迎宾模式Lincoln Embrace _Next Gen | 2022 U554 is 707's assumption; Will need to keep an eye on 747, apply new adds from 747 if timing allows. The experience is an orchestrated ”signature” entry and exit experience Includes multiple enablers working together to intelligently guide users to and from the vehicle, identify them, open for them and adjust the interior to them on the fly. Upon approach, the vehicle identifies the user, and provides personalized visual identification to attract the user’s attention (exterior lighting) and guide them to the vehicle. Approach detection/identification unlocks the vehicle automatically based on user ID. The user’s path to the vehicle is illuminated if needed so they can enter safely and comfortably. Doors open automatically and appropriately for the safety of the location, the weather, the time of day, the number of guests and location of users in relation to the car. The vehicle alters the atmosphere of its environment on approach to make it feel inviting to the users, with an element of personalization so “every Lincoln feels like my Lincoln”. The user can choose to select which doors to open on approach via different means (phone, voice) OTA updatable embrace lighting sequence to allow for the experience to evolve and feel new As you open the driver door, the pillar-to-pillar screen welcomes everyone with a specific theme | EESE / BET | Wu Bella / Zhou Travis / Eileen Feng |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y-1st | Y-1st |  |  | Y | [6 empty] | Phase 5 | No | R8 | 2021-10-20
SYNC+_0174 | SYNC+_0487 | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 聚合支付 Aggregate payment | 扫码支付的时候车机只显示一个二维码 | CVPP | Lu, Chao (C.) <clu42@ford.com> |  | MRD | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R12 | 2022-02-15
SYNC+_0176 |  | P# Messaging & Alerts 消息和提醒 | 1# Message Center | 车机端消息管理 Project Aspire_Aspire Notificaitons | Notifications from all connected devices and applications ( per the user's preferences or settings) can be chosen to be displayed on the Horizon display in non critical information zone during drive or stationary mode of the vehicle. | CVPP | Wang Jonny |  |  | Ford_InHouse | 10 | 0 | 90 | 0 | Y-1st | Y-Study |  |  | Y | [6 empty] | Phase 5 | No | R10 | 2021-12-15
SYNC+_0186 | SYNC+_0478 | Q# Seamless Interface | 2# Passenger Experience | 27'副驾本地及在线音乐/Offline&Online Music Player & audio manager |  | HMI | Xu, Amy <XYAFEI@ford.com> |  |  | SW_Tier1 | 40 | 60 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R12 | 2022-02-15
SYNC+_0187 | SYNC+_0483 | Q# Seamless Interface | 2# Passenger Experience | 27'地图/including Passenger Map&Navigation; |  | EESE/IVI(Diven) | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R12 | 2022-02-15
SYNC+_0188 | SYNC+_0479 | Q# Seamless Interface | 2# Passenger Experience | 27'空调设置(climate control from passenger area) |  | EESE/DI | Li, Jun (J.) <jli198@ford.com> |  | same with climate control | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R12 | 2022-02-15
SYNC+_0189 | SYNC+_0481 | Q# Seamless Interface | 2# Passenger Experience | 副驾在线视频Online Video-clarify |  | EESE/IVI(Diven) | Xu, Amy (X.) <xyafei@ford.com> |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R12 | 2022-02-15
SYNC+_0190 | SYNC+_0484 | Q# Seamless Interface | 2# Passenger Experience | 副驾天气预报Weather forecast | 27" touch -CD542. 之前天气是以卡片形式展示。 CD542 上面天气信息融入到背景中。添加了暖心贴士 | CVPP | Shi, Stella (J.) <jshi32@ford.com> |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R12 | 2022-02-15
SYNC+_0191 | SYNC+_0480 | Q# Seamless Interface | 2# Passenger Experience | 副驾视频播放(支持 DLNA)/Passenger Video Playback(Support DLNA |  | EESE/IVI(Diven) | Jia, Elaine (T.) <tjia2@ford.com> |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R12 | 2022-02-15
SYNC+_0193 | SYNC+_0477 | Q# Seamless Interface | 3# Driver Exlusive Screen Use Experience | 27” 屏幕扩展显示/Extend center or passenger display content(like Navi, to show the whole path in two screens) to two display (地图独占模式） |  | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | HW_Tier1 | 60 | 20 | 0 | 20 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R12 | 2022-02-15
SYNC+_0195 | SYNC+_0013 | Q# Seamless Interface | 4# Welcome/Farewell Animation | Lincoln主页及开机/关机动画的设计及开发 Customized welcome prompt/animation |  | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 2 | Yes | R5 | 2021-07-10
SYNC+_0197 | SYNC+_0496 | Q# Seamless Interface | 5# IOD - Information On (IVI) Display | 电车实时车况界面OD - Off Road; |  | EESE/IVI(Diven) | Yu, Diven (D.W.) <dyu12@ford.com> |  | Off-Road Status IOD APIM SPSS v1.0 Aug 23, 2019.pdf Off-Road Status IOD APIM Imp Guide v1.0 Aug 23, 2019.xlsx | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | -
SYNC+_0198 | SYNC+_0492 | Q# Seamless Interface | 5# IOD - Information On (IVI) Display | 电车实时车况界面OD - Pitch and Roll |  | EESE/IVI(Diven) | Yu, Diven (D.W.) <dyu12@ford.com> |  | Pitch and Roll SPSS v1.0.1 Dec 18, 2018 Pitch and Roll APIM Imp Guide v1.0.1 Dec 18, 2018 | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | -
SYNC+_0199 | SYNC+_0493 | Q# Seamless Interface | 5# IOD - Information On (IVI) Display | 电车实时车况界面IOD - SeatBelt (information on demand) |  | EESE/IVI(Diven) | Yu, Diven (D.W.) <dyu12@ford.com> |  | Seatbelt IOD SPSS v1.0 Dec 19, 2018 Seatbelt IOD APIM Imp Guide v1.0 Dec 19, 2018 | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | -
SYNC+_0200 | SYNC+_0494 | Q# Seamless Interface | 5# IOD - Information On (IVI) Display | 电车实时车况界面IOD - TPMS (Information on Demand) |  | EESE/IVI(Diven) | Yu, Diven (D.W.) <dyu12@ford.com> |  | TPMS Information On Demand SPSS v1.0 March 5, 2019 TPMS Information On Demand Imp Guide v1.0 March 5, 2019 | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | -
SYNC+_0201 | SYNC+_0495 | Q# Seamless Interface | 5# IOD - Information On (IVI) Display | 电车实时车况界面IOD - Trip Information On Demand 当前行程 |  | EESE/IVI(Diven) | Yu, Diven (D.W.) <dyu12@ford.com> |  | Trip Information on Demand SPSS v1.1 Nov 16, 2018 Trip Information on Demand APIM Imp Guide v1.1 Nov 16, 2018 | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | -
SYNC+_0202 | SYNC+_0489 | Q# Seamless Interface | 5# IOD - Information On (IVI) Display | 电车实时车况界面IOD- Behavior Coaching Display Client 我的驾驶怎么样？ |  | EESE/IVI(PT)(Diven) | Yu, Diven (D.W.) <dyu12@ford.com> |  | Behavior Coaching Display Client v2 APIM Imp Guide v1.0 Nov 19, 2018.xlsx Behavior Coaching Display Client v2 APIM SPSS v1.0 Nov 19, 2018.docx Behavior Coaching Display Client v2 APIM SPSS v1.0 Nov 19, 2018.pdf | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | -
SYNC+_0211 | SYNC+_0514 | R# EV Features 新能源汽车功能 | 1# Charging Setting | 充电状态Battery Status of Charge |  | CVPP | Ji, Jerry (Y.) <yji9@ford.com> |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx | Core_Service_Supplier | 20 | 0 | 0 | 80 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | R10 | 2021-12-15
SYNC+_0212 |  | R# EV Features 新能源汽车功能 | 1# Charging Setting | 出发时间设置Departure Time Settings |  | CVPP | Ji, Jerry (Y.) <yji9@ford.com> |  |  | Core_Service_Supplier | 20 | 0 | 0 | 80 | Y | N |  |  | Y | [6 empty] | Phase 2 | No | R10 | 2021-12-15
SYNC+_0213 |  | R# EV Features 新能源汽车功能 | 1# Charging Setting | 推荐充电时间Preferred Charge Time |  | CVPP | Ji, Jerry (Y.) <yji9@ford.com> |  |  | Core_Service_Supplier | 20 | 0 | 0 | 80 | Y | N |  |  | Y | [6 empty] | Phase 2 | No | R10 | 2021-12-15
SYNC+_0214 | SYNC+_0520 | R# EV Features 新能源汽车功能 | 2# Distance to Empty (DTE) | 剩余里程显示(云端)Cloud Enhanced Distance to Empty |  | CVPP | Ji, Jerry (Y.) <yji9@ford.com> |  | PRD Cloud_Enhanced_DTE_FS_v1.1.pdf | Core_Service_Supplier | 20 | 0 | 0 | 80 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | R10 | 2021-12-15
SYNC+_0216 | SYNC+_0522 | R# EV Features 新能源汽车功能 | 3# BEV Unique | 前备箱软按键 IVI Soft touch-frunk |  | EESE/IVI(Forrest) | chen, Emma<jchen276@ford.com> |  | Frunk Softswitch Interface Client SPSS v1.1 June 21 2019 | Core_Service_Supplier | 20 | 0 | 0 | 80 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | R10 | 2021-12-15
SYNC+_0217 | SYNC+_0507 | R# EV Features 新能源汽车功能 | 3# BEV Unique | 单踏板驾驶One Pedal Drive | 该功能工作时，driver release 油门，车速就会慢慢降下来（不能代替刹车），此时能量回收。 | EESE/IVI(PMT4)(Forrest) | Chen, Emma (J.) <jchen276@ford.com>/ Li, Xuedong (X.) <xli244@ford.com> |  | One-Pedal Drive APIM SPSS v1.0 May 14, 2019.pdf One-Pedal Drive APIM Imp Guide v1.0 May 14, 2019.xlsx | Core_Service_Supplier | 20 | 0 | 0 | 80 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | R10 | 2021-12-15
SYNC+_0218 | SYNC+_0521 | R# EV Features 新能源汽车功能 | 3# BEV Unique | 智慧充电Smart Charging |  | CVPP | Ji, Jerry (Y.) <yji9@ford.com> |  | Smart Charging PRD_v1.6.pdf | Core_Service_Supplier | 20 | 0 | 0 | 80 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | R10 | 2021-12-15
SYNC+_0219 | SYNC+_0519 | R# EV Features 新能源汽车功能 | 3# BEV Unique | 行程计划Trip Planner |  | CVPP | Ji, Jerry (Y.) <yji9@ford.com> |  | PRD EV Trip Planner APIM SPSS v1.0 Mar 15, 2019.pdf | SW_Tier1 | 20 | 80 | 0 | 0 | Y | N |  |  | Y | [6 empty] | Phase 4 | No | R10 | 2021-12-15
SYNC+_0220 | SYNC+_0390 | R# EV Features 新能源汽车功能 | 4# Charing Station Finder | 充电桩查找Station Finder | 在地图上寻找充电地方 | CVPPEPE | Ji, Jerry (Y.) <yji9@ford.com>;Dean Wu |  |  | SW_Tier1 | 20 | 80 | 0 | 0 | Y | N |  |  | Y | [6 empty] | Phase 2 | No | R10 | 2021-12-15
SYNC+_Z0001 | SYNC+_0333 | ZZ# Foundemental Function 基础功能 | 1# Air Quality 空气质量 | UFC Lite notification (空气净化状态提示) | 空气净化状态提示, function module. Part of AAR. | EESE/IVI-Distribute DI | Yao, Frank/DongYa |  |  | Core_Service_Supplier | 20 | 0 | 0 | 80 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R13 | 2022-03-15
SYNC+_Z0016 | SYNC+_0474 | ZZ# Foundemental Function 基础功能 | Backend Feature | 车机工程模式(支持车辆工厂模式)/IVI Engineering Mode | 中文+英文界面 | EESE/IVI(Forrest) | Wang, Fin (X.Y.) <xwang65@ford.com> |  | based on bezel diagnostic; Phase 2 mail - archive | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | Yes | R8 | 2021-10-20
SYNC+_Z0018 | SYNC+_0129 | ZZ# Foundemental Function 基础功能 | Big Data Analytics | 统计月度和年度激活量 Statistics monthly and annual system activation quantities |  | CVPP | Yu, Yaxing (Y.) |  |  | SW_Tier1 | 0 | 100 | ？ | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R12 | 2022-02-15
SYNC+_Z0021 | SYNC+_0358 | ZZ# Foundemental Function 基础功能 | Carrier | Carrier Backend Development 运营商后台开发 | associate 1 VIN with 2 SIMs; RNR platform; Online Mall; Jasper/M2M portal; Per APP billing, etc. | CVPP | Wang, Yuran |  |  | SW_Tier1 | 0 | ？ | 100 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R12 | 2022-02-15
SYNC+_Z0022 | SYNC+_0357 | ZZ# Foundemental Function 基础功能 | Carrier | RNR | 实名认证 | CVPP | Pan Yuan |  |  | SW_Tier1 | 0 | ？ | 100 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R12 | 2022-02-15
SYNC+_Z0029 | SYNC+_0509 | ZZ# Foundemental Function 基础功能 | Connected Services | Authorization车机授权 (FNV2 Based） |  | CVPP | Gu, Xiaosheng (X.) <xgu14@ford.com> |  | PRD DUEROS_CVPP_Authorization_PRD v1.0 | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R8 | 2021-10-20
SYNC+_Z0031 | SYNC+_0513 | ZZ# Foundemental Function 基础功能 | Connected Services | Carrier Feed |  | CVPP | Wang, Yuran<ywang422@ford.com> |  |  | TBD | 0 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R8 | 2021-10-20
SYNC+_Z0034 | SYNC+_0525 | ZZ# Foundemental Function 基础功能 | Connected Services | Message Center | Ford/Baidu both have the capability to push message. Phase 1- 30 text/Phase 4- H5,and more. Different | CVPP | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R10 | 2021-12-15
SYNC+_Z0040 | SYNC+_0431 | ZZ# Foundemental Function 基础功能 | General Connected Feature | Ford TCU Related features (Modem Reset, WiFi, WiFi Hotspot)- TCU transfer CAN data to IVI |  | CVPP | Pan, Yuan (Y.) <ypan23@ford.com> |  | WiFi Hotspot OnBoardClient v2 SPSS v1.3 July 15, 2019 | HW_Tier1 | 80 | 0 | 0 | 20 | Y | Y |  |  | Y | [6 empty] | Phase 4 | Yes | R5 | 2021-07-10
SYNC+_Z0042 | SYNC+_0451 | ZZ# Foundemental Function 基础功能 | General Connected Feature | Peripheral Provisioning |  | CVPP | Cui, Rebecca (H.) <hcui2@ford.com> |  | Peripheral Module Provisioning APIM Imp Guide v1.4 July 30, 2019.xlsx Peripheral Module Provisioning SPSS v1.4 July 30, 2019.docx Peripheral Module Provisioning SPSS v1.4 July 30, 2019.pdf | Core_Service_Supplier | 20 | 0 | 0 | 80 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R8 | 2021-10-20
SYNC+_Z0053 | SYNC+_0314 | ZZ# Foundemental Function 基础功能 | IVI Support Vehicle Function | Vehicle Setting |  | IVI | Wang, Fin (X.Y.) |  |  | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | Y |  |  | Y | [6 empty] | Phase 1 | Yes | R5 | 2021-07-10
SYNC+_Z0061 | SYNC+_0432 | ZZ# Foundemental Function 基础功能 | MCU features | 支持与仪表盘互动/Supporting interaction with cluster（Phone/Media/Navi） |  | EESE/IVI(Roger) | IVI-Chen, James (J.) <jchen303@ford.com>&IPC Cao, Helen (H.) <hcao22@ford.com> |  | folder: cluster Interaction | HW_Tier1 | 60 | 20 | 0 | 20 | Y | Y |  |  | Y | [6 empty] | Phase 1 | Yes | R8 | 2021-10-20
SYNC+_Z0062 | SYNC+_0169 | ZZ# Foundemental Function 基础功能 | Music | Music-音频设置入口 sound frequency setting |  | IVI | Song, Rui (Rex.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | Yes | R5 | 2021-07-10
SYNC+_Z0063 | SYNC+_0266 | ZZ# Foundemental Function 基础功能 | OTA | U盘升级 USB drive update（SOC) |  | IVI | Wang, Fin (X.Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Phase 1 | Yes | R3 | 2021-05-26
SYNC+_Z0065 | SYNC+_0154 | ZZ# Foundemental Function 基础功能 | Security Device | 网络安全解决方案 |  | Cyber Security | Shao, Jian (J.) |  |  | SW_Tier1 | 0 | 50 | 50 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R12 | 2022-02-15
SYNC+_Z0066 | SYNC+_0406 | ZZ# Foundemental Function 基础功能 | Settings | V2I Lite Settings | [5 empty] | Core_Service_Supplier | 0 | 0 | 0 | 100 | Y | Y |  |  | Y | [6 empty] | Phase 3 | No | R12 | 2022-02-15
SYNC+_Z0105 | SYNC+_0151 | ZZ# Foundemental Function 基础功能 | Soft Button | 手机端福特派&账号互通 Fordpass & account connection |  | CVPP-Distribute System | Wang, Johnny (J.) /Xu Xiao Kang |  |  | Core_Service_Supplier | 0 | 0 | 0 | 100 | Y | Y |  |  | Y | [6 empty] | Phase 2 | No | R10 | 2021-12-15
SYNC+_Z0123 | SYNC+_0337 | ZZ# Foundemental Function 基础功能 | System Setting - Others | First Mile Navigation/Last Mile Navigation/Vehicle locator | FindMyCar．First Mile Navigation/Last Mile Navigation/Vehicle locator | CVPP | Shi Stella/Lu Chao |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R12 | 2022-02-15
SYNC+_Z0124 | SYNC+_0313 | ZZ# Foundemental Function 基础功能 | System Setting - Others | Infotainment Diagnostic Spec- Speaker walk around 挨个喇叭发出声音（工程模式下显示） |  | IVI | Wang, Fin (X.Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | Yes | R5 | 2021-07-10
SYNC+_Z0131 | SYNC+_0006 | ZZ# Foundemental Function 基础功能 | System UI | 12.3' Landscape Launcher main cards | including weather, etc. | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | N | N |  |  | N | [6 empty] | Phase 1 | No | - | -
SYNC+_Z0132 | SYNC+_0007 | ZZ# Foundemental Function 基础功能 | System UI | 12.3' Landscape Luanch domain cards |  | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | N | N |  |  | N | [6 empty] | Phase 1 | No | - | -
SYNC+_Z0133 | SYNC+_0008 | ZZ# Foundemental Function 基础功能 | System UI | 12.3' Touch Screen HMI (Lincoln） | Persistent Bar;Domain Cards; Main Cards | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | N | N |  |  | N | [6 empty] | Phase 1 | No | - | -
SYNC+_Z0134 | SYNC+_0003 | ZZ# Foundemental Function 基础功能 | System UI | 12.8' Portrait Launcher -12.8' Portrait Launcher main cards | Weather, Voice command suggestion, Vehicle information | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | N | N |  |  | N | [6 empty] | Phase 1 | No | - | -
SYNC+_Z0135 | SYNC+_0004 | ZZ# Foundemental Function 基础功能 | System UI | 12.8' Portrait Launcher -12.8' Portrait Luanch domain cards | High series - Navigation, Online music, weather etc. Low series - Navigation, Online music, etc. | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | N | N |  |  | N | [6 empty] | Phase 1 | No | - | -
SYNC+_Z0136 | SYNC+_0005 | ZZ# Foundemental Function 基础功能 | System UI | 12.8' Portrait Launcher -12.8' Portrait Luanch persisten bar | High series - Vehicle control, temperature adjuster, climate status display, 360 camera, weather Low series - Vehicle control, temperature adjuster, climate status display, More Apps | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | N | N |  |  | N | [6 empty] | Phase 1 | No | - | -
SYNC+_Z0137 | SYNC+_0011 | ZZ# Foundemental Function 基础功能 | System UI | 12.8' Touch Screen HMI (Lincoln） | Persistent Bar;Domain Cards; Main Cards | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | N | N |  |  | N | [6 empty] | Phase 2 | No | - | -
SYNC+_Z0138 | SYNC+_0402 | ZZ# Foundemental Function 基础功能 | System UI | 13.2' Landscape Launcher main cards | including weather, etc. | HMI |  |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 3 | No | - | -
SYNC+_Z0139 | SYNC+_0403 | ZZ# Foundemental Function 基础功能 | System UI | 13.2' Landscape Luanch domain cards |  | HMI |  |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 3 | No | - | -
SYNC+_Z0140 | SYNC+_0404 | ZZ# Foundemental Function 基础功能 | System UI | 13.2' Touch Screen HMI (CD539ICA) | 13.2' Landscape Luanch persisten bar 13.2' Landscape Luanch domain cards 13.2' Landscape Launcher main cards | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | - | -
SYNC+_Z0141 | SYNC+_0458 | ZZ# Foundemental Function 基础功能 | System UI | 27“ 快捷面板/quick panel |  | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Design Guideline_CD542_To Supplier(11.15) compressed | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | - | -
SYNC+_Z0142 | SYNC+_0527 | ZZ# Foundemental Function 基础功能 | System UI | Animation [Background, others] | Home screen 上面的背景动效 | HMI | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y |  |  |  | Y | [6 empty] | Phase 4 | No | TBD
SYNC+_Z0143 |  | ZZ# Foundemental Function 基础功能 | System UI | Dual 23.6'+11.1 Touch HMI - Screen sharing to horizon display (Center Stack and Panoramic, and passenger/driver screen interaction) - Personalization |  | HMI | Sun, Xiao/Yu,Diven |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y |  | Y |  |  |  |  | Phase 4 | Yes | R3 | 2021-05-26
SYNC+_Z0144 | SYNC+_0524 | ZZ# Foundemental Function 基础功能 | System UI | English HMI(bezel diagnostic, etc.) |  | EESE/IVI(Forrest) | Wang, Fin (X.Y.) <xwang65@ford.com> |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | TBD
SYNC+_Z0145 | SYNC+_0377 | ZZ# Foundemental Function 基础功能 | System UI | Lincoln Branded HMI | Lincoln Branded Audio | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 2 | No | TBD
SYNC+_Z0146 | SYNC+_0396 | ZZ# Foundemental Function 基础功能 | System UI | Lincoln specific animations | 例如空调的动效 | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 2 | No | TBD
SYNC+_Z0147 | SYNC+_0012 | ZZ# Foundemental Function 基础功能 | System UI | UI&UE设计规范 |  | HMI | Xiao, Yun (Y.) |  |  | Ford HMI | 0 | 0 | 100 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | TBD
SYNC+_Z0148 | SYNC+_0482 | ZZ# Foundemental Function 基础功能 | System UI | 副驾主页/Passenger HomeScreen | 副驾在线视频/Online Video-clarify 副驾视频播放(支持 DLNA)/Passenger Video Playback(Support DLNA） 副驾在线视频/Online Video-clarify 副驾视频播放(支持 DLNA)/Passenger Video Playback(Support DLNA | EESE/IVI(Forrest) | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | TBD
SYNC+_Z0149 | SYNC+_0526 | ZZ# Foundemental Function 基础功能 | System UI | 快速切换最近使用的APP |  | HMI | Xiao, Yun (Y.) <yxiao21@ford.com> |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | TBD
SYNC+_Z0150 | SYNC+_0001 | ZZ# Foundemental Function 基础功能 | System UI | 百度相关功能HMI的UX、UI、动效设计及开发 | 包括语音、导航、随心听、个人中心、账号登录、支付、车家互联、安全、个性化车控 | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | TBD
SYNC+_Z0151 | SYNC+_0002 | ZZ# Foundemental Function 基础功能 | System UI | 除百度应用之外的车机功能UX、UI、功效设计及开发 | 收音机、电话、个性化车控、设置、ADAS、消息通知倒车设置等其它未列功能 | HMI | Xiao, Yun (Y.) |  |  | HW_Tier1 | 100 | 0 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | TBD
SYNC+_Z0154 | SYNC+_0450 | ZZ# Foundemental Function 基础功能 | TCU | TCU- 用户流量统计及购买/Cellular data purchase and management |  | CVPP | Lu, Chao (C.) <clu42@ford.com> |  | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf | ?? | 0 | 0 | 100 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R11 | 2022-01-07
SYNC+_Z0157 | SYNC+_0127 | ZZ# Foundemental Function 基础功能 | User Data Burying point | 用户使用数据埋点 Phase 1 | 统计功能使用情况和用户偏好 Statistics feature usage and user preferences | CVPP | Fan, Henry (H.) |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 2 | No | R13 | 2022-03-15
SYNC+_Z0158 | SYNC+_0128 | ZZ# Foundemental Function 基础功能 | User Data Burying point | 用户使用数据埋点 Phase 2 | 统计功能使用情况和用户偏好 Statistics feature usage and user preferences | CVPP | Fan, Henry (H.) |  |  | SW_Tier1 | 0 | 100 | 0 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R13 | 2022-03-15
SYNC+_Z0179 | SYNC+_0215 | ZZ# Foundemental Function 基础功能 | Vehicle Setting on IVI - Light | Light Setting-Auto highbeam |  | IVI-Distribute DAT | Amy Song |  |  | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | Y |  |  | Y | [6 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0067 | SYNC+_0301 | ZZ# Foundemental Function 基础功能 | Settings | 流量管理 |  | CVPP | Lu, Chao (C.) |  |  | SW_Tier1 | 0 | ？ | 100 | 0 | Y | Y |  |  | Y | [6 empty] | Phase 3 | No | R12 | 2022-02-15
SYNC+_0080 |  | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 盲点检测 Blind Spot Assist |  | Y-1st | Zhou, Wu (W.) | N | Y | [5 empty] | Y |  |  |  | Y | [6 empty] | Phase 2 | No | TBD
SYNC+_0083 | SYNC+_0446 | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 车道保持辅助 Lane keep aid |  | DAT | Zhang, Wayne (W.R.) <wzhan114@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | Core_Service_Supplier | 10 | 0 | 0 | 90 | Y | Y |  |  | Y | [6 empty] | Phase 4 | Yes | R5 | 2021-07-10
SYNC+_Z0225 |  | D# Co-Pilot360 驾驶辅助 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 自适应巡航设置 iACC 1.0 | 有ADAS地图里的限速信息+车端Camera 识别的 traffic Sign Recognition 跟ADAS 地图做了一个融合。U625 全系标配， 有的车型高配才有。 Intelligent Adaptive Cruise Control(iACC) is a feature built on top of ACC(Adaptive Cruise Control). It will utilize the forward facing camera to perform Traffic Sign Recognition(TSR) to identify the speed limit of the road. Then, iACC will update the set speed to the new speed limit, plus or minus the drivers preference. | N | Cui, Victor (M.) <mcui5@ford.com> | N | N | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R9 | 2021-11-17
SYNC+_Z0223 | SYNC+_0537 | D# Co-Pilot360 驾驶辅助 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 巡航 ACC | 有ADAS地图的车上面， traffic Sign Recognition 跟ADAS 地图做了一个融合。U625 全系标配， 有的车型高配才有。 Intelligent Adaptive Cruise Control(iACC) is a feature built on top of ACC(Adaptive Cruise Control). It will utilize the forward facing camera to perform Traffic Sign Recognition(TSR) to identify the speed limit of the road. Then, iACC will update the set speed to the new speed limit, plus or minus the drivers preference. | DAT | Cui, Victor (M.) <mcui5@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R9 | 2021-11-17
SYNC+_Z0228 | SYNC+_0440 | D# Co-Pilot360 驾驶辅助 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 限速和超速提醒 Traffic Sign Recognition (TSR) | Speed Limit and Overtaking Information Function (SLOIF) 限速和禁止超车显示。（只显示不干预). Overtaking 禁止超车 - 中国独有.一般的说TSR就是指的这个 | DAT | Cui, Victor (M.) <mcui5@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y |  |  | Y | [6 empty] | Phase 4 | Yes | R5 | 2021-07-10
SYNC+_Z0224 | SYNC+_0444 | D# Co-Pilot360 驾驶辅助 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 智能车速辅助 Intelligent Speed Assistance | 智能限速。 识别限速的情况下， 用户怎么踩油门，都不会超过该限速 | DAT | Cui, Victor (M.) <mcui5@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R9 | 2021-11-17
SYNC+_0085 | SYNC+_0242 | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 变道辅助 Lane Change Warning & Aid (LCWA)//also called as "Blind Spot Assist" |  | EESE/IVI-Distribute DAT | Zhou, Wu (W.) <wzhou44@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y |  |  | Y | [6 empty] | Phase 2 | Yes | R5 | 2021-07-10
SYNC+_Z0086 | SYNC+_0370 | Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Lincoln Seats shortcut | Lincoln Seats shortcut key-Lincoln unique MCS seats and seat adjustment；4 or 2 way lumbar | IVI-Distributed BS | Zhu, Jing Yuan (J.) <JZHU65@ford.com>；Wang, Fin (X.Y.) <xwang65@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y |  |  | Y | [6 empty] | Phase 2 | No | R6 | 2021-08-18
SYNC+_0100 | SYNC+_0502 | D# Co-Pilot360 驾驶辅助 | 4# Help Me Avoid Collisions 避免碰撞辅助 | 变道辅助 trail Turn Assist (Soft switch) |  | DAT | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  | TTA_SoftSwitch_FunctionSpecification_112519.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y |  |  | Y | [6 empty] | Phase 4 | No | R8 | 2021-10-20
SYNC+_0097 | SYNC+_0243 | D# Co-Pilot360 驾驶辅助 | 4# Help Me Avoid Collisions 避免碰撞辅助 | 交通预警 2.0 Cross Traffic Alert 2.0 | 增加倒档来车预警- 软按键功能 on/off | EESE/IVI-Distribute DAT | Zhou, Wu (W.) <wzhou44@ford.com> |  | Cross Traffic Alert APIM SPSS v1.4 Dec 2, 2020.pdf Cross Traffic Alert APIM Imp Guide v1.4 Dec 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y |  |  | Y | [6 empty] | Phase 2 | No | R9
SYNC+_0071 | SYNC+_0378 | D# Co-Pilot360 驾驶辅助 | 1# Help Me Park 停车辅助 | FAPA 硬/软按键 Fully automated park assist (FAPA) - hard short cut/HMI UI | Lincoln Fully automated park assist (hard shortcut keys/HMI) | DAT | He, Michael (X.) <xhe22@ford.com> |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y |  |  | Y | [6 empty] | Phase 2 | No | R9 | 2021-11-17
SYNC+_0075 | SYNC+_0259 | D# Co-Pilot360 驾驶辅助 | 1# Help Me Park 停车辅助 | 泊车辅助 RPA-Reverse Parking Aid | 4 ultra sonic sense (USS) only; Example obstical warning e.g fiesta high series | EESE/IVI-Distribute DAT | He, Michael (X.) <xhe22@ford.com> |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y |  |  | Y | [6 empty] | Phase 1 | No | R9 | 2021-11-17
SYNC+_0024 | SYNC+_0465 | C# Intelligent Digital Assitant 智能数字助手 | 1# Foundemental Voice Capability 基础语音功能 | 前排双音区语音助手识别率提高 Enhanced Accuracy for Dual Zone Voice Recognition | 硬降噪，提升了主副驾同时说话场景 识别率和唤醒率。 | EESE/IVI(Diven) | Qi, Xuliang <xqi14@ford.com> |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y |  |  | Y | [6 empty] | Phase 4 | Yes | R5 | 2021-07-10
SYNC+_0026 | SYNC+_0019 | C# Intelligent Digital Assitant 智能数字助手 | 1# Foundemental Voice Capability 基础语音功能 | 定向拾音（主驾增强）Oriented Voice recognition (Driver orientation enhancement) |  | EESE/IVI | Qi, Xuliang <xqi14@ford.com> |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y |  |  | Y | [6 empty] | Phase 1 | Yes | R5 | 2021-07-10
SYNC+_0243 |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 蓝牙电话接听/拒接 语音控制 Anwer/Reject A Coming Call (BT Connected) |  | EESE | Qi, Xuliang <xqi14@ford.com> |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 40% | 60% | 0% | 0% | Y | Y |  |  | Y | [6 empty] | Phase4 | No | R9
SYNC+_0033 |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | AR 导航 AR Navigation On Cluster (Driver Side) |  |  | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | Y | Y | Y | [7 empty] | Phase 4 | No | R12 | 2022-02-15
SYNC+_0038 |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 数字香氛 Digital Scent |  | EESE/IVI | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 10% | 60% | 0% | 30% | N | N | Y | [7 empty] | Phase 3 | No | - | -
SYNC+_0043 |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 随心拍 Travel Shooting | 利用AR导航摄像头拍照和视频，本地功能 |  | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | Y | [7 empty] | Phase 4 | No | R9 | 2021-11-17
SYNC+_0244 |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 语音控制 - 舒享时分/自由秘境 功能 Voice Control over "Relax/At Ease" |  | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 60% | 40% | 0% | Y | Y | [8 empty] | Phase3 | No | R13
SYNC+_0245 |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 语音智能家居控制 Voice Control Over Home Electronics | 智能家居添加智能设备后，可通过语音控制 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | Y | [7 empty] | Phase1 | No | R13
SYNC+_0246 |  | C# Intelligent Digital Assitant 智能数字助手 | 2# Voice Control - Vehicle Function 语音控制 - 车辆功能 | 语音发起蓝牙电话 Voice Initial A Phone Call | 支持号码簿联系人拨号；直接号码拨号；常见黄页号码（110；119 etc.) | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 40% | 60% | 0% | 0% | Y | Y | Y | [7 empty] | Phase1 | No | R9
SYNC+_0044 | SYNC+_0414 | C# Intelligent Digital Assitant 智能数字助手 | 3# Voice Control - IVI Application 语音控制 - 信息娱乐系统 | 电子用户手册语音搜索 E-Manual Voice Search | Voice Command open E-manual; Voice search content (20 keywords voice search） | EESE | Jiang, Wei (W.); Qi XuLiang |  |  |  | Ford_InHouse | 0% | 25% | 75% | 0% | Y | Y | Y | [7 empty] | Phase 3 | No | R13 | 2021-12-15
SYNC+_0242 |  | C# Intelligent Digital Assitant 智能数字助手 | 1# Foundemental Voice Capability 基础语音功能 | 非全时免唤醒 Voice Assistant Keep Listening Status in 30S once wakeup | 语音助手唤醒后，30s 内语音助手一直在听,无需再次唤醒 | EESE | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | Y | [7 empty] | Phase3 | Yes | R5
SYNC+_0045 | SYNC+_0042 | C# Intelligent Digital Assitant 智能数字助手 | 3# Voice Control - IVI Application 语音控制 - 信息娱乐系统 | 百度地图导航 Baidu Map Navigation | 语音发起导航 Activate NAV with Voice command 语音发起导航 Activate NAV with Voice command 语音发起导航 Activate NAV with Voice command 语音发起取消导航 Activate NAV with Voice command 语音结束导航 End/Cancel navigation with voice command-结束导航 End navigation 语音开打退出导航APP Entry Navigation APP with voice command 语音更改昼夜模式 Switch day/night mode with voice command 语音控制地图缩放 Zoom in/out with voice command 语音控制导航模式切换 Navigation mode switch with voice command-查看全程/全览 Check route status overview 语音控制导航模式切换 Navigation mode switch with voice command-继续导航 Continue navigation 语音控制地图模式切换 Map mode switch with voice command-正北模式/正北朝上 North mode/ Nav pointer oriented to north 语音控制地图模式切换 Map mode switch with voice command-跟随模式/车头朝上 Follow mode/Nav pointer oriented as Vhicle orientation 路况查询 traffic query 位置查询 location query 路况打开/关闭 open/close road condition 添加途径点 add pass-by 声控电子狗 Radar detector with voice recognition function-打开电子狗/进入巡航模式 Turn on radar dector 声控电子狗 Radar detector with voice recognition function-关闭电子狗/退出巡航模式 Turn off radar dector 路径规划策略调整 route planning streategy-推荐路线 Recommended route 路径规划策略调整 route planning streategy-时间优先 time prioritize 路径规划策略调整 route planning streategy-高速优先 High-way prioritize 路径规划策略调整 route planning streategy-不走高速 No highway 路径规划策略调整 route planning streategy-少收费 Less charging | EESE/IVI | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | Y | [7 empty] | Phase 1 | Yes | R5 | 2021-07-10
SYNC+_0046 | SYNC+_0066 | C# Intelligent Digital Assitant 智能数字助手 | 3# Voice Control - IVI Application 语音控制 - 信息娱乐系统 | 随心听 Suixinting | 音乐 Music 语音泛需求搜索 音乐 Music 分类需求搜索 有声 Audio book 语音泛需求搜索 有声 Audio book 分类需求搜索 新闻 News 语音控制曲目 Voice command to control music player 我喜欢这个 like this 我不喜欢这个 dis- like 语音泛需求搜索（打开音乐、播放歌曲）fuzzy search | EESE/IVI | Qi, Xuliang <xqi14@ford.com> |  |  | Voice recognition spec - 20191121.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | Y | [7 empty] | Phase 1 | Yes | R5 | 2021-07-10
SYNC+_0072 |  | D# Co-Pilot360 驾驶辅助 | 1# Help Me Park 停车辅助 | FAPA 语音推荐/指导 Fully automated park assist (FAPA) - Voice Recommend / Guidance |  | EESE/DAT | Zhang, Xiaojing (X.) <xzhan247@ford.com> - Voice/education；He, Michael (X.) -DAT Feature Owner |  |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y | Y | [7 empty] | Phase 2 | No | R9 | 2021-11-17
SYNC+_Z0082 | SYNC+_0240 | Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Lane keeping mode (alert, aid, alert + aid), alert intensity (high, medium, low), sensitvity (normal, increased), lane keeping aid (on, off), lane keeping alert (high, medium, low, on, off) |  | IVI-Distribute DAT | Zhu, Jing Yuan (J.) <JZHU65@ford.com> | Need confirm with PMT5 |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R6 | 2021-08-18
SYNC+_Z0233 | SYNC+_0447 | Vehicle Setting 车辆设置 | DAT Setting | 4# Help Me Avoid Collisions 避免碰撞辅助 - 碰撞缓解 Pre-collision Assist (Camera + Radar). Also called AEB |  | DAT | Wang, Lynn (X.) <xwang187@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 4 | Yes | R5 | 2021-07-10
SYNC+_Z0184 | SYNC+_0192 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lincoln colors | different color with Ford | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0048 | SYNC+_0325 | Vehicle Control 车辆控制 | Seat Control 座椅控制 | Multi contour seat-Custom Massage Patterns HMI for Multi-Contour Seats (U611) |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Multi Contoured Seats Client V2 SPSS v1.5 June 9, 2020.pdf Multi Contoured Seats Client V2 Imp Guide v1.5 June 9, 2020.xlsx Power Lumbar Seat Client APIM SPSS v1.1 Apr 5, 2017.pdf Power Lumbar Seat Client APIM Imp Guide v1.1 Apr 5, 2017.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 1 | Yes | R5 | 2021-07-10
SYNC+_Z0049 | SYNC+_0324 | Vehicle Control 车辆控制 | Seat Control 座椅控制 | Multi contour seat-Multi contour seat-Seat massage | 座椅按摩 | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Multi Contoured Seats Client V2 SPSS v1.5 June 9, 2020.pdf Multi Contoured Seats Client V2 Imp Guide v1.5 June 9, 2020.xlsx Power Lumbar Seat Client APIM SPSS v1.1 Apr 5, 2017.pdf Power Lumbar Seat Client APIM Imp Guide v1.1 Apr 5, 2017.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | Yes | R5 | 2021-07-10
SYNC+_Z0188 | SYNC+_0221 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting-auto unlock |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0189 | SYNC+_0220 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting-autolock |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0190 | SYNC+_0227 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting-Exterior light feedback |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0191 | SYNC+_0229 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting-Global unlock |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0192 | SYNC+_0224 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting-Intelligent access |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0193 | SYNC+_0225 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting-Key free |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0194 | SYNC+_0222 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting-mislock |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0195 | SYNC+_0228 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting-Remote unlock |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0196 | SYNC+_0223 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting-switch inhibit |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0198 | SYNC+_0231 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Mirror Setting-Reverse tilt |  | IVI-Distributed BS | Li, Xuedong (X.) <XLI244@ford.com> |  |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 2 | No | R8 | 2021-10-20
SYNC+_Z0207 | SYNC+_0430 | Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Ford Vehicle Settings On IVI [include: AutoHold, AutoStartStop.] |  | EESE/IVI(Forrest) | Chen, Emma (J.) <jchen276@ford.com> | Need delete |  | Settings In Infotainment CenterStack SPSS v1.20 Nov 2, 2020.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.20 Nov 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | Y | [7 empty] | Phase 4 | No | R8 | 2021-10-20
SYNC+_Z0267 |  |  |  | Programmable Electric Preconditioning and Charging (PEPC) (CDX746/7) | ZZ# Foundemental Function 基础功能 |  | Programmable Electric Proconditioning and Charging (PEPC) |  | EPE | Wu, Dean (D.) <dwu44@ford.com> | Andrade, Ana (A.C.) |  | EV Charge Programming v1 APIM SPSS v1.7 Aug 20, 2019_new.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | N | [8 empty] | - | - | -
Note on AC39: Huang, Feng (F.): 电车实时车况界面IOD需求（是否适用于707）需要进一步和Xuedong/HMI team一起讨论
Note on AC40: Huang, Feng (F.): 电车实时车况界面IOD需求（是否适用于707）需要进一步和Xuedong/HMI team一起讨论
Note on AC41: Huang, Feng (F.): 电车实时车况界面IOD需求（是否适用于707）需要进一步和Xuedong/HMI team一起讨论
Note on AC42: Huang, Feng (F.): 电车实时车况界面IOD需求（是否适用于707）需要进一步和Xuedong/HMI team一起讨论
Note on AC43: Huang, Feng (F.): 电车实时车况界面IOD需求（是否适用于707）需要进一步和Xuedong/HMI team一起讨论
Note on AC55: Zhou, Jiajia (J.): 1. R8为功能模式全功能释放节点。 2. 工程模式R5版本提供部分功能支持，具体支持功能请参考12/22 Huang Feng发出的Round2 MM。
Note on AC59: Huang, Feng (F.): 车机授权是指 FNVX CCS,1/19/2021：CCS R7 合入，R8 全功能. Dapeng 提供FNV3 related feature release road map.
Note on AC62: Huang, Feng (F.): 1. TCU的WiFi, WiFi Hotspot功能需求要Ford FO澄清。 2. YF暂定R2版本提供IVI芯片中的WIFI功能满足其他应用联网需求。
Note on AC67: Huang, Feng (F.): USB升级包括SOC+MCU 1.R3支持：SOC 2.R4支持：MCU
Note on AC85: Huang, Feng (F.): 参考SYNC+_0204
Note on AC100: Huang, Feng (F.): 完成台架信号调试完成（后续DV实验前释放的车控，车设功能也特指台架信号调试），特指SOC内部链路调通。假设DCV节点有实车提供，YFV可以在2个月内完成实车功能调试及功能释放。
Note on AC112: Huang, Feng (F.): 1. 双MIC功能R2版本实现，支持多音区及定位识别。 2.在CDC项目中目前对于MIC的回声消除和降噪（ECNR）采用软件方案，此方案依赖项目定点后买ECNR包，所以在Pre-DV前无法支持软件ECNR功能，这是风险项需要重点关注。
Note on AC113: Huang, Feng (F.): 参考SYNC+_0024

## PDL
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Feature_ID | Feature_Product_Suite | Feature_Group | Feature_Name | Feature_Description | VSEM ID | VSEM Summary | PO | Assumption Lead | FO/TL | FO/TL Supervisor | HMI Lead | Delivery Lead Team | Feature_Source | HW Enabler | Phase5 | P5_CDX707 | P5_CX788 | P5_CDX747 | P5_P702MCA | P5_U611MCA | P5_U625MCA
SYNC+_0001 | A# Navigation 地图导航 | 1# Navigation - Basic Function 基础导航功能 | 地图基础版（见《IOV-地图功能list) Foundamental version of Map | 见《IOV-地图功能list)。 支持地图包更新MOTA。 POI检索、地点收藏 POI search & store destinations 3D地图 3D Map 首页地图 Launcher Map 地图显示的夜间/白天模式 Night/Day Mode 实时交通播报 Real-time Traffic Broadcast 惯性导航 Inertial Navigation 超速提醒 Reminder of over speed 路线雷达 radar detection in routes 限行提醒 Reminder of traffic control rules |  |  | Eva Chen | ECDx | Yao, Tristan (Lan) <LYAO17@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0002 | A# Navigation 地图导航 | 1# Navigation - Basic Function 基础导航功能 | 开始导航倒计时/导航结束卡片 Starting/Ending Count Down |  |  |  | Eva Chen | ECDx | Yao, Tristan (Lan) <LYAO17@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Ford China/Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0003 | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 个性化底图-4S店POI显示 4S Dealer POI on Map | 福特品牌显示福特标，林肯品牌显示林肯标，野马显示野马标 |  |  | Eva Chen | ECDx | Yao, Tristan (Lan) <LYAO17@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Ford China/Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0004 | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 本地危险事件上报及播报 LHI (Local Hazard Information) | 危险事件上报及播报 |  |  | Eva Chen | ECDx | Lin, Shawn (X.) <xlin17@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Baidu/Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0006 | A# Navigation 地图导航 | 3# Navigation - Team Travel 组队出行 | 组队出行 Team Travel | 分享地址，支持Ford/Lincoln 车型间 语音对讲 |  |  | Eva Chen | ECDx | Yao, Tristan (Lan) <LYAO17@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0007 | A# Navigation 地图导航 | 4# POI Sharing/Receiving 地址分享 地址分享 | 微信地址分享 WeChat Send To Car | 微信中收到的地址可以长按选择百度地图，地址会同步给相同百度地图账号的车机端。首次需微信扫描车机二维码，关联账号 （又被叫做：微信互联） |  |  | Eva Chen | ECDx | Yao, Tristan (Lan) <LYAO17@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0008 | A# Navigation 地图导航 | 4# POI Sharing/Receiving 地址分享 地址分享 | 福特派/林肯之道地址分享 FordPass/LincolnWay Send to car | Send to car--把用户在FordPass 内置的地图查询的POI发送到车机 Send POI from smartphone APP to vehicle |  |  | Eva Chen/ Tony Liu | ECDx | Shi, Stella (J.) <jshi32@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | FordChina | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0009 | H# Service & Maintenance 车主服务 | 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | 车辆状态 Vehicle Status (Vehicle Locator车辆位置, Mileage总里程, DTE 续航里程， Tire Pressure 胎压）On IVI 或Fordpass/Lincoln Way， 同时支持智能音箱在家查询. | (Vehicle Locator车辆位置, Mileage总里程, DTE 续航里程， Tire Pressure 胎压。 车辆位置-熄火时最后的位置同步到FordPass/Lincoln Way.位置准确度有限， 更多用来标准大概区域。 IVI 端显示内容取决于项目仪表(大小，其他影响), 具体项目落地情况需与项目确认. Phase 1- 信息来源不同Cluster/TCU/ Phase 2- 全部TCU 提供信息 |  |  |  | ECDx | Chen, Wei (W.) <WCHEN160@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Baidu | SW | N | N | N | N | N | N | N
SYNC+_0010 | A# Navigation 地图导航 | 5# AR Navigation AR 导航 | AR 导航 AR Navigation | AR/专业地图切换AR/2D/Normal View Switch 终点目的地Destination Hint 道路吸附指引（主动）Road Guidance Arrow AR导航自动切换路线Road Guidance Arrow 语音指令Road Guidance Arrow 车道线偏离提醒Road Guidance Arrow 全览小地图Minimap overview 交通标志物识别TSR（Traffic Sign Recognition） |  |  |  | Tech Planning | Yu, Diven (D.W.) <dyu12@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu?? | HW | Y | Y | Y | Y | N | N | N
SYNC+_0011 | B# Multimedia 多媒体 | 1# Radio 电台/收音机 | FM/AM收音机 AM/FM Radio （Anteena Based天线接收） | 收音机 radio-基本控制(上一个/下一个) foundamental control 收音机 radio-输入频段 channel input 收音机 radio-启动/停止收音机 turn on/off 收音机 radio-手动调台 manual tuning 收音机 radio-收藏列表 collections； Baidu: 自带的随声听App音乐是具有收藏列表的。Baidu需要design 收藏列表的HMI，配合Tier1实现该功能。 收音机 radio-更新电台列表(扫描及更新）update channels 收音机 radio-FM2 相关的菜单及功能 |  |  |  | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Ford Global | HW | Y | Y | N | Y | Y | Y | Y
SYNC+_0012 | B# Multimedia 多媒体 | 1# Radio 电台/收音机 | 在线收音机/电台 Online Radio 资源提供方：蜻蜓FM | 资源能力提升. 资源涵盖不受传统radio 的地域限制。支持节目名称搜索，和收藏。 资源提供方：蜻蜓FM。 取决于电台是否做了online radio (有单独的license, 涵盖在phase 4 license 里面) Enhanced Online Radio (resource: 蜻蜓FM - 公版). with more radio programs without geograph constrains. Support voice command of "open online Radio" " Previouse one" " Next one" " Save". Availible for Phase 4 programs. Currently booked on CD542;U554;U725:P702;CX727. Other programs will need to book application cost if have display size differences. Attention: Keep pay attention to customer feedback and see opportunity of replace Traditional FM/AM using it. Things been called out by team - Data Consumption & Support 流量影响 - Online Radio's Resources & UE Improvement |  |  |  | ECDx | Wang, Fin (X.Y.) <xwang65@ford.com>; Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Ford China/Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0013 | B# Multimedia 多媒体 | 2# Bluetooh Phone 蓝牙电话 | 蓝牙电话 Bluetooh Phone | 接听挂断；通话记录 records；拨号 dial；通讯录搜索；通讯录 contacts；同步通讯录和通话记录 sync contacts& records；请勿打扰 DO NOT IDSTURB |  |  |  | EESE | Xu, Amy (X.) <xyafei@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Ford Global | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0014 | B# Multimedia 多媒体 | 3# Music 音乐 | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) | 增加一个蓝牙模块，用来链接蓝牙耳机。 场景： 主驾听音乐（vehicle speaker); 副驾可连接自己的蓝牙耳机， 在双开模式下选择不同音乐资源来听 （支持在线音乐合本地音乐；不支持FM/AM;和蓝牙音乐） |  |  |  | EESE | Xu, Amy (X.) <xyafei@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI(Diven) | Ford China | HW | Y | Y | N | Y | N | Y | Y
SYNC+_0015 | B# Multimedia 多媒体 | 3# Music 音乐 | 本地音乐-MTP音乐 MTP music/USB音乐 USB music/蓝牙音乐 BT music | MTP (Media Tranfer Protocol)，可以本地外接音乐设备如iPod, 手机 |  |  |  | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Ford Global | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0016 | B# Multimedia 多媒体 | 3# Music 音乐 | 随心听- Ximalaya 2.0 | 允许用户登录自己账户 Suixinting: Ximalaya allow user login and enjoy more paid audio resources |  |  |  | ECDx | Shi, Stella (J.) <jshi32@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford China/Baidu | Sw | Y | Y | Y | Y | Y | Y | Y
SYNC+_0017 | B# Multimedia 多媒体 | 3# Music 音乐 | 随心听- 音乐/新闻/有声书 (QQ 音乐-支持QQ 音乐账号登陆；喜马拉雅免费资源集成） | 可以基于账号及喜好记忆进行主动推荐 Audio book/News/Music recommended according to account & preference |  |  |  | ECDx | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0018 | B# Multimedia 多媒体 | 3# Music 音乐 | 随心听-QQ 音乐2.0 Suixinting: QQ Music 2.0 | 1.随心听VIP试听功能。 2.随心听歌曲切换音质。 3.同步手机端QQ音乐的歌单数据（默认自带歌单、自创建歌单、收藏的歌单）。 4.随心听增加歌手入口以及歌手搜索功能。 5. 登录页toast提示使用VIP账号登录，登录后显示账号是否是绿钻账号。 |  |  |  | ECDx | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Baidu/Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0019 | B# Multimedia 多媒体 | 4# Video 视频 | USB视频播放 Video- USB video | 需要支持主流视频格式 |  |  |  | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Ford Global | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0020 | B# Multimedia 多媒体 | 4# Video 视频 | 爱奇艺 (在线视频APP) Video - Streaming video Iqiyi |  |  |  |  | ECDx | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0021 | B# Multimedia 多媒体 | 4# Video 视频 | 视频、音乐、图片DLNA投屏到车机显示器区分主副驾/Video Playback and Video and Photo project to Display(Driver and Passenger) via DLNA |  |  |  |  | EESE | Jia, Elaine (T.) <tjia2@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI(Diven) | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0022 | B# Multimedia 多媒体 | 5# Sound & Effect 音效 | 底特律之音 Detroit Symphony Orchestra chimes | Detroit Symphony Orchestra chimes (林肯飞行家上面的底特律交响乐团打造的提示音） |  |  |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Ford Global | HW-外置功放支持立体音效 | Y | Y | N | Y | N | Y | N
SYNC+_0023 | B# Multimedia 多媒体 | 5# Sound & Effect 音效 | 电动车独有音效 EV Unique Chime (CDX727 lead) | Lead by CD727. Details need to be updated |  |  |  | EESE |  | Xu, Roger (.) <pxu15@ford.com> |  | EESE | Ford Global | HW-外置功放支持立体音效 | Y | N | N | N | N | N | N
SYNC+_0025 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 播报能力+语音包 Multiple TTS (可切换） | 交互信息、提示信息、百度百科、电子说明书等语音播报， 并支持多种TTS 台湾女声（金莎语音PhaseII）、情感女声、标准女声，标准男声。 地图场景下有更丰富的语音包下载使用。 |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0027 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 所见即可说 Voice command on IVI displayed touch elements | 系统界面可看见的文字，均可语音控制，部分APP包括爱奇艺的播放控制、外卖、酒店、智慧停车场、电影票、也支持。 |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu/Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0028 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 打断式交互 全双工语音 Barge-in | 在语音助理进行播报时，用户可随时进行进一步的交互或说出新的命令，让助理执行相关操作，而无需等待播报结束； 支持双方同时说，互不干扰 |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0029 | C# Intelligent Digital Assitant 智能数字助手 | 2# Natual Language Recognition 自然语音识别 | 普通话识别 Mandarin Rocognition | 本地/在线语音识别，将用户语音识别为文字. 识别率，根据背景噪声的大小高噪85%、中噪90%、低噪92%。 方言识别率低，取消了 。 方言识别率目前较低 |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0030 | C# Intelligent Digital Assitant 智能数字助手 | 2# Natual Language Recognition 自然语音识别 | 中英文混杂识别-电话域 Chinese/English mixed phone book recognition | 2000 英文词识别率74%， 不支持其他域 |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0031 | C# Intelligent Digital Assitant 智能数字助手 | 2# Natual Language Recognition 自然语音识别 | 离线指令 Offline Command | >500+ Offline comands |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0032 | C# Intelligent Digital Assitant 智能数字助手 | 2# Natual Language Recognition 自然语音识别 | 中英文混杂 - 音乐域/导航 Mandarin/English mixed language recognition - music/navigation | 识别率74% |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0034 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 前舱盖打开控制 Frunk Control -Open | CDX727 (BEV) _lead |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Ford China | HW | Y | N | N | Y | N | N | N
SYNC+_0035 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 后备箱打开控制 Trunk Control-Open |  |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE | Ford China | HW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0036 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 天窗/遮阳帘控制 Roof window control | 天窗和遮阳帘可以分开控制。但是都由一条CAN 总线实现 |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Ford China | HW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0037 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 座椅加热/通风控制/按摩 Seat Heating&Cooling/Seat Vented/Seat Massage | 三个功能可分开并且强依赖硬件，需核对项目HW Book 情况，确定具体落地 |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Ford China | HW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0039 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 方向盘加热 Heated Steering Wheels Control |  |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Ford China | HW | Y | Y | N | Y | Y | Y | Y
SYNC+_0040 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 氛围灯开关 Ambient Lighting on/off | 打开/关闭 |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Ford China | HW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0041 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 空调;风量和风向 A/C | "出风等级控制 Air volume-增加风量 出风等级控制 Air volume-风量大一点 出风等级控制 Air volume-减少风量 出风等级控制 Air volume-风量小一点 出风等级控制 Air volume-风量正常 出风等级控制 Air volume-调整风量到xx档" "空气系统控制 Climate system control-调整出风方向/下一个出风方向 Air flow direction 空气系统控制 Climate system control-打开/关闭自动除霜系统 defrost 空气系统控制 Climate system control-打开/关闭内循环 recirc 空气系统控制 Climate system control-打开/关闭空气清新系统 fresh air 空气系统控制 Climate system control-打开/关闭后挡风除霜 rear deforst 空气系统控制 Climate system control-打开/关闭自动模式 Auto mode" "打开/关闭空调 open/close AC 空调控制 AC control-设置空调温度到xx度 Temp setting 空调控制 AC control-提高温度 Temp up 空调控制 AC control-降低温度 Temp down 空调控制 AC control-温度最低/最低温度 LO 空调控制 AC control-温度最高/最高温度 HI" |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0042 | C# Intelligent Digital Assitant 智能数字助手 | 5# VPA 形象化语音助手 | 语音助手1.5/2.0 VPA 1.5/2.0 (融合贯通生态的智能化的语音助手） | Include baidu 小程序. V1.5 - 形象是2D的 (首先于phase 4 车型的系统能力限制）。 V2.0 - 形象是3D的, 适用于Phase 5的车型。CNECDMPORT-171 Leading Intelligent skills ( 小度助手/百度语音最新版能力- 具体内容规划参照Product Owner-20201204 add. Plus VPA2.0 or 3.0 leading by Product Owner Chiu, Lulu Support in cabin vehicle control (ideally all), and all IVI software contents e.g navigation, open an app, user manual inquiry, search & play multimedia contents (music, audio book, video, etc). .facilitate conversation for relaxzation (joking, wikipidia, story, lite games) .Have visual character to express emotional elements (thinking, happy, listening) |  |  | Suo, Feifei (F.) <FSUO@ford.com>; Liang, Arthor; | ECDx | Suo, Feifei (F.) <FSUO@ford.com> | Yang, Chris (K.) <kyang21@ford.com> |  | EC Lead | Ford China | SW | Y-1st | Y-1st | Y | Y | Y | Y | Y
SYNC+_0047 | C# Intelligent Digital Assitant 智能数字助手 | 8# Multizone Voice Control 分区语音控制 | Dual Zone Voice Control 主副驾双音区分区控制 | 声源定位. 抢麦功能，判定用户方位，排除车内其他干扰、显示定位方向双音区分区语音控制 Dual Zone Voice Control. 支持主副驾分区控制。 目前双音区， 支持(空调, 方向盘加热, 座椅加热/按摩, 主副驾多媒体内容) 分区控制。 |  |  |  | Tech Planning | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | HW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0048 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 唤醒词 - 品牌唤醒词 Brand wake-up commands | “你好，福特/林肯”默认唤醒词。Contain one-shot feature |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0049 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 免唤醒 - 全局/情景免唤醒 Wake-up Free | 全局免唤醒 - 包含包含QQ音乐/有声/新闻/在线电台/本地电台/本地音乐/蓝牙音乐/爱奇艺等应用运行时（包含后台运行）都可识别指令 （暂停/播放/上一首/下一首). 情景免唤醒 - 电话;随心看;导航;系统控制应用界面打开的情况下， 无需唤醒， 可以识别相关的指令 （接听/拒听电话；地图控制；第几个;上一页/下一页等） |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0050 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 唤醒词 - 自定义 Customized Wake-up keyword 林肯的语音唤醒词“你好，林肯” Lincoln wake-up commands 福特的语音唤醒词“你好，福特” Ford wake-up commands 核心功能场景化免唤醒命令 Wake-up command is not mandatory to activate for key functions |  |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0051 | C# Intelligent Digital Assitant 智能数字助手 | 4# Life Services 生活服务 | 语音查询服务 | 语音查询服务（资讯/百科/游戏，笑话）-天气、股票、汇率、火车票、机票、航班信息、限号、百度百科、成语接龙、笑话等。 世界之最 Most ** of the world 支持查询世界上之最、中国之最 Support searching the most ** of the world/China 人物百科 Celebrity encyclopedia 支持娱乐明星、体育明星、历史人物等名人的重要信息（身高、体重、家乡、星座）、婚姻状况、亲属（如老婆、老公、女朋友）Support searching celebrity info 地理 Geography "支持查询某物的面积、长度、高度、食物的热量 Support searching something's dimension & food calorie" 天气 Weather "支持国内2560个城市和海外主要城市的6天内天气查询和当日生活指数查询。 Support weather info & related index search of 2560 domestic cities & main oversea cities." 彩票 Lotery 支持查询博彩类开奖结果(大乐透、七星彩、体彩、排列五、福彩、双色球）Support searching loteray info 日历 Calendar 支持查询节假日、节气时间 Support searching holiday date & China traditional solarterm dates 机票/航班信息 air ticket/flight info """支持查询机票/航班信息 support air ticket/flight info searching""" 汇率 Exchange rate "支持世界主要货币之间的兑换换算。 Support mainstreen currency exchange calculation" 火车票 train "支持查询火车票 support train ticket searching" 热映电影 Popular movie 支持电影实体查找（包括电影名、演员、类型等）Support movie searching 电影票/外卖 movie ticket/take away "支持购买电影票/外卖 support paying moive ticket" 电视剧基础属性 Episodes 支持查询电视剧的播出时间、电影的上映时间 Episodes'airtime 笑话 Jokes 支持文字笑话的询问与播报 Support reading literal jokes 股价 Share price 支持美股、港股、沪深股市的公司市值股价和大盘指数查询 Support US/HK/Shanghai/Shenzhen share price & stock index searching 诗词 Poem "支持唐诗宋词的完整篇章或上下句、作者、出处查询。 Support China acient poem searching & related info, i.e. writer" 闲聊 Chat 自由聊天，每句话都能有回应 Responding to every voice command/message 限行 Traffic control info - License plate restriction 查询6个主要限行城市（北京、杭州、兰州、成都、天津、武汉）的限行信息。 Support searching 6 main cities which implemented traffic control rules |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0068 | C# Intelligent Digital Assitant 智能数字助手 | 6# Voice Command - IVI System Control 系统控制 | 音乐、收音机、在线电台、新闻、有声、爱奇艺、随心拍 等 | 本地媒体 收音机 打开 打开/播放/我想听收音机 切换到/收听/请打开/听/我要听… 关闭 关闭/退出收音机 停止/关掉… 把…关掉/关上 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 调台/搜索 上一台/下一台/上一个台/上一个频道/上一个频点/前一个/下一个台/后一个/ 播放/我要听104.3/FM88.8/AM538.0中国之声 扫描/更新/刷新/搜索电台 电台收藏 收藏 取消收藏 "USB音乐 （双开，声源定位）" 打开 打开/播放/我想听USB音乐/U盘音乐 "打开/播放/我想听主驾USB音乐/U盘音乐 打开/播放/我想听副驾USB音乐/U盘音乐" 关闭 关闭/退出USB音乐/U盘音乐 "关闭/退出主驾USB音乐/U盘音乐 关闭/退出副驾USB音乐/U盘音乐" 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 模式切换 随机播放/单曲循环/顺序播放/歌曲列表循环/列表循环音乐 "蓝牙音乐 " 打开 打开/播放/我想听蓝牙音乐 关闭 关闭/退出蓝牙音乐 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 在线媒体 "在线电台 " 打开 打开/播放/我想听/我要听（在线电台/在线收音机） 关闭 关闭/退出（在线电台/在线收音机） 播放控制 暂停 播放 调台/搜索 上一台/下一台 播放/我要听中国之声 切换播放路径 播放 切换 电台收藏 收藏 取消收藏 泛需求 打开随心听 打开（播放/我想听）在线音乐/随心听 "打开主驾（在线音乐/随心听） 播放主驾（在线音乐/随心听） 我想听主驾（在线音乐/随心听） 打开副驾（在线音乐/随心听） 播放副驾（在线音乐/随心听） 我想听副驾（在线音乐/随心听） " 关闭随心听 "关闭（在线音乐/随心听） 退出（在线音乐/随心听）" "关闭主驾（在线音乐/随心听） 退出主驾（在线音乐/随心听） 关闭副驾（在线音乐/随心听） 退出副驾（在线音乐/随心听）" "QQ音乐 （双开，声源定位）" 打开 （打开/播放/我想听）QQ音乐 "（打开/播放/我想听）主驾QQ音乐 （打开/播放/我想听）副驾QQ音乐" 关闭 "关闭（QQ音乐/在线音乐） 退出（QQ音乐/在线音乐）" "关闭主驾QQ音乐 退出主驾QQ音乐 关闭副驾QQ音乐 退出副驾QQ音乐" 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 模式切换 随机播放/单曲循环/顺序播放/歌曲列表循环/列表循环音乐 音乐点播 听歌意图，例：我想听歌/随便来首歌 听听音乐/放个歌/来点音乐/给我放首歌/有音乐么 播放/我想听/放一首/我要听/放/听/来首+ 歌曲名称 播放/我想听/放一首/我要听/放/听/来首+ 歌手名称的歌 播放/我想听/放一首/我要听/放/听/来首+歌手名称的歌曲名称 播放/我想听+歌曲类型的歌 歌曲收藏 收藏/加入收藏/帮我收藏 取消收藏/给我取消收藏 播放歌曲信息查询 歌手名称：这首歌是谁唱的 歌曲名称：现在播放的是什么歌 专辑：这首歌是什么专辑 泛问答（现在放的是什么） "有声 （双开，声源定位）" 打开 "打开（有声/有声读物） 播放（有声/有声读物） 我想听（有声/有声读物）" "打开主驾（有声/有声读物） 打开副驾（有声/有声读物） 播放主驾（有声/有声读物） 播放副驾有声/有声读物 我想听主驾（有声/有声读物） 我想听副驾（有声/有声读物）" 关闭 "关闭（有声/有声读物） 退出（有声/有声读物）" "关闭主驾（有声/有声读物） 退出主驾（有声/有声读物） 关闭副驾（有声/有声读物） 退出副驾（有声/有声读物）" 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 模式切换 随机播放/顺序播放/歌曲列表循环/列表循环音乐 有声点播 播放/我想听+ 有声名称 播放/我想听+有声类型（小说/有声书/相声/脱口秀/评书/故事/公开课等） 播放/我想听/我要听/播一段+专辑名 播放/我想听/我要听/播一段+主讲人的节目/作品 播放/我想听/我要听/播一段+主讲人的+分类 播放/我想听/我要听/播一段+专辑名的+节目名 播放/我想听/我要听/播一段+主讲人+专辑名 有声收藏 收藏/加入收藏/帮我收藏 取消收藏/给我取消收藏 播放有声信息查询 有声名称：现在播放的是什么节目 作者名称：这个节目是谁播讲的 专辑：这个节目是哪张专辑里的 泛问答（现在放的是什么） "新闻 （双开，声源定位）" 打开 打开/播放/我想听新闻 "（打开/播放/我想听）主驾新闻 （打开/播放/我想听）副驾新闻" 关闭 关闭/退出新闻 关闭/退出主/副驾新闻 播放控制 别播了/音乐暂停/别放了/暂停/暂停音乐/播放暂停 继续播放/继续放/接着放/开始播放/播放/继续播/接着播 重新播放/从头开始播/重播/再听一遍/再放一遍 上一曲/上一个/播放上一个/前一个/上一首/播上一首 下一曲/下一个/跳过这首歌/切歌/换一首/下一个/播放下一首/切换下一首 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 模式切换 顺序播放/歌曲列表循环/列表循环音乐 新闻搜索 播放意图，例：今日新闻/有什么头条新闻 播放/我想听/今天的/最近的+新闻名称的新闻 播放/我想听/今天的/最近的+地域的新闻 播放/我想听/今天的/最近的/搜索+人物/事件的新闻 "爱奇艺 (支持可见即可说)" 打开 打开/我想看爱奇艺/随心看 关闭 关闭/退出爱奇艺/随心看 播放控制 暂停/播放 上一集/下一集 快进/快进到1分10秒/快进10s 快退/快退到1分10秒/快退10s 影片搜索 播放/我想看+ 视频名称 播放/我想看+影视类别 可见即可说 随心拍 打开/关闭随心拍 打开随心拍 关闭随心拍 拍照控制 拍照 视频控制 录制视频 |  |  | Joseph Lu | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0070 | C# Intelligent Digital Assitant 智能数字助手 | 5# VPA 形象化语音助手 | 语音助手VPA 1.0 (形象化的语音助手） | Avatar Only. 语音助手形象化。 |  |  |  | ECDx | Suo, Feifei (F.) <FSUO@ford.com> | Yang, Chris (K.) <kyang21@ford.com> |  | EC Lead | Ford China | SW | N | N | N | N | N | N | N
SYNC+_0082 | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 车路协同 V2I Lite (Beta) | 纯软件的基于IVI 的China Local Solution including 4 features •Traffic Light Information(TLI) •Green Light Notification (GLN) •Green Light Optimal Speed Advisory(GLOSA) •Red Light Violation Warning(RLVW) |  |  |  | ECDx | Li, Yifei (Y.) <nli26@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford | HW-CGEA1.3C | Y | Y | Y | Y | N | N | N
SYNC+_0103 | E# Access & Authorization 车钥匙 | 1# Keyfob 传统车钥匙 | 我的钥匙MyKey | XCL decision to stop this implementation from P702/MY21U554MCA Settings-Clear my keys Settings-Create my key Settings-My key status Settings-Volume limiter |  |  |  | EESE |  |  |  | EESE/IVI-Distributed System | Ford Global | SW | N | N | N | N | N | N | N
SYNC+_0106 | E# Access & Authorization 车钥匙 | 2# Phone As A Key (PaaK) 手机钥匙 | 手机钥匙Phone as key(PaaK) | Regular PAAK. 4 doors 天线1+ 6 或1+x， Backup Startup Passcode (BSP) 选配，refer to feature owner cascade。 + EV PaaK CNECDMPORT-225 | F001670 |  |  | ECDx | Chen, Kiefer (Y.) <ychen290@ford.com> | Ji, Jerry (Y.) <yji9@ford.com> |  | EC Lead | Ford Global | HW | Y | N | Y | N | N | N | N
SYNC+_0108 | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | 人脸识别账户登录Face ID - Driver (Registration, Recognition, Account, Personalization, Welcome) | Stand alone Facial ID camera, not DSMC. |  |  |  | Tech Planning | Jia, Elaine (T.) <tjia2@ford.com>; Wang, Johnny (J.) <jwang308@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI(Diven) | Baidu/Ford China | HW-IR Camera | Y | Y | TBD | TBD | N | N | N
SYNC+_0109 | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | IVI 驾驶员状态监控和报警 IVI Driver Status Monitor & Alert (Fatigue, Distraction, Dangers Behaviour) | Lead by CD542. Base on IVI IR Camera. 有相应的声音和IVI Display提醒 跟DAT 域的DSMC 不同。 |  |  |  | Tech Planning | Jia, Elaine (T.) <tjia2@ford.com>; Wang, Johnny (J.) <jwang308@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI(Diven) | FordChina/Baidu | HW-IR Camera (IVI域) | Y | N | N | Y | N | N | N
SYNC+_0110 | B# Multimedia 多媒体 | 3# Music 音乐 | 舱内娱乐Cabin On-live 1.0 | First deploy to CDX707 with in car KTV and in car passenger DLNA |  |  |  | ECDx | Yu, Yaxing (Y.) <yyu55@ford.com> | fan, Henry (H.) <hfan11@ford.com> | Meng, Sheena (M.) <MXIA10@ford.com> | EC Lead | Ford Global | HW | Y-1st | Y-1st | Y- Study | Y | N | N | N
SYNC+_0112 | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程解锁/启动 Remote Door Lock/Engine Start | Remote Door unlock/start engine. 空调/座椅/方向盘加热 也会自动上一次熄火前的设置 | F003415, F003370 |  |  | ECDx | Lin, Shawn (X.) <xlin17@ford.com> | Lin, Shawn (X.) <xlin17@ford.com> |  | EC Lead | Ford Global | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0113 | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程鸣笛闪灯 Vehicle Announcement via FordPass | [Shawn] Non IVI seting provides additional Command & Control ability to customer that customer can remotely active the light （转向灯） and horn to locate their vehicle. Lead: CX482PHEV.FordPass have two solutions to meet different program architecture with additional testing cost. Currently planned on Fordpass. Additional LincolnWay UI will be required if need. FordPass远程控制灯光/鸣笛 Remote control lighting/horn.4G 信号 支持。Customer benefit 场景： 找车。 现有的keyfob 蓝牙模块有~40米。 (Lead phase 2: CX482/Lincoln Way (Not Ready) |  |  |  | ECDx | Lin, Shawn (X.) <xlin17@ford.com> | Lin, Shawn (X.) <xlin17@ford.com> |  | EC Lead | Ford Global | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0114 | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程空调控制 Remote Climate Control (RCC) via FordPass/Lincoln Way | CNECDMPORT-344 [Shawn] Need IVI setting Will allow customer’s to select their personal settings for cabin temperature, max defrost and heated/cooled seats. Customer can view the current vehicle cabin temperature and the last HVAC settings through the mobile app. 空调， 通风除霜，座椅加热，油车跟remote start 联动 （~10分钟后， 用户可以选择延时，否则engine stop)。新增项：实时显示，分开各项分开设置。支持FNV2架构。Gasoline and EV。 Lead：CD764. Feasible for programs with FNV2 architecture |  |  |  | ECDx | Lin, Shawn (X.) <xlin17@ford.com> | Lin, Shawn (X.) <xlin17@ford.com> |  | EC Lead | Ford Global | SW -FNV2 | Y | Y | Y | Y | Y | Y | Y
SYNC+_0115 | G# Remote Control 远程控制 | 2# In Cabin Remote Controller (Phone) 座舱内手机遥控器 | 座舱内手机遥控 Project Aspire_Ultimate Remote Control | URC as operate interface to enable My Seat Space, from CDX747,and C/O to U718 Benfit: - Provides a space which a passenger feels in control and can enjoy their time in the vehicle - Provide a centralized way for a passenger to make their space confortable for them without disturbing others in the vehicle - Provide freedom for the driver/1R passenger of being the constant caretaker for the rest of the vehicle - alternative to myseatspace or multi-zone voice control or second row screen which are not in 707's assumption |  |  |  | ECDx | No FO/TL in China | No FO/TL in China |  | EC Lead | Ford Global | TBD | Y-1st | N | N | Y-1st | N | N | N
SYNC+_0116 | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 爱车探索Demo Mode | Including 重温欢迎仪式 Replay Welcome Approach 配置介绍 Features Walkthrough |  |  |  | ECDx | Xiao, Yun (Y.) <yxiao21@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com>;Lee, Grace (G.) <glee51@ford.com> |  | EC Lead | Ford China | SW | Y | Y | Y | Y | Y | N | N
SYNC+_0117 | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 1.5 | 1. Online content update（cloud storage) 支持内容通过云端更新（静默升级，无需OTA, 用户无感知) - Phase 4 全系 planned， phase 3 in progress; 2. 支持全量纸质手册 . 福特车型（5本); 林肯车型（6本); V1.0 只支持Owner's manual 3. 多媒体手册内容 (video形式本地存储， 具备流媒体形式，但目前没有内容对接）。支持后备箱踢脚 (CDX482/483 only)。 需Program/feature owner drive content design. 4. Voice Command open E-manual; Voice search content (20 keywords voice search) |  |  |  | ECDx | Jiang, Wei (W.) <wjiang33@ford.com> | Zhang, Qing (Q.) <qzhang90@ford.com> |  | EC Lead | Ford China | SW | Y | N | N | N | N | N | N
SYNC+_0118 | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 2.0 | 1. AI Voice Search (Inhouse Developped). 云端支持 inhouse MPP 合作开发. POC 开发完成， waiting for approve. | F002370 |  |  | ECDx | Jiang, Wei (W.) <wjiang33@ford.com> | Zhang, Qing (Q.) <qzhang90@ford.com> |  | EC Lead | Ford China | SW | Y-1st | Y-1st | Y | Y | Y | Y | Y
SYNC+_0119 | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 1.0 | Paper "Owners' manual" go digital on IVI. OTA to support any contents updates/changes. |  |  |  | ECDx | Yao, Jiang (J.) <JYAO19@ford.com> | Zhang, Qing (Q.) <qzhang90@ford.com> |  | EC Lead | Ford China | SW | N | N | N | N | N | N | N
SYNC+_0120 | H# Service & Maintenance 车主服务 | 2# Traffic Violation Checking 违章查询 | 违章查询 Query traffic violations (IVI) | Baidu: 用户终端查询是需要收费的。 |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0122 | H# Service & Maintenance 车主服务 | 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | 车辆警示 Vehicle Health Alerts (VHA) | 传统显示再Cluster 上的各种故障报警(40多项), ECG 将信号传统到IVI及Fordpass/Lincoln Way 显示.建议保养时间/保养项目/里程 2021 Q1 手机端上线. |  |  |  | ECDx | Chen, Wei (W.) <WCHEN160@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford Global | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0123 | H# Service & Maintenance 车主服务 | 4# Dealer Service Booking 经销商服务预定 | 保养及在线预约 OSB - Online Service Booking | Dearler Search. /Vehicle Maintenance and the service booking 保养在线预约 OSB-订单查询 order inquiry 保养在线预约 OSB-保养预约 Service booking， time and leave a note for maintenance items 保养在线预约 OSB-建议保养项目 Base on mile display user manual suggested maintenance item when user click on this . |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Ford China | SW | On Hold | On Hold | On Hold | On Hold | On Hold | On Hold | On Hold
SYNC+_0124 | H# Service & Maintenance 车主服务 | 5# User Feedback Channel 用户反馈 | 用户反馈Customer Feedback1.0 | QR code scan and submit via phone. 2021-02: 对于提交反馈的用户， 车机端会有个消息提醒：”感谢你的反馈。“ |  |  | Shang, Qiong (Q.) <qshang@ford.com> | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Ford China | SW | N | N | N | N | N | N | N
SYNC+_0125 | H# Service & Maintenance 车主服务 | 5# User Feedback Channel 用户反馈 | 用户反馈Customer Feedback 2.0 | Improved version.车机上进行语音录入用户反馈。增加手机上的交互xx. target timing 是CX727 第一个OTA cadence |  |  | Shang, Qiong (Q.) <qshang@ford.com> | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0126 | I# Safety & Security 安全 | 1# Emergency Services 紧急救援 | 升级版紧急救援/服务 eCall | CN-CAP Safety (5 stars) driven features. Dedicated TCU, Microphone， Speaker. Automatic trigger condition is the same as current EA design(Oil pump cut off or air bag deploy); leverage current EA call center Yesway(95智驾). CN Regulation on e-call to be expected in 2024 (TBD) | F000997 |  |  | ECDx | Ren, Siyuan (Alex.) <sren6@ford.com> | Ji, Jerry (Y.) <yji9@ford.com> |  | EC Lead | Ford China | HW | Y | Y | Y | Y | TBD | Y | Y
SYNC+_0127 | I# Safety & Security 安全 | 1# Emergency Services 紧急救援 | 紧急救援Emergency Assistance (EA) | 紧急救援，被动触发。 Emergency Assistance will be triggered when airbag pump out or oil pipe line cut off. An emergency call will be placed to China call center (95智驾 by customer's phone connected with Sync+ by bluetooth, and after line open, call center will provide corresponding services per customer's needs. |  |  |  | ECDx | Ren, Siyuan (Alex.) <sren6@ford.com> | Ji, Jerry (Y.) <yji9@ford.com> |  | EC Lead | Ford China | SW | Y | N | N | N | Y | N | N
SYNC+_0128 | I# Safety & Security 安全 | 1# Emergency Services 紧急救援 | 道路救援Road Side Assitance (RSA) | 道路救援， 用户IVI端一键触发(蓝牙电话）（安联） - 拨打道路救援电话，获取道路救援服务 - 入口：车机端"道路救援"应用，其存储着固定的道路救援电话号码 - 通过蓝牙连接的手机拨打道路救援电话 |  |  |  | ECDx | Ren, Siyuan (Alex.) <sren6@ford.com> | Ji, Jerry (Y.) <yji9@ford.com> |  | EC Lead | Ford China | HW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0129 | I# Safety & Security 安全 | 2# Safety Reminder 安全提醒 | 儿童座椅报警Child Restraint System (CRS) - ( e.g BT Child seat 蓝牙座椅) | BT Child seat 蓝牙座椅, 蓝牙通信反馈儿童座椅是否正确安装了。CNCAP 安全需求，车载需要支持与CRS 实现通信功能. 通信的具体形式是蓝牙传输. 目前仅支持环球娃娃品牌下的部分型号. CNCAP 5星要求。 |  |  |  | EESE | Xu, Amy (X.) <xyafei@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI | Ford Global | HW-低功耗蓝牙模块 | Y | Y | Y | Y | TBD | Y | Y
SYNC+_0130 | J# Health & Wellness | 1# Air Quality 空气质量 | 座舱空气质量检测CAQ(Cabin Air Quality) | 后装方案 |  |  |  | EESE |  | 0 |  | EC Lead | TBD | HW | N | N | N | N | N | N | N
SYNC+_0131 | J# Health & Wellness | 1# Air Quality 空气质量 | 智能新风Auto Air Refresh (AAR) G1 | 显示车内PM2.5, 提醒是否内外循环切换 |  |  |  | ECDx | wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Ford Global | HW - AAR Sensor (PM2.5） | N | N | N | N | N | N | N
SYNC+_0132 | J# Health & Wellness | 1# Air Quality 空气质量 | 智能新风Auto Air Refresh (AAR) G2 (Blue Shield) | Blue Shield. 增加了主动干预，自行切换；点火后， 自动打开空调；行驶中， 提醒是否开空调 （不主动干预，因为会引起driver 紧张，安全影响） | F001211 |  |  | ECDx | Shi, Stella (J.) <jshi32@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford China | HW - AAR Sensor (PM2.5） | Y | Y | Y | Y | Y | Y | Y
SYNC+_0133 | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 数字香氛 Digital scent 1.0 | 4 scents |  |  |  | EESE | Zhang, Xiaojing (X.) <XZHAN247@ford.com> | Zhang, Qing (Q.) <qzhang90@ford.com> |  | PMT5 | Ford China | HW | N | N | N | N | N | N | N
SYNC+_0134 | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 数字香氛 Digital Scent 2.0 (New Scents) | New scents can work with imersive experience, e.g rejuvenations for customer heath & wellness, as well as Purify. |  |  |  | EESE | Wang, Yan Jing (Y.) <ywang458@ford.com> - FO ; Chen, Minghui (M.) <MCHEN122@ford.com>- 软件相关 | Zhang, Michael (X.) <xzhang66@ford.com> |  | BI | Ford China | HW | Y-1st | Y-1st | N | Y | N | Y | N
SYNC+_0135 | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 活力恢复 Project Aspire_Rejuvenation | Project Aspire: Relax is a feature/capability that allows to provide a user specific experience to induce calming or relaxing experience. The feature is a combination of effects in a vehicle to including- Digital scent- Advanced welcome with complimentary light and sound scheme in various parts of vehicle such as ambient lighting , Horizon display , center stack etc- Relax moment can be initiated and controlled via HMI. This feature also uses FordPass to download calm app, install, set up calm experience (ambient color, cabin temo, length of experience, other HVAC controls), save and then start calm experience with chatbot and FB messenger. 相比Relax mode, 新增空调，EM register, |  |  |  | ECDx | Zhu, Jiawei (J.) <JZHU101@ford.com> | Mao, Eric (Xin) <xmao6@ford.com> |  | EESE | Ford Global | HW-FNV3, DSM5 (Positional) and many others | Y-1st | OTA | N | Y-1st | N | N | N
SYNC+_0136 | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 舒享时分Relax/自由秘境At Ease | Pre-Global Rejuvenation. China Local solution. 林肯车型正式名称 - 舒享时分Relax/ 车型f福特正式名称 - 自由秘境At Ease; 目前项目主题都有不一样的地方（Room 一样的差别较小） |  |  | Zheng Sun, (764- Liu, Zichao) | ECDx | Zhang, Xiaojing (X.) <XZHAN247@ford.com> | 0 |  | EC Lead | Ford China | HW-DSM | Y | Y | Y | N | N | Y | Y
SYNC+_0137 | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 个人时光 Smart Scene - Personal Enjoyment | Personal Enjoyment 个人时光 Lead: CDx764 CD764 Implantation -Buddle setting to provide wonderful movie watch experiences in the copilot seat. Target Parking experience when customer watch movie for more than 30 minutes. Drive side is not considered in this design as long movie watching experience is not encouraged as for bad HMI or blocked sight. Buddle setting including Digital Scent, lighting , massage seat setting, enhanced co-pilot seat audio effect. Driver are expected to move to co-pilot seat to use this feature. Research shows that this movement won’t be a boundary as long as the experience is good. Moving forward, more enjoyment like game and other leisure enjoyment will be add. Developpment in progress. Smart Scene is part of phase 4 discussion with Desay. Product/Feature owner to provide details. Feature OTA Capability depends on Vehicle HW and display set e.g whether screen covers co-pilot seat). |  |  | Zheng Sun, (764- Liu, Zichao) | ECDx | Shi, Stella (J.) <jshi32@ford.com> | Zhang, Qing (Q.) <qzhang90@ford.com> | Meng, Sheena (M.) <MXIA10@ford.com> | EC Lead | Ford China | HW | Y | Y | Y | Y | N | Y | Y
SYNC+_0138 | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 车机相册 IVI Picture Gallery | 支持车机本地/USB 图片和视频资源浏览/播放。 具体功参考技术文档。可参照现有手机相册的实现 |  |  |  | EESE | Jia, Elaine (T.) <tjia2@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI(Diven) | Ford China | SW | Y | OTA | Y | Y | Y | Y | Y
SYNC+_0139 | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 客人模式Smart Scene - Guest Mode | could be triggered by copilot seat door or seat sensor，or activate by voice command by customer. Guide guest to IVI contents (e.g music) in the meanwhile protect car owners privacy by removing owners' search records. Co-drive mode (lead by Grace lee) is more for onboard a family member or friends. -Challenges: part of the design is to give privacy to driver. requires removal of driver's or other users search records. require baidu implementation. currently dont have Baidu responses. -OTA Feasibility: designed for 27Inch Touch Screen. consider HMI changes for other programs. |  |  | Zheng Sun, (764- Liu, Zichao) | ECDx | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) | Fan, Henry (H.) <hfan11@ford.com> | Meng, Sheena (M.) <MXIA10@ford.com> | EC Lead | Ford China | SW | Y | Y | N | Y | N | Y | Y
SYNC+_0140 | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 智慧指令 Smart Scene - Smart Order | Buddled setting for (CD764 MVP - 4 orders including 客人模式；通勤模式；冬日模式；夏日模式 。根据设定条件,IVI 屏幕主动推荐“智能指令”or activate by voice command. Allow customization on IVI/Fordpass。 - Challenges：1-limited modules in the vehicle is controllable. 2-Not a high priority for Ford global. Therefore setting on FordPass and send to car is not feasible even in 2021 . |  |  | Zheng Sun, (764- Liu, Zichao) | ECDx | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) | Fan, Henry (H.) <hfan11@ford.com> | Meng, Sheena (M.) <MXIA10@ford.com> | EC Lead | Ford China | HW | Y | Y | N | Y | N | Y | Y
SYNC+_0141 | K# Social & Operation 社交及运营服务 | 4# Personal Productivity 工作效率 | 车机日历Project Aspire_Routines / Daily View_IVI Calendar 2.0 | This experience provides capability to Ford / Lincoln user to access personalized calendar or day to day schedule while in the vehicle and different aspects influencing the customers daily life. The Experience covers different aspects such as Integrating into calendar, reminders appointments etc. Integrating into traffic (ETA , Traffic) Integrating into routine destinations or accessing customers locations per calendar Integrating into vehicle data such as Fuel/charge level and ability to predict fueling/charging time in the busy day. This is the day view that margaret has once she hoped in her vehicle. - From Project Aspire User calendar is an enabler to this function. For reference 764 have IVI Calendar (Local Design), need to work with global core team understandingthe global design. |  |  | Liang, Arthur | ECDx | wang, Johnny (J.) <jwang308@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford China | SW | N | N | N | N | N | N | N
SYNC+_0142 | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 电影票预定 Movie Ticket Booking 美团外卖MeiTuanTake-away 鲜花预定Order flower delivery 机票查询 Flight search 火车票查询 Train ticket search 酒店预定 Hotel booking | 资源来自爱奇艺。查看热映电影;选座购票;付款;"鲜花预定（含二维码支付） Order flower delivery" 机票查询 Flight search 火车票查询 Train ticket search 酒店预定 Hotel booking |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0143 | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 福特/林肯金融 Ford Credit | 账务记录 |  |  |  | ECDx | Lu, Chao (C.) <clu42@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford Global | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0145 | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 随心拍Traveling Shooting | Need AR Navigation Camera |  |  |  | Tech Planning/ECDx | Jia, Elaine (T.) <tjia2@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI(Diven) | Ford China | HW | Y | OTA | Y | Y | N | N | N
SYNC+_0151 | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 随心拍Travel Shooting 2.0 Project Aspire_Photos (GPS Created Trip Summary) | Share picutres & trip highlights (ex. Wechat or Facebook story report out). Ideas of things to share: selfie if taken with interior facial camera, personal photos taken during the trip, locations visited/passed, number of miles traveled, etc. |  |  | Liang, Arthur | ECDx | TBD | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE | Ford China | HW | Y-1st | N | N | N | N | N | N
SYNC+_0152 | K# Social & Operation 社交及运营服务 | 3# Entertainment 娱乐 | 时空秘信Surprise/Secret message | customer can schedule supirse message such as "Happy Birthday" |  |  |  | ECDx | Jiang, Wei (W.) <WJIANG33@ford.com> Grace Lee (TBD) | Zhang, Qing (Q.) <qzhang90@ford.com> |  | EC Lead | Ford China | bar: HW to N
SYNC+_0154 | K# Social & Operation 社交及运营服务 | 4# Personal Productivity 工作效率 | 视频会议 Project Aspire_Video Phone Calling / Video Conferencing (Meeting Mode)_CN | Demonstrate a Video call capability using the center stack with a Web application. The Functionality provides a view for Video conferencing in stationary mode. Includes conference experience , voice or audio in call and document viewing and sharing capabilities. These are listed as two items on Project Aspire Master List |  |  | Chen, Eva | ECDx | Temporary Wang, Johnny (J.) <JWANG308@ford.com> | Fan Henry (TBD) |  | EC Lead | 3rd Party App | HW | Y-1st | Y-1st | N | OTA | N | N | N
SYNC+_0155 | K# Social & Operation 社交及运营服务 | 4# Personal Productivity 工作效率 | 车机日历IVI Calendar 1.0 | Generic calendar with Chinese traditional calendar/Holidays/Customer personal Events-Event Management (Add;Edit/Delete). IVI system will remind customer these recorded events on screen with voice broadcaste. Roadmap with more features to be implemented in upcoming phases. |  |  |  | ECDx | Zhang, Xiaojing (X.) <XZHAN247@ford.com> | Zhang, Qing (Q.) <qzhang90@ford.com> |  | Ec Lead | Ford China | SW | N | N | N | N | N | N | TBD
SYNC+_0156 | K# Social & Operation 社交及运营服务 | 5# In Vehicle Gaming 车载游戏 | 舱内娱乐Carbin on live 2.0 | Cabin on live will include in car gaming(3rd party) |  |  | Yu, Yaxing | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | 3rd Party App | SW | Y-1st | OTA | Y-Study | Y-1st | TBD | TBD | TBD
SYNC+_0157 | K# Social & Operation 社交及运营服务 | 6# Marketplace / Apps Anywhere 应用商店 | 车机应用商店Apps Anywhere(SYNC+) | Market Place is a extension of Ford Pass where following options are available for a customer - Chosen experiences such as relax could be purchased and downloaded to the vehicle - Chosen dashboards ( Videos , Static wallpapers) can be purchased and downloaded to the vehicle . Marketplace today is only QSR (Quick Service Retail -coffee, gas, etc). Buying any application purchases is not contained. Apps Anywhere build a foundation to support the application purchases. All on hold |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Ford Global | SW | Y-1st | OTA | Y-Study | Y-Study | Y-Study | Y-Study | Y-Study
SYNC+_0158 | K# Social & Operation 社交及运营服务 | 7# Web Browser & Browser Based Application 浏览器和网页版应用 | 车载游览器/浏览器应用Project Aspire_Streaming Web / Applications | Previous name is 车载游览器/浏览器应用Project Aspire_Streaming Web / Applications IQIYI is the assumption (Carryover Feature) The feature discribed below from project aspire is optional Using Chromium with QT the team integrated the following websites in to the ASPIRE experience. Each web application has a icon in the center stack that starts in the center stack and then can be casted to the horizon display. The user can scroll, pan select, play, pause, etc. just as they can on any website. |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | 3rd Party App | bar: HW to N
SYNC+_0159 | Q# Seamless Interface | 8# Wallpaper 墙纸 | 壁纸 Project Aspire_Dash Backgrounds (Dual 23.6+11.1/or 27") | like your wallpaper on your phone or PC. The customer can personalize their dashboard with images, videos and sound. Content can be placed on top of the dashboard like on your PC and phone wallpaper. A dashboard covers the entire horizon screen. Project Aspire planed wallpaper/background including Luxury/Doggy dash/Dolphin/Live aquarium/Bloom/Comb/Dots/Houston Skyline/Kids photos/New York Aerial |  |  |  | HMI? | HMI Ye, Rou (R.) <RYE1@ford.com> | Zhu, Julia (L.) <LZHU68@ford.com> |  | HMI | Ford Global | SW | Y-1st | Y-1st | N | Y | N | Y | Y
SYNC+_0160 | L# IoT(Internet of Things) 车家互联 | 1# Vehicle to Home | 车家互联 ( “小度家居”扫码) Vehicle to Home | 扫描车机端显示二维码关联 “小度家居”， 之后在该平台上面关联的设备都会显示在IVI 界面， 并且支持语音远程启动。“你好福特，打开我家里的扫地机器人”，提前开扫地机器人 Turn on cleaning robert/提前开灯 Turn on lights/提前开空调 Turn on AC(at home) an others in advance |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Baidu | bar: HW to N
SYNC+_0161 | L# IoT(Internet of Things) 车家互联 | 1# Vehicle to Home | 车家互联Project Aspire_General IOT (Smart Home)_CN (UI grahic upgrade -IVI端） |  |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Ford China | SW | Y-1st | Y-1st | Y | Y | Y | Y | Y
SYNC+_0162 | L# IoT(Internet of Things) 车家互联 | 2# Home to Vehicle | 家车互联Project Aspire_General IOT (Smart Home)_CN ( Home to Vehicle) | (UI grahic upgrade + Home to Vehicle Home (XiaoDu Smart Speaker) to vehicle platform |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Baidu | SW | On Hold | On Hold | On Hold | On Hold | On Hold | On Hold | On Hold
SYNC+_0163 | M# Personalization & Account 账号和个人设置 | 1# Account 账号 | 车机端百度账号登陆(By 福特派/lincoln app) Baidu Login |  |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Baidu | bar: HW to N
SYNC+_0164 | M# Personalization & Account 账号和个人设置 | 1# Account 账号 | 车机端福特账号和百度账号同时登陆 (By 福特派 or 林肯之道App） Baidu and Ford/Lincoln Account dual Login | 车机端用户显示二维码， 用户通过福特派/林肯之道APP扫描二维码实现林肯/福特和百度账号互通。车机端会同时登陆福特/林肯账号和百度账号。 目前支持8个。 |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Ford China | bar: HW to N
SYNC+_0165 | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | 个性化设置记忆 Enhanced Memory | Seat settings, HMI Theme setting etc recorded in Enhanced Memory; 座椅，HMI 主题等多个性化设置选项profile记录在Enhanced Memory 里面. Normally support 3 profiles with hard switch. Some program go switchless. |  |  |  | ECDx | Xu, Andy (X.) <XXU71@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford Global | HW - DSM;ABS;DSP, etc. | Y | Y | N | Y | Y | Y | Y
SYNC+_0166 | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | 基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP) | (ProgramMarketing）Personal Portable Profiles - Create a setup wizard on IVI/Fordpass for customer - Passenger account & profile (could be after J1 - OTA upgrade) - Portble profile. If user move to another vehicle , I can migration all my setting preference with this account/profile effortlessly. Project Aspire： Demostrated profile creation in the cnterstack for three driver profiles and one passenger profile. PPP with DSM5 (Driver Seat Module 5) o Configured to support 10 profiles o Configured such that positional settings are portable to/from vehicle o Physical memory switches ARE NOT present, Auto Save is configured Enabled o Anthropometric Translation is supported. PPP without DSM5 o Configured to support 3 profiles only o Positional settings not portable to/from vehicle due to lack of DSM5 o Physical memory switches ARE present, Auto Save configured Disabled o Anthropometric Translation is NOT supported. |  |  |  | ECDx | Xu, Andy (X.) <xxu71@ford.com> | Mao, Eric (Xin) <xmao6@ford.com> |  |  | Ford Global | HW-FNV3, DSM5 (Positional) and many others | Y-1st | OTA | N | Y | TBD | Y | Y
SYNC+_0167 | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | 快捷设置Rocket setup | 4S交车前，工作人员会带着车主进行首次设置的界面 | F002470 |  |  | ECDx | Gu, Xiaosheng (X.) <xgu14@ford.com> | Dai, Gordon (K.) <kdai1@ford.com> |  | EC Lead | Ford Global | SW | Y | N | TBD | N | TBD | N | N
SYNC+_0170 | N# Engagement | 1# Appreciation | 车辆迎宾模式 Lincoln Embrace / Ford Welcome &Farewell | 福特品牌叫做 welcome & Farewell. 林肯品牌叫做Lincoln Embrace. Coorindated exterior/interior lights and IVI display to create welcome/farewell experiences. Might slight varies on programs as per HW assumption differences The feature is intended to be able to either "Welcome" or bid "Farewell" to the Driver based off how he/she interacts with the vehicle. The manner in which the vehicle shall interact with the Driver is by controlling the Exterior Lights, Interior Lights, or Vehicle Displays. |  |  |  | EESE | Bella Wu --> Chen, Huizhen (H.) <HCHEN188@ford.com> | Mao, Eric (Xin) <xmao6@ford.com> |  | EESE/IVI-Distributed System | Ford Global | bar: SW to N
SYNC+_0171 | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 智慧停车 Smart Parking | -查看实时车位；-搜索附近的停车场；-停车场付费（含二维码支付） |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Baidu | bar: SW to N
SYNC+_0172 | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 小额免密支付Seamless Payment | 百度带进来的部分生态，电影票，酒店，喜马拉雅 （不含美团外卖） 可以支持免密支付。 小额（单次不超过200CNY) 免密支付 （二维码扫描， 支付宝账号绑定。免密支付不支持微信付款） |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Baidu | bar: SW to N
SYNC+_0173 | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 聚合支付 Aggregate payment +百度-我的钱包 Baidu Wallet | 我的钱包 支付设置 我的钱包 聚合收银台 我的钱包 账单 我的钱包 订单中心 order center； |  |  |  | ECDx | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Baidu | bar: SW to N
SYNC+_0175 | P# Messaging & Alerts 消息和提醒 | 1# Message Center | 消息&消息中心 notification & notification center | Ford/Baidu both have the capability to push message. Phase 1- 30 text/Phase 4- H5,and more. Different "消息： - 消息展示方式：消息体、消息中心、状态栏的消息状态提醒 - 样式定义：消息体、状态提醒的样式 - 消息展示规则、优先级与冲突机制处理 消息中心： - 各种消息的接收、存储、查看" |  |  |  | EESE | Wang, Johnny (J.) <jwang308@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | EC Lead | Ford China/Baidu | bar: SW to N
SYNC+_0192 | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 联合驾趣 Co-Driver | 副驾区域显示车辆/行驶状态/可以发起POI 搜索， 设置导航路线. Lead CD542 27'L touch screen |  |  |  | HMI? | Li, Qiyang (Q.) <QLI111@ford.com> | Lee, Grace (G.) <glee51@ford.com> |  |  | Ford China | SW | Y | N | N | N | N | Y | Y
SYNC+_0194 | Q# Seamless Interface | 3# Welcome/Farewell Animation | 开机/关机动画 IVI Display Welcome & Farewelll Animation (Display Visual Elements) | 目前分为Ford/Lincoln/Muatang BEV (CX727C) |  |  |  | HMI? | Xiao, Yun (Y.) <yxiao21@ford.com> | Lee, Grace (G.) <glee51@ford.com> |  | HMI | Ford Global | bar: SW to N
SYNC+_0196 | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 电车实时车况界面 IOD Information On Demand/Display | 常规cluster 上面显示的信息 (车辆状况，油耗，胎压，里程， 我的驾驶怎么样？等等）输出至IVI界面，利用IVI Display 大屏的优势做了更直观的见面显示和相应的人机交互（例如下拉菜单）等更新。 Lead:CDX727 |  |  |  | HMI? |  | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE/IVI(Diven) | Ford Global | SW | Y | N | N | Y | N | N | N
SYNC+_0203 | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 27寸主副驾屏幕区域交互模式 27" HMI 3 Modes 独自 (Solo)；合作驾驶 （Co-pilot)；独立（individual) Provide Enhaned Passenger Experience. | 独占 (Solo)；合作驾驶 （Co-pilot)；分屏（individual） |  |  |  | HMI? | HMI Liu, Luisa (Fan.) <fliu43@ford.com> | Zhu, Julia (L.) <LZHU68@ford.com> |  | EESE/IVI(Forrest) | Ford China | SW | Y | N | N | N | N | Y | Y
SYNC+_0204 | Q# Seamless Interface | 4# HMI Theme | 精简（屏幕）模式 Calm Screen | 精简屏幕 - 提供预置背景图片供用户选择 |  |  |  | HMI? | HMI Ye, Rou (R.) <RYE1@ford.com> | Zhu, Julia (L.) <LZHU68@ford.com> |  | HMI | Ford Global | bar: SW to N
SYNC+_0205 | Q# Seamless Interface | 4# HMI Theme | 多界面主题Multi-Theme | 3套主题每个主题都有白天/夜晚模式 |  |  |  | HMI? | Xiao, Yun (Y.) <yxiao21@ford.com> | Lee, Grace (G.) <glee51@ford.com> |  | HMI | Ford Global | bar: SW to N
SYNC+_0206 | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 界面个性化设置，和屏与屏之间内容分发HMI Screen Mirroring/Casting + HMI Personalization （再launcher，允许用户自定义）For Dual 23.6+11.1 | 从11.1 touch screen 投射到pano屏幕的不同区域 |  |  |  | HMI? | HMI Liu, Luisa (Fan.) <fliu43@ford.com> | Zhu, Julia (L.) <LZHU68@ford.com> |  | HMI/EESE | Ford Global | HW | Y-1st | Y-1st | N | Y | N | N | N
SYNC+_0207 | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | HUD信息显示EESE/IVI info showed in HUD | CAN互动，消息协议由Ford定义。 导航，里程，多媒体，电话等信息在HUD上的显示。 (IVI 提供信号， HUD owner 决定显示信息） 仪表控制导航的功能：同步目的地收藏，设置目的地途经点Cluster control EESE/IVI Navigation。 来电号码及名称显示，接听，挂电话 incoming caller ID display，answer call， hang-up call 广播，专辑信息、歌名、歌手 Album info,song & singer and Radio 导航服务，转向、ETA等信息 turn lane,radar detector & ETA |  |  |  | HMI? | Chen, James (J.) <jchen303@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE/IVI | Ford Global | SW | Y | N | Y | N | N | Y | Y
SYNC+_0208 | R# EV Features 新能源汽车功能 | 1# Charging | BEV Unique Charging - FB4 | DC Charging 80% SoC EV App Experience CNECDMPORT-330 FB4 Carry over Charging station Finder Pay for Charging Smart Wall Box Wallbox Installation |  |  | Gao, Richard | ECDX | Peng, Ivan (F.) <FPENG6@ford.com> | Ji, Jerry (Y.) <YJI9@ford.com> |  | EC Lead | Ford Global | SW | Y | N | N | Y | N | N | N
SYNC+_0209 | R# EV Features 新能源汽车功能 | 1# Charging | 充电接口灯设置Charge Port Light Settings | On：Illuminates when plugging in，opening doors， pressing the unlock button on your remote and while charging. Off：Does not illuminate. Limited：Illuminates only when plugging in，opening doors，or pressing the unlock button on your remote. CD391PHEV 有三个选项 : “ on, off & Limited” U6xx只有两个选项“on，off” |  |  |  | EESE | Wu, Dean (D.) <dwu44@ford.com> | Ma, Hao (H.) <hma12@ford.com> |  | EPE | Ford Global | SW | Y | N | N | Y | N | N | N
SYNC+_0210 | R# EV Features 新能源汽车功能 | 3# EV Powertrain Related | 动力流动画显示Power Flow | Power Flow |  |  |  | EESE | HMI Liu, Luisa (Fan.) <fliu43@ford.com> | Ma, Hao (H.) <hma12@ford.com> |  | EPE | Ford Global | SW | Y | Y | N | N | N | N | N
SYNC+_0221 | S# 系统升级 | 1# CAN 升级 | CAN 升级 |  |  |  |  | EESE | Wang, Fin (X.Y.) <xwang65@ford.com> | Wu WenZhong, Forrest (W.) <wwu28@ford.com> |  | EESE | Ford Global | bar: SW to N
SYNC+_0222 | S# 系统升级 | 2# OTA | IVI空中升级SYNC+ OTA | SYNC+ OTA only. Housed under MMOTA from Phase 4 |  |  |  | ECDx | Pan, Yuan (Y.) <ypan23@ford.com> | Pan, Yuan (Y.) <ypan23@ford.com> |  | EC Lead | Ford Global | bar: SW to N
SYNC+_0223 | S# 系统升级 | 2# OTA | 多模块空中升级 Multi Module OTA (MMOTA) (including: USB Update for TCU and ECG; IVI VMCU, CCPU...) | Multi Module including sync+ |  |  |  | ECDx | Pan, Yuan (Y.) <ypan23@ford.com> | Pan, Yuan (Y.) <ypan23@ford.com> |  | EC Lead | Ford Global | bar: SW to N
SYNC+_0228 | B# Multimedia 多媒体 | 3# Music 音乐 | MySeatSpace | The vision of MySeatSpace is to give customers an isolated immersive audio experience, enabling each occupant to listen to their own audio without disturbing others in the vehicle. This feature further enables in-car communication, private phone calls, media stream sharing and audio enhancements |  |  |  | Tech Planning | TBD | TBD |  |  | Ford Global | HW | Y-1st | N | N | Y-1st | N | N | N
SYNC+_0229 | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | Video Interface Throughout Cabin (Rear Seat Monitor, w/ expanded request: allow 2R see 1R) | Driver can see the rear row situation on the screen by leveraging full cabin camera, to ease the worry on taking care of kid. (in-cabin baby monitoring) Kid(s) can see driver via 2nd row display and communicate w/ their parent, to avoid unsafe actions. (via 2nd row screen) |  |  |  | TBD/Tech Planning if camera related | TBD | TBD |  |  |  | HW | Y-1st | N | N | OTA | Y | N | N
SYNC+_0231 | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | Mobile Device Viewer | C/O global content Remote 360 view (exterior + full cabin camera) |  |  |  | ECDx | ideation, no yet FO assign | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford Global | HW | Y-1st | N | N | Y-1st | Y | N | N
SYNC+_0232 | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | Night Vision | from 747 prioritized global OTA concepts Act as a guardian by providing a sense of safety and security in dark areas by highlighting animals, pedestrians and objects in the field of view when the customer is away from or inside their vehicle |  |  |  | Tech Planning | TBD | TBD |  |  |  | HW | Y-1st | N | N | Y-1st | N | N | N
SYNC+_0234 | R# EV Features 新能源汽车功能 | 4# Dealer Service Booking 经销商服务预定 | Valet Charging | - Valet Mode - Auto authorization (Preliminary access to vehicle) - Remote tracking of valet charging status - Remote monitoring of cabin |  |  | Gao, Richard | ECDx | Peng, Ivan (F.) <FPENG6@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | HW | Y-1st | N | N | Y-1st | N | N | N
SYNC+_0239 | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 最新版领先市场的地图导航能力 Leading Connected Map/Navi | 参照持续更新的Baidu Mainline 内容。Baseline 参照 Baidu Mainline 2020-11-30 版本feature 清单，同时应包含 落地前供应商能提供的最新版 |  |  |  | ECDx | Yao, Tristan (Lan) <LYAO17@ford.com> | Xu, Roger (.) <pxu15@ford.com> |  | EESE | Ford China | SW | Y-1st | Y-1st | Y | Y | Y | Y | Y
SYNC+_0240 | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | 多模交互 Image recognition - Multi-Mode (Hand Gusture / Head / Emotion) | 基于手势(hand guesture)，点头/摇头（head), 笔嘘-多媒体静音， 收藏，返回，屏幕左右滑动等作为指令识别。 具体逻辑见feature Document |  |  |  | Tech Planning | Jia, Elaine (T.) <tjia2@ford.com>; Wang, Johnny (J.) <jwang308@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE | Ford China/Baidu | HW-IR Camera | Y | N | N | N | N | N | N
SYNC+_0241 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | One-Shot 唤醒词加命令一起处理 | “你好福特， 帮我打开空调” Insead of " 你好福特“”在" "帮我打开空调“ |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | EESE | Baidu | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0247 | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 5G 车路协同 5G V2I | Global V2I: 4 feature offerings including 1-Traffic Light Information(TLI) 2-Green Light Notification (GLN) 3-Green Light Optimal Speed Advisory(GLOSA) 4-Red Light Violation Warning(RLVW). |  |  |  | ECDx | Li, Yifei (Y.) <nli26@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford Global/Ford China | 5G T-Box | Y-1st | Y-1st | N | N | TBD | Y | Y
SYNC+_0248 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 多轮交互/上下文交互 | 支持多轮交互和上下文理解 |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0249 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 取消两字拒识 (降低误识率采取的策略) | 取消两字拒识从phase 4开始：不执行两个字的语音指令，主要体现在可见即可说的语音能力. 针对可以在两个字的指令前增加“打开”或“点击”以执行语音指令，比如界面有“电话”，可说“打开电话”执行可见即可说指令 |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0250 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 语音退出 | 可通过语音“退出”等，暂停语音服务 |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0251 | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | 闲聊 | 没被其它垂类召回 最后才会走到闲聊，闲聊没有固定的策略，是算法模型，通过自己学习网上的聊天，系统自己生成聊天 |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0252 | C# Intelligent Digital Assitant 智能数字助手 | 3# Vehicle Services 车辆服务 | 车辆状态查询 | 胎压、油量、电量、违章 |  |  | SW | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0253 | C# Intelligent Digital Assitant 智能数字助手 | 3# Vehicle Services 车辆服务 | 车主手册 | 车辆电子说明书 |  |  | Jiang Wei | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0254 | C# Intelligent Digital Assitant 智能数字助手 | 3# Vehicle Services 车辆服务 | EV/PHEV 充电功能 | 出发时间控制、充电计划控制、查找充电桩 "phase4： 1、周边搜：语音指令语义解析后根据AK来判断直接从服务端拉数据，还是把语义结果返回给语音客户端，再走地图搜索，在语音POI列表页显示，同时tts播报""为您找到了x个充电的地方，您要去第几个""，后续流程同语音搜索POI导航流程； 2、沿途搜：走目前默认逻辑" " CX482&CX483ICA： 1、周边搜：语音指令语义解析后根据AK来判断直接从服务端拉数据，还是把语义结果返回给语音客户端，再走地图搜索，在语音POI列表页显示，同时tts播报""为您找到了x个充电的地方，您要去第几个""，后续流程同语音搜索POI导航流程； 2、沿途搜：走目前默认逻辑" |  |  |  | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | N | N | Y | N | N | N
SYNC+_0255 | C# Intelligent Digital Assitant 智能数字助手 | 6# Voice Command - IVI System Control 系统控制 | 专业导航 | 导航APP 打开导航/地图 退出导航/地图 继续导航 POI搜索 我要去<POI> 导航到<POI> 周边搜索 附近<POI> 附近的<POI> 添加途径点 中途去一下··· 半路去一下··· 添加途径点··· 导航+路线偏好 导航到<POI>不走高速 想去<POI>走省钱路线 导航去<POI>高速优先 导航去<POI>少收费 路线切换 推荐路线 高速优先 躲避拥堵 省钱路线 智能推荐 重新规划路线 地图缩放 放大地图 地图放到最大 缩小地图 地图缩到最小 路况开关 打开路况 关闭路况 昼夜模式切换 白天模式 黑夜模式 导航模式切换 查看全程 继续导航 巡航模式开关 打开巡航模式 关闭巡航模式 视图切换 车头朝上 正北模式 2D视图 3D模式 切换视图 路况查询 a点附近 具体道路 a点到b点 收藏当前点 收藏当前定位地点 收藏当前地址 常用地址 我要修改家庭地址 设置公司的地址 导航回家/回公司 我要回家/公司 导航回家/公司 我的位置查询 我的位置 我现在在哪儿 我在哪里 我现在在哪里 路况上报 上报路况 上报事故 上报施工 上报封路 上报事故 上报危险 导航音量 增加导航音量 导航音量小一点 打开导航声音 关闭导航声音 播报模式 打开新手模式 打开专家模式 行程中问答 如何行驶 红绿灯数量 驾车时长 前方限速 前方路况 酒店 电影院 美食 天气 限号 AR与2D map切换 打开AR导航 切换到AR导航 切换到专业导航 |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0256 | C# Intelligent Digital Assitant 智能数字助手 | 6# Voice Command - IVI System Control 系统控制 | AR导航 | AR与2D map切换 打开AR导航 切换到AR导航 切换到专业导航 |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | N | N | N
SYNC+_0257 | C# Intelligent Digital Assitant 智能数字助手 | 6# Voice Command - IVI System Control 系统控制 | 系统控制(IVI模块系统级别） | 界面通用-返回主界面、界面导航、翻页、选择 BT电话-接听、挂断、拨打电话、搜索、更新通讯录、切换设备 音量控制 -增大音量、减小音量、系统静音 系统设置-蓝牙设置、WiFi设置、车载热点设置、更换主题、屏幕控制、精简屏幕控制、显示屏幕控制、驾驶模式控制 账户管理 -人脸识别 Launcher卡片-Launcher上可见即可说的支持说明 |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0258 | C# Intelligent Digital Assitant 智能数字助手 | 4# Life Services 生活服务 | 在线应用 | 在线应用-外卖、酒店、智慧停车场 |  |  | SW | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0259 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 香氛Digital Scent | 打开 打开香氛 关闭 关闭香氛 设置香味 换一种味道 打开第一/二/三种香味 调高浓度 浓度调高（步进为1） 浓度调到具体值（共3个等级，高中低） 调低浓度 浓度调低（步进为1） |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | HW | Y | Y | N | Y | N | Y | N
SYNC+_0260 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | Relax | relax模式调节 "打开森林模式/森林绮镜 进入森林模式/森林绮镜" "打开（大海模式/海屿之恋） 进入（大海模式/海屿之恋）" "打开馥郁暖心 进入馥郁暖心" "打开放松模式 进入放松模式" "关闭（森林模式/森林绮境） 退出（森林模式/森林绮境）" "关闭（大海模式/海屿之恋） 退出（大海模式/海屿之恋）" "关闭馥郁暖心 退出馥郁暖心" "关闭放松模式 退出放松模式" 换一(种/个)+放松模式 |  |  | Lu Joseph | ECDx | Qi, Xuliang <xqi14@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Ford China | HW | Y | Y | Y | N | N | Y | Y
SYNC+_0261 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 2排座椅控制 2nd row Seat Control （7座车） | 3R Vehicle. Having this button to allow driver return the 2R Power seat easily without park & get off & return the seat. Return the 2R seat will give the way to the 3R. - Lead by U611ICA |  |  | Lu Joseph | ECDx | ideation, no yet FO assign |  |  |  | Ford China | HW-2nd row power captain seat | Y | N | N | TBD | N | Y | Y
SYNC+_0262 | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程车门关闭状态显示/查看 Vehicle Locking Status Check; | 功能描述：Fordpass APP 端 显示车门上锁的状态。 硬件依赖/开发量： App 端 UI 变更 + 车端TCU 测试验证. OTA：无需OTA. 手机端更新。 车端需要部署相应的测试工作。 部署现状： Fordpass - Timing：Q2/Q3 2021 -Lead Program: CD727; LincolnWay- Planned for CD764. Currently prioritize for Phase 4 车型。Phase 1-3, 没有技术方面的阻碍，更多的是allocate limited resource for priority programs. |  |  | Tony Liu | ECDx | Lin, Shawn (X.) <xlin17@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead | Ford Global | HW - TCU; | Y | Y | Y | Y | Y | Y | Y
SYNC+_0263 | C# Intelligent Digital Assitant 智能数字助手 | 7# Voice Command - Vehicle Function 语音控制 - 车辆功能 | 驾驶辅助功能问答及播报 DAT - Voice Support | Wave I: FAPA - Lead by CX727/CD542; Wav II: b.Wave II: ADA1.0; Lane Biasing; Exit Warning; 逐步上车。 支持OTA. 具体见FO Spec 文档。 |  |  |  | ECDx | Qi, Xuliang <xqi14@ford.com> | bar: SW to Y
SYNC+_0264 | J# Health & Wellness | 1# Air Quality 空气质量 | EM(Electro-Mechanical) Register | 新增电动马达，可以提供循环扫风模式（上下扫/左右扫）， 崭新的HMI 更加Iintuitive 直观的展现风向，用户可以直接touch 来改变风向；自动循环扫风模式设计有风向变化动效直观展示变化；有预设模式，并记忆用户设置； 支持单个出风口控制， 和驾驶员/副驾乘客侧 多个出风口捆绑设置； - China Lead: 707 会配合语音控制一起打造 |  |  |  | EESE | Wang, Wei (W.) <wwang199@ford.com> (Body) | Chen, Paul (D.) <dchen56@ford.com> |  | BI |  | - HW: ` 崭新硬件：电动马达 （目前除了707 别的项目都未预设） `RCCM: SW Upgrade | Y-1st | Y-1st | N | Y | N | N | N
SYNC+_0265 | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 车路协同 4G V2I Lite (Production) | V2I Lite (Production) For FNV2: 支持更多城市； |  |  |  | ECDx | Li, Yifei (Y.) <nli26@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | HW- FNV2 | Y | N | Y | N | Y | N | Y
SYNC+_0266 | Q# Seamless Interface | 4# Intuitive Vehicle Control | Lancher - 3D Car Model with vehicle controls | This is a replacement of the format of the Launcher Car model with added functionality. Number of vehicle controls / functionalities will be added into this model. Need Kanzi rendering engine. the 3D object can be references in term of the structure for other programs, however it will still be a unique model for each program since each vehicle looks different. |  |  |  | HMI? | HMI Yao, Jeffery (J.) <jyao12@ford.com> - FO assign之前可以联系 |  |  |  |  | HW | Y-1st | Y-1st | TBD | Y | Y | Y | Y
SYNC+_0267 | A# Navigation 地图导航 | 5# AR Navigation AR 导航 | AR HUD | AR Navi on Windshield. May have more to add on later on. |  |  |  | Tech Planning | Zhang, Yong (Y.) <YZHAN468@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  |  |  | HW- AR HUD | Y-1st | N | Y-1st | N | N | N | N
SYNC+_0269 | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 天气 Weather | phase1-4是launcher 一部分。 Phase 5 作为独立App。显示天气， PM2.5 (点击进入AAR 界面）等。目前只显示当天的。资源方：百度. |  |  |  | ECDx | Shi, Stella (J.) <jshi32@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y-1st | Y-1st | Y | Y | Y | Y | Y
SYNC+_0270 | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 1.0 | CNECDMPORT-136，CNECDMPORT-135(CX727) |  |  | Grace Zhang | ECDx | Guo, Edward (T.) <tguo9@ford.com> | Qin, Yvonne (Yiyi) <yqin13@ford.com> |  | EC Lead |  | SW | N | N | N | N | N | N | N
SYNC+_0271 | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 1.5 | CNECDMPORT-343 |  |  | Grace Zhang | ECDx | Guo, Edward (T.) <tguo9@ford.com> | Qin, Yvonne (Yiyi) <yqin13@ford.com> |  | EC Lead |  | SW | N | N | N | N | N | N | N
SYNC+_0272 | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 2.0 | CNECDMPORT-651 |  |  | Grace Zhang | ECDx | Zhou, Calvin (.) <QZHOU31@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y-1st | Y-1st | OTA | Y | OTA | Y | Y
SYNC+_0273 | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | Remote Window Control / Window Status (China) | CNECDMPORT-413 |  |  | Tony Liu | ECDx | Lin, Shawn (X.) <xlin17@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y | Y | Y | Y | TBD | Y | Y
SYNC+_0274 | R# EV Features 新能源汽车功能 | 1# Charging | BEV Unique Charging - FB5 | Trip Planner(APP/IVI) Intelligent Range(CE-DTE) FB4 C/O enhancement(Preferred Charging time/departure time) |  |  | Gao, Richard | ECDX | Peng, Ivan (F.) <FPENG6@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y | N | N | Y | N | N | N
SYNC+_0275 | J# Health & Wellness | Ford_Signature Experience_Welcoming & Empathetic | SenseMyMood 1.0 | CNECDMPORT-347 |  |  | Arthur Liang | ECDx |  |  |  | EC Lead |  | SW | Y-1st | N | TBD | N | N | N | N
SYNC+_0276 | J# Health & Wellness | Ford_Signature Experience_Welcoming & Empathetic | SenseMyMood 2.0 |  |  |  | Arthur Liang | ECDx |  |  |  | EC Lead |  | SW | N | N | N | N | N | N | N
SYNC+_0277 | J# Health & Wellness | Ford_Signature Experience_Welcoming & Empathetic | SenseMyMood 3.0 |  |  |  | Arthur Liang | ECDx |  |  |  | EC Lead |  | SW | N | N | N | N | N | N | N
SYNC+_0278 | J# Health & Wellness | Lincoln_Signature Experience_Embrace | Digital Embrace 1.0 | CNECDMPORT-375 |  |  | Arthur Liang | ECDx | ideation, no yet FO assign | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y-1st | Y | N | Y | N | Y | N
SYNC+_0279 | J# Health & Wellness | Lincoln_Signature Experience_Embrace | Digital Embrace 2.0 |  |  |  | Arthur Liang | ECDx | ideation, no yet FO assign | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | N | N | N | N | N | N | N
SYNC+_0280 | J# Health & Wellness | Lincoln_Signature Experience_Embrace | Digital Embrace 3.0 |  |  |  | Arthur Liang | ECDx | ideation, no yet FO assign | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | N | N | N | N | N | N | N
SYNC+_0281 | J# Health & Wellness | Lincoln_Signature Experience_Rejuvenate | Smart Wellness 1.0 | CNECDMPORT-397 |  |  | Sun Zheng | ECDx | Zhou, Calvin (.) <qzhou31@ford.com> | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y-1st | Y | N | Y | N | Y | N
SYNC+_0282 | J# Health & Wellness | Lincoln_Signature Experience_Rejuvenate | Smart Wellness 2.0 |  |  |  | Sun Zheng | ECDx | ideation, no yet FO assign | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y-1st | N | N | N | N | N | N
SYNC+_0283 | H# Service & Maintenance 车主服务 | 6# Customer Care 客户关怀 | FNOC 1.0 | CNECDMPORT-613 FNOC－First Notification of Care - Weather related |  |  | Wayne Chen | ECDx | ideation, no yet FO assign | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y | Y | Y | Y | Y | Y | Y
SYNC+_0284 | H# Service & Maintenance 车主服务 | 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | FNOS | CNECDMPORT-114 - Oil Life Prediction / China SYNC+ IVI |  |  |  | ECDx | Chen, Wei (W.) <WCHEN160@ford.com> | Lu, Chao (C.) <CLU42@ford.com> |  | EC Lead |  | SW | Y | Y | Y | N | N | Y | Y
SYNC+_0285 | H# Service & Maintenance 车主服务 | 1# Life Service 生活服务 | 加油 - Oil Service | 小桔加油，易加油，团油 |  |  | Johnny Wang | ECDx | ideation, no yet FO assign | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y-1st | Y-1st | Y | Y | Y | Y | Y
SYNC+_0286 | H# Service & Maintenance 车主服务 | 1# Life Service 生活服务 | 洗车 - Car wash | 途虎洗车，盛大，橙牛 |  |  | Johnny Wang | ECDx | ideation, no yet FO assign | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y-1st | Y-1st | Y | Y | Y | Y | Y
SYNC+_0287 | K# Social & Operation 社交及运营服务 | 6# Marketplace / Apps Anywhere 应用商店 | Market Place | CNECDMPORT-189 |  |  | Zhang, Rui | ECDx | ideation, no yet FO assign | Fan, Henry (H.) <hfan11@ford.com> |  | EC Lead |  | SW | Y-1st | Y-1st | Y | Y | Y | Y | Y
SYNC+_0288 | E# Access & Authorization 车钥匙 | 2# Phone As A Key (PaaK) 手机钥匙 | 手机钥匙 BUN Paak | CNECDMPORT-269 BUN Paak apply to FNV3 based programs. |  |  | liu, zichao | ECDx | Chen, Kiefer (Y.) <ychen290@ford.com> | Ji, Jerry (Y.) <yji9@ford.com> |  | EC Lead |  | SW | Y-1st | Y | N | Y | Y | Y | Y
Note on Q78: Ma, Jian (J.): CDX707 Study TIB12
Note on Q84: Ma, Jian (J.): CDX707 Study TIB12