## Read Me
| Feature status | Vendor need quotation or not？ | Comments
Project | Y | √
| Y-Study | √ | 功能确定要上，待需求澄清后，可报价， 1EC,2EC 不包含，3EC包含报价包中（如果3EC 无法提供完成的需求文档，就需要在PA 之后走DCR流程）
| Y-1st | √
| OnHold | ꭓ
| Y-OTA | √ | 1EC,2EC如果需求不明确， 可以不包含，3EC包含报价包中（如果3EC 无法提供完成的需求文档，就需要在PA 之后走DCR流程）
| N | ꭓ

## FIP History
Version | Date | Contact | Change List
V0 | 2020-12-16 | James Chen | Provide the V0 version for vendors to input the SW release version.
V0 | 2020-12-16 | Huang Feng | Add a / b version information
V1.0 | 2020-12-17 | Huang Feng | Huang Feng Update FDL information based on FIP round1 meeting during 10:00-11:45 am.
V1.1 | 2020-12-21 | Zhou Jiajia | Update Pre-DV Req(Column AC) after discussion with Sherry Shang, James Chen.
V1.2 | 2020-12-22 | Huang Feng | Huang Feng Update FDL information based on FIP round3 meeting during 16:00-17:00 pm.
V1.3 | 2021-01-07 | Zhou Jiajia | Zhou Jiajia update FDL information and add comment based on FIP round3 meeting during 10:00-11:30 am.
V1.4 | 2021-01-11 | Huang Feng | Huang Feng Update FDL information based on FIP round5 meeting during 13:30-14:30 pm.
V1.5 | 2021-01-14 | Zhou Jiajia | Zhou Jiajia Update FDL information based on FIP round6 meeting during 10:00-11:00 am.
V1.6 | 2021-01-18 | Zhou Jiajia | Zhou Jiajia Update FDL information and release version(Parts of R10 plan ahead) based on FIP round7 meeting during 13:30-14:30 pm.
V1.7 | 2021-01-21 | Zhou Jiajia | Zhou Jiajia Update FDL information and release version(Parts of R12 plan ahead) based on FIP round8 meeting during 10:00-11:00 am.
V1.8 | 2021-01-25 | Zhou Jiajia | Zhou Jiajia Update FDL information and release version(Parts of R13/TBD plan ahead，Del column AF/AG) based on FIP round9 meeting during 10:00-11:00 am.
V1.9 | 2021-01-30 | Zhou Jiajia | Zhou Jiajia add the sheet“Summary” to show the feature distribution curve.
V2.0 | 2021-02-01 | Huang Feng | Huang Feng Update release version based on FIP V1.9 meeting during 16:00-17:30 pm.
V2.1 | 2021-02-03 | Zhou Jiajia | Update the FDL information for SYNC+_Z0020/SYNC+_Z0023/SYNC+_0128/SYNC+_0020/SYNC+_0068/SYNC+_0117/SYNC+_0118/SYNC+_0135/SYNC+_0136 based on CVPP regular meeting during 14:00-15:00.
V2.2 | 2021-03-09 | Chen Jiazu | Update the following features' FO, SYNC+_0010/SYNC+_0135/SYNC+_0152/SYNC+_0175/SYNC+_0134/SYNC+_0136/SYNC+_0145/SYNC+_0170/SYNC+_0194/SYNC+_0204/SYNC+_0205/SYNC+_0183/SYNC+_0159/SYNC+_0166/SYNC+_0203/SYNC+_0184/SYNC+_0206/SYNC+_0226/SYNC+_0240/SYNC+_Z0100/SYNC+_Z0101/SYNC+_Z0204/SYNC+_Z0059/SYNC+_Z0126/SYNC+_Z0002/SYNC+_Z0199/SYNC+_Z0007/SYNC+_Z0111/SYNC+_Z0017/SYNC+_0004/SYNC+_0008/SYNC+_0009/SYNC+_0016/SYNC+_0082/SYNC+_0247/SYNC+_Z0227/SYNC+_0120/SYNC+_0124/SYNC+_0125/SYNC+_0123/SYNC+_0131/SYNC+_0142/SYNC+_0141/SYNC+_0143/SYNC+_0149/SYNC+_0158/SYNC+_0160/SYNC+_0161/SYNC+_0162/SYNC+_0163/SYNC+_0164/SYNC+_0122/SYNC+_0171/SYNC+_0172/SYNC+_0173/SYNC+_0132/SYNC+_0165/SYNC+_0231/SYNC+_0234/SYNC+_0236/SYNC+_0238/SYNC+_0223/SYNC+_Z0128/SYNC+_Z0033/SYNC+_Z0038/SYNC+_Z0155/SYNC+_Z0020/SYNC+_Z0024/SYNC+_Z0023/SYNC+_Z0030/SYNC+_Z0041/SYNC+_Z0032
V2.3 | 2021-03-29 | Zhou Jiajia | Add column V/W/X for SW release version and plan Update FDL for "SYNC+_0159","SYNC+_0070"(Change from inhouse to Core service),"SYNC+_0077"(Change from inhouse to YFVE) Update comment for "SYNC+_0154","SYNC+_0156"
V2.4 | 2021-03-21 | Chen Jiazu | Update with 0324 Master Feature List. Update Porduct Suite: SYNC+_Z0227,SYNC+_Z0229,SYNC+_Z0230,SYNC+_Z0231,SYNC+_Z0232,SYNC+_Z0277,SYNC+_Z0278,SYNC+_Z0279,SYNC+_Z0280,SYNC+_Z0281,SYNC+_0223,SYNC+_0221,SYNC+_0222 Update Feature Group: SYNC+_0025，SYNC+_0027，SYNC+_0028，SYNC+_0029，SYNC+_0030，SYNC+_0032，SYNC+_0031，SYNC+_0241，SYNC+_0034，SYNC+_0035，SYNC+_0036，SYNC+_0037，SYNC+_0039，SYNC+_0040，SYNC+_0041，SYNC+_0042，SYNC+_0047，SYNC+_0048，SYNC+_0050，SYNC+_0049，SYNC+_0068，SYNC+_0070，SYNC+_0051，SYNC+_0074，SYNC+_0112，SYNC+_0141，SYNC+_0113，SYNC+_0114，SYNC+_0204，SYNC+_0154，SYNC+_0238，SYNC+_0115，SYNC+_0223，SYNC+_0221，SYNC+_0222，SYNC+_0227 Update Feature Name: SYNC+_0025，SYNC+_0028，SYNC+_0030，SYNC+_0032，SYNC+_0241，SYNC+_0034，SYNC+_0042，SYNC+_0047，SYNC+_0048，SYNC+_0050，SYNC+_0049，SYNC+_0068，SYNC+_0070，SYNC+_0082，SYNC+_0051，SYNC+_0095，SYNC+_0101，SYNC+_0098，SYNC+_0074，SYNC+_0110，SYNC+_0117，SYNC+_0118，SYNC+_0112，SYNC+_0141，SYNC+_0152，SYNC+_0113，SYNC+_0114，SYNC+_0203，SYNC+_0091，SYNC+_0240，SYNC+_Z0187，SYNC+_Z0197，SYNC+_0228 Update Feature Description: SYNC+_0025，SYNC+_0028，SYNC+_0029，SYNC+_0047，SYNC+_0049，SYNC+_0068，SYNC+_0082，SYNC+_0247，SYNC+_0051，SYNC+_0093，SYNC+_0089，SYNC+_0092，SYNC+_0098，SYNC+_0117，SYNC+_0119，SYNC+_0118，SYNC+_0124，SYNC+_0125，SYNC+_0129，SYNC+_0113，SYNC+_0114，SYNC+_0172 Update CDX707 column: SYNC+_0247，SYNC+_0118，SYNC+_0151，SYNC+_0158，SYNC+_0162，SYNC+_0156，SYNC+_0157，SYNC+_0153 Update CDX747 column: SYNC+_0247，SYNC+_0237，SYNC+_0110，SYNC+_0118，SYNC+_0141，SYNC+_0151，SYNC+_0158，SYNC+_0162，SYNC+_Z0240，SYNC+_0154，SYNC+_0156，SYNC+_0157，SYNC+_0153，SYNC+_Z0236，SYNC+_Z0238，SYNC+_Z0255，SYNC+_Z0055，SYNC+_Z0054 Delete: SYNC+_0024，SYNC+_0026，SYNC+_0243，SYNC+_0033，SYNC+_0038，SYNC+_0043，SYNC+_0244，SYNC+_0245，SYNC+_0246，SYNC+_0044，SYNC+_0242，SYNC+_0045，SYNC+_0046，SYNC+_0072，SYNC+_Z0082，SYNC+_Z0233，SYNC+_Z0184，SYNC+_Z0048，SYNC+_Z0049，SYNC+_Z0188，SYNC+_Z0189，SYNC+_Z0190，SYNC+_Z0191，SYNC+_Z0192，SYNC+_Z0193，SYNC+_Z0194，SYNC+_Z0195，SYNC+_Z0196，SYNC+_Z0198，SYNC+_Z0207 Add CX788 column. Add: SYNC+_0248，SYNC+_0249，SYNC+_0250，SYNC+_0251，SYNC+_0252，SYNC+_0253，SYNC+_0254，SYNC+_0255，SYNC+_0256，SYNC+_0257，SYNC+_0258，SYNC+_0259，SYNC+_0260，SYNC+_0263
V2.5 | 2021-04-14 | Zhou Jiajia | CX707 Release Plan update: Change SYNC+_0129（Child Restraint System） from R12(DCV3) to R10(DCV1). CX788 Feature scope update: "Y-study" for the feature ID: SYNC+_0156/SYNC+_0157/SYNC+_0115/SYNC+_0110/SYNC+_0135, "Y" for SYNC+_0196 “N” for SYNC+_Z0012 Add column "Z" to "AC" for CX788 release plan
V2.6 | 2021-04-14 | Chen Jiazu | Add SYNC+_0261 二排座椅控制 for U611 Add SYNC+_0265 V2I Lite for788
V2.7 | 2021-04-29 | Zhou Jiajia | Update CX788 FIP and HMI Dependency Plan.
V2.8 | 2021-05-08 | Zhou Jiajia | Update CX788 FIP(Column AC/AD will be updated accroding to the approved VPP)， change SYNC+_Z0028 intergration plan from R5 to R7 in CDX707/CX788, because of no HMI UX requirement about this feature.
V2.9 | 2021-05-10 | Chen Jiazu | Add Dev Spec for followin feature: SYNC+_0022,SYNC+_0256,SYNC+_0260,SYNC+_0253,SYNC+_0012,SYNC+_0015,SYNC+_0017,SYNC+_0018,SYNC+_0134,SYNC+_0095,SYNC+_0255,SYNC+_0165,SYNC+_Z0159~SYNC+_Z0177,SYNC+_0259,SYNC+_0248~SYNC+_0251，SYNC+_0020，SYNC+_0090，SYNC+_0091,SYNC+_0093,SYNC+_0252,SYNC+_0257,SYNC+_0258,SYNC+_0263,SYNC+_Z0056
v2.10 | 2021-05-18 | Chen Jiazu | Add Dev Spec for followin feature: SYNC+_Z0126,SYNC+_Z0038,SYNC+_Z0032,SYNC+_0221,SYNC+_0126,SYNC+_0127,SYNC+_0128,SYNC+_0163,SYNC+_0164
v2.11 | 2021-05-24 | Chen Jiazu | Add Dev Spec for following feature: SYNC+_0112,SYNC+_Z0092,SYNC+_0074
v2.12 | 2021-06-11 | Chen Jiazu | Add SYNC+_0266 Lancher - 3D Car Model with vehicle controls Update following features' FO: SYNC+_0139,SYNC+_0140,SYNC+_0153,SYNC+_Z0052,SYNC+_Z0069,SYNC+_Z0070,SYNC+_Z0077,SYNC+_Z0088 Delete the following feature from CDX707: SYNC+_Z0068 Adaptive Steering SYNC+_Z0078 Grade Assits SYNC+_Z0079 Hill Decent Control SYNC+_Z0080 Hill start assist SYNC+_Z0083 Lincoln Camera Shortcut key SYNC+_Z0084 Lincoln Drive Assist Shortcut key SYNC+_Z0095 Tow Haul SYNC+_Z0098 Trailer Sway SYNC+_0115 座舱内手机遥控 Project Aspire_Ultimate Remote Control SYNC+_0153 娱乐座舱Cabin On-Live （曾用名音乐派 Music Boom. Former name: JukeBox） SYNC+_0149 路书 (App -去兜风) Project Aspire_Route 66 / Tourist Mode (Education and Historical POIs)_CN (Route 66/Travel Book)
v2.13 | 2021-06-22 | Chen Jiazu | Update SYNC+_Z0101 Feature Name to ‘Ambient Lighting 128 Color’ Delete SYNC+_Z0100 Ambient Lighting - Breath Control (setting: on/off)
v2.14 | 2021-06-23 | Chen Jiazu
v2.15 | 2021-07-02 | Zhou Jiajia | CDX707 Change list: SYNC+_0123 保养及在线预约: On Hold SYNC+_0156 车载游戏:Y-OTA Updated CDX707 sw release plan: SYNC+_Z0032 SYNC+_Z0033 SYNC+_Z0039 SYNC+_Z0041 SYNC+_Z0043 SYNC+_Z0054 SYNC+_Z0101 SYNC+_0138 SYNC+_0145 SYNC+_0151 SYNC+_0157 SYNC+_0266 Add CX747 SW Integration Plan in Column AD-AF.
v2.16 | 2021-07-05 | Zhou Jiajia | Updated CDX707 Autosar related feature integration plan with Zheng Wei, Huang Feng. Align CDX747 Plan with vendors and HMI team.
v2.17 | 2021-07-13 | Chen Jiazu | Add Dev Spec for: SYNC+_0122 SYNC+_Z0045 Fob Free Entry and Ignition (NFC) Update Dev Spec for: SYNC+_0098，SYNC+_Z0068，SYNC+_Z0075,SYNC+_Z0076,SYNC+_Z0077,SYNC+_Z0091,SYNC+_Z0093,SYNC+_Z0094,SYNC+_Z0096,SYNC+_Z0097,SYNC+_Z0078,SYNC+_Z0079,SYNC+_Z0080,SYNC+_Z0095,SYNC+_Z0098,SYNC+_Z0178,SYNC+_Z0180，SYNC+_Z0181，SYNC+_Z0182，SYNC+_Z0183，SYNC+_Z0185，SYNC+_Z0186，SYNC+_Z0187，SYNC+_Z0197，SYNC+_Z0200，SYNC+_Z0201，SYNC+_Z0202，SYNC+_Z0203，SYNC+_Z0204，SYNC+_Z0205，SYNC+_Z0206，SYNC+_Z0208，SYNC+_Z0209，SYNC+_Z0210，SYNC+_Z0211，SYNC+_Z0212，SYNC+_Z0213，SYNC+_Z0214，SYNC+_Z0215，SYNC+_Z0216，SYNC+_Z0217，SYNC+_Z0227,SYNC+_Z0229,SYNC+_Z0231,Blind Spot Information System (BLIS) (CDX746/7),Perimeter Anti-Theft Alarm (CDX746/7) Add Heated Steering Wheel (CDX746/7) Passenger Airbag Deactivation (CDX746/7) Seat Temperature Control (CDX746/7) Power Liftgate (CDX746/7)
v2.18 | 2021-07-15 | Chen Jiazu | SYNC+_0042 update FDL to Ford_InHouse Delete SYNC+_0113,SYNC+_0114,SYNC+_0167,SYNC+_Z0027,SYNC+_Z0025,SYNC+_Z0046,SYNC+_Z0071,SYNC+_Z0072,SYNC+_Z0073,SYNC+_Z0074,SYNC+_Z0087,SYNC+_Z0200,SYNC+_Z0203,SYNC+_Z0205
V2.19 | 2021-08-04 | Chen Jiazu | Remove SYNC+_Z0057 FNOS (Phase5 use AutoSar) Add VSEM ID for following item:SYNC+_0073,SYNC+_0090,SYNC+_0106,SYNC+_0112,SYNC+_0132,SYNC+_0134,SYNC+_Z0075,SYNC+_Z0114,SYNC+_Z0281 Remove VSEM ID for following items:SYNC+_Z0212 Add following feature:SYNC+_0267,SYNC+_0269,SYNC+_0270,SYNC+_0271,SYNC+_0272,SYNC+_0273,SYNC+_0275,SYNC+_0276,SYNC+_0277,SYNC+_0278,SYNC+_0279,SYNC+_0280,SYNC+_0281,SYNC+_0282,SYNC+_0283,SYNC+_0284,SYNC+_Z0282,SYNC+_Z0283,SYNC+_Z0284,SYNC+_Z0285,SYNC+_Z0286,SYNC+_Z0287,SYNC+_Z0288,SYNC+_Z0289,SYNC+_Z0290,SYNC+_Z0291,SYNC+_Z0292,SYNC+_Z0293,SYNC+_Z0294,SYNC+_Z0295,SYNC+_Z0296,SYNC+_Z0297 Update Following items' Product Suite:SYNC+_0234,SYNC+_Z0240,SYNC+_Z0244 Update Following items' Feature Group:SYNC+_0221 Update Following items' feature name: -SYNC+_0221 'CAN/USB 升级' --> 'CAN 升级' -SYNC+_0011 'FM/AM收音机 AM/FM Radio' --> ' FM/AM收音机 AM/FM Radio （Anteena Based天线接收）' -SYNC+_0042 '语音助手2.0 VPA 2.0 (融合贯通生态的智能化的语音助手）' --> '语音助手1.5/2.0 VPA 1.5/2.0 (融合贯通生态的智能化的语音助手）' -SYNC+_0110 '后排乘客数字体验 2nd Row Digital Experiences including Cabin On-live (Jukebox)' --> '舱内娱乐Cabin On-live 1.0 ' -SYNC+_0156 '车载游戏 Project Aspire_In-Vehcle Gaming (Gaming Mode)' --> '舱内娱乐Carbin on live 2.0' -SYNC+_0157 '车机应用市场Project Aspire_Marketplace / Apps Anywhere' --> '车机应用商店Apps Anywhere(SYNC+)' -SYNC+_0158 'Lidget 2.0' --> '车载游览器/浏览器应用Project Aspire_Streaming Web / Applications' -SYNC+_0159 '壁纸 Project Aspire_Dash Backgrounds (Dual 23.6+11.1)' --> '壁纸 Project Aspire_Dash Backgrounds (Dual 23.6+11.1/or 27")' -SYNC+_0166 '基于云端的用户档案Project Aspire_Personal Portable Profiles' --> '基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP)' -SYNC+_0249 '两字拒识 (降低误识率采取的策略)' --> '取消两字拒识 (降低误识率采取的策略)' -SYNC+_0265 '车路协同 V2I Lite (Production)' --> '车路协同 4G V2I Lite (Production)' -SYNC+_0090 '360 摄像头图像 360 Camera Image' --> ’360 摄像头图像 360 Camera Image 1.0‘ Update Project Info for CX788
V2.19 | 2021-08-06 | Zhou Jiajia | Update CDX707 SYNC+_0269 天气,SYNC+_Z0282 车机管家 SW delivery plan. Update 747 SW release plan for the features with confirmed feature develop leader
v2.20 | 2021-08-14 | Chen Jiazu | Check with BOF and review with AFO to do the following modification: Add following feature for CDX707: SYNC+_Z0247,SYNC+_Z0289，F002216/A Add following feature for CDX707 TBD: SYNC+_Z0258,SYNC+_Z0244,SYNC+_Z0257,SYNC+_Z0241,SYNC+_Z0295,SYNC+_Z0287,SYNC+_Z0292,SYNC+_Z0297,SYNC+_Z0097，SYNC+_Z0246，F000810 Add VSEM ID F000903 to SYNC+_Z0227 F000064 to SYNC+_0170 F000908 to SYNC+_Z0091 F001430 to SYNC+_0101
v2.21 | 2021-08-15 | Zhou Jiajia | Update the SW release plan for the following Feature in CDX707. SYNC+_0073,SYNC+_0089,SYNC+_0091,SYNC+_0098,SYNC+_0134,SYNC+_Z0246,SYNC+_Z0097 Book the SW release version for the following feature: VESM ID F002216/A VESM ID F000564 FIP ID SYNC+_Z0289
v2.22 | 2021-08-18 | Chen Jiazu | Check with BOF and review with AFO to do the following modification: Update SYNC+_0170 description Update SYNC+_0170 develop rating (Baidu 100%->80, Core Service 0% ->20%) Add Dev Spec Lincoln Embrace_v2.2.2_CDX707_updated.pdf to SYNC+_0170 Update SYNC+_0170 FO Wu, Bella (Y.) <YWU150@ford.com> -> Chen, Huizhen (H.) <hchen188@ford.com> Add FO to SYNC+_Z0289 Wang, Vincent (X.) <xwang151@ford.com> Add description for SYNC+_Z0289 Add new feature F000800 Heated Mirror Add VSEM ID F000910\F000911 to SYNC+_Z0075 Cruise Control Type Update SYNC+_Z0075 feature name 'Cruise control- Type (Adaptive, intelligent, normal), tolerance' -->'Cruise Control Setting' Change SYNC+_Z0097 TSR CDX707 project into 'N' -->'Y' Add description for SYNC+Z0097 Add FO Xu, Xi Hai (X.) <xxu61@ford.com> to F002216/A Add Feature Description to F002216/A Add Feature Developer Leader information for F002216/A (Core_Service 90%, HW_Tier1 10%) Add FO Zhou, Travis (C.X.) <czhou17@ford.com> to SYNC+_Z0241 Update SYNC+_0134 Dev Spec Digital Scent PRD - for CDX707C 20210318.doc --> Digital Scent PRD - for CDX707C 20210714.doc Update SYNC+_Z0058 Dev Spec ES-H1BT-1A278-AA-V6.5_DRAFT.docx --> ES-H1BT-1A278-AA-V7.0.pdf Update SYNC+_0165 Enhanced_Memory_With_Soft_Button_Feature_Level_Specification_v1.2_Sep_27, 2020.docx -->Enhanced_Memory_With_Soft_Button_Feature_Level_Specification_v1.3_Aug_13, 2021.docx Add FO for Liu, Hongxin (H.) <HLIU162@ford.com> for F000564 Add description for F000564 Update SYNC+_0098 FO info Zhou, Wu (W.) <wzhou44@ford.com> -->Liu, Hongxin (H.) <HLIU162@ford.com> Add description for SYNC+_Z0281 Lane Centering Assist Add Dev Spec for SYNC+_Z0281 Lane Centering Assist Add description for SYNC+_Z0091 Pre Collision Assist Update SYNC+_0074 Li, Xin (X.) <xli268@ford.com> --> Update SYNC+_0101 FO Zhou, Wu (W.) <wzhou44@ford.com> -->Liu, Hongxin (H.) <HLIU162@ford.com> Update SYNC+_0101 Feature Description, add Dev Spec Add VSEM ID F002054 for SYNC+_Z0279 Add description for SYNC+_Z0279
v2.23 | 2021-08-19 | Chen Jiazu | Check with BOF and review with AFO to do the following modification: Add VSEM ID F000016/E to SYNC+_Z0070 Add VSEM ID F000123 to SYNC+_Z0176 Add VSEM ID F000162 to SYNC+_Z0212 Add SYNC+_Z0293 Power Liftgate Soft switch to CDX707 project scope Add VSEM ID F00158 to SYNC+_Z0047 Multi contour seat Add SYNC+_Z0287 First Row Seat Position Control to CDX707 project scope Add description & FO for SYNC+_Z0287 First Row Seat Position Control Update FO for SYNC+_Z0047 Li, Xuedong (X.) <XLI244@ford.com> -->Du, Hao (H.) <HDU9@ford.com> Add FO for SYNC+_Z0297 Add VSEM ID F003518 for SYNC+_Z0167 Front Row Seat Heated Add VSEM ID F003518 for SYNC+_Z0168 Front Seat Vent Update FO for SYNC+_Z0047 Yao, Frank (F.) <FYAO2@ford.com>/DongYa --> Du, Hao (H.) <HDU9@ford.com> Update FO for SYNC+_Z0176 Yan Yao, Frank (F.) <FYAO2@ford.com>/DongYa -->Yan, Sophie (C.) <cyan10@ford.com> Add Product Suite name 'Vehicle Control 车辆控制' to SYNC+_Z0247 Add Feature Group name 'Climate Control 空调控制' to SYNC+_Z0247 Add FO and Description for SYNC+_Z0247 Heated Backlight (climate) Add VSEM ID F001006 to SYNC+_Z0181 Light Setting-daytime lights Update FO for SYNC+_Z0181,SYNC+_Z0180 ,SYNC+_Z0178 Li, Xuedong (X.) <XLI244@ford.com> --> Zhou, Travis (C.X.) <czhou17@ford.com> Add VSEM ID F001027 to SYNC+_Z0178 Light Setting-Adaptive headlamps Add VSEM ID F000139 to SYNC+_Z0216 Windows (remote open/close) Update FO for SYNC+_Z0216 Li, Xuedong (X.) <XLI244@ford.com> -->Li, Shiyuan (S.) <sli163@ford.com> Add VSEM ID F000400 to SYNC+_Z0213 Remote start Update FO for SYNC+_Z0216 Lin, Shawn (X.) <xlin17@ford.com> --> Li, Shiyuan (S.) <sli163@ford.com> Delet the following feature from CDX707 project scope SYNC+_Z0244,SYNC+_Z0258,SYNC+_Z0257
v2.23 | 2021-08-20 | Zhou Jiajia | Update the SW plan for the 707 feature item: SYNC+_Z0247 SYNC+_Z0047 SYNC+_Z0297
v2.24 | 2021-08-26 | Zhou Jiajia | Update F000171,change 707 to Yes Update F000810 CDX707 update to Yes,and CX747 update to C/O Update SYNC+_Z0293，Update F0000162->F0000165 Add F003074/F000121/F000189/F000864/F000604/F003413/F003414/F003370/F003415/F001047 Add F000178 for U611 Update F000810 time plan&Fo JJin17 Update the SW plan for the 707 feature item: 1. Map related feature full function ready with UI COB DCV1. SYNC+_0002,SYNC+_0003,SYNC+_0006,SYNC+_0007,SYNC+_0239 2.Suixinting, Aqiyi full function ready with UI COB DCV1. SYNC+_0018,SYNC+_0020 3. Welcome/Farewell Animation should be ready COB DCV0.1. SYNC+_0194 4. Multi theme release plan change to DCV3(pending Studio/UI plan). SYNC+_0205 5. Update the customer feedback/Vehicle to home/Account etc. to DCV1(aligned with Baidu, YFVE). SYNC+_0125，SYNC+_0160/SYNC+_0161,SYNC+_0164，SYNC+_0172，SYNC+_0173，SYNC+_0106，SYNC+_0128,SYNC+_0010
v2.25 | 2021-08-31 | Chen Jiazu | Update SYNC+_Z0240 project info add CDX707,747 & U611 Add following feature for CDX747: F000818,F005350,F003410,F003411,F000864,F003074 Update SYNC+_Z0289 TPMS CDX747 project scope New-->C/O Change N to C/O for CDX747 about F002216/A F000122 change New to C/O for CDX747 F000913/C change N to C/O for CDX747 F000800 change idle to C/O for CDX747 F000760 change new to CO for CDX747 F000171 change new to CO for CDX747 Add U625 MCA project info
v2.26 | 2021-09-03 | Chen Jiazu | Add Integrated AVAS for CDX747 project Update following features' Dev_Spec for CDX747 Quotation F003090 Cabin & Battery Overheat Management F000760 AEIS (Auto Engine Idle Shutdown) for BEV F001023 Automatic Dynamic Leveling SYNC+_0134 F004410 数字香氛 Digital Scent 2.0 (New Scents) SYNC+_0264 F003951 EM(Electro-Mechanical) Register SYNC+_Z0263 F003751 Enhanced Dash Camera SYNC+_0228 F003519 My Seat Space (MSS) (CDX746/7) SYNC+_Z0259 F000058/C Map/Dome Lights(RSD - Manual Interior Lighting) SYNC+_0135 F003072 活力恢复 Project Aspire_Rejuvenation SYNC+_Z0262 F003417 Integrated Sentinel(Video-Based Vehicle Monitoring) SYNC+_Z0253 F003090 Cabin & Battery Overheat Management SYNC+_Z0251 F002870 Stowable Steering Column w/ Deploying Tray Change following item from C/O --> New for CDX747 SYNC+_Z0185 单色氛围灯 single color ambient lighting SYNC+_Z0186 多色氛围灯 multi color ambient lighting SYNC+_Z0079 Hill Decent Control Change following item from New-->C/O for CDX747 SYNC+_Z0297 Seat Temperature Control Setting for Remote Start SYNC+_Z0287 First Row Seat Position Control SYNC+_Z0295 Heated Steering Wheel Setting for Remote Start SYNC+_Z0293 Power Liftgate Soft switch Change following item project socpe to N for CDX747 SYNC+_Z0095 Tow Haul (Setting) SYNC+_Z0098 Trailer Sway (Setting)
v2.27 | 2021-09-06 | Xia Xiaojin | Base on the CX788 IVI PDL feature list_20210902 ,delete the following feature from CDX788: SYNC+_0011 FM/AM收音机 AM/FM Radio （Anteena Based天线接收） SYNC+_0109 IVI 驾驶员状态监控和报警 IVI Driver Status Monitor & Alert (Fatigue, Distraction, Dangers Behaviour) SYNC+_0196 电车实时车况界面 IOD Information On Demand/Display SYNC+_0115 座舱内手机遥控 Project Aspire_Ultimate Remote Control SYNC+_0124 用户反馈Customer Feedback1.0 SYNC+_0117 车机端电子版用户手册 E-Manual 1.5 SYNC+_0135 活力恢复 Project Aspire_Rejuvenation SYNC+_0141 车机日历Project Aspire_Routines / Daily View_IVI Calendar 2.0 SYNC+_0151 随心拍Travel Shooting 2.0 Project Aspire_Photos (GPS Created Trip Summary) SYNC+_0158 车载游览器/浏览器应用Project Aspire_Streaming Web / Applications SYNC+_0264 EM(Electro-Mechanical) Register SYNC+_0070 语音助手VPA 1.0 (形象化的语音助手） SYNC+_0127 紧急救援Emergency Assistance (EA) SYNC+_0163 车机端百度账号登陆(By 福特派/lincoln app) Baidu Login Base on the PDL Angel 's meeting(2021/09/07) , delete the following feature from CDX788 SYNC+_Z0047Multi contour seat -Seat adjust -Custom Massage Patterns HMI for Multi-Contour Seats (U611) -Seat massage SYNC+_Z0088 Multi-Contoured Seats (Massage Seats) SYNC+_Z0079 Hill Decent Control SYNC+_Z0176 Steering wheel heated SYNC+_Z0213 Base on the CX788 IVI PDL feature list_20210902 ,add the following feature from CDX788: SYNC+_0021 视频、音乐、图片DLNA投屏到车机显示器区分主副驾/Video Playback and Video and Photo project to Display(Driver and Passenger) via DLNA Base on the PDL Angel 's meeting(2021/09/07) , add the following feature from CDX788 F000800 Heated Mirrors
V2.28 | 2021-09-08 | Zhou Jiajia | 707 sw plan updated as below: 1.Add the feature release plan DCV1 for F000800 <Heated Mirrors> 2.Add VSEM ID F000136 for SYNC+_0036 3. Change F003515 <Surround View Cameras> from DCV2 to DCV1. 4. Add SW release plan R04 for F004711 <Steering Horizon Control> 5. Change SYNC+_0154 视频会议 status to On hold 747 information updated as below: 1.SYNC+_0267<AR HUD> 747 N; 2. Add FDL for SYNC+_Z0262 <Integrated Sentinel(Video-Based Vehicle Monitoring)>; 3. Add FDL for SYNC+_Z0292<二排座椅控制>; 4.Change SYNC+_0154 视频会议 status to On hold; 5. Change SYNC+_0226 <Project Aspire _14C. (New) Karaoke – RED _CN> to N; 6.Add FDL Coreservice to SYNC+_0231<Mobile Device Viewer>. 7.Update 747 Feature integration plan aligned with vendors(Risk for the feature highlighted in yellow, no plan for the agile feature highlighted in red)
V2.29 | 2021-09-09 | Xia Xiaojin | Base on the 0908 Unified IVI PDL Alignment meeting ,Update the following features for all of projects: Part 1:ECDX team feedback no need,delete as below features list SYNC+_0224 Special Memory SYNC+_0225 Kid Media Content/Game_CN SYNC+_0226 Project Aspire _14C. (New) Karaoke – RED _CN SYNC+_0227 Multi-zone voice control (1&2 Rows) SYNC+_0237 Smart Warm-up SYNC+_0238 Remote control of Frunk Carplay Part2 :Remove Duplicate part Delete SYNC+_0153 娱乐座舱Cabin On-Live （曾用名音乐派 Music Boom. Former name: JukeBox）,Duplicate with SYNC+_0110 Delete SYNC+_0149 路书 (App -去兜风) Project Aspire_Route 66 / Tourist Mode (Education and Historical POIs)_CN (Route 66/Travel Book)，Duplicate with SYNC+_0110 Delete SYNC+_0230 PPP with Stowable Steering Wheel position ，Duplicate with SYNC+_0166 Delete SYNC+_0268 BEV Unique Charging， Duplicate with SYNC+_0208 Delete SYNC+_Z0064 安装/运行福特指定的第三方软件/VP硬件对应的软件，后面会用小程序替代。 Part 3：Modify Feature_Product_Suite 、Feature_Group,Feature name、Feature_Description SYNC+_0110 update Feature_Product_Suite 、Feature_Group SYNC+_0159 Feature_Product_Suite SYNC+_0228 update Feature_Product_Suite 、Feature_Group SYNC+_0267 update Feature_Product_Suite 、Feature_Group、Feature_Description SYNC+_0208 update Feature name、Feature_Description SYNC+_0109 Add Feature_Description SYNC+_0135 Modify Feature_Description SYNC+_0136 Modify Feature_Description SYNC+_0166 Modify Feature_Description SYNC+_0208 Modify Feature_Description SYNC+_0240 Modify Feature_Description Part 4：Per EDCX PMO ‘s comments,Modify Feature_Product_Suite. System Function 系统功能==>"T# System Function 系统功能", System Setting 系统设置==>"U# System Setting 系统设置", Vehicle Control 车辆控制==>"V# Vehicle Control 车辆控制", Vehicle Setting 车辆设置==>"W# Vehicle Setting 车辆设置" Part 5:Per BOF cascade result,Modify as below items for CX 788 1.Update F000097 feature name and Feature Description. 2.Add F000165/D Power Liftgate Soft switch 3.Add F000122 Heated Backlight (climate) 4.Add SYNC+_0004/F003451 Local Hazard Information (LHI) 5.Add SYNC+_Z1002/F000564 Blindspot Detection 5.针对无IVI PDL ID的条目，增加新编号，从SYNC+_Z1000开始 XCL Change List: 1.SYNC+_0082 车路协同 V2I Lite (Beta) Phase5 N. SYNC+_0265 车路协同 4G V2I Lite (Production) Phase5 Yes.
V2.29 | 2021-09-10 | Zhou Jiajia | 1.Update Column U/V(Change level) information for CX788 with James, Xiaojin 2.Update Column AW to AY for SW integration plan for CX788.
V3.0 | 2021-09-15 | Xia Xiaojin | 1.Per 9/13 788 FIP Update QA and Alignment Meeting(F2F) Round1's discussion, delete as below items for CX 788 SYNC+_0113 远程鸣笛闪灯 Vehicle Announcement via FordPass SYNC+_0114 远程空调控制 Remote Climate Control (RCC) via FordPass/Lincoln Way SYNC+_Z0072 Climate Menu SYNC+_Z0073 Climate Mode Selection SYNC+_0015 本地音乐-MTP音乐 MTP music/USB音乐 USB music/蓝牙音乐 BT music SYNC+_0137 个人时光 Smart Scene - Personal Enjoyment SYNC+_0117 车机端电子版用户手册 E-Manual 1.5 Per the latest PDL ，Add as below features SYNC+_0285 加油 - Oil Service SYNC+_0286 洗车 - Car wash SYNC+_0287 Market Place 2.To matching PDL‘s format,split Feature Implementation Plan into 3 sheets Sheet1 :01Customer Facing Sheet2:02Basic Function Sheet3:03BOF 3.Delete as below items for all of project SYNC+_0184 双23.6寸全景屏+11.1寸横屏（可触摸）23.6'x2 (Pano -Non Touch) +11.1 Touch SYNC+_0177 12.3寸横屏12.3' Landscape SYNC+_0178 12.8寸横屏12.8' Landscape SYNC+_0179 12.8寸竖屏12.8' Partrait SYNC+_0180 12寸横屏12' Landscape SYNC+_0181 13.2寸横屏13.2' Landscape SYNC+_0182 15.5寸竖屏15.5' Portrait SYNC+_0183 27寸横屏 (可触摸）27' Landscape 4.Modify FO For CD 788 SYNC+_Z0004 Audio Management SYNC+_0265 车路协同 4G V2I Lite (Production) SYNC+_Z1003 Heated Mirrors SYNC+_0285 加油 - Oil Service SYNC+_0286 洗车 - Car wash SYNC+_Z0282 车机管家 SYNC+_Z1023 ADAS Map 5.Per PDL ‘s information, modify as below Feature_Description SYNC+_0029 SYNC+_0042 SYNC+_0265 SYNC+_0106 SYNC+_0118 SYNC+_0126 SYNC+_0170 SYNC+_0272
V3.1 | 2021-09-18 | Xia Xiaojin | Add " Read Me" for user to read sync+ Phase5 FIP file. 1.Per 9/17 788 FIP Update QA and Alignment Meeting(F2F) Round2's discussion, modify as below items for CX788 Add SYNC+_0011 FM/AM收音机 AM/FM Radio （Anteena Based天线接收）,update Feature_Description Add SYNC+_0015 本地音乐-MTP音乐 MTP music/USB音乐 USB music/蓝牙音乐 BT music Modify feature name , Feature_Description Add SYNC+_Z0003 Active Noise Cancellationg (ANC) Tuning SYNC+_0266 Modify Feature Development Leader SYNC+_0265 Add comments in Feature Development Leader SYNC+_0143 Add comments in Feature Development Leader SYNC+_Z0221 CHUD (TFT HUD) - setting Add FO SYNC+_Z0155 车载热点 WifiHotspot Change FO 2. Delete changes for CX788 Delete SYNC+_0138 车机相册 IVI Picture Gallery（Currently no FO） Delete SYNC+_0145 随心拍Traveling Shooting（Currently no FO） Delete SYNC+_0159 壁纸 Project Aspire_Dash Backgrounds (Dual 23.6+11.1/or 27") For CDX 707 .CDX747.Phase 5 Delete SYNC+_Z0096 Traction Control 3.788 Timing Update 3.1 Change SYNC+_0036 plan from DCV Beta1 to Beta 3.2 Add FDL for SYNC+_0285~SYNC+_0287 3.3 Add SW release plan DCV Beta for SYNC+_Z0003 3.4 Change SYNC+_0265 plan from DCV2 to DCV3 4. Move as below BOF feature to Customer Facing SYNC+_0077 5G 车路协同 5G V2V SYNC+_0082 车路协同 V2I Lite (Beta) SYNC+_0247 5G 车路协同 5G V2I SYNC+_0232 Night Vision 5.On hold as below feature ,no need quotation SYNC+_0273 Remote Window Control / Window Status (China) onHold 6.BOF cascade as below features for CX788 SYNC+_Z1015 Cellular Remote Start / Stop (U6XX) SYNC+_Z0216 Power Folding Mirrors w & w/o autofold (RSD - Mirror Fold)
V3.2 | 2021-09-29 | Xia Xiaojin | U6111 01 Customer Facing Sheet Base on the Ford China (SYNC+) IVI Feature PDL_Living Document_U611MCA_U625MCA_2021-09-27 Add as below New feature item SYNC+_0274 BEV Unique Charging - FB5 SYNC+_0288 手机钥匙 BUN Paak SYNC+_0289 Lidget/Fidget/Widget 3.0 Change as below feature from N to "Y" SYNC+_0113、SYNC+_0114、SYNC+_0207、SYNC+_0261、SYNC+_0278 Delete the following feature for U611 SYNC+_0010、SYNC+_0108、SYNC+_0110、SYNC+_0116、SYNC+_0117、SYNC+_0135、SYNC+_0141、SYNC+_0145、SYNC+_0151、SYNC+_0154、SYNC+_0156、SYNC+_0158、SYNC+_0206、SYNC+_0256、SYNC+_0264、SYNC+_0272、SYNC+_0279、SYNC+_0115、SYNC+_0167、SYNC+_0265 Delete SYNC+_0076、SYNC+_0092、SYNC+_0094 （duplicate with 03 BOF ） U625 01 Customer Facing Sheet Base on the Ford China (SYNC+) IVI Feature PDL_Living Document_U611MCA_U625MCA_2021-09-27 , delete the following feature for U625MCA SYNC+_0272、SYNC+_0156、SYNC+_0155 Add as below featues SYNC+_0106、SYNC+_0262、SYNC+_0285、SYNC+_0286、SYNC+_0287 On Hold as below feature SYNC+_0273 The other changes Add SYNC+_0285、SYNC+_0286 for CDX 707 and CDX 747 Add SYNC+_0289 for CDX 747
V3.3 | 2021-09-30 | Xia Xiaojin/ Zhou Jiajia | Deleted the following duplicate feature in 01Customer Facing SYNC+_0247 SYNC+_0077 SYNC+_0082 SYNC+_0232 Jiajia ：Add U 6xxx Timing
V3.4 | 2021-10-19 | Xia Xiaojin | Per 00 Ford China (SYNC+) IVI Feature PDL_Living Document_20211013,change as below items: 01 Customer Facing 1.移动原CustomerFacing中如下HMI Lead的Feature至BasicFunction：SYNC+_0159，SYNC+_0194，SYNC+_0203，SYNC+_0204，SYNC+_0205，SYNC+_0206，SYNC+_0207,SYNC+_0221 2. 移动原BasicFunction中如下Feature至CustomerFacing中： SYNC+_Z0023，T# System Function 系统功能，Carrier，流量套餐app端流量查询购买 data plan query & oder SYNC+_Z0032，T# System Function 系统功能，Carrier，CCS (Connectivity Connectivity Setting) 3.SYNC+3.0: 1. 合并<C# Intelligent Digital Assitant 智能数字助手>Suite分类中EE Lead Delivery的Feature条目为一条，调整详情如下： 删除SYNC+_0025 <播报能力+语音包 Multiple TTS (可切换）> 删除SYNC+_0027 <所见即可说 Voice command on IVI displayed touch elements"> 删除SYNC+_0028 <打断式交互 全双工语音 Barge-in"> 删除SYNC+_0048 <唤醒词 - 品牌唤醒词 Brand wake-up commands"> 删除SYNC+_0049 <免唤醒 - 全局/情景免唤醒 Wake-up Free"> 删除SYNC+_0050 <唤醒词 - 自定义 Customized Wake-up keyword；林肯的语音唤醒词“你好，林肯” Lincoln wake-up commands；福特的语音唤醒词“你好，福特” Ford wake-up commands；核心功能场景化免唤醒命令 Wake-up command is not mandatory to activate for key functions"> 删除SYNC+_0241 <One-Shot 唤醒词加命令一起处理"> 删除SYNC+_0248 <多轮交互/上下文交互"> 删除SYNC+_0249 <取消两字拒识 (降低误识率采取的策略)"> 删除SYNC+_0250 <语音退出"> 删除SYNC+_0251 <闲聊"> 删除SYNC+_0029 <普通话识别 Mandarin Rocognition"> 删除SYNC+_0030 <中英文混杂识别-电话域 Chinese/English mixed phone book recognition"> 删除SYNC+_0031 <离线指令 Offline Command"> 删除SYNC+_0032 <中英文混杂 - 音乐域/导航 Mandarin/English mixed language recognition - music/navigation"> 删除SYNC+_0252 <车辆状态查询> 删除SYNC+_0253 <车主手册> 删除SYNC+_0254 <EV/PHEV 充电功能 > 删除SYNC+_0051 <语音查询服务> 删除SYNC+_0258 <(百度小程序) 在线应用> 删除SYNC+_0068 <音乐、收音机、在线电台、新闻、有声、爱奇艺、随心拍 等> 删除SYNC+_0255 <专业导航> 删除SYNC+_0256 <AR导航> 删除SYNC+_0257 <系统控制(IVI模块系统级别）> 删除SYNC+_0034 <前舱盖打开控制 Frunk Control -Open> 删除SYNC+_0035 <后备箱打开控制 Trunk Control-Open> 删除SYNC+_0036 <天窗/遮阳帘控制 Roof window control> 删除SYNC+_0037 <座椅加热/通风控制/按摩 Seat Heating&Cooling/Seat Vented/Seat Massage > 删除SYNC+_0039 <方向盘加热 Heated Steering Wheels Control> 删除SYNC+_0040 <氛围灯开关 Ambient Lighting on/off> 删除SYNC+_0041 <空调;风量和风向 A/C> 删除SYNC+_0259 <香氛Digital Scent> 删除SYNC+_0260 <Relax> 删除SYNC+_0261 <2排座椅控制 2nd row Seat Control （7座车）> 删除SYNC+_0263 <驾驶辅助功能问答及播报 DAT - Voice Support> 删除SYNC+_0047 <Dual Zone Voice Control 主副驾双音区分区控制> 增加SYNC+_0025 <Voice Recognition Systems> 02 Basic Function Combine SYNC+_Z0054 and SYNC+_Z0055 in SYNC+_Z0015 （Delete SYNC+_Z0054 and SYNC+_Z0055 ） combine SYNC+_Z0115 、SYNC+_Z0116 and SYNC+_Z0117 in SYNC+_Z0058 ,modify SYNC+_Z0058 Feature_Description . Delete SYNC+_Z0110 Ford Software development Requirements（no basic funtion） update as below feature group /name or describation SYNC+_Z0081 Hardbutton Behavior SYNC+_Z0240 后排娱乐空调控制面板 Rear entertainment control(Climate/Audio) - U611 SYNC+_Z0122 Driving restriction SYNC+_Z0130 百度输入法 Baidu Input SYNC+_Z0156 Consumer Behavior Data (IVI related)埋点 SYNC+_Z0030 Baidu数据平台 SYNC+_Z0032 CCS (Connectivity Connectivity Setting) SYNC+_Z0033 Provisioning SYNC+_Z0038 Embedded Modem Reset/Master reset SYNC+_Z0039 FNV2 - FCI Protocol SYNC+_Z0041 IP Pass Through Client SYNC+_Z0043 Wireless Interface Router(WIR) SYNC+_Z0155 车载热点 WifiHotspot Added: 4.新增BasicFunction中Feauture：SYNC+_Z1024，Suite“T# System Function 系统功能”，Group“Bluetooth 蓝牙”，名字“Bluetooth music ” 5.新增BasicFunction中Feauture：SYNC+_Z1025，Suite“T# System Function 系统功能”，Group“Bluetooth 蓝牙”，名字“蓝牙耳机 ” Remove as below 02 basic funtion feature to “03 BOF ” Sheet SYNC+_Z0241 Automatic Dynamic Leveling SYNC+_Z0261 Considerate Prompts SYNC+_Z0256 Power Folding Mirrors w & w/o autofold (RSD - Mirror Fold) SYNC+_Z0235 Rear Seat Occupant Alert SYNC+_Z0263 Enhanced Dash Camera SYNC+_Z0250 PDLC SkyLite Digital Shade SYNC+_Z0262 Integrated Sentinel(Video-Based Vehicle Monitoring) SYNC+_Z0251 Stowable Steering Column w/ Deploying Tray SYNC+_Z0286 Drive Control Optimization SYNC+_Z1006 Classic Memory SYNC+_Z1009 Key in Reminder SYNC+_Z1010 Fob Free Entry and Ignition (NFC) SYNC+_Z0290 Steering Horizon Control SYNC+_Z0291 Rear Fog Lights SYNC+_Z1011 Blind_Spot_Assist SYNC+_Z1012 Plug and Charge SYNC+_Z0296 Passenger Airbag Disable Indicate Telltale Per Liu, Hailan (H.) 's email , update 01 customer facing SYNC+_0196 update feature name (Remove 电车) All Sync+ 3.0 Programs： 1. 新的SYNC+_0025 <Voice Recognition Systems>，针对所有项目，标记为Y Add SYNC+_0290 "人脸识别账户登录Face ID - Driver (DAT-DSMC)" as phase 5 starting from CDX707, Face ID feature are deployed on DAT-DSMC. Modified SYNC+_0108"人脸识别账户登录Face ID - Driver (IVI Stand alone IR Camera)" as "N" for all phase 5, as so far do not see any programs are going to take stand alone approach. ForP702MCA and U 718 Project. Confirmed with James , identify P702MCA and U 718 scope in 02 basic function. Update timing(Jiajia) SYNC+_0223 多模块空中升级 Multi Module OTA (MMOTA) SYNC+_0221 CAN 升级
V3.5 | 2021-11-06 | Xiaxiaojin | Modify P 702 MCA 02 Basic function 02 Basic function ,Progaram confirm P702 Support ESE Change from N to "Y" SYNC+_Z0006 Engine Sound Enhancement (ESE) Per 00 Ford China (SYNC+) IVI Feature PDL_Living Document_P702MCA_v1.1_20211105's information , updated FIP for P702MCA First time to maintain P702 MCA "01 Customering facing"and "03 BOF 's Feature Scope in FIP 01 Customering facing Modify as below featue 's name and Feature_Description SYNC+_0122 车辆状态和警示 Vehicle Health Alert and Status SYNC+_0247 5G Uu+PC5 车路协同 V2I LITE Move as below features from" 01Customer Facing" to "03 BOF" SYNC+_0215 剩余里程显示Range Ring-Nav Screen (DTE) SYNC+_0236 Cloud Based Battery Management System "03 BOF " Added as below 18 new features for P 702MCA SYNC+_Z0249 Electrochromatic Automatic Day/Night Mirrors SYNC+_Z1027 AWD / 4WD: Torque Transfer for Handling & Traction (P702 MCA) SYNC+_Z1028 Active Exhaust (P702 MCA) SYNC+_Z1029 Trail 1-Pedal Driving (P702 MCA) SYNC+_Z1030 Trailer Brake Control (P702 MCA) SYNC+_Z1031 Automatic Engine Idle Shutdown (P702 MCA) SYNC+_Z1032 Distance Indication (P702 MCA) SYNC+_Z1033 Trail Turn Assist (TTA) (P702 MCA) SYNC+_Z1034 Trail Control (TRAIL) (P702 MCA) SYNC+_Z1036 Trailer Light Check (FNV3) (MY24 P702 MCA) SYNC+_Z1037 Auto Electric Park Brake (AEPB) aka AEPB or Park Hold (P702 MCA) SYNC+_Z1038 Neutral Flat Tow (Recreational Tow) (P702 MCA) SYNC+_Z1039 Trailer Profiles and Settings (P702 MCA) SYNC+_Z1040 Blind Spot Assist (Formerly LCWA or Lane Change Warning & Aid) (P702 MCA) SYNC+_Z1041 Electronic Locking Differential (eLD / eLocker) (P702 MCA) SYNC+_Z1043 Cellular Remote Start / Stop (MY24 P702 MCA) SYNC+_Z1044 Cellular Remote Door Lock/Unlock (P702 MCA) SYNC+_Z1045 2-Speed 4WD (P702 MCA)
V3.5.1 | 2021-11-06 | Xia Xiaojin | Per 00 Ford China (SYNC+) IVI Feature PDL_Living Document_CDX747_v1.2_20211105's information , updated FIP for CDX747 01Customer Facing Change as below feature list from Y to "N" SYNC+_0011 FM/AM收音机 AM/FM Radio （Anteena Based天线接收） SYNC+_0109 IVI 驾驶员状态监控和报警 IVI Driver Status Monitor & Alert (Fatigue, Distraction, Dangers Behaviour) SYNC+_0106 手机钥匙Phone as key(PaaK) SYNC+_0117 车机端电子版用户手册 E-Manual 1.5 SYNC+_0141 车机日历Project Aspire_Routines / Daily View_IVI Calendar 2.0 SYNC+_0151 随心拍Travel Shooting 2.0 Project Aspire_Photos (GPS Created Trip Summary) SYNC+_0155 车机日历IVI Calendar 1.0 SYNC+_0208 BEV Unique Charging - FB4 SYNC+_0272 Lidget/Fidget/Widget 2.0 SYNC+_0279 Digital Embrace 2.0 SYNC+_0284 FNOS On Hold as below features SYNC+_0123 保养及在线预约 OSB - Online Service Booking SYNC+_0162 家车互联Project Aspire_General IOT (Smart Home)_CN ( Home to Vehicle) SYNC+_0273 Remote Window Control / Window Status (China) OTA as below features SYNC+_0229 Video Interface Throughout Cabin (Rear Seat Monitor, w/ expanded request: allow 2R see 1R) Add as below features SYNC+_0293 EV Charge Programming SYNC+_0294 EV Trip Planner SYNC+_0295 Intelligent Range(CE-DTE) SYNC+_0287 Market Place SYNC+_0288 手机钥匙 BUN Paak Change as below feature‘s change level SYNC+_0166 基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP) 03BOF Change as below feature list from Y to "N" SYNC+_Z0076 Driver alert SYNC+_Z0078 Grade Assits SYNC+_Z0080 Hill start assist SYNC+_Z0200 Air suspension SYNC+_Z0205 Easy access height SYNC+_Z0213 Remote start (activate, climate, auto, last setting, seats and wheels, duration) SYNC+_Z0232 4# Help Me Avoid Collisions 避免碰撞辅助 - 十字路口碰撞预警 Intersection Assist SYNC+_Z0277 4# Help Me Avoid Collisions 避免碰撞辅助_COLLISION MITIGATION SYS(FBFAB) SYNC+_Z0278 2# Help Me Drive 驾驶辅助_车距提示 DADI(Distance Alert, Distance Indicator) SYNC+_Z0244 Hazard Light SYNC+_Z0288 Perimeter Anti-Theft Alarm SYNC+_Z1017 EV Charge Programming SYNC+_Z1018 Buttonless Push To Start – BEV SYNC+_Z0235 Rear Seat Occupant Alert SYNC+_Z0286 Drive Control Optimization SYNC+_0215 剩余里程显示Range Ring-Nav Screen (DTE) SYNC+_0236 Cloud Based Battery Management System SYNC+_Z1020 Cellular Scheduled Remote Start SYNC+_Z1012 Plug and Charge Change as below feature‘s change level SYNC+_Z1019 Cellular Remote Start w/Extend Remote Start FNV3
V3.5.2 | 2021-11-08 | xia,xiaojin | Per FIP mismatch list 1105 ,changed as features: change SYNC+_0159 8# Wallpaper 墙纸 Development Leader change SYNC+_Z0083 Lincoln Camera Shortcut key Development Leader Change SYNC+_Z0216 Windows (remote open/close) scope from Y to N for CX 788 Delete 'SYNC+_Z0076' Driver alert （Duplicated） Delete SYNC+_0284 FNOS for all project （此功能为2021.8.4增加的AGLIE feature, VHA FNOS CNECDMPORT-114 - Oil Life Prediction / China SYNC+ IVI对IVI侧没有影响） Change as below feature from Y to N in CDX 707 SYNC+_Z0084 Lincoln Drive Assist Shortcut key SYNC+_0112 and SYNC+_Z0213 are duplicated, Delete SYNC+_Z0213 SYNC+_Z0287 First Row Seat Position Control ，and CDX 747 will change to leading project .Scope change to Y-1st SYNC+_Z0172 Rear climate fan SYNC+_Z0173 Rear climate mode SYNC+_Z0174 Rear climate temp Merage as below3 features in SYNC+_Z0091 Pre Collision Assist SYNC+_Z0232 (Delete) SYNC+_Z0277 (Delete) SYNC+_Z0278 (Delete)
V3.6 | 2021-11-09 | xia,xiaojin | Per Copy of 00 Ford China (SYNC+) IVI Feature PDL_Living Document_CX788_v1.3_20211025,update CX 788 FIP 01 Customer facing SYNC+_0210 动力流动画显示Power Flow Modify N -> Y SYNC+_0167 快捷设置Rocket setup Modify Y -> N. (Confirmed with Vehicle Program / Portfolio / PO) 03 BOF New added SYNC+_Z1026 Oil Minder for CX788
| 2021-11-10 | ZhangYing | 对U6系列HMI进行分组，并更新各个feature integrate version
| 2021-11-15 | ZhangYing | 更新如下U625 feature 集成版本和HMI分组： 1> Grade Assits change HMI 'N/A' to 'Group A', change integrete version to 'DCV Beta' 2> Tow Haul change HMI 'N/A' to 'Group A', change integrete version to 'DCV Beta' 3> Perimeter Anti-Theft Alarm change HMI 'N/A' to 'Group A', change integrete version to 'DCV Beta' 4> Driver_Information_Display_Control change HMI 'N/A' to 'Group A', change integrete version to 'DCV Beta' 5> 车路协同 4G V2I Lite (Production) change integrete version to 'DCV3'
| 2021-11-16 | ZhangYing | 更新CDX747 feature版本信息
V3.7 | 11/19/21 | James Chen | Update Product Suite name for following item: SYNC+_Z0023 'ZZ# Foundemental Function 基础功能' --> 'T# System Function 系统功能' SYNC+_Z0032 'ZZ# Foundemental Function 基础功能' --> 'T# System Function 系统功能' Update Feature Name for Follow Item: SYNC+_0108 '人脸识别账户登录Face ID - Driver(Registration, Recognition, Account, Personalization, Welcome)' --> '人脸识别账户登录Face ID - Driver(IVI Stand alone IR Camera)' SYNC+_0120 '违章查询 Query traffic violations (IVI)' --> '(百度小程序) 违章查询 Query traffic violations (IVI)' SYNC+_0142 '电影票预定 Movie Ticket Booking 美团外卖MeiTuanTake-away 鲜花预定Order flower delivery 机票查询 Flight search 火车票查询 Train ticket search 酒店预定 Hotel booking' --> ‘(百度小程序) 电影票预定 Movie Ticket Booking 美团外卖MeiTuanTake-away 鲜花预定Order flower delivery 机票查询 Flight search 火车票查询 Train ticket search 酒店预定 Hotel booking" SYNC+_0265 '车路协同 4G V2I Lite (Production)' --> 4G/5G Uu车路协同 V2I Lite (Production) SYNC+_0285 '加油 - Oil Service' --> '(百度小程序) 加油 - Oil Service' SYNC+_0286 '洗车 - Car wash' --> '(百度小程序) 洗车 - Car wash' Update Feature Description for following item: SYNC+_0009,SYNC+_0108,SYNC+_0115,SYNC+_0163,SYNC+_0210
V3.7 | 11/19/21 | James Chen | Add following item for P702MCA SYNC+_0247 5G Uu+PC5 车路协同 V2I LITE Delete following item for P702MCA: SYNC+_0011 FM/AM收音机 AM/FM Radio （Anteena Based天线接收 SYNC+_0138 车机相册 IVI Picture Gallery SYNC+_0229 Video Interface Throughout Cabin (Rear Seat Monitor, w/ expanded request: allow 2R see 1R) SYNC+_0231 Mobile Device Viewer
v3.8 | 11/25/21 | James Chen | Add 'F005110 Performance Shift Indicator' for P702MCA
v3.9 | 2021-12-07 | NiuChun | SYNC+_Z0262 change VSEM ID from F003417 to F005770 SYNC+_Z0044 change Feature Name from Auto Dim to Smooth Dimming Add 'F000400 Remote start (activate, climate, auto, last setting, seats and wheels, duration)' for U718 Add 'F004151 3-Way Splitgate' for U718 Add 'F002992 Auto Tow / Haul' for U718 Add 'F003870 Trailer Lights and Charging' for U718 Add 'F000147 Power Adjustable Mirrors' for U718 Add 'F001031 Sign Based Light Mode' for U718 Add 'F000166 Power Running Boards' for U718
v3.10 | 2021-12-08 | James Chen | Add following item for CDX747: SYNC+_Z1046 F000816 Programmable Electric Preconditioning and Charging (PEPC) SYNC+_Z1047 F000149 Mirror Dip / Tilt SYNC+_Z1012 F002430 Plug and Charge SYNC+_Z0288 F000178/D Perimeter Anti-Theft Alarm Remove following item for CDX747: SYNC+_Z0103 Power Running Boards (PRB) SYNC+_Z0203 Cargo Loading SYNC+_Z0211 Power running boards (auto, on, off) SYNC+_Z0079 F000090/C Hill Decent Control SYNC+_0145 随心拍Traveling Shooting SYNC+_0138 车机相册 IVI Picture Gallery SYNC+_0196 实时车况界面 IOD Information On Demand/Display SYNC+_0283 FNOC 1.0 Update following feature name: SYNC+_0122 '车辆状态和警示 Vehicle Health Alert and Status' --> '车辆警示与车辆状态 Vehicle Health Alert and Status(VH)' SYNC+_0196 '实时车况界面 IOD Information On Demand/Display' --> '电车实时车况界面 IOD Information On Demand/Display'
v4.0 | 2021-12-09 | WangPeng | Update CDX788 related information based on 00 Ford China (SYNC+) IVI Feature PDL Living Document CX788_v1.5_20211129.xlsx 01.CustomerFacing SYNC+_0196 IOD Information On Demand/Display modify N -> Y , add changeLevel C/O. SYNC+_0283 FNOC 1.0 add local FO Chen, Wei (W.) <WCHEN160@ford.com>, modify N -> Y, add changeLevel C/O. SYNC+_0284 FNOS add local FO Chen, Wei (W.) <WCHEN160@ford.com>, modify N -> Y, add changeLevel C/O. 03.BOF SYNC+_Z0210 Passenger Airbag modify N -> Y, add changeLevel C/O. SYNC+_Z0070 Auto Stop Start change loacl FO from Bush, Duane (D.R.) to Li, Yanzhi (Y.) <YLI380@ford.com>. SYNC+_Z0077 Engine Stop Start threshold modify N -> Y, add changeLevel C/O. SYNC+_Z1011 Blind_Spot_Assist add local FO Liu, Hongxin (H.) <HLIU162@ford.com>, modify N -> Y, add changeLevel New.
V4.1 | 2021-12-11 | Yang,Hanhan | 1.Add SW release version for P702MCA 2. Update the SW version for CX788 01.CustomerFacing SYNC+_0196 IOD Information On Demand/Display add release timing DCV0 SYNC+_0283 FNOC 1.0 add release timing DCV3 SYNC+_0284 FNOS add release timing DCV3 SYNC+_0210 Power Flow add release timing DCV Beta SYNC+_0025 Voice Recognition Systems add release timing DCV Beta 03.BOF SYNC+_Z0210 Passenger Airbag add release timing DCV Beta SYNC+_Z0077 Engine Stop Start threshold add release timing DCV Beta SYNC+_Z1011 Blind_Spot_Assist add release timing DCV Beta
V4.2 | 2021-12-16 | ZhangYing | Update U6xxMCA BOF (with VISM ID items) schedule 1. F003631 Base Park Aid move to DCV Beta1 2. F002930 Repa move to DCV Beta1 3. F002032 PPP move to DCV Beta1 4. F002370 digital owner manual 2.0 move to DCV Beta
V4.3 | 2021-12-16 | Niu Chun | Modify F003870 Trailer Lights and Charging,Change Level will be set as NEW for U718 Modify F001031 Sign Based Light Mode,Change Level will be set as NEW for U718 Modify F000166 Power Running Boards,Change Level will be set as NEW for U718 Udpate Global Feature Owner for U718
V4.4 | 2021-12-23 | Wang Peng | Update CDX788 related information based on 00 Ford China (SYNC+) IVI Feature PDL_Living Document_CX788_v1.6_20211221.xlsx 01.CustomerFacing 1. SYNC+_0196 IOD Information On Demand/Display modify Y -> N. 2. SYNC+_0011 FM/AM收音机 AM/FM Radio （Anteena Based天线接收） modify Y -> N （This state was omitted from the previous version and has not been modified). 03. EOF 1. SYNC+_Z0256 Power Folding Mirrors w & w/o autofold (RSD - Mirror Fold) modify N -> Y. change Global Feature Owner from Strzelczyk, Anthony (A.) to D, SelvaMuthu (D.) <dselva@ford.com>, change level : C/O, Release CX788 Version in GPDS : DCV beta. 2. Add a feature : SYNC+_Z1048 Power moonroof and shade, status is Y-1st, add Global Feature Owner A R, Kashyap (.) <akashya2@ford.com>, change level : New, Release CX788 Version in GPDS : DCV beta.
V4.5 | 2021-12-30 | ZhangYing | delay U6xxMCA some feature delivery date due to HMI sign off UI delay 1 month: 1> SYNC+_0266 3D car model: delivery date move to DCV1 2> SYNC+_0073 FAPA: delivery date move to DCV Beta1 3> SYNC+_0076 REPA: delivery date move to DCV0
V4.6 | 2022-01-07 | Wang Peng | Update CX788 related information based on 00 Ford China (SYNC+) IVI Feature PDL_Living Document_CX788_v1.7_20220107.xlsx 01.CustomerFacing 1. SYNC+_0123 保养及在线预约 OSB - Online Service Booking modify N -> On Hold 2. SYNC+_0156 舱内娱乐Cabin on live 2.0 Modify Y-study to N 3. SYNC+_Z0023 流量套餐app端流量查询购买 data plan query & order modify Y -> N 4. SYNC+_0296 4G/5G Entertainment Connectivity Subscription modify N -> Y, add local FO Zhang, Rui (R.) RZHANG63@ford.com, Release CX788 Version in GPDS : DCV2 5. rename SYNC+_Z0032 from CCS (Connectivity Connectivity Setting) to CCS (Customer Connectivity Setting) on customer facing sub table cross carline 6. change Product Owner for following 2 features from Chen, Wei to Hu, Lina (L.) LHU31@ford.com SYNC+_0283 FNOC SYNC+_0284 FNOS 7. SYNC+_0283 FNOC modify Y -> N 8. change feature description for SYNC+_0122 to VH collects diagnostic data from the vehicle and presents it to customer via mobile app OR IVI in the form of Vehicle Status, which displays the most up-to-date information such as Odometer, Fuel Level, Oil Life, Tire Pressure, Distance to empty, Vehicle Location etc. and Vehicle Health notification/alert with contextual information based on the vehicle’s current condition (such as MIL/WIL and DTCs). 9. change feature owner for SYNC+_0175 notification from Johnny Wang To Zhang, Xu (X.) <XZHAN304@ford.com> 03. EOF 1. SYNC+_Z0172 Rear climate fan(后排空调风速) modify Y->N 2. SYNC+_Z0173 Rear climate mode(后排空调模式) modify Y->N 3. SYNC+_Z0174 Rear climate temp(后排空调温度) modify Y->N 4. SYNC+_Z0232 Contained in SYNC+_Z0091, Mark N 5. SYNC+_Z0277 Contained in SYNC+_Z0091, Mark N 6. SYNC+_Z0278 Contained in SYNC+_Z0091, Mark N
V4.6.1 | 2022-01-10 | ZhangYing | Add U718 release timing and release template
V4.6.2 | 2022-01-13 | Zhou Jiajia | Update the SYNC+_Z0070/Z0103/Z0256 自动启停，电动踏板和后视镜折叠的setting项 FDL from HW Tier1 to Coreservice
V4.6.3 | 2022-01-14 | Wang Peng | Update CX788: 03. EOF 1. SYNC+_Z1011 Blind_Spot_Assist modify Y - > N, This feature has nothing to do with IVI。 2. SYNC+_Z1015 Cellular Remote Start / Stop (U6XX) modify Y -> N
V4.7 | 2022-01-19 | Deyin CHEN | Update CDX707: 1. Update the FDL for a bunch of features 2. Re-shcedule a bunch of overdue feautres
V4.7.1 | 2022-01-21 | Deyin CHEN | Update CDX707: 1. Change the SYNC+_Z1023 release version from DCV1 to DCV4
V4.7.2 | 2022-01-28 | Niu Chun | Update U718: add SYNC+_Z1051 to F004151 3-Way Splitgate Feature ID of column for U718 add SYNC+_Z1049 to F002992 Auto Tow / Haul Feature ID of column for U718 add SYNC+_Z1050 to F003870 Trailer Lights and Charging Feature ID of column for U718 add SYNC+_Z1052 to F000147 Power Adjustable Mirrors Feature ID of column for U718 add SYNC+_Z1053 to F001031 Sign Based Light Mode Feature ID of column for U718 add SYNC+_Z0103 to F000166 Power Running Boards Feature ID of column for U718 Modify SYNC+_0010 AR 导航 AR Navigation,Change Level will be set as C/O for U718 Modify SYNC+_0074 倒车制动辅助 Reverse Brake Assist (RBA),Change Level will be set as C/O for U718 Modify SYNC+_0170 车辆迎宾模式 Lincoln Embrace / Ford Welcome &Farewell,Change Level will be set as C/O for U718 Modify SYNC+_Z0293 Power Liftgate Soft switch will be set as N for U718 add SYNC+_Z1042 to F005110 Performance Shift Indicator Feature ID of column for U718 Modify SYNC+_0228 MySeatSpace will be set as N for U718 Modify SYNC+_0115 Project Aspire_Ultimate Remote Control will be set as N for U718 Modify SYNC+_Z1021 Augmented Reality will be set as N for U718 Modify SYNC+_0010 AR 导航 AR Navigation will be set as N for U718 Modify SYNC+_Z0072 Climate Menu will be set as N for U718 Modify SYNC+_Z0073 Climate Mode Selection will be set as N for U718 Modify SYNC+_Z0074 Climate Rear Control will be set as N for U718 Modify SYNC+_Z0077 Engine Stop Start threshold will be set as Y for U718 Modify SYNC+_Z0085 Lincoln Park Assist Shortcut key will be set as Y for U718 Modify SYNC+_0094 多种摄像头 Multi Camera - CHMSL/AUX Camera/Rock Crawl will be set as N for U718 Modify SYNC+_0092 前视摄像头 Off Road Front View Camera will be set as N for U718 Modify SYNC+_0093 后视摄像头 Rear Camera On Demand will be set as N for U718 Modify SYNC+_0095 数字倒车影像 Rearview Camera - RVC (Digital) will be set as N for U718 Modify SYNC+_0110 舱内娱乐Cabin On-live 1.0 will be set as Y for U718 Modify SYNC+_0123 保养及在线预约 OSB - Online Service Booking will be set as N for U718 Modify SYNC+_0157 车机应用商店Apps Anywhere(SYNC+) will be set as Y-Study for U718 Modify SYNC+_0162 家车互联Project Aspire_General IOT (Smart Home)_CN ( Home to Vehicle) will be set as N for U718 Modify SYNC+_0273 Remote Window Control / Window Status (China) will be set as N for U718
V4.7.3 | 2022-02-16 | Deyin CHEN | Update CDX707: 1. SYNC+_Z0153 Location Service （仪表指南针，etc.） update the FDL 2. SYNC+_0110 舱内娱乐Cabin On-live 1.0, change the release version to DCV5 3. SYNC+_0156 舱内娱乐Cabin on live 2.0 change the releasse version to R09
V4.7.4 | 2022-02-17 | Wang Peng | Update CX788 related information based on 00 Ford China (SYNC+) IVI Feature PDL_Living Document_CX788_v1.8_20220125.xlsx 01.Customer Facing SYNC+_0106 手机钥匙Phone as key(PaaK) modify Y->N
V4.7.5 | 2022-02-20 | Yang Hanhan | Update CX788 release time Customer facing: change SYNC+_0010 AR 导航 AR Navigation release version from DCV0 to DCV2 change SYNC+_0267 AR HUD release version from DCV0 to DCV2 DCV Alpha to DCV2 change SYNC+_0223 多模块空中升级 Multi Module OTA (MMOTA) release version from DCVBeta to DCV1 change SYNC+_0210 动力流动画显示Power Flow release version from DCVBeta to DCVBeta1 change SYNC+_0266 Lancher - 3D Car Model with vehicle controls release version from DCVBeta1 to DCV0 change SYNC+_Z0032 CCS (Customer Connectivity Setting) release version from DCV Beta to DCV1 change SYNC+_0126 升级版紧急救援/服务 eCall release version from DCV Beta to DCV Beta1 change SYNC+_0170 车辆迎宾模式 Lincoln Embrace / Ford Welcome &Farewell release version from DCV Alpha to DCV1 Basic Function change SYNC+_Z1023 ADAS Map release version from DCV1 to R01 依赖于实车联调 change SYNC+_Z0033 Provisioning release version from DCV Beta to R01 依赖于实车联调 change SYNC+_Z0284 Funtion Safety release version from DCV Alpha to DCV1 change SYNC+_Z0002 SYNC+_Z0005 SYNC+_Z0007 SYNC+_Z0120 SYNC+_Z0122 SYNC+_Z0128 SYNC+_Z0155 release version to DCV Beta1 change SYNC+_Z0003 SYNC+_Z0014 SYNC+_Z0035 SYNC+_Z0152 SYNC+_Z0199 release version to DCV0 change SYNC+_Z0058 SYNC+_Z0111 SYNC+_0194 release version to DCV1 change SYNC+_0207 release version to DCV2 change SYNC+_Z0017 SYNC+_Z0041 SYNC+_Z0043 release version to DCV1 change SYNC+_Z0037 release version to DCV3 BOF: change SYNC+_Z0092 release version to DCV Beta1 change SYNC+_Z1007 SYNC+_Z1008 SYNC+_Z0289 release version to DCV0 change SYNC+_0089 SYNC+_0090 SYNC+_0091 SYNC+_0093 SYNC+_0095 SYNC+_0098 release version to DCV1 change SYNC+_Z0044 release version to DCV0
V4.8 | 2022-02-22 | Gaoling | Create First draft of CX821 's Customer facing feature list
V4.8.1 | 2022-02-22 | Deyin CHEN | Update CDX707 FIP: 1. Change SYNC+_0205 release plan from DCV3 to DCV4 2. Change SYNC+_Z0240 release plan from DCV3 to DCV4
V4.8.2 | 2022-02-22 | NiuChun | Update U718: Modify SYNC+_Z0084 Lincoln Drive Assist Shortcut key will be set as N for U718 Modify SYNC+_Z0088 Multi-Contoured Seats(Massage Seats) will be set as N for U718 Modify SYNC+_Z0092 Rear Park Aid will be set as N for U718 Modify SYNC+_0114 远程空调控制 Remote Climate Control (RCC) via FordPass/Lincoln Way will be set as N for U718 Modify SYNC+_0166 基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP) will be set as N for U718 Modify SYNC+_Z0187 Lock Setting Change Description of column for U718 Modify SYNC+_0110 舱内娱乐Cabin On-live 1.0 Change Level of column, it will be set C/O for U718 Modify SYNC+_Z0088 Multi-Contoured Seats(Massage Seats) will be set as Y for U718 Modify SYNC+_Z0078 Grade Assits Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0080 Hill start assist Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0095 Tow Haul Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0098 Trailer Sway Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0202 Aux Heater Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0205 Easy access height Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0208 Park Heater Change Level of column, it will be set NEW for U718 Modify SYNC+_Z1027 AWD / 4WD: Torque Transfer for Handling & Traction Change Level of column, it will be set NEW for U718 Modify SYNC+_Z1036 Trailer Light Check (FNV3) Change Level of column, it will be set NEW for U718 Modify SYNC+_Z1037 Auto Electric Park Brake (AEPB) aka AEPB or Park Hold Change Level of column, it will be set NEW for U718 Modify SYNC+_Z1039 Remote startChange Level of column, it will be set NEW for U718 Modify SYNC+_Z0087 Lincoln Seats shortcut key Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0172 Rear climate fan Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0173 Rear climate mode Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0174 Rear climate temp Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0186 多色氛围灯 Low Beam Switch Change Level of column, it will be set NEW for U718 Modify SYNC+_Z1019 Cellular Remote Start w/Extend Remote Start FNV3 Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0256 Power Folding Mirrors w & w/o autofold (RSD - Mirror Fold) Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0262 Integrated Sentinel(Video-Based Vehicle Monitoring) Change Level of column, it will be set NEW for U718 Modify SYNC+_Z1010 Fob Free Entry and Ignition (NFC) Change Level of column, it will be set N for U718 Modify SYNC+_Z0291 Rear Fog Lights Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0101 Ambient Lighting 128 Color Change Level of column, it will be set Minor for U718 Modify SYNC+_Z0079 Hill Decent Control Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0287 First Row Seat Position Control Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0292 Second Row Seat Position Control Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0083 Lincoln Camera Shortcut key Change Level of column, it will be set NEW for U718 Modify SYNC+_Z0246 AEIS (Auto Engine Idle Shutdown) Change Level of column, it will be set Major for U718
V4.8.3 | 2022-02-23 | ZhangYing | Update U718 delivery date
V4.8.4 | 2022-02-25 | ZhangYing | Update U718 delivery version to Beat SYNC+_0014; SYNC+_0021; SYNC+_0122; SYNC+_0126; SYNC+_0132;SYNC+_0223; SYNC+_Z0019; SYNC+_Z0081; SYNC+_0074; SYNC+_0089; SYNC+_0090; SYNC+_0098; SYNC+_Z0085; SYNC+_Z0167; SYNC+_Z0168; SYNC+_Z0247; SYNC+_Z0289;
V4.8.5 | 2022-03-02 | Wang Peng | Update the status of CX788 features 01. Customer Facing SYNC+_0123 保养及在线预约 OSB - Online Service Booking modify -> N SYNC+_0162 家车互联Proj ect Aspire_General IOT (Smart Home)_CN ( Home to Vehicle) modify -> N SYNC+_0273 Remote Window Control / Window Status (China) modify -> N 02.Basic Function SYNC+_Z1024 bluetooth Music Release CX788 Version in GPDS : DCV Beta, add local FO Xu, Xin XXU91@ford.com 03. BOF SYNC+_Z1026 Oil Minder Release CX788 Version in GPDS : DCV Beta, add local FO Pang, Larry PPANG5@ford.com
V4.8.6 | 2022-03-04 | Niu Chun | U718： Modify SYNC+_Z0232/SYNC+_Z0277/SYNC+_Z0278/SYNC+_Z1051/SYNC+_Z1049/SYNC+_Z1050/SYNC+_Z1052/SYNC+_Z1053/SYNC+_Z0103 Feature Development Leader of column Add Steering Column / Pedal Position Control Modify SYNC+_Z1010 Fob Free Entry and Ignition (NFC) Change Level of column, it will be set Minor
V4.8.7 | 2022-03-09 | ZhangYing | update U611MCA feature delivery date 1. SYNC+_0073 FAPA: DCV Beta1 --> DCV1 2. SYNC+_0076 REPA: DCV0 --> DCV1 3. SYNC+_Z0002 A2B: DCV Beta --> DCV1 4. SYNC+_Z0003 ANC tuning: DCV Beta1 --> DCV2
V4.8.8 | 2022-03-18 | ZhangYing | update version name: DCV Alpha --> DCV Alpha1; DCV Beta --> DCV Alpha2; DCV Beta1 --> DCV Beta; DCV0 --> DCV Beta1; DCV1 --> DCV0; DCV2 --> DCV1; DCV3 --> DCV2 update U6xxMCA feature delivery version 1. SYNC+_0073 FAPA: DCV Beta1 --> DC0 2. SYNC+_0076 REPA: DCV0 --> DCV0 3. SYNC+_Z0002 A2B: DCV Beta --> DCV0 4. SYNC+_Z0003 ANC tuning: DCV Beta1 --> DCV1 5. SYNC+_0223 MMOTA DCV beta --> DCV1 6. SYNC+_Z0006 Engine Sound Enhancement (ESE) DCV Beta1 --> DCV0 7. SYNC+_Z0010 Noise cancellation for Baidu VR DCV Beta1 --> DCV1 8. SYNC+_Z0199 ANC DCV Beta --> DCV0
V4.8.9 | 2022-03-29 | NiuChun | U718： add Feature ID SYNC+_Z1054 to feature name Steering Column / Pedal Position Control Modify SYNC+_Z1053 Sign Based Light Mode Change Level of column, it will be set N Modify SYNC+_Z1050 Trailer Lights and Charging Change Level of column, it will be set N Modify SYNC+_Z0075 Cruise Control Setting VSEM ID of column,it wiil be add F000579 Modify SYNC+_0103 我的钥匙MyKey VSEM ID of column, it will be set F000173 Modify SYNC+_Z1010 Fob Free Entry and Ignition (NFC) Change Level of column, it will be set N Modify SYNC+_Z0217 Wipers (courtesy, rain, reverse) VSEM ID of column, it will be set F000065/F000066/F000067 Modify SYNC+_Z1027 AWD / 4WD: Torque Transfer for Handling & Traction Change Level of column, it will be set N Modify SYNC+_Z0213 Remote start (activate, climate, auto, last setting, seats and wheels, duration) Change Level of column, it will be set C/O U6XX: U625 03BOF Sheet modify SYNC+_Z0185 单色氛围灯 single color ambient lighting set column of U625 MCA as Y modify SYNC+_Z0186 多色氛围灯 multi color ambient lighting set column of U625 MCA as Y modify SYNC+_Z1008 Driver_Information_Display_Control set column of U625 MCA as N U625 01 Customer Facing Sheet modify SYNC+_0011 FM/AM收音机 AM/FM Radio （Anteena Based天线接收） set column of U611 MCA as N, set column of U625 MCA as N modify SYNC+_0138 车机相册 IVI Picture Gallery set column of U611 MCA as N, set column of U625 MCA as N modify SYNC+_0166 基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP) set column of U611 MCA as N, set column of U625 MCA as N modify SYNC+_0192 联合驾趣 Co-Driver set column of U611 MCA as N modify SYNC+_0283 FNOC 1.0 set column of U611 MCA as N, set column of U625 MCA as N modify SYNC+_0157 车机应用商店Apps Anywhere(SYNC+) set column of U611 MCA as Y, set column of U625 MCA as Y modify SYNC+_0196 实时车况界面 IOD Information On Demand/Display set column of Phase5 as Y,set column of U611 MCA as Y, set column of U625 MCA as Y
| 2022-04-07 | ZhangYing | update U6xxMCA delivery version: 1. SYNC+_0136 舒享时分Relax/自由秘境At Ease change DCV Alpha2 --> DCV2 2. SYNC+_0192 联合驾趣 Co-Driver change DCV1 --> DCV2 3. SYNC+_0137 个人时光 Smart Scene - Personal Enjoyment DCV1 --> DCV2 4. SYNC+_0152 时空秘信Surprise/Secret message DCV1 --> DCV2 5. SYNC+_0042 语音助手1.5/2.0 VPA 1.5/2.0 (融合贯通生态的智能化的语音助手） DCV Beta --> DCV2 6. SYNC+_0118 车机端电子版用户手册 E-Manual 2.0 DCV Alpha2 --> DCV Beta1 7. SYNC+_0077 5G 车路协同 5G V2V DCV2 --> R06 update U718 delivery version: 1. SYNC+_0077 5G 车路协同 5G V2V DCV3 --> R05
V4.9.1 | 2022-04-13 | NiuChun | U611&U625 Modify SYNC+_Z0101 Ambient Lighting 128 Color Change Level of column, it will be set N Modify SYNC+_Z0185 单色氛围灯 single color ambient lighting Change Level of column, it will be set N Modify SYNC+_Z0186 multi color ambient lighting Change Level of column, it will be set Y U718 Modify SYNC+_Z0101 Ambient Lighting 128 Color Change Level of column, it will be set N Modify SYNC+_Z0186 multi color ambient lighting Change Level, it will be set C/O
V4.9.2 | 2022-04-26 | ZhangYing | update U6xxMCA feature delivery version 1. SYNC+_Z0020 Carrier DCV Beta --> DCV Beta1 2. SYNC+_0091 泊车辅助显示 Rear/Front/Side Visual Parking Aid DCV Beta --> DCV Beta1 3. SYNC+_Z0002 A2B Functional DCV0 --> DCV1 4. SYNC+_Z0003 Active Noise Cancellationg (ANC) Tuning DCV1 --> DCV3 5. SYNC+_Z0006 Engine Sound Enhancement (ESE) DCV0 --> DCV1 6. SYNC+_Z0008 Lincoln more speakers audio & ANC tuning DCV1 --> DCV3 7. SYNC+_Z0010 Noise cancellation for Baidu VR DCV1 --> DCV3 8. SYNC+_Z0199 Active Noise Cancellation DCV0 --> DCV1 9. SYNC+_Z0283 部分界面中英文显示 DCV Alpha --> TBD 10. SYNC+_Z0284 Funtion Safety DCV Alpha --> DCV0 11. SYNC+_Z0038 Embedded Modem Reset/Master reset DCV Alpha --> DCV0 12. SYNC+_0136 舒享时分Relax/自由秘境At Ease DCV2 --> DCV3 13. SYNC+_0137 个人时光 Smart Scene - Personal Enjoyment DCV2 --> DCV3 14. SYNC+_0139 客人模式Smart Scene - Guest Mode DCV1 --> DCV3 15. SYNC+_0140 智慧指令 Smart Scene - Smart Order DCV1 --> DCV3 16. SYNC+_0152 时空秘信Surprise/Secret message DCV2 --> DCV3 17. SYNC+_0118 车机端电子版用户手册 E-Manual 2.0 DCV Beta1 --> TBD 18. SYNC+_Z1023 ADAS Map DCV Alpha2 --> DCV1
V4.9.3 | 2022-05-10 | ZhangYing | update U6xxMCA timing 1. SYNC+_Z0092 Rear Park Aid DCV Alpha2 --> DCV Beta1 2. SYNC+_0091 泊车辅助显示 Rear/Front/Side Visual Parking Aid DCV Beta1 --> DCV Beta
V4.9.4 | 2022-05-17 | NiuChun | U611&U625 1.set SYNC+_0018 as N due to "SYNC+_0018" Merged to “SYNC+_0017" 2.set SYNC+_0161 as N due to "SYNC+_0161" Merged to "SYNC+_0160" 3.set SYNC+_0272 Lidget/Fidget/Widget 2.0 as Y, and set SYNC+_0289 Lidget/Fidget/Widget 3.0 as TBD 4.set SYNC+_0281 Smart Wellness 1.0 as N due to Smart wellness drop off from SYNC+3.0 rescope. 5.move SYNC+_0022 底特律之音 from 'customer facing' to 'basic function'
V4.9.5 | 2022-05-17 | ZhangYing | Update U6xxMCA timing 1. SYNC+_Z0126 DCV Alpha2 --> DCV0 Update U6xxMCA FDL 1. F000171 Classic Memory add FDL as Core_Service_Supplier 2. SYNC+_0289 Lidget/Fidget/Widget 3.0 add FDL as Inhouse

## 01Customer Facing
Feature ID | VSEM ID | Component/s | Product Suite | Feature Group | Feature Name | Feature_Description | Lead Team | Local Feature Owner | Global Feature Owner | Dev Spec | Feature Development Leader | HW_Tier 1 | SW_Tier 1 | Ford IVI In-House | Core Service Provider | Phase5 | CDX707 | Release Version in GPDS | Original Release Date to REC | Original Release Date to FO/CAF(2weeks) | CDX747 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | CDX747 Release Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | CX788 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release CX788 Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | U611 MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner | U611 HMI Group | U611 Release Version in GPDS | U625 MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner | U625 HMI Group | U625 Release Version in GPDS | P702MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release P702MCA Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | U718 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release U718 Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | CX821 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release CX821 Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | 1st - phase # | Pre-DV Req | HMI Group | Target Versio
SYNC+_0001 | F000218/Q | Map&Navigation | A# Navigation 地图导航 | 1# Navigation - Basic Function 基础导航功能 | 地图基础版（见《IOV-地图功能list) Foundamental version of Map | 见《IOV-地图功能list)。 支持地图包更新MOTA。 POI检索、地点收藏 POI search & store destinations 3D地图 3D Map 首页地图 Launcher Map 地图显示的夜间/白天模式 Night/Day Mode 实时交通播报 Real-time Traffic Broadcast 惯性导航 Inertial Navigation 超速提醒 Reminder of over speed 路线雷达 radar detection in routes 限行提醒 Reminder of traffic control rules | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> | Deaibes, William (W.) | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 20% | 80% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Yao, Tristan (Lan) <LYAO17@ford.com> | Deaibes, William (W.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_0011 | F000349 | Radio | B# Multimedia 多媒体 | 1# Radio 电台/收音机 | FM/AM收音机 AM/FM Radio （Anteena Based天线接收） | 9/17:CDX747，CX788 AM 不需要,FM 需要 收音机 radio-基本控制(上一个/下一个) foundamental control 收音机 radio-输入频段 channel input 收音机 radio-启动/停止收音机 turn on/off 收音机 radio-手动调台 manual tuning 收音机 radio-收藏列表 collections； Baidu: 自带的随声听App音乐是具有收藏列表的。Baidu需要design 收藏列表的HMI，配合Tier1实现该功能。 收音机 radio-更新电台列表(扫描及更新）update channels 收音机 radio-FM2 相关的菜单及功能 | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Murry, Tyrone (T.D.) | AMFM Tuner of Standalone AHU SPSS v1.8.pdf Auto Store_AM FM SPSS.pdf CD539C519D568_HMI_收音机_V1.0_20180912.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | N |  |  |  | N | N |  |  |  | - | - | - | N | Minor | phase 5全系取消 | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Murry, Tyrone (T.D.) | DCV Beta | 2022-03-12 | 2022-03-19 | N | N | N | N | N | N | N | N | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | - | DCV Alpha2 | N | N | N | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Nowack, Frank (.) <fnowack2@ford.com> | - |  |  | N | N |  |  | Murry, Tyrone (T.D.) |  | - |  | N | N |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Murry, Tyrone (T.D.) |  | - |  | Phase 1 | Yes | Group A | -
SYNC+_0013 | F000345/K | BT Phone | B# Multimedia 多媒体 | 2# Bluetooh Phone 蓝牙电话 | 蓝牙电话 Bluetooh Phone | 接听挂断；通话记录 records；拨号 dial；通讯录搜索；通讯录 contacts；同步通讯录和通话记录 sync contacts& records；请勿打扰 DO NOT IDSTURB | EESE | Xu, Amy (X.) <xyafei@ford.com> | Balakrishnan, Sabarish (S.) | BT Connectivity APIM SPSS v3.0 Feb 14, 2019.pdf BT Connectivity APIM Imp Guide v3.0 Feb 14, 2019.xlsx Phase5 Bt多路电话--PRD.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Xu, Amy (X.) <xyafei@ford.com> | Balakrishnan, Sabarish (S.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  | Cartwright, Timothy (T.) |  | DCV Beta |  | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> | Cartwright, Timothy (T.) |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_0014 |  | Music | B# Multimedia 多媒体 | 3# Music 音乐 | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) | 增加一个蓝牙模块，用来链接蓝牙耳机。 场景： 主驾听音乐（vehicle speaker); 副驾可连接自己的蓝牙耳机， 在双开模式下选择不同音乐资源来听 （支持在线音乐合本地音乐；不支持FM/AM;和蓝牙音乐） | EESE | Xu, Amy (X.) <xyafei@ford.com> |  | Phase5 副屏蓝牙--PRD.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Xu, Amy (X.) <xyafei@ford.com> |  | - | - | - | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - | N | N | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | DCV Beta |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_0015 | F000379/G | Music | B# Multimedia 多媒体 | 3# Music 音乐 | 本地音乐-MTP音乐 MTP music/USB音乐 USB music/蓝牙音乐 BT music | MTP (Media Tranfer Protocol)，可以本地外接音乐设备如iPod, 手机 | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Ahmed, Basheer (B.) | Media Player APIM SPSS v1.15 Jul 1, 2017.pdf Media Player APIM Imp Guide v1.15.1 Jul 1, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Ahmed, Basheer (B.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  | Ahmed, Basheer (B.) |  | DCV Beta |  | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Ahmed, Basheer (B.) |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_0016 |  | Music | B# Multimedia 多媒体 | 3# Music 音乐 | 随心听- Ximalaya 2.0 | 允许用户登录自己账户 Suixinting: Ximalaya allow user login and enjoy more paid audio resources | ECDX | Shi, Stella (J.) <jshi32@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Shi, Stella (J.) <jshi32@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Shi, Stella (J.) <jshi32@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_0017 |  | Music | B# Multimedia 多媒体 | 3# Music 音乐 | 随心听- 音乐/新闻/有声书 (QQ 音乐-支持QQ 音乐账号登陆；喜马拉雅免费资源集成） | 可以基于账号及喜好记忆进行主动推荐 Audio book/News/Music recommended according to account & preference | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Online Music APIM PRD v1.0 Feb 8, 2021.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_0018 |  | Music | B# Multimedia 多媒体 | 3# Music 音乐 | 随心听-QQ 音乐2.0 Suixinting: QQ Music 2.0 | 1.随心听VIP试听功能。 2.随心听歌曲切换音质。 3.同步手机端QQ音乐的歌单数据（默认自带歌单、自创建歌单、收藏的歌单）。 4.随心听增加歌手入口以及歌手搜索功能。 5. 登录页toast提示使用VIP账号登录，登录后显示账号是否是绿钻账号。 | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Online Music APIM PRD v1.0 Feb 8, 2021.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group E | DCV Alpha2 | N | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group E | DCV Alpha2 | N | Minor | Adapt new scree size 12' | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | DCV Beta |  | Phase 2 | Yes | Group A | DCV Beta
SYNC+_0019 | F000379/G | Music | B# Multimedia 多媒体 | 4# Video 视频 | USB视频播放 Video- USB video | 需要支持主流视频格式 | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Media Player APIM SPSS v1.15 Jul 1, 2017.pdf Media Player APIM Imp Guide v1.15.1 Jul 1, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  | Ahmed, Basheer (B.) |  | DCV Beta |  | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Ahmed, Basheer (B.) |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_0020 |  | Video | B# Multimedia 多媒体 | 4# Video 视频 | 爱奇艺 (在线视频APP) Video - Streaming video Iqiyi |  | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Video Player APIM PRD v1.0 Feb 8, 2021.pdf Video Player APIM PRD v1.0 Feb 8, 2021.pdf | SW_Tier1 | 20% | 80% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | DCV Beta |  | Phase 1 | No | Group A | DCV Beta
SYNC+_0021 |  | DLNA | B# Multimedia 多媒体 | 4# Video 视频 | 视频、音乐、图片DLNA投屏到车机显示器区分主副驾/Video Playback and Video and Photo project to Display(Driver and Passenger) via DLNA |  | EESE | 6_目前funding只cover707,Jia, Elaine (T.) <tjia2@ford.com> |  | DLNA投屏V0.2--PRD.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV0 | 2021-10-20 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Jia, Elaine (T.) <tjia2@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  |  |  | Group A | DCV Alpha2 | Y | C/O |  | 0 |  | Group A | DCV Alpha2 | Y | C/O |  | 6_目前funding只cover707,Jia, Elaine (T.) <tjia2@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | 6_目前funding只cover707,Jia, Elaine (T.) <tjia2@ford.com> |  |  | DCV Beta |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_0023 |  | Audio | B# Multimedia 多媒体 | 5# Sound & Effect 音效 | 电动车独有音效 EV Unique Chime (CDX727 lead) | Lead by CD727. Details need to be updated | EESE | Li Alvin (LLI156@ford.com) |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Li Alvin (LLI156@ford.com) |  | - | - | - | N | N |  | 0 |  | N/A | - | N | N |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 4 | No |  | DCV0
SYNC+_0192 |  | Multi-Screen Interaction | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 联合驾趣 Co-Driver | 副驾区域显示车辆/行驶状态/可以发起POI 搜索， 设置导航路线. Lead CD542 27'L touch screen | HMI | Li, Qiyang (Q.) <QLI111@ford.com> |  |  | Ford_InHouse | 0% | 0% | 90% | 10% | Y | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Lee, Grace (G.) <glee51@ford.com>Liu, Luisa |  | - | - | - | N | N |  | 0 |  | N/A | DCV3 | N | New |  | Li, Qiyang (Q.) <QLI111@ford.com> |  | Group C | DCV2 | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 4 | No |  | DCV2
SYNC+_0002 |  | Map&Navigation | A# Navigation 地图导航 | 1# Navigation - Basic Function 基础导航功能 | 开始导航倒计时/导航结束卡片 Starting/Ending Count Down |  | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV Alpha2 | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV1 |  |  | Y | C/O |  |  |  |  | DCV1 |  | Y | C/O |  |  |  |  | DCV1 |  | Phase 2 | No | Group A | DCV1
SYNC+_0003 |  | Map&Navigation | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 个性化底图-4S店POI显示 4S Dealer POI on Map | 福特品牌显示福特标，林肯品牌显示林肯标，野马显示野马标 | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | Minor | HMI UIUE change | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV0 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV0 | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV1 |  |  | Y | C/O |  |  |  |  | DCV1 |  | Y | C/O |  |  |  |  | DCV1 |  | Phase 2 | No | Group A | DCV1
SYNC+_0004 | F003451 | Map&Navigation | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 本地危险事件上报及播报 LHI (Local Hazard Information) | 危险事件上报及播报 | ECDX | Li, Yifei (Y.) <nli26@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV Beta2 | 2021-09-15 | - | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | Minor | HMI UIUE change | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Yifei (Y.) <nli26@ford.com> |  | Group E | DCV0 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Yifei (Y.) <nli26@ford.com> |  | Group E | DCV0 | Y | C/O |  | Li, Yifei (Y.) <nli26@ford.com> |  | DCV1 |  |  | Y | C/O |  |  |  |  | DCV1 |  | Y | C/O |  |  |  |  | DCV1 |  | Phase 2 | No | Group A | DCV1
SYNC+_0006 |  | Map&Navigation | A# Navigation 地图导航 | 3# Navigation - Team Travel 组队出行 | 组队出行 Team Travel | 分享地址，支持Ford/Lincoln 车型间 语音对讲 | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | Minor | HMI UIUE change | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV0 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV0 | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV1 |  |  | Y | C/O |  |  |  |  | DCV1 |  | Y | C/O |  |  |  |  | DCV1 |  | Phase 1 | No | Group A | DCV1
SYNC+_0007 |  | Map&Navigation | A# Navigation 地图导航 | 4# POI Sharing/Receiving 地址分享 地址分享 | 微信地址分享 WeChat Send To Car | 微信中收到的地址可以长按选择百度地图，地址会同步给相同百度地图账号的车机端。首次需微信扫描车机二维码，关联账号 （又被叫做：微信互联） | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | Minor | HMI UIUE change | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV0 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV0 | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV1 |  |  | Y | C/O |  |  |  |  | DCV1 |  | Y | C/O |  |  |  |  | DCV1 |  | Phase 2 | No | Group A | DCV1
SYNC+_0008 |  | Map&Navigation | A# Navigation 地图导航 | 4# POI Sharing/Receiving 地址分享 地址分享 | 福特派/林肯之道地址分享 FordPass/LincolnWay Send to car | Send to car--把用户在FordPass 内置的地图查询的POI发送到车机 Send POI from smartphone APP to vehicle | ECDX | Shi, Stella (J.) <jshi32@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV Beta2 | 2021-09-15 | - | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | Minor | HMI UIUE change | Shi, Stella (J.) <jshi32@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  | Group E | DCV0 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  | Group E | DCV0 | Y | C/O |  | Shi, Stella (J.) <jshi32@ford.com> |  | DCV1 |  |  | Y | C/O |  |  |  |  | DCV1 |  | Y | C/O |  |  |  |  | DCV1 |  | Phase 1 | No | Group A | DCV1
SYNC+_0010 |  | AR Navigation | A# Navigation 地图导航 | 5# AR Navigation AR 导航 | AR 导航 AR Navigation | AR/专业地图切换AR/2D/Normal View Switch 终点目的地Destination Hint 道路吸附指引（主动）Road Guidance Arrow AR导航自动切换路线Road Guidance Arrow 语音指令Road Guidance Arrow 车道线偏离提醒Road Guidance Arrow 全览小地图Minimap overview 交通标志物识别TSR（Traffic Sign Recognition） | EESE | Ding, Sunny (X.) <XDING13@ford.com> |  |  | SW_Tier1 | 30% | 70% | 0% | 0% | Y | Y | R00 | 2022-05-18 | 2022-06-01 | Y | C/O |  |  |  | R00 | 2023-04-12 | 2023-04-29 | Y | Major | AR Nav need display in AR HUD. | Ding, Sunny (X.) <XDING13@ford.com> |  | DCV2 | 2022-06-10 | 2022-06-23 | N | N |  | Yu, Diven (D.W.) <dyu12@ford.com> |  | N/A | - | N | N |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | DCV0 |  | Phase 4 | Yes | Group A | DCV0
SYNC+_0012 |  | Online Radio | B# Multimedia 多媒体 | 1# Radio 电台/收音机 | 在线收音机/电台 Online Radio 资源提供方：蜻蜓FM | 资源能力提升. 资源涵盖不受传统radio 的地域限制。支持节目名称搜索，和收藏。 资源提供方：蜻蜓FM。 取决于电台是否做了online radio (有单独的license, 涵盖在phase 4 license 里面) Enhanced Online Radio (resource: 蜻蜓FM - 公版). with more radio programs without geograph constrains. Support voice command of "open online Radio" " Previouse one" " Next one" " Save". Availible for Phase 4 programs. Currently booked on CD542;U554;U725:P702;CX727. Other programs will need to book application cost if have display size differences. Attention: Keep pay attention to customer feedback and see opportunity of replace Traditional FM/AM using it. Things been called out by team - Data Consumption & Support 流量影响 - Online Radio's Resources & UE Improvement | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Online Radio APIM PRD v1.0 Feb 8, 2021.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  |  |  |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_0109 |  | DMS Warning | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | IVI 驾驶员状态监控和报警 IVI Driver Status Monitor & Alert (Fatigue, Distraction, Dangers Behaviour) | Lead by CD542. Base on IVI IR Camera. 有相应的声音和IVI Display提醒 跟DAT 域的DSMC 不同。 | EESE | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  | FaceID with DSMC Function Specification_V8 _20201215.pdf | SW_Tier1 | 20% | 80% | 0% | 0% | Y | N |  |  |  | N | N |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | N | N | N | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  | - | - | - | N | N |  | 6_目前funding concerns |  | N/A | - | N | N |  | Xu, Amy (X.) <xyafei@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | Y - Study | N |  | 6_目前funding concerns(no FO) |  |  | - |  | Phase 4 | No | Group B | -
SYNC+_0196 |  | Multi-Screen Interaction | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 实时车况界面 IOD Information On Demand/Display | 常规cluster 上面显示的信息 (车辆状况，油耗，胎压，里程， 我的驾驶怎么样？等等）输出至IVI界面，利用IVI Display 大屏的优势做了更直观的见面显示和相应的人机交互（例如下拉菜单）等更新。 Lead:CDX707 | EESE | 3_No yet China FO assign |  | Fuel Economy SPSS v1.1 January 31, 2019 Fuel Economy APIM Imp Guide v1.1 January 31, 2019 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | - | - | - | N | N |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | N | N | N | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | - | - | Y | Y | Y | Y | Y | Y | Y | Y | N |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 4 | No | Group B | -
SYNC+_0115 | F003071 | Cabin Remote Controller | G# Remote Control 远程控制 | 2# In Cabin Remote Controller (Phone) 座舱内手机遥控器 | 座舱内手机遥控 Project Aspire_Ultimate Remote Control | URC as operate interface to enable My Seat Space, from CDX747,and C/O to U718 Benfit: - Provides a space which a passenger feels in control and can enjoy their time in the vehicle - Provide a centralized way for a passenger to make their space confortable for them without disturbing others in the vehicle - Provide freedom for the driver/1R passenger of being the constant caretaker for the rest of the vehicle - alternative to myseatspace or multi-zone voice control or second row screen which are not in 707's assumption | ECDX | 2_Security checking, No FO/TL in China | Reed, Gregory (G.D.) |  | SW_Tier1 | 20% | 80% | 0% | 0% | Y-1st | N | - | - | - | Y-1st | New |  |  |  | DCV2 | 2023-01-24 | - | N | N | N | Shawn, Lin | Reed, Gregory (G.D.) | - | - | - | N | N |  | 2_Security checking, No FO/TL in China |  | N/A | - | N | N |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  | Thabet, Safwan (S.A.) |  | - |  | N | N |  |  | Thabet, Safwan (S.A.) |  | DCV0 |  | Phase 5 | No | Group C | DCV Beta
SYNC+_0042 |  | VPA | C# Intelligent Digital Assitant 智能数字助手 | 5# VPA 形象化语音助手 | 语音助手1.5/2.0 VPA 1.5/2.0 (融合贯通生态的智能化的语音助手） | Include baidu 小程序. V1.5 - 形象是2D的 (首先于phase 4 车型的系统能力限制）。 V2.0 - 形象是3D的, 适用于Phase 5的车型。CNECDMPORT-171 Leading Intelligent skills ( 小度助手/百度语音最新版能力- 具体内容规划参照Product Owner-20201204 add. Plus VPA2.0 or 3.0 leading by Product Owner Chiu, Lulu Support in cabin vehicle control (ideally all), and all IVI software contents e.g navigation, open an app, user manual inquiry, search & play multimedia contents (music, audio book, video, etc). .facilitate conversation for relaxzation (joking, wikipidia, story, lite games) .Have visual character to express emotional elements (thinking, happy, listening) | ECDX | Suo, Feifei (F.) <FSUO@ford.com>; basic voice service - Joseph Lu |  |  | Ford_InHouse | 0% | 25% | 75% | 0% | Y-1st | Y-1st | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | Y | C/O | N | Suo, Feifei (F.) <FSUO@ford.com> |  | DCV0 | 2022-06-10 | 2022-06-23 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Suo, Feifei (F.) <FSUO@ford.com>; basic voice service - Joseph Lu |  | Group B | DCV2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Suo, Feifei (F.) <FSUO@ford.com>; basic voice service - Joseph Lu |  | Group B | DCV2 | Y | Minor | Adapt new scree size 12' | Suo, Feifei (F.) <FSUO@ford.com>; basic voice service - Joseph Lu |  | DCV2 |  |  | Y | C/O |  |  |  |  | DCV0 |  | Y | C/O |  | Xie, Jie (J.) <JXIE49@ford.com> |  |  | DCV0 |  | Phase 5 | No | Group B | DCV0
SYNC+_0124 |  |  | H# Service & Maintenance 车主服务 | 5# User Feedback Channel 用户反馈 | 用户反馈Customer Feedback1.0 | QR code scan and submit via phone. 2021-02: 对于提交反馈的用户， 车机端会有个消息提醒：”感谢你的反馈。“ | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Wang, Johnny (J.) <jwang308@ford.com> |  | - | - | - | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A | - | N | N |  | Zhang, Kerry (Y) <yzhan142@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N | [6 empty] | N | N | [6 empty] | Phase 1 | No
SYNC+_0265 |  |  | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 4G/5G Uu车路协同 V2I Lite (Production) | V2I Lite (Production) For FNV2: 支持更多城市； | ECDX | Li, Yifei (Y.) <nli26@ford.com> |  |  | Ford_InHouse | 0% | 20% | 60% | 20% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV3 | 2023-02-24 | 2022-03-30 | Y | C/O | N | Liyifei <nli26@ford.com> |  | DCV3 | 2022-09-10 | 2022-09-24 | N | N |  | Li, Yifei (Y.) <nli26@ford.com> |  | N/A | - | Y | New |  | Li, Yifei (Y.) <nli26@ford.com> |  | N/A | DCV2 | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | Y | C/O |  |  |  |  | - |  | Phase4 | No |  | -
SYNC+_0103 | F000173 | My Key | E# Access & Authorization 车钥匙 | 1# Keyfob 传统车钥匙 | 我的钥匙MyKey | XCL decision to stop this implementation from P702/MY21U554MCA Settings-Clear my keys Settings-Create my key Settings-My key status Settings-Volume limiter | EESE |  |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Xu, Andy (X.) <xxu71@ford.com> |  | - | - | - | N | N |  | Xu, Andy (X.) <xxu71@ford.com> |  | N/A | - | N | N |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N | [6 empty] | N | N | [6 empty] | Phase 2 | No
SYNC+_0106 | F001670/A F001372 |  | E# Access & Authorization 车钥匙 | 2# Phone As A Key (PaaK) 手机钥匙 | 手机钥匙Phone as key(PaaK) | Regular PAAK. 4 doors 天线1+ 6 或1+x， Backup Startup Passcode (BSP) 选配，refer to feature owner cascade。 + EV PaaK CNECDMPORT-225 | ECDX | Chen, Kiefer (Y.) <ychen290@ford.com> | Hamel, Jeffrey (J.) |  | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Chen, chiefer | Hamel, Jeffrey (J.) |  |  |  | Y |  | Need check with FO | Chen, Kiefer (Y.) <ychen290@ford.com> |  | Group A | DCV Alpha2 | Y |  | Need check with FO | Chen, Kiefer (Y.) <ychen290@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - | N | N | N | N |  |  | Al-abdulrasul, Ahmed (A.) |  | - |  | Y | C/O |  | Zhang, Yan (Y.) <YZHAN481@ford.com> | Al-abdulrasul, Ahmed (A.) |  | - |  | Phase 2 | No | Group A | DCV1
SYNC+_0108 |  | Face ID | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | 人脸识别账户登录Face ID - Driver (IVI Stand alone IR Camera) | Stand alone Facial ID camera, not DAT - DSMC. (Registration, Recognition, Account, Personalization, Welcome | EESE | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  | FaceID with DSMC Function Specification_V8 _20201215.pdf | SW_Tier1 | 20% | 80% | 0% | 0% | N | N | DCV1 | 2021-12-15 | 2021-12-29 | N | N |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | HMI UIUE change | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | N | N |  | 6_目前funding只cover707,Jia, Elaine (T.) <tjia2@ford.com> |  | N/A | - | N | N |  | Xu, Amy (X.) <xyafei@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | Y-study | N |  | NO FO-ASK |  |  | - |  | Phase 4 | No | Group A | -
SYNC+_0110 |  |  | B# Multimedia 多媒体 | 3# Music 音乐 | 舱内娱乐Cabin On-live 1.0 | First deploy to CDX707 with in car KTV and in car passenger DLNA | ECDX | Xiang, Zhengxi (Z.) <zxiang6@ford.com> |  |  | TBD |  |  |  |  | Y-1st | Y-1st | DCV5 | 2022-04-20 | 2022-05-04 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y-Study |  |  | Yu, Yaxing (Y.) <yyu55@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | N | N |  | Xiang, Zhengxi (Z.) <zxiang6@ford.com> |  | N/A | - | N | N |  | Shi, Stella (J.) <jshi32@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | Y | C/O |  |  |  |  | DCV3 |  | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | DCV3 |  | Phase 5 | No |  | DCV3
SYNC+_0112 | F003415,F001047 |  | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程解锁/启动 Remote Door Lock/Engine Start | Remote Door unlock/start engine. 空调/座椅/方向盘加热 也会自动上一次熄火前的设置 | ECDX | Lin, Shawn (X.) <xlin17@ford.com> | Syed, Imtiaz (I.S.) | Cellular Remote Start, Extend Remote Start & Cancel Remote Start Feature Document v1.1.pdf Cellular Remote Start, Extend Remote Start & Cancel Remote Start Function Specification v1.0.pdf FNV2 Remote Start and Schedule Remote Start PRD v3.2.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Jia, Elaine (T.) <tjia2@ford.com> | Syed, Imtiaz (I.S.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Lin, Shawn (X.) <xlin17@ford.com> | Garrido, Priscilla (P.C.) <pgarrid2@ford.com> | DCV Beta |  |  | Y | C/O |  |  | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  | Phase 1 | No | Group B | DCV Beta
SYNC+_0113 |  |  | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程鸣笛闪灯 Vehicle Announcement via FordPass | [Shawn] Non IVI seting provides additional Command & Control ability to customer that customer can remotely active the light （转向灯） and horn to locate their vehicle. Lead: CX482PHEV.FordPass have two solutions to meet different program architecture with additional testing cost. Currently planned on Fordpass. Additional LincolnWay UI will be required if need. FordPass远程控制灯光/鸣笛 Remote control lighting/horn.4G 信号 支持。Customer benefit 场景： 找车。 现有的keyfob 蓝牙模块有~40米。 (Lead phase 2: CX482/Lincoln Way (Not Ready) | ECDX | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y | N |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Jia, Elaine (T.) <tjia2@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | New |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | New |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | DCV Beta |  | Phase 2 | No |  | DCV Beta
SYNC+_0114 |  |  | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | 远程空调控制 Remote Climate Control (RCC) via FordPass/Lincoln Way | CNECDMPORT-344 [Shawn] Need IVI setting Will allow customer’s to select their personal settings for cabin temperature, max defrost and heated/cooled seats. Customer can view the current vehicle cabin temperature and the last HVAC settings through the mobile app. 空调， 通风除霜，座椅加热，油车跟remote start 联动 （~10分钟后， 用户可以选择延时，否则engine stop)。新增项：实时显示，分开各项分开设置。支持FNV2架构。Gasoline and EV。 Lead：CD764. Feasible for programs with FNV2 architecture | ECDX | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y | N |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | HMI Yao, Jeffery (J.) <jyao12@ford.com> - FO assign之前可以联系 |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | New |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | New |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV Beta |  |  | N | N |  |  |  |  | - |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | DCV Beta |  | Phase 4 | No |  | DCV Beta
SYNC+_0116 |  | User Guide | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 爱车探索Demo Mode | Including 重温欢迎仪式 Replay Welcome Approach 配置介绍 Features Walkthrough | EESE | temporary Ding, Wei (W.) <WDING15@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | R00 | 2022-05-18 | 2022-06-01 | Y | C/O |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | Minor | HMI UIUE change | Zhou, Calvin (.) <QZHOU31@ford.com> |  | DCV2 | 2022-08-10 | 2022-08-24 | N | N |  | temporary Ding, Wei (W.) <WDING15@ford.com> |  | N/A | - | N | N |  | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  | N/A | N/A | Y | Minor | Adapt new scree size 12' | temporary Ding, Wei (W.) <WDING15@ford.com> |  | DCV2 |  |  | Y | Major |  |  |  |  | DCV3 |  | Y | C/O |  | temporary Ding, Wei (W.) <WDING15@ford.com> |  |  | DCV3 |  | Phase 4 | No | Group B | DCV3
SYNC+_0119 |  |  | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 1.0 | Paper "Owners' manual" go digital on IVI. OTA to support any contents updates/changes. | ECDX | Yao, Jiang (J.) <JYAO19@ford.com> |  |  | Ford_InHouse | 0% | 10% | 90% | 0% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Lin, Shawn (X.) <xlin17@ford.com> |  | - | - | - | N | N |  | Yao, Jiang (J.) <JYAO19@ford.com> |  | N/A | - | N | N |  | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N | [6 empty] | N | N | [6 empty] | Phase 2 | No
SYNC+_0117 | F002370 | User Guide | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 1.5 | 1. Online content update（cloud storage) 支持内容通过云端更新（静默升级，无需OTA, 用户无感知) - Phase 4 全系 planned， phase 3 in progress; 2. 支持全量纸质手册 . 福特车型（5本); 林肯车型（6本); V1.0 只支持Owner's manual 3. 多媒体手册内容 (video形式本地存储， 具备流媒体形式，但目前没有内容对接）。支持后备箱踢脚 (CDX482/483 only)。 需Program/feature owner drive content design. 4. Voice Command open E-manual; Voice search content (20 keywords voice search) | EESE | Jiang, Wei (W.) <wjiang33@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV3 | 2022-09-10 | 2022-09-24 | N | N |  | Jiang, Wei (W.) <wjiang33@ford.com> |  | N/A | - | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  | Hari, Srikanth (S.) |  | - |  | N | N |  | Jiang, Wei (W.) <wjiang33@ford.com> | Hari, Srikanth (S.) |  | - |  | Phase 4 | No | Group B | -
SYNC+_0118 | F002370 | User Guide | H# Service & Maintenance 车主服务 | 1# Interactive User Guide 车主指导 | 车机端电子版用户手册 E-Manual 2.0 | 1. AI Voice Search (Inhouse Developped). 云端支持 inhouse MPP 合作开发. POC 开发完成， waiting for approve. | EESE | Jiang, Wei (W.) <wjiang33@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-TBD | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | Y | Minor | HMI UIUE change | Jiang, Wei (W.) |  | DCV3 | 2022-09-10 | 2022-09-24 | Y | C/O |  | Jiang, Wei (W.) <wjiang33@ford.com> |  | Group C | TBD | Y | C/O |  | Jiang, Wei (W.) <wjiang33@ford.com> |  | Group C | TBD | Y | Minor | Adapt new scree size 12' | Jiang, Wei (W.) <wjiang33@ford.com> |  | DCV2 |  |  | Y | C/O |  |  | Hari, Srikanth (S.) |  | DCV3 |  | Y | C/O |  | Jiang, Wei (W.) <wjiang33@ford.com> | Hari, Srikanth (S.) |  | DCV3 |  | Phase 5 | No | Group B | DCV3
SYNC+_0120 |  |  | H# Service & Maintenance 车主服务 | 2# Traffic Violation Checking 违章查询 | (百度小程序) 违章查询 Query traffic violations (IVI) | Baidu: 用户终端查询是需要收费的。 | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | C/O | N | Lu, Chao (C.) <clu42@ford.com> |  | DCV Beta1 | 2022-04-30 | - | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV0 | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV0 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV1 |  |  | Y | C/O |  |  |  |  | DCV1 |  | Y | C/O |  | Xie, Jie (J.) <JXIE49@ford.com> |  |  | DCV1 |  | Phase 2 | No | Group B | DCV1
SYNC+_0122 | F001048/F |  | H# Service & Maintenance 车主服务 | 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | 车辆警示与车辆状态 Vehicle Health Alert and Status(VH) | VH collects diagnostic data from the vehicle and presents it to customer via mobile app OR IVI in the form of Vehicle Status, which displays the most up-to-date information such as Odometer, Fuel Level, Oil Life, Tire Pressure, Distance to empty, Vehicle Location etc. and Vehicle Health notification/alert with contextual information based on the vehicle’s current condition (such as MIL/WIL and DTCs). | ECDX | Chen, Wei (W.) <WCHEN160@ford.com> | McKinstry, Roy (R.S.) | ECPI_VSHA_Feature_Requirement_Document_v1_1.docx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Lu, Chao (C.) <clu42@ford.com> | McKinstry, Roy (R.S.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Chen, Wei (W.) <WCHEN160@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Chen, Wei (W.) <WCHEN160@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Chen, Wei (W.) <WCHEN160@ford.com> |  | DCV Beta |  |  | Y | Minor |  |  | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  | Y | C/O |  | Chen, Wei (W.) <WCHEN160@ford.com> | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_0123 |  |  | H# Service & Maintenance 车主服务 | 4# Dealer Service Booking 经销商服务预定 | 保养及在线预约 OSB - Online Service Booking | Dearler Search. /Vehicle Maintenance and the service booking 保养在线预约 OSB-订单查询 order inquiry 保养在线预约 OSB-保养预约 Service booking， time and leave a note for maintenance items 保养在线预约 OSB-建议保养项目 Base on mile display user manual suggested maintenance item when user click on this . | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  | MRD OSB MRD.pdf | SW_Tier1 | 0% | 100% | 0% | 0% | Y | On Hold | DCV4 | 2022-03-23 | 2022-04-06 | On Hold | N |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | N | N | N | Wang, Johnny (J.) <jwang308@ford.com> |  | - | - | - | On Hold | On Hold |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group C | DCV2 | On Hold | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A: Group C; N/A: DCV2; N: On Hold; N: Wang, Johnny (J.) <jwang308@ford.com>; -: DCV3; Y: N; C/O: N |  |  |  |  | - |  | on hold | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | DCV3 |  | Phase 4 | No | Group B | DCV3
SYNC+_0125 |  |  | H# Service & Maintenance 车主服务 | 5# User Feedback Channel 用户反馈 | 用户反馈Customer Feedback 2.0 | Improved version.车机上进行语音录入用户反馈。增加手机上的交互xx. target timing 是CX727 第一个OTA cadence | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | C/O | N | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV Beta1 | 2022-04-30 | - | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group D | DCV1 | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group D | DCV1 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV2 |  |  | Y | C/O |  |  |  |  | DCV1 |  | Y | C/O |  | Xie, Jie (J.) <JXIE49@ford.com> |  |  | DCV1 |  | Phase 4 | No | Group B | DCV2
SYNC+_0126 | F000997 |  | I# Safety & Security 安全 | 1# Emergency Services 紧急救援 | 升级版紧急救援/服务 eCall | CN-CAP Safety (5 stars) driven features. Dedicated TCU, Microphone， Speaker. Automatic trigger condition is the same as current EA design(Oil pump cut off or air bag deploy); leverage current EA call center Yesway(95智驾). CN Regulation on e-call to be expected in 2024 (TBD) | ECDX | Ren, Siyuan (Alex.) <sren6@ford.com> | Berro, Hussein (H.) | eCall-PRD v1.2.pdf EECS Audio Client SPSS v1.1 November 1, 2018.pdf EECS Display Client (eCall) SPSS v1.0 March 16, 2018.pdf | HW_Tier1 | 60% | 0% | 0% | 40% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Ren, Siyuan (Alex.) | Berro, Hussein (H.) | DCV Beta1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - | N | N | Y | C/O |  |  | Carl, James (J.R.) |  | DCV Beta |  | Y | C/O |  | Ren, Siyuan (Alex.) <sren6@ford.com> | Carl, James (J.R.) |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_0128 |  |  | I# Safety & Security 安全 | 1# Emergency Services 紧急救援 | 道路救援Road Side Assitance (RSA) | 道路救援， 用户IVI端一键触发(蓝牙电话）（安联） - 拨打道路救援电话，获取道路救援服务 - 入口：车机端"道路救援"应用，其存储着固定的道路救援电话号码 - 通过蓝牙连接的手机拨打道路救援电话 | ECDX | Ren, Siyuan (Alex.) <sren6@ford.com> |  | DUEROS_CVPP_RSA_PRD v1.2.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | Y | C/O | N | Ren, Siyuan (Alex.) <sren6@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  | Group A | DCV Beta1 | Y | C/O |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  | Group A | DCV Beta1 | Y | Minor | Adapt new scree size 12' | Ren, Siyuan (Alex.) <sren6@ford.com> |  | DCV Beta1 |  |  | Y | C/O |  |  |  |  | DCV0 |  | Y | C/O |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | DCV0 |  | Phase 1 | No | Group B | DCV0
SYNC+_0129 |  | BT Child Seat | I# Safety & Security 安全 | 2# Safety Reminder 安全提醒 | 儿童座椅报警Child Restraint System (CRS) - ( e.g BT Child seat 蓝牙座椅) | BT Child seat 蓝牙座椅, 蓝牙通信反馈儿童座椅是否正确安装了。CNCAP 安全需求，车载需要支持与CRS 实现通信功能. 通信的具体形式是蓝牙传输. 目前仅支持环球娃娃品牌下的部分型号. CNCAP 5星要求。 | EESE | Xu, Amy (X.) <xyafei@ford.com> |  | 基于BT检测儿童安全座椅状态功能--PRD.docx | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | Y | C/O | N | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Beta1 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Beta1 | N | N | N | N | N | - | N | N | Y | C/O |  |  |  |  | DCV Beta1 |  | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | DCV Beta1 |  | Phase 4 | No | Group A | DCV Beta
SYNC+_0130 |  |  | J# Health & Wellness | 1# Air Quality 空气质量 | 座舱空气质量检测CAQ(Cabin Air Quality) | 后装方案 | ECDX |  |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Tong Tian |  | - | - | - | N | N |  | Tong Tian |  | N/A | - | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N | [6 empty] | N | N | [6 empty] | Phase 1 | No
SYNC+_0131 |  |  | J# Health & Wellness | 1# Air Quality 空气质量 | 智能新风Auto Air Refresh (AAR) G1 | 显示车内PM2.5, 提醒是否内外循环切换 | ECDX | Shi, Stella (J.) <jshi32@ford.com> |  | DUEROS_CVPP_AAR v1.3.1_ChinaMarket_Sync+_20210225.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Shi, Stella |  | - | - | - | N | N |  | Shi, Stella (J.) <jshi32@ford.com> |  | N/A | - | N | N |  | Xu, Andy (X.) <XXU71@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N | [6 empty] | N | N | [6 empty] | Phase 2 | No
SYNC+_0132 | F001211 |  | J# Health & Wellness | 1# Air Quality 空气质量 | 智能新风Auto Air Refresh (AAR) G2 (Blue Shield) | Blue Shield. 增加了主动干预，自行切换；点火后， 自动打开空调；行驶中， 提醒是否开空调 （不主动干预，因为会引起driver 紧张，安全影响） | ECDX | Shi, Stella (J.) <jshi32@ford.com> | Hasan, SM Fairus (S.) <shasan13@ford.com> | DUEROS_CVPP_AAR v1.3.1_ChinaMarket_Sync+_20210225.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Shi, Stella (J.) <jshi32@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Shi, Stella (J.) <jshi32@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Shi, Stella (J.) <jshi32@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Shi, Stella (J.) <jshi32@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  | Shi, Stella (J.) |  | DCV Beta |  | Y | C/O |  | Shi, Stella (J.) <jshi32@ford.com> | Shi, Stella (J.) |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_0133 |  |  | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 数字香氛 Digital scent 1.0 | 4 scents | BI | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  |  | Core_Service_Supplier | 10% | 0 | 0% | 90 | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Chen, Minghui (M.) <MCHEN122@ford.com> |  | - | - | - | N | N |  | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  | N/A | - | N | N |  | Bella Wu --> Chen, Huizhen (H.) <HCHEN188@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N | [6 empty] | N | N | [6 empty] | Phase 3 | No
SYNC+_0134 | F004410 F003130 |  | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 数字香氛 Digital Scent 2.0 (New Scents) | New scents can work with imersive experience, e.g rejuvenations for customer heath & wellness, as well as Purify. | BI | Wang, Yan Jing (Y.) <ywang458@ford.com> - FO ; Chen, Minghui (M.) <MCHEN122@ford.com>- 软件相关 |  | Digital Scent PRD - for CDX707C 20210714.doc Boundary Diagram - Digital Scent Feature -2020-2-10.vsdx Feature Document Digital Scent - China 0331.docx LIN Communication Matrix 0.4_SAE J2602_Phase 4 Release 2020-10-19.xlsx PRD Digital Scent for CD764 2021-1-25.mht | Core_Service_Supplier | 10% | 0 | 0% | 90 | Y-1st | Y-1st | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Chen, Minghui (M.) <MCHEN122@ford.com> |  | - | - | - | Y | C/O |  | Wang, Yan Jing (Y.) <ywang458@ford.com> - FO ; Chen, Minghui (M.) <MCHEN122@ford.com>- 软件相关 |  | Group A | DCV Alpha2 | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | Y | C/O |  |  | Thakur, Bhavna (B.) |  | DCV Beta |  | Y | C/O |  | Wang, Yan Jing (Y.) <ywang458@ford.com> - FO ; Chen, Minghui (M.) <MCHEN122@ford.com>- 软件相关 | Thakur, Bhavna (B.) |  | DCV Beta |  | Phase 5 | No | Group A | DCV Beta
SYNC+_0135 | F003072 | Relax Mode | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 活力恢复 Project Aspire_Rejuvenation | Project Aspire: Relax is a feature/capability that allows to provide a user specific experience to induce calming or relaxing experience. The feature is a combination of effects in a vehicle to including- Digital scent- Advanced welcome with complimentary light and sound scheme in various parts of vehicle such as ambient lighting , Horizon display , center stack etc- Relax moment can be initiated and controlled via HMI. This feature also uses FordPass to download calm app, install, set up calm experience (ambient color, cabin temo, length of experience, other HVAC controls), save and then start calm experience with chatbot and FB messenger. 相比Relax mode, 新增空调，EM register, | EESE | Zhu, Jiawei (J.) <JZHU101@ford.com> | Shetty, Sohan (S.R.) | Rejuvenate Feature_Document_rev1_20210305.docx Rejuvenate Function_Specification_rev0_20210305 (1).docx Rejuvenate Implementation_Specification_rev0_20210305 (4).docx | Ford_InHouse | 0% | 0% | 90% | 10% | Y-1st | Y-OTA | R09 | 2023-04-14 | 2023-04-28 | Y-1st | New |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | N | N | N | Liu, Kai (K.) <kliu63@ford.com> | Shetty, Sohan (S.R.) | - | - | - | N | N |  | Zhu, Jiawei (J.) <JZHU101@ford.com> |  | N/A | - | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | Y | Minor |  |  | Shetty, Sohan (S.R.) |  | DCV Beta |  | Y | C/O |  | Zhu, Jiawei (J.) <JZHU101@ford.com> | Shetty, Sohan (S.R.) |  | DCV Beta |  | Phase 5 | No | Group B | DCV0
SYNC+_0136 |  | Relax Mode | J# Health & Wellness | 2# Rejuvenation 活力恢复 | 舒享时分Relax/自由秘境At Ease | Pre-Global Rejuvenation. China Local solution. 林肯车型正式名称 - 舒享时分Relax/ 车型f福特正式名称 - 自由秘境At Ease; 目前项目主题都有不一样的地方（Room 一样的差别较小） | EESE | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  |  | Ford_InHouse | 0% | 0% | 90% | 10% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | N | N |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  | DCV0 | 2022-06-10 | 2022-06-23 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  | Group A | DCV3 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  | Group A | DCV3 | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | Y | C/O |  | Zhou, Calvin (.) <QZHOU31@ford.com> |  |  | - |  | Phase 4 | No |  | DCV1
SYNC+_0137 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 个人时光 Smart Scene - Personal Enjoyment | Personal Enjoyment 个人时光 Lead: CDx764 CD764 Implantation -Buddle setting to provide wonderful movie watch experiences in the copilot seat. Target Parking experience when customer watch movie for more than 30 minutes. Drive side is not considered in this design as long movie watching experience is not encouraged as for bad HMI or blocked sight. Buddle setting including Digital Scent, lighting , massage seat setting, enhanced co-pilot seat audio effect. Driver are expected to move to co-pilot seat to use this feature. Research shows that this movement won’t be a boundary as long as the experience is good. Moving forward, more enjoyment like game and other leisure enjoyment will be add. Developpment in progress. Smart Scene is part of phase 4 discussion with Desay. Product/Feature owner to provide details. Feature OTA Capability depends on Vehicle HW and display set e.g whether screen covers co-pilot seat). | ECDX | Shi, Stella (J.) <jshi32@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | N | N | N | Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  | DCV2 | 2022-08-10 | 2022-08-24 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  | Group B | DCV3 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  | Group B | DCV3 | N | N | N | N | N | - | N | N | Y | C/O |  |  |  |  | DCV2 |  | Y | C/O |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | DCV2 |  |  | No | Group B | DCV2
SYNC+_0138 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 车机相册 IVI Picture Gallery | 支持车机本地/USB 图片和视频资源浏览/播放。 具体功参考技术文档。可参照现有手机相册的实现 | ECDX |  |  |  | SW_Tier1 | 20% | 80% | 0% | 0% | Y | Y-OTA | R09 | 2023-04-14 | 2023-04-28 | N | N |  |  |  | DCV2 | 2023-01-24 | - | N | N | N |  |  | DCV2 | 2022-08-10 | 2022-08-24 | N | N | N | N | N | N | N | N | Minor | New HMI layout and UE for 12.3'+27' Display | Jia, Elaine (T.) <tjia2@ford.com> |  | N/A N/A: Group C; N/A N/A: DCV2; N N: N; N N: Jia, Elaine (T.) <tjia2@ford.com>; - -: -; Y Y: N; C/O Minor: N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 4 | No | Group C | -
SYNC+_0139 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 客人模式Smart Scene - Guest Mode | could be triggered by copilot seat door or seat sensor，or activate by voice command by customer. Guide guest to IVI contents (e.g music) in the meanwhile protect car owners privacy by removing owners' search records. Co-drive mode (lead by Grace lee) is more for onboard a family member or friends. -Challenges: part of the design is to give privacy to driver. requires removal of driver's or other users search records. require baidu implementation. currently dont have Baidu responses. -OTA Feasibility: designed for 27Inch Touch Screen. consider HMI changes for other programs. | ECDX | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  |  | Ford_InHouse | 10% | 0% | 90% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | N | N | N | Sun, Zheng (Z.) <ZSUN6@ford.com>(PO) Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); |  | - | - | - | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  | Group B | DCV3 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  | Group B | DCV3 | N | N | N | N | N | - | N | N | Y | C/O |  |  |  |  | DCV2 |  | Y | C/O |  | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  |  | DCV2 |  | Phase 4 | No | Group B | DCV2
SYNC+_0140 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 智慧指令 Smart Scene - Smart Order | Buddled setting for (CD764 MVP - 4 orders including 客人模式；通勤模式；冬日模式；夏日模式 。根据设定条件,IVI 屏幕主动推荐“智能指令”or activate by voice command. Allow customization on IVI/Fordpass。 - Challenges：1-limited modules in the vehicle is controllable. 2-Not a high priority for Ford global. Therefore setting on FordPass and send to car is not feasible even in 2021 . | ECDX | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  |  | Ford_InHouse | 10% | 0% | 90% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | N | N | N | Sun, Zheng (Z.) <ZSUN6@ford.com>(PO) Liu, Hailan (H.) <HLIU142@ford.com> (Supporting Engineer); |  | - | - | - | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  | Group B | DCV3 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  | Group B | DCV3 | N | N | N | N | N | - | N | N | Y | C/O |  |  |  |  | DCV2 |  | Y | C/O |  | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) |  |  | DCV2 |  | Phase 4 | No | Group B | DCV2
SYNC+_0141 |  |  | K# Social & Operation 社交及运营服务 | 4# Personal Productivity 工作效率 | 车机日历Project Aspire_Routines / Daily View_IVI Calendar 2.0 | This experience provides capability to Ford / Lincoln user to access personalized calendar or day to day schedule while in the vehicle and different aspects influencing the customers daily life. The Experience covers different aspects such as Integrating into calendar, reminders appointments etc. Integrating into traffic (ETA , Traffic) Integrating into routine destinations or accessing customers locations per calendar Integrating into vehicle data such as Fuel/charge level and ability to predict fueling/charging time in the busy day. This is the day view that margaret has once she hoped in her vehicle. - From Project Aspire User calendar is an enabler to this function. For reference 764 have IVI Calendar (Local Design), need to work with global core team understandingthe global design. | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | N | DCV1 | 2021-12-15 | 2021-12-29 | N | N |  |  |  | DCV2 | 2023-01-24 | - | N | N | N | Shi, Stella (J.) <jshi32@ford.com> |  | - | - | - | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 5 | No | Group B | -
SYNC+_0142 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | (百度小程序) 电影票预定 Movie Ticket Booking 美团外卖MeiTuanTake-away 鲜花预定Order flower delivery 机票查询 Flight search 火车票查询 Train ticket search 酒店预定 Hotel booking | 资源来自爱奇艺。查看热映电影;选座购票;付款;"鲜花预定（含二维码支付） Order flower delivery" 机票查询 Flight search 火车票查询 Train ticket search 酒店预定 Hotel booking | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV3 | 2023-02-24 | 2022-03-30 | Y | C/O | N | Lu, Chao (C.) <clu42@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV2 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV2 |  |  | Y | C/O Mini app 707 TBD |  |  |  |  | DCV1 |  | Y | C/O |  | Xie, Jie (J.) <JXIE49@ford.com> |  |  | DCV2 |  | Phase 1 | No | Group B | DCV2
SYNC+_0143 |  |  | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 福特/林肯金融 Ford Credit | 账务记录 | ECDX | Lu, Chao (C.) <clu42@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | Y | C/O | N | Lu, Chao (C.) <clu42@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Lu, Chao (C.) <clu42@ford.com> |  | Group C | DCV1 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Lu, Chao (C.) <clu42@ford.com> |  | Group C | DCV1 | Y | Minor | Adapt new scree size 12' | Lu, Chao (C.) <clu42@ford.com> |  | DCV2 |  |  | Y | C/O |  |  |  |  | DCV2 |  | Y | C/O |  | Lu, Chao (C.) <clu42@ford.com> |  |  | DCV2 |  | Phase 2 | No | Group B | DCV2
SYNC+_0145 |  |  | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 随心拍Traveling Shooting | Need AR Navigation Camera | ECDX |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | N | R09 | 2023-04-14 | 2023-04-28 | N | N |  |  |  | DCV3 | 2023-02-24 | 2022-07-26 | N | N | N |  |  | DCV Beta | 2022-03-12 | 2022-03-19 | N | N |  | Jia, Elaine (T.) <tjia2@ford.com> |  | N/A | - | N | N |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 4 | No | Group C | -
SYNC+_0151 |  |  | K# Social & Operation 社交及运营服务 | 2# Travel Service 出行服务 | 随心拍Travel Shooting 2.0 Project Aspire_Photos (GPS Created Trip Summary) | Share picutres & trip highlights (ex. Wechat or Facebook story report out). Ideas of things to share: selfie if taken with interior facial camera, personal photos taken during the trip, locations visited/passed, number of miles traveled, etc. | ECDX |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y-OTA | R09 | 2023-04-14 | 2023-04-28 | N | N |  |  |  | DCV3 | 2023-02-24 | 2022-07-26 | N | N | N |  |  | - | - | - | N | N |  |  |  | N/A | - | N | N |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 5 | No | Group C | -
SYNC+_0152 |  | Customer Reminder | K# Social & Operation 社交及运营服务 | 3# Entertainment 娱乐 | 时空秘信Surprise/Secret message | customer can schedule supirse message such as "Happy Birthday" | EESE | temporary Jiang, Wei (W.) <WJIANG33@ford.com> Grace Lee (TBD) |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | Y | C/O | N | Lee, Grace (G.) <glee51@ford.com> |  | DCV0 | 2022-06-10 | 2022-06-23 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | temporary Jiang, Wei (W.) <WJIANG33@ford.com> Grace Lee (TBD) |  | Group B | DCV3 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | temporary Jiang, Wei (W.) <WJIANG33@ford.com> Grace Lee (TBD) |  | Group B | DCV3 | Y | Minor | Adapt new scree size 12' | temporary Jiang, Wei (W.) <WJIANG33@ford.com> Grace Lee (TBD) |  | DCV 2 |  |  | Y | If 1.0 – C/O If 2.0 - New |  |  |  |  | DCV2 |  | Y | C/O |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | DCV2 |  | Phase 4 | No | Group B | DCV2
SYNC+_0154 |  |  | K# Social & Operation 社交及运营服务 | 4# Personal Productivity 工作效率 | 视频会议 Project Aspire_Video Phone Calling / Video Conferencing (Meeting Mode)_CN | Demonstrate a Video call capability using the center stack with a Web application. The Functionality provides a view for Video conferencing in stationary mode. Includes conference experience , voice or audio in call and document viewing and sharing capabilities. These are listed as two items on Project Aspire Master List | ECDX | Temporary Wang, Johnny (J.) <JWANG308@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | On Hold | DCV3 | 2022-02-16 | 2022-03-02 | N | On Hold |  |  |  | DCV2 | 2023-01-24 | - | N | N | N | Wang, Johnny |  | - | - | - | N | N |  | Temporary Wang, Johnny (J.) <JWANG308@ford.com> |  | N/A | - | N | N |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 5 | No | Group B | DCV0
SYNC+_0156 |  |  | K# Social & Operation 社交及运营服务 | 5# In Vehicle Gaming 车载游戏 | 舱内娱乐Cabin on live 2.0 | Cabin on live will include in car gaming(3rd party) | ECDX | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-OTA | R09 | 2023-04-14 | 2023-04-28 | N | N |  |  |  | N/A | N/A | N/A | N |  |  | Fan Henry |  | DCV1 | 2022-07-10 | 2022-07-24 | N | N |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | N/A | - | N |  |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 5 | No |  | DCV3
SYNC+_0155 |  | Customer Reminder | K# Social & Operation 社交及运营服务 | 4# Personal Productivity 工作效率 | 车机日历IVI Calendar 1.0 | Generic calendar with Chinese traditional calendar/Holidays/Customer personal Events-Event Management (Add;Edit/Delete). IVI system will remind customer these recorded events on screen with voice broadcaste. Roadmap with more features to be implemented in upcoming phases. |  | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Liu, Hailan (H.) <hliu142@ford.com> |  | - | - | - | N | N |  | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  | N/A | - | N |  |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 4 | No | - | DCV3
SYNC+_0157 |  |  | K# Social & Operation 社交及运营服务 | 6# Marketplace / Apps Anywhere 应用商店 | 车机应用商店Apps Anywhere(SYNC+) | Market Place is a extension of Ford Pass where following options are available for a customer - Chosen experiences such as relax could be purchased and downloaded to the vehicle - Chosen dashboards ( Videos , Static wallpapers) can be purchased and downloaded to the vehicle . Marketplace today is only QSR (Quick Service Retail -coffee, gas, etc). Buying any application purchases is not contained. Apps Anywhere build a foundation to support the application purchases. All on hold | ECDX | Chen, Joey (Jun.) |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-OTA | R09 | 2023-04-14 | 2023-04-28 | Y-Study | C/O |  |  |  | DCV3 | 2023-02-24 | 2022-07-26 | Y-OTA | C/O | N | Fan Henry |  | R08 | 2023-06-24 | 2023-07-07 | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group C | DCV2 | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A N/A: Group C; N/A N/A: DCV2; N N: Y-Study; N N: Chen, Joey (Jun.); - -: DCV3; Y Y: Y-Study |  |  |  |  | DCV2 |  | Y | NEW |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | DCV2 |  | Phase 5 | No | Group C | DCV3
SYNC+_0158 |  |  | K# Social & Operation 社交及运营服务 | 7# Web Browser & Browser Based Application 浏览器和网页版应用 | 车载游览器/浏览器应用Project Aspire_Streaming Web / Applications | Previous name is 车载游览器/浏览器应用Project Aspire_Streaming Web / Applications IQIYI is the assumption (Carryover Feature) The feature discribed below from project aspire is optional Using Chromium with QT the team integrated the following websites in to the ASPIRE experience. Each web application has a icon in the center stack that starts in the center stack and then can be casted to the horizon display. The user can scroll, pan select, play, pause, etc. just as they can on any website. | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st | Y-Study | DCV3 | 2022-02-16 | 2022-03-02 | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Fan Henry (TBD) |  | - | - | - | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A | - | N | N |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 5 | No |  | DCV3
SYNC+_0160 |  |  | L# IoT(Internet of Things) 车家互联 | 1# Vehicle to Home | 车家互联 ( “小度家居”扫码) Vehicle to Home | 扫描车机端显示二维码关联 “小度家居”， 之后在该平台上面关联的设备都会显示在IVI 界面， 并且支持语音远程启动。“你好福特，打开我家里的扫地机器人”，提前开扫地机器人 Turn on cleaning robert/提前开灯 Turn on lights/提前开空调 Turn on AC(at home) an others in advance | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | C/O | N | Lu, Chao (C.) <clu42@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group D | DCV0 | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group D | DCV0 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV1 |  |  | Y | C/O Or remove |  |  |  |  | DCV1 |  | Y | C/O |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | DCV1 |  | Phase 1 | No | Group B | DCV1
SYNC+_0161 |  |  | L# IoT(Internet of Things) 车家互联 | 1# Vehicle to Home | 车家互联Project Aspire_General IOT (Smart Home)_CN (UI grahic upgrade -IVI端） |  | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y-1st | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | C/O | N | Lu, Chao (C.) <clu42@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | N | N | N | N | N | N | N | N | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group C | DCV0 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV1 |  |  | Y | C/O Or remove |  |  |  |  | DCV1 |  | Y | C/O |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | DCV1 |  | Phase 5 | No | Group B | DCV1
SYNC+_0162 |  |  | L# IoT(Internet of Things) 车家互联 | 2# Home to Vehicle | 家车互联Project Aspire_General IOT (Smart Home)_CN ( Home to Vehicle) | (UI grahic upgrade + Home to Vehicle Home (XiaoDu Smart Speaker) to vehicle platform | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | On Hold | DCV4 | 2022-03-23 | 2022-04-06 | On Hold | N |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | N | C/O | N | Lu, Chao (C.) <clu42@ford.com> |  | DCV3 | 2022-09-10 | 2022-09-24 | On Hold | On Hold |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group C | DCV0 | On Hold |  |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group C | DCV0 | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | on hold | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | DCV3 |  | Phase 5 | No | Group B | DCV3
SYNC+_0164 |  |  | M# Personalization & Account 账号和个人设置 | 1# Account 账号 | 车机端福特账号和百度账号同时登陆 (By 福特派 or 林肯之道App） Baidu and Ford/Lincoln Account dual Login | 车机端用户显示二维码， 用户通过福特派/林肯之道APP扫描二维码实现林肯/福特和百度账号互通。车机端会同时登陆福特/林肯账号和百度账号。 目前支持8个。 | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  | 【福特phase5】MRD_账号模块个人中心 ID0164_林肯CDX707CDX747福特CDX788_V1.2_2021_05_14.docx | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group B | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group B | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_0165 | F000172,F000171 |  | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | 个性化设置记忆 Enhanced Memory | Seat settings, HMI Theme setting etc recorded in Enhanced Memory; 座椅，HMI 主题等多个性化设置选项profile记录在Enhanced Memory 里面. Normally support 3 profiles with hard switch. Some program go switchless. | ECDX | Xu, Andy (X.) <XXU71@ford.com> | Rahman, Naomee (N.) | Enhanced Memory APIM SPSS v1.11 October 18, 2019.pdf Enhanced Memory APIM Imp Guide v1.11 October 18, 2019.xlsx Enhanced Memory APIM SPSS With Soft Button v1.91 Feb 10, 2020.docx Enhanced_Memory_With_Soft_Button_Feature_Level_Specification_v1.2_Sep_27, 2020.docx | Core_Service_Supplier | 10% | 10% | 0% | 80% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Xu, Andy (X.) <XXU71@ford.com> | Rahman, Naomee (N.) | - | - | - | Y | C/O |  | Xu, Andy (X.) <XXU71@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Xu, Andy (X.) <XXU71@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xu, Andy (X.) <XXU71@ford.com> | Rahman, Naomee (N.) | DCV Beta |  |  | Y | C/O |  |  | Stephens, Walter (W. L.) |  | DCV Beta |  | Y | C/O |  | Xu, Andy (X.) <XXU71@ford.com> | Stephens, Walter (W. L.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_0166 | F002032 Rocket Setup - F002470 BLE Autopair - F002491 Autosave - F002830" | Personalization | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | 基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP) | (ProgramMarketing）Personal Portable Profiles - Create a setup wizard on IVI/Fordpass for customer - Passenger account & profile (could be after J1 - OTA upgrade) - Portble profile. If user move to another vehicle , I can migration all my setting preference with this account/profile effortlessly. Project Aspire： Demostrated profile creation in the cnterstack for three driver profiles and one passenger profile. PPP with DSM5 (Driver Seat Module 5) o Configured to support 10 profiles o Configured such that positional settings are portable to/from vehicle o Physical memory switches ARE NOT present, Auto Save is configured Enabled o Anthropometric Translation is supported. PPP without DSM5 o Configured to support 3 profiles only o Positional settings not portable to/from vehicle due to lack of DSM5 o Physical memory switches ARE present, Auto Save configured Disabled o Anthropometric Translation is NOT supported. | EESE | Xu, Andy (X.) <xxu71@ford.com> |  | Auto Save Feature Spec - Rev F (1).docx Auto Save Functional Specification - Decide - Rev A.docx Auto Save Implementation Specification - Rev C.docx PPP Feature Document v1.2.docx PPP Implementation Spec v1.1 (2).docx PPP Profile Interface Client Functional Spec v1.1.docx PPP Profile Setting Server Functional Specification v1.1.docx PPPServer SPSS Draft2_SimpleSmart2.docx | Core_Service_Supplier | 10% | 10% | 0% | 80% | Y-1st | Y-OTA | R09 | 2023-04-14 | 2023-04-28 | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Xu, Andy (X.) <xxu71@ford.com> |  | - | - | - | N | C/O |  | Xu, Andy (X.) <xxu71@ford.com> |  | Group B | DCV Beta | N | C/O |  | Xu, Andy (X.) <xxu71@ford.com> |  | Group B | DCV Beta | Y | Minor | Adapt new scree size 12' | Xu, Andy (X.) <xxu71@ford.com> | Stephens, Walter (W. L.) <wstephe1@ford.com> | DCV Beta |  |  | N | N |  |  | Stephens, Walter (W. L.) |  | - |  | N | N |  | Xu, Andy (X.) <xxu71@ford.com> | Stephens, Walter (W. L.) |  | DCV0 |  | Phase 5 | No | Group C | DCV0
SYNC+_0167 | F002470 |  | M# Personalization & Account 账号和个人设置 | 2# Personalized Profile 个人设置档案 | 快捷设置Rocket setup | 4S交车前，工作人员会带着车主进行首次设置的界面 | ECDX | Gu, Xiaosheng (X.) <xgu14@ford.com> |  | Spec draft available Dec. 19th | Core_Service_Supplier | 10% | 10% | 0% | 80% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Gu, Xiaosheng (X.) <xgu14@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | N | N |  | Gu, Xiaosheng (X.) <xgu14@ford.com> |  | N/A | - | N | N |  | HMI Yao, Jeffery (J.) <jyao12@ford.com> - FO assign之前可以联系 |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  | Gu, Xiaosheng (X.) <xgu14@ford.com> |  |  | - |  | Phase 2 | No |  | -
SYNC+_0170 | F004174 F000064 | Welcome&Farewell | N# Engagement | 1# Appreciation | 车辆迎宾模式 Lincoln Embrace / Ford Welcome &Farewell | 福特品牌叫做 welcome & Farewell. 林肯品牌叫做Lincoln Embrace. Coorindated exterior/interior lights and IVI display to create welcome/farewell experiences. Might slight varies on programs as per HW assumption differences The feature is intended to be able to either "Welcome" or bid "Farewell" to the Driver based off how he/she interacts with the vehicle. The manner in which the vehicle shall interact with the Driver is by controlling the Exterior Lights, Interior Lights, or Vehicle Displays. | EESE | Chen, Huizhen (H.) <HCHEN188@ford.com> | Fuller, Darnell (D.) | Lincoln Embrace_v2.2.2_CDX707_updated.pdf Welcome Farewell_Messages_Signals_V2.xlsx | HW_Tier1 | 80% | 0% | 0% | 20% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | 新的开关机动画 | Chen, Huizhen (H.) <hchen188@ford.com> | Fuller, Darnell (D.) | DCV1 | 2022-02-12 | - | Y | C/O |  | Bella Wu --> Chen, Huizhen (H.) <HCHEN188@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Bella Wu --> Chen, Huizhen (H.) <HCHEN188@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Chen, Huizhen (H.) <HCHEN188@ford.com> | Ramos, Josafa (J.N.) <jramo120@ford.com> | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Chen, Huizhen (H.) <HCHEN188@ford.com> |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_0171 |  |  | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 智慧停车 Smart Parking | -查看实时车位；-搜索附近的停车场；-停车场付费（含二维码支付） | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV3 | 2023-02-24 | 2022-03-30 | Y | C/O | N | Lu, Chao (C.) <clu42@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV2 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV1 |  |  | Y | C/O Mini app 707 TBD |  |  |  |  | DCV1 |  | Y | C/O |  | Wang, Johnny (J.) <jwang308@ford.com> |  |  | DCV1 |  | Phase 1 | No | Group B | DCV1
SYNC+_0172 |  |  | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 小额免密支付Seamless Payment | 百度带进来的部分生态，电影票，酒店，喜马拉雅 （不含美团外卖） 可以支持免密支付。 小额（单次不超过200CNY) 免密支付 （二维码扫描， 支付宝账号绑定。免密支付不支持微信付款） | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | C/O | N | Lu, Chao (C.) <clu42@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group D | DCV0 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group D | DCV0 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV1 |  |  | Y | C/O Or Remove |  |  |  |  | DCV1 |  | Y | C/O |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | DCV1 |  |  | No | Group B | DCV1
SYNC+_0173 |  |  | O# Payment Services 支付服务 | 1# Payment & Wallet 支付和钱包 | 聚合支付 Aggregate payment +百度-我的钱包 Baidu Wallet | 我的钱包 支付设置 我的钱包 聚合收银台 我的钱包 账单 我的钱包 订单中心 order center； | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | C/O | N | Lu, Chao (C.) <clu42@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group D | DCV0 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group D | DCV0 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV1 |  |  | Y | C/O Or Remove |  |  |  |  | DCV1 |  | Y | C/O |  | Kan, Bing (B.) <BKAN@ford.com> |  |  | DCV1 |  | Phase 1 | No | Group B | DCV1
SYNC+_0175 |  |  | P# Messaging & Alerts 消息和提醒 | 1# Message Center | 消息&消息中心 notification & notification center | Ford/Baidu both have the capability to push message. Phase 1- 30 text/Phase 4- H5,and more. Different "消息： - 消息展示方式：消息体、消息中心、状态栏的消息状态提醒 - 样式定义：消息体、状态提醒的样式 - 消息展示规则、优先级与冲突机制处理 消息中心： - 各种消息的接收、存储、查看" | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Zhang, Xu (X.) <XZHAN304@ford.com> |  | DCV Beta1 | 2022-04-30 | - | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Johnny (J.) <jwang308@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Zhang, Xu (X.) <XZHAN304@ford.com> |  |  | DCV Beta |  | Phase 1 | No | Group A | DCV Beta
SYNC+_0223 | F001192/C |  | S# 系统升级 | 2# OTA | 多模块空中升级 Multi Module OTA (MMOTA) (including: USB Update for TCU and ECG; IVI VMCU, CCPU...) | Multi Module including sync+ | ECDX | Wang, Jennifer (J.) <jwang373@ford.com> | Gudemaranahalli, Rohini Pr (R.) | 547914_D_001_IVSU_Vehicle_Function_USB_Updates v3.0.pdf 547918_F_001_In Vehicle Software Update Vehicle FIS_v6.0.pdf 547923_A_001_IVSU Vehicle Function Download Manager v1.0.pdf 548171_H_001_IVSU_Vehicle_Function_HMI v4.0.docx 583758_B_001_IVSU_Vehicle_Function_Diff Updater_v2.0.pdf | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | FNV架构从3变成2 | Wang, Jennifer (J.) <jwang373@ford.com> | Gudemaranahalli, Rohini Pr (R.) | DCV1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> |  | Group A | DCV1 | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> |  | Group A | DCV1 | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> | Gudemaranahalli, Rohini Pr (R.) <rgudemar@ford.com> | DCV Beta |  |  | Y | C/O |  |  | Carter, Jason (J.) |  | DCV Beta |  | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> | Carter, Jason (J.) |  | DCV Beta |  | Phase 4 | No | Group B | DCV Beta
SYNC+_0239 |  | Map&Navigation | A# Navigation 地图导航 | 2# Navigation - Intelligent Function 智能导航功能 | 最新版领先市场的地图导航能力 Leading Connected Map/Navi | 参照持续更新的Baidu Mainline 内容。Baseline 参照 Baidu Mainline 2020-11-30 版本feature 清单，同时应包含 落地前供应商能提供的最新版 | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  | 福特车机地图产品说明书01-专业地图v1.3_正式版.pdf Phase5 地图AR+惯导硬件要求指标.xlsx | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y-1st | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE change | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV Alpha2 | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Group E | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | DCV Beta |  | Phase 5 | No | Group A | DCV Beta
SYNC+_0208 | F001065 |  | R# EV Features 新能源汽车功能 | 1# Charging | BEV Unique Charging - FB4 | DC Charging 80% SoC EV App Experience CNECDMPORT-330 FB4 Carry over Charging station Finder Pay for Charging Smart Wall Box Wallbox Installation | ECDX | Peng, Ivan (F.) <FPENG6@ford.com> | Rela, Pedro (P.R.) | Cloud Enhanced DTE APIM SPSS v1.2 Nov 19, 2020.docx EV Charge Programming v1 APIM SPSS v1.7 Aug 20, 2019_new.pdf | Core_Service_Supplier | 20% | 0% | 0% | 80% | N | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Yang, Jessica (Yu.) <yyang158@ford.com> | Rela, Pedro (P.R.) | - | - | - | N | N |  | Peng, Ivan (F.) <FPENG6@ford.com> |  | N/A | - | N | N |  | Yang, Jessica (Yu.) <yyang158@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N | [6 empty] | N | N |  | Peng, Ivan (F.) <FPENG6@ford.com> |  |  |  |  | Phase 2 | No | Group A | DCV Beta
SYNC+_0209 | F001065 | EV Features | R# EV Features 新能源汽车功能 | 1# Charging | 充电接口灯设置Charge Port Light Settings | On：Illuminates when plugging in，opening doors， pressing the unlock button on your remote and while charging. Off：Does not illuminate. Limited：Illuminates only when plugging in，opening doors，or pressing the unlock button on your remote. CD391PHEV 有三个选项 : “ on, off & Limited” U6xx只有两个选项“on，off” | EPE | Wu, Dean (D.) <dwu44@ford.com> |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | N |  |  |  | Y | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N | Wu, Dean (D.) <dwu44@ford.com> |  | - | - | - | N | N |  | Wu, Dean (D.) <dwu44@ford.com> |  | N/A | - | N | N |  | Wu, Dean (D.) <dwu44@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | Y-Study | N |  | Wu, Dean (D.) <dwu44@ford.com> |  |  | - |  | Phase 2 | No | Group A | DCV Beta
SYNC+_0210 | F002970 | EV Features | R# EV Features 新能源汽车功能 | 3# EV Powertrain Related | 动力流动画显示Power Flow | Power Flow - PHEV & FHEV | EPE | 4_HMI |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | Y | New |  |  |  | DCV Beta1 | - | - | N | N |  | 4_HMI |  | N/A | - | N | N |  | Wu, Dean (D.) <dwu44@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase 2 | No |  | DCV Beta
SYNC+_0222 |  |  | S# 系统升级 | 2# OTA | IVI空中升级SYNC+ OTA | SYNC+ OTA only. Housed under MMOTA from Phase 4 | ECDX | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Core_Service_Supplier | 40% | 0% | 0% | 60% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Pan, Yuan (Y.) <ypan23@ford.com> |  | - | - | - | N | N |  | Pan, Yuan (Y.) <ypan23@ford.com> |  | N/A | - | N | N |  | Pan, Yuan (Y.) <ypan23@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N | [6 empty] | N | N | [6 empty] | Phase 1 | No
SYNC+_0247 |  |  | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 5G Uu+PC5 车路协同 V2I LITE | Global V2I: 4 feature offerings including 1-Traffic Light Information(TLI) 2-Green Light Notification (GLN) 3-Green Light Optimal Speed Advisory(GLOSA) 4-Red Light Violation Warning(RLVW). | ECDX | Li, Yifei (Y.) <nli26@ford.com> |  |  | Ford_InHouse | 0% | 10% | 60% | 30% | Y-1st | Y-1st | DCV3 | 2022-02-16 | 2022-03-02 | TBD | N |  |  |  | DCV3 | 2023-02-24 |  | N | N | N | Li, Yifei (Y.) <nli26@ford.com> |  | - | - | - | Y | C/O |  | Li, Yifei (Y.) <nli26@ford.com> |  | Group C | DCV2 | Y | C/O |  | Li, Yifei (Y.) <nli26@ford.com> |  | Group C | DCV2 | Y | N | N | N | N | ? | N | N | Y | C/O |  |  |  |  | DCV3 |  | N | N |  |  |  |  | DCV3 |  | Phase5 | No |  | DCV3
SYNC+_0228 | F003519 | My Seat Space | B# Multimedia 多媒体 | 3# Music 音乐 | MySeatSpace | The vision of MySeatSpace is to give customers an isolated immersive audio experience, enabling each occupant to listen to their own audio without disturbing others in the vehicle. This feature further enables in-car communication, private phone calls, media stream sharing and audio enhancements | EESE | 3_No yet China FO assign | Cintron, Austin (A.) | MySeatSpace_Feature_Document_PSC.docx MySeatSpace_FeatureDoc_V1_08132021.docx MySeatSpace_Function Specs_V1_08132021.docx MySeatSpace_Implementation Spec_V1_08132021.docx | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y-1st | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N |  | Cintron, Austin (A.) | - | - | - | N | N |  | 3_No yet China FO assign |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  | Gajjar, Jayneel Asutosh (J.) |  | - |  | N | N |  |  | Gajjar, Jayneel Asutosh (J.) |  | DCV1 |  | Phase5 | Yes | Group A | DCV Beta
SYNC+_0229 |  | DMS Warning | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | Video Interface Throughout Cabin (Rear Seat Monitor, w/ expanded request: allow 2R see 1R) | Driver can see the rear row situation on the screen by leveraging full cabin camera, to ease the worry on taking care of kid. (in-cabin baby monitoring) Kid(s) can see driver via 2nd row display and communicate w/ their parent, to avoid unsafe actions. (via 2nd row screen) |  | 3_No yet China FO assign ? Diven Yu |  |  | SW_Tier1 | 20% | 80% | 0% | 0% | Y-1st | N |  |  |  | OTA | N |  |  |  | TBD | 2022-03-16 | 2022-03-30 | N | N | N | Chen Eva xchen87@ford.com |  | - | - | - | N | N |  | 3_No yet China FO assign ? Diven Yu |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | 3_No yet China FO assign ? Diven Yu | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  | Phase5 | No | Group A | DCV0
SYNC+_0231 | F002812 |  | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | Mobile Device Viewer | C/O global content Remote 360 view (exterior + full cabin camera) | ECDX | 1_to_Efirst, no yet FO assign | Moreno Bautista, Ariana (A.) |  | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y-1st | N | - | - | - | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Shi, Stella (J.) <jshi32@ford.com> | Moreno Bautista, Ariana (A.) | - | - | - | N | N |  | 1_to_Efirst, no yet FO assign |  | N/A | - | N | N |  | Shi, Stella (J.) <jshi32@ford.com> |  | N/A | N/A | N | N | N | 1_to_Efirst, no yet FO assign | N | - | N | N | N | N |  |  |  |  | - |  | N(FNV3) | N |  | Zhang, Xu (X.) <XZHAN304@ford.com> |  |  | - |  | Phase5 | No | Group A | DCV Beta
SYNC+_0234 |  |  | R# EV Features 新能源汽车功能 | 4# Dealer Service Booking 经销商服务预定 | Valet Charging | - Valet Mode - Auto authorization (Preliminary access to vehicle) - Remote tracking of valet charging status - Remote monitoring of cabin | ECDX | Peng, Ivan (F.) <FPENG6@ford.com> | [7 empty] | Y-1st | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Chen, Kiefer (Y.) <ychen290@ford.com> |  | - | - | - | N | N |  | Peng, Ivan (F.) <FPENG6@ford.com> |  | N/A | - | N | N |  | Chen, Kiefer (Y.) <ychen290@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  | Peng, Ivan (F.) <FPENG6@ford.com> |  |  | - |  |  | No |  | -
SYNC+_0240 |  | DMS Warning | F# ISP (Intelligent Sensing Platform) 智能感应平台 | 1# Camera Related 摄像头相关 | 多模交互 Image recognition - Multi-Mode (Hand Gusture / Head / Emotion) | 基于手势(hand guesture)，点头/摇头（head), 笔嘘-多媒体静音， 收藏，返回，屏幕左右滑动等作为指令识别。 具体逻辑见feature Document | EESE | Jia, Elaine (T.) <tjia2@ford.com> | [7 empty] | Y | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Jia, Elaine (T.) <tjia2@ford.com> |  | - | - | - | N | N |  | Jia, Elaine (T.) <tjia2@ford.com>; Wang, Johnny (J.) <jwang308@ford.com> |  | N/A | - | N | N |  | Jia, Elaine (T.) <tjia2@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | Y-Study | N |  | Jia, Elaine (T.) <tjia2@ford.com>; Wang, Johnny (J.) <jwang308@ford.com> |  |  | - |  |  | No |  | -
SYNC+_0264 | F003951 | Air Quality | J# Health & Wellness | 1# Air Quality 空气质量 | EM(Electro-Mechanical) Register | 新增电动马达，可以提供循环扫风模式（上下扫/左右扫）， 崭新的HMI 更加Iintuitive 直观的展现风向，用户可以直接touch 来改变风向；自动循环扫风模式设计有风向变化动效直观展示变化；有预设模式，并记忆用户设置； 支持单个出风口控制， 和驾驶员/副驾乘客侧 多个出风口捆绑设置； - China Lead: 707 会配合语音控制一起打造 | BI | Wang, Wei (W.) <wwang199@ford.com> (Body) | Smith, George (G.) | EM Registers Function Spec 02162021_Climate System (1).docx EM Registers Function Spec 02162021_Climate System.docx EM Registers Function Spec 02162021_HMI System.docx EM Registers Function Spec 03252021.docx Feature Document 02242021 EM Register.docx EM Registers Function Spec 06072021_HMISystem.docx EM_Registers_FeatureDocument2_0_06072120.docx FIS_06072021_GE2_Variant_v102 6-7-21.docx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st | Y-1st | DCV4 | 2022-03-23 | 2022-04-06 | Y | Minor |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Wang, Wei (W.) <wwang199@ford.com> | Smith, George (G.) | - | - | - | N | N |  | Wang, Wei (W.) <wwang199@ford.com> (Body) |  | N/A | - | N | N |  | Wang, Wei (W.) <wwang199@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | Y | C/O |  |  | Vandenbrink, Terry (T.) |  | DCV Beta |  | N | N |  | Wang, Wei (W.) <wwang199@ford.com> (Body) | Vandenbrink, Terry (T.) |  | DCV Beta |  | Phase5 | No | Group A | DCV Beta
SYNC+_0266 |  | Car Model | Q# Seamless Interface | 4# Intuitive Vehicle Control | Lancher - 3D Car Model with vehicle controls | This is a replacement of the format of the Launcher Car model with added functionality. Number of vehicle controls / functionalities will be added into this model. Need Kanzi rendering engine. the 3D object can be references in term of the structure for other programs, however it will still be a unique model for each program since each vehicle looks different. | HMI | 4_HMI Yao, Jeffery (J.) <jyao12@ford.com> - FO assign之前可以联系 |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st | Y-1st | DCV1 | 2021-12-15 | 2021-12-29 | Y | Major |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | Y | Major | 新的3D 车模渲染 | HMI Yao, Jeffery (J.) <jyao12@ford.com> - FO assign之前可以联系 |  | DCV0 | 2022-04-30 | - | Y | Major | New HMI layout and UE for 12.3'+27' Display | Yao, Jeffery (J.) <jyao12@ford.com> - FO assign之前可以联系 |  | Group B | DCV Beta1 | Y | Major | New HMI layout and UE for 12.3'+27' Display | Yao, Jeffery (J.) <jyao12@ford.com> - FO assign之前可以联系 |  | Group B | DCV Beta1 | Y | Major | New Car Model | 4_HMI Yao, Jeffery (J.) <jyao12@ford.com> - FO assign之前可以联系 |  | DCV0 |  |  | Y | TBD |  |  |  |  | DCV0 |  | Y | Y |  | 4_HMI Yao, Jeffery (J.) <jyao12@ford.com> - FO assign之前可以联系 |  |  | DCV0 |  | Phase5 | No | Group A | DCV0
SYNC+_0070 |  | VPA | C# Intelligent Digital Assitant 智能数字助手 | 5# VPA 形象化语音助手 | 语音助手VPA 1.0 (形象化的语音助手） | Avatar Only. 语音助手形象化。 |  | Suo, Feifei (F.) <FSUO@ford.com> |  |  | Core_Service_Supplier | 0% | 0% | 0% | 100% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Suo, Feifei (F.) <FSUO@ford.com> |  | - | - | - | N | N |  | Suo, Feifei (F.) <FSUO@ford.com> |  | N/A | - | N | N |  | Suo, Feifei (F.) <FSUO@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  | Yang, Chris (K.) <kyang21@ford.com> |  |  | - |  | Phase 3 | No |  | -
SYNC+_0009 |  | VHA | H# Service & Maintenance 车主服务 | 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | 车辆状态 Vehicle Status (Vehicle Locator车辆位置, Mileage总里程, DTE 续航里程， Tire Pressure 胎压）On IVI 或Fordpass/Lincoln Way， 同时支持智能音箱在家查询. | Bin to SYNC+0122 from Phase 2. (Vehicle Locator车辆位置, Mileage总里程, DTE 续航里程， Tire Pressure 胎压。 车辆位置-熄火时最后的位置同步到FordPass/Lincoln Way.位置准确度有限， 更多用来标准大概区域。 IVI 端显示内容取决于项目仪表(大小，其他影响), 具体项目落地情况需与项目确认. Phase 1- 信息来源不同Cluster/TCU/ Phase 2- 全部TCU 提供信息 | EESE | Chen, Wei (W.) <WCHEN160@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Lu, Chao (C.) <clu42@ford.com> |  | - | - | - | N | N |  | Chen, Wei (W.) <WCHEN160@ford.com> |  | N/A | - | N | N |  | Lu, Chao (C.) <clu42@ford.com> |  | N/A | N/A | N | N | N | Chen, Wei (W.) <WCHEN160@ford.com> | N | - | N | N | N | N | [6 empty] | N | N | [6 empty] | Phase 1 | No
SYNC+_0127 |  |  | I# Safety & Security 安全 | 1# Emergency Services 紧急救援 | 紧急救援Emergency Assistance (EA) | 紧急救援，被动触发。 Emergency Assistance will be triggered when airbag pump out or oil pipe line cut off. An emergency call will be placed to China call center (95智驾 by customer's phone connected with Sync+ by bluetooth, and after line open, call center will provide corresponding services per customer's needs. | ECDX | Ren, Siyuan (Alex.) <sren6@ford.com> |  | Draft Emergency Assistance APIM_DuerOS SPSS.pdf | Ford_InHouse | 25% | 0% | 75% | 0% | Y | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Ren, Siyuan (Alex.) <sren6@ford.com> |  | - | - | - | N | N |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  | N/A | - | N | N |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  | N/A | N/A | Y | Minor | Adapt new scree size 12' | Ren, Siyuan (Alex.) <sren6@ford.com> |  | 没有这个功能，与Ren siyuan确认下 |  |  | N | N |  |  |  |  | - |  | N | N |  | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | - |  | Phase 3 | No |  | -
SYNC+_0163 |  |  | M# Personalization & Account 账号和个人设置 | 1# Account 账号 | 车机端百度账号登陆(By 福特派/lincoln app) Baidu Login |  | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  | 【福特phase5】MRD_账号模块个人中心 ID0164_林肯CDX707CDX747福特CDX788_V1.2_2021_05_14.docx | SW_Tier1 | 0% | 100% | 0% | 0% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Wang, Johnny (J.) <jwang308@ford.com> |  | - | - | - | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A | - | N | N |  | Wang, Johnny (J.) <jwang308@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N | [6 empty] | N | N | [6 empty] | Phase 1 | No
SYNC+_0267 |  | AR Navigation | A# Navigation 地图导航 | 5# AR Navigation AR 导航 | AR HUD | AR Navi on Windshield. May have more to add on later on. | EESE | Zhang, Yong (Y.) <YZHAN468@ford.com> |  |  | SW_Tier1 | 30% | 60% | 0 | 10% | Y-1st | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | Y-1st | NEW | 需要在AR HUD 显示导航、ADAS、车速、等相关信息 | Zhang, Yong (Y.) <YZHAN468@ford.com> |  | DCV2 | 2022-02-12 | - | N | N |  | Zhang, Yong (Y.) <YZHAN468@ford.com> |  | N/A | - | N | N |  | Zhang, Yong (Y.) <YZHAN468@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | Y-Study | N |  | Zhang, Yong (Y.) <YZHAN468@ford.com> |  |  | - |  |  |  | - | DCV0
SYNC+_0269 |  | Launcher | K# Social & Operation 社交及运营服务 | 1# Life Service 生活服务 | 天气 Weather | phase1-4是launcher 一部分。 Phase 5 作为独立App。显示天气， PM2.5 (点击进入AAR 界面）等。目前只显示当天的。资源方：百度. |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y-1st | DCV2 | 2022-01-12 | 2022-01-26 | Y | Y |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | HMI UIUE change | Shi, Stella (J.) <jshi32@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  | Group D | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  | Group D | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Shi, Stella (J.) <jshi32@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | DCV Beta |  | Phase5 | No | Group A | DCV Beta
SYNC+_0270 |  |  | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 1.0 | CNECDMPORT-136，CNECDMPORT-135(CX727) |  | Guo, Edward (T.) <tguo9@ford.com> | [8 empty] | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | N | N |  | Guo, Edward (T.) <tguo9@ford.com> |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | -
SYNC+_0271 |  |  | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 1.5 | CNECDMPORT-343 |  | Guo, Edward (T.) <tguo9@ford.com> | [8 empty] | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | N | N |  | Guo, Edward (T.) <tguo9@ford.com> |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | -
SYNC+_0272 |  |  | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 2.0 | CNECDMPORT-440 | ECDX | Zhou, Calvin (.) <QZHOU31@ford.com> | [8 empty] | Y-first | R00 | 2022-05-18 | 2022-06-01 | N | N |  |  |  | TBD |  |  | Y-OTA | C/O | N | Zhou, Calvin (.) <QZHOU31@ford.com> |  | R08 | 2023-06-24 | 2023-07-07 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Stella (J.) <jshi32@ford.com> |  | Group D | DCV Alpha2 | Y | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | R00
SYNC+_0273 |  |  | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | Remote Window Control / Window Status (China) | CNECDMPORT-413 | ECDX | Lin, Shawn (X.) <xlin17@ford.com> | [8 empty] | N |  |  |  | On Hold | N |  |  |  | DCV2 | 2023-01-24 | - | N | OnHold |  | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | On Hold | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV1 | On Hold | Minor | New HMI layout and UE for 12.3'+27' Display | Lin, Shawn (X.) <xlin17@ford.com> |  | N/A: Group A; N/A: DCV1; N: On Hold; N: Lin, Shawn (X.) <xlin17@ford.com>; -: DCV2; Y: N; C/O: N |  |  |  |  | - |  | On Hold | N |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | DCV3 |  |  |  | Group A | DCV3
SYNC+_0275 |  |  | J# Health & Wellness | Ford_Signature Experience_Welcoming & Empathetic | SenseMyMood 1.0 | CNECDMPORT-347 | ECDX | Zhou, Calvin (.) <qzhou31@ford.com> | [8 empty] | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | N | N |  | Zhou, Calvin (.) <qzhou31@ford.com> |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | -
SYNC+_0276 |  |  | J# Health & Wellness | Ford_Signature Experience_Welcoming & Empathetic | SenseMyMood 2.0 |  | ECDX | Zhou, Calvin (.) <qzhou31@ford.com> | [8 empty] | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | N | N |  | Zhou, Calvin (.) <qzhou31@ford.com> |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | -
SYNC+_0277 |  |  | J# Health & Wellness | Ford_Signature Experience_Welcoming & Empathetic | SenseMyMood 3.0 |  | ECDX | Zhou, Calvin (.) <qzhou31@ford.com> | [8 empty] | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | N | N |  | Zhou, Calvin (.) <qzhou31@ford.com> |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | -
SYNC+_0278 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Embrace | Digital Embrace 1.0 | CNECDMPORT-375 | ECDX | 1_to_Efirst, no yet FO assign |  |  | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | N |  |  |  | Y | N |  |  |  | DCV2 | 2023-01-24 | - | N | N | N |  |  | - | - | - | Y | New |  |  |  | Group C | DCV1 | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | Y | TBD – C/O 707 |  |  |  |  | DCV2 |  | Y | C/O |  | Zhang, Xu (X.) <XZHAN304@ford.com> |  |  | DCV2 |  |  |  |  | DCV2
SYNC+_0279 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Embrace | Digital Embrace 2.0 |  | ECDX | 0_ideation, no yet FO assign | [8 empty] | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | N | N |  | 0_ideation, no yet FO assign |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | DCV2
SYNC+_0280 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Embrace | Digital Embrace 3.0 |  | ECDX | 0_ideation, no yet FO assign | [8 empty] | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | N | N |  | 0_ideation, no yet FO assign |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | -
SYNC+_0281 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Rejuvenate | Smart Wellness 1.0 | CNECDMPORT-397 | ECDX | Zhou, Calvin (.) <qzhou31@ford.com> | [8 empty] | N |  |  |  | Y | Y |  |  |  | DCV3 | 2023-02-24 |  | N | N | N |  |  | - | - | - | N | C/O |  | Zhou, Calvin (.) <qzhou31@ford.com> |  | Group C | DCV2 | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | Y | TBD – C/O 707 |  |  |  |  | DCV3 |  | Y | C/O |  | Zhou, Calvin (.) <qzhou31@ford.com> |  |  | DCV3 |  |  |  |  | R00
SYNC+_0282 |  |  | J# Health & Wellness | Lincoln_Signature Experience_Rejuvenate | Smart Wellness 2.0 |  | ECDX | 0_ideation, no yet FO assign | [8 empty] | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | N | N |  | 0_ideation, no yet FO assign |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | -
SYNC+_0283 |  |  | H# Service & Maintenance 车主服务 | 6# Customer Care 客户关怀 | FNOC 1.0 | CNECDMPORT-613 FNOC－First Notification of Care - Weather related |  | Chen, Wei (W.) <WCHEN160@ford.com> | [7 empty] | Y-1st | N |  |  |  | N | N |  |  |  | DCV3 | 2023-02-24 | - | N | N | N | Hu, Lina (L.) LHU31@ford.com |  |  | - | - | N | N |  | 0_ideation, no yet FO assign |  | N/A | - | N | Minor | New HMI layout and UE for 12.3'+27' Display | 0 |  | Group C | DCV2 | Y | Minor | Adapt new scree size 12' | Chen, Wei (W.) <WCHEN160@ford.com> |  | DCV3 |  |  | N | N |  |  |  |  | - |  | Y | C/O |  | Chen, Wei (W.) <WCHEN160@ford.com> |  |  | - |  |  |  | - | DCV3
SYNC+_0284 |  | VHA | H# Service & Maintenance 车主服务 | 3# Vehicle Health Alert (VHA) 车辆健康状况提醒 | FNOS | CNECDMPORT-114 - Oil Life Prediction / China SYNC+ IVI |  | Chen, Wei (W.) <WCHEN160@ford.com> | [8 empty] | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | Y | C/O | N | Hu, Lina (L.) LHU31@ford.com |  | DCV3 | - | - | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, Wei (W.) <WCHEN160@ford.com> |  | N/A | N/A | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, Wei (W.) <WCHEN160@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | Y | TBD |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  | - | -
SYNC+_0262 |  |  | G# Remote Control 远程控制 | 1# FordPass Remote Control 福特派远程控制 | (App only ,no impact IVI )远程车门关闭状态显示/查看 Vehicle Locking Status Check; | 功能描述：Fordpass APP 端 显示车门上锁的状态。 硬件依赖/开发量： App 端 UI 变更 + 车端TCU 测试验证. OTA：无需OTA. 手机端更新。 车端需要部署相应的测试工作。 部署现状： Fordpass - Timing：Q2/Q3 2021 -Lead Program: CD727; LincolnWay- Planned for CD764. Currently prioritize for Phase 4 车型。Phase 1-3, 没有技术方面的阻碍，更多的是allocate limited resource for priority programs. | ECDX | Lin, Shawn (X.) <xlin17@ford.com> | [7 empty] | Y | N |  |  |  | Y | N |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | xlin17@ford.com |  | - |  |  | Y | New |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | New |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | DCV Beta |  |  |  | Group A | DCV0
SYNC+_0285 |  |  | H# Service & Maintenance 车主服务 | 1# Life Service 生活服务 | (百度小程序) 加油 - Oil Service | 小桔加油，易加油，团油 | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | Y |  |  |  | DCV3 | 2022-07-11 | 2022-07-26 | Y | Minor | 小程序 | Jessica yang<yyang158@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | Y | Minor | HMI 适配 | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV2 | Y | Minor | HMI 适配 | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV2 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV3 |  |  | Y | C/O Mini app 707 |  |  |  |  | DCV1 |  | N | N |  | Xie, Jie (J.) <JXIE49@ford.com> |  |  | DCV2 |  |  |  | Group C | DCV3
SYNC+_0286 |  |  | H# Service & Maintenance 车主服务 | 1# Life Service 生活服务 | (百度小程序) 洗车 - Car wash | 途虎洗车，盛大，橙牛 | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y-1st | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | Y |  |  |  | DCV3 | 2022-07-11 | 2022-07-26 | Y | Minor | 小程序 | Jessica yang<yyang158@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | Y | Minor | HMI 适配 | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV2 | Y | Minor | HMI 适配 | Wang, Johnny (J.) <jwang308@ford.com> |  | Group E | DCV2 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV3 |  |  | Y | C/O Mini app 707 |  |  |  |  | DCV1 |  | Y | C/O |  | Xie, Jie (J.) <JXIE49@ford.com> |  |  | DCV2 |  |  |  | Group C | DCV3
SYNC+_0287 |  |  | K# Social & Operation 社交及运营服务 | 6# Marketplace / Apps Anywhere 应用商店 | Market Place | CNECDMPORT-189 | ECDX | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Ford_InHouse | 0% | 0% | 100% | 0% | Y-1st |  |  |  |  | Y |  |  |  |  | DCV3 | 2022-07-11 | 2022-07-26 | Y | Minor | 小程序 | Wang, Johnny (J.) <jwang308@ford.com> |  | DCV3 | 2022-09-10 | 2022-09-24 | Y | New |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group C | DCV2 | Y | New |  | Wang, Johnny (J.) <jwang308@ford.com> |  | Group C | DCV2 | Y | Minor | Adapt new scree size 12' | Wang, Johnny (J.) <jwang308@ford.com> |  | TBD |  |  | Y | C/O |  |  |  |  | DCV3 |  | Y | C/O |  | Chen, Joey (Jun.) |  |  | DCV3 |  |  |  | Group C | DCV3
SYNC+_0077 |  | V2X | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 5G 车路协同 5G V2V | Global V2V including 1- Intersection Movement Assist(IMA) 2-Left Turn Assist(LTA); 3- Emergency Electronic Brake Light(EEBL).V2X including V2I and V2V and further more. | EESE | Wu, Jianfei(J.) |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y-1st | Y-1st | R00 | 2022-05-18 | 2022-06-01 | Y | C/O |  |  |  | DCV3 | 2023-02-24 | - | N | N | N |  |  | - | - | - | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhang, Kerry (Y) <yzhan142@ford.com> |  | Group C | R06 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhang, Kerry (Y) <yzhan142@ford.com> |  | Group C | R06 | N | N | N |  |  | - | N | N | Y | C/O |  |  |  |  | R05 |  | N | N |  |  |  |  | DCV3 |  | Phase 5 | No | Group C | DCV3
SYNC+_0082 |  | V2X | D# Co-Pilot360 驾驶辅助 | 2# Help Me Drive 驾驶辅助 | 车路协同 V2I Lite (Beta) | 纯软件的基于IVI 的China Local Solution including 4 features •Traffic Light Information(TLI) •Green Light Notification (GLN) •Green Light Optimal Speed Advisory(GLOSA) •Red Light Violation Warning(RLVW) | EESE | Li, Yifei (Y.) <nli26@ford.com> |  |  | Ford_InHouse | 0% | 20% | 60% | 20% | N | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | N | N |  | Li, Yifei (Y.) <nli26@ford.com> |  | N/A | - | N | N |  | Li, Yifei (Y.) <nli26@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  | Li, Yifei (Y.) <nli26@ford.com> |  |  | - |  | Phase 3 | No | Group B | -
SYNC+_0232 |  | V2X | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | Night Vision | from 747 prioritized global OTA concepts Act as a guardian by providing a sense of safety and security in dark areas by highlighting animals, pedestrians and objects in the field of view when the customer is away from or inside their vehicle |  | 3_No yet China FO assign |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y-1st | N |  |  |  | Y-1st | New |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | N | N | N |  |  | - | - | - | N | N |  | 3_No yet China FO assign |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | TBD | TBD |  |  |  |  | - |  | N | N |  |  |  |  | DCV3 |  | Phase5 | No | Group A | DCV3
SYNC+_0274 |  |  | R# EV Features 新能源汽车功能 | 1# Charging | BEV Unique Charging - FB5 | Trip Planner(APP/IVI) Intelligent Range(CE-DTE) FB4 C/O enhancement(Preferred Charging time/departure time) | ECDX | Peng, Ivan (F.) <FPENG6@ford.com> | [7 empty] | Y | N |  |  |  | N |  |  |  |  | N/A | N/A | N/A | N | [7 empty] | N | N |  | Peng, Ivan (F.) <FPENG6@ford.com> |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | N | N |  |  |  |  | - |  |  |  |  | -
SYNC+_0288 | F001670 |  | E# Access & Authorization 车钥匙 | 2# Phone As A Key (PaaK) 手机钥匙 | 手机钥匙 BUN Paak | CNECDMPORT-269 BUN Paak apply to FNV3 based programs. | ECDX | Chen, Kiefer (Y.) <ychen290@ford.com> | [7 empty] | Y-1st |  |  |  |  | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | N | [7 empty] | N | N |  | Zou, Hong (H.) <HZOU9@ford.com> |  | N/A | - | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | Y | C/O 747 |  |  | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  | N | N |  |  | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  |  |  |  | DCV0
SYNC+_0289 |  |  | K# Social & Operation 社交及运营服务 | Ford/Lincoln/BEV - Signatuer Experience | Lidget/Fidget/Widget 3.0 | CNECDMPORT-651 | ECDX | Zhou, Calvin (.) <QZHOU31@ford.com> | [5 empty] | 100% |  | Y-1st |  |  |  |  | Y | Y |  |  |  | DCV3 |  |  | N | [7 empty] | TBD | New |  | Zhou, Calvin (.) <QZHOU31@ford.com> |  | Group C | DCV2 | TBD |  |  | Zhou, Calvin (.) <QZHOU31@ford.com> |  | Group C | DCV2 | N | N | N | N | N | - | N | N | Y | TBD – C/O 764 |  |  |  |  | DCV3 |  | Y | C/O |  | Zhou, Calvin (.) <QZHOU31@ford.com> |  |  | DCV3 |  |  |  |  | DCV3
SYNC+_0025 |  | VR | C# Intelligent Digital Assitant 智能数字助手 | 1# Voice Interaction Capability 语音交互能力 | Voice Recognition Systems | Input is using your voice to start a command. Output is things like infotainment, navigation, phone, and media can be controlled through voice. |  | Zhang, Meijuan (M.) <MZHAN102@ford.com> |  |  | SW_Tier1 | 0 | 100% | 0 | 0 | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | Y |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y |  |  |  |  | DCV Beta |  |  | Y |  |  |  |  | Group A | DCV Alpha2 | Y |  |  |  |  | Group A | DCV Alpha2 | Y | C/O |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z0023 |  |  | T# System Function 系统功能 | Carrier | 流量套餐app端流量查询购买 data plan query & order | 流量套餐app端流量查询购买 data plan query & oder TCU- 用户流量统计及购买/Cellular data purchase and management Setting 流量管理 | ECDX |  |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | N | N | Move to 4G/5G subscription | Lu, Chao (C.) <clu42@ford.com> |  |  |  |  | Y | C/O |  | Lu, Chao (C.) <clu42@ford.com> |  | Group B | DCV1 | Y | C/O |  | Lu, Chao (C.) <clu42@ford.com> |  | Group B | DCV1 | Y | Minor | Adapt new scree size 12' |  |  | DCV2 |  |  | Y | C/O |  |  |  |  | DCV2 |  | N | C/O |  |  |  |  | DCV2 |  | Phase 1 | No | Group B | DCV2
SYNC+_Z0032 | F001040/E |  | T# System Function 系统功能 | Connected Services | CCS (Customer Connectivity Setting) | 中国SYNC+ IVI端没有专门固定的设置界面。(global 版是一直有的）。中国采用用户授权 (手机端触发），允许后台获取用户数据（TCU） | ECDX | Gu, Regina (Q.) <qgu12@ford.com> | Pechlivanidis, Savvas (S.) | Customer Connectivity Settings Client APIM SPSS v1.5 Apr 22, 2020.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Gu, Regina (Q.) <qgu12@ford.com> | Pechlivanidis, Savvas (S.) | DCV1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  | Group A | DCV Alpha2 | N | Minor | Adapt new scree size 12' | Gu, Regina (Q.) | Ogail, Khaled (K.) <kogail@ford.com> | - |  |  | Y | C/O |  |  | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  | Y | C/O |  | Gu, Regina (Q.) <QGU12@ford.com> | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_0290 |  |  |  |  | 人脸识别账户登录Face ID - Driver (DAT-DSMC) | CDX707 first deployed this feature on DAT -DSMC camera. | EESE | 6_目前funding只cover707,Jia, Elaine (T.) <tjia2@ford.com> |  |  | SW_Tier1 | 30% | 70% | 0% | 0% | Y-1st | Y | DCV1 | 2021-12-15 | 2021-12-29 | N | N |  |  |  | N/A | N/A | N/A | Y |  |  |  |  | DCV Beta | 2022-03-12 | 2022-03-19 | N |  |  |  |  | N/A |  | N |  |  |  |  | N/A | N/A | N | N | N | N | N | - | N | N | N | N |  |  |  |  | - |  | Y | C/O |  | 6_目前funding只cover707,Jia, Elaine (T.) <tjia2@ford.com> |  |  | - |  |  |  |  | DCV1
SYNC+_0293 |  |  | R# EV Features 新能源汽车功能 | 1# Charging | EV Charge Programming | [15 empty] | Y | New |  | Peng, Ivan (F.) FPENG6@ford.com |  | DCV Beta1 | 2022-08-31 | - | N | [12 empty] | N/A | N/A | [5 empty] | N/A | N/A | N | N | N |  |  | - | N | N | N | N |  |  |  |  | - |  | Y | C/O |  | Peng, Ivan (F.) FPENG6@ford.com |  |  | - |  |  |  |  | -
SYNC+_0294 |  |  | R# EV Features 新能源汽车功能 | 1# Charging | EV Trip Planner | [15 empty] | Y | New |  | Peng, Ivan (F.) FPENG6@ford.com |  | DCV Beta1 | 2022-08-31 | - | N | [12 empty] | N/A | N/A | [5 empty] | N/A | N/A | N | N | N |  |  | - | N | N | N | N |  |  |  |  | - |  | Y | C/O |  | Peng, Ivan (F.) FPENG6@ford.com |  |  | - |  |  |  |  | -
SYNC+_0295 |  |  | R# EV Features 新能源汽车功能 | Electric Distance To Empty (eDTE) | Intelligent Range(CE-DTE) | [15 empty] | Y | New |  | Peng, Ivan (F.) FPENG6@ford.com |  | DCV Beta1 | 2022-08-31 | - | N | [35 empty] | - |  | Y | C/O |  | Peng, Ivan (F.) FPENG6@ford.com |  |  | - |  |  |  |  | - | bar: N to N; - to TBD
SYNC+_0296 |  |  | K# Social & Operation 社交及运营服务 | 6# Subscription 订阅 | 4G/5G Entertainment Connectivity Subscription | CNECDMPORT-687 | ECDX | Qi, Xingyu (X.) <XQI15@ford.com> | [7 empty] | Y-1st |  |  |  |  | Y | [7 empty] | Y | C/O | Minor | Zhang, Rui (R.) RZHANG63@ford.com |  | DCV2 | [30 empty] | DCV2 |  | TBD | N |  | Qi, Xingyu |  |  | DCV2 |  |  |  |  | DCV2
SYNC+0291 |  |  |  |  | CX727 Super Entertainment Package | CNECDMPORT-679 At first multimedia entertainment is the most popular ways in Vehicle,Super Entertainment Package can better meet the needs and experience of most customers for vehicle entertainment. | [60 empty] | TBD | N |  | No FO
SYNC+0292 |  |  |  |  | DAT Subscription Service | CNECDMPORT-217 (CX727) | [60 empty] | Y-Study | N |  | No FO
SYNC+_0297 |  |  |  |  | Show car mode - CX | CNECDMPORT-687 | [60 empty] | Y | New |  | Sheng Ling
Minigame Center
Magic box 1.0
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline is CDX707
Note on AS1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline is CDX707
Note on AQ2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.8第一版功能release, 5.8完成所有切图
Note on AX2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3.8第一版功能release, 5.8完成所有切图
Note on AA3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm with Program with the stragety of AM/FM. --Frank Reply: deleted confirmed by tech planing
Note on AX3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: deleted by tech planing
Note on BN5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on BN12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on AX14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sulei: FO资源没有到位，HMI sign off时需要与FO hand shake
Note on BN15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beta也需集成相应feature
Note on BN16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beta也需集成相应feature
Note on BN17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beta也需集成相应feature
Note on BN18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beta也需集成相应feature
Note on BN19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beta也需集成相应feature
Note on BN20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beta也需集成相应feature
Note on BQ23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HW dependency
Note on AQ26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 需要sulei带回去再次study，SWAN相关会于group E中释放
Note on AX26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 需要sulei带回去再次study，SWAN相关会于group E中释放
Note on BE26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 与Nancy Liu沟通什么时候交付，Agile feature, 建议DCV2交付
Note on L28: Xia, Xiao Jin (X.): InHouse develop interface yzhan295@ford.com
Note on AI28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 所有信号相关于DCV Beta完成验证.
Note on AY28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change 'N/A' to 'DCV3'
Note on BE36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 与Nancy Liu沟通什么时候交付，Agile feature, 建议DCV2交付
Note on BE39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 与Nancy Liu沟通什么时候交付，Agile feature, 建议DCV2交付
Note on BN41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on BN44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on AQ46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: China unique solution, have opportunity to move to B/C
Note on AX46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: China unique solution, have opportunity to move to B/C
Note on BN49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on F55: Zhou, Jiajia (J.): 车机相册FDL有哪一方承担（SW_Tier1 or Inhouse），需要FO进一步确认
Note on L60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ford interface Lu, Chao (C.) <CLU42@ford.com>
Note on BE60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check with Jiajia
Note on V62: Ma, Jian (J.): CDX707 Study TIB12
Note on V65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cheier:会打包到Second Row的Online Cabin里
Note on AQ72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa: 需求未澄清
Note on AX72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa: 需求未澄清
Note on AA74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potential pull ahead this feature to DCV0.
Note on AQ76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa: 需要与studio确认时间, 建议Group A @Jack. Guo
Note on AX76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa: 需要与studio确认时间, 建议Group A @Jack. Guo
Note on BN81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on AA89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need further study.
Note on V91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Still on study，not in BoF
Note on BN93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on AQ94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI 3D car model UI sign off from 1215release source delay to 1.28
Note on AX94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI 3D car model UI sign off release source from 1.10 delay to 1.28
Note on AA113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Included in message center, Confirmed by Stone.
Note on AX113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need ECDX Chen.Wei confirm
Note on CA119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requirement and Road map should be confirmed by tech planning and program. --Frank.
Note on AA121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending requirement clarification.
Note on AR125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 语音设置需要在Group A中
Note on AY125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 语音设置需要在Group A中

## 02 Basic Function
Feature ID | VSEM ID | Component/s | Feature Product_Suite | Feature Group | Feature Name | Feature_Description | Lead Team | Local Feature Owner | Global Feature Owner | Dev_Spec | Feature Development Leader | HW_Tier 1 | SW_Tier 1 | Ford IVI In-House | Core Service Provider | Phase5 | CDX707 | Release Version in GPDS | Original Release Date to REC | Original Release Date to FO/CAF(2weeks) | CDX747 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | CDX747 Release Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | CX788 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release CX788 Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | U611 MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner | U611 HMI Group | U611 Release Version in GPDS | U625 MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner | U625 HMI Group | U625 Release Version in GPDS | P702MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release P702MCA Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | U718 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release U718 Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | CX821 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release P702MCA Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | 1st - phase # | Pre-DV Req | HMI Group | Target version
SYNC+_Z0283 |  | System Setting | T# System Function 系统功能 | Basic Function 基础功能 | 部分界面中英文显示 | 提供部分页面的英文显示用于支持北美工厂生产的下线测试。 | EESE | James, Chen |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y-1st | Y-1st | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  | James, Chen |  | - | - | - | Y | C/O |  | James, Chen |  | Group A | TBD | Y | C/O |  | James, Chen |  | Group A | TBD | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | James, Chen |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase5 | No | Group A | DCV Alpha
SYNC+_Z0284 |  | Funtion Safety | T# System Function 系统功能 | Basic Function 基础功能 | Funtion Safety | 需要支持功能安全相关的实现（包含仪表部分） | EESE | Ding,Dean |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y-1st | Y-1st | R04 | 2022-06-15 | 2022-06-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Ding,Dean |  | DCV1 | 2022-02-12 | - | Y | C/O |  | Ding,Dean |  | Group A | DCV0 | Y | C/O |  | Ding,Dean |  | Group A | DCV0 | Y | C/O |  | Ding,Dean |  | DCV 2 |  |  | Y | C/O |  | Ding,Dean |  |  | DCV Beta |  | Y | C/O |  | Ding,Dean |  | DCV 2 |  |  | Phase5 | No | Group A | DCV Alpha
SYNC+_Z1023 |  | ADAS Map | A# Navigation 地图导航 | Advance Map Function高级地图功能 | ADAS Map |  | EESE | Victor Cui <MCUI5@ford.com> |  |  | SW_Tier1 | 0% | 90% | 0% | 10% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Victor Cui <MCUI5@ford.com> |  | R01 | 2022-07-10 | 2022-07-24 | Y | C/O |  | Victor Cui |  | Group E | DCV1 | Y | C/O |  | Victor Cui |  | Group E | DCV1 | Y | C/O |  | Victor Cui <MCUI5@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Victor Cui <MCUI5@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Victor Cui <MCUI5@ford.com> |  | DCV Beta |  |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z1000 |  | Launcher | T# System Function 系统功能 | HMI人机交互 | Launcher UI 主页UI |  | HMI |  |  |  | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y | DCV1 | 2021-12-15 | 2021-12-19 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | HMI UIUE update |  |  | DCV Alpha | 2022-02-12 | - | Y | Major | New HMI layout and UE for 12.3'+27' Display |  |  | Group A | DCV Alpha1 | Y | Major | New HMI layout and UE for 12.3'+27' Display |  |  | Group A | DCV Alpha2 | Y | Major | Adapt new scree size 12' |  |  | DCV Alpha |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | Major | Adapt new scree size 12' |  |  | DCV Alpha |  |  | Phase 1 | No | Group A | DCV Alpha
SYNC+_Z1001 |  | System UI | T# System Function 系统功能 | HMI人机交互 | System UI 系统UI |  | HMI | Luisa, Liu |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-19 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | HMI UIUE update | Luisa, Liu |  | DCV Alpha | 2022-02-12 | - | Y | Major | New HMI layout and UE for 12.3'+27' Display | Luisa, Liu |  | Group A | DCV Alpha1 | Y | Major | New HMI layout and UE for 12.3'+27' Display | Luisa, Liu |  | Group A | DCV Alpha2 | Y | Major | Adapt new scree size 12' | Luisa, Liu |  | DCV Beta |  |  | Y | C/O |  | Luisa, Liu |  |  | DCV Beta |  | Y | Major | Adapt new scree size 12' | Luisa, Liu |  | DCV Beta |  |  | Phase 1 | No | Group A | DCV Alpha
SYNC+_Z0002 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | A2B Functional | A2B 音频数据总线高低音质衔接功能 | EESE | Liu, Yang (Y.) <YLIU307@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | Major |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | N | Liu, Yang (Y.) <YLIU307@ford.com> |  | DCV Beta1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Liu, Yang (Y.) <YLIU307@ford.com> |  | Group A | DCV1 | Y | C/O |  | Liu, Yang (Y.) <YLIU307@ford.com> |  | Group A | DCV1 | Y | C/O |  | Liu, Yang (Y.) <YLIU307@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Liu, Yang (Y.) <YLIU307@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Liu, Yang (Y.) <YLIU307@ford.com> |  | DCV Alpha |  |  | Phase 1 | Yes | Group A | DCV Alpha
SYNC+_Z0003 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Active Noise Cancellationg (ANC) Tuning | ANC/ESE Tuning | VE | Yao, Keita (Y.) <yyao21@ford.com> |  | Electrical Sound Enhancement SPSS_Diagnostics.pdf Electrical Sound Enhancement SPSS V1.2 Oct 27, 2017.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | R04 | 2022-06-15 | 2022-06-29 | N | N |  |  |  | N/A | N/A | N/A | Y | C/O | N | Yao, Keita (Y.) <yyao21@ford.com> |  | DCV0 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  | Group A | DCV3 | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  | Group A | DCV3 | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  |  | DCV Beta1 |  | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  | DCV Alpha |  |  | Phase 2 | Yes |  | DCV Alpha
SYNC+_Z0004 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Audio Management |  | EESE | MXIA13@ford.com |  | Audio Management APIM Imp Guide v1.5.1 Sep 26, 2018.xlsx Audio Management Logical to Physical CAN signal mapping Sep 7, 2018.docx Audio Management SPSS v1.5 Sep 7, 2018.pdf Audio Management Supplement SYNC 4.1 July 13th, 2018.docx Audio Settings Deployment May 9th, 2019.docx Audio Settings Logical to Physical CAN signal mapping Sep 6, 2018.docx Audio Settings v2 APIM Imp Guide v1.1 May 23, 2019.xlsx Audio Settings v2 APIM SPSS v1.1 May 23, 2019.pdf | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y | Y | DCV Beta | 2021-07-18 | - | Y | Major |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | N | MXIA13@ford.com |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li Alvin (LLI156@ford.com) |  | Group A | DCV Alpha1 | Y | C/O |  | Li Alvin (LLI156@ford.com) |  | Group A | DCV Alpha2 | Y | C/O |  | MXIA13@ford.com |  | DCV Beta |  |  | Y | C/O |  | MXIA13@ford.com |  |  | DCV Beta |  | Y | C/O |  | MXIA13@ford.com |  | DCV Beta |  |  | Phase 4 | Yes | Group A | DCV0
SYNC+_Z0005 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Brand Audio Config (Lincoln/Ford) | 品牌音箱调校 | EESE | Tian, Chen (C.) <CTIAN3@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | Major |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | N | Tian, Chen (C.) <CTIAN3@ford.com> |  | DCV Beta1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Tian, Chen (C.) <CTIAN3@ford.com> |  | Group A | DCV Alpha1 | Y | C/O |  | Tian, Chen (C.) <CTIAN3@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Tian, Chen (C.) <CTIAN3@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Tian, Chen (C.) <CTIAN3@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Tian, Chen (C.) <CTIAN3@ford.com> |  | DCV Alpha |  |  | Phase 1 | No | Group A | DCV Alpha
SYNC+_Z0006 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Engine Sound Enhancement (ESE) | ESE Tuning 引擎音增强 | VE | Yao, Keita (Y.) <yyao21@ford.com> |  | Electrical Sound Enhancement SPSS_Diagnostics.pdf Electrical Sound Enhancement SPSS V1.2 Oct 27, 2017.pdf Electrical Sound Enhancement Sub-SYNC Imp Guide V1.0 Oct 27, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | N | N |  |  |  | N/A | N/A | N/A | N |  |  | Yao, Keita (Y.) <yyao21@ford.com> |  | - | - | - | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  | Group A | DCV1 | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  | Group A | DCV1 | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  | DCV Beta1 |  |  | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  |  | DCV Beta1 |  | Y | C/O |  | Yao, Keita (Y.) <yyao21@ford.com> |  | DCV Beta1 |  |  | Phase 1 | No |  | DCV Alpha
SYNC+_Z0007 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | EQ tool |  | EESE | Liu, Yang (Y.) <yliu307@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | Major |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Liu, Yang (Y.) <yliu307@ford.com> |  | DCV Beta1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Liu, Yang (Y.) <yliu307@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Liu, Yang (Y.) <yliu307@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Liu, Yang (Y.) <yliu307@ford.com> |  | DCV Beta1 |  |  | Y | C/O |  | Liu, Yang (Y.) <yliu307@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Liu, Yang (Y.) <yliu307@ford.com> |  | DCV Beta1 |  |  | Phase 2 | Yes | Group A | DCV Alpha
SYNC+_Z0008 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Lincoln more speakers audio & ANC tuning | Lincoln more speakers audio & ANC tuning. Revel QLI | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | Major |  |  |  | DCV Beta1 | 2022-08-31 | - | N |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  | - | - | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV3 | N | N | N | N | N | N | DCV3 | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | - |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | - |  |  | Phase 2 | No | Group A | DCV Alpha
SYNC+_Z0009 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Lincoln Rear Audio Controls | Touch screen U611 | EESE | Chen, James (J.) <jchen303@ford.com> |  | Rear Audio Control APIM SPSS v1.4 Jul 1, 2017.pdf Rear Audio Control APIM Imp Guide v1.4 Jul 1, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y-1st | New |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | N |  |  | Chen, James (J.) <jchen303@ford.com> |  | - | - | - | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | Group A | DCV Alpha2 | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | N | N | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | - |  |  | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  |  | DCV Beta |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | - |  |  | Phase 2 | No | Group A | DCV Alpha
SYNC+_Z0010 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Noise cancellation for Baidu VR |  | EESE | Qi Xuliang/Alvin Li |  | Voice recognition spec - 20191121.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV0 | 2021-10-20 | 2021-11-03 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Zhang, Meijuan (M.) <MZHAN102@ford.com>/Alvin Li |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Qi Xuliang/Alvin Li |  | Group A | DCV3 | Y | C/O |  | Qi Xuliang/Alvin Li |  | Group A | DCV3 | Y | C/O |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>/Alvin Li |  | DCV Alpha |  |  | Y | C/O |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>/Alvin Li |  |  | DCV0 |  | Y | C/O |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>/Alvin Li |  | DCV Alpha |  |  | Phase 1 | No | Group A | DCV Alpha
SYNC+_Z0011 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Radio reception test |  | EESE | Wu, Andy (Z.J.) <zwu21@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | Y | C/O | N | Wu, Andy (Z.J.) <zwu21@ford.com> |  | DCV2 | 2022-08-10 | 2022-08-24 | Y | C/O |  | Wu, Andy (Z.J.) <zwu21@ford.com> |  | Group A | DCV1 | Y | C/O |  | Wu, Andy (Z.J.) <zwu21@ford.com> |  | Group A | DCV1 | Y | C/O |  | Wu, Andy (Z.J.) <zwu21@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Wu, Andy (Z.J.) <zwu21@ford.com> |  |  | - |  | Y | C/O |  | Wu, Andy (Z.J.) <zwu21@ford.com> |  | DCV Alpha |  |  | Phase 1 | No | Group C | DCV Alpha
SYNC+_Z0012 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Rear Audio Controls | Ford - Hard button/Touch screen U611 | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Rear Audio Control APIM SPSS v1.4 Jul 1, 2017 Rear Audio Control APIM Imp Guide v1.4 Jul 1, 2017 | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | N |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  | - | - | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha1 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | N | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | - |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | N | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | - |  |  | Phase 4 | No | Group A | DCV Alpha
SYNC+_Z0013 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Revel QIS 3D Audio (Audio System, settings) | Lincoln -only | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Audio Settings APIM SPSS v1.4 Nov 6, 2019 Audio Settings APIM Imp Guide v1.4 Nov 6, 2019 | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  | - | - | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N | N | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | - |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | - |  |  | Phase 4 | No | Group A | DCV Alpha
SYNC+_Z0014 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Speakers Config | Ford - up to 14 speakers. Lincoln - Up to 28 speakers （U611). Revel with QLI | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-19 | Y | Major |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV0 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha1 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Alpha |  |  | Phase 2 | No | Group A | DCV Alpha
SYNC+_Z0015 |  | Log System | T# System Function 系统功能 | Basic Function 基础功能 | Log system |  | EESE | Chen, Deyin |  | Phase5 CDC Log System Specification.docx | HW_Tier1 | 60% | 10% | 10% | 20% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Alpha | 2022-05-30 | - | Y | C/O | N | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | N/A | DCV Alpha1 | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | DCV Alpha |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Alpha |  |  | Phase 4 | Yes | NA | DCV Alpha
SYNC+_Z0017 |  | Ethernet | ZZ# Foundemental Function 基础功能 | Basic Function 基础功能 | Implement/Integrate Ford SOA Structure |  | EESE | Liu, Dapeng (D.) <dliu79@ford.com> |  | pending by Dapeng's input | Core_Service_Supplier | 25% | 0% | 0% | 75% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | FNV 架构变化 | Liu, Dapeng (D.) <dliu79@ford.com> |  | DCV1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0019 |  | BT Phone | T# System Function 系统功能 | Bluetooth 蓝牙 | Bluetooth Phone | 通话功能界面 请勿打扰 DO NOT IDSTURB 同步通讯录和通话记录 sync contacts& records 通讯录 contacts 通讯录搜索 拨号 dial 通话记录 records 电话设置 | EESE | Xu, Amy (X.) <xyafei@ford.com> |  | BT Connectivity APIM SPSS v3.0 Feb 14, 2019.pdf BT Connectivity APIM Imp Guide v3.0 Feb 14, 2019.xlsx Phase5 Bt多路电话--PRD.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0020 |  |  | ZZ# Foundemental Function 基础功能 | Carrier | Carrier | Carrier API integration with Baidu 与百度的接口集成- Carrier Backend Development 运营商后台开发 Carrier Feed API integration with FORD 与福特的接口集成 API integration with Baidu 与百度的接口集成 Carrier Backend Development 运营商后台开发 SIM Management SIM卡管理 retail data plan API, data usage query API, order API, payment API, invoice API, usage notification API, etc. RNR Carrier Feed associate 1 VIN with 2 SIMs; RNR platform; Online Mall; Jasper/M2M portal; Per APP billing, etc. | ECDX | Wang, Yuran<ywang422@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | N |  |  |  | Y | C/O |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | 百度侧与中国联通的开发工作已在CD542项目完成，无额外工作量。 | Wang, Yuran<ywang422@ford.com> |  | DCV1 | 2022-07-10 | 2022-07-24 | Y | C/O |  | Wang, Yuran<ywang422@ford.com> |  | Group B | DCV Beta1 | Y | C/O |  | Wang, Yuran<ywang422@ford.com> |  | Group B | DCV Beta1 | Y | C/O |  | Wang, Yuran<ywang422@ford.com> |  | DCV 0 |  |  | Y | C/O |  | Wang, Yuran<ywang422@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Wang, Yuran<ywang422@ford.com> |  | DCV 0 |  |  | Phase 1 | No | Group B | NA
SYNC+_Z0024 |  | Multi-Screen Interaction | T# System Function 系统功能 | 信息多屏互动 | 2D Map in Cluster (study) |  | EESE | Ding, Sunny (X.) <XDING13@ford.com> |  |  | SW_Tier1 | 40% | 60% | 0% | 0% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  | Ding, Sunny (X.) <XDING13@ford.com> |  | - | - | - | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> |  | Group C | DCV Alpha2 | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> |  | Group C | DCV Alpha2 | Y | Minor | Adapt new cluster scree size 12.3' | Ding, Sunny (X.) <XDING13@ford.com> |  | DCV 0 |  |  | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> |  |  | DCV0 |  | Y | Minor | Adapt new cluster scree size 12.3' | Ding, Sunny (X.) <XDING13@ford.com> |  | DCV 0 |  |  | Phase 4 | No | Group A | DCV0
SYNC+_Z0025 |  | Multi-Screen Interaction | T# System Function 系统功能 | 信息多屏互动 | 导航服务，转向、ETA等信息 turn lane,radar detector & ETA | CAN互动，消息协议由Ford定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | Core_Service_Supplier | 20% | 20% | 0% | 60% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N |  |  | Chen, James (J.) <jchen303@ford.com> |  | - | - | - | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | N/A | N/A | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | N | N | Y-1st | New |  | Chen, James (J.) <jchen303@ford.com> |  | DCV 0 |  |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  |  | - |  | Y-1st | New |  | Chen, James (J.) <jchen303@ford.com> |  | DCV 0 |  |  | Phase 1 | No |  | DCV0
SYNC+_Z0026 |  | Multi-Screen Interaction | T# System Function 系统功能 | 信息多屏互动 | 来电号码及名称显示，接听，挂电话 incoming caller ID display，answer call， hang-up call | CAN互动，消息协议由Ford定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | - | - | - | N |  |  | Chen, James (J.) <jchen303@ford.com> |  | - | - | - | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | Group C | DCV Alpha2 | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | Group C | DCV Alpha2 | Y | New |  | Chen, James (J.) <jchen303@ford.com> |  | DCV 0 |  |  | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  |  | DCV0 |  | Y | New |  | Chen, James (J.) <jchen303@ford.com> |  | DCV 0 |  |  | Phase 1 | No | - | DCV0
SYNC+_Z0027 |  | Multi-Screen Interaction | T# System Function 系统功能 | 信息多屏互动 | 仪表控制导航的功能：同步目的地收藏，设置目的地途经点Cluster control IVI Navigation。 | CAN互动，消息协议由Ford定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | Core_Service_Supplier | 20% | 20% | 0% | 60% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N |  |  | Chen, James (J.) <jchen303@ford.com> |  | - | - | - | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | N/A | N/A | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | N | N | Y | New |  | Chen, James (J.) <jchen303@ford.com> |  | DCV 0 |  |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  |  | - |  | Y | New |  | Chen, James (J.) <jchen303@ford.com> |  | DCV 0 |  |  | Phase 2 | No |  | DCV0
SYNC+_Z0028 |  | Multi-Screen Interaction | T# System Function 系统功能 | 信息多屏互动 | 广播，专辑信息、歌名、歌手 Album info,song & singer and Radio | CAN互动，消息协议由Ford定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | Core_Service_Supplier | 60% | 20% | 0% | 20% | Y | N |  |  | - | N | N |  |  |  | N/A | N/A | N/A | N |  |  | Chen, James (J.) <jchen303@ford.com> |  | - | - | - | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | N/A | N/A | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | N | N | Y | New |  | Chen, James (J.) <jchen303@ford.com> |  | DCV 0 |  |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  |  | - |  | Y | New |  | Chen, James (J.) <jchen303@ford.com> |  | DCV 0 |  |  | Phase 1 | Yes |  | DCV0
SYNC+_Z0030 |  |  | ZZ# Foundemental Function 基础功能 | Connected Services | Baidu数据平台 |  | ECDX | Fan, Henry (H.) <hfan11@ford.com> |  | PRD DUEROS_CVPP_Ford and Baidu Accoun_Phase 2_PRD_v1.4.pdf | SW_Tier1 | 0% | 90% | 10% | 0% | Y | Y | DCV0 | 2021-10-20 | 2021-11-03 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Fan, Henry (H.) <hfan11@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Fan, Henry (H.) <hfan11@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Fan, Henry (H.) <hfan11@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Fan, Henry (H.) <hfan11@ford.com> |  | R00 |  |  | Y | C/O |  | Fan, Henry (H.) <hfan11@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Fan, Henry (H.) <hfan11@ford.com> |  | R00 |  |  | Phase 1 | No | Group A | DCV Beta
SYNC+_Z0033 |  |  | ZZ# Foundemental Function 基础功能 | Connected Services | Provisioning | 1. IVI TCU Provisioning - Baidu cloud, Ford cloud 2. TCU/ECG/BLEM provisioning - Baidu cloud, Ford cloud | ECDX | Cui, Rebecca (H.) <hcui2@ford.com> |  | Peripheral Module Provisioning SPSS v1.3 Apr 10, 2019.pdf | SW_Tier1 | 10% | 80% | 0% | 10% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Cui, Rebecca (H.) <hcui2@ford.com> |  | R01 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Cui, Rebecca (H.) <hcui2@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Cui, Rebecca (H.) <hcui2@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Cui, Rebecca (H.) <hcui2@ford.com> |  | R00 |  |  | Y | C/O |  | Cui, Rebecca (H.) <hcui2@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Cui, Rebecca (H.) <hcui2@ford.com> |  | R00 |  |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0035 |  | Diagnostic | T# System Function 系统功能 | Diagnostic 诊断功能 | Fully Ford ECU Diagnostic&EOL |  | EESE | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | Y | C/O | N | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  | DCV0 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | DCV Beta | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | DCV Beta | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  | DCV 1 |  |  | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> Li, Xuedong (X.) <XLI244@ford.com> |  | DCV 1 |  |  | Phase 4 | No | NA | DCV Beta
SYNC+_Z0036 |  | Diagnostic | T# System Function 系统功能 | Diagnostic 诊断功能 | bezel diagnostic |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Bezel Diagnostics APIM SPSS v1.8 Sep 3, 2020.pdf Bezel Diagnostics APIM Imp Guide v1.8 Sep 3, 2020.xlsx Bezel Diagnostics Logical to Physical CAN signal mapping Sep 7, 2018.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | Minor |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV 1 |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV 1 |  |  |  | Yes | Group A | DCV Beta
SYNC+_Z0037 |  | Diagnostic | T# System Function 系统功能 | Diagnostic 诊断功能 | FNVx_Diagnostics_Analytics | log 小工具包含USB TCU Log， 以及上传云端。 | EESE | Liu, Dapeng (D.) <DLIU79@ford.com> |  |  | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | Y | Major | FNV 架构变化 | Liu, Dapeng (D.) <DLIU79@ford.com> |  | DCV3 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Liu, Dapeng (D.) <DLIU79@ford.com> |  | Group B | DCV Beta | Y | C/O |  | Liu, Dapeng (D.) <DLIU79@ford.com> |  | Group B | DCV Beta | Y | C/O |  | Liu, Dapeng (D.) <DLIU79@ford.com> |  | DCV 0 |  |  | Y | C/O |  | Liu, Dapeng (D.) <DLIU79@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Liu, Dapeng (D.) <DLIU79@ford.com> |  | DCV 0 |  |  |  | No | Group B | DCV Beta
SYNC+_Z0038 |  |  | ZZ# Foundemental Function 基础功能 | Connected Services | Embedded Modem Reset/Master reset |  | ECDX | Gu, Regina (Q.) <qgu12@ford.com> |  | Embedded Modem Reset OnBoardClient v2 SPSS v1.4 May 9, 2019.pdf MasterReset-Diagram.vsdx | HW_Tier1 | 70% | 0% | 0% | 30% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Gu, Regina (Q.) <qgu12@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  | Group A | DCV0 | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  | Group A | DCV0 | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  | DCV Beta1 |  |  | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  | DCV Beta1 |  |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0039 |  |  | ZZ# Foundemental Function 基础功能 | FNV | FNV2 - FCI Protocol | Ford Cloud Interface. 每个feature如需数据上传必须和云端签署的通信协议（安全相关）。用户感知不到 | ECDX | Liu, Dapeng (D.) <dliu79@ford.com> |  | FNV2-FCI Protocol SPSS v1.1 August 17, 2018 | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | FNV 架构变化 | Liu, Dapeng (D.) <dliu79@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Liu, Dapeng (D.) <dliu79@ford.com> |  | DCV Beta |  |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0041 |  |  | ZZ# Foundemental Function 基础功能 | FNV | IP Pass Through Client |  | ECDX | Lin, Shawn (X.) <xlin17@ford.com> |  | SPSS/PRD IP Pass Through Client Imp Guide v1.1 September 4, 2018.xlsx IP Pass Through Client SPSS v1.1 September 4, 2018.pdf | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | FNV 架构变化 | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV Beta |  |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0043 |  |  | ZZ# Foundemental Function 基础功能 | FNV | Wireless Interface Router(WIR) |  | ECDX | Lin, Shawn (X.) <xlin17@ford.com> |  | SPSS/PRD | Core_Service_Supplier | 20% | 0% | 0% | 70% | Y | Y | DCV2.1 | 2022-01-14 | 2022-01-24 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | FNV 架构变化 | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Lin, Shawn (X.) <xlin17@ford.com> |  | DCV Beta |  |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0051 |  | Audio | U# System Setting 系统设置 | Sound Setting 音效设置 | Speed compensated volume 根据车速调整音量 |  | EESE | Li Alvin (LLI156@ford.com) |  | Audio Settings APIM SPSS v1.6 Sep 29, 2020.pdf Audio Settings APIM Imp Guide v1.6 Sep 29, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li Alvin (LLI156@ford.com) |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li Alvin (LLI156@ford.com) |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li Alvin (LLI156@ford.com) |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Li Alvin (LLI156@ford.com) |  | DCV Alpha |  |  | Y | C/O |  | Li Alvin (LLI156@ford.com) |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Li Alvin (LLI156@ford.com) |  | DCV Alpha |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0056 |  |  | T# System Function 系统功能 | Basic Function 基础功能 | CAN signals （contain carry over signals） |  | EESE | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  | Y2021_FNV3_CMDB_v21.02_HS3_V2.DBC | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | FNV 架构变化引起部分signal 的messgae id 变化 | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Ding, Sunny (X.) <XDING13@ford.com> Xu, Tao (T.) <txu15@ford.com> |  | DCV Alpha |  |  |  | Yes | Group A | DCV Beta
SYNC+_Z0057 |  |  | T# System Function 系统功能 | Basic Function 基础功能 | FNOS |  | EESE | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | N | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N |  |  | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  | - | - | - | N | N |  | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  | N/A | N/A | N | N |  | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  | N | N | N | C/O |  | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  | - |  |  | N | N |  | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  |  | - |  | N | C/O |  | Xu, Tao (T.) <txu15@ford.com> Ding, Sunny (X.) <XDING13@ford.com> |  | - |  |  | Phase 1 | Yes |  | -
SYNC+_Z0058 | F000061 | Illumination | T# System Function 系统功能 | Basic Function 基础功能 | Illumination | Brightness Display off 显示/亮度设置 display/brightness setting | EESE | Li, Qiyang (Q.) <QLI111@ford.com> | Reis, Pedro (P.A.) | ES-H1BT-1A278-AA-V7.0.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Qiyang (Q.) <QLI111@ford.com> | Reis, Pedro (P.A.) | DCV1 | 2022-03-12 | 2022-03-19 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, James (J.) <jchen303@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, James (J.) <jchen303@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Li, Qiyang (Q.) <QLI111@ford.com> | Reis, Pedro (P.A.) | DCV Beta |  |  | Y | C/O |  | Li, Qiyang (Q.) <QLI111@ford.com> | Rodrigues, Igor (I.P.) |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Li, Qiyang (Q.) <QLI111@ford.com> | Reis, Pedro (P.A.) | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0059 |  |  | T# System Function 系统功能 | System Upgrade 系统升级 | MCU software download (via CAN) |  | EESE | Xu, Tao (T.) <txu15@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | Y | C/O | N | Xu, Tao (T.) <txu15@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  | DCV Alpha |  |  | Phase 1 | Yes | NA | DCV Beta
SYNC+_Z0060 |  | Power Management | T# System Function 系统功能 | Basic Function 基础功能 | Power management |  | EESE | Chen, James (J.) <jchen303@ford.com> |  | Power Management APIM SPSS v1.13 Sep 23, 2020.pdf Power Management APIM Imp Guide v1.13 Sep 23, 2020.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Chen, James (J.) <jchen303@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | DCV Alpha |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0081 |  | Hardbutton | T# System Function 系统功能 | Basic Function 基础功能 | Hardbutton Behavior | IVI interface via press physical switch 实体键IVI交互 Climate (menu and rear shortcut keys)-climate in rear display Climate (menu and rear shortcut keys)-Auto Air Refresh (AAR) Climate (menu and rear shortcut keys)-Rear- Tri or Quad Zone climate Lincoln Seats Lincoln Camera Shortcut key Lincoln Park Assist Shortcut key-Autoparking Lincoln Park Assist Shortcut key-Park aid on off Adaptive Steering BTT Light (Blind Spot Trailer Tow) Hill Decent Control Speed Limit Information / Speed Sign Recognition Traffic Sign Recognition Speed Limiter Rear Park Aid Tow Haul Engine Stop Start threshold PADI Grade Assits Trailer Sway Driver alert Hill start assist Wrong Way alert Cross Traffic Alert Blind Spot Pre Collision Assist (pre collision assist, distance indication, active breaking, evasive steer assist, alert sensitivity (high medium low)) Lane keeping mode (alert, aid, alert + aid), alert intensity (high, medium, low), sensitvity (normal, increased), lane keeping aid (on, off), lane keeping alert (high, medium, low, on, off) Cruise control- Type (Adaptive, intelligent, normal), tolerance Traction Control Auto Hold Auto Stop Start modified mini ICP Multi-Function Knob | HMI | Yao, Jeffery (J.) <jyao12@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV2.1 | 2022-01-14 | 2022-01-24 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | 新的icp 需要适配 | Yao, Jeffery (J.) <jyao12@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Yao, Jeffery (J.) <jyao12@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Yao, Jeffery (J.) <jyao12@ford.com> |  | Group A | DCV Alpha2 | Y |  |  | Yao, Jeffery (J.) <jyao12@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Yao, Jeffery (J.) <jyao12@ford.com> |  |  | DCV Beta |  | Y |  |  | Yao, Jeffery (J.) <jyao12@ford.com> |  | DCV Beta |  |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0107 |  |  | T# System Function 系统功能 | Basic Function 基础功能 | Autosar |  | EESE | Song, Robert (J.) <jsong30@ford.com> |  | AUTOSAR SOW_2019.0-WGC1NJ5520MQ2-2.zip AUTOSAR\AUTOSAR SOW_2019.0-WGC1NJ5520MQ2.zip AUTOSAR\AUTOSAR SOW_2019.0.zip | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Song, Robert (J.) <jsong30@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Song, Robert (J.) <jsong30@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Song, Robert (J.) <jsong30@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Song, Robert (J.) <jsong30@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Song, Robert (J.) <jsong30@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Song, Robert (J.) <jsong30@ford.com> |  | DCV Alpha |  |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0108 |  |  | T# System Function 系统功能 | Basic Function 基础功能 | Ford Cyber Security Requirements |  | ECDX | Shao, Jian (J.) <JSHAO13@ford.com> |  | App_signing_requirements_ver 1.3.pdf Bluetooth_Security_Spec_1.0.docx C.13 Ford_CyberAssurance-SOW_ReleaseV1.3(EE).doc FESN Generation Spec_V0.6.pdf IVI Security Requirements v7.docx Key Material Requirements.docx Key Packaging Spec_V0.72.pdf Operating_Systems_Security_Requirements_RC3.docx Phase4 Security RR_20191024 .xlsx S26_Secure_Channel_v1_04_Release.doc Vehicle and Mobility Security Data Logging Standard.pdf Vehicle-Mobility-Security-Data-Logging_Standard_v06-04Apr18.pdf Vehicle_HotSpot_and_AP_Client_Specification_v.2_final.pdf Vehicle_to_Cloud_Security_Spec_1.1.pdf | HW_Tier1 | 30% | 40% | 20% | 10% | Y | Y | R04 | 2022-06-15 | 2022-06-29 | Y | C/O |  |  |  | R05 | 2023-06-15 | 2023-06-29 | Y | C/O | N | Shao, Jian (J.) <JSHAO13@ford.com> |  | DCV3 | 2022-09-10 | 2022-09-24 | Y | C/O |  | Shao, Jian (J.) <JSHAO13@ford.com> |  | Group D | R05 | Y | C/O |  | Shao, Jian (J.) <JSHAO13@ford.com> |  | Group D | R05 | Y | C/O |  | Shao, Jian (J.) <JSHAO13@ford.com> |  | DCV 2 |  |  | Y | C/O |  | Shao, Jian (J.) <JSHAO13@ford.com> |  |  | R05 |  | Y | C/O |  | Shao, Jian (J.) <JSHAO13@ford.com> |  | DCV 2 |  |  | Phase 4 | No | Group C | R05
SYNC+_Z0109 |  | Ethernet | T# System Function 系统功能 | Basic Function 基础功能 | Ford Ethernet |  | EESE | Xu, Tao (T.) <txu15@ford.com> |  | AutomotiveEthernetHardwareReviewTestMethod-00.06.03.400-AB.docx AutomotiveEthernetLinkImplementationSpecification-00.06.01.001-AC.docx AutomotiveEthernetModuleLevelDesignVerificationMethod-00.06.01.301-AB.docx AutomotiveEthernetPhysicalLayerSpecification-00.06.03.003-AB.docx AutomotiveEthernetSoftwareReviewChecklist-00.06.01.402-AB.docx AutomotiveEthernetSwitchChecklist-00.06.01.403-AA.docx AutomotiveEthernetSwitchImplementationSpecification-00.06.01.002-AA.docx AutomotiveEthernetSystemLevelDesignVerificationMethod-00.06.01.313-AB.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Xu, Tao (T.) <txu15@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  | DCV Alpha |  |  | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Xu, Tao (T.) <txu15@ford.com> |  | DCV Alpha |  |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0111 |  |  | T# System Function 系统功能 | Basic Function 基础功能 | FPD LINK III |  | EESE | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  | FPDLinkIIICableandConnectorAssemblyDesignVerficationChecklist-00.06.01.306-AA.docx FPDLinkIIICableandConnectorAssemblySpecification-00.06.01.005-AA.docx FPDLinkIIIImplementationReviewChecklist-00.06.01.405-AA.docx FPDLinkIIILinkImplementationSpecification-00.0 | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Alpha | 2022-05-30 | - | Y | C/O | N | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  | DCV1 | 2022-02-12 | - | Y | C/O |  | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  | N/A | DCV Alpha1 | Y | C/O |  | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  |  |  | DCV Alpha |  |  | Y | C/O |  | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  |  | DCV Beta |  | Y | C/O |  |  |  | DCV Alpha |  |  | Phase 4 | Yes | Group A | DCV Alpha
SYNC+_Z0112 |  | Audio | U# System Setting 系统设置 | Voice Setting 语音设置 | 语音设置 audio setting |  | EESE | Zhang, Meijuan (M.) <MZHAN102@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Zhang, Meijuan (M.) <MZHAN102@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Qi, Xuliang <xqi14@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Qi, Xuliang <xqi14@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Zhang, Meijuan (M.) <MZHAN102@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Zhang, Meijuan (M.) <MZHAN102@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Zhang, Meijuan (M.) <MZHAN102@ford.com> |  | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0113 |  | BT Setting | T# System Function 系统功能 | Bluetooth 蓝牙 | Bluetooth Setting 蓝牙设置 |  | EESE | Xu, Amy (X.) <xyafei@ford.com> |  | BT Connectivity APIM SPSS v3.0 Feb 14, 2019.pdf BT Connectivity APIM Imp Guide v3.0 Feb 14, 2019.xlsx Phase5 Bt多路电话--PRD.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Amy (X.) <xyafei@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0114 | F001050 | Date&Time | U# System Setting 系统设置 | General Setting 常规设置 | 日期和时间设置 date&time setting | 详情请参考Ford的HMI Spec | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  | Global Clock Strategy Specification Ver 1.8.pdf APIM Clock Strategy v1.4 Feb 6 2014.pdf APIM Clock Strategy ImplGuide v1.4 Oct 9, 2020.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Huang, Xue (X.) <XHUANG93@ford.com> | Agostinho, Veruska (V.D.) <VAGOSTIN@ford.com> | DCV Beta |  |  | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> | Agostinho, Veruska (V.D.) |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Huang, Xue (X.) <XHUANG93@ford.com> | Agostinho, Veruska (V.D.) <VAGOSTIN@ford.com> | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0120 |  | Audio | T# System Function 系统功能 | Audio System 音频系统 | Support Ford external DSP module by A2B |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Analog Devices A2B Hardware Review 000603.512 AD.doc Analog Devices A2B link Data Link and Physical Layer 000603 501 AD.doc Analog Devices A2B Link Implementation Specification V1_1.docx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | Major |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Beta1 | 2022-02-12 | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  |  |  | DCV Beta |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O |  |  |  | DCV Beta |  |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0121 |  | General Setting | U# System Setting 系统设置 | General Setting 常规设置 | Disclaimer | Content to be aligned with CVPP and baidu | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | Y | C/O | N | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase 1 | No | Group C | DCV Beta
SYNC+_Z0122 |  | Driving Restriction | U# System Setting 系统设置 | Basic Function 基础功能 | Driving restriction | To Stop/cancel video playing when condition not correct. | EESE | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Driver Restrictions APIM SPSS v1.3 October 26 2018.pdf Driver Restrictions APIM Imp Guide v1.3.1 September 10 2020.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | DCV Beta1 | 2022-02-12 | - | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase 1 | No | Group A | DCV Beta
SYNC+_Z0125 |  | General Setting | U# System Setting 系统设置 | General Setting 常规设置 | 关于本机 | IVI sw version, VIN IVI ESN, TCU ESN… | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0126 |  |  | U# System Setting 系统设置 | General Setting 常规设置 | 恢复出厂设置 reset（Master Reset） | 详情请参考Ford的HMI Spec | ECDX | Gu, Regina (Q.) <qgu12@ford.com> |  | Embedded Modem Reset OnBoardClient v2 SPSS v1.4 May 9, 2019.pdf MasterReset-Diagram.vsdx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Gu, Regina (Q.) <qgu12@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  | Group A | DCV0 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Gu, Regina (Q.) <qgu12@ford.com> |  | Group A | DCV0 | Y | Minor | Adapt new scree size 12' | Gu, Regina (Q.) <qgu12@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Gu, Regina (Q.) <qgu12@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Gu, Regina (Q.) <qgu12@ford.com> |  | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0127 |  | Audio | U# System Setting 系统设置 | Sound Setting 音效设置 | 声音设置 sound setting | 详情请参考Ford的HMI Spec Mixed Mode Presets Autoset Preset Sound Settings - Treble/Mid/Bass Sound Settings - Balance/Fade Sound Settings - Speed Compensated Volume Sound Settings - Occupancy Mode | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Audio Settings APIM SPSS v1.6 Sep 29, 2020.pdf Audio Settings APIM Imp Guide v1.6 Sep 29, 2020.xlsx | SW_Tier1 | 0% | 0% | 0% | 100% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0128 |  |  | U# System Setting 系统设置 | Wi-Fi Setting Wi-Fi 设置 | Wifi 热点 Wifi Hot Spot | Wifi hot spot (WHS)- SSID or password. Refer to current sync 3 | ECDX | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Pan, Yuan (Y.) <ypan23@ford.com> |  | DCV Beta1 | 2022-02-12 | - | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Pan, Yuan (Y.) <ypan23@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase 2 | Yes | Group A | DCV Beta
SYNC+_Z0129 |  | WiFi Setting | U# System Setting 系统设置 | Wi-Fi Setting Wi-Fi 设置 | wifi设置 wifi setting | 详情请参考Ford的HMI Spec | EESE | Yu, Diven (D.W.) <dyu12@ford.com> |  | WiFi Configuration APIM SPSS v1.5 Sep 7, 2017.pdf WiFi Configuration APIM Imp Guide v1.5 Sep 7, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-07-18 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yu, Diven (D.W.) <dyu12@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yu, Diven (D.W.) <dyu12@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yu, Diven (D.W.) <dyu12@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0130 |  | Input | T# System Function 系统功能 | Basic Function 基础功能 | 百度输入法 Baidu Input | 拼音+手写+数字、符号、英文键盘 和其它 且支持联想、记忆、当前热词功能等。 | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group D | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group D | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0152 |  | Date&Time | T# System Function 系统功能 | Basic Function 基础功能 | Ford Clock Strategy |  | EESE | Huang, Xue (X.) <XHUANG93@ford.com> |  | APIM Clock Strategy v1.4 Feb 6 2014.pdf APIM Clock Strategy ImplGuide v1.4 Oct 9, 2020.xlsx Global Clock Strategy Specification Ver 1.8.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV0 | 2022-02-12 | - | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Beta |  |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0153 |  | Map&Navigation | T# System Function 系统功能 | Basic Function 基础功能 | Location Service （仪表指南针，etc.） |  | EESE | Yao, Tristan (Lan) <LYAO17@ford.com> |  | Location Service APIM SPSS v1.10 July 10, 2019.pdf Location Service APIM Imp Guide v1.10 July 10, 2019.xlsx | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | 707项目的GPS数据走TCU 传输 .788 GPS 数据实在CDC上直接处理 | Yao, Tristan (Lan) <LYAO17@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Yao, Tristan (Lan) <LYAO17@ford.com> |  |  | DCV Beta |  | Y | C/O |  | Huang, Xue (X.) <XHUANG93@ford.com> |  | DCV Beta |  |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0155 | F000974/E |  | ZZ# Foundemental Function 基础功能 | Connected Services | 车载热点 WifiHotspot | Ford TCU Related features (Modem Reset, WiFi, WiFi Hotspot)- TCU transfer CAN data to IVI Wifi hot spot (WHS)- SSID or password. Refer to current sync 3 Wi-Fi hotspot - TCU as WIFI Server (IVI provide HMI) | ECDX | Qi, Xingyu (X.) <XQI15@ford.com> | Nahle, Wassim (W.) | WiFi Hotspot OnBoardClient v2 SPSS v1.4 September 22, 2020.pdf WiFi Hotspot OnBoardClient v2 Imp Guide v1.4 September 22, 2020.xlsx | HW_Tier1 | 80% | 0% | 0% | 20% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Pan, Yuan (Y.) <ypan23@ford.com> | Nahle, Wassim (W.) | DCV Beta1 | 2022-02-12 | - | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Vega martinez, Oscar (O.) <ovegamar@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Pan, Yuan (Y.) <ypan23@ford.com> | Akhoirshida, Mohammed (M.) |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Vega martinez, Oscar (O.) <ovegamar@ford.com> |  | DCV Beta |  |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0156 |  |  | T# System Function 系统功能 | Basic Function 基础功能 | Consumer Behavior Data (IVI related)埋点 | 统计功能使用情况和用户偏好 Statistics feature usage and user preferences | EESE | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | Y | C/O | N | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  | DCV3 | 2022-09-10 | 2022-09-24 | Y | C/O |  | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  | N/A | DCV2 | Y | C/O |  | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  | N/A | DCV2 | Y | C/O |  | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  | DCV3 |  |  | Y | C/O |  | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  |  | DCV3 |  | Y | C/O |  | Gu, Zhong Tian (Z.) <zgu10@ford.com> |  | DCV3 |  |  | Phase 1 | No | Group C | DCV3
SYNC+_Z0199 |  | ANC | T# System Function 系统功能 | Audio System 音频系统 | Active Noise Cancellation |  | EESE | Ding, Jack (F.) <fding@ford.com> |  | ANC SPSS v1.4 Oct 7 2013.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | R04 | 2022-06-15 | 2022-06-29 | Y | Minor |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Ding, Jack (F.) <fding@ford.com> |  | DCV0 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Ding, Jack (F.) <fding@ford.com> |  | N/A | DCV1 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Ding, Jack (F.) <fding@ford.com> |  | N/A | DCV1 | Y | C/O |  |  |  | DCV Beta |  |  | Y | C/O |  | Ding, Jack (F.) <fding@ford.com> |  |  | DCV Beta |  | Y | C/O |  |  |  | DCV Beta |  |  | Phase 2 | Yes | Group A | DCV Beta
SYNC+_Z0218 |  | General Setting | U# System Setting 系统设置 | General Setting 常规设置 | Unit Setting-Measurement Units | Same as ford settings | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020.pdf Vehicle Settings APIM Imp Guide v1.24 Nov 2, 2020.xlsx Vehicle Settings Logical to Physical CAN signal mapping Oct 30, 2019.docx | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | DCV Beta2 | 2021-09-15 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0219 |  | General Setting | U# System Setting 系统设置 | General Setting 常规设置 | Unit Setting-Temperature | Same as ford settings | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020.pdf Vehicle Settings APIM Imp Guide v1.24 Nov 2, 2020.xlsx Vehicle Settings Logical to Physical CAN signal mapping Oct 30, 2019.docx | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | DCV Beta2 | 2021-09-15 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0220 |  | General Setting | U# System Setting 系统设置 | General Setting 常规设置 | Unit Setting-Tire Pressure Units; | Feature owners are from related functions | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020.pdf Vehicle Settings APIM Imp Guide v1.24 Nov 2, 2020.xlsx Vehicle Settings Logical to Physical CAN signal mapping Oct 30, 2019.docx | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | DCV Beta2 | 2021-09-15 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0240 |  | Multi-Screen Interaction | T# System Function 系统功能 | 信息多屏互动 | 后排娱乐空调控制面板 Rear entertainment control(Climate/Audio) - U611 | 扶手箱后面有个小屏。CAN互动，消息协议由Lincoln定义 | EESE | Chen, James (J.) <jchen303@ford.com> |  | Rear Audio Control APIM SPSS v1.4 Jul 1, 2017.pdf Rear Audio Control APIM Imp Guide v1.4 Jul 1, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | N |  |  | Chen, James (J.) <jchen303@ford.com> |  | - | - | - | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | Group A | DCV Beta | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | N | N | N | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | - |  |  | Y | C/O |  | Chen, James (J.) <jchen303@ford.com> |  |  | - |  | N | C/O |  | Chen, James (J.) <jchen303@ford.com> |  | - |  |  | Phase 1 | No | Group A | -
SYNC+_Z0282 |  |  | ZZ# Foundemental Function 基础功能 | Basic Function 基础功能 | 车机管家 | 百度主线用于管理主线内功能的隐私权限设置 | ECDX | gu,regina<QGU12@FORD.COM> |  |  | SW_Tier1 | 0% | 100% | 0% | 0% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV2 | 2023-01-24 | - | Y | C/O | N | gu,regina<QGU12@FORD.COM> |  | DCV3 | 2022-09-10 | 2022-09-24 | Y | C/O |  | gu,regina |  | Group D | DCV1 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | gu,regina |  | Group D | DCV1 | Y | Minor | Adapt new scree size 12' | gu,regina<QGU12@FORD.COM> |  | DCV2 |  |  | Y | C/O |  | gu,regina<QGU12@FORD.COM> |  |  | DCV2 |  | Y | Minor | Adapt new scree size 12' | gu,regina<QGU12@FORD.COM> |  | DCV2 |  |  | Phase2 | No | Group C | DCV2
SYNC+_Z1024 |  | BT Music | T# System Function 系统功能 | Bluetooth 蓝牙 | Bluetooth music |  | EESE | Xu, Amy (X.) <xyafei@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O | [6 empty] | Y |  |  | Xu, Xin XXU91@ford.com |  | DCV Beta |  |  | Y |  |  |  |  | Group A | DCV Alpha2 | Y |  |  |  |  | Group A | DCV Alpha2 | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Beta |  |  | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | DCV Beta | [5 empty] | DCV Beta
SYNC+_Z1025 |  | BT Headset | T# System Function 系统功能 | Bluetooth 蓝牙 | 蓝牙耳机 |  | EESE | Xu, Amy (X.) <xyafei@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O | [6 empty] | N | [7 empty] | Y |  |  |  |  | Group A | DCV Alpha2 | Y |  |  |  |  | Group A | DCV Alpha2 | N | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | - |  |  | Y | C/O |  |  |  |  | DCV Beta |  | N | C/O |  | Xu, Amy (X.) <xyafei@ford.com> |  | - | [5 empty] | DCV Beta
SYNC+_0194 |  | Welcome&Farewell | Q# Seamless Interface | 3# Welcome/Farewell Animation | 开机/关机动画 IVI Display Welcome & Farewelll Animation (Display Visual Elements) | 目前分为Ford/Lincoln/Muatang BEV (CX727C) | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Major | 新的开关机动画 | Liu, Luisa (Fan.) <fliu43@ford.com> |  | DCV1 | 2022-02-12 | - | Y | New | New welcome animation |  |  | Group A | DCV Alpha2 | Y | New | New HMI layout and UE for 12.3'+27' Display | 0 |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Liu, Luisa (Fan.) <fliu43@ford.com> |  | DCV Beta |  |  | Y | C/O |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | DCV Beta |  | Y | Minor | Adapt new scree size 12' | Liu, Luisa (Fan.) <fliu43@ford.com> |  | DCV Beta |  |  | Phase 1 | No | Group A | DCV Beta
SYNC+_0204 |  | Calm Screen | Q# Seamless Interface | 4# HMI Theme | 精简（屏幕）模式 Calm Screen | 精简屏幕 - 提供预置背景图片供用户选择 | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | Minor | HMI UIUE change | Liu, Luisa (Fan.) <fliu43@ford.com> |  | DCV2 | 2022-08-10 | 2022-08-24 | Y | Minor | New HMI layout for system setting |  |  | Group C | DCV0 | Y | Minor | New HMI layout for system setting | 0 |  | Group C | DCV Beta1 | Y | Minor | Adapt new scree size 12' | Liu, Luisa (Fan.) <fliu43@ford.com> |  | DCV Beta1 |  |  | Y | C/O |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | DCV1 |  | Y | Minor | Adapt new scree size 12' | Liu, Luisa (Fan.) <fliu43@ford.com> |  | DCV Beta1 |  |  | Phase 1 | Yes | Group B | DCV1
SYNC+_0205 |  | Theme | Q# Seamless Interface | 4# HMI Theme | 多界面主题Multi-Theme | 3套主题每个主题都有白天/夜晚模式 | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | HW_Tier1 | 70% | 10% | 10% | 10% | Y | Y | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | Y | Major | HMI UIUE change | Liu, Luisa (Fan.) <fliu43@ford.com> |  | DCV3 | 2022-09-10 | 2022-09-24 | Y | Major | New HMI layout and UE for 12.3'+27' Display |  |  | Group C | DCV0 | Y | Major | New HMI layout and UE for 12.3'+27' Display | 0 |  | Group C | DCV Beta1 | Y | Minor | Adapt new scree size 12' | Liu, Luisa (Fan.) <fliu43@ford.com> |  | DCV3 |  |  | Y | C/O |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | DCV3 |  | Y | Minor | Adapt new scree size 12' | Liu, Luisa (Fan.) <fliu43@ford.com> |  | DCV3 |  |  | Phase 1 | No | Group B | DCV3
SYNC+_0203 |  | Multi-Screen Interaction | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 27寸主副驾屏幕区域交互模式 27" HMI 3 Modes 独自 (Solo)；合作驾驶 （Co-pilot)；独立（individual) Provide Enhaned Passenger Experience. | 独占 (Solo)；合作驾驶 （Co-pilot)；分屏（individual） | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Liu, Luisa (Fan.) <fliu43@ford.com> |  | - | - | - | Y | New |  |  |  | Group A | DCV Alpha1 | Y | New |  | 0 |  | Group A | DCV Alpha2 | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  | - |  |  | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | - |  | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  | - |  |  | Phase 4 | No |  | DCV Alpha
SYNC+_0206 |  | Multi-Screen Interaction | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | 界面个性化设置，和屏与屏之间内容分发HMI Screen Mirroring/Casting + HMI Personalization （再launcher，允许用户自定义）For Dual 23.6+11.1 | 从11.1 touch screen 投射到pano屏幕的不同区域 | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | HW_Tier1 | 40% | 40% | 20% | 0% | Y-1st | Y-1st | DCV0 | 2021-10-20 | 2021-11-03 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Liu, Luisa (Fan.) <fliu43@ford.com> |  | - | - | - | N | N |  | 4_HMI |  | N/A | N/A | N | N |  | Zhou, Calvin (.) <QZHOU31@ford.com> |  | N | N | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  | - |  |  | Y | C/O |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | DCV Beta |  | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  | - |  |  | Phase 5 | No | Group A | DCV Alpha
SYNC+_0207 |  | Multi-Screen Interaction | Q# Seamless Interface | 2# Multi-Screen Interaction 多屏/分区 互动 | HUD信息显示EESE/IVI info showed in HUD | CAN互动，消息协议由Ford定义。 导航，里程，多媒体，电话等信息在HUD上的显示。 (IVI 提供信号， HUD owner 决定显示信息） 仪表控制导航的功能：同步目的地收藏，设置目的地途经点Cluster control EESE/IVI Navigation。 来电号码及名称显示，接听，挂电话 incoming caller ID display，answer call， hang-up call 广播，专辑信息、歌名、歌手 Album info,song & singer and Radio 导航服务，转向、ETA等信息 turn lane,radar detector & ETA | EESE | Chen, James (J.) <jchen303@ford.com> |  |  | HW_Tier1 |  |  |  |  | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | Y | New | IVI need transfer Nav and phonecall inforamtion to HUD via TP message. | Chen, James (J.) <jchen303@ford.com> |  | DCV2 | 2022-02-12 | - | Y | New | TP协议传输导航和来电信息给外部独立的HUD | Chen, James (J.) <jchen303@ford.com> |  | Group C | DCV Beta | Y | New | TP协议传输导航和来电信息给外部独立的HUD | Chen, James (J.) <jchen303@ford.com> |  | Group C | DCV Beta | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | - |  |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  |  | - |  | N | N |  | Chen, James (J.) <jchen303@ford.com> |  | - |  |  | Phase 2 | No |  | DCV Beta
SYNC+_0159 |  | Theme | Q# Seamless Interface | 8# Wallpaper 墙纸 | 壁纸 Project Aspire_Dash Backgrounds (Dual 23.6+11.1/or 27") | like your wallpaper on your phone or PC. The customer can personalize their dashboard with images, videos and sound. Content can be placed on top of the dashboard like on your PC and phone wallpaper. A dashboard covers the entire horizon screen. Project Aspire planed wallpaper/background including Luxury/Doggy dash/Dolphin/Live aquarium/Bloom/Comb/Dots/Houston Skyline/Kids photos/New York Aerial | HMI | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | HW_Tier1 | 100% | 0% | 0% | 0% | N | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Liu, Luisa (Fan.) <fliu43@ford.com> |  | - | - | - | Y | C/O |  |  |  | Group B | N/A | Y | C/O |  | 0 |  | Group B | N/A | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  | - |  |  | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | - |  | N | N |  | Liu, Luisa (Fan.) <fliu43@ford.com> |  | - |  |  | Phase 5 | No | Group B | DCV3
SYNC+_0221 | F001192/C |  | S# 系统升级 | 1# CAN 升级 | CAN 升级 |  | EESE | Wang, Jennifer (J.) <jwang373@ford.com> | Gudemaranahalli, Rohini Pr (R.) | In Vehicle Software Update (IVSU) APIM SPSS v2.8 May 30, 2019.pdf In Vehicle Software Update (IVSU) APIM Imp Guide v2.8 May 30, 2019.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV0 | 2022-11-24 | 2022-12-07 | Y | C/O | N | Wang, Jennifer (J.) <jwang373@ford.com> | Gudemaranahalli, Rohini Pr (R.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Wang, Fin (X.Y.) <xwang65@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  | Wang, Fin (X.Y.) <xwang65@ford.com> |  | N/A | DCV Alpha2 | Y | C/O |  |  |  | DCV Beta |  |  | Y | C/O |  |  | Carter, Jason (J.) |  | DCV Beta |  | Y | C/O |  |  |  | DCV Beta |  |  | Phase 1 | No | NA | DCV Beta
SYNC+_0022 |  | Audio |  | 5# Sound & Effect 音效 | 底特律之音 Detroit Symphony Orchestra chimes | Detroit Symphony Orchestra chimes (林肯飞行家上面的底特律交响乐团打造的提示音） | EESE | Li Alvin (LLI156@ford.com) |  | Alerts v3 APIM SPSS v1.1 Mar 17, 2020.pdf Alerts v3 APIM_4.2 Imp Guide v1.1 Mar 17, 2020.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Li Alvin (LLI156@ford.com) |  | - | - | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | N | N |  | Zhang, Meijuan (M.) <MZHAN102@ford.com>; Qi, Xuliang <xqi14@ford.com> |  | N/A | N/A | N | N | N | N | N | - | N | N | Y | C/O |  |  |  |  | DCV Beta |  | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | Yes | Group A | DCV0
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline is CDX707
Note on AS1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline is CDX707
Note on BE2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 支持FNA FDJ BB，主要界面需要中英文显示
Note on BU2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 支持FNA FDJ BB，主要界面需要中英文显示
Note on AI4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 所有信号相关要在DCV Beta完成.
Note on BE4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 所有信号相关要在DCV Beta完成.
Note on BM4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 所有信号相关要在DCV Beta完成.
Note on BU4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 所有信号相关要在DCV Beta完成.
Note on AQ5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa: 暂时输出764版本，后期会再更新group A
Note on AX5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa: 暂时输出764版本，后期会再更新group A
Note on AQ6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa: C/O 764, 暂时输出764 version,
Note on AX6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa: C/O 764, 暂时输出764 version,
Note on AA7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: High risk. 1. MCU侧开发预计12/M完成，Beta1集成. 2.Android 侧音频仲裁策略逻辑预计基于基线HQX1.2.1 DCV2 完成.
Note on AR7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: external APM based on 24ch AMP 3/E arrive, need confirm agian
Note on BE7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: YF需要有Harman对手件进行联调，相关功能先按照SPSS要求集成
Note on BN7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: audio相关feature先实现内置功放发声，外置功放等待哈曼对手件联调
Note on BU7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: YF需要有Harman对手件进行联调，相关功能先按照SPSS要求集成
Note on AR8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: based on A2B feature delivery
Note on BN16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AM/FM已经删除，reception测试
Note on BN22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on AA39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Follow CDX707, 12/15 Full CAN Release
Note on BE41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 依赖于正式屏幕的提供时间，1.5月的调试周期
Note on BU41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 依赖于正式屏幕的提供时间，1.5月的调试周期
Note on AA43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Power management may be minor/major change.
Note on BE43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Power模式需要UI界面功能，需要放在Beta版本
Note on BU43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Power模式需要UI界面功能，需要放在Beta版本
Note on BN44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on BE46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 全功能之后才能上功能安全
Note on BU46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 全功能之后才能上功能安全
Note on AA65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: High risk of ANC/ESE MBBM PO issue.
Note on AQ73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa：需要Jacky与studio确认时间
Note on AX73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI Lisa：需要Jacky与studio确认时间
Note on AQ78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 需要确认HUD包含具体哪些信息
Note on AX78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 需要确认HUD包含具体哪些信息
Note on AQ79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: deleted
Note on AX79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: deleted

## 03 BOF
Feature ID | VSEM ID | Component/s | Product Suite | Feature Group | Feature Name | Feature_Description | Lead Team | Local Feature Owner | Global Feature Owner | Dev Spec | Feature Development Leader | HW_Tier 1 | SW_Tier 1 | Ford IVI In-House | Core Service Provider | Phase5 | CDX707 | Release Version in GPDS | Original Release Date to REC | Original Release Date to FO/CAF(2weeks) | CDX747 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | CDX747 Release Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | CX788 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release CX788 Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | U611 MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner | U611 HMI Group | U611 Release Version in GPDS | U625 MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner | U625 HMI Group | U625 Release Version in GPDS | P702MCA | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release P702MCA Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | U718 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release U718 Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | CX821 | Change Level | Change Description | Local Feature Owner | Global Feature Owner | Release U718 Version in GPDS | Release Date to REC | Release Date to FO/CAF(2weeks) | 1st - phase # | Pre-DV Req | HMI Group | Target Version
SYNC+_0073 | F000280 F000789 | Parking Assist | D# Co-Pilot360 驾驶辅助 | 1# Help Me Park 停车辅助 | 全自动泊车 Fully Automated Parking (FAPA) also called APA | Gen1 - Gen X 不停升级中。具体参照Feature Owner Cascade 信息. FAPA starts from 2018 C519. Enhanced Active Park Assist (EAPA) added perpendicular parking maneuvers to Ford's Active Park Assist (APA) feature. Active Park Assist 2.0 (APA2.0 makes the entire process a one-touch operation by automating the throttle and brake; the user is not required to give any input to get the vehicle into the space. | EESE | He, Michael (X.) <xhe22@ford.com> | Rashidzadeh, Hejir (H.) | Active Park Assist V2 APIM SPSS v1.11 Mar 23, 2020.pdf Active Park Assist V2 APIM Imp Guide v1.11 Mar 23, 2020.xlsx | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | He, Michael (X.) <xhe22@ford.com> | Rashidzadeh, Hejir (H.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Major |  | He, Michael (X.) <xhe22@ford.com> |  | Group B | DCV0 | Y | Major | New HMI layout and UE for 12.3'+27' Display | He, Michael (X.) <xhe22@ford.com> |  | Group B | DCV0 | N | N | N | N | N | - |  |  | N | N | N | He, Michael (X.) <xhe22@ford.com> |  |  | - |  | N | N | N | He, Michael (X.) <xhe22@ford.com> |  |  | - |  | Phase 1 | No | Group B | -
SYNC+_0074 | F001330 | RBA | D# Co-Pilot360 驾驶辅助 | 4# Help Me Avoid Collisions 避免碰撞辅助 | 倒车制动辅助 Reverse Brake Assist (RBA) | (倒车时识别静态物体依托radar，超声波雷达和rear camera) | EESE | Li, Yifan (Y.) <YLI381@ford.com> | Cheng, Samuel (S.) | Reverse Brake Assist SPSS v1.2 May 17, 2021.pdf Reverse Brake Assist APIM Imp Guide v1.2 May 17, 2021.xlsx | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Li, Yifan (Y.) <YLI381@ford.com> | Cheng, Samuel (S.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Yifan (Y.) <YLI381@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Yifan (Y.) <YLI381@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Li, Yifan (Y.) <YLI381@ford.com> | Cheng, Samuel (S.) <scheng31@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Yifan (Y.) <YLI381@ford.com> | Cheng, Samuel (S.) |  | DCV Beta |  | Y | C/O | carryover 2024P702MCA New HMI layout and UE for 11.1'+23.6*2' Display | Li, Yifan (Y.) <YLI381@ford.com> | Cheng, Samuel (S.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_0076 | F002930 | Parking Assist | D# Co-Pilot360 驾驶辅助 | 1# Help Me Park 停车辅助 | 远程泊车辅助 Remote Park Assist (RePA) |  | EESE | He, Michael (X.) <xhe22@ford.com> | Rashidzadeh, Hejir (H.) | Remote Active Park Assist SPSS v1.0 Feb 4, 2020 | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | Y-1st | DCV4 | 2022-03-23 | 2022-04-06 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | He, Michael (X.) <xhe22@ford.com> | Rashidzadeh, Hejir (H.) | - | - | - | Y | C/O |  | He, Michael (X.) <xhe22@ford.com> |  | Group B | DCV0 | Y | Major | New HMI layout and UE for 12.3'+27' Display | He, Michael (X.) <xhe22@ford.com> |  | Group B | DCV0 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | He, Michael (X.) <xhe22@ford.com> | Rashidzadeh, Hejir (H.) |  | DCV Beta |  | Y | C/O | carryover 747 | He, Michael (X.) <xhe22@ford.com> | Rashidzadeh, Hejir (H.) |  | DCV Beta |  | Phase 5 | No | Group B | DCV Beta
SYNC+_0089 | F003515 | Camera | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 360 摄像头图像 2.0 360 Camera Image 2.0 | 增加点:offset views+软按键 driving tube in front/rear offset views offset views==front left/front right/rear left/rear right | EESE | Li, Xin (X.) <xli268@ford.com> | Salcido-zarco, Alejandro (A.) | Multi-Camera Client APIM SPSS v1.14 Mar 31, 2021.pdf Multi-Camera Client APIM Imp Guide v1.14 Mar 31, 2021.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Li, Xin (X.) <xli268@ford.com> | Salcido-zarco, Alejandro (A.) | DCV Alpha | 2022-02-12 | - | Y | Major |  | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Li, Xin (X.) <xli268@ford.com> | Raghunathan, Aishwarya (A.) <ARAGHUN4@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Xin (X.) <xli268@ford.com> | Midde, Vijaya Kumar (V.) |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xin (X.) <xli268@ford.com> | Midde, Vijaya Kumar (V.) |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_0094 |  | Camera | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 多种摄像头 Multi Camera - CHMSL/AUX Camera/Rock Crawl | ional item的，重卡unique，但是中国基本用不到 [Susan FIP:360camera基础上再增加一些摄像头] | EESE | Li, Xin (X.) <xli268@ford.com> |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | N | - | - | - | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Li, Xin (X.) <xli268@ford.com> |  | - | - | - | N | N |  | Li, Xin (X.) <xli268@ford.com> |  | N/A | N/A | N | N |  | Li, Xin (X.) <xli268@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Li, Xin (X.) <xli268@ford.com> |  |  | - |  | N |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | DCV Beta |  | Phase 4 | No |  | DCV Beta
SYNC+_0090 | F003515 F000292 | Camera | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 360 摄像头图像 360 Camera Image 1.0 | IVI 界面用户可以自行打开。使用场景例如 出停车位，变道. 360°全景影像设置 setting "Front/Rear view (Front/Side/Rear Zoom 前/后的四拼图，后路放大视图)" 2D模式 "视角切换图 split view (Rear/Front wideangle view,单路广角视图)" "俯视图 plan view (Rear/Front+ Plan View 全景加前或后的单路视图)" | EESE | Li, Xin (X.) <xli268@ford.com> | Salcido-zarco, Alejandro (A.) | Multi-Camera Client APIM SPSS v1.14 Mar 31, 2021.pdf Multi-Camera Client APIM Imp Guide v1.14 Mar 31, 2021.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Li, Xin (X.) <xli268@ford.com> | Salcido-zarco, Alejandro (A.) | DCV Alpha | 2022-02-12 | - | Y | Major |  | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Li, Xin (X.) <xli268@ford.com> | Salcido-zarco, Alejandro (A.) | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Xin (X.) <xli268@ford.com> | Midde, Vijaya Kumar (V.) |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xin (X.) <xli268@ford.com> | Midde, Vijaya Kumar (V.) |  | DCV Beta |  | Phase 1 | No | Group A | DCV Beta
SYNC+_0091 | F003631 | Camera | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 泊车辅助显示 Rear/Front/Side Visual Parking Aid | 障碍物距离显示 display distance to blocks (乌龟图);Park aid visual display (incl front rear and side) | EESE | Li, Xin (X.) <xli268@ford.com> | Al-Zaher, Sarya (S.) | Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.pdf Visual Park Assist Graphic Client V2 APIM Imp Guide v1.6 Dec 8, 2017.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Li, Xin (X.) <xli268@ford.com> | Al-Zaher, Sarya (S.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Beta | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Beta | Y | Minor | Adapt new scree size 12' | Li, Xin (X.) <xli268@ford.com> | Al-Zaher, Sarya (S.) <salzaher@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Xin (X.) <xli268@ford.com> | Al-Zaher, Sarya (S.) |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xin (X.) <xli268@ford.com> | Al-Zaher, Sarya (S.) |  | DCV Beta |  | Phase 1 | No | Group B | DCV Beta
SYNC+_0092 |  | Camera | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 前视摄像头 Off Road Front View Camera | 前视影像可以延时一段时间 | EESE | Li, Xin (X.) <xli268@ford.com> |  | Off-road Front View Camera APIM Implementation Guide ver1_0 May 31 2013.xls Off-road Front View Camera APIM SPSS ver1_0 May 31 2013.doc Off-road Front View Camera APIM SPSS ver1_0 May 31 2013.pdf | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Li, Xin (X.) <xli268@ford.com> |  | - | - | - | Y | C/O |  | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Li, Xin (X.) <xli268@ford.com> |  | DCV Beta |  |  | N | N | N | Li, Xin (X.) <xli268@ford.com> |  |  | - |  | N |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_0093 |  | Camera | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 后视摄像头 Rear Camera On Demand | 后视影像在R挡切换时可以延时一段时间，车速高于10km/h终止 | EESE | Li, Xin (X.) <xli268@ford.com> |  | Rear Camera On Demand APIM SPSS v1.1 June 21, 2019 Rear Camera On Demand APIM Imp Guide v1.1 June 21, 2019 | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV Beta | 2021-08-01 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Li, Xin (X.) <xli268@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | N | N | N | Li, Xin (X.) <xli268@ford.com> |  |  | - |  | N |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | DCV Beta |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_0095 |  | Camera | D# Co-Pilot360 驾驶辅助 | 3# Help Me See 视觉辅助 | 数字倒车影像 Rearview Camera - RVC (Digital) | Camera on demand;Rear view camera； IVI 绘制动态辅助线； RVC 叠加AR BPA | EESE | Li, Xin (X.) <xli268@ford.com> |  | Digital RVC SPSS v1.4 April 26, 2019.pdf Digital RVC APIM Imp Guide v1.4 April 26, 2019.xlsx | HW_Tier1 | 100% | 0% | 0% | 0% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Li, Xin (X.) <xli268@ford.com> |  | DCV1 | 2022-02-12 | - | Y | C/O |  | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | Y | Major | New HMI layout and UE for 12.3'+27' Display | Li, Xin (X.) <xli268@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | N | N | N | Li, Xin (X.) <xli268@ford.com> |  |  | - |  | N |  |  | Li, Xin (X.) <xli268@ford.com> |  |  | DCV Beta |  | Phase 2 | Yes | Group A | DCV Beta
SYNC+_0098 | F000565 | CTA | D# Co-Pilot360 驾驶辅助 | 4# Help Me Avoid Collisions 避免碰撞辅助 | 倒挡来车预警 Cross Traffic Alert (CTA) | 倒挡来车预警, 大屏上面HMI显示左右两侧动态箭头; Phase 2 增加倒档来车预警- 软按键功能 on/off | EESE | Liu, Hongxin (H.) <HLIU162@ford.com> | Rossi, Antonio (A. R.) | Cross Traffic Alert APIM SPSS v1.5 Apr 1, 2021.pdf Cross Traffic Alert APIM Imp Guide v1.5 Apr 1, 2021.xlsx | HW_Tier1 | 80% | 0% | 0% | 20% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Liu, Hongxin (H.) <HLIU162@ford.com> | Rossi, Antonio (A. R.) | DCV1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Liu, Hongxin (H.) <HLIU162@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Liu, Hongxin (H.) <HLIU162@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Liu, Hongxin (H.) <HLIU162@ford.com> | Rossi, Antonio (A. R.) | DCV Beta |  |  | Y | C/O | carryover 707 | Liu, Hongxin (H.) <HLIU162@ford.com> | Rossi, Antonio (A. R.) |  | DCV Beta |  | Y | C/O | carryover 747 | Liu, Hongxin (H.) <HLIU162@ford.com> | Rossi, Antonio (A. R.) |  | DCV Beta |  | Phase 1 | No | Group A | DCV Beta
SYNC+_0101 | F001430 |  | D# Co-Pilot360 驾驶辅助 | 4# Help Me Avoid Collisions 避免碰撞辅助 | 开车门路况辅助 Exit Warning （DAT2.1） | IVI need implement Clear Exit Assist Setting and Pop-Up Warning | EESE | Liu, Hongxin (H.) <HLIU162@ford.com> |  | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Liu, Hongxin (H.) <HLIU162@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Liu, Hongxin (H.) <HLIU162@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Liu, Hongxin (H.) <HLIU162@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Liu, Hongxin (H.) <HLIU162@ford.com> | Kaur, Gagandeep (G.) <gkaur12@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Liu, Hongxin (H.) <HLIU162@ford.com> | Kaur, Gagandeep (G.) |  | DCV Beta |  | Y | C/O | carryover 747 | Liu, Hongxin (H.) <HLIU162@ford.com> | Kaur, Gagandeep (G.) |  | DCV Beta |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0221 |  | HUD | W# Vehicle Setting 车辆设置 | Vehicle Setting | CHUD (TFT HUD) - setting |  | EESE | Li, Eureka (Y.) <YLI326@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | Y | New | 包含HUD亮度调节、高度调节、水平调节、内容设置菜单 | Shi, Lei (L.) <LSHI36@ford.com> |  | DCV Alpha | 2022-02-12 | - | Y | Y |  | Li, Jianxin (J.) <jli294@ford.com> |  | Group A | DCV Beta | N | N |  | Li, Jianxin (J.) <jli294@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Shi, Lei (L.) <LSHI36@ford.com> |  |  | - |  | N | N | N | Shi, Lei (L.) <LSHI36@ford.com> |  |  | - |  | Phase 4 | No |  | -
SYNC+_Z0044 | F000061 |  | W# Vehicle Setting 车辆设置 | IVI Support Vehicle Function | Smooth Dimming | 自动灯光变暗 | EESE | Chen, James (J.) <JCHEN303@ford.com> |  |  | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | DCV Beta1 | 2021-08-01 | - | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Chen, James (J.) <JCHEN303@ford.com> |  | DCV0 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Chen, James (J.) <JCHEN303@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Chen, James (J.) <JCHEN303@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Li, Qiyang (Q.) <QLI111@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Chen, James (J.) <JCHEN303@ford.com> | Rodrigues, Igor (I.P.) |  | DCV Beta |  | Y | C/O | carryover 747 | Chen, James (J.) <JCHEN303@ford.com> | Rodrigues, Igor (I.P.) |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0045 | F000549 | Drive Mode | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Drive Modes | 正常驾驶 运动驾驶 经济驾驶 | CED |  | Meza morales, Luis Enrique (L.) | Selectable Drive Mode SPSS v1.4 Aug 17, 2020.pdf Selectable Drive Mode APIM Imp Guide v1.4 Aug 17, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N |  | Meza morales, Luis Enrique (L.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  |  |  | Group A | DCV Alpha2 | Y | C/O |  |  |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Kudale, Anjaneya (A.M.) <AKUDALE1@ford.com> | DCV Beta |  |  | Y | Minor | carryover 2022 U553/554 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | Kudale, Anjaneya (A.M.) |  | DCV Beta |  | Y | Minor | carryover 2022 U553/554 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | Kudale, Anjaneya (A.M.) |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0046 |  | Drive Mode | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Drive Modes |  | CED | Luis Meza |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | N | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Luis Meza |  | - | - | - | N | N |  | Luis Meza |  | N/A | N/A | N | N |  | Luis Meza |  | N/A | N/A | N | N | N | N | N | - |  |  | Y |  |  | Luis Meza |  |  |  |  | Y |  |  | Luis Meza |  |  |  |  | Phase 1 | Yes | Group A
SYNC+_Z0047 | F00158 F0003516 | Seat | V# Vehicle Control 车辆控制 | Seat Control 座椅控制 | Multi contour seat -Seat adjust -Custom Massage Patterns HMI for Multi-Contour Seats (U611) -Seat massage | 座椅调节 | EESE | Du, Hao (H.) <HDU9@ford.com> |  | Multi Contoured Seats Client V2 SPSS v1.5 June 9, 2020.pdf Multi Contoured Seats Client V2 Imp Guide v1.5 June 9, 2020.xlsx Power Lumbar Seat Client APIM SPSS v1.1 Apr 5, 2017.pdf Power Lumbar Seat Client APIM Imp Guide v1.1 Apr 5, 2017.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Du, Hao (H.) <HDU9@ford.com> |  | - | - | - | Y | C/O |  | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | Major | CDX707: manual for Pitch and Slide 718: Power Latch Release for Pitch and Slide 718: add 4 way power lumbar | Du, Hao (H.) <HDU9@ford.com> |  |  | DCV Beta |  | Y | Major | CDX747: manual for Pitch and Slide 718: Power Latch Release for Pitch and Slide 718:add 4 way power lumbar | Du, Hao (H.) <HDU9@ford.com> |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0050 | F001046/C | Wireless Charging | W# Vehicle Setting 车辆设置 | IVI Support Vehicle Function | Phone Wireless Charging notification | 无线充电提示 | EESE | Lyu, Qingtao (Q.) <qlyu@ford.com> | Grifka, Brian (B.M.) | Wireless Charging APIM SPSS v1.0 Oct 8, 2015.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV0.1 | 2021-11-17 | 2021-12-01 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Lyu, Qingtao (Q.) <qlyu@ford.com> | Grifka, Brian (B.M.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Lyu, Qingtao (Q.) <qlyu@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Lyu, Qingtao (Q.) <qlyu@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Lyu, Qingtao (Q.) <qlyu@ford.com> | Sorto, Silvia (S. S.) <ssouza32@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Lyu, Qingtao (Q.) <qlyu@ford.com> | Grifka, Brian (B.M.) |  | DCV Beta |  | Y | C/O | carryover 747 | Lyu, Qingtao (Q.) <qlyu@ford.com> | Grifka, Brian (B.M.) |  | DCV Beta |  | Phase 1 | No | Group A | DCV Beta
SYNC+_Z0052 |  | TCS | W# Vehicle Setting 车辆设置 | IVI Support Vehicle Function | TCS off | Soft button design（设计成软按键） | EESE | Goldbach, Michael (M.) <mgoldba3@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Goldbach, Michael (M.) <mgoldba3@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Goldbach, Michael (M.) <mgoldba3@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Goldbach, Michael (M.) <mgoldba3@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Goldbach, Michael (M.) <mgoldba3@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Goldbach, Michael (M.) <mgoldba3@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Goldbach, Michael (M.) <mgoldba3@ford.com> |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0069 | F000097 |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Auto Vehicle Hold (AVH) | Inputs are brake pedal, accelerator pedal (and clutch pedal if equipped), and a hard or soft button toggle. Output is the vehicle will hold the brakes until there is sufficient torque for forward motion, then the brakes will release. | EESE | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com> | James, Alex (J.A.) | Auto Hold APIM SPSS v1.1 Feb 20, 2017.pdf Auto Hold APIM Imp Guide v1.1 Feb 20, 2017.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com> | James, Alex (J.A.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Griffin, Bryan (B.) <bgriff79@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com> | Ferencz, Alexander (A.J.) |  | DCV Beta |  | Y | C/O | carryover 747 | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com> | Ferencz, Alexander (A.J.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0070 | F000016/E |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Auto Stop Start |  | EESE | Bush, Duane (D.R.) <dbush@ford.com> |  | Auto Start Stop SPSS v1.1 Oct 25, 2018.pdf Auto Start Stop APIM Imp Guide v1.1 Oct 25, 2018.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | N | N |  |  |  | N/A | N/A | N/A | Y | C/O | N | Li, Yanzhi (Y.) <YLI380@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Bush, Duane (D.R.) <dbush@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Bush, Duane (D.R.) <dbush@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Alawieh, Khoder (K.) <KALAWIEH@ford.com> | DCV Beta |  |  | Y | Minor | carryoverU611/U625,P702MCA New HMI layout and UE for 11.1'+23.6*2' Display | Bush, Duane (D.R.) <dbush@ford.com> | Rojas, David (D.) |  | DCV Beta |  | Y | Minor | carryoverU611/U625,P702MCA New HMI layout and UE for 11.1'+23.6*2' Display | Bush, Duane (D.R.) <dbush@ford.com> | Rojas, David (D.) |  | DCV Beta |  | Phase 2 | No |  | DCV Beta
SYNC+_Z0071 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | BTT Light (Blind Spot Trailer Tow) |  | EESE | Shan, Susan (D.) <DSHAN@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Shan, Susan (D.) <DSHAN@ford.com> |  | - | - | - | N | N |  | Shan, Susan (D.) <DSHAN@ford.com> |  | N/A | N/A | N | N |  | Shan, Susan (D.) <DSHAN@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | Y | NEW |  | Shan, Susan (D.) <DSHAN@ford.com> |  |  | DCV Beta |  | Y | NEW |  | Shan, Susan (D.) <DSHAN@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0072 |  | Climate | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Climate Menu | 按下此快捷键后IVI弹出空调控制页面，显示额外的空调控制软按键 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | Y |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | - |  | N |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 2 | No |  | DCV Beta
SYNC+_Z0073 |  | Climate | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Climate Mode Selection | 按下此快捷键后IVI弹出吹风模式弹窗，提供额外的三种吹风模式选择软按键 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | Y |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | N/A | N/A | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | - |  | N |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 4 | No |  | DCV Beta
SYNC+_Z0074 |  | Climate | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Climate Rear Control | 按下此快捷键后IVI弹出后排空调控制页面，提供额外的后排空调控制软按键 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | - | - | - | Y | Y |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | - |  | N |  |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 2 | No |  | DCV Beta
SYNC+_Z0068 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Adaptive Steering |  | EESE | Zhang, Isaac (S.) <szhang42@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Zhang, Isaac (S.) <szhang42@ford.com> |  | - | - | - | N | N |  | Zhang, Isaac (S.) <szhang42@ford.com> |  | N/A | N/A | N | N |  | Zhang, Isaac (S.) <szhang42@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | Y | NEW |  | Zhang, Isaac (S.) <szhang42@ford.com> |  |  | DCV Beta |  | Y | NEW |  | Zhang, Isaac (S.) <szhang42@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0075 | VF004044 F000910 F000911 F000912 F000579 | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Cruise Control Setting | Include following setting item: -Cruise control- Type (Adaptive, intelligent, normal), -tolerance | EESE | Cui, Victor (M.) <mcui5@ford.com> | Sarkar, Animesh (A.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Cui, Victor (M.) <mcui5@ford.com> | Sarkar, Animesh (A.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | Major |  | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Cui, Victor (M.) <mcui5@ford.com> | Matthews, Jason (J.C.) <jmatth99@ford.com> Sarkar, Animesh (A.) <ASARKAR7@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Cui, Victor (M.) <mcui5@ford.com> | Matthews, Jason (J.C.) Sarkar, Animesh (A.) |  | DCV Beta |  | Y | C/O | carryover 747 | Cui, Victor (M.) <mcui5@ford.com> | Matthews, Jason (J.C.) Sarkar, Animesh (A.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0077 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Engine Stop Start threshold |  | EESE | Bush, Duane (D.R.) <dbush@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | N | N |  |  |  | N/A | N/A | N/A | Y | C/O | N | Bush, Duane (D.R.) <dbush@ford.com> |  | DCV Beta | - | - | Y | C/O |  | Bush, Duane (D.R.) <dbush@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Bush, Duane (D.R.) <dbush@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Bush, Duane (D.R.) <dbush@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Bush, Duane (D.R.) <dbush@ford.com> |  |  | DCV Beta |  | Y |  |  | Bush, Duane (D.R.) <dbush@ford.com> |  |  | DCV Beta |  | Phase 2 | No |  | DCV Beta
SYNC+_Z0085 |  | Shortcut Keys | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Lincoln Park Assist Shortcut key | hard button trigger LPA screen | EESE | He, Michael (X.) <xhe22@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | He, Michael (X.) <xhe22@ford.com> |  | - | - | - | Y | C/O |  | He, Michael (X.) <xhe22@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | He, Michael (X.) <xhe22@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | He, Michael (X.) <xhe22@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | He, Michael (X.) <xhe22@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0087 |  | Shortcut Keys | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Lincoln Seats shortcut key | Lincoln Seats shortcut key-4 or 2 way lumbar | EESE | Zhou, Weifu (W.) <wzhou43@ford.com> |  | Power Lumbar Seat Client APIM SPSS v1.1 Apr 5, 2017.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Zhou, Weifu (W.) <wzhou43@ford.com> |  | - | - | - | N | N |  | Zhou, Weifu (W.) <wzhou43@ford.com> |  | N/A | N/A | N | N |  | Zhou, Weifu (W.) <wzhou43@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | Y | NEW |  | Zhou, Weifu (W.) <wzhou43@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Zhou, Weifu (W.) <wzhou43@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0088 | F000158 | Shortcut Keys | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Multi-Contoured Seats (Massage Seats) |  | EESE | Du, Hao (H.) <hdu9@ford.com> | Santos, Roger (R.M.) | Multi Contoured Seats Client V2 SPSS v1.5 June 9, 2020.pdf Multi Contoured Seats Client V2 Imp Guide v1.5 June 9, 2020.xlsx Power Lumbar Seat Client APIM SPSS v1.1 Apr 5, 2017.pdf Power Lumbar Seat Client APIM Imp Guide v1.1 Apr 5, 2017.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Du, Hao (H.) <hdu9@ford.com> | Santos, Roger (R.M.) | - | - | - | Y | C/O |  | Du, Hao (H.) <hdu9@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | Du, Hao (H.) <hdu9@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | Du, Hao (H.) <hdu9@ford.com> |  |  | DCV Beta |  | Y | Major | CDX747: manual for Pitch and Slide 718: Power Latch Release for Pitch and Slide 718:add 4 way power lumbar | Du, Hao (H.) <hdu9@ford.com> |  |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0091 | F000513 F004999 F000908 | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Pre Collision Assist | PSA setting menu, refer setting SPSS VS-FUN-REQ-233569/B-Pre-Collision Assist (pre collision assist, distance indication, active breaking, evasive steer assist, alert sensitivity (high medium low)) | EESE | Zhu, Jinpeng (J.) <jzhu85@ford.com> | Wang, Haisu (H. Gelan, Ibrahim (I.S.)) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Zhu, Jinpeng (J.) <jzhu85@ford.com> | Wang, Haisu (H. Gelan, Ibrahim (I.S.)) | DCV1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Zhu, Jinpeng (J.) <jzhu85@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhu, Jinpeng (J.) <jzhu85@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Zhu, Jinpeng (J.) <jzhu85@ford.com> | Hampton, Michael (M.W.) <MHAMPT47@ford.com> Wang, Haisu (H.) <hwang153@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Zhu, Jinpeng (J.) <jzhu85@ford.com> | Wang, Haisu (H.) Nambo, Victor (V.) |  | DCV Beta |  | Y | C/O | carryover 747 | Zhu, Jinpeng (J.) <jzhu85@ford.com> | Wang, Haisu (H.) Nambo, Victor (V.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0092 |  | Shortcut Keys | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Rear Park Aid |  | EESE | He, Michael (X.) <xhe22@ford.com> |  | Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | He, Michael (X.) <xhe22@ford.com> |  | DCV Beta1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | He, Michael (X.) <xhe22@ford.com> |  | Group A | DCV Beta1 | Y | C/O |  | He, Michael (X.) <xhe22@ford.com> |  | Group A | DCV Beta1 | Y | Minor | Adapt new scree size 12' | He, Michael (X.) <xhe22@ford.com> |  | DCV Beta |  |  | N | N | N | He, Michael (X.) <xhe22@ford.com> |  |  | - |  | Y | C/O | carryover 747 | He, Michael (X.) <xhe22@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0093 |  | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Speed Limit Information / Speed Sign Recognition |  | EESE | Cui, Victor (M.) <mcui5@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Cui, Victor (M.) <mcui5@ford.com> |  | DCV1 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Cui, Victor (M.) <mcui5@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Cui, Victor (M.) <mcui5@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Cui, Victor (M.) <mcui5@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0094 |  | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Speed Limiter |  | EESE | Cui, Victor (M.) <mcui5@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Cui, Victor (M.) <mcui5@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Cui, Victor (M.) <mcui5@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Cui, Victor (M.) <mcui5@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Cui, Victor (M.) <mcui5@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0096 |  | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Traction Control |  | EESE |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N |  |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  |  |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display |  |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O | carryover 707 |  |  |  | DCV Beta |  | Y | C/O | carryover 747 |  |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0099 |  | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Wrong Way alert |  | EESE | Cui, Victor (M.) <mcui5@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Cui, Victor (M.) <mcui5@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Cui, Victor (M.) <mcui5@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Cui, Victor (M.) <mcui5@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Cui, Victor (M.) <mcui5@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0100 |  | Ambient Lighting | W# Vehicle Setting 车辆设置 | Soft Button | Ambient Lighting - Breath Control (setting: on/off) |  | BI | Sun, Qiming (Q.) <qsun31@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | N | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Sun, Qiming (Q.) <qsun31@ford.com> |  | - | - | - | N | N |  | Sun, Qiming (Q.) <qsun31@ford.com> |  | N/A | N/A | N | N |  | Sun, Qiming (Q.) <qsun31@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Sun, Qiming (Q.) <qsun31@ford.com> |  |  |  |  | N | N | N | Sun, Qiming (Q.) <qsun31@ford.com> |  |  |  |  | Phase 4 | No | Group A
SYNC+_Z0101 |  | Ambient Lighting | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Ambient Lighting 128 Color |  | BI | Sun, Qiming (Q.) <qsun31@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Sun, Qiming (Q.) <qsun31@ford.com> |  | - | - | - | N | C/O |  | Sun, Qiming (Q.) <qsun31@ford.com> |  | Group A | DCV Alpha2 | N | C/O |  | Sun, Qiming (Q.) <qsun31@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | N | Minor | CDX707:128 Color U718:7 Color | Sun, Qiming (Q.) <qsun31@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Sun, Qiming (Q.) <qsun31@ford.com> |  |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0103 |  |  | W# Vehicle Setting 车辆设置 | Soft Button | Power Running Boards (PRB) |  | EESE | Wang Yan jing |  | Power Running Boards Softswitch InterfaceClient SPSS v1.0 October 5, 2018.pdf Power Running Boards Softswitch InterfaceClient Imp Guide v1.0 October 5, 2018.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | N | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Wang Yan jing |  | - | - | - | Y | C/O |  | Wang Yan jing |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang Yan jing |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | Wang Yan jing |  |  | DCV Beta |  | Y | C/O | carryover 747 | Wang Yan jing |  |  | DCV Beta |  | Phase 4 | No | Group A | DCV Beta
SYNC+_Z0104 |  |  | W# Vehicle Setting 车辆设置 | Soft Button | Power Tailgate (FordPass/SYNC); |  | EESE | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  | TailGate Softswitch InterfaceClient Imp Guide v1.3 June 25, 2019.xlsx TailGate Softswitch InterfaceClient SPSS v1.3 June 25, 2019.pdf | Core_Service_Supplier | 0% | 0% | 0% | 100% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  | - | - | - | Y | C/O |  | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  | DCV Beta |  |  | N | N | N | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  |  | - |  | N | N | N | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  |  | - |  | Phase 4 | No | Group A | -
SYNC+_Z0083 |  | Shortcut Keys | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Lincoln Camera Shortcut key | Lincoln Camera Shortcut key-360, standard rear, etc, Includes all HMI views | EESE |  |  |  | HW_Tier1 | 90% | 0% | 0% | 10% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  |  | - | - | - | Y | Y |  |  |  | Group A | DCV Alpha2 | Y | C/O |  |  |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 |  |  |  | DCV Beta |  | TBD | [5 empty] | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0084 |  | Shortcut Keys | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Lincoln Drive Assist Shortcut key | & Park aid on off；hard button trigger LPA screen | EESE | He, Michael (X.) <xhe22@ford.com> |  | Shortcut Key Driver Assist SPSS v1.2 Nov 26, 2019.pdf Shortcut Key Driver Assist APIM Imp Guide v1.2.1 Jan 24, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | He, Michael (X.) <xhe22@ford.com> |  | - | - | - | Y | Y |  | He, Michael (X.) <xhe22@ford.com> |  | Group A | DCV Alpha2 | Y | C/O |  | He, Michael (X.) <xhe22@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | N | N | N | He, Michael (X.) <xhe22@ford.com> |  |  | - |  | Y | C/O | carryover 747 | He, Michael (X.) <xhe22@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0097 | F000913/C | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Traffic Sign Recognition | TSR setting item | EESE | Cui, Victor (M.) <mcui5@ford.com> | Sarkar, Animesh (A.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Cui, Victor (M.) <mcui5@ford.com> | Sarkar, Animesh (A.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Cui, Victor (M.) <mcui5@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Cui, Victor (M.) <mcui5@ford.com> | Sarkar, Animesh (A.) <ASARKAR7@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Cui, Victor (M.) <mcui5@ford.com> | Sarkar, Animesh (A.) |  | DCV Beta |  | Y | C/O | carryover 747 | Cui, Victor (M.) <mcui5@ford.com> | Sarkar, Animesh (A.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0089 |  | Shortcut Keys | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | Multi-Function Knob |  | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV1 | - | - | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | N/A | N/A | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | - |  | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | - |  | Phase 2 | No |  | -
SYNC+_Z0090 |  | Shortcut Keys | V# Vehicle Control 车辆控制 | Shortcut Keys 快捷键 | PADI |  | EESE | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Xu, Xi Hai (X.) <xxu61@ford.com> |  | DCV1 | - | - | N | N |  | Xu, Xi Hai (X.) <xxu61@ford.com> |  | N/A | N/A | N | N |  | Xu, Xi Hai (X.) <xxu61@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | - |  | N | N | N | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | - |  | Phase 2 | No |  | -
SYNC+_Z0078 |  | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Grade Assits |  | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Wang, Peggy (M.N.) <mwang43@ford.com> |  | - | - | - | N | N |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  | N/A | N/A | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Wang, Peggy (M.N.) <mwang43@ford.com> |  | DCV Beta |  |  | Y | NEW |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | DCV Beta |  | Y | NEW |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0079 | F000090/C | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Hill Decent Control |  | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> | Brown, Andrew (A.A.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Wang, Peggy (M.N.) <mwang43@ford.com> | Brown, Andrew (A.A.) | - | - | - | Y-1st | New |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Wang, Peggy (M.N.) <mwang43@ford.com> | Brown, Andrew (A.A.) <abrown75@ford.com> | DCV Beta |  |  | Y | NEW | U718 is a soft switch | Wang, Peggy (M.N.) <mwang43@ford.com> | Brown, Andrew (A.A.) |  | DCV Beta |  | Y | Minor | U718 is a soft switch | Wang, Peggy (M.N.) <mwang43@ford.com> | Brown, Andrew (A.A.) |  | DCV Beta |  |  | No | Group A | DCV Beta
SYNC+_Z0080 |  | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Hill start assist | Aways On, on need IVI implement a soft switch | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Wang, Peggy (M.N.) <mwang43@ford.com> |  | - | - | - | Y | Y |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Wang, Peggy (M.N.) <mwang43@ford.com> |  | DCV Beta |  |  | Y | NEW |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | DCV Beta |  | Y | NEW |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0095 |  | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Tow Haul |  | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Settings In Infotainmen CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Wang, Peggy (M.N.) <mwang43@ford.com> |  | - | - | - | N | N |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  | N/A | N/A | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Group A | DCV Alpha2 | Y | New | New Setting Item | Wang, Peggy (M.N.) <mwang43@ford.com> |  | DCV Beta |  |  | Y | NEW |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | DCV Beta |  | Y | NEW |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0098 |  | Driver Assistance | W# Vehicle Setting 车辆设置 | Driver Assistance Setting 驾驶辅助设置 | Trailer Sway |  | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Wang, Peggy (M.N.) <mwang43@ford.com> |  | - | - | - | N | N |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  | N/A | N/A | N | N |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  | N/A | N/A | Y | New | New Setting Item | Wang, Peggy (M.N.) <mwang43@ford.com> |  | DCV Beta |  |  | Y | NEW |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | DCV Beta |  | Y | NEW |  | Wang, Peggy (M.N.) <mwang43@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0159 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | AC - face | 空调吹脸 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0160 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | AC - feet | 空调吹脚 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0161 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | AC on/off | AC开关 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0162 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Auto AC | 自动 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0163 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Demist | 除雾 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0164 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Driver temp | 主驾温度 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0165 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Dual AC | 双区空调 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0166 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Fan | 风速 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0167 | F003518 | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Front Row Seat Heated | 前排座椅加热 | EESE | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) <smlynar1@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  | DCV Beta |  | Y | C/O | carryover 747 | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0168 | F003518 | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Front Seat Vent | 前排座椅吹风 | EESE | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) <smlynar1@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  | DCV Beta |  | Y | C/O | carryover 747 | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0169 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Max AC | 空调最大 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0170 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Max windshield | 挡风除霜 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0171 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Passenger temp | 副驾温度 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0172 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Rear climate fan | 后排空调风速 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  |  | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | NEW |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0173 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Rear climate mode | 后排空调模式 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  |  | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | NEW |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0174 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Rear climate temp | 后排空调温度 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  |  | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | NEW |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0175 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Recirc. | 车内循环 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0176 | F000123 | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Steering wheel heated | 方向盘加热 | EESE | Yan, Sophie (C.) <cyan10@ford.com> |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Yan, Sophie (C.) <cyan10@ford.com> |  | - | - | - | Y | C/O |  | Yan, Sophie (C.) <cyan10@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yan, Sophie (C.) <cyan10@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yan, Sophie (C.) <cyan10@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yan, Sophie (C.) <cyan10@ford.com> | Shirazawa, Diogo (D.H.) |  | DCV Beta |  | Y | C/O | carryover 747 | Yan, Sophie (C.) <cyan10@ford.com> | Shirazawa, Diogo (D.H.) |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0177 |  | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Windshield | 挡风玻璃 | EESE | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | Minor | HMI UIUE update | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Alpha | 2022-02-12 | - | Y | C/O |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | C/O | carryover 707 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV0 |  | Y | C/O | carryover 747 | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 1 | Yes | Group A | DCV Beta
SYNC+_Z0178 | F001027 | Light | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-Adaptive headlamps |  | EESE | Zhou, Travis (C.X.) <czhou17@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Zhou, Travis (C.X.) <czhou17@ford.com> |  | - | - | - | Y | C/O |  | Zhou, Travis (C.X.) <czhou17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhou, Travis (C.X.) <czhou17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Zhou, Travis (C.X.) <czhou17@ford.com> | Petrosino, Dominick (D.) <dpetrosi@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Zhou, Travis (C.X.) <czhou17@ford.com> | Petrosino, Dominick (D.) |  | DCV Beta |  | Y | C/O | carryover 747 | Zhou, Travis (C.X.) <czhou17@ford.com> | Petrosino, Dominick (D.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0180 | F001014 | Light | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-Autolamp delay | 747jira中删除该feature | EESE | Zhou, Travis (C.X.) <czhou17@ford.com> | D'Agostino, Antonio (A.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Zhou, Travis (C.X.) <czhou17@ford.com> | D'Agostino, Antonio (A.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Zhou, Travis (C.X.) <czhou17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhou, Travis (C.X.) <czhou17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Zhou, Travis (C.X.) <czhou17@ford.com> | D'Agostino, Antonio (A.) | DCV Beta |  |  | Y | C/O | carryover 707 | Zhou, Travis (C.X.) <czhou17@ford.com> | Antunes, Mauricio (M.C.) |  | DCV Beta |  | Y | Minor | carryover MY2021 P702 New HMI layout and UE for 11.1'+23.6*2' Display | Zhou, Travis (C.X.) <czhou17@ford.com> | Antunes, Mauricio (M.C.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0181 | F001006 | Light | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-daytime lights |  | EESE | Zhou, Travis (C.X.) <czhou17@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Zhou, Travis (C.X.) <czhou17@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Zhou, Travis (C.X.) <czhou17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhou, Travis (C.X.) <czhou17@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Zhou, Travis (C.X.) <czhou17@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Zhou, Travis (C.X.) <czhou17@ford.com> | Antunes, Mauricio (M.C.) |  | DCV Beta |  | Y | C/O | carryover 747 | Zhou, Travis (C.X.) <czhou17@ford.com> | Antunes, Mauricio (M.C.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0182 |  | Light | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-Glare Free lighting |  | EESE | Song, Amy (S.) <ssong18@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Song, Amy (S.) <ssong18@ford.com> |  | - | - | - | Y | C/O |  | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Song, Amy (S.) <ssong18@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Song, Amy (S.) <ssong18@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Song, Amy (S.) <ssong18@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0183 | F000052/C | Light | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Light Setting-welcome lights |  | EESE | Wu, Bella (Y.) <ywu150@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Wu, Bella (Y.) <ywu150@ford.com> |  | - | - | - | Y | C/O |  | Wu, Bella (Y.) <ywu150@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wu, Bella (Y.) <ywu150@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | Wu, Bella (Y.) <ywu150@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Wu, Bella (Y.) <ywu150@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0185 | F000063/C | Ambient Lighting | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | 单色氛围灯 single color ambient lighting | 车型只支持单色氛围灯 | EESE | Li, Xuedong (X.) <XLI244@ford.com> | Gemade, Ralph (R.) | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> | Gemade, Ralph (R.) | - | - | - | N | New |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  | Gemade, Ralph (R.) <rgemade@ford.com> | DCV Beta |  |  | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> | Lins, Ronaldo (R.) |  | - |  | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> | Lins, Ronaldo (R.) |  | - |  | Phase 1 | No | Group A | -
SYNC+_Z0186 | F000063/C | Ambient Lighting | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | 多色氛围灯 multi color ambient lighting | 车型支持多色氛围灯 | EESE | Li, Xuedong (X.) <XLI244@ford.com> | Gemade, Ralph (R.) | Vehicle Settings APIM SPSS v1.24 Nov 2, 2020 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | New | 新增7色氛围灯设置项 | Li, Xuedong (X.) <XLI244@ford.com> | Gemade, Ralph (R.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | New |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  | Gemade, Ralph (R.) <rgemade@ford.com> | DCV Beta |  |  | Y | C/O | carryover U6XX MCA | Li, Xuedong (X.) <XLI244@ford.com> | Lins, Ronaldo (R.) |  | DCV Beta |  | Y | C/O | 新增7色氛围灯设置项 carryover 747 | Li, Xuedong (X.) <XLI244@ford.com> | Lins, Ronaldo (R.) |  | DCV Beta |  | Phase 1 | No | Group A | DCV Beta
SYNC+_Z0187 | F004256 F002951 F004255 | Lock | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Lock Setting |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> | SOUZA, GABRIELLE DESIREE (G.C.) Griffin, Zachary (Z. D.) Silva, Nivea (N.B.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> | SOUZA, GABRIELLE DESIREE (G.C.) Griffin, Zachary (Z. D.) Silva, Nivea (N.B.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Silva, Nivea (N.B.) <nsilv103@ford.com> SOUZA, GABRIELLE DESIREE (G.C.) <GSOUZA64@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 Walk Away Locking (U71x) delete Power Central Lock Suite (U71x) need to do Automatic Lock Suite need to do | Li, Xuedong (X.) <XLI244@ford.com> | Almeida, Carlos (C.A.) GOMES, FERNANDO (F.) |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xuedong (X.) <XLI244@ford.com> | Almeida, Carlos (C.A.) GOMES, FERNANDO (F.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0197 |  | Mirror | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Mirror Setting |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> | Strzelczyk, Anthony (A.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> | Strzelczyk, Anthony (A.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Strzelczyk, Anthony (A.) | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | TBD |  |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0200 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Air suspension |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> |  | - | - | - | Y | Y |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> |  |  | - |  | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> |  |  | - |  | Phase 2 | No | Group A | -
SYNC+_Z0201 |  | Audio | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Alarm (ask on exit ,sensor set, perimeter, all sensors active) |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O | carryover U611/625 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover U611/625 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0202 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Aux Heater | Setting menu in IVI. For detail definition please refer 'VS-FUN-REQ-262499/A-Aux Heater' chapter in 'Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf' | EESE |  |  | Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021.pdf Settings In Infotainment CenterStack APIM Imp Guide v1.24 Oct 7, 2021.xlsx Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | - | - | - | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | N/A | N/A | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | N/A | N/A | Y | New | New Setting Item |  |  | DCV Beta |  |  | Y | NEW |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Y | NEW |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0203 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Cargo Loading |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> |  | - | - | - | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | N/A | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> |  |  | - |  | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> |  |  | - |  | Phase 2 | No | Group A | -
SYNC+_Z0204 |  | Audio | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Chimes |  | EESE | Cao,Helen |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Cao,Helen |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Cao,Helen |  | Group A | DCV Alpha2 | Y | C/O |  | Cao,Helen |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Cao,Helen |  | DCV Beta |  |  | Y | C/O | carryover 707 | Cao,Helen |  |  | DCV Beta |  | Y | C/O | carryover 747 | Cao,Helen |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0205 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Easy access height |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> |  | - | - | - | Y | Y |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | N | N |  | Li, Xuedong (X.) <XLI244@ford.com> |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | NEW |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | NEW |  | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0206 |  | Seat | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Easy Entry / Easy Exit (Seat Adjustment) |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0208 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Park Heater | Setting menu in IVI. For detail definition please refer 'VS-FUN-REQ-234362/B-Park Heater' chapter in 'Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021' | EESE |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | - | - | - | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | N/A | N/A | N | N |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | N/A | N/A | Y | New | New Setting Item | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  | DCV Beta |  |  | Y | NEW |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Y | New |  | Yao, Frank (F.) <FYAO2@ford.com>/DongYa |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0209 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Park Lock Control |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0210 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Passenger Airbag |  | EESE | Xu, Xi Hai (X.) <xxu61@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Xu, Xi Hai (X.) <xxu61@ford.com> |  | DCV Beta | - | - | Y | C/O |  | Xu, Xi Hai (X.) <xxu61@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Xi Hai (X.) <xxu61@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xu, Xi Hai (X.) <xxu61@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Xu, Xi Hai (X.) <xxu61@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0211 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Power running boards (auto, on, off) |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | N | N |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Li, Xuedong (X.) <XLI244@ford.com> |  | - | - | - | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0212 | F000162 |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Rear liftgate |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0214 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Silent Mode |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0215 |  |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Tire Mobility Kit |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Xuedong (X.) <XLI244@ford.com> |  |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0216 | F000139 |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Windows (remote open/close) |  | EESE | Li, Shiyuan (S.) <sli163@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Li, Shiyuan (S.) <sli163@ford.com> |  | - | - | - | Y | C/O |  | Li, Shiyuan (S.) <sli163@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Shiyuan (S.) <sli163@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Li, Shiyuan (S.) <sli163@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Li, Shiyuan (S.) <sli163@ford.com> | Freitas, Valdemir (V. R.) |  | DCV Beta |  | Y | C/O | carryover 747 | Li, Shiyuan (S.) <sli163@ford.com> | Freitas, Valdemir (V. R.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0217 | F000065/F000066/F000067 |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Wipers (courtesy, rain, reverse) |  | EESE | Li, Xuedong (X.) <XLI244@ford.com> | Johnson, Geoffrey (G.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Li, Xuedong (X.) <XLI244@ford.com> | Johnson, Geoffrey (G.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Li, Xuedong (X.) <XLI244@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Johnson, Geoffrey (G.) | DCV Beta |  |  | Y | Minor | carryover U611/625 New HMI layout and UE for 11.1'+23.6*2' Display | Li, Xuedong (X.) <XLI244@ford.com> | Uttar, Nikhil (N.) |  | DCV Beta |  | Y | Minor | carryover U611/625 New HMI layout and UE for 11.1'+23.6*2' Display | Li, Xuedong (X.) <XLI244@ford.com> | Uttar, Nikhil (N.) |  | DCV Beta |  | Phase 2 | No | Group A | DCV Beta
SYNC+_Z0222 |  | Seat | W# Vehicle Setting 车辆设置 | Soft Button | SoftButton - Chauffeur Seat Control |  | EESE | TBD | [7 empty] | N | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | TBD |  | - | - | - | N | N |  | TBD |  | N/A | N/A | N | N |  | TBD |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | TBD |  |  |  |  | N | N | N | TBD | [5 empty] | No
SYNC+_Z0227 | vFG000456/ vFG000284/ vFG000668/ vFG002069/ F000903 | DAT Setting | W# Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 车道偏离预警 Lane Keeping System(LKA+LDW） | Input is the steering wheel button and the camera reading the lane lines. Output is the haptic steering feel and the steering wheel turning of the vehicle if it is veering out of the lane. | EESE | Zhang, Wayne (W.R.) <wzhan114@ford.com> | Patil, Pranav (P.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Zhang, Wayne (W.R.) <wzhan114@ford.com> | Patil, Pranav (P.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Zhang, Wayne (W.R.) <wzhan114@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Zhang, Wayne (W.R.) <wzhan114@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Zhang, Wayne (W.R.) <wzhan114@ford.com> | Patil, Pranav (P.) | DCV Beta |  |  | Y | C/O | carryover 707 | Zhang, Wayne (W.R.) <wzhan114@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Zhang, Wayne (W.R.) <wzhan114@ford.com> |  |  | DCV Beta |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0229 | F000285/B | DAT Setting | W# Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 驾驶员警告系统 Driver Alert System (DAS) | 利用车外front camera，检测车道线和行车轨迹来判断驾驶员状态（疲劳+酒家+不清醒） | EESE | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) <CUPTAIN@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) |  | DCV Beta |  | Y | C/O | carryover 747 | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) |  | DCV Beta |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0230 | FO to confirm VSEM ID | DAT Setting | W# Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助 - 高速主动辅助 Active Driver Assist or ADA (DAT2.0) | high way assit 由两种模式， 其中hands free 的就是ADA. Active Driver Assist will control steering, throttle, and braking of the vehicle with only driver supervision. The feature is only availible on prequalified sections of divided highways called "Blue Zones: while the drivers' attention is on the road. The driver's attention will be monitored with a driver facing camera. ADA buids upon ACC with lane centerin to offer hands free mode on highways while in the blue zone. | EESE | Ni, Anthony (H.A.) <hni1@ford.com> | Gotadki, Shruti (S. P.) |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Ni, Anthony (H.A.) <hni1@ford.com> | Gotadki, Shruti (S. P.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Ni, Anthony (H.A.) <hni1@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Ni, Anthony (H.A.) <hni1@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | Ni, Anthony (H.A.) <hni1@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Ni, Anthony (H.A.) <hni1@ford.com> |  |  | DCV Beta |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0231 | F004650(707) F000918(788) | DAT Setting | W# Vehicle Setting 车辆设置 | DAT Setting | 3# Help Me See 视觉辅助 - 自适应远光灯 Auto High beam | uses the forward looking camera to identify leading or oncoming vehicles. If the vehicle in front is determined to be too close, the headlamps automatically switch from the high beam setting to the low beam setting. Once an on-coming vehicles passes, or th leading vehicle is out of range, the vehicle will automacticakky switch back to the high beam setting. | EESE | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) <CUPTAIN@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) |  | DCV Beta |  | Y | C/O | carryover 747 | Song, Amy (S.) <ssong18@ford.com> | Uptain, Charles (C.E.) |  | DCV Beta |  | Phase 4 | Yes | Group A | DCV Beta
SYNC+_Z0236 |  | Seat | V# Vehicle Control 车辆控制 | Seat Control 座椅控制 | Third Row Seat Position Control | To be confirm |  | TBD |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st(TBD) | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | TBD |  | - | - | - | N | N |  | TBD |  | N/A | N/A | N | N |  | TBD |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | TBD |  |  | - |  | N | N | N | TBD |  |  | - |  | Phase5 | No |  | -
SYNC+_Z0238 |  |  | V# Vehicle Control 车辆控制 | Seat Control 座椅控制 | Driver Information Display Control (DIDC) | To be confirm |  | TBD |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st(TBD) | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | TBD |  | - | - | - | N | N |  | TBD |  | N/A | N/A | N | N |  | TBD |  | N/A | N/A | N | N | N | N | N | - | N | N | N |  | N | TBD |  |  |  |  | N |  | N | TBD |  |  |  |  | Phase5 | No
SYNC+_Z0255 | F003110 | Seat | V# Vehicle Control 车辆控制 | Seat Control 座椅控制 | Rear Seat Controls Lockout: - Window - Door - Audio - Climate | To be confirm | EESE | TBD | Ganna, Spurthi Varma (S.) |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st(TBD if impact IVI) | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | TBD | Ganna, Spurthi Varma (S.) | - | - | - | N | N |  | TBD |  | N/A | N/A | N | N |  | TBD |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | TBD |  |  | - |  | N | N | N | TBD |  |  | - |  | Phase5 | No | Group A | -
SYNC+_Z0279 | F002054 | DAT Setting | W# Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助_高速驾驶辅助Highway Assist - Lane Biasing(DAT2.1 new feature) | IVI need implement Lan Biasing Setting menu | EESE | Song, Amy (S.) <ssong18@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Song, Amy (S.) <ssong18@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | Song, Amy (S.) <ssong18@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Song, Amy (S.) <ssong18@ford.com> |  |  | DCV Beta |  | Phase2 | No | Group A | DCV Beta
SYNC+_Z0280 |  | DAT Setting | W# Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助_Assisted Lane Change |  | EESE | Song, Amy (S.) <ssong18@ford.com> |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Song, Amy (S.) <ssong18@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Song, Amy (S.) <ssong18@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Song, Amy (S.) <ssong18@ford.com> |  | DCV Beta |  |  | Y | C/O | carryover 707 | Song, Amy (S.) <ssong18@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Song, Amy (S.) <ssong18@ford.com> |  |  | DCV Beta |  | Phase2 | No | Group A | DCV Beta
SYNC+_Z0281 | F000742 | DAT Setting | W# Vehicle Setting 车辆设置 | DAT Setting | 2# Help Me Drive 驾驶辅助_Lane Centering Assist | 在中控侧需要实现带有车道保持居中的CC设置项，具体参考Setting文档VS-SR-REQ-333005/C-with Lane Centering | EESE | Ni, Anthony (H.A.) <hni1@ford.com> |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Ni, Anthony (H.A.) <hni1@ford.com> |  | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Ni, Anthony (H.A.) <hni1@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Ni, Anthony (H.A.) <hni1@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Ni, Anthony (H.A.) <hni1@ford.com> | Nagavally, Rahul Reddy (R.) <rnagaval@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Ni, Anthony (H.A.) <hni1@ford.com> | Nagavally, Rahul Reddy (R.) |  | DCV Beta |  | Y | C/O | carryover 747 | Ni, Anthony (H.A.) <hni1@ford.com> | Nagavally, Rahul Reddy (R.) |  | DCV Beta |  | Phase2 | No | Group A | DCV Beta
SYNC+_Z0246 | F000760 | AEIS | W# Vehicle Setting 车辆设置 | Vehicle Setting | AEIS (Auto Engine Idle Shutdown) | For CDX747 project this feature called DSI | EESE |  | Engelbrecht, CP (C.) | For BEV: Idle Management SPSS v1.1 Jul 9, 2021.pdf For Gas: Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021.pdf Settings In Infotainment CenterStack APIM Imp Guide v1.24 Oct 7, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | Major |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | N |  | Engelbrecht, CP (C.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  |  |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display |  |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Engelbrecht, CP (C.) | DCV Beta |  |  | Y | Major | carryover 707 |  | Engelbrecht, CP (C.) |  | DCV Beta |  | Y | C/O | carryover 747 |  | Engelbrecht, CP (C.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z0244 | F001009 | Light | V# Vehicle Control 车辆控制 | Light Control 灯光控制 | Hazard Light |  | EESE |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | [5 empty] | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  | Clavel, Matheus (M.C.) |  | - |  | N | N | N |  | Clavel, Matheus (M.C.) |  | - |  |  |  | Group A | -
SYNC+_Z0276 | F002710 |  | W# Vehicle Setting 车辆设置 | Foundemental | 单踏板驾驶One Pedal Drive |  | EPE | Wu, Dean (D.) <dwu44@ford.com> |  | One-Pedal Drive APIM SPSS v1.0 May 14, 2019.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N | Wu, Dean (D.) <dwu44@ford.com> |  |  |  |  | N | N |  | Wu, Dean (D.) <dwu44@ford.com> |  | N/A | N/A | N | N |  | Wu, Dean (D.) <dwu44@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Wu, Dean (D.) <dwu44@ford.com> |  |  | - |  | N | N | N | Wu, Dean (D.) <dwu44@ford.com> |  |  | - |  |  |  | Group A | -
SYNC+_Z0258 | F000998 | Light | V# Vehicle Control 车辆控制 | Light Control 灯光控制 | Low Beam Switch | RSD - Headlamp switch - Low Beam Includes Auto Lamps and Manual Low Beam | EESE |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N | [5 empty] | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  | Mattos, Andre Licurgo (A.L.) <amattos4@ford.com> | DCV Beta |  |  | Y | NEW |  |  | Mattos, Andre Licurgo (A.L.) |  | DCV Beta |  | Y | C/O | carryover 747 |  | Mattos, Andre Licurgo (A.L.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z0259 | F000058/C | Light | V# Vehicle Control 车辆控制 | Light Control 灯光控制 | Map/Dome Lights (RSD - Manual Interior Lighting) |  | EESE |  |  | FD_Overhead Lights_1.docx FIS_Overhead Lights_1.docx FS_Overhead Lights_1.docx Overhead Lights_RSD_BD.vsdx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N | [5 empty] | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_Z0257 | F001012/B | Light | V# Vehicle Control 车辆控制 | Light Control 灯光控制 | Parking Light (North America) Position Light (EU & China) (RSD - Headlamp switch - Park Lamps) – Includes license plate |  | EESE |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N | [5 empty] | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  | Costa, Marcelo (M.N.) <MCOST104@ford.com> | DCV Beta |  |  | Y | NEW | carryover 747,but 718 do not have RSD |  | Costa, Marcelo (M.N.) |  | DCV Beta |  | Y | Minor | carryover 747,but 718 do not have RSD |  | Costa, Marcelo (M.N.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z0253 | F003090 |  | W# Vehicle Setting 车辆设置 |  | Cabin & Battery Overheat Management |  | EESE |  | Collins, Lynn (L.) | FIS_03092021 (2).docx FIS_03092021 (4).docx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N |  | Collins, Lynn (L.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_Z0247 | F000122/B | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Heated Backlight (climate) | Rear Derfost soft button后挡风玻璃加热 Hardbutton Indicator 硬按键指示灯（如果有） Pop-Up message Status Bar | EESE | Shi, Song (S.S.) <sshi24@ford.com> | Hossain, Mohammed (M.A.) | Climate Control APIM SPSS v1.0 May 28, 2021.pdf Climate Control APIM Imp Guide v1.0 May 28, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | N | Shi, Song (S.S.) <sshi24@ford.com> | Hossain, Mohammed (M.A.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Shi, Song (S.S.) <sshi24@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Shi, Song (S.S.) <sshi24@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | C/O | carryover 707 | Shi, Song (S.S.) <sshi24@ford.com> |  |  | DCV Beta |  | Y | C/O | carryover 747 | Shi, Song (S.S.) <sshi24@ford.com> |  |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z0285 | F001212/A | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Driver Focused Mode |  | EESE |  | Wijaya, Halim (H.) | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ.pdf 04_06_00 Driver Focused Mode vA.docx DFM FD 3.9.21 del.docx DFM FIS 3.26.21e.docx DFM FS 3.9.21 nd.docx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N |  | Wijaya, Halim (H.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  | Wijaya, Halim (H.) | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_Z0287 | F003516 | Seat | V# Vehicle Control 车辆控制 | Seat Control 座椅控制 | First Row Seat Position Control | IVI need add Cushion Extension in Multi contour seat view | EESE | Du, Hao (H.) <HDU9@ford.com> | Aguilar, Diana (D.S.) |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N | Du, Hao (H.) <HDU9@ford.com> | Aguilar, Diana (D.S.) |  |  |  | Y | C/O |  | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Beta1 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Beta1 | Y | Minor | Adapt new scree size 12' | Du, Hao (H.) <HDU9@ford.com> | Sahutske, Matthew (M.J.) <msahuts1@ford.com> | DCV Beta |  |  | Y | NEW | The Passenger Seat on CDX747 includes the option to have Calf Rest, for U71X those seats have Thigh Extension in place of Calf Rest U71X has the option for a 4 way power lumbar that is not available on CDX747 | Du, Hao (H.) <HDU9@ford.com> | Sahutske, Matthew (M.J.) |  | DCV Beta |  | Y | Minor | U71X has the option for a 4 way power lumbar that is not available on CDX747 | Du, Hao (H.) <HDU9@ford.com> | Sahutske, Matthew (M.J.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z1002 | F000564 |  | W# Vehicle Setting 车辆设置 | Vehicle Setting | Blindspot Detection | Menu Setting for BLS | EESE | Liu, Hongxin (H.) <HLIU162@ford.com> | Crosby, Michael (M.C.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Liu, Hongxin (H.) <HLIU162@ford.com> | Crosby, Michael (M.C.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Liu, Hongxin (H.) <HLIU162@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Liu, Hongxin (H.) <HLIU162@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Liu, Hongxin (H.) <HLIU162@ford.com> | Crosby, Michael (M.C.) | DCV Beta |  |  | Y | C/O | carryover 707 | Liu, Hongxin (H.) <HLIU162@ford.com> | Crosby, Michael (M.C.) |  | DCV Beta |  | Y | C/O | carryover 747 | Liu, Hongxin (H.) <HLIU162@ford.com> | Crosby, Michael (M.C.) |  | DCV Beta |  |  | No | Group A | DCV Beta
SYNC+_Z0288 | F000178/D |  | W# Vehicle Setting 车辆设置 | Vehicle Setting | Perimeter Anti-Theft Alarm |  | EESE |  | Talaga, Joshua (J.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y | New |  |  |  | N/A | N/A | N/A | N | N | N |  | Talaga, Joshua (J.) |  |  |  | N | N |  |  | Mortarotti, Mariano (M.) | N/A | N/A | Y | Minor | New HMI layout and UE for 12.3'+27' Display |  |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Martinez, Diego (D.) <dmart546@ford.com> | DCV Beta |  |  | Y | Minor | carryover 2024 U611/625 New HMI layout and UE for 11.1'+23.6*2' Display |  | Loiola, Victor Henrique (V.P.) |  | DCV Beta |  | Y | NEW |  |  | Loiola, Victor Henrique (V.P.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z0292 | F003517 |  | V# Vehicle Control 车辆控制 | Seat Control 座椅控制 | Second Row Seat Position Control |  |  |  | Aguilar, Diana (D.S.) | CDX747 SRS Feature Document.docx CDX746_747 2nd Row Seat Position Control- 052021.vsdx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N |  | Aguilar, Diana (D.S.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | Y | NEW | CDX747 have all manual Pitch and Slide, for U71X those seat all have a Power Latch Release for the Manual Pitch and Slide CDX747 have manual Fold Flat, for U71X those seat all have an option for Power Fold Flat |  | Sahutske, Matthew (M.J.) |  | DCV Beta |  | Y | Major | CDX747 have all manual Pitch and Slide, for U71X those seat all have a Power Latch Release for the Manual Pitch and Slide CDX747 have manual Fold Flat, for U71X those seat all have an option for Power Fold Flat |  | Sahutske, Matthew (M.J.) |  | DCV Beta |  | Phase5 | No | Group A | DCV Beta
SYNC+_Z0294 | F002010/B |  | V# Vehicle Control 车辆控制 | Soft Button | Frunk Soft Switch |  |  |  | Butler, Jordan (J.) | Frunk Softswitch Interface Client SPSS v1.2 July 15, 2020 Frunk Softswitch Interface Client v2 SPSS v1.0 July 15, 2020 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N |  | Butler, Jordan (J.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_Z0295 | F000123/C |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Heated Steering Wheel Setting for Remote Start |  |  | Yan, Sophie (C.) <cyan10@ford.com> | Shirazawa, Diogo (D.H.) | Settings In Infotainment CenterStack SPSS v1.21 Mar 31, 2021（Seats and Steering Wheel - Remote Start） | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N | Yan, Sophie (C.) <cyan10@ford.com> | Shirazawa, Diogo (D.H.) |  |  |  | Y | C/O |  | Yan, Sophie (C.) <cyan10@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Yan, Sophie (C.) <cyan10@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Yan, Sophie (C.) <cyan10@ford.com> | Shirazawa, Diogo (D.H.) <dshiraza@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Yan, Sophie (C.) <cyan10@ford.com> | Shirazawa, Diogo (D.H.) |  | DCV Beta |  | Y | C/O | carryover 747 | Yan, Sophie (C.) <cyan10@ford.com> | Shirazawa, Diogo (D.H.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z0297 | F003518 | Seat | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Seat Temperature Control Setting for Remote Start |  |  | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) | Settings In Infotainment CenterStack SPSS v1.21 Mar 31, 2021 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta1 | 2022-08-31 | - | N | N | N | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  |  |  | Y | C/O |  | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Du, Hao (H.) <HDU9@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) | DCV Beta |  |  | Y | C/O | carryover 707 | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  | DCV Beta |  | Y | C/O | carryover 747 | Du, Hao (H.) <HDU9@ford.com> | Mlynarczyk, Stephanie (S.A.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z0293 | F000165/D |  | V# Vehicle Control 车辆控制 | Soft Button | Power Liftgate Soft switch |  | EESE |  | Gunaratnam, Raj (M.) | LiftGate Softswitch Interface Client SPSS v1.2 June 21 2019.pdf LiftGate Softswitch Interface Client Imp Guide v1.2 June 21 2019.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV2 | 2022-01-12 | 2022-01-26 | Y | C/O |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | N |  | Gunaratnam, Raj (M.) | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  |  |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display |  |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z1003 | F000800 | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Heated Mirrors | 包含前除霜、后除霜、最大除霜 包含Remote Start Setting项 | EESE | Xie, Will (W.) <wxie15@ford.com> | D, SelvaMuthu (D.)<DSELVA@FORD.COM> | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Climate Control APIM SPSS v1.0 May 28, 2021.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N |  | D, SelvaMuthu (D.)<DSELVA@FORD.COM> | DCV Beta | 2022-03-12 | 2022-03-19 | Y | C/O |  | Xie, Will (W.) <wxie15@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xie, Will (W.) <wxie15@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Melo, Isabela (I. P.) <imelo4@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 |  | Melo, Isabela (I. P.) |  | DCV Beta |  | Y | C/O | carryover 747 |  | Melo, Isabela (I. P.) |  | DCV Beta |  | Phase1 | No | Group A | DCV Beta
SYNC+_Z1004 | F003074 F000121 | Climate | V# Vehicle Control 车辆控制 | Climate Control 空调控制 | Heated Wiper Blade Heated Windshield |  | EESE |  | Lima, Dorivaldo (.) | FNV2 Climate Control System HMI Requirements (EFP_RCCM) vZ Climate Control APIM SPSS v1.0 May 28, 2021 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N | N | N |  | Lima, Dorivaldo (.) |  |  |  | Y-1st | New |  |  |  | Group A | DCV Alpha2 | Y | New |  |  |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Lima, Dorivaldo (.) | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  | Phase5 | No | Group A | -
SYNC+_Z1005 | F000189 | Keypad | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Keypad |  | EESE |  | Ferreira, Eliane (E.C.) | Vehicle Settings APIM SPSS v1.23 Mar 19, 2020 | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N |  | Ferreira, Eliane (E.C.) |  |  |  | Y-1st | New |  |  |  | Group A | DCV Alpha2 | Y | New |  |  |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Ferreira, Eliane (E.C.) | DCV Beta |  |  | Y | Minor | carryover U611 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | Ferreira, Eliane (E.C.) |  | DCV Beta |  | Y | Minor | carryover U611 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | Ferreira, Eliane (E.C.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1007 | F002216/A |  |  |  | Global Beltminder | IOD页面一个子项，仪表侧做逻辑处理，IVI侧只需要做显示逻辑 | EESE | Xu, Xi Hai (X.) <xxu61@ford.com> | Dsouza, Aston (.) |  | Core_Service | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y | C/O |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | N | Xu, Xi Hai (X.) <xxu61@ford.com> | Dsouza, Aston (.) | DCV0 | 2022-03-12 | 2022-03-19 | Y | C/O |  | Xu, Xi Hai (X.) <xxu61@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Xu, Xi Hai (X.) <xxu61@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Xu, Xi Hai (X.) <xxu61@ford.com> | Dsouza, Aston (.) | DCV Beta |  |  | Y | Minor | carryover U553/554 MCA New HMI layout and UE for 11.1'+23.6*2' Display | Xu, Xi Hai (X.) <xxu61@ford.com> | Ferreira, Islan Peterson (I.P.) |  | DCV Beta |  | Y | Minor | carryover U553/554 MCA New HMI layout and UE for 11.1'+23.6*2' Display | Xu, Xi Hai (X.) <xxu61@ford.com> | Ferreira, Islan Peterson (I.P.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z1008 | F000810 |  |  |  | Driver_Information_Display_Control | IOD：Fuel Economy Other：Trip Summary at key off “FHEV not ready to drive” | EPE | Jin Flora< JJIN17@ford.com> | Sousa, Filipe (F.B.) |  | Core_Service | 10% | 0% | 0% | 90% | Y | Y | DCV3 | 2022-02-16 | 2022-03-02 | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | Y | C/O | N | Jin Flora< JJIN17@ford.com> | Sousa, Filipe (F.B.) | DCV0 | 2022-03-12 | 2022-03-19 | N | N |  | Jin Flora< JJIN17@ford.com> |  | N/A | N/A | N | Major | New HMI layout and UE for 12.3'+27' Display | Jin Flora< JJIN17@ford.com> |  | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | N | N | N | Jin Flora< JJIN17@ford.com> |  |  | - |  | N | N | N | Jin Flora< JJIN17@ford.com> |  |  | - |  |  |  | Group A | -
SYNC+_Z0289 | F000109/D FNG000760 |  |  |  | TPMS | IOD页面显示胎压监控信息,IVI不做任何胎压检测逻辑处理，只负责做对应人机交互界面的显示 | EESE | Wang, Vincent (X.) <xwang151@ford.com> | Dave, Brijesh (B.) | 2016 TPM Sensor ES-9L2T-1A150-AF.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | Y | C/O |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O | N | Wang, Vincent (X.) <xwang151@ford.com> | Dave, Brijesh (B.) | DCV0 | 2022-03-12 | 2022-03-19 | Y | Major |  | Wang, Vincent (X.) <xwang151@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | New HMI layout and UE for 12.3'+27' Display | Wang, Vincent (X.) <xwang151@ford.com> |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' | Wang, Vincent (X.) <xwang151@ford.com> | Baldi, Valter (V. Z.) <vbaldi@ford.com> | DCV Beta |  |  | Y | C/O | carryover 707 | Wang, Vincent (X.) <xwang151@ford.com> | Silva, Tays (T.C.) |  | DCV Beta |  | Y | C/O | carryover 747 | Wang, Vincent (X.) <xwang151@ford.com> | Silva, Tays (T.C.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z1013 | F000864 |  |  |  | Power Release/Cinch Doors |  | EESE |  | Weiler, Jonathan (J.P.) | [6 empty] | Y-1st | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N |  |  |  | Weiler, Jonathan (J.P.) |  |  |  | Y-1st | New |  |  | Weiler, Jonathan (J.P.) | Group A | DCV Alpha2 | Y-1st | New |  |  | Weiler, Jonathan (J.P.) | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_Z1014 | F000604 |  |  |  | Engine Starting Stationary | Cluster feature no impact in IVI domain | EESE |  | Hall, Jonathan (J.) | [6 empty] | Y-1st | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N |  |  |  | Hall, Jonathan (J.) |  |  |  | Y-1st | New |  |  | Hall, Jonathan (J.) | Group A | DCV Alpha2 | Y-1st | New |  |  | Hall, Jonathan (J.) | Group A | DCV Alpha2 | N | N | N | N | N | - |  |  | Y | Minor | carryover U611 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | Hall, Jonathan (J.) |  | DCV Beta |  | Y | Minor | carryover U611 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | Hall, Jonathan (J.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1015 | F003413,F003414,F003370 |  |  |  | Cellular Remote Start / Stop (U6XX) |  | ECDX |  | Syed, Imtiaz (I.S.) |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y-1st | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N |  |  |  | Syed, Imtiaz (I.S.) |  |  |  | Y-1st | New |  |  | Syed, Imtiaz (I.S.) | Group A | DCV Alpha2 | Y-1st | New |  |  | Syed, Imtiaz (I.S.) | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Syed, Imtiaz (I.S.) | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1016 | F000818 |  |  |  | Plug In Charging (PIC) | [5 empty] | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N | [7 empty] | N | N |  |  |  | N/A | N/A | N |  |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  | Phase5 | No | Group A | -
SYNC+_Z1017 | F005350 |  |  |  | EV Charge Programming | [5 empty] | Core_Service_Supplier | 10% | 0% | 0% | 90% |  | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | [7 empty] | N | N |  |  |  | N/A | N/A | N |  |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | [5 empty] | N | N | N | [5 empty] | Phase5 | No | Group A
SYNC+_Z1018 | F005310 |  |  |  | Buttonless Push To Start – BEV | [5 empty] | Core_Service_Supplier | 10% | 0% | 0% | 90% |  | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | [7 empty] | N | N |  |  |  | N/A | N/A | N |  |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | [5 empty] | N | N | N | [5 empty] | Phase5 |  | Group A
SYNC+_Z1019 | F003410 |  |  |  | Cellular Remote Start w/Extend Remote Start FNV3 | [5 empty] | SW_Tier1 | 10% | 60% | 0% | 30% |  | N |  |  |  | Y | C/O |  |  |  | DCV Beta1 | 2022-08-31 | - | N | [7 empty] | N | N |  |  |  | N/A | N/A | N |  |  |  |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | Y | NEW |  |  | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  | Y | C/O | carryover 747 |  | Al-abdulrasul, Ahmed (A.) |  | DCV Beta |  | Phase5 |  | Group A | DCV Beta
SYNC+_Z1020 | F003411 |  |  |  | Cellular Scheduled Remote Start | [5 empty] | SW_Tier1 | 10% | 80% | 0% | 10% |  | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | [7 empty] | N | N |  |  |  | N/A | N/A | N |  |  |  |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  |  | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  | Phase5 |  | Group A | -
SYNC+_Z1021 | F003774 |  |  |  | Augmented Reality |  |  |  |  | Augmented Reality_AR_ Feature Document_v2.1_7_14_2021.pdf Augmented Reality_AR_Functional Document_v2.1_7_14_2021.pdf Augmnted Reality_AR_Feature Implementation Specification_v1.1 _07_14_2021.pdf | [6 empty] | N |  |  |  | Y-1st | New |  |  |  | DCV1 | 2022-12-24 | 2023-01-07 | N | [7 empty] | N | N |  |  |  | N/A | N/A | N |  |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  | Abdelhamid, Mahmoud (M.) |  | - |  | N | N | N |  | Abdelhamid, Mahmoud (M.) |  | DCV Beta |  |  |  | Group B | DCV Beta
SYNC+_Z1022 |  |  | ZZ# Foundemental Function 基础功能 |  | Integrated AVAS (Acoustic Vehicle Alerting System) | IVI need integrate AVAS algorithm, to make sure the external speaker can generate alrm sound during low speed. | EESE |  |  | AVAS Feature Document.docx ES-HU5T-14G113-AE.doc FS-ML3T-14G113-AB v1.4_base.docx | HW_Tier1 | 100% | 0% | 0% | 0% |  | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  |  |  | - | - | - | N | N |  |  |  | N/A | N/A | N |  |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  | Phase5 | No | Group A | -
SYNC+_Z0241 | F001023 |  | ZZ# Foundemental Function 基础功能 |  | Automatic Dynamic Leveling | NO impact for IVI | EESE | Zhou, Travis (C.X.) <czhou17@ford.com> | Gajjar, Jayneel Asutosh (J.) | [6 empty] | N | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N |  |  | Zhou, Travis (C.X.) <czhou17@ford.com> | Gajjar, Jayneel Asutosh (J.) |  |  |  | N | N |  | Zhou, Travis (C.X.) <czhou17@ford.com> |  | N/A | N/A | N | N |  | Zhou, Travis (C.X.) <czhou17@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Zhou, Travis (C.X.) <czhou17@ford.com> | Lima, Alexa Larissa (A.d.) |  | - |  | N | N | N | Zhou, Travis (C.X.) <czhou17@ford.com> | Lima, Alexa Larissa (A.d.) |  | - |  |  |  |  | -
SYNC+_Z0261 | F001149/E |  | ZZ# Foundemental Function 基础功能 |  | Considerate Prompts |  | ECDX | Lu, Chao (C.) <clu42@ford.com> | Gonzalez, Cesar (C.) | ECPI_VSHA_Feature_Requirement_Document_v1_1.docx | [5 empty] | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N |  |  | Lu, Chao (C.) <clu42@ford.com> | Gonzalez, Cesar (C.) |  |  |  | N | N |  | Lu, Chao (C.) <clu42@ford.com> |  | N/A | N/A | N | N |  | Lu, Chao (C.) <clu42@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Lu, Chao (C.) <clu42@ford.com> |  |  | - |  | N | N | N | Lu, Chao (C.) <clu42@ford.com> |  |  | - |  |  |  |  | -
SYNC+_Z0256 | F000148/D |  | V# Vehicle Control 车辆控制 | Softbutton | Power Folding Mirrors w & w/o autofold (RSD - Mirror Fold) |  | EESE |  | Strzelczyk, Anthony (A.) | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N | DCV3 | 2022-02-16 | 2022-03-02 | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | Y | C/O |  |  | D, SelvaMuthu (D.) <dselva@ford.com> | DCV beta |  |  | Y-1st | New |  |  |  | Group A | DCV Alpha2 | Y | New |  |  |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Strzelczyk, Anthony (A.) | DCV Beta |  |  | Y | NEW |  |  | Strzelczyk, Anthony (A.) |  | DCV Beta |  | Y | C/O | carryover 747 |  | Strzelczyk, Anthony (A.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z0235 | F004130 |  | ZZ# Foundemental Function 基础功能 |  | Rear Seat Occupant Alert |  | SE-->EESE |  | Nunes, Liandro (L. F.) | Rear Seat Occupant Alert APIM SPSS v1.3 Jun 4, 2021.pdf Rear Seat Occupant Alert APIM Imp Guide v1.3 Jun 4, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N |  |  |  | Nunes, Liandro (L. F.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_Z0263 | F003751 |  | ZZ# Foundemental Function 基础功能 |  | Enhanced Dash Camera |  | EESE |  | Eteer, Malik (M.) | DRAFT_Integrated Dash Cam PDC SPSS 060421.docx ENG-768637B-VideoRecorderService_Draft_2021-06-15.docx Feature Document 2021-05-19.docx VideoPlayback_VSEMExport.docx ConOps_EDC_v0.03.docx ConOps_IDC_v0.06.docx Feature Document 2021-05-21 meteer Markup.docx IDC-FunctionalSpecDocument.docx | Core_Service_Supplier | 40% | 0% | 0% | 60% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  |  | Eteer, Malik (M.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_Z0250 | F003170 |  | V# Vehicle Control 车辆控制 | Softbutton | PDLC SkyLite Digital Shade |  | SE-->EESE |  | Vandenbrink, Terry (T.) |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N |  |  |  | Vandenbrink, Terry (T.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_Z0262 | F005770 |  | ZZ# Foundemental Function 基础功能 |  | Integrated Sentinel(Video-Based Vehicle Monitoring) |  | SE-->EESE |  | Luken, Richard (R.) | ENG-754753E-CameraManagerService - Released.docx H90_SYNC4_Sentinel_D_v0_03_MY21.vsd Sent_FD_20210617a_Phoenix.docx Sent_FIS_20210617b_Phoenix.docx Sent_FS_20210617a_Phoenix.docx Sentinel CAN an SOA signals revised.xlsx Sentinel Revised Proposal July 07 2021.pptx Sentinel SPSS -Draft_V4_7_9.docx Spec 负责人.PNG | HW_Tier1 | 50% | 0% | 0% | 50% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  |  | Luken, Richard (R.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | Y | NEW |  |  | Minous, Corey (C.) |  | DCV Beta |  | Y | C/O | carryover 747 |  | Minous, Corey (C.) |  | DCV Beta |  | Phase5 | Yes | Group A | DCV Beta
SYNC+_Z0251 | F002870 |  | V# Vehicle Control 车辆控制 | Softbutton | Stowable Steering Column w/ Deploying Tray |  | SE-->EESE |  | Lau, Tok (T. W.) | ConOps_Stowable Steering Wheel_v0.13.docx Feature Connected Data Analytics_SSW.xlsx FeatureDocSSW2_22.docx FunctionalSpecSSDTS2_24.docx SSW_FIS_3_2_2021.docx SSW_FIS_SCMB_062821.docx | [5 empty] | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  |  | Lau, Tok (T. W.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  | Phase5 |  | Group A | -
SYNC+_Z0286 | F004530/A |  | ZZ# Foundemental Function 基础功能 |  | Drive Control Optimization | Include the following feature: Buttonless Push to Start Feature Document AEIS (DSIS) Feature Document PPO (Pro Power Onboard) Feature Document(not for CDX747) RePA (Remote Park Assist) Feature Document Global Belt Minder Feature Document Multi-Contour Seat Feature Document Power Center Lock Suite Feature Document Classic Memory (EE/EE) Feature Document Welcome / Farewell Feature Document Lincoln Embrace Feature Document NFC (Near Field Communication) Feature Document Perimeter Anti-Theft Alarm Feature Document Range Selection Feature Document RSOA (Rear Seat Occupant Alert) Feature Document Walk Away Locking Feature Document | SE-->EESE |  |  | Buttonless Push to Start Feature Document AEIS (DSIS) Feature Document PPO (Pro Power Onboard) Feature Document(not for CDX747) RePA (Remote Park Assist) Feature Document Global Belt Minder Feature Document Multi-Contour Seat Feature Document Power Center Lock Suite Feature Document Classic Memory (EE/EE) Feature Document Welcome / Farewell Feature Document Lincoln Embrace Feature Document NFC (Near Field Communication) Feature Document Perimeter Anti-Theft Alarm Feature Document Range Selection Feature Document RSOA (Rear Seat Occupant Alert) Feature Document Walk Away Locking Feature Document | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | [7 empty] | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_Z1006 | F000171 |  | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Classic Memory |  | SE-->EESE |  | Brasileiro, Matheus (M.B.) | Enhanced_Memory_With_Soft_Button_Feature_Level_Specification_v1.3_Aug_13, 2021 | Core_Service_Supplier | 10% | 10% | 0% | 80% | Y | N |  |  |  | Y | C/O |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  |  | Brasileiro, Matheus (M.B.) |  |  |  | Y | C/O |  |  |  | Group A | DCV Alpha2 | Y | C/O |  |  |  | Group A | DCV Alpha2 | Y | Minor | Adapt new scree size 12' |  | Brasileiro, Matheus (M.B.) <mfern203@ford.com> | DCV Beta |  |  | Y | Minor | impact in cluster |  | Brasileiro, Matheus (M.B.) |  | DCV Beta |  | Y | Minor | impact in cluster |  | Brasileiro, Matheus (M.B.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z1009 | F001790 |  | ZZ# Foundemental Function 基础功能 |  | Key in Reminder |  | SE-->EESE |  | Silva, Diego (D.M.) | [6 empty] | N | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N |  |  |  | Silva, Diego (D.M.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  | Marques, Nathan (N. C.) |  |  |  | N | N | N |  | Marques, Nathan (N. C.)
SYNC+_Z1010 | F002070 | NFC | W# Vehicle Setting 车辆设置 | Vehicle Setting 车辆设置 | Fob Free Entry and Ignition (NFC) | Cluster feature no impact in IVI | SE-->EESE |  | Ehsan, Farhan (F.) | NFC Entry & Start InterfaceClient SPSS v1.1 July 9, 2021.pdf NFC Entry & Start InterfaceClient Imp Guide v1.1 July 9, 2021.xlsx | [5 empty] | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  |  | Ehsan, Farhan (F.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  | Bonnell-Kangas, Aaron (A.) <abonnel1@ford.com> | DCV Beta |  |  | N | N | N |  | Zuniga lopez guerrero, Gonzalo (G.) |  | - |  | Y | C/O | carryover 747 |  | Zuniga lopez guerrero, Gonzalo (G.) |  | DCV Beta |  |  |  | Group B | DCV Beta
SYNC+_Z0290 | F004711 |  | ZZ# Foundemental Function 基础功能 |  | Steering Horizon Control | 方向盘多功能按键 | SE-->EESE | Zhu, Jing Yuan (J.) <JZHU65@ford.com> | Li, Richard (R.Y.) |  | HW_Tier1 | 70% | 10% | 10% | 10% | Y | Y | R00 | 2022-05-18 | 2022-06-01 | Y | Minor |  |  |  | DCV Beta | 2022-07-31 | 2022-08-14 | N |  |  | Zhu, Jing Yuan (J.) <JZHU65@ford.com> | Li, Richard (R.Y.) |  |  |  | N | N |  | Zhu, Jing Yuan (J.) <JZHU65@ford.com> |  | N/A | N/A | N | N |  | Zhu, Jing Yuan (J.) <JZHU65@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | Y | Minor | vs 747,SHC has not mirror adjustments for 718,it is hard mirror switches standard add pedal & column & mirror adjustment function | Zhu, Jing Yuan (J.) <JZHU65@ford.com> | Li, Richard (R.Y.) |  | DCV Beta |  | Y | Minor | vs 747,SHC has not mirror adjustments for 718,it is hard mirror switches standard | Zhu, Jing Yuan (J.) <JZHU65@ford.com> | Li, Richard (R.Y.) |  | DCV Beta |  |  |  | Group B | DCV Beta
SYNC+_Z0291 | F001010/B |  | V# Vehicle Control 车辆控制 | Softbutton | Rear Fog Lights |  | EESE |  | D'Agostino, Antonio (A.) |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | DCV Beta1 | 2022-08-31 | - | N |  |  |  | D'Agostino, Antonio (A.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | Y | Minor | Adapt new scree size 12' |  | D'Agostino, Antonio (A.) <adagost3@ford.com> | DCV Beta |  |  | Y | NEW |  |  | Antunes, Mauricio (M.C.) |  | DCV Beta |  | Y | C/O | carryover 747 |  | Antunes, Mauricio (M.C.) |  | DCV Beta |  |  |  | Group A | DCV Beta
SYNC+_Z1011 | F001451 | DAT Setting | W# Vehicle Setting 车辆设置 | DAT Setting | Blind_Spot_Assist | This is a IPC feature,no impact in IVI | EESE |  | McWilliams, John (J.S.) |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N |  | Liu, Hongxin (H.) <HLIU162@ford.com> | McWilliams, John (J.S.) | DCV Beta |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  | McWilliams, John (J.S.) |  | - |  | N | N | N |  | McWilliams, John (J.S.) |  | - |  |  |  |  | -
SYNC+_Z1012 | F002430 |  | ZZ# Foundemental Function 基础功能 |  | Plug and Charge |  | ECDX | Wang, Yixuan (Vovo) <ywang219@ford.com> | Jujavarapu, Sandeep (S.) | Plug and Charge SPSS v1.7 Jun 28, 2021.pdf Plug and Charge APIM Imp Guide v1.7 Jun 28, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | N/A | N/A | N/A | N |  |  | Wang, Yixuan (Vovo) <ywang219@ford.com> | Jujavarapu, Sandeep (S.) |  |  |  | N | N |  | Wang, Yixuan (Vovo) <ywang219@ford.com> |  | N/A | N/A | N | N |  | Wang, Yixuan (Vovo) <ywang219@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | Wang, Yixuan (Vovo) <ywang219@ford.com> |  |  | - |  | N | N | N | Wang, Yixuan (Vovo) <ywang219@ford.com> |  |  | - |  |  |  | Group A | -
SYNC+_Z0296 | F002214/A |  | ZZ# Foundemental Function 基础功能 |  | Passenger Airbag Disable Indicate Telltale |  |  |  | Dsouza, Aston (.) |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y-1st | New |  |  |  | TBD | 2022-03-16 | 2022-03-30 | N |  |  |  | Dsouza, Aston (.) |  |  |  | N | N |  |  |  | N/A | N/A | N | N |  |  |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  | Group A | -
SYNC+_0215 |  |  | R# EV Features 新能源汽车功能 | 2# Distance to Empty (DTE) | 剩余里程显示Range Ring-Nav Screen (DTE) | Range Ring-Nav Screen 可续航里程在导航界面的显示 | EPE | Wu, Dean (D.) <dwu44@ford.com> |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Wu, Dean (D.) <dwu44@ford.com> |  | - | - | - | N | N |  |  |  | N/A | N/A | N | N |  | Wu, Dean (D.) <dwu44@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  | Phase 2 | No | Group A | -
SYNC+_0236 | F000812 |  | R# EV Features 新能源汽车功能 | 2# Distance to Empty (DTE) | Cloud Based Battery Management System | Including： - Battery lifetime extension 电池寿命延长 - Range optimization 里程优化 - Battery health monitor 电池健康监测 - Real time driving recommendation based on DTC 基于DTC的实时驾驶建议 - Battery performance digital certificate | ECDX | Yang, Jessica (Yu.) <yyang158@ford.com> |  | Cloud Enhanced DTE APIM SPSS v1.2 Nov 19, 2020.docx | [5 empty] | N | N |  |  |  | N | N |  |  |  | N/A | N/A | N/A | N | N | N | Yang, Jessica (Yu.) <yyang158@ford.com> |  | - | - | - | N | N |  | Yang, Jessica (Yu.) <yyang158@ford.com> |  | N/A | N/A | N | N |  | Yang, Jessica (Yu.) <yyang158@ford.com> |  | N/A | N/A | N | N | N | N | N | - |  |  | N | N | N | [5 empty] | N | N | N | [5 empty] | Phase5 | No | Group A
SYNC+_Z0249 | F000146/B |  |  |  | Electrochromatic Automatic Day/Night Mirrors | [10 empty] | N | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | N | N | N | N | N | - |  |  | N | N | N | [5 empty] | N | N | N
SYNC+_Z1027 | F001131 |  |  |  | AWD / 4WD: Torque Transfer for Handling & Traction | Display Status of AWD System in Sync，it is cluster feature，not impact IVI |  |  |  | AWD_4WD FIS Version 1.1.docx AWD_4WD FD Version 3.1.docx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N |  |  |  | +AR165E166AU166:AV166 |  |  | Y | New |  |  | Brizuela, Israel (B.) <IMORAL25@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | DCV Beta |  | Y | Minor | carryover P702 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  |  |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1028 | F005090 |  |  |  | Active Exhaust | Setting menu in IVI. For detail definition please refer 'VS-FUN-REQ-280671/B-Exhaust Mode' chapter in 'Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf' | EESE |  |  | Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021.pdf Settings In Infotainment CenterStack APIM Imp Guide v1.24 Oct 7, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Silva, Lucas (L.F.) <lsilv200@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1029 | F003420 |  |  |  | Trail 1-Pedal Driving | Soft button, refer 'Off-Road Controls APIM SPSS v1.1 Oct 2, 2020.pdf' chapter '4.6 ORC-FUN-REQ-393749/A-Select Hill Descent Control, Trail Control, or Trail One-Pedal Drive Soft-Switch' | EESE |  |  | Off-Road Controls APIM SPSS v1.1 Oct 2, 2020.pdf Off-Road Controls APIM Imp Guide v1.1 Oct 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Brown, Andrew (A.A.) <abrown75@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1030 | F000744 |  |  |  | Trailer Brake Control | Setting menu in IVI. For detail definition please refer 'VS-FUN-REQ-280668/A-Trailer Brake' chapter in 'Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf' | EESE |  |  | Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021.pdf Settings In Infotainment CenterStack APIM Imp Guide v1.24 Oct 7, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Gonzalez, Cesar (C.) <cgonz204@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1032 | F000906 |  |  |  | Distance Indication | Setting menu in IVI. For detail definition please refer 'VS-FUN-REQ-233569/B-Pre-Collision Assist' chapter in 'Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf' | EESE |  |  | Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021.pdf Settings In Infotainment CenterStack APIM Imp Guide v1.24 Oct 7, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Podsiad, Nikole (N.T.) <npodsiad@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1033 | F002030 |  |  |  | Trail Turn Assist (TTA) | TTA Soft Switch, refer 'Off-Road Controls APIM SPSS v1.1 Oct 2, 2020.pdf' Chapter '4.4 ORC-FUN-REQ-393726/A-Select Off-Road Turn Assist Soft-Switch' (Vehicle Setting SPSS chapter '3.20 VS-FUN-REQ-375892/A-Trail Turn Assist' should be ingore) TTA IOD, refer 'Off-Road Status IOD APIM SPSS v1.0 Aug 23, 2019.pdf' | EESE |  |  | Off-Road Controls APIM SPSS v1.1 Oct 2, 2020.pdf Off-Road Controls APIM Imp Guide v1.1 Oct 2, 2020.xlsx Off-Road Status IOD APIM SPSS v1.0 Aug 23, 2019.pdf Off-Road Status IOD APIM Imp Guide v1.0 Aug 23, 2019.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Dickinson, Taylor (G.T.) <GDICKIN6@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1034 | F000539 |  |  |  | Trail Control (TRAIL) | Soft button, refer 'Off-Road Controls APIM SPSS v1.1 Oct 2, 2020.pdf' chapter '4.6 ORC-FUN-REQ-393749/A-Select Hill Descent Control, Trail Control, or Trail One-Pedal Drive Soft-Switch' | EESE |  |  | Off-Road Controls APIM SPSS v1.1 Oct 2, 2020.pdf Off-Road Controls APIM Imp Guide v1.1 Oct 2, 2020.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Brown, Andrew (A.A.) <abrown75@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1036 | F002052 |  |  |  | Trailer Light Check (FNV3) | The Trailer Light Check feature will allow the vehicle user to independently visually check the light operation of a towed trailer. Upon activation of the feature the vehicle and trailer lights will illuminate in a particular sequence to help the user confirm all lights are operational. | EESE |  |  | Trailer Light Check APIM SPSS v1.1 Feb 2, 2021.pdf Trailer Light Check APIM Imp Guide v1.1 Feb 2, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Vieira, Eric Aleksander (E.A.) <evieira1@ford.com> | DCV Beta |  |  | Y | NEW |  |  | Antunes, Mauricio (M.C.) |  | DCV Beta |  | Y | Minor | carryover P702 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | Antunes, Mauricio (M.C.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1037 | F003514 |  |  |  | Auto Electric Park Brake (AEPB) aka AEPB or Park Hold | Auto EPB feature should help the user in Vehicle to Trailer hitching process. Its idea is to keep the vehicle in a standstill (if the conditions apply) so the user can inspect the vehicle to Hitch distance. IVI shoud provide a softbutton to cumtomer to enable/disable AutoEPB. | EESE |  |  | Auto EPB SPSS v1.0 Oct 11, 2018.pdf Auto EPB APIM Imp Guide v1.0 Oct 11, 2018.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Ferencz, Alexander (A.J.) <aferenc3@ford.com> | DCV Beta |  |  | Y | NEW |  |  | Ferencz, Alexander (A.J.) |  | DCV Beta |  | Y | Minor | carryover P702 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | Ferencz, Alexander (A.J.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1038 | F003421 |  |  |  | Neutral Flat Tow (Recreational Tow) | Setting menu in IVI. For detail definition please refer 'VS-FUN-REQ-333160/B-Neutral Tow' chapter in 'Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf' | EESE |  |  | Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021.pdf Settings In Infotainment CenterStack APIM Imp Guide v1.24 Oct 7, 2021.xlsx | [5 empty] | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Tronolone, Ulisses (U.F.) <utronolo@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1039 | F003257 |  |  |  | Trailer Profiles and Settings |  | EESE |  |  | Trailer Settings SPSS v1.5 Sep 17, 2021.pdf Trailer Settings APIM Imp Guide v1.5 Sep 17, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Rodriguez-flores, Raul (R.) <rrodr368@ford.com> | DCV Beta |  |  | Y | NEW |  |  | Rodriguez-flores, Raul (R.) |  | DCV Beta |  | Y | Minor | Details in JIRA https://www.jira.ford.com/browse/FD-90209 |  | Rodriguez-flores, Raul (R.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1041 | F000029 |  |  |  | Electronic Locking Differential (eLD / eLocker) | Display elocker Oil Temperature Display eLocker selection Feedback eLocker Soft button | EESE |  |  | Off-Road Controls APIM SPSS v1.1 Oct 2, 2020.pdf Off-Road Controls APIM Imp Guide v1.1 Oct 2, 2020.xlsx Off-Road Status IOD APIM SPSS v1.0 Aug 23, 2019.pdf Off-Road Status IOD APIM Imp Guide v1.0 Aug 23, 2019.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Kshavarz, Mahmoud (M.) <mkshavar@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1043 | F003411 |  |  |  | Cellular Remote Start / Stop | Setting menu for Remote SS CCS setting for Vehicle Connectivity,Data enable | ECDX |  |  | Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021.pdf Settings In Infotainment CenterStack APIM Imp Guide v1.24 Oct 7, 2021.xlsx | SW_Tier1 | 10% | 60% | 0% | 30% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  |  | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1044 | F003412 |  |  |  | Cellular Remote Door Lock/Unlock | CCS setting for Vehicle Connectivity,Data enable | ECDX |  |  | Cellular Remote Door Lock & Unlock Feature Document v1.1.pdf | SW_Tier1 | 10% | 80% | 0% | 10% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  |  | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z1045 | F005111 |  |  |  | 2-Speed 4WD | Cluster feature no impact in IVI domain | EESE | [8 empty] | N | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | N | N | N | N |  | - |  |  | N | N | N | [5 empty] | N | N | N
SYNC+_Z1026 | F004550 |  |  | Oil Minder / Level | Oil Minder | IVI need implement soft button 'Input is vehicle driving data and interacting with HMI to reset vehicle oil minder. Output oil life percentage display and recommendation for an oil change. | EESE |  |  |  | Core_Service_Supplier | 20% | 0% | 0% | 80% | Y | N |  |  |  | N | [7 empty] | Y | New |  | Pang, Larry PPANG5@ford.com |  | DCV Beta |  |  | N | [6 empty] | N | [6 empty] | N | N | N | N | N | - |  |  | Y | Minor | carryover U553/554 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | McCliment, Greg (G.A.) |  | DCV Beta |  | Y | Minor | carryover U553/554 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | McCliment, Greg (G.A.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1042 | F005110 |  |  |  | Performance Shift Indicator | This feature allows the driver to select a "Shift Point" and "Shift Tone". When enabled, the cluster will provide different graphics display (like the LEDs in F1 steering wheel) to help the driver to shift on selected "Shift Point". | EESE |  |  | Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021.pdf Settings In Infotainment CenterStack APIM Imp Guide v1.24 Oct 7, 2021.xlsx | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | [7 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | Y | New |  |  | Reis, Deovandro (D.) <dreis7@ford.com> | DCV Beta |  |  | N | N | N |  |  |  | - |  | N | N | N |  |  |  | - |  |  |  |  | -
SYNC+_Z0213 | F000400 |  |  |  | Remote start (activate, climate, auto, last setting, seats and wheels, duration) | [5 empty] | Core_Service_Supplier |  |  |  |  | Y | Y | DCV1 | 2021-12-15 | 2021-12-29 | N | N | [36 empty] | Y | C/O | carryover 707 |  | Reis, Leonardo (L.) |  | DCV Beta |  | Y | Minor | carryover 2024 P702 MCA New HMI layout and UE for 11.1'+23.6*2' Display |  | Reis, Leonardo (L.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z0232 |  |  |  |  | 4# Help Me Avoid Collisions 避免碰撞辅助 - 十字路口碰撞预警 Intersection Assist | [5 empty] | Core_Service_Supplier | 10% | 0% | 0% | 90% |  | N |  |  |  | N | N | [6 empty] | N | N | [28 empty] | N | N | N
SYNC+_Z0277 |  |  |  |  | 4# Help Me Avoid Collisions 避免碰撞辅助_COLLISION MITIGATION SYS(FBFAB) | [5 empty] | Core_Service_Supplier | 10% | 0% | 0% | 90% |  |  | DCV1 | 2021-12-15 | 2021-12-29 | N | N | [6 empty] | N | N | [28 empty] | N | N | N
SYNC+_Z0278 |  |  |  |  | 2# Help Me Drive 驾驶辅助_车距提示 DADI(Distance Alert, Distance Indicator) | [5 empty] | Core_Service_Supplier | 10% | 0% | 0% | 90% |  | N |  |  |  | N | N | [6 empty] | N | N | [28 empty] | Y | NEW |  |  |  |  | DCV Beta
SYNC+_Z1051 | F004151 |  |  |  | 3-Way Splitgate | IVI need implement soft button |  |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N | N | [5 empty] | N | N | N | [5 empty] | N | N | N |  |  |  |  | N | N | N |  |  |  |  | N | N | N | [5 empty] | Y | NEW |  |  | Bono, Amanda (A.) |  | DCV Beta |  | Y | NEW |  |  | Bono, Amanda (A.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1049 | F002992 |  |  |  | Auto Tow / Haul | [5 empty] | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N | N | [5 empty] | N | N | N | [5 empty] | N | N | N |  |  |  |  | N | N | N |  |  |  |  | N | N | N | [5 empty] | Y | NEW |  |  | Busale, Gaston (G. B.) |  | DCV Beta |  | Y | NEW |  |  | Busale, Gaston (G. B.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1050 | F003870 |  |  |  | Trailer Lights and Charging | This is a IPC feature,no impact in IVI |  |  |  |  | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N | N | [5 empty] | N | N | N | [5 empty] | N | N | N |  |  |  |  | N | N | N |  |  |  |  | N | N | N | N | N | N | N | N | N | N |  |  | Amanaganti, Srinath (S.) |  | DCV Beta |  | Y | NEW |  |  | Amanaganti, Srinath (S.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1052 | F000147 |  |  |  | Power Adjustable Mirrors | [5 empty] | SW_Tier 1 | 10% | 90% | 0% | 0% | Y | N |  |  |  | N | N | [6 empty] | N | [7 empty] | N | N | N |  |  |  |  | N | N | N |  |  |  |  | N | [7 empty] | Y | C/O | carryover 707 |  | Strzelczyk, Anthony (A.) |  | DCV Beta |  | Y | C/O | carryover 747 |  | Strzelczyk, Anthony (A.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1053 | F001031 |  |  |  | Sign Based Light Mode | [5 empty] | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N | N | [27 empty] | N | N | N | [5 empty] | N | N | N |  | Petrosino, Dominick (D.) |  | DCV Beta |  | Y | NEW |  |  | Petrosino, Dominick (D.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z0103 | F000166 |  |  |  | Power Running Boards | [5 empty] | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | N | N | N | [5 empty] | N | N | N | [5 empty] | N | N | N |  |  |  |  | N | N | N |  |  |  |  | Y | NEW | [6 empty] | Y | C/O | carryover 707 |  | Vargas, Angel Eduardo (A.) |  | DCV Beta |  | Y | NEW |  |  | Vargas, Angel Eduardo (A.) |  | DCV Beta |  |  |  |  | DCV Beta
SYNC+_Z1046 | F000816 |  |  |  | Programmable Electric Preconditioning and Charging (PEPC) | Setting Menu for Charing |  |  |  | Ev Charge Programming APIM SPSS v1.7 Aug 20, 2019.pdf | Core_Service_Supplier | 10% | 0% | 0% | 90% | Y | N |  |  |  | Y | NEW | [6 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | N | [7 empty] | N | N | N |  |  |  | - |  | N | [5 empty] | - |  |  |  |  | -
SYNC+_Z1047 | F000149 |  |  |  | Mirror Dip / Tilt | Enable/Disable soft switch is in menu for the SYNC screen if drivers do not want their mirrors to dip. Detail refer Chapter '3.3.15.1.2 VS-SR-REQ-234361/D-Reverse Tilt Mirrors' in 'Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf' |  |  |  | Settings In Infotainment CenterStack SPSS v1.22 Apr 23, 2021.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM Imp Guide v1.22 Apr 23, 2021.xlsx | [6 empty] | N |  |  |  | Y | NEW | [6 empty] | N | [7 empty] | N | [6 empty] | N | [6 empty] | N | [7 empty] | N | N | N |  |  |  | - |  | N | [5 empty] | - |  |  |  |  | -
SYNC+_Z1048 | F000136 |  |  | Power moonroof and shade | Power moonroof and shade | [10 empty] | Y | N | [11 empty] | Y-1st | New | Add Power moonroof and shade |  | A R, Kashyap (.) <akashya2@ford.com> | DCV beta | [24 empty] | N | N | N
SYNC+_Z1054 | F004690 |  | ZZ# Foundemental Function 基础功能 | Vehicle Control 车辆控制 | Steering Column / Pedal Position Control | The adjustment function is integrated into steering horizon control |  |  |  |  | SW_Tier 1 | 10% | 70% | 0% | 20% | Y | N | N | N | N | N | [37 empty] | Y | NEW | add function safety requirement
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline is CDX707
Note on AS1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline is CDX707
Note on AQ2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI UI release date from 12.15 delay to 1.28.2022
Note on AR2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: based on UE sign off 3/7, UI sign off 3/15
Note on AX2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI sign off UI from 1215 delay to 1.28.2022
Note on BN3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on AQ4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI sign off UI from 1.10 delay to 2.15
Note on AR4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: based on UE sign off 3/7, UI sign off 3/15
Note on AX4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HMI sign off UI from 1.10 delay to 2.15
Note on BN5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on BN7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on BN12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feature Name is Clear Exit
Note on BN30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on F46: Huang, Feng (F.): Will Xie 回复707项目只有MINI ICP, 无该功能
Note on AX48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change 'N/A' to 'Group A'
Note on AY48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change 'NA' to 'DCV Beta'
Note on AX51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change 'N/A' to 'Group A'
Note on AY51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change 'NA' to 'DCV Beta'
Note on BN61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sig off 4/21
Note on BN62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sig off 4/21
Note on BN70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off before 4/30
Note on F100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BOF没有这条，只有ADA1.5 （Lane Biasing）
Note on BN115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sig off 4/21
Note on AX119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change 'N/A' to 'Group A'
Note on AY119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change 'NA' to 'DCV Beta'
Note on BN125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sig off 4/21
Note on AX129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change 'N/A' to 'Group A'
Note on AY129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change 'NA' to 'DCV Beta'
Note on BN130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UI sign off 4/30
Note on V142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This feature alaready included by VHA in CDX747 project
Note on AA147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: R&R should further study between inhouse & YFVE.
Note on AA148: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need FO support clarify the requirement.
Note on AA152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need FO support clarify the requirement.
Note on BE168: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 有动画的话开发需要延期？需要确认

## Summary
Sheet name | 10/30/2021 Total Feature Nubs | 11/06/2021 Total Feature Nubs | 11/09/2021 Total Feature Nubs
Update Comments | First Summary | 01Customer Facing Removed 2 feature ID to 03BOF 03BOF new added 18 feature IDs for P 702 MCA
01Customer Facing | 130 | 128 | 131
02 Basic Function | 79 | 79 | 79
03 BOF | 161 | 181 | 177