## Feature QA list
CDX747 Feature Issue List @0915
New Feature ID | VSEM ID | Feature_Name | Lead Team | Local Feature Owner | Global Feature Owner | CDX707 | CDX747 | issue requester | Assignee(Read SPEC and Support Issue Clarification) | Issue description | Create date | Priority | Issue status | Due data | SW release version | Remark
SYNC+_0228 | F003519 | My Seat Space | EESE |  | Cintron, Austin (A.) |  |  | YF-Lu Peng | Li, Qiyang | <0914>: '1. 'My Seat Space includes In Car Communication --> Is In Car Communication performed in Phoenix Audio Controller? Diven: yes 2. 'BLE control and BLE audio for Phoenix Domain Controller and Phoenix Audio Controller --> Do all the BLE audio go into Phoenix Audio Controller? And the Phoenix Domain Controller just need to handle the BLE controls? Diven: IVI just handle BLE control (cellphone send BLE control to IVI, IVI translate BLE control to CAN bus). No additional BT audio for IVI module. 3. 'My Seat Space can support two phone calls at the same time --> Phoenix Domain Controller can't support two phone calls at the same time. Do you have any design for two phones calls? Diven: My Seat Space does not add more BT phone call audio requirement to IVI. The addtional BT phone call of MSS is handled in external modules (PAC/Amplifier) 4. 'System allows for per zone personalized audio experiences --> If zones are personalized, do zones plays music from each phone's audio? Diven: Yes, each zone can play different content, like BT audio, radio, etc. Detail need to refer to A2B SPSS. Or URC controls the SYNC to produce different audio to each zone? Diven: the zonal music will come from different sources. IVI provides some of the sources, like radio, online/offline music, BT audio for phones connected to IVI. The PAC will also be the audio source, to provide BT music for phones connected to PAC. URC use APP on cellphone as HMI for control MMS functions like audio source selection for the zones. 5. 'My Seat Space allows users to share audio to other zones --> For media sharing, does that mean phone BLE audio streaming is shared to other zones through SYNC? For MSS, the additional Bluetooth Audio are shared directly from PAC (with BT chipset) to the zone speaker. Only one Bluetooth audio stream are shared from IVI(SYNC), which use the existing BT audio channel on A2B bus. <0915>: vendors need check with FO directly | 17/9/2021 | Gating | Closed | 17/9/2021
SYNC+_Z0255 | F003110 | Rear Seat Controls Lockout: - Window - Door - Audio - Climate | EESE | TBD | Ganna, Spurthi Varma (S.) | N | New | TS-Zhu Jiang | Pasha, Aamir (A.) | <0914> No Local FO, No spec. feature not clear, need cascade <0915> vendors need contacnt FO detail QA <0918> qiyang: according current spec make quote, if spec have big change later need re-quote in the future qyang will release all spec this afternoon ~9.18 @qiyang <0922> yipeng already send to related FO, but no respond | 17/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z0291 | F001010/B | Rear Fog Lights (CDX746/7) | EESE |  | Weiler, Jonathan (J.P.) | N | New | TS-Zhu Jiang | Pasha, Aamir (A.) | 2021/9/14 No Local FO, No spec. feature not clear, need cascade <0915> NO SPSS need check 9/16/2021:Qiyang We could not find the detailed impacts to APIM by current feature spec, feature spec released date is 2019, so current spec could not cover modified impacts to APIM about reductive switch design. Pls help push FO to share the latest spec. 9/16/2021:Aamir I’ll need to start a new discussion on this. Recently had a new FO assigned to these features. SPSS team still waiting on requirements from FO. FDL team needs to do a deep dive on Reductive exterior lighting. 9/16/2021:Qiyang could you give the target date for the spec? <0918> qiyang: no CDX747 feature spec, only have a description that IVI have software button, can't support RFQ, need Aamir confirm | 17/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z1013 | F000864 | Power Release/Cinch Doors | EESE |  | Weiler, Jonathan (J.P.) | N | New | TS-Zhu Jiang | Pasha, Aamir (A.) | 2021/9/14 No Local FO, No spec. feature not clear, need cascade <0915> NO SPEC 9/16/2021Qiyang: rough spec is not enough for us to quote, pls push FO to share more; <0918> can't see IVI impact in feature spec, can't support RFQ, need Aamir confirm | 17/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z1016 | F000818 | Plug In Charging (PIC) | EPE |  | Barkah, David (D.) | N | New | TS-Zhu Jiang | Roy Xu | 2021/9/14 No FO, No spec. feature not clear, need cascade <0915> NO SPEC, need ECDX check local FO <0918> Ivan: FO not Ivan, need check with EPE side Ivan will provide FNA FO name list, Roy will email contact them @Roy xu alk to DR Zeng Yuan for the EV ECUs (BECM, BCCM etc) Ryan Hunt for the EV accessory ECUs El-housseiny, Ghassan (G.) <gelhouss@ford.com> for BCM Contact the sync team for APIM/IPC <0922> Roy: spec already sent by email, is it support quote? @Zhujiang | 17/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z1017 | F005350 | EV Charge Programming | ECDX |  |  | N | New | TS-Zhu Jiang | Li, Daisy (Y.P.) | 2021/9/14 No FO, No spec. feature not clear, need cascade <0915> NO SPEC, need ECDX check local FO <0918> Ivan: next spec 10.22 will release TS: quota assesment based phase4 UE/spec | 17/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_Z1018 | F005310 | Buttonless Push To Start – BEV |  |  | Cristiano, Wander (W. R.) | N | New | TS-Zhu Jiang | Pasha, Aamir (A.) | 2021/9/14 No FO, No spec. feature not clear, need cascade <0915> FO: this item will not as feature, will be deleted, need Aamir confirm again 9/16/2021:Aamir has this new feature for CDX747, just impact to cluster; 9/16/2021:Qiyang pls push FO to share spec 9/16/2021: Aamir FO cascaded specs to Eureka Li in VSEM CPKG-007965. Please reassign task to Eureka (column J) <0918> need clarifyied by cluster | 17/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_Z1019 | F003410 | Cellular Remote Start w/Extend Remote Start FNV3 | ECDX | Lin, Shawn (X.) | Syed, Imtiaz (I.S.) | N | New | TS-Zhu Jiang | Lin, Shawn (X.) | 2021/9/14 No FO, No spec. feature not clear, need cascadec <0915>need Daisy confirm whether local FO is Lin, Shawn (X.) and FO need cotact with vendors to clarify QA <0918> Shawn: C/O CDX707 --> FIP need update @xiaojin@James --> clarified <0916> Daisy: FO Shawn Lin had clarified with Supplier. | 17/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_Z1020 | F003411 | Cellular Scheduled Remote Start | ECDX | Lin, Shawn (X.) | Syed, Imtiaz (I.S.) | N | New | TS-Zhu Jiang | Lin, Shawn (X.) | 2021/9/14 No FO, No spec. feature not clear, need cascade <0915>need Daisy confirm whether local FO is Lin, Shawn (X.) and FO need cotact with vendors to clarify QA <0918> Shawn: delete this feature | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_Z0285 | F001212/A | Driver Focused Mode | EESE |  | Wijaya, Halim (H.) | N | New | TS-Zhu Jiang | Chen, James (J.) | <0914> 功能名称： Driver Focused Mode 问题描述： 4.2.2 章节中描述了DFM功能关闭时需要恢复乘客之前的设定值（passenger setpoint display），那这些设置项在DFM模式开启前的状态是否由CoreService层去记录？ 4.2.2 章节中描述了DFM功能的前置条件 （Outside Air Temperature ≥ HMI_ DfmAmbientActivation ），关于这个车外温度是通过传感器获取还是通过网络获取？ 4.2.2 章节中关于截图的需求描述，该功能是否是ECU自身实现？ <0915> FO need check and reply @James | 14/9/2021 | Gating | Open | 24/9/2021 |  | Develop
SYNC+_Z0296 | F002214/A | Passenger Airbag Disable Indicate Telltale |  |  | Dsouza, Aston (.) | N | New | TS-Zhu Jiang | Li, Qiyang | <0914> 功能名称： Passenger Airbag Disable Indicate Telltale 问题描述： No spec No Local FO <0915> there is spec in GitHub, please clarify detail QA | 14/9/2021 | Gating | Open | 24/9/2021 |  | Develop
SYNC+_Z0235 | F004130 | Rear Seat Occupant Alert | SE-->EESE |  | Nunes, Liandro (L. F.) | N | New | TS-Zhu Jiang | Pasha, Aamir (A.) | <0914> 功能名称： Rear Seat Occupant Alert 问题描述： 后排乘客警告。主要用户后排门打开或者关闭时，进行的警报，同时在熄火或者点火的时候，有后排乘客对主驾的提示。那么是否只是需要添加系统设置对该警告进行配置。 文档中的PPT里有相关设置项和warning界面，我们要负责的是否就是PPT呈现的内容 <0915> qiyang side delete -> need confirm why delete 9/16/2021Qiyang Currently, APIM_CIM is not contained in the component list for this feature in the jira system, so we will not quote for this feature, if it’s going to be implemented on the CDX747 in the future, it should be go through DCR process, Pls aware. 9/16/2021:Aamir Agreed, per FO this feature is not compatible with APIM_CIM at this time. Issue Resolved. | 14/9/2021 | Gating | Closed | 24/9/2021 |  | Develop
SYNC+_Z0244 | F001009 | Hazard Light | EESE |  |  | N | New | TS-Zhu Jiang | IPC | <0914> 功能名称： Hazard Light 问题描述： 1.No FO NO Spec; <0915> need confirm IPC FO, vendors need handshake with ICP FO direclty | 14/9/2021 | Gating | Open | 24/9/2021 |  | Develop
SYNC+_Z0250 | F003170 | PDLC SkyLite Digital Shade | SE-->EESE |  | Vandenbrink, Terry (T.) | N | New | TS-Zhu Jiang | Li, Xuedong | <0914> 功能名称： PDLC SkyLite Digital Shade 问题描述： No spec No Local FO <0915> there is spec in GitHub, please clarify detail QA | 14/9/2021 | Gating | Open | 24/9/2021 |  | Develop
SYNC+_Z0253 | F003090 | Cabin & Battery Overheat Management | SE-->EESE |  | Collins, Lynn (L.) | N | New | TS-Zhu Jiang | Li, Qiyang | <0914> 功能名称： Cabin & Battery Overheat Management 问题描述： 无法理解功能需求到底是什么，需要FO澄清 <0915> vendors need handshake with FO directly and list QA | 14/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z0257 | F001012/B | Parking Light (North America) Position Light (EU & China) (RSD - Headlamp switch - Park Lamps) – Includes license plate | EESE |  |  | N | New | TS-Zhu Jiang | Pasha, Aamir (A.) | <0914> Function name： Parking Light (North America) Position Light (EU & China) (RSD - Headlamp switch - Park Lamps) – Includes license plate Issue description： No FO No Spec; <0915> no spec 9/16/2021:Qiyang We could not find the detailed impacts to APIM by current feature spec, feature spec released date is 2019, so current spec could not cover modified impacts to APIM about reductive switch design. Pls help push FO to share the latest spec. 9/16/2021:Aamir I’ll need to start a new discussion on this. Recently had a new FO assigned to these features. SPSS team still waiting on requirements from FO. FDL team needs to do a deep dive on Reductive exterior lighting. 9/16/2021:Qiyang could you give the target date for the spec? | 14/9/2021 | IG | Open | 24/9/2021 |  | Develop
SYNC+_Z0258 | F000998 | Low Beam Switch | EESE |  |  | N | New | TS-Zhu Jiang | Pasha, Aamir (A.) | <0914> Function name： Low Beam Switch Issue description： No FO No Spec; <0915> no spec 9/16/2021:Qiyang We could not find the detailed impacts to APIM by current feature spec, feature spec released date is 2019, so current spec could not cover modified impacts to APIM about reductive switch design. Pls help push FO to share the latest spec. 9/16/2021:Aamir I’ll need to start a new discussion on this. Recently had a new FO assigned to these features. SPSS team still waiting on requirements from FO. FDL team needs to do a deep dive on Reductive exterior lighting. 9/16/2021:Qiyang could you give the target date for the spec? | 14/9/2021 | IG | Open | 24/9/2021 |  | Develop
SYNC+_Z0259 | F000058/C | Map/Dome Lights (RSD - Manual Interior Lighting) | EESE |  | Santana, Gabriel (G.D.) | N | New | TS-Zhu Jiang | Li, Xuedong | <0914> 功能名称： Map/Dome Lights (RSD - Manual Interior Lighting) 问题描述： No FO No Spec; <0915> there is spec in GitHub, please list detail QA | 14/9/2021 | Gating | Open | 24/9/2021 |  | Develop
SYNC+_Z0288 | F000178/D | Perimeter Anti-Theft Alarm | EESE |  | Talaga, Joshua (J.) | N | New | TS-Zhu Jiang | Pasha, Aamir (A.) | <0914> 功能名称： Perimeter_Anti-Theft_Alarm 问题描述： Spec 文档中未找到关于 “Perimeter_Anti-Theft_Alarm”相关的功能描述。 <0915> no spec 9/16/2021:Qiyang As for china market no CSM will be offered, so this feature has no impact to APIM_CIM told by feature owner @Koessler, Sebastian (S.), so pls help to double confirm with FO and remove APIM_CIM from the component list in jira system. 9/16/2021:Aamir Per PDL CSM is available in China. Need alignment with China PMT 5. 9/16/2021:Qiyang pls push FO to align with china PMT5. 9/16/2021: Aamir Response from FO, In case vehicle is equipped with a CSM there need to be an Alarm menu integrated to the APIM to allow to disable the CSM (Set Motion Sensors to OFF) for one arming cycle as well a selectable prompt that will be displayed everytime the ignition is turned off, which allows the customer to set Motion Sensors to OFF. But this should be nothing new for the APIM. @Qiyang - is Frank Yang PMT 5 China lead? 9/22/2021:Frank sent CSM D&R name to Aamir and FO; | 14/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_0196 |  | 电车实时车况界面 IOD Information On Demand/Display | EESE | Yu, Diven (D.W.) <dyu12@ford.com> |  | N | New | YF-Lu Peng | Li, Xuedong，cluter | <0914> Missing Spec. <0915> follow CDX707 | 14/9/2021 | Low | Closed |  |  | Quote
SYNC+_0115 | F003071 | 座舱内手机遥控 Project Aspire_Ultimate Remote Control | ECDX | Shawn, Lin, | Reed, Gregory (G.D.) | N | New | YF-Lu Peng | Iris, Zhu, Daisy.Li | <0914> Missing Spec, What do YF need to do？ <0915> need confirm this item need dropped or not @ Iris.Zhu <0918> Daisy: URC still under scoping, confirm with Roy that this feature need included, but need confirm who is the development leader All vendors need check spec and have clarification meeting by 9.22 if necessary ~9.22 @Li, Daisy (Y.P.) @Xu, Roy (C) @YFVE @TS @Baidu <0922>YF: Assume included in My seat space. URC is phone control for My seat space. 需要跟PO和APP确认IVI上的影响。 | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_0208 | F001065 | BEV Unique Charging | ECDX | Peng, Ivan (F.) <FPENG6@ford.com> | Rela, Pedro (P.R.) | N | New | YF-Lu Peng | Peng. Ivan | <0914> Missing Spec, What do YF need to do？ <0915> YF need handshake with local FO clarify detail QA <0918> Baidu: follow CDX717 strategy Ivan: need re-classify EV charging category and confirm Charging programing contains, BEV charge contains? And align with EESE/Baidu @Peng, Ivan (F.) EESE: xiaojin/James need double check FIP, if not exist will delete @Xiao Jin Xia@Chen, James (J.) <0922> Ivan had clarified and shared spec. to YF. | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_0215 |  | 剩余里程显示Range Ring-Nav Screen (DTE) | EPE | Wu, Dean (D.) <dwu44@ford.com> |  | N | New | YF-Lu Peng | delete | <0914> Missing Spec, What do YF need to do？ <0915> not in cascade list and no related FO handshake with IVI team | 14/9/2021 | Low | Closed |  |  | Quote
SYNC+_0229 |  | Video Interface Throughout Cabin (Rear Seat Monitor, w/ expanded request: allow 2R see 1R) |  | Chen Eva xchen87@ford.com |  | N | New | YF-Lu Peng | Li, Daisy (Y.P.) | <0914> Missing Spec, What do YF need to do？ <0915> not include in 1EC, on hold --> future OTA | 14/9/2021 | Low | Closed |  |  | Quote
s | F002812 | Mobile Device Viewer | ECDX | Regina. Gu | Moreno Bautista, Ariana (A.) | N | New | YF-Lu Peng | Regina. Gu | <0914> Missing Spec, What do YF need to do？ <0915> Aamir: spec will included into CCS spec by 9.30 also need Daisy.Li check new CCS spec (0930 version) delta change items @Daisy.Li CCS FO Regina GU <0923> Daisy: MDV will boundle with Sentinel. Iris to follow up with Global FO to get spec. and necessary documents to support RFQ quotation. 初步评估： TS: 告警触发，视频存储功能 YF: 摄像头驱动调通n. | 14/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_0232 |  | Night Vision |  |  |  | N | New | YF-Lu Peng | Yu, Diven (D.W.) | <0914> Missing Spec, What do YF need to do？ <0915> already included into AR feature (SYNC+1021, VSEM: F003774) in CDX747, delete this item also Daisy need further check @Daisy.Li <0923> Daisy: it's different between AR and night vision, need clarify with vendors detail spec @Diven | 14/9/2021 | IG | Open |  |  | Quote
SYNC+_0236 | F000812 | Cloud Based Battery Management System | ECDX | Yang, Jessica (Yu.) <yyang158@ford.com> |  | N | New | YF-Lu Peng | Li, Daisy (Y.P.) | <0914> Missing Spec, What do YF need to do？ <0915> already deleted in JIRA cascade, later will update in FIP | 14/9/2021 | Low | Closed |  |  | Quote
SYNC+_0264 | F003951 | EM(Electro-Mechanical) Register | BI | Wang, Wei (W.) <wwang199@ford.com> | Vandenbrink, Terry (T.) | Y-1st | New | YF-Lu Peng | Li. Qiyang | <0914> Missing Spec. currently no FO in charge of CDX747 <0915> already have SPSS in JIRA, will send later, vendor need handshake with FO directly @Zhengwei <0918> qiyang will check difference between CDX707 and CDX747 with FO <0922> Aamir: Terry Vandenbrink will be new FO, qiyang need contact | 14/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z0251 | F002870 | Stowable Steering Column w/ Deploying Tray | SE-->EESE |  | Lau, Tok (T. W.) | N | New | YF-Lu Peng | Li, Xuedong | <0914> Without division of Development, What do YF need to do？ <0915> vendors should handshake with FO and list QA list <0918> YFVE: 需确认是否YFVE仅做信号透传，上层APP由iinhouse做？@TS @Xuedong Xuedong: YFVE只需要做信号透传，TS做APP开发，但是需要确认开发所需信号 ~9.22@yipeng@xuedong <0922> Zhang Yipeng: no spec yet qiyang: latest spec already upload to GitHub <0923> Zhang yi peng: current spec can support quote and already reply signal number, need YFVE check @Lupeng | 14/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z0286 | F004530/A | Drive Control Optimization | SE-->EESE |  |  | N | New | YF-Lu Peng | Pasha, Aamir (A.) | <0914> Missing Spec. should delete this feature <0915> need Aamir confirm with FO whether this feature need delete or not 9/16/21: Please delete | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_Z0290 | F004711 | Steering Horizon Control | SE-->EESE | Zhu, Jing Yuan (J.) <JZHU65@ford.com> | Li, Richard (R.Y.) | Y | Minor | YF-Lu Peng | Chen, James (J.) | <0914> Where is the change point? <0915> add all vehicle related control function --> handshake with James Chen <0918> James: 对比CDX707, CDX747需增加后视镜,转向柱, 踏板控制的software button控制，其他部分C/O CDX707 | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_Z0291 | F001010/B | Rear Fog Lights | EESE |  | D'Agostino, Antonio (A.) | N | New | YF-Lu Peng | Pasha, Aamir (A.) | <0914> Missing Spec. ICP features 2021/9/14 No Local FO, No spec. feature not clear, need cascade <0915> NO SPSS need check duplicated with colum 5 | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_Z1012 | F002430 | Plug and Charge | ECDX | Wang, Yixuan (Vovo) <ywang219@ford.com> | Jujavarapu, Sandeep (S.) | N | New | YF-Lu Peng | Li, Daisy (Y.P.) | <0914> Missing Spec. <0915> Ford Vendors need check with FO directy <0918> Ivan: this is Adward side feature, need contact Vovo ask for spec, Roy need help push @Roy @Vovo <0922> Daisy: c/o CX727, only Cloud and App development, no function on IVI. | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_Z0292 | F003517 | Second Row Seat Position Control |  |  | Aguilar, Diana (D.S.) | TBD | New | YF-Lu Peng | Chen, James (J.) | <0914> Missing Spec. <0915> need check with FO direcly and clarify <0918> need check detail control signals and remark @James <0922> James: already sent related signal and spec, is it support quote? @LuPeng | 14/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z0296 | F002214/A | Passenger Airbag Disable Indicate Telltale |  |  |  | N | New | YF-Lu Peng | Li, Qiyang | <0914> Missing Spec. <0915> there is spec in GitHub, please clarify detail QA <0918> IVI just support indicator, no software button, not impact quota , qiyang will write down feature related signals @qiyang | 14/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_0272 |  | Lidget/Fidget/Widget 2.0 |  | Shawn. Lin |  | Y-first | Y | YF-Lu Peng | Calvin Zhou | <0914> Missing Spec, Without division of Development and description of the change point. <0915> vendor need handshake with Shawm.Lin/Daisy.Li directly and share detail QA <0918> push FO share spec to vendors and development job division confirm @Daisy.Li <0922> Daisy: YF: 需要实现集成 Agile process | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_0273 |  | Remote Window Control / Window Status (China) |  | Shawn. Lin |  | Y | Y | YF-Lu Peng | Li, Daisy (Y.P.) | <0914> Missing Spec, Without division of Development and description of the change point. <0915> vendor need handshake with Shawm.Lin/Daisy.Li directly and share detail QA <0918> Daisy: this feature is on hold, this time RFQ drop | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_0279 |  | Digital Embrace 2.0 |  | Johnny Wang |  | Y | Y | YF-Lu Peng | Li, Daisy (Y.P.) | <0914> Missing Spec, Without division of Development and description of the change point. <0915> vendor need handshake with Daisy.Li directly and share detail QA <0918> push Jonny Wang share feature spec and confirm with FO vendors' development job devision @Daisy.Li <0922> Daisy: YF: 实现开关机动画做替换，路径切换。 TS: Digital embrace app 开发，实现跟中国cloud 云端CMS平台推送开关机动画 IVI PDL/FIP Shall be changed to Digital Embrace 1.0 <0923> Daisy: spec already provided | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_0281 |  | Smart Wellness 1.0 |  | Calvin Zhou |  | Y | Y | YF-Lu Peng | Li, Daisy (Y.P.) | <0914> Missing Spec, Without division of Development and description of the change point. <0915> vendor need handshake with Daisy.Li directly and share detail QA <0918> push Jonny Wang share feature spec and confirm with FO vendors' development job devision @Calvin Zhou <0922> Daisy: YF: 需要实现集成 Agile process | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
SYNC+_0283 |  | FNOC 1.0 |  |  |  | Y | Y | YF-Lu Peng | N/A | <0914> Missing Spec, Without division of Development and description of the change point. <0915> This feature has been deleted | 14/9/2021 | Low | Closed |  |  | Quote
SYNC+_0284 |  | FNOS |  |  |  | Y | Y | YF-Lu Peng | N/A | <0914> Missing Spec, Without division of Development and description of the change point. <0915> This feature has been deleted | 14/9/2021 | Low | Closed |  |  | Quote
| F003074 F000121 | Heated Wiper Blade Heated Windshield |  |  | Lima, Dorivaldo (.) | N | New | YF-Lu Peng | Li, Qiyang | <0914> Missing Spec. <0915> there is spec in GitHub, please check spec | 14/9/2021 | Low | Closed |  |  | Quote
| F000864 | Power Release/Cinch Doors |  |  | Weiler, Jonathan (J.P.) | N | New | YF-Lu Peng | Pasha, Aamir (A.) | <0914> Missing Spec, Without division of Developmen. What do YF need to do？ <0915> NO SPEC duplicated issue with colume 5 | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
| F000818 | Plug In Charging (PIC) | EPE? |  |  | N | New | YF-Lu Peng | Roy.Xu | <0914> Missing Spec. <0915> NO SPEC, need ECDX check local FO <0918> YFVE: need list related signal, Roy will help to push related FO handshake @Roy@EPE <0922> Roy: already sent related spec, YFVE need check whether support quote? @Lupeng | 14/9/2021 | IG | Open | 17/9/2021 |  | Quote
| F005350 | EV Charge Programming | ECDX |  |  | N | New | YF-Lu Peng | Ivan Peng | <0914> Missing Spec. <0915> NO SPEC, need ECDX check local FO <0918> YFVE: need list related signal, Ivan will help to check, need NA assesment ~22@Ivan Daisy: <0918> Ivan: next spec 10.22 will release TS: quota assesment based phase4 UE/spec | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
| F005310 | Buttonless Push To Start – BEV |  |  |  | N | New | YF-Lu Peng | Pasha, Aamir (A.) | <0914> Missing Spec. <0915> FO: this item will not as feature, will delete, need Aamir confirm again duplicated issue with colume 8 <0918> need clarifyied by cluster | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
| F003410 | Cellular Remote Start w/Extend Remote Start FNV3 |  |  |  | N | New | YF-Lu Peng | Shawn.Lin | <0914> Missing Spec, Without division of Developmen. What do YF need to do？ <0915>need Daisy confirm whether local FO is Lin, Shawn (X.) and FO need cotact with vendors to clarify QA duplicated issue with colume 9 | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
| F003411 | Cellular Scheduled Remote Start |  |  |  | N | New | YF-Lu Peng | Shawn.Lin | <0914> Missing Spec, Without division of Developmen. What do YF need to do？ <0915>need Daisy confirm whether local FO is Lin, Shawn (X.) and FO need cotact with vendors to clarify QA duplicated issue with colume 10 | 14/9/2021 | IG | Closed | 17/9/2021 |  | Quote
| F003774 | Augmented Reality |  |  |  | N | New | YF-Lu Peng | Zhang, Yong (Y.) | <0914> Missing Spec, Without division of Developmen. What do YF need to do？ <0915> vendor need directly handshake with FO and clarify <0918> need further check with zhangyong detail progress | 14/9/2021 | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z0087 |  | Lincoln Seats shortcut key | EESE | Zhou, Weifu (W.) <wzhou43@ford.com> |  | N | C/O | TS-Zhu Jiang | Chen, James (J.) | <0915> 707标注"N"，747标注"C/O" 需要确认该功能是否可以Carry Over 707 <0915> delete this item, later wil update FIP also Lisa neec confirm 747 CL&U, A65 is same with 707 @ Lisa.Gao | 15/9/2021 | Low | Closed |  |  | Quote
SYNC+_Z0078 |  | Grade Assits | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  | N | C/O | TS-Zhu Jiang | Chen, James (J.) | <0915> 707标注"N"，747标注"C/O" 需要确认该功能是否可以Carry Over 707 <0915> delete this item, later wil update FIP | 15/9/2021 | Low | Closed |  |  | Quote
SYNC+_Z0080 |  | Hill start assist | Chassis | Wang, Peggy (M.N.) <mwang43@ford.com> |  | N | C/O | TS-Zhu Jiang | Chen, James (J.) | <0915> 707标注"N"，747标注"C/O" 需要确认该功能是否可以Carry Over 707 <0915> delete this item, later wil update FIP | 15/9/2021 | Low | Closed |  |  | Quote
SYNC+_Z0200 |  | Air suspension | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | N | C/O | TS-Zhu Jiang | Chen, James (J.) | <0915> 707标注"N"，747标注"C/O" 需要确认该功能是否可以Carry Over 707 <0915> delete this item, later wil update FIP | 15/9/2021 | Low | Closed |  |  | Quote
SYNC+_Z0203 |  | Cargo Loading | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | N | C/O | TS-Zhu Jiang | Chen, James (J.) | <0915> 707标注"N"，747标注"C/O" 需要确认该功能是否可以Carry Over 707 <0915> delete this item, later wil update FIP | 15/9/2021 | Low | Closed |  |  | Quote
SYNC+_Z0205 |  | Easy access height | EESE | Li, Xuedong (X.) <XLI244@ford.com> |  | N | C/O | TS-Zhu Jiang | Chen, James (J.) | <0915> 707标注"N"，747标注"C/O" 需要确认该功能是否可以Carry Over 707 <0915> delete this item, later wil update FIP | 15/9/2021 | Low | Closed |  |  | Quote
SYNC+_0166 | F002032 Rocket Setup - F002470 BLE Autopair - F002491 Autosave - F002830" | 基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP) | EESE | Xu, Andy (X.) <xxu71@ford.com> |  | Y-OTA | C/O | TS-Zhu Jiang | Li, Daisy (Y.P.) | <0915> 707标注"Y-OTA"，747标注"C/O" 需要确认该功能是否可以Carry Over 707 <0915> 747 Yes-minor change, inhouse check whether impact RFQ | 15/9/2021 | Low | Closed |  |  | Quote
SYNC+_0283 |  | FNOC 1.0 |  |  |  | Y | Y | TS-Zhu Jiang | N/A | <0915> 该功能前期澄清结果为删除，目前Fip表里标注还是"Y",需要确认是否删除 | 15/9/2021 | Low | Closed |  |  | Quote
SYNC+_0284 |  | FNOS |  |  |  | Y | Y | TS-Zhu Jiang | N/A | <0915> 该功能前期澄清结果为删除，目前Fip表里标注还是"Y",需要确认是否删除 | 15/9/2021 | Low | Closed |  |  | Quote
SYNC+_Z0262 | F003417 | Integrated Security Camera | EESE |  | Minous Corey or TBD |  | Y | Ford-Huang Xue | Huang, Xue (X.) | 1. Are Interior cameras for sentinel directly connected to SYNC+ ? Cause 747 Boundary Diagram and sentinel IFS are inconsistent 2. How implementing Audio data Recording? Like which audio, Is the audio directly connected to SYNC+…… 3. Could you provide RTSP/CAN/SOA communication protocol and Interface definition? | 15/9/2021 | Gating | Open | 24/9/2021 |  | Develop
| F002054 | Active Drive Assist 1.2 |  |  | Gotadki, Shruti (S. P.) |  |  |  | Pasha, Aamir (A.) | 9/16/2021:Qiyang we don’t receive any feature level spec about this feature, so we could not confirm which setting is for this feature in setting SPSS, to my knowledge, currently our setting SPSS could not cover this feature due to uncompleted feature spec. pls help push FO to share the latest spec. 9/16/2021:Aamir Have you reviewed the feature level specs in VSEM? 9/16/2021:Qiyang feature spec released date is 2020, this is a new feature, feature spec of vesm could not cover this feature, pls push FO to cascade latest spec 9/16/2021: Aamir I've requested FO to clarify what changes are coming for HMI/ IPC spec. DTG 10/22/21. To clarify this is not a new feature. It is currently available on 21MY CX727 <0918> qiyang: no featuer spec support RFQ |  | IG | Open | 17/9/2021 |  | Quote
| F002930 | Remote Park Assist | [6 empty] | Pasha, Aamir (A.) | 9/16/2021:Aamir Latest SPSS is for P702. Cannot confirm if changes are needed for CDX746/7. Feature is still with research and application feature will only assess after application readiness is achieved. Can we use the existing SPSS as a benchmark and go thru DCR process when more details are available? |  | IG | Open | 17/9/2021 |  | Quote
| F000158 | Multi-Contour Seat | [6 empty] | Pasha, Aamir (A.) | 9/16/2021:Aamir Multi Contoured Seats Client V2 SPSS v1.5 currently available. New MCS release to account for the new Massage Off design and the addition of 5 more massage patterns to display, estimated completion of v1.6 is Oct/15/21. |  | IG | Open | 17/9/2021 |  | Quote
| F000810 | Driver Information Display Control (CDX746/7) | [6 empty] | Pasha, Aamir (A.) | 9/22/2021:Aamir ask FO to share all the STSS under this feature to DUEROS;
SYNC+_0209 |  | 充电接口灯设置Charge Port Light Settings | EPE | Wu, Dean (D.) <dwu44@ford.com> |  | N | New | TS-Zhu Jiang | Ivan Peng | <0919> NO SPEC, and need check local FO |  | IG | Open | 17/9/2021 |  | Quote
SYNC+_Z0276 | F002710 | 单踏板驾驶One Pedal Drive | EPE | Wu, Dean (D.) <dwu44@ford.com> |  | N | New | TS-Zhu Jiang | Ivan Peng | <0919> NO SPEC, there is a feature name SYNC+_0217 but deleted,what's the difference and need check local Fo |  | IG | Open | 17/9/2021 | Quote | Quote
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline is CDX707

## Detail SW Maturity
FORD JIRA | [19 empty] | 747 IVI FIP China | [6 empty] | Pre condition & Enablers |  | SW Maturity | [6 empty] | Comment | Local FO for 707
Displaying 97 issues at 12/Sep/21 10:16 PM.
Key | Issue Type | Parent Link | Reporter | Summary | Status | Created | Assignee | Component/s | Source Requirement ID | Target end | Resolution | Executive Summary | Epic Link | Level of Change | Change start date | Lead Vehicle Program | Vehicle Program | Labels | GPDS Milestone | Source Requirement ID | remark | New feature ID | CDX747 | CDX747 release version in GPDS | Release data to REC | Release Date to FO/CAF(2weeks) | Spec Clarification | UI sign off | FDJ DCV Beta INI/DI 2022/01/06 | FDJ DCV Beta1 INI/DI 2022/02/28 | DCV BB DCV0 DI 2022/03/30 | DCV MRD DCV1 DI 2022/04/30 | DCV DCV2 PI 2022/06/14 | DCV DCV3 PI 2022/07/25 | PEC R00 PI 2022/09/15
FSW-8846 | Initiative | FSW-3888Plug in Charging (PIC) | Deddeh, Tony (T.) | Plug In Charging (PIC) (CDX746/7) | Developing | 2021-08-16 12:39 | Barkah, David (D.) | APIM_CDC, APIM_CIM, BCCM, BCM, BECM, EVCM, HPCM | F000818 |  | Unresolved | 1. Boundary Diagram uploaded to VSEM (Yes). 2. Level of Change Analysis form uploaded to Feature Program Sharepoint (Yes). |  | Carryover from another program |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747 | 080-VM-FEC | F000818 |  | SYNC+_Z1016 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | ECDX Lead, no spec need check with FO | 0
FSW-8845 | Initiative | FSW-444EV Charge Programming | Borgaonkar, Pankaj (P.) | EV Charge Programming (CDX746/7) | Developing | 2021-08-16 12:39 | Castrejon, Felipe (F.) | APIM_CDC, APIM_CIM, ECG, HPCM, TCU | F005350 |  | Unresolved | 1. Boundary Diagram uploaded to VSEM (Yes). 2. Level of Change Analysis form uploaded to Feature Program Sharepoint (Yes). |  | Carryover from another program |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747 | 080-VM-FEC | F005350 |  | SYNC+_Z1017 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | ECDX Lead, no spec need check with FO | 0
FSW-8663 | Initiative | FSW-2465Power Release Door | McInally, Steven (M.) | Power Release Doors (CDX747) | Developing | 2021-08-06 11:27 | Dasari, Kovidha (K.R.) | APIM_CDC, APIM_CIM, BCM, DCME, DCMF, DCMG, DCMH, ECG_Gateway, EVCM, RCM | F000864 |  | Unresolved |  |  | Modified |  | 2021 CX727 | 2024 CDX747 | CDX747 | 080-VM-FEC | F000864 |  | SYNC+_Z1013 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | Spec and feature clarification should be lead by AFO COB 09/30 UI sign off version should be released COB 10/30. | 0
FSW-8545 | Initiative | FSW-4753Drive Control Optimization | Sarracini, Fernando (FSJ.) | Buttonless Push To Start – BEV (CDX746/7) | Developing | 2021-07-22 15:40 | Cristiano, Wander (W. R.) | ABS, APIM_CDC, APIM_CIM, BCM, EVCM, GSM, HPCM | F005310 |  | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO, Green | 080-VM-FEC | F005310 |  | SYNC+_Z1018 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | Spec and feature clarification should be lead by AFO COB 09/30 UI sign off version should be released COB 10/30. | 0
FSW-4969 | Initiative | FSW-2412Tuner AM/FM/HD | Tengler, Dave (D.R.) | Tuner AM/FM/HD (CDX746/7) | Developing | 2021-01-28 12:16 | Murry, Tyrone (T.D.) | ACM, APIM_CDC, APIM_CIM, ECG_Gateway, RACM, TCU | VSEM ID: F000349 |  | Unresolved |  |  | Carryover |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000349 |  | SYNC+_0011 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | Confirm if AM del or not COB 09/30. | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com>
FSW-4755 | Initiative | FSW-4754Steering Wheel Horizon Control | Reppenhagen, Nancy (N.B.) | Steering Horizon Control (CDX746/7) | Developing | 2021-01-19 23:03 | Li, Richard (R.Y.) | APIM_CDC, APIM_CIM, ECG_Gateway, SCCM, SIMA | VSEM ID: F004711 |  | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, U717/718 | 080-VM-FEC | F004711 |  | SYNC+_Z0290 | Minor | DCV2 | 2022-05-30 | 2022-06-14 | [6 empty] | DI | DI | PI | Late requirement in CDX707/CDX747 | Zhu, Jing Yuan (J.) <JZHU65@ford.com>
FSW-4752 | Initiative | FSW-4753Drive Control Optimization | Waszczenko, Lisa (L.M.) | Drive Control Optimization (CDX746/7) | Open | 2021-01-19 23:00 | Lin, Hua (H.) | ABS, APIM_CDC, APIM_CIM, BCM, DDM, DSM, EVCM, GSM, HPCM, PDM, SCMC, SCMD, SCMG, SCMH | DCO: F004530/A Buttonless Start: F005310 | 2022-06-30 | Unresolved |  |  | New |  | 2024 CDX747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO |  | DCO: F004530/A Buttonless Start: F005310 |  | DCO: SYNC+_Z0286 BEV: SYNC+_Z1018 | N | DCO: DCV0 BEV: DCV Beta1 | DCO: 3/16/2022 BEV: 2/16/2022 | DCO: 3/30/2022 BEV: - | 2021-09-30 | 2021-10-30 | NA | [6 empty] | can't see in feature, should delete | #N/A
FSW-4476 | Initiative | FSW-657Park Aid | Nasser, Ebrahim (E.) | Base Park Aid (CDX746/7) | Developing | 2021-01-06 22:13 | Al-Zaher, Sarya (S.) | APIM_CDC, APIM_CIM, BCM, EVCM, IPMA (ADAS) | F003631 |  | Unresolved |  |  | Carryover |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003631 |  | SYNC+_0091 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | DI | DI | PI | PI | PI | Suppose C.O CDX707, further confirm with AFO needed. | Li, Xin (X.) <xli268@ford.com>
FSW-4427 | Initiative | FSW-2078Digital Scent | Schneider, Don (D.P.) | Digital Scent (China) (CDX746/7) | Developing | 2020-12-17 14:35 | Malainy, Mark (S.) | APIM_CIM, RCCM | VSEM ID: F004410 |  | Unresolved |  |  | Carryover |  | 2023 CDX707 | 2024 CDX747 | CDX747, China, Green | 080-VM-FEC | F004410 |  | SYNC+_0134 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Chen, Minghui (M.) <MCHEN122@ford.com>
FSW-4426 | Initiative | FSW-1870Auto Air Refresh | Schneider, Don (D.P.) | Auto Air Refresh (AAR) for CHINA Markets (CDX746/7) | Developing | 2020-12-17 14:34 | Hasan, SM Fairus (S.) | APIM_CIM, RACM, RCCM |  |  | Unresolved |  |  | Carryover |  |  | 2024 CDX747 | CDX747, China | 080-VM-FEC |  |  | SYNC+_0132 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Shi, Stella (J.) <jshi32@ford.com>
FSW-4425 | Initiative | FSW-494Fob Free Entry and Ignition (NFC) - F002070 | Trupiano, Rita (M.P.) | Fob Free Entry and Ignition (NFC) (CDX746/7 (GE2)) | Developing | 2020-12-17 14:33 | Sepulveda, Reinaldo (R. R.) | APIM_CDC, APIM_CIM, BCM, RFA | VSEM ID: F002070 |  | Unresolved |  |  | Modified |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO, Green, J1, NFC, UWB | 080-VM-FEC | F002070 |  | SYNC+_Z1010 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-10-30 |  |  | DI | DI | PI | PI | PI | vendors need confirm detail spec with AFO then can confirm IVI HIM/GUI work | 0
FSW-4423 | Initiative | FSW-2603Power Central Lock Suite | Muneratto, Daniel (D.M.) | Power Central Lock Suite (CDX746/7) | Developing | 2020-12-17 14:21 | Silva, Nivea (N.B.) | APIM_CDC, APIM_CIM, BCM, DCME, DCMF, DCMG, DCMH, DDM, PDM, RGTM, TCU | F004255 |  | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO, Yellow | 080-VM-FEC | F004255 | F004256 F002951 F004255 Lock Setting | SYNC+_Z0187 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-4422 | Initiative | FSW-2695Automatic Lock Suite | Muneratto, Daniel (D.M.) | Automatic Lock Suite (CDX746/7) | Developing | 2020-12-17 14:20 | SOUZA, GABRIELLE DESIREE (G.C.) | APIM_CDC, APIM_CIM, BCM, DDM, ECG_Gateway, PDM, RCM | F004256 |  | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Yellow | 080-VM-FEC | F004256 | F004256 F002951 F004255 Lock Setting | SYNC+_Z0187 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-3155 | Initiative | FSW-365Active Park Assist - FG | Nasser, Ebrahim (E.) | Active Park Assist (CDX746/7) | Developing | 2020-10-14 13:17 | Rashidzadeh, Hejir (H.) | ABS, APIM_CDC, APIM_CIM, EVCM, GSM, PSCM | VSEM ID F000280 |  | Unresolved |  |  | Carryover |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F000280 |  | SYNC+_0073 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | INI | DI | DI | PI | PI | #N/A | He, Michael (X.) <xhe22@ford.com>
FSW-2910 | Initiative | FSW-770Blind Spot Information System (BLIS) - F000564 | Nasser, Ebrahim (E.) | Blind Spot Information System (BLIS) (CDX746/7) | Developing | 2020-10-06 16:23 | Crosby, Michael (M.C.) | APIM_CDC, APIM_CIM, BCM, DDM, EVCM, IPMA (ADAS), SODX | F000564 |  | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F000564 |  | SYNC+_Z1002 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Liu, Hongxin (H.) <HLIU162@ford.com>
FSW-2908 | Initiative | FSW-2122Programmable Electric Preconditioning and Charging (PEPC) | Oliveira, Eude (E.O.) | Programmable Electric Preconditioning and Charging (PEPC) (CDX746/7) | Developing | 2020-10-06 15:49 | Andrade, Ana (A.C.) | APIM_CDC, APIM_CIM, BCCM, BECM, EVCM, HPCM, TCU | F000816 | 2022-09-09 | Unresolved |  |  | Modified |  | 2022 P702 BEV | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000816 |  | SYNC+_0208 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | ECDX Lead | Yang, Jessica (Yu.) <yyang158@ford.com>
FSW-2604 | Initiative | FSW-464Mobile Device Viewer for Vehicle Cameras (MDVVC) | Chapekis, Steven (S.A.) | Mobile Device Viewer for Vehicle Cameras (CDX746/7) | Developing | 2020-09-17 08:31 | Moreno Bautista, Ariana (A.) | APCA, APIM_CDC, APIM_CIM, AUX, BCM, Cabin, Cargo, CCS, CHMSL, Consent, CSS, CVFMA, ECG, FordPass_App, Front Camera, IPMA (ADAS), Left Side Camera, MDVC FI, PDB, Rear Camera, Right Side Camera, SSP, TCU, Threat Model, TMC, VCS | Source Requirement ID | 2022-11-23 | Unresolved | The MDVVC (Mobile Device Viewer for Vehicle Cameras) feature is a key-off feature that allows the customer to stream live video feed from the vehicle camera to a mobile device (through FordPass app) to allow remote monitoring of a vehicle. FordPass allows the user to select specific vehicle camera views from a set of available. |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, RoadMapExclusion | 080-VM-FEC | F002812 |  | SYNC+_0231 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | No spec | Shi, Stella (J.) <jshi32@ford.com>
FSW-2577 | Initiative | FSW-2127Surround View Cameras | Nasser, Ahmad (A.M.) | Surround View Cameras (CDX746/7) | Developing | 2020-09-10 10:50 | Salcido-zarco, Alejandro (A.) | APIM_CDC, APIM_CIM, IPMA (ADAS) | F003515 | 2022-11-23 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003515 |  | SYNC+_0089 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xin (X.) <xli268@ford.com>
FSW-2576 | Initiative | FSW-1137IP and Switch Illumination (Smooth Dimming) | Freitas, Bruno (B.G.) | Smooth Dimming (CDX746/7) | Developing | 2020-09-10 10:48 | Martinez, João Victor (J.F.) | APIM_CDC, APIM_CIM, BCM, DDM, ECG_Gateway, GSM, ICP, RCCM, RCM, TCU | VSEM ID F000061 | 2022-11-23 | Unresolved |  |  | Modified |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000061 |  | SYNC+_Z0058 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Qiyang (Q.) <QLI111@ford.com>
FSW-2528 | Initiative | FSW-1439Ambient Lighting | Freitas, Bruno (B.G.) | Ambient Lighting (CDX746/7) | Developing | 2020-09-08 07:52 | Gemade, Ralph (R.) | ALE, APIM_CDC, APIM_CIM, BCM, RACM | VSEM ID F000063/C | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000063/C |  | SYNC+_Z0185 | New | DCV Beta | 2021-12-23 | 2022-01-06 | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-2135 | Initiative | FSW-1225Lane Centering Assist (LCA) | Wegienka, Kevin (K.) | Lane Centering Assist (LCA) (CDX746/7) | Developing | 2020-08-19 11:46 | Nagavally, Rahul Reddy (R.) | APIM_CDC, APIM_CIM, IPMA (ADAS), PSCM | F000742 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000742 |  | SYNC+_Z0281 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Ni, Anthony (H.A.) <hni1@ford.com>
FSW-1861 | Initiative | FSW-1868Driver Focused Mode | Johnston, William (Bill.) | Driver Focused Mode (CDX746/7) | Developing | 2020-08-03 11:16 | Venkatesan, Vinod (V.) | APIM_CDC, APIM_CIM, RCCM | VSEM ID F001212/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001212/A |  | SYNC+_Z0285 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1860 | Initiative | FSW-1863Passenger Aribag Deactivation | Appukutty, Jayagopal (J.) | Passenger Airbag Deactivation (CDX746/7) | Developing | 2020-08-03 11:16 | Dsouza, Aston (.) | APIM_CDC, APIM_CIM, OCS, RCM | F002214/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F002214/A |  | SYNC+_Z0296 | New | TBD | 2022-03-16 | 2022-03-30 |  |  |  | DI | [6 empty] | 0
FSW-1858 | Initiative | FSW-1865Integrated Dash Camera | Mahmood, Hamid (H.) | Integrated Dash Camera (CDX746/7) | Developing | 2020-08-03 11:16 | Eteer, Malik (M.) | APIM_CDC, APIM_CIM, ARM, ECG | VSEM ID F003751 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | 2022PriorityWorkshopSubmission, CDX746/747, China, RoadMapExclusion, confirm-containability, roadmap2023 | 080-VM-FEC | F003751 |  | SYNC+_Z0263 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI |  | 0
FSW-1857 | Initiative | FSW-1869EM Register | Johnston, William (Bill.) | Electro Mechanical (EM) Register (CDX746/7) | Developing | 2020-08-03 11:16 | Vandenbrink, Terry (T.) | APIM_CDC, APIM_CIM, RCCM | VSEM ID F003951 |  | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | 2022PriorityWorkshopSubmission, CDX746/747, China, confirm-containability, roadmap2023 | 080-VM-FEC | F003951 |  | SYNC+_0264 | Minor | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | currently no CDX747 FO for this feature, need FO support | Wang, Wei (W.) <wwang199@ford.com>
FSW-1849 | Initiative | FSW-1475Power Folding Mirrors (Lock/Unlock) | Zuraw, Timothy (T.) | Power Folding Mirrors (CDX746/7) | Developing | 2020-08-03 11:16 | Strzelczyk, Anthony (A.) | APIM_CDC, APIM_CIM, DDM, PDM | F000148/D | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000148/D |  | SYNC+_Z0256 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1846 | Initiative | FSW-1452Position/Parking Light | Neves, Adriana Duarte (A.D.) | Parking Light / Position Light (CDX746/7) | Developing | 2020-08-03 11:16 | Costa, Marcelo (M.N.) | APIM_CDC, APIM_CIM, BCM, LDM | F001012/B | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Red | 080-VM-FEC | F001012/B |  | SYNC+_Z0257 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | no spec | 0
FSW-1845 | Initiative | FSW-1451Manual Low Beam | Neves, Adriana Duarte (A.D.) | Low Beam (CDX746/7) | Developing | 2020-08-03 11:16 | Mattos, Andre Licurgo (A.L.) | APIM_CDC, APIM_CIM, BCM, HCM, LDM, SCCM | F000998 | 2022-11-14 | Unresolved |  |  | Modified |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Red | 080-VM-FEC | F000998 |  | SYNC+_Z0258 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | no spec | 0
FSW-1844 | Initiative | FSW-1443Map/Dome Lighting (Manual Interior Lighting) | Freitas, Bruno (B.G.) | Overhead Lighting (CDX746/7) | Developing | 2020-08-03 11:16 | Santana, Gabriel (G.D.) | ABS, APIM_CDC, APIM_CIM, BCM, ECG_Gateway, HCM, PDB | F000058/D | 2022-11-14 | Unresolved |  |  | Modified |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000058/D | F000058/C Map/Dome Lights (RSD - Manual Interior Lighting) | SYNC+_Z0259 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1842 | Initiative | FSW-1446Fog Light - F001010 | Meffe, Eloy (J.) | Rear Fog Lights (CDX746/7) | Developing | 2020-08-03 11:16 | Suzart, Joyce (J.) | APIM_CDC, APIM_CIM, BCM | F001010 | 2022-11-14 | Unresolved |  |  | Modified |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001010 | F001010/B Rear Fog Lights | SYNC+_Z0291 | N | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 | NA | [6 empty] | IPC function | 0
FSW-1837 | Initiative | FSW-660Pre-Collision Assist (PCA) | Seiler, Rebecca (R.L.) | Pre-Collision Assist (CDX746/7) | Developing | 2020-08-03 11:16 | Gelan, Ibrahim (I.S.) | ABS, APIM_CDC, APIM_CIM, BCM, EVCM, TCU | F004999 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F004999 |  | SYNC+_Z0091 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Zhu, Jinpeng (J.) <jzhu85@ford.com>
FSW-1836 | Initiative | FSW-1473Lane Keeping System | Sorgenfrei, Birgit (B.L.) | Lane Keeping System (CDX746/7) | Developing | 2020-08-03 11:16 | Patil, Pranav (P.) | APIM_CDC, APIM_CIM, IPMA (ADAS), PSCM | VSEM ID vFG000456/ vFG000284/ vFG000668/ vFG002069/ | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | VSEM ID vFG000456/ vFG000284/ vFG000668/ vFG002069/ |  | SYNC+_Z0227 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Zhang, Wayne (W.R.) <wzhan114@ford.com>
FSW-1835 | Initiative | FSW-1223Driver Alert System | Sorgenfrei, Birgit (B.L.) | Driver Alert System (CDX746/7) | Developing | 2020-08-03 11:16 | Uptain, Charles (C.E.) | APIM_CDC, APIM_CIM, BCM, EVCM, IPMA (ADAS) | VSEM ID F000285/B | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000285/B |  | SYNC+_Z0229 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Song, Amy (S.) <ssong18@ford.com>
FSW-1834 | Initiative | FSW-504Intelligent Adaptive Cruise Control | Abinoja, Eddie (E.O.) | Intelligent Adaptive Cruise Control (iACC) (CDX746/7) | Developing | 2020-08-03 11:16 | Sarkar, Animesh (A.) | APIM_CDC, APIM_CIM, IPMA (ADAS) | VSEM ID VF004044 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | VF004044 | VF004044 F000910 F000911 F000912 Cruise Control Setting | SYNC+_Z0075 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Cui, Victor (M.) <mcui5@ford.com>
FSW-1833 | Initiative | FSW-639Reverse Brake Assist | Nasser, Ebrahim (E.) | Reverse Brake Assist (CDX746/7) | Developing | 2020-08-03 11:16 | Cheng, Samuel (S.) | ABS, APIM_CDC, APIM_CIM, IPMA (ADAS) | F001330 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F001330 |  | SYNC+_0074 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Yifan (Y.) <YLI381@ford.com>
FSW-1832 | Initiative | FSW-658Cross Traffic Alert (CTA) | Nasser, Ebrahim (E.) | Cross Traffic Alert with Braking (CDX746/7) | Developing | 2020-08-03 11:16 | Rossi, Antonio (A. R.) | ABS, APIM_CDC, APIM_CIM, BCM, DDM, EVCM, IPMA (ADAS), PDM, SODX | VSEM ID F000565 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000565 |  | SYNC+_0098 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Liu, Hongxin (H.) <HLIU162@ford.com>
FSW-1831 | Initiative | FSW-659Evasive Steering Assist | Mattern, Don (D.) | Evasive Steer Assist (CDX746/7) | Developing | 2020-08-03 11:16 | Wang, Haisu (H.) | ABS, APIM_CDC, APIM_CIM, IPMA (ADAS), PSCM | VSEM ID F000513 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 S650 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000513 | Pre Collision Assist 同F004999 | SYNC+_Z0091 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Zhu, Jinpeng (J.) <jzhu85@ford.com>
FSW-1830 | Initiative | FSW-2526Blind Spot Assist | Abinoja, Eddie (E.O.) | Blind Spot Assist (CDX746/7) | Developing | 2020-08-03 11:16 | McWilliams, John (J.S.) | APIM_CDC, APIM_CIM, DDM, IPMA (ADAS), PDM, PSCM | VSEM ID F001451/C | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001451/C |  | SYNC+_Z1011 | N | 0 | 0 | 0 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | 0
FSW-1829 | Initiative | FSW-2091Enhanced Active Driver Assist | Wegienka, Kevin (K.) | Active Drive Assist 1.2 (CDX746/7) | Developing | 2020-08-03 11:16 | Gotadki, Shruti (S. P.) | APIM_CDC, APIM_CIM, CMR, IPMA (ADAS), PSCM | FO to confirm VSEM ID | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 CX483 MCA | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | FO to confirm VSEM ID |  | SYNC+_Z0230 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | No spec | Ni, Anthony (H.A.) <hni1@ford.com>
FSW-1828 | Initiative | FSW-375Remote Park Assist (RePA) | Nasser, Ebrahim (E.) | Remote Park Assist (RePA) 2024 CDX746/7 | Developing | 2020-08-03 11:16 | Rashidzadeh, Hejir (H.) | ABS, APIM_CDC, APIM_CIM, BCM, ECG_Gateway, EVCM, FordPass_App, GSM, IPMA (ADAS), LincolnWay, PSCM, RFA | F002930 | 2022-11-14 | Unresolved |  |  | New |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | Applications, CDX746/747, China, DCO, NO_KEYFOB | 090-PG-TT | F002930 |  | SYNC+_0076 | C/O | DCV3 | 2022-07-11 | 2022-07-26 | [7 empty] | DI | DI | No spec | He, Michael (X.) <xhe22@ford.com>
FSW-1825 | Initiative | FSW-407Phone As A Key & Backup Starting Passcode (PaaK & BSP) | Considine, Susan (S.) | Phone as a Key (PaaK) "BUN" w/o Keyfob 2024 CDX746/7 | Developing | 2020-08-03 11:16 | Hamel, Jeffrey (J.) | APIM_CDC, APIM_CIM, BCM, ECG, FordPass_App, LincolnWay, RFA, TCU | F001670/A | 2022-11-14 | Unresolved |  |  | Modified |  | 2022 U540N | 2024 CDX746, 2024 CDX747 | BCM, CDX746/747, CSTF, China, FNV3, J1, NFC, NO_KEYFOB, PaaK, PaaKBSP | 080-VM-FEC | F001670/A | 同F001372 | SYNC+_0106 | C/O | DCV Beta1 | 2022-02-16 | - |  |  |  | DI | DI | DI | DI | PI | PI | #N/A | Chen, chiefer
FSW-1822 | Initiative | FSW-443Plug and Charge | Kumar, Salaj (S.) | Plug and Charge (24 CDX746/7) | Developing | 2020-08-03 11:16 | Jujavarapu, Sandeep (S.) | APIM_CDC, APIM_CIM, ECG, OBCC, TCU | F002430 | 2023-04-11 | Unresolved |  |  | Carryover |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, EC-FO, HMPC | 080-VM-FEC | F002430 |  | SYNC+_Z1012 | New | TBD | 2022-03-16 | 2022-03-30 |  |  |  | DI | [5 empty] | spec received by qiyang | Wang, Yixuan (Vovo) <ywang219@ford.com>
FSW-1820 | Initiative | FSW-1173First Row Seat Position Control | Olsen, Bill (W.J.) | First Row Seat Position Control (CDX746/7) | Developing | 2020-08-03 11:16 | Aguilar, Diana (D.S.) | APIM_CDC, APIM_CIM, DSM, ECG_Gateway, RACM, SCMB, SCMK, SCML | VSEM ID F003516 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | 5D, CDX746/747, China, Yellow | 080-VM-FEC | F003516 |  | SYNC+_Z0287 | C/O | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | #N/A | Du, Hao (H.) <HDU9@ford.com>
FSW-1818 | Initiative | FSW-2394Seat Temperature Control | Olsen, Bill (W.J.) | Seat Temperature Control (CDX746/7) | Developing | 2020-08-03 11:16 | Mlynarczyk, Stephanie (S.A.) | APIM_CDC, APIM_CIM, DSM, RACM, RCCM, TCU | F003518 | 2022-11-14 | Unresolved |  |  | Modified |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003518 | 2 new feature ID, SYNC+_Z0167: Front Row Seat Heated，SYNC+_Z0168: Front Seat Vent | SYNC+_Z0167 SYNC+_Z0168 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | #N/A
FSW-1817 | Initiative | FSW-388Multi-Contour Seats | Barreto, Rafael (R.V.) | Multi-Contour Seat (CDX746/7) | Developing | 2020-08-03 11:16 | Santos, Roger (R.M.) | APIM_CDC, APIM_CIM, BCM, DSM, RACM, SCMC, SCMD, SCMG, SCMH | F000158 | 2022-11-14 | Unresolved |  |  | Modified |  | Not Listed | 2024 CDX747 | CDX747, China, DCO | 080-VM-FEC | F000158 |  | SYNC+_Z0088 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | No spec | Du, Hao (H.) <hdu9@ford.com>
FSW-1816 | Initiative | FSW-2149Power Open/Close Liftgate | Holub, Patrick (P.K.) | Power Liftgate (CDX746/7) | Developing | 2020-08-03 11:16 | Gunaratnam, Raj (M.) | APIM_CDC, APIM_CIM, BCM, RGTM | F000162/D | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000162/D | can't match F000162 --> rear liftgate F000165/D --> power liftgate SW switch | SYNC+_Z0212 SYNC+_Z0293 | C/O | DCV Beta DCV Beta1 | 12/23/2021 2/16/2022 | 1/6/2022 '- |  |  |  | DI | DI | DI | PI | PI | PI | #N/A | #N/A
FSW-1813 | Initiative | FSW-2444Front Automatic Wiping | Yousif, Meisam (M.L.) | Front Automatic Wiping (CDX746/7) | New | 2020-08-03 11:16 | Uttar, Nikhil (N.) | APIM_CDC, APIM_CIM, BCM, SCCM | F000066 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000066 |  | SYNC+_Z0217 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-1811 | Initiative | FSW-456Auto Hold | Mlynarczyk, Scott (S.L.) | Auto Hold (CDX746/7) | Developing | 2020-08-03 11:16 | James, Alex (J.A.) | ABS, APIM_CDC, APIM_CIM | VSEM ID F000097/E | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000097/E | F000097 --> auto vehicle hold | SYNC+_Z0069 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com>
FSW-1809 | Initiative | FSW-760Automatic High Beam (AHBC/GFHB/ADB) - FNV3 | Sorgenfrei, Birgit (B.L.) | Auto High Beam Controller (CDX746/7) | Developing | 2020-08-03 11:16 | Uptain, Charles (C.E.) | APIM_CDC, APIM_CIM, BCM, HCM, IPMA (ADAS), LDM, SCCM | VSEM ID F004650 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F004650 | F004650（707） F000918(788) 3# Help Me See 视觉辅助 - 自适应远光灯 Auto High beam | SYNC+_Z0231 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Song, Amy (S.) <ssong18@ford.com>
FSW-1805 | Initiative | FSW-2879Tire Pressure Monitoring System | Sarracini, Fernando (FSJ.) | TPMS (CDX746/7) | Developing | 2020-08-03 11:16 | Silva, Tays (T.C.) | APIM_CDC, APIM_CIM, BCM, RTM | F000109/D | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 S650 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000109/D | F000109/D FNG000760 | SYNC+_Z0289 | C/O | DCV Beta1 | 2022-02-16 | - |  |  |  |  | INI | DI | DI | PI | PI | Pending Cluster IOD logic realization | Wang, Vincent (X.) <xwang151@ford.com>
FSW-1804 | Initiative | FSW-652Beltminder | Appukutty, Jayagopal (J.) | Global Beltminder (CDX746/7) | Developing | 2020-08-03 11:16 | Dsouza, Aston (.) | APIM_CDC, APIM_CIM, RCM | F002216/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO | 080-VM-FEC | F002216/A |  | SYNC+_Z1007 | C/O | DCV Beta1 | 2022-02-16 | - |  |  |  | INI | DI | DI | DI | PI | PI | Pending Cluster IOD logic realization | Xu, Xi Hai (X.) <xxu61@ford.com>
FSW-1799 | Initiative | FSW-2106Heated Backlight | Cruz, Mauricio (M.C.) | Heated Backlight (CDX746/7) | Developing | 2020-08-03 11:16 | Mota, Kaique (K.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, PDB, RCCM | VSEM ID F000122/B | 2022-11-29 | Unresolved |  |  | Carryover |  | 2023 CD539 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000122/B |  | SYNC+_Z0247 | C/O | DCV Beta1 | 2022-02-16 | - |  |  | DI | DI | DI | DI | PI | PI | PI | need confirm with FO detail spec and check timing plan | Shi, Song (S.S.) <sshi24@ford.com>
FSW-1798 | Initiative | FSW-2697Exit Warning | Nasser, Ebrahim (E.) | Exit Warning (CDX746/7) | Developing | 2020-08-03 11:16 | Kaur, Gagandeep (G.) | APIM_CDC, APIM_CIM, BCM, DCME, DCMF, DCMG, DCMH, IPMA (ADAS) | VSEM ID F001430/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2024 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001430/A | F001430 | SYNC+_0101 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Liu, Hongxin (H.) <HLIU162@ford.com>
FSW-1794 | Initiative | FSW-2073Core Media Player | Nasrallah, Hussein (H.) | Core Media Player (CDX746/7) | Developing | 2020-08-03 11:16 | Ahmed, Basheer (B.) | APIM_CDC, APIM_CIM, RACM | VSEM ID F000379/G | 2022-11-14 | Unresolved |  |  | Carryover |  | Not Listed | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F000379/G |  | SYNC+_0015 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com>
FSW-1790 | Initiative | FSW-1117Navigation | Chararah, Bilal (B.) | Navigation Systems (CDX746/7) | Developing | 2020-08-03 11:15 | Deaibes, William (W.) | APIM_CDC, APIM_CIM, TCU | F000218/Q | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000218/Q |  | SYNC+_0001 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  |  | INI | DI | DI | DI | PI | PI | Pending on Location service FNV3 technical solution(GNSS in TCU B6) | Yao, Tristan (Lan) <LYAO17@ford.com>
FSW-1789 | Initiative | FSW-1157Traffic Sign Recognition (TSR) | Abinoja, Eddie (E.O.) | Traffic Sign Recognition (CDX746/7) | Developing | 2020-08-03 11:15 | Sarkar, Animesh (A.) | APIM_CDC, APIM_CIM, IPMA (ADAS) | F000913/C | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000913/C |  | SYNC+_Z0097 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Cui, Victor (M.) <mcui5@ford.com>
FSW-1785 | Initiative | FSW-3800CCS - Carline Feature Delivery | Kahlen, Micha (M.) | Customer Connectivity Settings (CDX746/7) | Developing | 2020-08-03 11:15 | Pechlivanidis, Savvas (S.) | APIM_CDC, APIM_CIM, ECG, TCU | VSEM ID F001040/E | 2022-11-14 | Unresolved |  |  | Carryover |  | Not Listed | 2024 CDX746, 2024 CDX747 | CDX746/747, China, RED | 080-VM-FEC | F001040/E |  | SYNC+_Z0032 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Gu, Regina (Q.) <qgu12@ford.com>
FSW-1781 | Initiative | FSW-2139E-Shifter | Awadi, Ahmed (A.) | Range Selection (CDX746/7) | Developing | 2020-08-03 11:15 | Kotha, Mahender (M.) | ABS, APIM_CDC, APIM_CIM, BCM, DCME, ECG_Gateway, EVCM, GSM, HPCM | VSEM ID F000956/C | 2022-11-14 | Unresolved |  |  | Modified |  | Not Listed | 2024 CDX746, 2024 CDX747 | 5D, CDX746/747, China, DCO, YELLOW | 080-VM-FEC | F000956/C | ONLY IMPACT IPC | #N/A | N | #N/A | #N/A | #N/A |  |  | NA | [6 empty] | #N/A | #N/A
FSW-1777 | Initiative | FSW-2107Heated Mirrors | Cruz, Mauricio (M.C.) | Heated Mirrors (CDX746/7) | Developing | 2020-08-03 11:15 | Melo, Isabela (I. P.) | APIM_CDC, APIM_CIM, BCM, DCDC, DDM, ECG_Gateway, EVCM, HPCM, PDM, RCCM | VSEM ID F000800/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2022 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000800/A | F000800 | SYNC+_Z1003 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Xie, Will (W.) <wxie15@ford.com>
FSW-1771 | Initiative | FSW-1170Cellular Remote Start | Drummond, Colin (C.) | Cellular Remote Start w/Extend Remote Start FNV3 (CDX746/7) | Developing | 2020-08-03 11:15 | Syed, Imtiaz (I.S.) | APIM_CDC, APIM_CIM, BCM, ECG, EVCM, RCCM, TCU | VSEM ID: F003410 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003410 |  | SYNC+_Z1019 | New | DCV Beta1 | 2022-02-16 | - |  |  |  | DI | DI | DI | PI | PI | PI | ECDX Lead | 0
FSW-1770 | Initiative | FSW-1171Cellular Schedule Remote Start | Drummond, Colin (C.) | Cellular Scheduled Remote Start (CDX746/7) | Developing | 2020-08-03 11:15 | Syed, Imtiaz (I.S.) | APIM_CDC, APIM_CIM, BCM, ECG, EVCM, TCU | VSEM ID F003411 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F003411 |  | SYNC+_Z1020 | New | DCV Beta1 | 2022-02-16 | - |  |  |  | DI | DI | DI | PI | PI | PI | ECDX Lead | 0
FSW-1763 | Initiative | FSW-1455Turn Indicator Light | Silva, Davi (D.M.) | Turn Indicator (CDX746/7) | Developing | 2020-08-03 11:15 | TEIXEIRA, IGOR (I.) | APIM_CDC, APIM_CIM, BCM, HCM, LDM, SCCM | VSEM ID: F001007 | 2022-11-14 | Unresolved |  |  | Modified |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001007 | ONLY IMPACT IPC | #N/A | N | #N/A | #N/A | #N/A |  |  | NA | [6 empty] | #N/A | #N/A
FSW-1762 | Initiative | FSW-2129Vehicle Health Alert and Status and Vehicle Location | Aekka, Venkat (V.R.) | Vehicle Health Alert and Status, and Vehicle Location (CDX746/7) | Developing | 2020-08-03 11:15 | McKinstry, Roy (R.S.) | APIM_CDC, APIM_CIM, Cloud, ECG, TCU, TMC | VSEM ID: F001048/F | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001048/F |  | SYNC+_0122 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Lu, Chao (C.) <clu42@ford.com>
FSW-1758 | Initiative | FSW-1440Automatic Dynamic Leveling | Neves, Adriana Duarte (A.D.) | Automatic Dynamic Leveling (CDX746/7) | Developing | 2020-08-03 11:15 | Lima, Alexa Larissa (A.d.) | APIM_CDC, APIM_CIM, HCM, LDM, VDM | VSEM ID F001023 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001023 |  | SYNC+_Z0241 | N | 0 | 0 | 0 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | Zhou, Travis (C.X.) <czhou17@ford.com>
FSW-1754 | Initiative | FSW-1084Digital Owner's Manual | Cruse, Christopher (C.D.) | Digital Owner's Manual (CDX746/7) | Developing | 2020-08-03 11:15 | Hari, Srikanth (S.) | APIM_CDC, APIM_CIM, ECG_Gateway, TCU | VSEM ID F002370 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F002370 |  | SYNC+_0117 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | DI | DI | DI | DI | PI | ECDX Lead | Jiang, Wei (W.)
FSW-1753 | Initiative | FSW-2145Frunk | McInally, Steven (M.) | Frunk (CDX746/7) | Developing | 2020-08-03 11:15 | Butler, Jordan (J.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, FHCM, RFA | VSEM ID F002010/B | 2022-10-14 | Unresolved |  |  | Modified |  | 2022 P702 BEV | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F002010/B |  | SYNC+_Z0294 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1751 | Initiative | FSW-2150Hands Free Phone | Al dallal, Alabbas (A.M.) | Handsfree Phone (CDX746/7) | Developing | 2020-08-03 11:15 | Balakrishnan, Sabarish (S.) | APIM_CDC, APIM_CIM | VSEM ID F000345/K | 2022-11-14 | Unresolved |  |  | Carryover |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F000345/K |  | SYNC+_0013 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Xu, Amy (X.) <xyafei@ford.com>
FSW-1750 | Initiative | FSW-1447Hazard Light | Silva, Davi (D.M.) | Hazard Light (CDX746/7) | Developing | 2020-08-03 11:15 | TEIXEIRA, IGOR (I.) | APIM_CDC, APIM_CIM, BCM, LDM | VSEM ID F001009 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001009 |  | SYNC+_Z0244 | N | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 | NA | [6 empty] | IPC function | 0
FSW-1743 | Initiative | FSW-1233Speedometer | Catani, Norberto (N.C.) | Speedometer (CDX746/7) | Developing | 2020-08-03 11:15 | Santiago, Karen (K.T.) | ABS, APIM_CDC, APIM_CIM, BCM, EVCM | F000665/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, green | 080-VM-FEC | F000665/A | ONLY IMPACT IPC | #N/A | N | #N/A | #N/A | #N/A |  |  | NA | [6 empty] | #N/A | #N/A
FSW-1741 | Initiative | FSW-212In-Vehicle Software Updates (MMOTA) Capabilities - F001192 | Thorne, Nicholas (N.A.) | In-Vehicle Software Update (CDX746/7) | Developing | 2020-08-03 11:15 | Gudemaranahalli, Rohini Pr (R.) | APIM_CDC, APIM_CIM, BCM, ECG, EVCM, TCU | VSEM ID F001192/C | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F001192/C |  | SYNC+_0221 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | DI | DI | DI | DI | PI | ECDX Lead | Wang, Jennifer (J.) <jwang373@ford.com>
FSW-1740 | Initiative | FSW-2113One Pedal Drive (1PD) | Miyashita, Eduardo (E.M.) | One Pedal Drive (CDX746/7) | Developing | 2020-08-03 11:15 | Padilha, Rodrigo (R. P.) | ABS, APIM_CDC, APIM_CIM, BCM, ECG_Gateway, EVCM, HPCM | F002710 | 2022-11-14 | Unresolved |  |  | Modified |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F002710 |  | SYNC+_Z0276 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | Wu, Dean (D.) <dwu44@ford.com>
FSW-1738 | Initiative | FSW-1417Idle Shutdown | Braithwaite, Paul (P.) | Auto Engine Idle Shutdown (CDX746/7) | Developing | 2020-08-03 11:15 | Engelbrecht, CP (C.) | APIM_CDC, APIM_CIM, BCM, EVCM | VSEM ID F000760 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO | 080-VM-FEC | F000760 |  | SYNC+_Z0246 | Major | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1737 | Initiative | FSW-2080Driver Information Display Control (DIDC) | Oliveira, Eude (E.O.) | Driver Information Display Control (CDX746/7) | Developing | 2020-08-03 11:15 | Sousa, Filipe (F.B.) | APIM_CDC, APIM_CIM, ECG_Gateway | VSEM ID: F000810 | 2022-11-14 | Unresolved |  |  | Modified |  | Not Listed | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000810 |  | SYNC+_Z1008 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | DI | DI | DI | DI | PI | No spec | Jin Flora< JJIN17@ford.com>
FSW-1735 | Initiative | FSW-2069Charge Status Indication (CSI) | Deddeh, Tony (T.) | Charge Status Indicator (CDX746/7) | Developing | 2020-08-03 11:15 | Mohar, Maria (M.) | APIM_CDC, APIM_CIM, BCCM, BCM, BECM, EVCM, HPCM | VSEM ID F001065 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001065 |  | SYNC+_0208 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-11-15 |  | DI | [5 empty] | ECDX Lead | Yang, Jessica (Yu.) <yyang158@ford.com>
FSW-1724 | Initiative | FSW-1395Wireless Accessory Charging | Oliveira, Eude (E.O.) | Wireless Accessory Charging (CDX746/7) | Developing | 2020-08-03 11:15 | Oliveira Neto, Aderbal (A. R.) | APIM_CDC, APIM_CIM, BCM, WCM, WCMC | F001046/D | 2022-11-14 | Unresolved |  |  | Modified |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001046/D | F001046/C --> Phone Wireless Charging notification | SYNC+_Z0050 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Lyu, Qingtao (Q.) <qlyu@ford.com>
FSW-1721 | Initiative | FSW-2118Perimeter Anti-Theft Alarm | Patel, Nimish (N.H.) | Perimeter Anti-Theft Alarm (CDX746/7) | Developing | 2020-08-03 11:15 | Talaga, Joshua (J.) | APIM_CDC, APIM_CIM, BCM, TCU | F000178/D | 2022-11-14 | Unresolved |  |  | Carryover |  | 2022 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO | 080-VM-FEC | F000178/D |  | SYNC+_Z0288 | N | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | 0
FSW-1703 | Initiative | FSW-1129Walk Away Lock | Cherman, Andre (A.L.) | Walk Away Lock (CDX746/7) | Developing | 2020-08-03 11:15 | Ruis, Ramon (R.) | APIM_CDC, APIM_CIM, BCM, DCME, DCMF, DCMG, DCMH, DDM, ECG_Gateway, FordPass_App, PDB, PDM, RFA | F002951 | 2022-11-14 | Unresolved |  |  | Modified |  | Not Listed | 2024 CDX746, 2024 CDX747 | CDX746/747, CSTF, China, DCO, J1, NO_KEYFOB, PaaK | 080-VM-FEC | F002951 | F004256 F002951 F004255 lock setting | SYNC+_Z0187 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-1698 | Initiative | FSW-1224Key in Reminder (KIR) | Miranda, Airton (A. W.) | Key in Reminder (CDX746/7) | Developing | 2020-08-03 11:15 | Silva, Diego (D.M.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway | VSEM ID F001790 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Green | 080-VM-FEC | F001790 |  | SYNC+_Z1009 | N | 0 | 0 | 0 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | 0
FSW-1697 | Initiative | FSW-1203Heated Steering Wheel | Cruz, Mauricio (M.C.) | Heated Steering Wheel (CDX746/7) | Developing | 2020-08-03 11:15 | Shirazawa, Diogo (D.H.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, HPCM, RCCM, SCCM | VSEM ID F000123/C | 2022-11-14 | Unresolved |  |  | Carryover |  | 2022 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000123/C |  | SYNC+_Z0295 | C/O | DCV Beta1 | 2022-02-16 | - |  |  |  | DI | DI | DI | PI | PI | PI | need confirm detail spec with FO and check timing plan | Yan, Sophie (C.) <cyan10@ford.com>
FSW-1693 | Initiative | FSW-412eCall | Nasrallah, Hussein (H.) | Pan-Euorpean eCall (CDX746/7) | Developing | 2020-08-03 10:41 | Berro, Hussein (H.) | ACM, APIM_CDC, APIM_CIM, DSP, TCU | F000997 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F000997 |  | SYNC+_0126 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | ECDX Lead | Ren, Siyuan (Alex.)
FSW-1687 | Initiative | FSW-2405Cabin & Battery Overheat Management (old name TMOS) | Johnston, William (Bill.) | Cabin & Battery Overheat Management (old name TMOS) (CDX746/7) | Developing | 2020-05-21 08:19 | Collins, Lynn (L.) | ACCM, APIM_CDC, APIM_CIM, BCM, BECM, ECG_Gateway, EVCM, GSM, RCCM | VSEM ID: F003090 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003090 |  | SYNC+_Z0253 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1496 | Initiative | FSW-2066Augmented Reality | Yousif, Meisam (M.L.) | Augmented Reality (CDX746/7) | Developing | 2020-07-27 22:30 | Abdelhamid, Mahmoud (M.) | APIM_CDC, APIM_CIM, AR Camera, ARM, FIR Camera, HHDD, IPMA (ADAS) | VSEM ID F003774 | 2022-10-18 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | Aspire, CDX746/747, China, Red, VCSEDashboard | 080-VM-FEC | F003774 |  | SYNC+_Z1021 | New | DCV1 | 2022-04-15 | 2022-04-30 | 2021-10-30 | 2021-12-15 |  |  |  | DI | DI | DI | PI |  | 0
FSW-1299 | Initiative | FSW-2406Second Row Seat Position Control | Olsen, Bill (W.J.) | Second Row Seat Position Control (CDX746/7) | Developing | 2020-07-17 12:21 | Aguilar, Diana (D.S.) | APIM_CDC, APIM_CIM, DSM, ECG_Gateway, EVCM, RACM, SCMB, SCMK, SCML | F003517 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX747 | 5D, CDX747, China, Yellow | 080-VM-FEC | F003517 |  | SYNC+_Z0292 | New | DCV Beta | 2021-12-23 | 2022-01-06 | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1124 | Initiative | FSW-373Selectable Drive Mode | Awadi, Ahmed (A.) | Selectable Drive Mode (CDX746/7) | Developing | 2020-07-07 10:08 | Meza morales, Luis Enrique (L.) | ABS, APIM_CDC, APIM_CIM, EVCM, IPMA (ADAS), PSCM, VDM | VSEM ID: F000549 | 2023-06-12 | Unresolved |  |  | Modified |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F000549 |  | SYNC+_Z0045 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | 0
FSW-1071 | Initiative | FSW-414WiFi Hotspot | Taleb, Yamen (Y.J.) | WiFi Hotspot (CDX746/7) | Developing | 2020-06-02 22:35 | Vega martinez, Oscar (O.) | APIM_CDC, APIM_CIM, ECG, TCU | VSEM ID: F000974/E |  | Unresolved |  |  | Carryover |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F000974/E |  | SYNC+_Z0155 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | ECDX Lead | Pan, Yuan (Y.) <ypan23@ford.com>
FSW-1061 | Initiative | FSW-1059F003074/A;1 Heated Wiper Blade - HWB | Cruz, Mauricio (M.C.) | Heated Wiper Blade (CDX746/7) | Developing | 2020-05-29 11:08 | Lima, Dorivaldo (.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, EVCM, PDB, RCCM | VSEM ID: F003074 | 2022-11-14 | Unresolved |  |  | Modified |  | 2022 P702 BEV | 2024 CDX747 | CDX747, China, Green | 080-VM-FEC | F003074 | F003074 F000121 Heated Wiper Blade Heated Windshield | SYNC+_Z1004 | New | DCV Beta | 2021-12-23 | 2022-01-06 | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-895 | Initiative | FSW-892Rear Seat Controls Lockout - F003110 | Holub, Patrick (P.K.) | Rear Seat Controls Lockout (Modified) (CDX746/7) | Developing | 2020-05-08 15:20 | Ganna, Spurthi Varma (S.) | APIM_CDC, APIM_CIM, BCM, RACM, RCCM | F003110 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003110 |  | SYNC+_Z0255 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | no SPSS | TBD
FSW-894 | Initiative | FSW-702Classic Memory - F000171 | Miranda, Airton (A. W.) | Classic Memory - FNV3 (CDX746/7) | Developing | 2020-05-08 15:20 | Brasileiro, Matheus (M.B.) | APIM_CDC, APIM_CIM, BCM, DDM, DSM, ECG_Gateway, EVCM, PDM, RCM, SCMB, SCMG, SCMH | VSEM ID F000171 | 2022-11-14 | Unresolved |  |  | Modified |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO, Green | 080-VM-FEC | F000171 |  | SYNC+_Z1006 | N | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | 0
FSW-893 | Initiative | FSW-377Enhanced Memory - F000172 | Torres, Nhi (N.) | Enhanced Memory - FNV3 (CDX746/7) | Developing | 2020-05-08 15:20 | Rahman, Naomee (N.) | ABS, ACM, APIM_CDC, APIM_CIM, BCM, DDM, DSM, DSP, IPMA (ADAS), PDM, RCCM, SCCM, SCMB, SCMG, SCMH | VSEM ID F000172 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Green, NO_KEYFOB | 080-VM-FEC | F000172 |  | SYNC+_0165 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  |  | DI | DI | DI | PI | PI | PI | #N/A | Xu, Andy (X.) <XXU71@ford.com>
FSW-891 | Initiative | FSW-647Welcome / Farewell | Cherman, Andre (A.L.) | Lincoln Embrace (Modified) (CDX747) | Developing | 2020-05-08 12:32 | Petrilli, Bianca (B. D.) | ACM, APIM_CDC, APIM_CIM, BCM, DASM, DDM, ECG_Gateway, HCM, LDM, PDM, RACM | F004174 | 2022-11-14 | Unresolved |  |  | Modified |  | 2020 U611 | 2024 CDX747 | CDX747, China, DCO, Green, NO_KEYFOB | 080-VM-FEC | F004174 | F004174 F000064 | SYNC+_0170 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Chen, Huizhen (H.) <hchen188@ford.com>
FSW-890 | Initiative | FSW-886PDLC SkyLite Digital Shade (PSDS) | Barreto, Rafael (R.V.) | PDLC SkyLite Digital Shade (PSDS - CDX747) | Developing | 2020-05-08 12:32 | Tronolone, Ulisses (U.F.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, HCM, LincolnWay, PDB, RACM, RCCM, SCMB | F003170 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX747 | CDX747, China, Yellow, roadmap2023 | 080-VM-FEC | F003170 |  | SYNC+_Z0250 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-889 | Initiative | FSW-885Stowable Steering Column with Deployable Tray | Deddeh, Tony (T.) | Stowable Steering Column with Deployable Tray (CDX746/7) | Developing | 2020-05-08 12:32 | Lau, Tok (T. W.) | ABS, APIM_CDC, APIM_CIM, BCM, DSM, ECG_Gateway, EVCM, RCM, SCMB | F002870 |  | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, roadmap2023 | 080-VM-FEC | F002870 |  | SYNC+_Z0251 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI |  | 0
FSW-882 | Initiative | FSW-8497Sentinel | Zuraw, Timothy (T.) | Sentinel Experience Phase 3(CDX746/7) | Developing | 2020-05-08 09:20 | Minous, Corey (C.) | APIM_CDC, APIM_CIM, BCM, Cloud, ECG, FordPass_App, IPMA (ADAS), PDB, TCU | F003417 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023.5 V710 | 2024 CDX747 | Aspire, CDX747, China, Red, RoadMapExclusion, roadmap2023 | 080-VM-FEC | F003417 |  | SYNC+_Z0262 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | need further clarify feature then can clarify TS&YFVE job devision, current questions as below: 1. Will the North American team provide an implementation library or binary for "CameraService" on SYNC+? 2. In the IDC architecture, what is the progress of the software solutions for other ECUs other than SYNC+? Is there a corresponding FO support? 3. The video stream and vehicle-related metadata recorded by VRP can be played through the cloud. Is there any legal risk to this function in China? 4. The video stream is transmitted based on the RTSP protocol. Can you provide more definitions about the protocol and the function definition of video stream transmission? 5. When playing back the recorded video, will the HMI directly play it through the video file path, or use the VideoPlayBackService of the VRP to report the video stream to the HMI for display? 6. Does the recorded video contain audio stream data？ 7. How to stop recording of Integrated Security Camera (Sentinel) Feature？ 8. What is the metadata file format associated with the video？ | 0
FSW-744 | Initiative | FSW-738My Seat Space (MSS) | Cauley, Jason (J.F.) | My Seat Space (MSS) (CDX746/7) | Developing | 2020-04-27 21:31 | Cintron, Austin (A.) | ACM, APIM_CDC, APIM_CIM, DSP, RACM | F003519 | 2022-11-29 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX747 | CDX747, China, Yellow, confirm-containability, roadmap2023 | 105-VM-J1 | F003519 |  | SYNC+_0228 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-11-30 | 2022-01-11 | [5 empty] | DI | DI | this is a complicated feature and related muti-model, considering the difference between Phoenix and SYNC+ need further check spec with FO, for development it's better to set a local FO to support. Current questions as below: TS: should MSS develop based on Android 11? | 0
FSW-741 | Initiative | FSW-737Rejuvenate Mode | Reppenhagen, Nancy (N.B.) | Rejuvenate Mode (CDX747) | Developing | 2020-04-27 21:31 | Shetty, Sohan (S.R.) | APIM_CDC, APIM_CIM, BCM, DSM, ECG, EVCM, RCCM, SCMB, TCU | F003072 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX747 | 2022PriorityWorkshopSubmission, Aspire, CDX747, China, VESC_Portfolio, roadmap2023 | 080-VM-FEC | F003072 |  | SYNC+_0135 | New | DCV3 | 2022-07-11 | 2022-07-26 | 2021-10-30 | 2021-12-30 |  |  |  |  | DI | DI | PI | ECDX Lead | Liu, Kai (K.) <kliu63@ford.com>
FSW-740 | Initiative | FSW-712Ultimate Remote Control - F003071 | Cauley, Jason (J.F.) | Ultimate Remote Control (CDX746/7) | Developing | 2020-04-27 21:30 | Thabet, Safwan (S.A.) | ACM, APIM_CDC, APIM_CIM, ECG, FordPass_App, LincolnWay, RCCM, SCMB, SCMC, SCMD, SCME, SCMF, SCMG, SCMH, SCMK, SCML | F003071 | 2022-11-14 | Unresolved | The team is working together but still many unknowns. Team is unaware of any business goals / expectations beyond launch / availability. This makes it somewhat difficult to assess implementation options by any metric beyond risk to launch and / or possible negative impact to the broader ecosystem. |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | Aspire, CDX746/747, China, Green, VESC_Portfolio, roadmap2023 | 080-VM-FEC | F003071 |  | SYNC+_0115 | New | DCV2 | 2022-05-30 | 2022-06-14 | 2021-10-30 | 2021-12-30 |  |  |  |  | DI | DI | PI | ECDX Lead | Shawn, Lin
FSW-122 | Initiative | FSW-432Personal Vehicle Profile (PPP) - F000102 | Metcalf, Thomas (T.D.) | Personalized and Portable User Profile (PPP) (CDX746/7) | Developing | 2019-05-15 14:11 | Bauer, Justin (J.) | ABS, ACM, APIM_CDC, APIM_CIM, BCM, CVFMA, DDM, DSM, DSP, ECG, FordPass_App, IPMA (ADAS), LincolnWay, PDM, PPP FI, RCCM, SCA-CAP, SCCM, SCMB, SCMG, SCMH, TCU | "PPP - F002032 Rocket Setup - F002470 BLE Autopair - F002491 Autosave - F002830" | 2022-11-29 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | 2022PriorityWorkshopSubmission, Aspire, CDX746/747, China, ECG, Green, NO_KEYFOB, SInitTopListProductSuite, VCSEDashboard, roadmap2023 | 105-VM-J1 | "PPP - F002032 Rocket Setup - F002470 BLE Autopair - F002491 Autosave - F002830" |  | SYNC+_0166 | C/O | DCV3 | 2022-07-11 | 2022-07-26 | 2021-11-30 | 2022-01-11 | [5 empty] | DI | DI |  | Xu, Andy (X.) <xxu71@ford.com>
Generated at Sun Sep 12 22:16:06 EDT 2021 by Li, Qiyang (Q.) using Jira 8.13.8#813008-sha1:0e9b72fb99b51299615816b8dfb60d79baa93322.
Formulas:
Release data to REC = VLOOKUP(U:U,'[1]Feature Implementation Plan'!$A:$AT,46,0)
Release Date to FO/CAF(2weeks) = VLOOKUP(U:U,'[1]Feature Implementation Plan'!$A:$AU,47,0)
Note on Y96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need FO support clarify the requirement.
Note on Y97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: R&R should further study between inhouse & YFVE.
Note on Y101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potential pull ahead this feature to DCV0.

## Issue Summary (hidden)
Pasha, Aamir (A.) | Chen, James (J.) | Huang, Xue (X.) | IPC | Li, Daisy (Y.P.)
10 | 3 | 1 | 1 | 13

## Summary (hidden)
Cluster | No Spec | Further Spec Clarification
11 | 10 | 76