## Read Me
Template Information
| Template Name | FoC Supplier SW Report Template
| Version | R003
| Author | yjian
| Release Date | 2020-03-17
How to Use
Supplier will need to complete this report based on supplier SW internal plan and Ford SW release schedule
Supplier will be responsbile to update this document when Ford SW release schedule updated
Supplier SW release cadence can be named based on supplier's input
Any change of this document after accepted by Ford need to be reviewed with Ford D&R and SW team
TPB and TP3 are only available for underbody modules
Yellow font in Software Development Plan is only showed as examples, supplier should input based on actual module information
Please contact YJIAN @ford.com for template questions.

## Software Development Plan
Supplier SW Development Plan
Module Support Functions |  |  | Feature Function Spec Version ( HUD Software is part of CDC software in QNX driver, SPEC bellows as reference only) | Funtion Handshake Date | SW Implementation Status
[6 empty] | 2021-01-13 | 2021-02-24 | 2021-03-17 | 2021-05-05 | 2021-06-09 | 2021-07-07 | 2021-08-04 | 2021-08-31 | 2021-11-03 | 2021-12-22
Supplier SW release cadence
[6 empty] | ） | B02 | B03 | B04 | C01 | C02 | D01 | … | … | …
Ford SW Release Cadence
[6 empty] | DCV Beta | DCV 0 | DCV 1 | DCV 2 | DCV 3 | R00 | R04 | R05 | R06 | R07
Basic Funtions
Diagnostics through LVDS |  |  | Generic Global Diagnostic Specification -- GGDS-00.06.15.001-005 ECU Configuration Specification -- ECUConfigSpec-00.06.15.003-004 Diagnostic Fault Coverage and DTC Numbers Design Consideration -- DiagFaultCovAndDTCNmbrsDesignConsid_00.06.15.601-003 Software Download Specification -- SWDL-00.06.15.002-007 Data Compression and Encryption Specification -- DataCompressionEncryption-00.06.15.005-003
Module Funtions
BT Phone HUD SPSS |  |  | BT Phone HUD Imp Guide v1.2 Jul 7, 2015 BT Phone HUD SPSS v1.2 Jul 7, 2015
Global Clock Strategy Specification |  |  | Global Clock Strategy Specification Ver 1.7
NAV Repeater HUD SPSS |  |  | NAV Repeater HUD Imp Guide v1.1 Aug 20 2015 NAV Repeater HUD SPSS v1.1 Aug 20 2015 NAV Repeater V2 HUD Imp Guide v1.1 Aug 20 2015 NAV Repeater V2 HUD SPSS v1.1 Aug 20 2015 | bar: DCV 2
HUD_Speedometer Gauge Digital |  |  | HUD_Speedometer Gauge Digital - CGEA1.3_v1.3
HMI handling |  |  | HUD_HMI_Handling_CGEA1.3_v1.17
Engineering test mode ETM function |  |  | Engineering Test Mode ETM Function-CGE1.3_v1.137 | bar: DCV 2 to DCV 3
ACC Cluster Interface Specification |  |  | ACC Cluster Interface Specification - ver28p3 - 20190712 | bar: DCV 2
CGEA13 PCA Cluster Interface Specification |  |  | CGEA13 PCA Cluster Interface Specification - ver 027 - 20180802
HUD Image Adjustment Function |  |  | HUD Image Adjustment Function -CGE1.3_v2.1
HUD_Adjustable Speed Limiter Device (with Optional Intelligent Speed Assistance) |  |  | HUD_Adjustable Speed Limiter Device (with Optional Intelligent Speed Assistance) - CGEA1.3_v1.5
HUD_Blind Spot Alert and Cross Traffic Alert |  |  | HUD_Blind Spot Alert and Cross Traffic Alert -CGEA1.3_v1.2
HUD_Display Language Selection |  |  | HUD_Display Language Selection - CGEA1.3_v1.1
HUD_Display Unit Selection |  |  | HUD_Display Unit Selection - CGEA1.3_v1.1
HUD_Distance to Empty Function |  |  | HUD_Distance to Empty Function - CGEA1.3_v1.2
HUD_Highway Assist FNV2 |  |  | HUD_Highway Assist FNV2_v1.2 | bar: DCV 2
HUD_Image_Brightness_Function |  |  | HUD_Image_Brightness_Function_CGEA1.3_v1.12
HUD_Memory_Save_and_Recall |  |  | HUD_Memory_Save_and_Recall_CGEA1.3_v1.11 HUD_Memory_Save_and_Recall - CGEA1.3_v1.12 | bar: DCV 2
HUD_Outside Air Temp Function |  |  | HUD_Outside Air Temp Function - CGEA1.3_v1.1
HUD_Showroom Mode |  |  | HUD_Showroom Mode - CGEA1.3 | bar: DCV 2 to DCV 3
HUD_Speed_Limit_Function |  |  | HUD_Speed_Limit_Function_CGEA1.3_v1.3
Lane Keeping System |  |  | Lane Keeping System - CGEA1.3 v2.1 | bar: DCV 2
HUD_Traffic_Sign Recognition |  |  | HUD_Traffic_Sign Recognition_FNV2_v1.1 | bar: DCV 2
HUD_Gear_Shift_Control_Mirror |  |  | HUD_Gear_Shift_Control_Mirror_CGEA1.3_v1.6
HUD_Infotatinment_QuickActionButton_Control_Mirror |  |  | HUD_Infotatinment_QuickActionButton_Control_Mirror - CGEA1.3_v1.3 HUD_Infotainment_QuickActionButton_Control_Mirror_v1.4
HUD_Left_Turn_Right_Turn_Hazard_Signal_Telltale |  |  | HUD_Left_Turn_Right_Turn_Hazard_Signal_Telltale_CGEA1.3_v1.2
HUD_Welcome_Goodbye_Strategy |  |  | HUD_Welcome_Goodbye_Strategy_-_CGEA1.3_v1.15 | bar: DCV 2
HUD_Operational Modes and Voltage Range Strategies |  |  | HUD_Operational Modes and Voltage Range Strategies - CGEA1.3_v1.3 Power Management HUD Imp Guide v1.0 JuL 25 2014 Power Management HUD SPSS v1.0 JuL 25 2014
HUD_V2I | bar: DCV 2
Over/Under temperature protection |  |  | HUD SDR v1.4 6July2020
Calibrations
HUD wraping |  |  | TBD( need co-work with HUD supplier)
Display and HUD MCU software update through LVDS |  |  | TBD( need co-work with HUD/display supplier)
AR content(from Baidu App) integration |  |  | TBD( need co-work with Baidu)
20% | Not implemented | Few or no functions are implemented. This stage can not perform any functional testing.
50% | Partially implemented | Unit development. There are some functions of SW module completed. Functional test cannot be performed at this stage.
70% | Largely implemented | Unit development completed and entering the integration stage. Some features can be presented but unable to perform a functional testing.
INI | Intial | Full functionality SW implemented without verification on component level
DI | Design Intent | Coding of Feature complete and per feature deployment feature verification performed by Supplier on component level.
PI | Production Intent | Feature fully verified as per deployment on component level by Suppliers DV. Feature is subject to system level verification test. Base technologies (Network Mangement, Diagnostic incl. Part1 &2, etc.) verified per component by suppliers.
PR | Production Ready | DV complete for the feature and signed off by feature owner. Final Diagnostic Part 1 and Part 2 DV Test Report (100% passed)

## Software Release Plan
Supplier SW Release Plan
Release Part number Information |  | TPB | TP3 | DCV Beta | DCV0 | DCV1 | DCV2 | DCV3 | R00 | R04 | R05 | R06 | R07
Planned Release Date |  |  |  | 2020-12-11 | 2021-01-13 | 2021-03-12 | 2021-04-28 | 2021-06-09 | 2021-07-14 | 2021-09-01 | 2021-09-28 | 2021-10-27 | 2021-12-22
Delivery Assembly | 0xF113
Core Assembly | 0xF111
Strategy | 0xF188
Calibration | 0xF124
Configuration | 0xF10A
Secondary Bootloader
Part II | 0xF110
Signal Configuration | 0xF108