## Feature QA list
CDX747 Feature Issue List @0915
New Feature ID | VSEM ID | Feature_Name | Lead Team | Local Feature Owner | Global Feature Owner | CDX707 | U265MCA | issue requester | Assignee(Read SPEC and Support Issue Clarification) | Issue description | Create date | Priority | Issue status | Due data | SW release version | Remark
SYNC+_0123 |  | 保养及在线预约 OSB - Online Service Booking | ECDX |  |  | On hold | On hold | Baidu-Liumiao | Su, Lei (L.) | CDX788未澄清，需要FO澄清 |  | IG | open | 24/9 |  | Quote
SYNC+_0138 |  | 车机相册 IVI Picture Gallery | ECDX |  |  | Y-OTA | Y | Baidu-Liumiao | Su, Lei (L.) | 需要FO澄清 |  | IG | open | 24/10 |  | Quote
SYNC+_0207 |  | HUD信息显示EESE/IVI info showed in HUD | EESE |  |  | N | Y | Baidu-Liumiao | Chen, James (J.) | 需要FO澄清 2021/09/23 Xia xiaojin：正常显示来电人信息， 显示导航turn by turn 的信息和路名 |  | IG | open | 24/11 |  | Quote
SYNC+_0149 |  | 路书 (App -去兜风) Project Aspire_Route 66 / Tourist Mode (Education and Historical POIs)_CN (Route 66/Travel Book) | ECDX |  |  |  |  | Baidu-Liumiao | Su, Lei (L.) | 跟ECDX对接中，建议在明确方案前这个工时不包含此功能， |  | IG | open | 24/12 |  | Quote
SYNC+_0162 |  | 家车互联Project Aspire_General IOT (Smart Home)_CN ( Home to Vehicle) | ECDX |  |  |  |  | Baidu-Liumiao | Su, Lei (L.) | 目前747/788都为Onhold状态，是否保持一致 |  | IG | open | 24/13 |  | Quote
SYNC+_0166 | F002032 Rocket Setup - F002470 BLE Autopair - F002491 Autosave - F002830" | 基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP) | ECDX |  |  |  |  | Baidu-Liumiao | Su, Lei (L.) | 2021/9/11 Liumiao ：follow当前PPP策略 |  | IG | open | 24/14 |  | Quote
SYNC+_0183 |  | 27寸横屏 (可触摸）27' Landscape | EESE |  |  |  |  | Baidu-Liumiao | Chen, James (J.) | 2021/9/11 Liumiao 沿用CD542H HMI设计； 20210923_Xia Xiaojin:此条将来会删除。对应的HMI 设计变更会包含在各个feature change description（详细HMI 设计以HMI eSOW 为准。 |  | IG | open | 24/15 |  | Quote
SYNC+_0192 |  | 联合驾趣 Co-Driver | HMI |  |  |  |  | Baidu-Liumiao | Chen, James (J.) | 2021/9/11 Liumiaofollow CD542H设计； 2021/09/23 Xia xiaojin：HMI 反馈目前C/O 542逻辑设计 |  | IG | open | 24/16 |  | Quote
SYNC+_0203 |  | 27寸主副驾屏幕区域交互模式 27" HMI 3 Modes 独自 (Solo)；合作驾驶 （Co-pilot)；独立（individual) Provide Enhaned Passenger Experience. | HMI |  |  |  |  | Baidu-Liumiao | Chen, James (J.) | 2021/9/11 Liumiao ：follow CD542H设计规范 2021/09/23 Xia xiaojin：HMI 反馈目前C/O 542逻辑设计 |  | IG | open | 24/17 |  | Quote

## Detail SW Maturity
FORD JIRA | [19 empty] | 747 IVI FIP China | [6 empty] | Pre condition & Enablers |  | SW Maturity | [6 empty] | Comment | Local FO for 707
Displaying 97 issues at 12/Sep/21 10:16 PM.
Key | Issue Type | Parent Link | Reporter | Summary | Status | Created | Assignee | Component/s | Source Requirement ID | Target end | Resolution | Executive Summary | Epic Link | Level of Change | Change start date | Lead Vehicle Program | Vehicle Program | Labels | GPDS Milestone | Source Requirement ID | remark | New feature ID | CDX747 | CDX747 release version in GPDS | Release data to REC | Release Date to FO/CAF(2weeks) | Spec Clarification | UI sign off | FDJ DCV Beta INI/DI 2022/01/06 | FDJ DCV Beta1 INI/DI 2022/02/28 | DCV BB DCV0 DI 2022/03/30 | DCV MRD DCV1 DI 2022/04/30 | DCV DCV2 PI 2022/06/14 | DCV DCV3 PI 2022/07/25 | PEC R00 PI 2022/09/15
FSW-8846 | Initiative | FSW-3888Plug in Charging (PIC) | Deddeh, Tony (T.) | Plug In Charging (PIC) (CDX746/7) | Developing | 2021-08-16 12:39 | Barkah, David (D.) | APIM_CDC, APIM_CIM, BCCM, BCM, BECM, EVCM, HPCM | F000818 |  | Unresolved | 1. Boundary Diagram uploaded to VSEM (Yes). 2. Level of Change Analysis form uploaded to Feature Program Sharepoint (Yes). |  | Carryover from another program |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747 | 080-VM-FEC | F000818 |  | SYNC+_Z1016 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | ECDX Lead, no spec need check with FO | 0
FSW-8845 | Initiative | FSW-444EV Charge Programming | Borgaonkar, Pankaj (P.) | EV Charge Programming (CDX746/7) | Developing | 2021-08-16 12:39 | Castrejon, Felipe (F.) | APIM_CDC, APIM_CIM, ECG, HPCM, TCU | F005350 |  | Unresolved | 1. Boundary Diagram uploaded to VSEM (Yes). 2. Level of Change Analysis form uploaded to Feature Program Sharepoint (Yes). |  | Carryover from another program |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747 | 080-VM-FEC | F005350 |  | SYNC+_Z1017 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | ECDX Lead, no spec need check with FO | 0
FSW-8663 | Initiative | FSW-2465Power Release Door | McInally, Steven (M.) | Power Release Doors (CDX747) | Developing | 2021-08-06 11:27 | Dasari, Kovidha (K.R.) | APIM_CDC, APIM_CIM, BCM, DCME, DCMF, DCMG, DCMH, ECG_Gateway, EVCM, RCM | F000864 |  | Unresolved |  |  | Modified |  | 2021 CX727 | 2024 CDX747 | CDX747 | 080-VM-FEC | F000864 |  | SYNC+_Z1013 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | Spec and feature clarification should be lead by AFO COB 09/30 UI sign off version should be released COB 10/30. | 0
FSW-8545 | Initiative | FSW-4753Drive Control Optimization | Sarracini, Fernando (FSJ.) | Buttonless Push To Start – BEV (CDX746/7) | Developing | 2021-07-22 15:40 | Cristiano, Wander (W. R.) | ABS, APIM_CDC, APIM_CIM, BCM, EVCM, GSM, HPCM | F005310 |  | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO, Green | 080-VM-FEC | F005310 |  | SYNC+_Z1018 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | Spec and feature clarification should be lead by AFO COB 09/30 UI sign off version should be released COB 10/30. | 0
FSW-4969 | Initiative | FSW-2412Tuner AM/FM/HD | Tengler, Dave (D.R.) | Tuner AM/FM/HD (CDX746/7) | Developing | 2021-01-28 12:16 | Murry, Tyrone (T.D.) | ACM, APIM_CDC, APIM_CIM, ECG_Gateway, RACM, TCU | VSEM ID: F000349 |  | Unresolved |  |  | Carryover |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000349 |  | SYNC+_0011 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | Confirm if AM del or not COB 09/30. | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com>
FSW-4755 | Initiative | FSW-4754Steering Wheel Horizon Control | Reppenhagen, Nancy (N.B.) | Steering Horizon Control (CDX746/7) | Developing | 2021-01-19 23:03 | Li, Richard (R.Y.) | APIM_CDC, APIM_CIM, ECG_Gateway, SCCM, SIMA | VSEM ID: F004711 |  | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, U717/718 | 080-VM-FEC | F004711 |  | SYNC+_Z0290 | Minor | DCV2 | 2022-05-30 | 2022-06-14 | [6 empty] | DI | DI | PI | Late requirement in CDX707/CDX747 | Zhu, Jing Yuan (J.) <JZHU65@ford.com>
FSW-4752 | Initiative | FSW-4753Drive Control Optimization | Waszczenko, Lisa (L.M.) | Drive Control Optimization (CDX746/7) | Open | 2021-01-19 23:00 | Lin, Hua (H.) | ABS, APIM_CDC, APIM_CIM, BCM, DDM, DSM, EVCM, GSM, HPCM, PDM, SCMC, SCMD, SCMG, SCMH | DCO: F004530/A Buttonless Start: F005310 | 2022-06-30 | Unresolved |  |  | New |  | 2024 CDX747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO |  | DCO: F004530/A Buttonless Start: F005310 |  | DCO: SYNC+_Z0286 BEV: SYNC+_Z1018 | N | DCO: DCV0 BEV: DCV Beta1 | DCO: 3/16/2022 BEV: 2/16/2022 | DCO: 3/30/2022 BEV: - | 2021-09-30 | 2021-10-30 | NA | [6 empty] | can't see in feature, should delete | #N/A
FSW-4476 | Initiative | FSW-657Park Aid | Nasser, Ebrahim (E.) | Base Park Aid (CDX746/7) | Developing | 2021-01-06 22:13 | Al-Zaher, Sarya (S.) | APIM_CDC, APIM_CIM, BCM, EVCM, IPMA (ADAS) | F003631 |  | Unresolved |  |  | Carryover |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003631 |  | SYNC+_0091 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | DI | DI | PI | PI | PI | Suppose C.O CDX707, further confirm with AFO needed. | Li, Xin (X.) <xli268@ford.com>
FSW-4427 | Initiative | FSW-2078Digital Scent | Schneider, Don (D.P.) | Digital Scent (China) (CDX746/7) | Developing | 2020-12-17 14:35 | Malainy, Mark (S.) | APIM_CIM, RCCM | VSEM ID: F004410 |  | Unresolved |  |  | Carryover |  | 2023 CDX707 | 2024 CDX747 | CDX747, China, Green | 080-VM-FEC | F004410 |  | SYNC+_0134 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Chen, Minghui (M.) <MCHEN122@ford.com>
FSW-4426 | Initiative | FSW-1870Auto Air Refresh | Schneider, Don (D.P.) | Auto Air Refresh (AAR) for CHINA Markets (CDX746/7) | Developing | 2020-12-17 14:34 | Hasan, SM Fairus (S.) | APIM_CIM, RACM, RCCM |  |  | Unresolved |  |  | Carryover |  |  | 2024 CDX747 | CDX747, China | 080-VM-FEC |  |  | SYNC+_0132 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Shi, Stella (J.) <jshi32@ford.com>
FSW-4425 | Initiative | FSW-494Fob Free Entry and Ignition (NFC) - F002070 | Trupiano, Rita (M.P.) | Fob Free Entry and Ignition (NFC) (CDX746/7 (GE2)) | Developing | 2020-12-17 14:33 | Sepulveda, Reinaldo (R. R.) | APIM_CDC, APIM_CIM, BCM, RFA | VSEM ID: F002070 |  | Unresolved |  |  | Modified |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO, Green, J1, NFC, UWB | 080-VM-FEC | F002070 |  | SYNC+_Z1010 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-10-30 |  |  | DI | DI | PI | PI | PI | vendors need confirm detail spec with AFO then can confirm IVI HIM/GUI work | 0
FSW-4423 | Initiative | FSW-2603Power Central Lock Suite | Muneratto, Daniel (D.M.) | Power Central Lock Suite (CDX746/7) | Developing | 2020-12-17 14:21 | Silva, Nivea (N.B.) | APIM_CDC, APIM_CIM, BCM, DCME, DCMF, DCMG, DCMH, DDM, PDM, RGTM, TCU | F004255 |  | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO, Yellow | 080-VM-FEC | F004255 | F004256 F002951 F004255 Lock Setting | SYNC+_Z0187 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-4422 | Initiative | FSW-2695Automatic Lock Suite | Muneratto, Daniel (D.M.) | Automatic Lock Suite (CDX746/7) | Developing | 2020-12-17 14:20 | SOUZA, GABRIELLE DESIREE (G.C.) | APIM_CDC, APIM_CIM, BCM, DDM, ECG_Gateway, PDM, RCM | F004256 |  | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Yellow | 080-VM-FEC | F004256 | F004256 F002951 F004255 Lock Setting | SYNC+_Z0187 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-3155 | Initiative | FSW-365Active Park Assist - FG | Nasser, Ebrahim (E.) | Active Park Assist (CDX746/7) | Developing | 2020-10-14 13:17 | Rashidzadeh, Hejir (H.) | ABS, APIM_CDC, APIM_CIM, EVCM, GSM, PSCM | VSEM ID F000280 |  | Unresolved |  |  | Carryover |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F000280 |  | SYNC+_0073 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | INI | DI | DI | PI | PI | #N/A | He, Michael (X.) <xhe22@ford.com>
FSW-2910 | Initiative | FSW-770Blind Spot Information System (BLIS) - F000564 | Nasser, Ebrahim (E.) | Blind Spot Information System (BLIS) (CDX746/7) | Developing | 2020-10-06 16:23 | Crosby, Michael (M.C.) | APIM_CDC, APIM_CIM, BCM, DDM, EVCM, IPMA (ADAS), SODX | F000564 |  | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F000564 |  | SYNC+_Z1002 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Liu, Hongxin (H.) <HLIU162@ford.com>
FSW-2908 | Initiative | FSW-2122Programmable Electric Preconditioning and Charging (PEPC) | Oliveira, Eude (E.O.) | Programmable Electric Preconditioning and Charging (PEPC) (CDX746/7) | Developing | 2020-10-06 15:49 | Andrade, Ana (A.C.) | APIM_CDC, APIM_CIM, BCCM, BECM, EVCM, HPCM, TCU | F000816 | 2022-09-09 | Unresolved |  |  | Modified |  | 2022 P702 BEV | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000816 |  | SYNC+_0208 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | ECDX Lead | Yang, Jessica (Yu.) <yyang158@ford.com>
FSW-2604 | Initiative | FSW-464Mobile Device Viewer for Vehicle Cameras (MDVVC) | Chapekis, Steven (S.A.) | Mobile Device Viewer for Vehicle Cameras (CDX746/7) | Developing | 2020-09-17 08:31 | Moreno Bautista, Ariana (A.) | APCA, APIM_CDC, APIM_CIM, AUX, BCM, Cabin, Cargo, CCS, CHMSL, Consent, CSS, CVFMA, ECG, FordPass_App, Front Camera, IPMA (ADAS), Left Side Camera, MDVC FI, PDB, Rear Camera, Right Side Camera, SSP, TCU, Threat Model, TMC, VCS | Source Requirement ID | 2022-11-23 | Unresolved | The MDVVC (Mobile Device Viewer for Vehicle Cameras) feature is a key-off feature that allows the customer to stream live video feed from the vehicle camera to a mobile device (through FordPass app) to allow remote monitoring of a vehicle. FordPass allows the user to select specific vehicle camera views from a set of available. |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, RoadMapExclusion | 080-VM-FEC | F002812 |  | SYNC+_0231 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | No spec | Shi, Stella (J.) <jshi32@ford.com>
FSW-2577 | Initiative | FSW-2127Surround View Cameras | Nasser, Ahmad (A.M.) | Surround View Cameras (CDX746/7) | Developing | 2020-09-10 10:50 | Salcido-zarco, Alejandro (A.) | APIM_CDC, APIM_CIM, IPMA (ADAS) | F003515 | 2022-11-23 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003515 |  | SYNC+_0089 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xin (X.) <xli268@ford.com>
FSW-2576 | Initiative | FSW-1137IP and Switch Illumination (Smooth Dimming) | Freitas, Bruno (B.G.) | Smooth Dimming (CDX746/7) | Developing | 2020-09-10 10:48 | Martinez, João Victor (J.F.) | APIM_CDC, APIM_CIM, BCM, DDM, ECG_Gateway, GSM, ICP, RCCM, RCM, TCU | VSEM ID F000061 | 2022-11-23 | Unresolved |  |  | Modified |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000061 |  | SYNC+_Z0058 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Qiyang (Q.) <QLI111@ford.com>
FSW-2528 | Initiative | FSW-1439Ambient Lighting | Freitas, Bruno (B.G.) | Ambient Lighting (CDX746/7) | Developing | 2020-09-08 07:52 | Gemade, Ralph (R.) | ALE, APIM_CDC, APIM_CIM, BCM, RACM | VSEM ID F000063/C | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000063/C |  | SYNC+_Z0185 | New | DCV Beta | 2021-12-23 | 2022-01-06 | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-2135 | Initiative | FSW-1225Lane Centering Assist (LCA) | Wegienka, Kevin (K.) | Lane Centering Assist (LCA) (CDX746/7) | Developing | 2020-08-19 11:46 | Nagavally, Rahul Reddy (R.) | APIM_CDC, APIM_CIM, IPMA (ADAS), PSCM | F000742 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000742 |  | SYNC+_Z0281 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Ni, Anthony (H.A.) <hni1@ford.com>
FSW-1861 | Initiative | FSW-1868Driver Focused Mode | Johnston, William (Bill.) | Driver Focused Mode (CDX746/7) | Developing | 2020-08-03 11:16 | Venkatesan, Vinod (V.) | APIM_CDC, APIM_CIM, RCCM | VSEM ID F001212/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001212/A |  | SYNC+_Z0285 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1860 | Initiative | FSW-1863Passenger Aribag Deactivation | Appukutty, Jayagopal (J.) | Passenger Airbag Deactivation (CDX746/7) | Developing | 2020-08-03 11:16 | Dsouza, Aston (.) | APIM_CDC, APIM_CIM, OCS, RCM | F002214/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F002214/A |  | SYNC+_Z0296 | New | TBD | 2022-03-16 | 2022-03-30 |  |  |  | DI | [6 empty] | 0
FSW-1858 | Initiative | FSW-1865Integrated Dash Camera | Mahmood, Hamid (H.) | Integrated Dash Camera (CDX746/7) | Developing | 2020-08-03 11:16 | Eteer, Malik (M.) | APIM_CDC, APIM_CIM, ARM, ECG | VSEM ID F003751 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | 2022PriorityWorkshopSubmission, CDX746/747, China, RoadMapExclusion, confirm-containability, roadmap2023 | 080-VM-FEC | F003751 |  | SYNC+_Z0263 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI |  | 0
FSW-1857 | Initiative | FSW-1869EM Register | Johnston, William (Bill.) | Electro Mechanical (EM) Register (CDX746/7) | Developing | 2020-08-03 11:16 | Vandenbrink, Terry (T.) | APIM_CDC, APIM_CIM, RCCM | VSEM ID F003951 |  | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | 2022PriorityWorkshopSubmission, CDX746/747, China, confirm-containability, roadmap2023 | 080-VM-FEC | F003951 |  | SYNC+_0264 | Minor | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | currently no CDX747 FO for this feature, need FO support | Wang, Wei (W.) <wwang199@ford.com>
FSW-1849 | Initiative | FSW-1475Power Folding Mirrors (Lock/Unlock) | Zuraw, Timothy (T.) | Power Folding Mirrors (CDX746/7) | Developing | 2020-08-03 11:16 | Strzelczyk, Anthony (A.) | APIM_CDC, APIM_CIM, DDM, PDM | F000148/D | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000148/D |  | SYNC+_Z0256 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1846 | Initiative | FSW-1452Position/Parking Light | Neves, Adriana Duarte (A.D.) | Parking Light / Position Light (CDX746/7) | Developing | 2020-08-03 11:16 | Costa, Marcelo (M.N.) | APIM_CDC, APIM_CIM, BCM, LDM | F001012/B | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Red | 080-VM-FEC | F001012/B |  | SYNC+_Z0257 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | no spec | 0
FSW-1845 | Initiative | FSW-1451Manual Low Beam | Neves, Adriana Duarte (A.D.) | Low Beam (CDX746/7) | Developing | 2020-08-03 11:16 | Mattos, Andre Licurgo (A.L.) | APIM_CDC, APIM_CIM, BCM, HCM, LDM, SCCM | F000998 | 2022-11-14 | Unresolved |  |  | Modified |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Red | 080-VM-FEC | F000998 |  | SYNC+_Z0258 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI | no spec | 0
FSW-1844 | Initiative | FSW-1443Map/Dome Lighting (Manual Interior Lighting) | Freitas, Bruno (B.G.) | Overhead Lighting (CDX746/7) | Developing | 2020-08-03 11:16 | Santana, Gabriel (G.D.) | ABS, APIM_CDC, APIM_CIM, BCM, ECG_Gateway, HCM, PDB | F000058/D | 2022-11-14 | Unresolved |  |  | Modified |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000058/D | F000058/C Map/Dome Lights (RSD - Manual Interior Lighting) | SYNC+_Z0259 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1842 | Initiative | FSW-1446Fog Light - F001010 | Meffe, Eloy (J.) | Rear Fog Lights (CDX746/7) | Developing | 2020-08-03 11:16 | Suzart, Joyce (J.) | APIM_CDC, APIM_CIM, BCM | F001010 | 2022-11-14 | Unresolved |  |  | Modified |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001010 | F001010/B Rear Fog Lights | SYNC+_Z0291 | N | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 | NA | [6 empty] | IPC function | 0
FSW-1837 | Initiative | FSW-660Pre-Collision Assist (PCA) | Seiler, Rebecca (R.L.) | Pre-Collision Assist (CDX746/7) | Developing | 2020-08-03 11:16 | Gelan, Ibrahim (I.S.) | ABS, APIM_CDC, APIM_CIM, BCM, EVCM, TCU | F004999 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F004999 |  | SYNC+_Z0091 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Zhu, Jinpeng (J.) <jzhu85@ford.com>
FSW-1836 | Initiative | FSW-1473Lane Keeping System | Sorgenfrei, Birgit (B.L.) | Lane Keeping System (CDX746/7) | Developing | 2020-08-03 11:16 | Patil, Pranav (P.) | APIM_CDC, APIM_CIM, IPMA (ADAS), PSCM | VSEM ID vFG000456/ vFG000284/ vFG000668/ vFG002069/ | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | VSEM ID vFG000456/ vFG000284/ vFG000668/ vFG002069/ |  | SYNC+_Z0227 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Zhang, Wayne (W.R.) <wzhan114@ford.com>
FSW-1835 | Initiative | FSW-1223Driver Alert System | Sorgenfrei, Birgit (B.L.) | Driver Alert System (CDX746/7) | Developing | 2020-08-03 11:16 | Uptain, Charles (C.E.) | APIM_CDC, APIM_CIM, BCM, EVCM, IPMA (ADAS) | VSEM ID F000285/B | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000285/B |  | SYNC+_Z0229 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Song, Amy (S.) <ssong18@ford.com>
FSW-1834 | Initiative | FSW-504Intelligent Adaptive Cruise Control | Abinoja, Eddie (E.O.) | Intelligent Adaptive Cruise Control (iACC) (CDX746/7) | Developing | 2020-08-03 11:16 | Sarkar, Animesh (A.) | APIM_CDC, APIM_CIM, IPMA (ADAS) | VSEM ID VF004044 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | VF004044 | VF004044 F000910 F000911 F000912 Cruise Control Setting | SYNC+_Z0075 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Cui, Victor (M.) <mcui5@ford.com>
FSW-1833 | Initiative | FSW-639Reverse Brake Assist | Nasser, Ebrahim (E.) | Reverse Brake Assist (CDX746/7) | Developing | 2020-08-03 11:16 | Cheng, Samuel (S.) | ABS, APIM_CDC, APIM_CIM, IPMA (ADAS) | F001330 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F001330 |  | SYNC+_0074 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Yifan (Y.) <YLI381@ford.com>
FSW-1832 | Initiative | FSW-658Cross Traffic Alert (CTA) | Nasser, Ebrahim (E.) | Cross Traffic Alert with Braking (CDX746/7) | Developing | 2020-08-03 11:16 | Rossi, Antonio (A. R.) | ABS, APIM_CDC, APIM_CIM, BCM, DDM, EVCM, IPMA (ADAS), PDM, SODX | VSEM ID F000565 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000565 |  | SYNC+_0098 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Liu, Hongxin (H.) <HLIU162@ford.com>
FSW-1831 | Initiative | FSW-659Evasive Steering Assist | Mattern, Don (D.) | Evasive Steer Assist (CDX746/7) | Developing | 2020-08-03 11:16 | Wang, Haisu (H.) | ABS, APIM_CDC, APIM_CIM, IPMA (ADAS), PSCM | VSEM ID F000513 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 S650 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000513 | Pre Collision Assist 同F004999 | SYNC+_Z0091 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Zhu, Jinpeng (J.) <jzhu85@ford.com>
FSW-1830 | Initiative | FSW-2526Blind Spot Assist | Abinoja, Eddie (E.O.) | Blind Spot Assist (CDX746/7) | Developing | 2020-08-03 11:16 | McWilliams, John (J.S.) | APIM_CDC, APIM_CIM, DDM, IPMA (ADAS), PDM, PSCM | VSEM ID F001451/C | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001451/C |  | SYNC+_Z1011 | N | 0 | 0 | 0 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | 0
FSW-1829 | Initiative | FSW-2091Enhanced Active Driver Assist | Wegienka, Kevin (K.) | Active Drive Assist 1.2 (CDX746/7) | Developing | 2020-08-03 11:16 | Gotadki, Shruti (S. P.) | APIM_CDC, APIM_CIM, CMR, IPMA (ADAS), PSCM | FO to confirm VSEM ID | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 CX483 MCA | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | FO to confirm VSEM ID |  | SYNC+_Z0230 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | No spec | Ni, Anthony (H.A.) <hni1@ford.com>
FSW-1828 | Initiative | FSW-375Remote Park Assist (RePA) | Nasser, Ebrahim (E.) | Remote Park Assist (RePA) 2024 CDX746/7 | Developing | 2020-08-03 11:16 | Rashidzadeh, Hejir (H.) | ABS, APIM_CDC, APIM_CIM, BCM, ECG_Gateway, EVCM, FordPass_App, GSM, IPMA (ADAS), LincolnWay, PSCM, RFA | F002930 | 2022-11-14 | Unresolved |  |  | New |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | Applications, CDX746/747, China, DCO, NO_KEYFOB | 090-PG-TT | F002930 |  | SYNC+_0076 | C/O | DCV3 | 2022-07-11 | 2022-07-26 | [7 empty] | DI | DI | No spec | He, Michael (X.) <xhe22@ford.com>
FSW-1825 | Initiative | FSW-407Phone As A Key & Backup Starting Passcode (PaaK & BSP) | Considine, Susan (S.) | Phone as a Key (PaaK) "BUN" w/o Keyfob 2024 CDX746/7 | Developing | 2020-08-03 11:16 | Hamel, Jeffrey (J.) | APIM_CDC, APIM_CIM, BCM, ECG, FordPass_App, LincolnWay, RFA, TCU | F001670/A | 2022-11-14 | Unresolved |  |  | Modified |  | 2022 U540N | 2024 CDX746, 2024 CDX747 | BCM, CDX746/747, CSTF, China, FNV3, J1, NFC, NO_KEYFOB, PaaK, PaaKBSP | 080-VM-FEC | F001670/A | 同F001372 | SYNC+_0106 | C/O | DCV Beta1 | 2022-02-16 | - |  |  |  | DI | DI | DI | DI | PI | PI | #N/A | Chen, chiefer
FSW-1822 | Initiative | FSW-443Plug and Charge | Kumar, Salaj (S.) | Plug and Charge (24 CDX746/7) | Developing | 2020-08-03 11:16 | Jujavarapu, Sandeep (S.) | APIM_CDC, APIM_CIM, ECG, OBCC, TCU | F002430 | 2023-04-11 | Unresolved |  |  | Carryover |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, EC-FO, HMPC | 080-VM-FEC | F002430 |  | SYNC+_Z1012 | New | TBD | 2022-03-16 | 2022-03-30 |  |  |  | DI | [5 empty] | spec received by qiyang | Wang, Yixuan (Vovo) <ywang219@ford.com>
FSW-1820 | Initiative | FSW-1173First Row Seat Position Control | Olsen, Bill (W.J.) | First Row Seat Position Control (CDX746/7) | Developing | 2020-08-03 11:16 | Aguilar, Diana (D.S.) | APIM_CDC, APIM_CIM, DSM, ECG_Gateway, RACM, SCMB, SCMK, SCML | VSEM ID F003516 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | 5D, CDX746/747, China, Yellow | 080-VM-FEC | F003516 |  | SYNC+_Z0287 | C/O | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | #N/A | Du, Hao (H.) <HDU9@ford.com>
FSW-1818 | Initiative | FSW-2394Seat Temperature Control | Olsen, Bill (W.J.) | Seat Temperature Control (CDX746/7) | Developing | 2020-08-03 11:16 | Mlynarczyk, Stephanie (S.A.) | APIM_CDC, APIM_CIM, DSM, RACM, RCCM, TCU | F003518 | 2022-11-14 | Unresolved |  |  | Modified |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003518 | 2 new feature ID, SYNC+_Z0167: Front Row Seat Heated，SYNC+_Z0168: Front Seat Vent | SYNC+_Z0167 SYNC+_Z0168 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | #N/A
FSW-1817 | Initiative | FSW-388Multi-Contour Seats | Barreto, Rafael (R.V.) | Multi-Contour Seat (CDX746/7) | Developing | 2020-08-03 11:16 | Santos, Roger (R.M.) | APIM_CDC, APIM_CIM, BCM, DSM, RACM, SCMC, SCMD, SCMG, SCMH | F000158 | 2022-11-14 | Unresolved |  |  | Modified |  | Not Listed | 2024 CDX747 | CDX747, China, DCO | 080-VM-FEC | F000158 |  | SYNC+_Z0088 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | No spec | Du, Hao (H.) <hdu9@ford.com>
FSW-1816 | Initiative | FSW-2149Power Open/Close Liftgate | Holub, Patrick (P.K.) | Power Liftgate (CDX746/7) | Developing | 2020-08-03 11:16 | Gunaratnam, Raj (M.) | APIM_CDC, APIM_CIM, BCM, RGTM | F000162/D | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000162/D | can't match F000162 --> rear liftgate F000165/D --> power liftgate SW switch | SYNC+_Z0212 SYNC+_Z0293 | C/O | DCV Beta DCV Beta1 | 12/23/2021 2/16/2022 | 1/6/2022 '- |  |  |  | DI | DI | DI | PI | PI | PI | #N/A | #N/A
FSW-1813 | Initiative | FSW-2444Front Automatic Wiping | Yousif, Meisam (M.L.) | Front Automatic Wiping (CDX746/7) | New | 2020-08-03 11:16 | Uttar, Nikhil (N.) | APIM_CDC, APIM_CIM, BCM, SCCM | F000066 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000066 |  | SYNC+_Z0217 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-1811 | Initiative | FSW-456Auto Hold | Mlynarczyk, Scott (S.L.) | Auto Hold (CDX746/7) | Developing | 2020-08-03 11:16 | James, Alex (J.A.) | ABS, APIM_CDC, APIM_CIM | VSEM ID F000097/E | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000097/E | F000097 --> auto vehicle hold | SYNC+_Z0069 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Hesseler, Karl-Peter (Carlo.) <khessele@ford.com>
FSW-1809 | Initiative | FSW-760Automatic High Beam (AHBC/GFHB/ADB) - FNV3 | Sorgenfrei, Birgit (B.L.) | Auto High Beam Controller (CDX746/7) | Developing | 2020-08-03 11:16 | Uptain, Charles (C.E.) | APIM_CDC, APIM_CIM, BCM, HCM, IPMA (ADAS), LDM, SCCM | VSEM ID F004650 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F004650 | F004650（707） F000918(788) 3# Help Me See 视觉辅助 - 自适应远光灯 Auto High beam | SYNC+_Z0231 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Song, Amy (S.) <ssong18@ford.com>
FSW-1805 | Initiative | FSW-2879Tire Pressure Monitoring System | Sarracini, Fernando (FSJ.) | TPMS (CDX746/7) | Developing | 2020-08-03 11:16 | Silva, Tays (T.C.) | APIM_CDC, APIM_CIM, BCM, RTM | F000109/D | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 S650 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000109/D | F000109/D FNG000760 | SYNC+_Z0289 | C/O | DCV Beta1 | 2022-02-16 | - |  |  |  |  | INI | DI | DI | PI | PI | Pending Cluster IOD logic realization | Wang, Vincent (X.) <xwang151@ford.com>
FSW-1804 | Initiative | FSW-652Beltminder | Appukutty, Jayagopal (J.) | Global Beltminder (CDX746/7) | Developing | 2020-08-03 11:16 | Dsouza, Aston (.) | APIM_CDC, APIM_CIM, RCM | F002216/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO | 080-VM-FEC | F002216/A |  | SYNC+_Z1007 | C/O | DCV Beta1 | 2022-02-16 | - |  |  |  | INI | DI | DI | DI | PI | PI | Pending Cluster IOD logic realization | Xu, Xi Hai (X.) <xxu61@ford.com>
FSW-1799 | Initiative | FSW-2106Heated Backlight | Cruz, Mauricio (M.C.) | Heated Backlight (CDX746/7) | Developing | 2020-08-03 11:16 | Mota, Kaique (K.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, PDB, RCCM | VSEM ID F000122/B | 2022-11-29 | Unresolved |  |  | Carryover |  | 2023 CD539 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000122/B |  | SYNC+_Z0247 | C/O | DCV Beta1 | 2022-02-16 | - |  |  | DI | DI | DI | DI | PI | PI | PI | need confirm with FO detail spec and check timing plan | Shi, Song (S.S.) <sshi24@ford.com>
FSW-1798 | Initiative | FSW-2697Exit Warning | Nasser, Ebrahim (E.) | Exit Warning (CDX746/7) | Developing | 2020-08-03 11:16 | Kaur, Gagandeep (G.) | APIM_CDC, APIM_CIM, BCM, DCME, DCMF, DCMG, DCMH, IPMA (ADAS) | VSEM ID F001430/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2024 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001430/A | F001430 | SYNC+_0101 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Liu, Hongxin (H.) <HLIU162@ford.com>
FSW-1794 | Initiative | FSW-2073Core Media Player | Nasrallah, Hussein (H.) | Core Media Player (CDX746/7) | Developing | 2020-08-03 11:16 | Ahmed, Basheer (B.) | APIM_CDC, APIM_CIM, RACM | VSEM ID F000379/G | 2022-11-14 | Unresolved |  |  | Carryover |  | Not Listed | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F000379/G |  | SYNC+_0015 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com>
FSW-1790 | Initiative | FSW-1117Navigation | Chararah, Bilal (B.) | Navigation Systems (CDX746/7) | Developing | 2020-08-03 11:15 | Deaibes, William (W.) | APIM_CDC, APIM_CIM, TCU | F000218/Q | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000218/Q |  | SYNC+_0001 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  |  | INI | DI | DI | DI | PI | PI | Pending on Location service FNV3 technical solution(GNSS in TCU B6) | Yao, Tristan (Lan) <LYAO17@ford.com>
FSW-1789 | Initiative | FSW-1157Traffic Sign Recognition (TSR) | Abinoja, Eddie (E.O.) | Traffic Sign Recognition (CDX746/7) | Developing | 2020-08-03 11:15 | Sarkar, Animesh (A.) | APIM_CDC, APIM_CIM, IPMA (ADAS) | F000913/C | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000913/C |  | SYNC+_Z0097 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Cui, Victor (M.) <mcui5@ford.com>
FSW-1785 | Initiative | FSW-3800CCS - Carline Feature Delivery | Kahlen, Micha (M.) | Customer Connectivity Settings (CDX746/7) | Developing | 2020-08-03 11:15 | Pechlivanidis, Savvas (S.) | APIM_CDC, APIM_CIM, ECG, TCU | VSEM ID F001040/E | 2022-11-14 | Unresolved |  |  | Carryover |  | Not Listed | 2024 CDX746, 2024 CDX747 | CDX746/747, China, RED | 080-VM-FEC | F001040/E |  | SYNC+_Z0032 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Gu, Regina (Q.) <qgu12@ford.com>
FSW-1781 | Initiative | FSW-2139E-Shifter | Awadi, Ahmed (A.) | Range Selection (CDX746/7) | Developing | 2020-08-03 11:15 | Kotha, Mahender (M.) | ABS, APIM_CDC, APIM_CIM, BCM, DCME, ECG_Gateway, EVCM, GSM, HPCM | VSEM ID F000956/C | 2022-11-14 | Unresolved |  |  | Modified |  | Not Listed | 2024 CDX746, 2024 CDX747 | 5D, CDX746/747, China, DCO, YELLOW | 080-VM-FEC | F000956/C | ONLY IMPACT IPC | #N/A | N | #N/A | #N/A | #N/A |  |  | NA | [6 empty] | #N/A | #N/A
FSW-1777 | Initiative | FSW-2107Heated Mirrors | Cruz, Mauricio (M.C.) | Heated Mirrors (CDX746/7) | Developing | 2020-08-03 11:15 | Melo, Isabela (I. P.) | APIM_CDC, APIM_CIM, BCM, DCDC, DDM, ECG_Gateway, EVCM, HPCM, PDM, RCCM | VSEM ID F000800/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2022 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000800/A | F000800 | SYNC+_Z1003 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Xie, Will (W.) <wxie15@ford.com>
FSW-1771 | Initiative | FSW-1170Cellular Remote Start | Drummond, Colin (C.) | Cellular Remote Start w/Extend Remote Start FNV3 (CDX746/7) | Developing | 2020-08-03 11:15 | Syed, Imtiaz (I.S.) | APIM_CDC, APIM_CIM, BCM, ECG, EVCM, RCCM, TCU | VSEM ID: F003410 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003410 |  | SYNC+_Z1019 | New | DCV Beta1 | 2022-02-16 | - |  |  |  | DI | DI | DI | PI | PI | PI | ECDX Lead | 0
FSW-1770 | Initiative | FSW-1171Cellular Schedule Remote Start | Drummond, Colin (C.) | Cellular Scheduled Remote Start (CDX746/7) | Developing | 2020-08-03 11:15 | Syed, Imtiaz (I.S.) | APIM_CDC, APIM_CIM, BCM, ECG, EVCM, TCU | VSEM ID F003411 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F003411 |  | SYNC+_Z1020 | New | DCV Beta1 | 2022-02-16 | - |  |  |  | DI | DI | DI | PI | PI | PI | ECDX Lead | 0
FSW-1763 | Initiative | FSW-1455Turn Indicator Light | Silva, Davi (D.M.) | Turn Indicator (CDX746/7) | Developing | 2020-08-03 11:15 | TEIXEIRA, IGOR (I.) | APIM_CDC, APIM_CIM, BCM, HCM, LDM, SCCM | VSEM ID: F001007 | 2022-11-14 | Unresolved |  |  | Modified |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001007 | ONLY IMPACT IPC | #N/A | N | #N/A | #N/A | #N/A |  |  | NA | [6 empty] | #N/A | #N/A
FSW-1762 | Initiative | FSW-2129Vehicle Health Alert and Status and Vehicle Location | Aekka, Venkat (V.R.) | Vehicle Health Alert and Status, and Vehicle Location (CDX746/7) | Developing | 2020-08-03 11:15 | McKinstry, Roy (R.S.) | APIM_CDC, APIM_CIM, Cloud, ECG, TCU, TMC | VSEM ID: F001048/F | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001048/F |  | SYNC+_0122 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Lu, Chao (C.) <clu42@ford.com>
FSW-1758 | Initiative | FSW-1440Automatic Dynamic Leveling | Neves, Adriana Duarte (A.D.) | Automatic Dynamic Leveling (CDX746/7) | Developing | 2020-08-03 11:15 | Lima, Alexa Larissa (A.d.) | APIM_CDC, APIM_CIM, HCM, LDM, VDM | VSEM ID F001023 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001023 |  | SYNC+_Z0241 | N | 0 | 0 | 0 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | Zhou, Travis (C.X.) <czhou17@ford.com>
FSW-1754 | Initiative | FSW-1084Digital Owner's Manual | Cruse, Christopher (C.D.) | Digital Owner's Manual (CDX746/7) | Developing | 2020-08-03 11:15 | Hari, Srikanth (S.) | APIM_CDC, APIM_CIM, ECG_Gateway, TCU | VSEM ID F002370 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F002370 |  | SYNC+_0117 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | DI | DI | DI | DI | PI | ECDX Lead | Jiang, Wei (W.)
FSW-1753 | Initiative | FSW-2145Frunk | McInally, Steven (M.) | Frunk (CDX746/7) | Developing | 2020-08-03 11:15 | Butler, Jordan (J.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, FHCM, RFA | VSEM ID F002010/B | 2022-10-14 | Unresolved |  |  | Modified |  | 2022 P702 BEV | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F002010/B |  | SYNC+_Z0294 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1751 | Initiative | FSW-2150Hands Free Phone | Al dallal, Alabbas (A.M.) | Handsfree Phone (CDX746/7) | Developing | 2020-08-03 11:15 | Balakrishnan, Sabarish (S.) | APIM_CDC, APIM_CIM | VSEM ID F000345/K | 2022-11-14 | Unresolved |  |  | Carryover |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F000345/K |  | SYNC+_0013 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Xu, Amy (X.) <xyafei@ford.com>
FSW-1750 | Initiative | FSW-1447Hazard Light | Silva, Davi (D.M.) | Hazard Light (CDX746/7) | Developing | 2020-08-03 11:15 | TEIXEIRA, IGOR (I.) | APIM_CDC, APIM_CIM, BCM, LDM | VSEM ID F001009 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2020 U625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001009 |  | SYNC+_Z0244 | N | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 | NA | [6 empty] | IPC function | 0
FSW-1743 | Initiative | FSW-1233Speedometer | Catani, Norberto (N.C.) | Speedometer (CDX746/7) | Developing | 2020-08-03 11:15 | Santiago, Karen (K.T.) | ABS, APIM_CDC, APIM_CIM, BCM, EVCM | F000665/A | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, green | 080-VM-FEC | F000665/A | ONLY IMPACT IPC | #N/A | N | #N/A | #N/A | #N/A |  |  | NA | [6 empty] | #N/A | #N/A
FSW-1741 | Initiative | FSW-212In-Vehicle Software Updates (MMOTA) Capabilities - F001192 | Thorne, Nicholas (N.A.) | In-Vehicle Software Update (CDX746/7) | Developing | 2020-08-03 11:15 | Gudemaranahalli, Rohini Pr (R.) | APIM_CDC, APIM_CIM, BCM, ECG, EVCM, TCU | VSEM ID F001192/C | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F001192/C |  | SYNC+_0221 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | DI | DI | DI | DI | PI | ECDX Lead | Wang, Jennifer (J.) <jwang373@ford.com>
FSW-1740 | Initiative | FSW-2113One Pedal Drive (1PD) | Miyashita, Eduardo (E.M.) | One Pedal Drive (CDX746/7) | Developing | 2020-08-03 11:15 | Padilha, Rodrigo (R. P.) | ABS, APIM_CDC, APIM_CIM, BCM, ECG_Gateway, EVCM, HPCM | F002710 | 2022-11-14 | Unresolved |  |  | Modified |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F002710 |  | SYNC+_Z0276 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | Wu, Dean (D.) <dwu44@ford.com>
FSW-1738 | Initiative | FSW-1417Idle Shutdown | Braithwaite, Paul (P.) | Auto Engine Idle Shutdown (CDX746/7) | Developing | 2020-08-03 11:15 | Engelbrecht, CP (C.) | APIM_CDC, APIM_CIM, BCM, EVCM | VSEM ID F000760 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO | 080-VM-FEC | F000760 |  | SYNC+_Z0246 | Major | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1737 | Initiative | FSW-2080Driver Information Display Control (DIDC) | Oliveira, Eude (E.O.) | Driver Information Display Control (CDX746/7) | Developing | 2020-08-03 11:15 | Sousa, Filipe (F.B.) | APIM_CDC, APIM_CIM, ECG_Gateway | VSEM ID: F000810 | 2022-11-14 | Unresolved |  |  | Modified |  | Not Listed | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000810 |  | SYNC+_Z1008 | C/O | DCV0 | 2022-03-16 | 2022-03-30 |  |  |  |  | DI | DI | DI | DI | PI | No spec | Jin Flora< JJIN17@ford.com>
FSW-1735 | Initiative | FSW-2069Charge Status Indication (CSI) | Deddeh, Tony (T.) | Charge Status Indicator (CDX746/7) | Developing | 2020-08-03 11:15 | Mohar, Maria (M.) | APIM_CDC, APIM_CIM, BCCM, BCM, BECM, EVCM, HPCM | VSEM ID F001065 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001065 |  | SYNC+_0208 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-11-15 |  | DI | [5 empty] | ECDX Lead | Yang, Jessica (Yu.) <yyang158@ford.com>
FSW-1724 | Initiative | FSW-1395Wireless Accessory Charging | Oliveira, Eude (E.O.) | Wireless Accessory Charging (CDX746/7) | Developing | 2020-08-03 11:15 | Oliveira Neto, Aderbal (A. R.) | APIM_CDC, APIM_CIM, BCM, WCM, WCMC | F001046/D | 2022-11-14 | Unresolved |  |  | Modified |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F001046/D | F001046/C --> Phone Wireless Charging notification | SYNC+_Z0050 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Lyu, Qingtao (Q.) <qlyu@ford.com>
FSW-1721 | Initiative | FSW-2118Perimeter Anti-Theft Alarm | Patel, Nimish (N.H.) | Perimeter Anti-Theft Alarm (CDX746/7) | Developing | 2020-08-03 11:15 | Talaga, Joshua (J.) | APIM_CDC, APIM_CIM, BCM, TCU | F000178/D | 2022-11-14 | Unresolved |  |  | Carryover |  | 2022 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO | 080-VM-FEC | F000178/D |  | SYNC+_Z0288 | N | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | 0
FSW-1703 | Initiative | FSW-1129Walk Away Lock | Cherman, Andre (A.L.) | Walk Away Lock (CDX746/7) | Developing | 2020-08-03 11:15 | Ruis, Ramon (R.) | APIM_CDC, APIM_CIM, BCM, DCME, DCMF, DCMG, DCMH, DDM, ECG_Gateway, FordPass_App, PDB, PDM, RFA | F002951 | 2022-11-14 | Unresolved |  |  | Modified |  | Not Listed | 2024 CDX746, 2024 CDX747 | CDX746/747, CSTF, China, DCO, J1, NO_KEYFOB, PaaK | 080-VM-FEC | F002951 | F004256 F002951 F004255 lock setting | SYNC+_Z0187 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Li, Xuedong (X.) <XLI244@ford.com>
FSW-1698 | Initiative | FSW-1224Key in Reminder (KIR) | Miranda, Airton (A. W.) | Key in Reminder (CDX746/7) | Developing | 2020-08-03 11:15 | Silva, Diego (D.M.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway | VSEM ID F001790 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Green | 080-VM-FEC | F001790 |  | SYNC+_Z1009 | N | 0 | 0 | 0 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | 0
FSW-1697 | Initiative | FSW-1203Heated Steering Wheel | Cruz, Mauricio (M.C.) | Heated Steering Wheel (CDX746/7) | Developing | 2020-08-03 11:15 | Shirazawa, Diogo (D.H.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, HPCM, RCCM, SCCM | VSEM ID F000123/C | 2022-11-14 | Unresolved |  |  | Carryover |  | 2022 P702 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F000123/C |  | SYNC+_Z0295 | C/O | DCV Beta1 | 2022-02-16 | - |  |  |  | DI | DI | DI | PI | PI | PI | need confirm detail spec with FO and check timing plan | Yan, Sophie (C.) <cyan10@ford.com>
FSW-1693 | Initiative | FSW-412eCall | Nasrallah, Hussein (H.) | Pan-Euorpean eCall (CDX746/7) | Developing | 2020-08-03 10:41 | Berro, Hussein (H.) | ACM, APIM_CDC, APIM_CIM, DSP, TCU | F000997 | 2022-11-14 | Unresolved |  |  | Carryover |  | 2023.5 V710 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F000997 |  | SYNC+_0126 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | ECDX Lead | Ren, Siyuan (Alex.)
FSW-1687 | Initiative | FSW-2405Cabin & Battery Overheat Management (old name TMOS) | Johnston, William (Bill.) | Cabin & Battery Overheat Management (old name TMOS) (CDX746/7) | Developing | 2020-05-21 08:19 | Collins, Lynn (L.) | ACCM, APIM_CDC, APIM_CIM, BCM, BECM, ECG_Gateway, EVCM, GSM, RCCM | VSEM ID: F003090 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003090 |  | SYNC+_Z0253 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1496 | Initiative | FSW-2066Augmented Reality | Yousif, Meisam (M.L.) | Augmented Reality (CDX746/7) | Developing | 2020-07-27 22:30 | Abdelhamid, Mahmoud (M.) | APIM_CDC, APIM_CIM, AR Camera, ARM, FIR Camera, HHDD, IPMA (ADAS) | VSEM ID F003774 | 2022-10-18 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | Aspire, CDX746/747, China, Red, VCSEDashboard | 080-VM-FEC | F003774 |  | SYNC+_Z1021 | New | DCV1 | 2022-04-15 | 2022-04-30 | 2021-10-30 | 2021-12-15 |  |  |  | DI | DI | DI | PI |  | 0
FSW-1299 | Initiative | FSW-2406Second Row Seat Position Control | Olsen, Bill (W.J.) | Second Row Seat Position Control (CDX746/7) | Developing | 2020-07-17 12:21 | Aguilar, Diana (D.S.) | APIM_CDC, APIM_CIM, DSM, ECG_Gateway, EVCM, RACM, SCMB, SCMK, SCML | F003517 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX747 | 5D, CDX747, China, Yellow | 080-VM-FEC | F003517 |  | SYNC+_Z0292 | New | DCV Beta | 2021-12-23 | 2022-01-06 | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-1124 | Initiative | FSW-373Selectable Drive Mode | Awadi, Ahmed (A.) | Selectable Drive Mode (CDX746/7) | Developing | 2020-07-07 10:08 | Meza morales, Luis Enrique (L.) | ABS, APIM_CDC, APIM_CIM, EVCM, IPMA (ADAS), PSCM, VDM | VSEM ID: F000549 | 2023-06-12 | Unresolved |  |  | Modified |  | 2021 CX727 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, GREEN | 080-VM-FEC | F000549 |  | SYNC+_Z0045 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | 0
FSW-1071 | Initiative | FSW-414WiFi Hotspot | Taleb, Yamen (Y.J.) | WiFi Hotspot (CDX746/7) | Developing | 2020-06-02 22:35 | Vega martinez, Oscar (O.) | APIM_CDC, APIM_CIM, ECG, TCU | VSEM ID: F000974/E |  | Unresolved |  |  | Carryover |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 090-PG-TT | F000974/E |  | SYNC+_Z0155 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | ECDX Lead | Pan, Yuan (Y.) <ypan23@ford.com>
FSW-1061 | Initiative | FSW-1059F003074/A;1 Heated Wiper Blade - HWB | Cruz, Mauricio (M.C.) | Heated Wiper Blade (CDX746/7) | Developing | 2020-05-29 11:08 | Lima, Dorivaldo (.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, EVCM, PDB, RCCM | VSEM ID: F003074 | 2022-11-14 | Unresolved |  |  | Modified |  | 2022 P702 BEV | 2024 CDX747 | CDX747, China, Green | 080-VM-FEC | F003074 | F003074 F000121 Heated Wiper Blade Heated Windshield | SYNC+_Z1004 | New | DCV Beta | 2021-12-23 | 2022-01-06 | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-895 | Initiative | FSW-892Rear Seat Controls Lockout - F003110 | Holub, Patrick (P.K.) | Rear Seat Controls Lockout (Modified) (CDX746/7) | Developing | 2020-05-08 15:20 | Ganna, Spurthi Varma (S.) | APIM_CDC, APIM_CIM, BCM, RACM, RCCM | F003110 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 U611/625 | 2024 CDX746, 2024 CDX747 | CDX746/747, China | 080-VM-FEC | F003110 |  | SYNC+_Z0255 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | no SPSS | TBD
FSW-894 | Initiative | FSW-702Classic Memory - F000171 | Miranda, Airton (A. W.) | Classic Memory - FNV3 (CDX746/7) | Developing | 2020-05-08 15:20 | Brasileiro, Matheus (M.B.) | APIM_CDC, APIM_CIM, BCM, DDM, DSM, ECG_Gateway, EVCM, PDM, RCM, SCMB, SCMG, SCMH | VSEM ID F000171 | 2022-11-14 | Unresolved |  |  | Modified |  |  | 2024 CDX746, 2024 CDX747 | CDX746/747, China, DCO, Green | 080-VM-FEC | F000171 |  | SYNC+_Z1006 | N | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 | NA | [6 empty] | IPC function | 0
FSW-893 | Initiative | FSW-377Enhanced Memory - F000172 | Torres, Nhi (N.) | Enhanced Memory - FNV3 (CDX746/7) | Developing | 2020-05-08 15:20 | Rahman, Naomee (N.) | ABS, ACM, APIM_CDC, APIM_CIM, BCM, DDM, DSM, DSP, IPMA (ADAS), PDM, RCCM, SCCM, SCMB, SCMG, SCMH | VSEM ID F000172 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023 P708 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, Green, NO_KEYFOB | 080-VM-FEC | F000172 |  | SYNC+_0165 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  |  | DI | DI | DI | PI | PI | PI | #N/A | Xu, Andy (X.) <XXU71@ford.com>
FSW-891 | Initiative | FSW-647Welcome / Farewell | Cherman, Andre (A.L.) | Lincoln Embrace (Modified) (CDX747) | Developing | 2020-05-08 12:32 | Petrilli, Bianca (B. D.) | ACM, APIM_CDC, APIM_CIM, BCM, DASM, DDM, ECG_Gateway, HCM, LDM, PDM, RACM | F004174 | 2022-11-14 | Unresolved |  |  | Modified |  | 2020 U611 | 2024 CDX747 | CDX747, China, DCO, Green, NO_KEYFOB | 080-VM-FEC | F004174 | F004174 F000064 | SYNC+_0170 | C/O | DCV Beta | 2021-12-23 | 2022-01-06 |  |  | DI | DI | DI | DI | PI | PI | PI | #N/A | Chen, Huizhen (H.) <hchen188@ford.com>
FSW-890 | Initiative | FSW-886PDLC SkyLite Digital Shade (PSDS) | Barreto, Rafael (R.V.) | PDLC SkyLite Digital Shade (PSDS - CDX747) | Developing | 2020-05-08 12:32 | Tronolone, Ulisses (U.F.) | APIM_CDC, APIM_CIM, BCM, ECG_Gateway, HCM, LincolnWay, PDB, RACM, RCCM, SCMB | F003170 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX747 | CDX747, China, Yellow, roadmap2023 | 080-VM-FEC | F003170 |  | SYNC+_Z0250 | New | DCV Beta1 | 2022-02-16 | - | 2021-09-30 | 2021-10-30 |  | DI | DI | DI | PI | PI | PI |  | 0
FSW-889 | Initiative | FSW-885Stowable Steering Column with Deployable Tray | Deddeh, Tony (T.) | Stowable Steering Column with Deployable Tray (CDX746/7) | Developing | 2020-05-08 12:32 | Lau, Tok (T. W.) | ABS, APIM_CDC, APIM_CIM, BCM, DSM, ECG_Gateway, EVCM, RCM, SCMB | F002870 |  | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | CDX746/747, China, roadmap2023 | 080-VM-FEC | F002870 |  | SYNC+_Z0251 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI |  | 0
FSW-882 | Initiative | FSW-8497Sentinel | Zuraw, Timothy (T.) | Sentinel Experience Phase 3(CDX746/7) | Developing | 2020-05-08 09:20 | Minous, Corey (C.) | APIM_CDC, APIM_CIM, BCM, Cloud, ECG, FordPass_App, IPMA (ADAS), PDB, TCU | F003417 | 2022-11-14 | Unresolved |  |  | Modified |  | 2023.5 V710 | 2024 CDX747 | Aspire, CDX747, China, Red, RoadMapExclusion, roadmap2023 | 080-VM-FEC | F003417 |  | SYNC+_Z0262 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-09-30 | 2021-11-15 |  |  | DI | DI | PI | PI | PI | need further clarify feature then can clarify TS&YFVE job devision, current questions as below: 1. Will the North American team provide an implementation library or binary for "CameraService" on SYNC+? 2. In the IDC architecture, what is the progress of the software solutions for other ECUs other than SYNC+? Is there a corresponding FO support? 3. The video stream and vehicle-related metadata recorded by VRP can be played through the cloud. Is there any legal risk to this function in China? 4. The video stream is transmitted based on the RTSP protocol. Can you provide more definitions about the protocol and the function definition of video stream transmission? 5. When playing back the recorded video, will the HMI directly play it through the video file path, or use the VideoPlayBackService of the VRP to report the video stream to the HMI for display? 6. Does the recorded video contain audio stream data？ 7. How to stop recording of Integrated Security Camera (Sentinel) Feature？ 8. What is the metadata file format associated with the video？ | 0
FSW-744 | Initiative | FSW-738My Seat Space (MSS) | Cauley, Jason (J.F.) | My Seat Space (MSS) (CDX746/7) | Developing | 2020-04-27 21:31 | Cintron, Austin (A.) | ACM, APIM_CDC, APIM_CIM, DSP, RACM | F003519 | 2022-11-29 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX747 | CDX747, China, Yellow, confirm-containability, roadmap2023 | 105-VM-J1 | F003519 |  | SYNC+_0228 | New | DCV0 | 2022-03-16 | 2022-03-30 | 2021-11-30 | 2022-01-11 | [5 empty] | DI | DI | this is a complicated feature and related muti-model, considering the difference between Phoenix and SYNC+ need further check spec with FO, for development it's better to set a local FO to support. Current questions as below: TS: should MSS develop based on Android 11? | 0
FSW-741 | Initiative | FSW-737Rejuvenate Mode | Reppenhagen, Nancy (N.B.) | Rejuvenate Mode (CDX747) | Developing | 2020-04-27 21:31 | Shetty, Sohan (S.R.) | APIM_CDC, APIM_CIM, BCM, DSM, ECG, EVCM, RCCM, SCMB, TCU | F003072 | 2022-11-14 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX747 | 2022PriorityWorkshopSubmission, Aspire, CDX747, China, VESC_Portfolio, roadmap2023 | 080-VM-FEC | F003072 |  | SYNC+_0135 | New | DCV3 | 2022-07-11 | 2022-07-26 | 2021-10-30 | 2021-12-30 |  |  |  |  | DI | DI | PI | ECDX Lead | Liu, Kai (K.) <kliu63@ford.com>
FSW-740 | Initiative | FSW-712Ultimate Remote Control - F003071 | Cauley, Jason (J.F.) | Ultimate Remote Control (CDX746/7) | Developing | 2020-04-27 21:30 | Thabet, Safwan (S.A.) | ACM, APIM_CDC, APIM_CIM, ECG, FordPass_App, LincolnWay, RCCM, SCMB, SCMC, SCMD, SCME, SCMF, SCMG, SCMH, SCMK, SCML | F003071 | 2022-11-14 | Unresolved | The team is working together but still many unknowns. Team is unaware of any business goals / expectations beyond launch / availability. This makes it somewhat difficult to assess implementation options by any metric beyond risk to launch and / or possible negative impact to the broader ecosystem. |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | Aspire, CDX746/747, China, Green, VESC_Portfolio, roadmap2023 | 080-VM-FEC | F003071 |  | SYNC+_0115 | New | DCV2 | 2022-05-30 | 2022-06-14 | 2021-10-30 | 2021-12-30 |  |  |  |  | DI | DI | PI | ECDX Lead | Shawn, Lin
FSW-122 | Initiative | FSW-432Personal Vehicle Profile (PPP) - F000102 | Metcalf, Thomas (T.D.) | Personalized and Portable User Profile (PPP) (CDX746/7) | Developing | 2019-05-15 14:11 | Bauer, Justin (J.) | ABS, ACM, APIM_CDC, APIM_CIM, BCM, CVFMA, DDM, DSM, DSP, ECG, FordPass_App, IPMA (ADAS), LincolnWay, PDM, PPP FI, RCCM, SCA-CAP, SCCM, SCMB, SCMG, SCMH, TCU | "PPP - F002032 Rocket Setup - F002470 BLE Autopair - F002491 Autosave - F002830" | 2022-11-29 | Unresolved |  |  | New |  | 2024 CDX746/747 | 2024 CDX746, 2024 CDX747 | 2022PriorityWorkshopSubmission, Aspire, CDX746/747, China, ECG, Green, NO_KEYFOB, SInitTopListProductSuite, VCSEDashboard, roadmap2023 | 105-VM-J1 | "PPP - F002032 Rocket Setup - F002470 BLE Autopair - F002491 Autosave - F002830" |  | SYNC+_0166 | C/O | DCV3 | 2022-07-11 | 2022-07-26 | 2021-11-30 | 2022-01-11 | [5 empty] | DI | DI |  | Xu, Andy (X.) <xxu71@ford.com>
Generated at Sun Sep 12 22:16:06 EDT 2021 by Li, Qiyang (Q.) using Jira 8.13.8#813008-sha1:0e9b72fb99b51299615816b8dfb60d79baa93322.
Formulas:
Release data to REC = VLOOKUP(U:U,'[1]Feature Implementation Plan'!$A:$AT,46,0)
Release Date to FO/CAF(2weeks) = VLOOKUP(U:U,'[1]Feature Implementation Plan'!$A:$AU,47,0)
Note on Y96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need FO support clarify the requirement.
Note on Y97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: R&R should further study between inhouse & YFVE.
Note on Y101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potential pull ahead this feature to DCV0.

## Issue Summary (hidden)
Pasha, Aamir (A.) | Chen, James (J.) | Huang, Xue (X.) | IPC | Li, Daisy (Y.P.)
10 | 3 | 1 | 1 | 13

## Summary (hidden)
Cluster | No Spec | Further Spec Clarification
11 | 10 | 76