## Phase3工时评估 (2) (hidden)
[9 empty] | 539 ICA |  |  |  | 483 ICA |  |  |  | 611 ICA
功能类别 | 模块名 | 功能描述 |  | feature总数 | 继承P1P2 | 新增feature | PM负责人 | PM估时 | UE估时 | UI估时 | RD估时 | QA估时 | UE估时 | UI估时 | RD估时 | QA估时 | UE估时 | UI估时 | RD估时 | QA估时
Launcher | SyetemUI | 新增：12.8、13.2屏幕适配，UE给出适配规则 |  | 17 | 11 | 6 | 姜明明 | 3 | 5 | 10 | 160 | 40 | 0 | 0 | 30 | 8 | 0 | 0 | 30 | 8
|  | 确认布局方案 | HMI CD539ICA 13.2布局方案确认（Home button 放在左上角，时钟显示放置中间） | [5 empty] | 10 | 10 |  |  | 0 | 0 |  |  | 0 | 0
|  | 整体适配规则 | [6 empty] | 30 | 30 |  |  | 0 | 0 |  |  | 0 | 0
|  | 输出已有视觉界面 适配界面，标注及切图资源 | [6 empty] | 12 | 120 |  |  | 0 | 0 |  |  | 0 | 0
|  | 483低配，新增蓝色皮肤 | 按原Phase2蓝色皮肤适配，不含皮肤重新调整设计 | [5 empty] | 0 | 0 |  |  | 20 | 180 | 50 |  | 0 | 0
| hud |  | 佳佳已确认此功能CD539ICA车型不上 | 7 | 7 | 0 | 姜明明 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 10 | 0 | 0 | 40 | 10
| 道路救援 | 新增：紧急救援 | 2019/12/10:之前评估与目前需求有较大差异，百度所需的工作量评估合理 | 3 | 2 | 1 | 姜明明 | 10 | 3 | 6 | 5 | 2 | 0 | 0 | 2 | 0.5 | 3 | 6 | 2 | 0.5
| 开关机动画 |  |  | 1 | 1 | 0 | 姜明明 | 3 | 0 | 1 | 3 | 1 | 0 | 1 | 2 | 0.5 | 0 | 1 | 2 | 0.5
| 免责声明 | 免责声明 | 12.1获取prd | 1 | 0 | 1 | 姜明明 | 5 | 0 | 1 | 4 | 1 | 0 | 1 | 4 | 1 | 0 | 1 | 4 | 1
| 输入法 |  | 2019/12/10：新项目，新车型，打包集成适配工作； | 1 | 1 | 0 | 单童 | 3 | 0 | 0 | 5 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 2 | 1
| 用户手册与反馈 |  |  | 3 | 3 | 0 | 朱诗韵 | 3 | 0 | 2 | 40 | 10 | 0 | 2 | 2 | 1 | 0 | 2 | 2 | 1
| 抖音 | 仅新增入口：TikTok on DuerOS，APP由福特进行开发 | 抖音的集成，基于原有IVI功能需要有额外的集成和调试（包括音源），需要YF一起参与评估，下周二CVPP上海F2F会议中具体讨论； 12.1可获取prd； 王驰负责跟进； | 1 | 0 | 1 | 姜明明 | 0.5 | 2 | 4 | 2 | 0.5 | 0 | 0 | 2 | 0.5 | 2 | 4 | 2 | 0.5
车模 | 车模 | 3D车模渲染，目前按Phase2 配置和颜色预估 | 福特1次性提供完整、可用的车模文件，百度渲染3次样片渲染稿及确认，按确认稿1次渲染全量用图；超量部份按实际完成时长计算 | [5 empty] | 12 | 120 |  |  | 12 | 120 |  |  | 12 | 120
语音语义 | 语音语义 | 新增：多音区 | 2019/12/10：539ICA所有语音界面确认和适配，每款车高中低配识别率优化和dsp调参，语音问题的支持和修复 | 85 | 84 | 1 | 林志桃（原） | 5 | 10 | 15 | 140 | 50 | 0 | 0 | 100 | 40 |  |  | 100 | 40
| VPA | VPA（虚拟语音助手）此功能投入较大,需求待澄清 | 11.4刚拿到需求，百度正在更新报价； 12.1可获取prd | 1 | 0 | 1 | 无 | 22 |  |  | 660 | 220
| 车控家 |  |  | 5 | 5 | 0 | 王驰 | 3 | 0 | 1 | 50 | 10 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 1
图像识别 | 图像识别 | 【随心听】OK开始播放、比嘘暂停播放、点赞收藏音乐 【导航】OK开始导航、点赞收藏POI、点头/摇头回应弹框问询、比嘘静音TTS、OK取消静音 …（具体见详细文档） | CD539ICA和U611ICA删除图像识别 | 36 | 0 | 36 | 陈鸿博 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
地图 | 基础地图 |  | UE/UI含设计走查工作 2019/12/10： 1.CD539ICA参考界面定制适配； 2.外部依赖验证调试（车辆服务、惯导调试、GPS等）和测试； | 20 | 20 | 0 | 陶诗量 | 5 | 12 | 24 | 120 | 36 | 5 | 10 | 60 | 18 | 5 | 10 | 60 | 18
| V2X | V2X（车路协同） 1）哪些场景，要展示什么（卡片），端上定制开发 2）高清数据需求（L4） 3）百度主线能力路测方案 | 目前需求还未完全明确，11.12在CVPP进行详细讨论； U625先上，Phase3车型按照复用进行评估 | 1 | 0 | 1 | 李志鹏/璞丽婧 | 20 | 5 | 5 | 10 | 10 | 5 | 5 | 10 | 10 | 5 | 5 | 10 | 10
| AR导航 | 新增：AR导航 | U611删除 | 1 | 0 | 1 | 穆颜龙 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
内容生态 | 内容生态 |  | 2019/12/10：483、611功能/界面较多，设计走查、修改会消耗人力 | 21 | 21 | 0 | 李丹/王驰 | 10 | 5 | 10 | 420 | 105 | 5 | 10 | 10 | 8 | 5 | 10 | 10 | 8
中台 | 消息中心 | 新增：客户数据共享协议 | 12.1获取prd | 4 | 3 | 1 | 单童 | 5 | 0 | 0 | 30 | 8 | 0 | 0 | 10 | 3 | 0 | 0 | 10 | 3
| 账号 | 多账户管理rely on faceID |  | 12 | 12 | 0 | 李博 | 5 | 2 | 4 | 60 | 20 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10
| 支付 |  |  | 5 | 5 | 0 | 黄敬凯 | 3 | 0 | 0 | 30 | 8 | 0 | 0 | 2 | 1 | 0 | 0 | 2 | 1
OTA | OTA |  |  | 4 | 4 | 0 | 叶欢 | 3 | 0 | 0 | 70 | 15 | 0 | 0 | 50 | 15 | 0 | 0 | 50 | 15
服务生态 | 流量 | 新增：流量套餐对RNR实名认证的支持 | 12.1获取prd； 2019/12/10：RNR还不确定具体需求，目前 看和多个app存在交互 | 3 | 2 | 1 | 朱柏臻（原） | 3 | 3 | 5 | 20 | 10 | 0 | 0 | 10 | 5 | 3 | 5 | 10 | 5
| 服务生态 | 新增：支付功能里电影票，鲜花（美团），餐品/外卖预定以及酒店可以支持免密支付 正在研发：预约保养 | 使用Baidu自己的方案； 2019/12/10：免密支付除ETCP外，之前并未有落地项目，开发工作量较大，且存在与第三方沟通成本 | 23 | 22 | 1 | 黄敬凯 | 5 | 5 | 10 | 240 | 60 | 0 | 0 | 40 | 15 | 5 | 10 | 40 | 15
安全 | 安全 |  |  | 1 | 1 | 0 | 牛兵帅 | 3 | 10 | 20 | 100 | 30 | 10 | 20 | 40 | 10 | 10 | 20 | 70 | 40
埋点 | 埋点 |  |  | 8 | 8 | 0 | 吴冬蜜（原） | 20 | 0 | 0 | 40 | 20 | 0 | 0 | 10 | 8 | 0 | 0 | 10 | 8
系统设置 | 系统设置 | 设计工作：对齐车辆设置，其余2套主题设计，全部应用适配 | 2019/12/10：车模适配，实车验证 | 30 | 30 | 0 | 谢承朋（原） | 5 | 0 | 40 | 80 | 25 | 0 | 40 | 60 | 15 | 0 | 40 | 60 | 15
车控 | 车况提醒 |  |  | 3 | 3 | 0 | 赵唯龙 | 5 | 0 | 1 | 60 | 15 | 0 | 1 | 40 | 10 | 0 | 1 | 40 | 10
| 车辆控制 | 车模配图，info book，UI工作量比较大 一款车30个工作日 | 车模需要ford提供已渲染完成车模，百度直接裁剪可用 2019/12/10：实车验证会消耗大量时间 | 96 | 96 | 0 | 韩雨哲 | 5 | 10 | 60 | 180 | 45 | 10 | 60 | 120 | 30 | 0 | 60 | 120 | 30
| 混动设置 | 仅CX483ICA这款车型（林肯） |  | 8 | 8 | 0 | 单童 | 5 | 0 | 0 | 0 | 0 | 5 | 10 | 240 | 60 | 0 | 0 | 0 | 0
| 驾驶辅助 | 新增：RVC动态辅助线、叠加ARBPA | 3种方案（第三种方案主要依赖于百度，第一第二依赖于YF），目前百度已经基于第二种方案完成了报价，Fin把三种方案share给到Baidu&YF,在Regular需求会议中继续澄清 2019/12/10：延锋底层提供接口，由百度绘制，均需要实车验证和调试。 同时动态辅助线为新功能，不确定因素较多，如实现方案 | 8 | 6 | 2 | 韩雨哲 | 0 | 10 | 20 | 90 | 30 | 10 | 20 | 30 | 15 | 10 | 20 | 30 | 15
| 物理按键 | 以具体车型为主，不同车辆，硬按键有所变化 |  | 22 | 22 | 0 | 谢承朋（原） | 5 | 10 | 10 | 30 | 8 | 0 | 0 | 20 | 5 | 0 | 0 | 20 | 5
| 蓝牙电话 |  | 2019/12/10：蓝牙电话包括 拨号盘（Dialer），通讯录（Contact），通话Incallui多个应用合并在一起。包含539ICA蓝牙电话所有界面的适配，后续问题修复 | 7 | 7 | 0 | 谢承朋（原） | 3 | 0 | 2 | 70 | 18 | 0 | 0 | 10 | 3 | 0 | 2 | 10 | 3
| 远程控制 | 新增：Phone as key(PaaK) 待定：实现车辆远程灯光/鸣笛控制 |  | 5 | 3 | 2 | 谢承朋（原） | 5 | 0 | 0 | 0 | 0 | 10 | 20 | 60 | 15 | 10 | 20 | 60 | 15
暂无分类 | 数字香薰 | Digital scent | 需要福特提供需求说明，确认prd提供时间 2019/12/10：语音指令添加后的调试及验证工作会占用较多工时 | 1 | 0 | 1 | 朱诗韵 | 10 | 0 | 0 | 0 | 0 | 1 | 2 | 40 | 10 | 1 | 2 | 20 | 10
| 在线商城 | P2已规划，未开发 |  | 2 | 2 | 0 | 王明（原） | 10 | 0 | 0 | 3 | 0.5 | 1 | 2 | 3 | 0.5 | 1 | 2 | 3 | 0.5
| 福特金融 |  | 2019/12/10：每个版本会进行集成及简单测试 | 1 | 1 | 0 | 陈鸿博 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 2 | 0 | 0
总数 |  |  |  | 447 | 390 | 57 |  | 196.5 | 156 | 531 | 2722 | 799 | 95 | 507 | 1111 | 330 | 73 | 344 | 831 | 300 | 7995.5
[9 empty] | 539 ICA |  |  |  | 483 ICA |  |  |  | 611 ICA
[9 empty] | 4208 |  |  |  | 2043 |  |  |  | 1548
[8 empty] | 4664 |  |  | 4664
[9 empty] | 210 | 22 | 4620 | 人天
[6 empty] | vpa | 300 | 4364 | 144 | 12 | 12 | 人/月 |  |  |  |  | ROM | 8 | 杨帆，建晓，廖冲，杨雄，建立
[6 empty] | 车控 | 700 | 3664 | 156 | 13 | 12 | [5 empty] | 地图 | 2 | 黄浩，明杰，张欣，盛进，俊磊，陈冰，俊峰，帆光
[6 empty] | 地图 | 60 | 3604 | 168 | 14 | 12 | [5 empty] | 安全 | 1
[6 empty] | 安全 | 90 | 3514 | 14人月 | 3696 |  |  |  | phev | 240 |  | 横向团队 | 2 | 账号服务端，随心服务端，语义服务端，语音技术部
[6 empty] | 语音 | 100 | 3414 | 13人月 | 3432 | [8 empty] | 4*0.5
[9 empty] | 12人月 | 3168 | [6 empty] | 总计 | 13
[10 empty] | 地图 | 240
[10 empty] | 安全 | 210
|  |  | 1250 |  |  |  | 6370.5 |  |  | VPA | 660
|  |  | 375 | [6 empty] | 车辆控制 | 1150
[10 empty] | 系统设置 | 200
[10 empty] | 语音 | 340
[17 empty] | 车况140人天 |  | 60 | 40 | 40 | 140
[17 empty] | phev 240人天 |  |  | 240 |  | 240
[17 empty] | 驾驶辅助 120 |  | 90 | 30 | 30 | 150
[17 empty] | 多屏互动80 |  |  | 40 | 40 | 80
[17 empty] | 系统设置200 |  | 80 | 60 | 60 | 200
[17 empty] | 车辆控制420 |  | 180 | 120 | 120 | 420
[17 empty] | 远程控制120 |  |  | 60 | 60 | 120
1350
[19 empty] | 20 | 10 | 10 | 40
[20 empty] | 30 |  | 30
[19 empty] | 50 | 20 | 20 | 90
[20 empty] | 20 | 20 | 40
[19 empty] | 30 | 20 | 20 | 70
[19 empty] | 120 | 80 | 80 | 280
[20 empty] | 50 | 50 | 100
650

## 工时汇总
Phase5 工时汇总—Feature（1-4）
Lead Team | New Feature |  | Minor/Major change feature |  | CDX707 | U611 | U611 | Total
| ID | Name | ID | Name | 工时/Hours | 工时/Hours | 工时/Hours | 工时/Hours
EESE |  | Night Vision | [5 empty] | 0
|  | Audio | [5 empty] | 0
|  | AVAS | [5 empty] | 0
|  |  |  | Vehicle Setting |  |  |  | 0
|  |  |  | PPP |  |  |  | 0
|  | … | … | …
0
ECDX | [7 empty] | 0
0
|  | … | … | … |  |  |  | 0
基础版本Full测试工时（一轮**小时） | [7 empty] | 0
基础版本Focus测试工时（一轮**小时） | [7 empty] | 0
Total | [7 empty] | 0

## 工时汇总-engineer
Phase5 工时汇总—Engineer（5）
Lead Team | 工作内容 | CDX707 | U611 | U621
System
| … | … | … | …
SW
| … | … | … | …
SWV
| … | … | … | …
Total

## Sheet1 (hidden)
Feature | Spec
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
DUEROS_CVPP_IOT(Vehicle to Home)_PRD v1.0
DUEROS_CVPP_IOT(Vehicle to Home)_ PRD v1.0
HMI flowchart to be provided by Visteon
HMI flowchart is provided by Visteon. CD539&C519_HMI_V0.2_20180720
H31a_SYNC_GEN3_Settings_RELEASED_v2_26_MY20
H31i_SYNC_GEN3_Wi-Fi_Settings_RELEASED_v0_35_3_MY2020
H31a_SYNC_GEN3_Settings_RELEASED_v2_26_MY20
A73d_Calendar_Date_Clock_Format_Market_Behavior_Table_RELEASED_v3_10_MY20.
H31k SYNC3 Settings to Centerstack (RELEASED) v4_4
A36d_APA_HmiStatus_Coding; H36b-Automatic Park Assist HMI Screenflow； H36e SHMI Driver Assist Active Park Assist CGEA1.3 SYNC Gen3 (RELEASED) v2_4
H36a SHMI Driver Assist RVC FlankGuard RELEASED v2_9
H36j SYNC GEN3 Driver Assist MultiCameraSystem RELEASED v2_4
H26f_SYNC_GEN3_CLIMATE_RELEASED_v2_09_MY20
DUEROS_CVPP_Ford and Baidu Account Binding_ PRD v1.0
DUEROS_CVPP_Car Wallet_PRD v1.0
DUEROS_CVPP_EOL PRD v1.0
DUEROS_CVPP_Carrier FEED_PRD v1.0
DUEROS_CVPP_Provisioning_PRD v1.0
DUEROS_CVPP_AHU Hardware Replacement_PRD v1.0
DUEROS_CVPP_CAQ (Cabin Air Quality)_ PRD v1.0
H39_Bezel Diagnostics_Gen3_RELEASED_v2_0
H78c-BCar Vehicle Settings Screenflow
A36d_APA_HmiStatus_Coding; H36e SHMI Driver Assist Active Park Assist CGEA1.3 SYNC Gen3 (RELEASED) v2_4
H74 MCS SYNC Gen3 RELEASED v1_5
H31k SYNC3 Settings to Centerstack (RELEASED) v4_5
H66b_SYNC_Gen3_TMC_and_On-Line_Traffic_RELEASED_v1_14
H22i_SYNC_GEN3_Calm_Screen_RELEASED_v1_04_MY20
H28a_SYNC_Gen3_Phone_RELEASED_v2_01_MY20