## Cover
NJTC-PRM-TM-01 RIO List | [5 empty] | Version: | 2.3
延锋伟世通电子科技(南京)有限公司
RIO List
RIO清单
| Project Name |  | CDX707
| EP ID |  | NA
| Ver.版本 | Date 发布日期 | Author 作者 | Change Description 变化描述 | Approvers 批准人 | Status 状态
| V0.1 | 2021-03-14 | Liu Yongxue | Initial | Sun Jiangyan | Released
YanFeng Visteon Electronics Technology (Nanjing) Co., Ltd
资产分类：B类

## Guideline
1 Introduction
- RIO = Risk Issue Opportunity
- Risks = uncertain events or conditions that, should they occur, would have a negative impact on the project in terms of Quality, Value, Speed/Timing and People/Resources. Projects should work towards eliminating or reducing the impact of the risk.
- Issues = Risk that have already occurred and have had a negative impact on the project in terms of Quality, Value, Speed/Timing and People/Resources. Appropriate actions regarding issues typically focus on addressing the issue related to the project.
- Opportunities = uncertain events or conditions that, should they occur, would have a Positive impact on the project in terms of Quality, Value, Speed/Timing and People/Resources. Projects should work towards taking advantage of Opportunities whenever possible.
2 Roles & Responsibilities
- PDTL:
Open a RIO
Assign/re-assign the owner of the RIO
Update RIO content if necessary
Track/close all the RIOs
- Team Members:
Identify RIOs and submit to PDTL
Implement action plan that he/she is assigned as the owner
Only system requirement related RIOs can be maintained by system engineer
3 Key Attributes of RIO
When a risk or issue or opportunity is identified, the PDTL should add it in this RIO list
RIO status track:
· Status: Select Open‘,’ Analyzing‘, ’Implementing‘, ‘Resolved’, ’Closed’ from the list box.
Open means a new problem and have not been analyzed;
Analyzing means doing problem analysis and response plan.
Implementing means implementing response/action plan
Resolved means response/action plan has done and problem has been resolved
Closed means the problems have been verified and can be closed.
RIO Identification:
· RIO: Select ‘Issue’, ‘Risk’, ‘Opportunity’ from the list box.
· Type: Select ‘Managerial’ , ’Technical’ from the list box.
· Source: Select one from the PD Internal, Plant, Customer, Supplier, Other as the RIO origin.
· Raised By/Raised Date: Enter the date and member name that RIO is identified.
· Description: Describe RIO in detail.
· Category: Select one from the PDTL, System, Software, Electrical, Mechanical, Testing, Supplier, Customer, Plant, Others
RIO Impact Analysis:
· Analysis Due Date:Due Date that expected analysis done
· Impact Description: Enter the description of the project impact.
· Impact Rating: Enter the rating from the following 3 options ‘Low’, ‘Medium’ and ‘High’, which is evaluated based on the criteria stated below:
Impact
Index | Cost | Timing | Quality
Low | Less than 5k$ dev cost | 1 week | Low
Medium | Between 5k$ and 50k$ dev cost | 2 weeks | Medium
High | Over 50k$ dev cost | 4 weeks | High
· Probility of Occurrence: To describe the possibility that the risk/opportunity will occur. There’re 3 options: ‘Low’, ‘Medium’ and ‘High’ which is rated based on the criteria stated in the following table:
Probability
Rating | Meaning
Low | < 20%
Medium | 20% to 70%
High | > 70%
For issue, this field will be "-" as it is always considered ‘high’.
· Severity:Depends on the degree of impact and the probility of occurrence
Severity |  | Probability
|  | Low | Medium | High | -
Impact | Low | Low | Low | Low | Low
| Medium | Medium | Medium | High | Medium
| High | Medium | High | High | High
RIO Response
· [Risk] Response Strategy: only for Rsik, select Avoidance, Transfer, Reduction, Acceptance from the list box.
· Counter Measure: To resolve the RIO, action plan needs to be developed, the action plan should be recorded in detail in the way of 5W1H etc.
· Responsible: Enter the name of the action owner
· [Risk]Emergency Measure: only for risk, define the action when response strategy and action plan is invalid
· Due Date: Planned complate date for action plan.If action plan cannot be completed within the due date or the RIO is not closed, the risk of RIO delay must be analyzed before the due date,
the action plan must be updated, and a new target due date must be planned, and a complete record must be made in the RIO.
· Action Record: Enter the description to track how the RIO progresses so far. It is recommended to update this field at least once per week.
· Approver: Who approve that the RIO can be closed

## RIO List
RIO List
RIO Identification | [9 empty] | Status | RIO Impact Analysis | [5 empty] | RIO Implementation Plan |  |  |  |  | Implement and verfication |  |  |  | Comments
ID. | RIO | Type | Source | Raised By | Raised Date | Description | assignee | remark | Category |  | Analysis Due Date | Impact Description | Impact | Probility | Severity | Actual Analysis Date | [Risk] Response Strategy | Counter Measure | Responsible | Due Date | [Risk]Emergency Measure | Action Record | Closed Date | Approver | EE Reply
001 | Issue | Technical | Customer | Huo Dongchen | 2021/12/3 | SYNC+_0170 车辆迎宾模式 Lincoln Embrace / Ford Welcome &Farewell的差异点是素材上的变化吗 | Chen, huizhen HCHEN188@ford.com | 718相比707有座椅位置变化，需要FO确认 @chen, huizhen
002 | Issue | Technical | Customer | Huo Dongchen | 2021/12/3 | SYNC+_0289 Lidget/Fidget/Widget 3.0 分工是什么，具体是什么功能，YF并没有发开过764项目 | zhou, calvin QZHOU31@ford.com | inhouse & Baidu开发, YFVE侧无关，3.0具体功能还未确定,2.0已经确定，需与FO沟通
003 | Issue | Technical | Customer | Huo Dongchen | 2021/12/3 | F004151 3-Way Splitgate的分工 |  | vehicle setting, trunk control, FDL inhouse, need niuchun add FO @NiuChun
004 | Issue | Technical | Customer | Huo Dongchen | 2021/12/3 | F002992 Auto Tow / Haul的分工 |  | vehicle setting, trunk control, FDL inhouse, need niuchun add FO @NiuChun
005 | Issue | Technical | Customer | Huo Dongchen | 2021/12/3 | SYNC+_0074 倒车制动辅助 Reverse Brake Assist (RBA)为什么借用702，屏的尺寸是和707一致的 |  | FDL inhouse, need confirm difference between 702&707, vendors need check spec
006 | Issue | Technical | Customer | Huo Dongchen | 2021/12/3 | 02 Basic Function 里面没有标明CO项 |  | C/O CDX707
007 | Issue | Technical | Customer | Huo Dongchen | 2021/12/3 | 718项目的燃油类型什么 |  | 燃油车，无混动
008 | Issue | Technical | Customer | Huo Dongchen | 2021/12/3 | UIUE借鉴的车型是，分别有几套UIUE | Lisa, Gao LGAO29@ford.com | 需要HMI team回复 @Lisa.Gao
009
023 | Issue
Note on K2: Diao, Songling (S.): Open means a new problem and have not been analyzed; Analyzing means doing problem analysis and response plan. Implementing means implementing response/action plan Resolved means response/action plan has done and problem has been resolved Closed means the problems have been verified and can be closed.
Note on O3: DSL: When RIO=Issue, Probility="-" When RIO=Risk or opportunity, Probility can be selected as "Low","Medium","High"
Note on R3: DSL: Only for Risk
Note on V3: DSL: Only for Risk