## Slide 1: Mode Card 1.0 CX727 delivery overall plan (WIP)
11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UE
11/28
8155 Dev Plan
S/O
12/26
Today
Scoping Plan
Final
Scoping
11/10
PRD
Frozen
11/25
Coding
V0
12/5
V1
12/12
S/O
1/17
V0
12/26
V1
1/3
UI
12/5
HLD
12/6
V0
12/19
V1
12/28
LLD
12/20
V1
12/29->1/4
SW
12/23
Test & Debug
Test
4/17
2nd
7/30
Validation
6/19
1st
7/10
727ICA B2
(8155)
OTA2
6/30 ？
OTA3
9/30 ？
OTA1
4/30 ？
OKTB
3/20
727ICA B3
(8155) Leading
PEC/FEC
12/1
DCV
8/30
OTA4
12/30 ？
DEMO for
Camp Mode
2/24->2/28
TC completed
1/20
TC Design
12/12
8155 Test Plan
UE
3/1
S/O
3/28
V0
3/7
V1
3/14
S/O
4/10
V0
3/20
V1
4/3
UI
3/7
HLD
3/8
V0
3/20
V1
3/29
LLD
3/21
V1
3/30
Legend
Mode Cade & Camp
Pet & Battery Save
APK completed
4/14->4/18
APK completed
6/27
TC completed
4/24
TC Design
3/8
Final
Scoping
1/12
PRD
Frozen
2/10
OTA3 integration
8/8
9/5
Validation
8/22
SW integrate
6/19
SW integrate
7/28
Screensaver
&Audio
2/10
Test
6/28
需要在2/3提供1个布谷鸟闹铃资源给inhouse开发
需要在2/10提供动效资源给inhouse开发，提前给HMI review

## Slide 2: Mode Card 1.0 CX821 delivery overall plan (WIP)
11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UE
12/28- 1/16
8295 Dev Plan
Today
Scoping Plan
Final
Scoping
11/10
PRD
Frozen
11/25
Coding
V1
1/6-1/20
S/O
2/10
S/O
2/28
V1
2/17
UI
2/6
HLD
1/30
V1
2/9
LLD
2/10
V1
2/16
SW
2/10
Test & Debug
Test
6/7
9/1
Validation
8/17
CX821
(8295) Leading
DCV
9/29
PEC
12/22
CX821
(8295) SW Integration
DCV0
5/20
DCV1
6/29
DCV2
8/3
DCV3
9/14
DCV4
10/12
R00
11/9
R04
12/14
TC Complete
3/10
TC Design
1/30
8295 Test Plan
Legend
Mode Cade & Camp
Pet & Battery Save
S/O
4/28
UE
4/11
V1
4/18
S/O
5/12
V1
4/28
UI
4/18
HLD
4/19
V1
4/25
LLD
4/24
V1
4/28
Final
Scoping
1/12
PRD
Frozen
2/10
APK completed
6/6
APK completed
7/25
TC Complete
5/30
TC Design
4/18
SW Integrate
8/2
SW Integrate
9/13
10/15
Validation
9/23
1. 需要在2/20先提供camp mode切图给inhouse开发
V0
2/6
SW
5/15

## Slide 3: Mode Card 1.0 test requirement (WIP)
10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
8155 Development Plan
727ICA B2
(8155)
MP1
1/31
OTA2
6/30 ？
OTA3
9/30 ？
OTA1
4/30 ？
Today
MP2
3/1
OKTB
3/20
727ICA B3
(8155) Leading
PEC/FEC
12/1
DCV
8/30
MP1
2/19
CX821
(8295) Leading
DCV
9/29
PEC
12/22
FEC
1/19
TT
1/31
PP
4/3
MP1
5/29
8295 Development Plan
OTA4
12/30 ？
CX821
(8295) SW Integration
DCV0
5/20
DCV1
6/29
DCV2
8/3
DCV3
9/14
DCV4
10/12
R00
11/9
R04
12/14
R06
2/1
R07
3/7
Coding
Test & Debug
Validation
APK Complete
4/14
Completed
7/24
Bug Free
6/13
Coding
Test & Debug
Full
APK Complete
5/15
9/1
Bug Free
7/15
R07.1
4/11
OKTB
3/26
DCV2
8/17
Mode Card feature has too many vehicle interface, for efficiency, need to book dedicated test vehicle
1500 case & 8 loops, each loop need 2 weeks full validation and 0.5 week for bug regression.
  For CX727, 2.5 weeks x 8 + B2 OTA S/O 4 weeks =24 weeks
  For CX821, 2.5 weeks x 8 =20 weeks
Full
10/18
DCV3
9/28
Full
11/10
DCV4
10/26
Full
12/7
R00
11/23
Full
Full
Full
Full
R04
R06
R07
R07.1

## Slide 4: Mode Card feature delivery overall plan – CXL (WIP)
需要确认HMI的接口人, @Tao Yali 11/15
kick-off meeting @Anthony&Dekang 11/16
Detailed UE/UI delivery Plan @Tao Yali 11/18
PRD冻结，involve HMI, 作为出UE的重要依据 @Ni Anthony 11/25
需要上CCM meeting（TBD） @Dekang&Anthony 11/21
Review 供应商报价合理性 @Geng Dekang
找Relax Mode供应商报价白噪声 11/21
UE签收完成后,In-house 开始开发 @Yu Ruizhe xx/xx
Lead Test Case design @Geng Dekang
给供应商下PO 12/12
SPEC & FMA @Geng Dekang xx/xx
Book实车资源用于测试 @Geng Dekang
以11/28开始，UE输出1-2week ，review  S/O
UE确定后，开始UI ，4 week, review  S/O
Demo: 露营模式进入条件，日间行车灯 off + HVAC on， 不满足进入条件就退出

## Slide 5: Mode Card 1.0 & Camp Scene delivery overall plan – CXL (WIP)
10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
UE
11/28
S/O
1/17
8155 Development Plan
727ICA B2
(8155)
MP1
1/31
OTA2
6/30 ？
OTA3
9/30 ？
OTA1
4/30 ？
Today
MP2
3/1
OKTB
3/20
727ICA B3
(8155) Leading
PEC/FEC
12/1
DCV
8/30
MP1
2/19
Scoping Plan
Final
Scoping
11/10
Place
PO
12/30
PRD
Frozen
11/25
UI UE Design
CX821
(8295) Leading
DCV
9/29
PEC
12/22
FEC
1/19
TT
1/31
PP
4/3
MP1
5/29
UE
1/3
S/O
3/6
8295 Development Plan
OTA4
12/30 ？
UI UE Design
CX821
(8295) SW Integration
DCV0
5/20
DCV1
6/29
DCV2
8/3
DCV3
9/14
DCV4
10/12
R00
11/9
R04
12/14
R06
2/1
R07
3/7
Coding
Test & Debug
Validation
APK Complete
4/14
Completed
7/24
Bug Free
6/13
Coding
Test & Debug
Validation & debug
APK Complete
5/15
Sprint x
10/15
APK 1st formal
Release
7/15
R07.1
4/11
UI
1/3
UI
2/3
OKTB
3/26