## Slide 1: Mode Card 1.0 CX727 delivery overall plan (WIP)
11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
UE
11/28
8155 Dev Plan
S/O
12/26
Today
Scoping Plan
Final
Scoping
11/10
PRD
Frozen
11/25
Coding
V0
12/5
V1
12/12
S/O
1/17
V0
12/26
V1
1/3
UI
12/5
HLD
12/6
V0
12/19
V1
12/28
LLD
12/20
V1
1/4
SW
12/23
Test & Debug
Test
4/17
2nd
7/30
Validation
6/19
1st
7/10
727ICA B2
(8155)
OTA1
7/15
OTA2
9/30 ？
OKTB
3/20 5/9
727ICA B3
(8155) Leading
PEC/FEC
12/1
DCV
8/30
OTA3
12/30 ？
DEMO for
Camp Mode
2/24->2/28
TC completed
2/10
TC Design
12/12
8155 Test Plan
UE
3/1
S/O
3/28
V0
3/7
V1
3/14
S/O
4/10
V0
3/20
V1
4/3
UI
3/7
HLD
3/8
V0
3/20
V1
3/29
LLD
3/21
V1
3/30
Legend
Mode Cade & Camp
Pet & Battery Save
APK completed
4/14->4/18
APK completed
6/27
TC completed
4/24
TC Design
3/8
Final
Scoping
1/19
PRD
Frozen
2/10
OTA3 integration
8/8
9/5
Validation
8/22
SW integrate
6/19
SW integrate
7/28
Screensaver
&Audio
2/10
Test
6/28
需要在2/3提供1个布谷鸟闹铃资源给inhouse开发
需要在2/10提供动效资源给inhouse开发,先找资源做placeholder,3月提供资源,提前给HMI review
拖拽功能控件独立出来，放到后面去实现，预估至少一周的effort

## Slide 2: Mode Card 1.0 CX821 delivery overall plan (WIP)
11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
8295 Dev Plan
UE
1/16
Today
Scoping Plan
Final
Scoping
11/10
PRD
Frozen
11/25
Coding
V1
1/20
S/O
2/10
S/O
2/28
V1
2/17
UI
2/6
HLD
1/30
V1
2/9
LLD
2/10
V1
2/16
SW
2/10
Test & Debug
Test
6/7
9/1
Validation
8/17
CX821
(8295) Leading
DCV
9/29
PEC
12/22
CX821
(8295) SW Integration
DCV0
5/20
DCV1
6/29
DCV2
8/3
DCV3
9/14
DCV4
10/12
R00
11/9
R04
12/14
TC Complete
3/17
TC Design
2/11
8295 Test Plan
Legend
Mode Cade & Camp
Pet & Battery Save
S/O
4/28
UE
4/11
V1
4/18
S/O
5/12
V1
4/28
UI
4/18
HLD
4/19
V1
4/25
LLD
4/24
V1
4/28
Final
Scoping
1/19
PRD
Frozen
2/10
APK completed
6/6
APK completed
7/25
TC Complete
5/30
TC Design
4/18
SW Integrate
8/1
SW Integrate
9/12
10/15
Validation
9/23
1. 需要在2/20先提供camp mode切图给inhouse开发
SW
5/15

## Slide 3: Mode Card 1.0 test requirement (WIP)
10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
8155 Development Plan
727ICA B2
(8155)
MP1
1/31
OTA2
6/30 ？
OTA3
9/30 ？
OTA1
4/30 ？
Today
MP2
3/1
OKTB
3/20
727ICA B3
(8155) Leading
PEC/FEC
12/1
DCV
8/30
MP1
2/19
CX821
(8295) Leading
DCV
9/29
PEC
12/22
FEC
1/19
TT
1/31
PP
4/3
MP1
5/29
8295 Development Plan
OTA4
12/30 ？
CX821
(8295) SW Integration
DCV0
5/20
DCV1
6/29
DCV2
8/3
DCV3
9/14
DCV4
10/12
R00
11/9
R04
12/14
R06
2/1
R07
3/7
Coding
Test & Debug
Validation
APK Complete
4/14
Completed
7/24
Bug Free
6/13
Coding
Test & Debug
Full
APK Complete
5/15
9/1
Bug Free
7/15
R07.1
4/11
OKTB
3/26
DCV2
8/17
Mode Card feature has too many vehicle interface, for efficiency, need to book dedicated test vehicle
1500 case & 8 loops, each loop need 2 weeks full validation and 0.5 week for bug regression.
  For CX727, 2.5 weeks x 8 + B2 OTA S/O 4 weeks =24 weeks
  For CX821, 2.5 weeks x 8 =20 weeks
Full
10/18
DCV3
9/28
Full
11/10
DCV4
10/26
Full
12/7
R00
11/23
Full
Full
Full
Full
R04
R06
R07
R07.1

## Slide 4: Mode Card _ 埋点需求
Mode card 运行时间 + 使用频率
Mode card 推荐场景 选用情况 + 使用频率
Mode card 自定义场景 条件/应用 选用情况 + 数据分析
Mode card 进入方式 （launcher/VR/quick panel）
Mode card 异常情况 （异常退出等）

## Slide 5: Boundary Diagram – Mode Card For CX727 8155 (WIP)
Android BSP
HAL/Framework
Ford API
HMI
MCU
Other
APPs
Mode Card
APIM
Navigation
VR
Bluetooth
Online Video
Launcher
HVAC
Media
Users
- Driver
- Passenger
- Other
Users
- Driver
- Passenger
- Other
ECG
CAN
Ethernet
BCM
HS1
Door Ajar Switch
Door Open/Close
Window/Mirror Position
Ignition Status
MS1
HVAC_RCCM
HS2
RCM
Seatbelt Status + seat occupant (Passenger)
MS1
DSM
A/C, Fan, Temperature……
Seat Status
FD1
HPCM
Vehicle Speed & DTE
SCCM
LIN
Window Switch
Mirror switch
Push Button
DRL/Day Night
Rain sensor
HS2
External
Temperature
Ambient Light
LIN
HS2
GSM
Gear Position
WIRE
DCU
WIRE
WIRE
MS1
AC Charging Status
BCCM
HS1
BECM
HS1
DC Charging Status
OBCC
HS1
SOC
Legend
Physical Interface
Energy Transfer
Data Transfer
External Influence
System Boundary
lock Status
Key/Phone/…
WIRE
EV APP
SMS
Call
ABS
FD1
SDM
IVISL
Ford Cloud
Alert
Environment
External
PM2.5
Internal
PM2.5
Internal
Temperature

## Slide 6: Boundary Diagram – Mode Card For CX821 (WIP)
Android BSP
HAL/Framework
Ford API
HMI
MCU
Other
APPs
Mode Card
APIM
Navigation
VR
Bluetooth
Online Video
Launcher
HVAC
Digital Scent
Users
- Driver
- Passenger
- Other
Users
- Driver
- Passenger
- Other
ECG
Digital Scent
LIN
ALCM
AL Dynamic
HS3
Private CAN
CAN
Ethernet
BCM
HS1
Door Switch
Door Open/Close
Window/Mirror Position
Ignition Status
MS1
HVACRCCM
HS2
RCM
Seatbelt Status + Seat occupant
MS1
DSM
A/C, Fan, Temperature……
Seat Status
FD1
HPCM
Charging Status
Vehicle Speed & DTE
Ford Cloud
SCCM_GSM
Gear Position
BCCM_OBCC
HS2
BECM
LIN
Window Switch
Mirror Switch
Push Button
DRL/Day Night
Rain/Light Sensor
HS2
HS2
SCMG
SCMH
MS1
Massage Status
DCU
WIRE
WIRE
AL Static
LIN
MS1
SOC
Key
Physical Interface
Energy Transfer
Data Transfer
External Influence
System Boundary
Lincoln Way
SMS
Alert
Lock Status
Push Button
WIRE
Call
FD1
ABS
SDM
IVISL
Environment
External
Temperature
Internal
PM2.5
Internal
Temperature
External
PM2.5

## Slide 7: Mode Card feature delivery overall plan – CXL (WIP)
需要确认HMI的接口人, @Tao Yali 11/15
kick-off meeting @Anthony&Dekang 11/16
Detailed UE/UI delivery Plan @Tao Yali 11/18
PRD冻结，involve HMI, 作为出UE的重要依据 @Ni Anthony 11/25
需要上CCM meeting（TBD） @Dekang&Anthony 11/21
Review 供应商报价合理性 @Geng Dekang
找Relax Mode供应商报价白噪声 11/21
UE签收完成后,In-house 开始开发 @Yu Ruizhe xx/xx
Lead Test Case design @Geng Dekang
给供应商下PO 12/12
SPEC & FMA @Geng Dekang xx/xx
Book实车资源用于测试 @Geng Dekang
以11/28开始，UE输出1-2week ，review  S/O
UE确定后，开始UI ，4 week, review  S/O
Demo: 露营模式进入条件，日间行车灯 off + HVAC on， 不满足进入条件就退出

## Slide 8: Mode Card 1.0 & Camp Scene delivery overall plan – CXL (WIP)
10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
UE
11/28
S/O
1/17
8155 Development Plan
727ICA B2
(8155)
MP1
1/31
OTA2
6/30 ？
OTA3
9/30 ？
OTA1
4/30 ？
Today
MP2
3/1
OKTB
3/20
727ICA B3
(8155) Leading
PEC/FEC
12/1
DCV
8/30
MP1
2/19
Scoping Plan
Final
Scoping
11/10
Place
PO
12/30
PRD
Frozen
11/25
UI UE Design
CX821
(8295) Leading
DCV
9/29
PEC
12/22
FEC
1/19
TT
1/31
PP
4/3
MP1
5/29
UE
1/3
S/O
3/6
8295 Development Plan
OTA4
12/30 ？
UI UE Design
CX821
(8295) SW Integration
DCV0
5/20
DCV1
6/29
DCV2
8/3
DCV3
9/14
DCV4
10/12
R00
11/9
R04
12/14
R06
2/1
R07
3/7
Coding
Test & Debug
Validation
APK Complete
4/14
Completed
7/24
Bug Free
6/13
Coding
Test & Debug
Validation & debug
APK Complete
5/15
Sprint x
10/15
APK 1st formal
Release
7/15
R07.1
4/11
UI
1/3
UI
2/3
OKTB
3/26