## CustomerFacing
[10 empty] | DCV Belta |  | DCV0 |  | DCV1 |  | DCV2 |  | DCV3 |  | R00 |  | R04 |  | R05 |  | R06 |  | R07 |  | Resouces
Feature_ID | Feature_Name | IVI SW Version | PO | FO/TL | FO/TL Supervisor | Test Owner | CX771 FNV2.1 Mar-2024 | CX821 FNV2.1 Mar-2024 | Release Test Case | test scenario | pass rate | test scenario | pass rate | test scenario | pass rate | test scenario | pass rate | test scenario | pass rate | test scenario | pass rate | test scenario | pass rate | test scenario | pass rate | test scenario | pass rate | test scenario | pass rate | DCV Vehicle | Comments
SYNC+_0296 | 4G/5G Entertainment Connectivity Subscription | DCV 1 | LI, Linan (L.) | Zhai, Qingqing (Q.) | Lu, Chao (C.) <clu42@ford.com> |  | Y | Y | [5 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
SYNC+_0265 | 4G/5G Uu车路协同 V2I Lite (Production) | DCV 1 | Li, Gerry (C.) | Zhang, Wei (W.) | Li, Yifei (Y.) <nli26@ford.com> |  | Y | Y | [5 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.2
SYNC+_0303 | Baidu Map 6.0 | DCV 1 | Chen, Eva (X.) <xchen87@ford.com> | Yao, Tristan (Lan) <LYAO17@ford.com> | Chen, Emma (J.) |  | Y | Y | TBD |  |  |  |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.25
NewFeature | Carplay | DCV 3 | Null | Xu, Harriet (J.) | Chen, Emma<jchen276@ford.com> |  | Y | Y | April-30 | [8 empty] | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.25
SYNC+_Z0032 | CCS (Customer Connectivity Setting) |  |  | Gu, Regina (Q.) <QGU12@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | Duplicate | Duplicate
SYNC+_0304 | Dash Camera |  | Li, Gerry (C.) | Niu, Kobe (Y.) | Chen, Yang (Y.) |  | Duplicate | Duplicate
NewFeature | EV Charge Programming 2.0 |  | Zhang, Sherry (Wen) <wzhang59@ford.com> | Peng, Ivan (F.) <FPENG6@ford.com> | Wang, Johnny (J.) <jwang308@ford.com> |  | Duplicate | Duplicate
SYNC+_0298 | Digital Muse |  | Yu, Yaxing (Y.) <YYU55@ford.com> | Cheng, Jesse (J.) | Chen, Emma (J.) |  | Y | N
SYNC+_0294 | EV Trip Planner（migrate to Baidu Map） | DCV 1 | Zhang, Sherry (Wen) <wzhang59@ford.com> | Shi, Stella (J.) <jshi32@ford.com>; | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | [5 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.2
SYNC+_0023 | EV Unique Chime (CDX727 lead) |  |  | Yu, Diven (D.W.) <dyu12@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | Y | N
SYNC+_0267 | HUD Based AR |  | Li, Gerry (C.) | Zhang, Yong (Y.) | Yu, Diven (D.W.) <dyu12@ford.com> |  | Y | N
NewFeature | Interactive EVSE（Engine Sound Simulator (sound simulation thru inside speaker)） | DCV 2 | Assignee from Jerry Team | Li, Xuedong (X.) | Chen, Emma<jchen276@ford.com> |  | Y | Y | TBD |  |  |  |  | / |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.05
SYNC+_0266 | Lancher - 3D Car Model with vehicle controls | DCV 1 | Shen, Carol (J.) | Wang, Pengcheng (P.) | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | [5 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.2
TBD | Low Range Alert | DCV 2 | Dong, Liang | Xu Zhang (phase 1) | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | [7 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
NewFeature | Multi-Zone Voice Control |  | Lu, Joseph | Yu, Diven (D.W.) <dyu12@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | Y | N
NewFeature | Muse 7.1+KTV | DCV 1 | Yu, Yaxing (Y.) <YYU55@ford.com> | Cheng, Jesse (J.) | Chen, Emma (J.) |  | N | Y | TBD |  |  |  |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
TBD | Plug and Charge |  | Sherry, Zhang | Ivan, Peng | Wang, Johnny (J.) <jwang308@ford.com> |  | Duplicate | Duplicate
SYNC+_0136 | Relax Mode 舒享时分Relax/自由秘境At Ease |  | Gao Richard | Zhou, Calvin (.) | Wang, Johnny (J.) <jwang308@ford.com> |  | Duplicate | Duplicate
NewFeature | My Sound Space Lite |  | Assignee from Jerry Team | Wang, Fin (X. Y.)<xwang65@ford.com> | Chen, Emma<jchen276@ford.com> |  | TBD | TBD
SYNC+_0010 | Screen Based AR |  | Chen, Eva (X.) <xchen87@ford.com> | Zhang, Yong (Y.) | Yu, Diven (D.W.) <dyu12@ford.com> |  | Y | N
SYNC+_0019 | USB视频播放 Video- USB video | DCV Belta | 4_more_functional_no_PO | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Chen, Emma (J.) |  | Y | Y |  |  |  | Smoke |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
NewFeature | Voice Recognition Systems (Jupiter Lite) | DCV 0 | Joseph Lu | Zhou, Dan (D.) | Yu, Diven (D.W.) <dyu12@ford.com> |  | Y | Y | TBD |  |  |  |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.05
SYNC+_0165 | 个性化设置记忆 Enhanced Memory |  | IVI-Wu, Shengjun; APP - Liu, Tony(zhichao) |  |  |  | Duplicate | Duplicate
SYNC+_0137 | 个人时光 Smart Scene - Personal Enjoyment | DCV 1 | Gao Richard | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | [5 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
SYNC+_0014 | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) | DCV Beta | 4_more_functional_no_PO | Xu, Amy (X.) <xyafei@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | Y | Y |  | Smoke |  | Full |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
SYNC+_0126 | 升级版紧急救援/服务 eCall |  | 1_temp Zhang, Rui (R.) <RZHANG63@ford.com> | Lu, Ying (Y.) | Wang, Johnny (J.) <jwang308@ford.com> |  | Duplicate | Duplicate |  | Smoke |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full
SYNC+_0223 | 多模块空中升级 Multi Module OTA (MMOTA) (including: USB Update for TCU and ECG; IVI VMCU, CCPU...) |  | 4_more_functional_no_PO | Pan, Yuan (Y.) <ypan23@ford.com> | Pan, Yuan (Y.) <ypan23@ford.com> |  | Duplicate | Duplicate
SYNC+_0129 | 儿童座椅报警Child Restraint System (CRS) - ( e.g BT Child seat 蓝牙座椅) | DCV Beta | 4_more_functional_no_PO | Xu, Amy (X.) <xyafei@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | Y | Y |  | Smoke |  | Full |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
SYNC+_0269 | 天气 Weather | DCV Beta | 0_Not yet assigned | Shi, Stella (J.) <jshi32@ford.com> | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y |  | Full |  | Full |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.2
SYNC+_0106 | 手机钥匙Phone as key(PaaK) |  | Liu, Zichao (Tony) <zliu83@ford.com> | Zhang, Yan (Y.) <YZHAN481@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | Duplicate | Duplicate
SYNC+_0139 | 客人模式Smart Scene - Guest Mode | DCV 1 | Gao Richard | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | [5 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
SYNC+_0152 | 时空秘信Surprise/Secret message |  | Lee, Grace (G.) <glee51@ford.com> | Kan, Bing (B.) <BKAN@ford.com> | Wang, Johnny (J.) <jwang308@ford.com> |  | N | N
SYNC+_0132 | 智能新风Auto Air Refresh (AAR) G2 (Blue Shield) |  | 0_Not yet assigned | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) | Wang, Johnny (J.) <jwang308@ford.com> |  | Duplicate | Duplicate
SYNC+_0140 | 智慧指令 Smart Scene - Smart Order | DCV 1 | Gao Richard | Shi, Stella (J.) <jshi32@ford.com>; Zou, Yujuan (Y.) <yzou32@ford.com> (HMI) | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | [5 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
SYNC+_0015 | 本地音乐-USB音乐 USB music/蓝牙音乐 BT music | DCV Beta | 4_more_functional_no_PO | Xiang, Zhengxi（USB） Xu, Amy（蓝牙） | Chen, Emma (J.) |  | Y | Y |  | Smoke |  | Full |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.05
SYNC+_0175 | 消息&消息中心 notification & notification center 百度强依赖 | DCV 0 | Yao, Jiang (J.) <JYAO19@ford.com> | Zhang, Xu (X.) <XZHAN304@ford.com> | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | TBD |  |  | Full |  | Full |  | Full |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.15
SYNC+_0020 | 爱奇艺 (在线视频APP) Video - Streaming video Iqiyi | DCV 3 | Wang Yu YWANG536 | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Chen, Emma (J.) |  | Y | Y | TBD | [8 empty] | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.05
NewFeature | 爱趣听Aiquting | DCV 0 | Jessica Yang | Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> | Chen, Emma<jchen276@ford.com> |  | Y | Y | TBD |  |  |  |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
SYNC+_0125 | 用户反馈Customer Feedback 2.0 | DCV 0 | SUN, Qianwen (Q.) | Xie, Jie (J.) <JXIE49@ford.com> | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | TBD |  |  | Full |  | Full |  | Full |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
SYNC+_0013 | 蓝牙电话 Bluetooth Phone | DCV Beta | 4_more_functional_no_PO | Xu, Amy (X.) <xyafei@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | Y | Y |  | Smoke |  | Full |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.1
SYNC+_0118 | 车机端电子版用户手册 E-Manual 2.0 |  | WEI, Xingna (X.) | Peng, Ivan (F.) <FPENG6@ford.com> | Wang, Johnny (J.) <jwang308@ford.com> |  | Duplicate | Duplicate |  | Smoke |  | Full |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full
SYNC+_0021 | 视频、音乐、图片DLNA投屏到车机显示器区分主副驾/Video Playback and Video and Photo project to Display(Driver and Passenger) via DLNA | DCV Beta | 4_more_functional_no_PO | Yu, Diven (D.W.) <dyu12@ford.com> | Yu, Diven (D.W.) <dyu12@ford.com> |  | Y | Y |  | Smoke |  | Full |  | Full |  | Smoke |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.25
SYNC+_0122 | 车辆警示与车辆状态 Vehicle Health Alert and Status(VH) |  | Chen, Wei (W.) <WCHEN122@ford.com> | Chen, Wei (W.) <WCHEN160@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | Duplicate | Duplicate
SYNC+_0114 | 远程空调控制 Remote Climate Control (RCC) via FordPass/Lincoln Way |  | Liu, Zichao (Tony) <zliu83@ford.com> | Lin, Shawn (X.) <xlin17@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | Duplicate | Duplicate
SYNC+_0112 | 远程解锁/启动 Remote Door Lock/Engine Start |  | Liu, Zichao (Tony) <zliu83@ford.com> | Lin, Shawn (X.) <xlin17@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | Duplicate | Duplicate
SYNC+_0262 | 远程车门关闭状态显示/查看 Vehicle Locking Status Check; |  | Liu, Zichao (Tony) <zliu83@ford.com> | Lin, Shawn (X.) <xlin17@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | Duplicate | Duplicate
SYNC+_0113 | 远程鸣笛闪灯 Vehicle Announcement via FordPass |  | Liu, Zichao (Tony) <zliu83@ford.com> | Lin, Shawn (X.) <xlin17@ford.com> | Lu, Chao (C.) <clu42@ford.com> |  | Duplicate | Duplicate
SYNC+_0042 | 语音助手VPA 2.0 (形象） | DCV 1 | wang, yujun | Xie, Jie (J.) <JXIE49@ford.com> | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | [5 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.2
NewFeature | 账号 MVP | DCV 2 | Li, Nian (N.) | Kan, Bing (B.) <BKAN@ford.com> | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | TBD | [6 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.25
SYNC+_Z0282 | 车机管家 | DCV 3 | Yao, Jiang jyao19 | Gu, Regina Xuliang Zhang, Xiaolei | Lu, Chao (C.) <clu42@ford.com> |  | Y | Y | [9 empty] | Full |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.05
SYNC+_0128 | 道路救援Road Side Assitance (RSA) | DCV 0 | Liu, Zichao (Tony) <zliu83@ford.com> | Xue, Peng(pxue1) | Wang, Johnny (J.) <jwang308@ford.com> |  | Y | Y | TBD |  |  | Full |  | Full |  | Full |  | Smoke |  | Full |  | Full |  | Full |  | Full |  | Full |  | 0.05
NewFeature | Mode Card 1.0 (场景卡片1.0) | DCV 2 | Ni Anthony hni1@ford.com | Ni Anthony hni1@ford.com | Chen, Emma (J.) |  | Y | Y | 2023-04-28 | [6 empty] | smoke_1 |  | smoke_2 |  | Full |  | Full |  | Full |  | Full |  | Full
Note on I12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: request to double check with 821 program
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 声音空间分割前后排，不同场景音效会播放给对应person
Note on H22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CX771: AR Navigation will go to 27” IVI HMI bundle with Navigation Map
Note on H50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pony VPA Reply: back to 蓝胖子
Note on H51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: pending on PO's new information
Note on I51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: pending on PO's new information
Note on Q54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 测试日期： 8/18-8/25 测试周期：1week 测试内容： 1. mode card 应用的进入，退出； 2. 各个推荐场景的进入，退出按钮点击； 3. 整体功能框架，界面检查； 4. UGC 页面的进入和退出 5. UGC 新卡片的创建和保存 6. UGC新卡片的运行和退出按钮点击 Reply: 1. 各个场景卡片的选择，进入主界面和退出 2. 各个推荐卡片的功能项检查 （非功能运行）
Note on S54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 测试日期： 9/22-9/29 测试周期：1week 测试内容： 1. mode card 应用的进入，退出； 2. 各个推荐场景的进入，退出按钮点击； 3. 整体功能框架，界面检查； 4. UGC 页面的进入和退出 5. UGC 新卡片的创建和保存 6. UGC新卡片的运行和退出按钮点击 Reply: 1. 各个场景卡片的选择，进入主界面和退出 2. 各个推荐卡片的功能项检查 （非功能运行） Reply: 支持DCV造车版本： － 空调类 － 影音类 (视爱趣听app 状况) － vehicle setting 类
Note on U54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 实车全功能sign off 测试： DCV4 软件版本 测试时间：10/30-11/10 根据车辆安排调整） 测试周期： 2weeks - 手动测试：全功能 - 自动化测试： 全功能 （需要做脚本，视脚本情况而定） R00 版本： 测试时间： 11/24-12/8 （根据车辆安排调整） 测试周期： 2weeks - 手动测试：全功能 - 自动化测试： 全功能