## Phase4 Master feature list V2.x
ID | Category | Function | Feature |  | Effort Estimation | [15 empty] | FO/Interface | [5 empty] | CD542 |  | CX727 | U725 | P702 | U554 MCA | U625ICA | CD764 | Cost Type | EOL Configuration |  | MRD review |  |  |  |  | 7 |  | Next Resp. | [7 empty] | SW release | 单屏-EMC |  | 27“屏幕-EMC |  | CX727 DCV0 | DCV1 60%? | DCV2 FULL FUNTION | DCV3 | R00/PEC | R04/FEC | R05/TT | R06/PP
|  |  |  | Feature carried from Phase 1/2/3 | Desay | Baidu | Ford SW | R&R | DCV0 MRD before 2019-11-20 | DCV1 60% MRD before 2020-02-14 | 100% MRD Before 2020-03-1 | Feature Signoff date | MRD Delivery Time | UE Delivery Time | UE Sign Off Time | UI Delivery Time | UI Sign Off Time | Ford SPSS/PRD | Supplier's output (MRD, Q&A, RD…) | HMI interaction Spec | Ford Feature owner | Ford HMI Lead | BAIDU FO | DESAY FO | Comments | KO Meeting | Ambient/Trend | Titanium/ST Line | Mid/High | Ford Bronco SUV | Ford Raptor F-150 Pickup truck | Lincoln Navigator Large SUV (3 row seat) | Explorer | Lincoln Sedan | License/ED&T |  | File Location | Review status | risk | # of review | Planned Available date | Actual available date | Planned release date | Actual release date |  | Comments | Open item | FNV2 | Category | sub-function | IVI validate | 供应商模块 |  | 2020-02-14 | 2020-03-19 | 2020-02-21 | 2020-03-29 | 2020-03-06 | 2020-05-06 | 2020-07-06 | 2020-08-26 | 2020-10-14 | 2020-11-20 | 2021-01-06 | 2021-04-07
1 | Basic features | EESE/System | Autosar |  | 100% | 0% | NA | Desay | x | x | x |  | N/A |  |  |  |  | AUTOSAR SOW_2019.0-WGC1NJ5520MQ2-2.zip AUTOSAR\AUTOSAR SOW_2019.0-WGC1NJ5520MQ2.zip AUTOSAR\AUTOSAR SOW_2019.0.zip | 不需要输出MRD | N/A | Jian, Ashley (Yao.) <yjian@ford.com> / Song, Robert (J.) <jsong30@ford.com> | N/A |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close | Mid |  | N.A | N.A | N.A | N.A | N.A | Desay Fully meet. No QA |  |  | Basic function | basic | bar: 2020-03-06 to 2020-05-06
2 | Basic features | EESE/System | Ford Ethernet |  | 90% | 0% | 10% | Desay | x - IP function | x | x |  | 2019-11-08 |  |  |  |  | AutomotiveEthernetHardwareReviewTestMethod-00.06.03.400-AB.docx AutomotiveEthernetLinkImplementationSpecification-00.06.01.001-AC.docx AutomotiveEthernetModuleLevelDesignVerificationMethod-00.06.01.301-AB.docx AutomotiveEthernetPhysicalLayerSpecification-00.06.03.003-AB.docx AutomotiveEthernetSoftwareReviewChecklist-00.06.01.402-AB.docx AutomotiveEthernetSwitchChecklist-00.06.01.403-AA.docx AutomotiveEthernetSwitchImplementationSpecification-00.06.01.002-AA.docx AutomotiveEthernetSystemLevelDesignVerificationMethod-00.06.01.313-AB.docx | Ford_MRD_Ethernet_V02.docx | N/A | Guo, Cheng Cheng (C.) <cguo12@ford.com> | N/A |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close | Mid |  | 2020-01-10 | 2020-02-04 | 2020-01-17 | 2020-01-20 | N.A | 1/13/2020: FO info clear, MRD to be available 1/14 2/5/2020: sign off |  |  | Basic function | basic | bar: 2020-03-06 to 2020-05-06
3 | Basic features | EESE/System | FPD LINK III |  | 100% | 0% | NA | Desay | x | x | x |  | N/A |  |  |  |  | FPDLinkIIICableandConnectorAssemblyDesignVerficationChecklist-00.06.01.306-AA.docx FPDLinkIIICableandConnectorAssemblySpecification-00.06.01.005-AA.docx FPDLinkIIIImplementationReviewChecklist-00.06.01.405-AA.docx FPDLinkIIILinkImplementationSpecification-00.0 | 不需要输出MRD | N/A | Guo, Cheng Cheng (C.) <cguo12@ford.com> | N/A |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close | Mid |  | N.A | N.A | N.A | N.A | N.A |  | 27" not ready, open item list will be provided after migrating this screen. / Feb. 2020 12/24/2019: ask Desay to fill checklist |  | Basic function | basic | bar: 2020-03-06 to 2020-05-06
4 | Basic features | EESE/System | Fully Ford ECU Diagnostic&EOL | Y | 90% | 10% | NA | Desay |  | x | x |  | 2020-01-10 |  |  |  |  | Phase4 Diag Req Sheet.xlsx | 合并到NO110 | N/A | Tian, Yuan (EESE.) <ytian22@ford.com> &Wang, Fin (X.Y.) <xwang65@ford.com> | N/A |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | CDD是由DESAY做 SPEC由Ford提供 |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  | 1 | 2019-12-23 | 2019-12-23 | 2019-12-30 | 2019-12-30 | N.A | Mamei: check when able to finalize the requriements. 12/24/2019: QA upload today 12/27/2019: wait feedback from Desay 12/30/2019: desay FO confirmed, GitHub updated.Close |  |  | Basic function | EOL | x | bar: 2020-05-06
5 | Basic features | EESE/System | Ford Cyber Security Requirements | Y | 50% | 50% | NA | Desay/Baidu |  | x | x |  | NA |  |  |  |  | App_signing_requirements_ver 1.3.pdf Bluetooth_Security_Spec_1.0.docx C.13 Ford_CyberAssurance-SOW_ReleaseV1.3(EE).doc FESN Generation Spec_V0.6.pdf IVI Security Requirements v7.docx Key Material Requirements.docx Key Packaging Spec_V0.72.pdf Operating_Systems_Security_Requirements_RC3.docx Phase4 Security RR_20191024 .xlsx S26_Secure_Channel_v1_04_Release.doc Vehicle and Mobility Security Data Logging Standard.pdf Vehicle-Mobility-Security-Data-Logging_Standard_v06-04Apr18.pdf Vehicle_HotSpot_and_AP_Client_Specification_v.2_final.pdf Vehicle_to_Cloud_Security_Spec_1.1.pdf | Desay -不需要输出MRD Baidu - 车机管家MRD | N/A | Ding, Dean (W.) <wding14@ford.com> / Huang, Eric (E.H.) <chuang98@ford.com> | N/A | niubingshuai <niubingshuai@baidu.com> | Ding Yunrong(Yunrong.Ding@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2019-12-30 | 2020-01-06 | 2020-01-06 | 2020-03-03 | F | Desay: Security_QA.xlsx Baidu: 1/2/2020: MRD available, Ford FO check 1/8/2020: Baidu mail FO to push the feedback 1/9/2020: send today 1/10/2020: postpone to today 1/13/2020: SunYing mail 2/6/2020: sign off for CD542 3/3/2020: scope change: key package process migrated from Supply feed. - confrmed with FO. | 2/6/2020: other program status not clear |  | Basic function | Cyber security |  | 安全 | bar: 2020-05-06
6 | Basic features | EESE/System | Ford Software development Requirements |  | 50% | 50% | NA | Desay |  | x | x |  | NA |  |  |  |  | 2018_1_Release_of_Generic_eSOW_SW_Attachment.zip |  | N/A | Jian, Ashley (Yao.) <yjian@ford.com> | N/A | sunying <sunying05@baidu.com> | Liu Xiaogang |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | N.A |  |  | N.A | N.A | N.A | N.A | N.A | Output: regular TDR meeting minutes |  |  | N.A | N.A | bar: 2020-05-06
7 | Basic features | EESE/system(inhouse) | Implement/Integrate Ford SOA Structure |  | 90% | 10% |  | Desay |  | x | x |  | 2020-01-10 |  |  |  |  | pending by Dapeng's input | SOAGateway MRD-v0.2.docx | N/A | Liu, Dapeng (D.) <dliu79@ford.com> | N/A |  | Ding Yunrong(Yunrong.Ding@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2020-01-10 | 2020-02-28 | 2020-01-17 | 2020-03-02 | D | 1/13/2020: Desay check today 2/12/2020: plan to close this before 2020/2/28: not linked to UE/UI, requirements are clear, send mail to close 3/2/2020: development on-going, tracking separately |  | x | FNV2 | FNV2-basic | bar: 2020-05-06
8 | Vehicle Features/Interfaces | EESE/System | Welcome&Farewell | Y | 90% | 10% | NA | Desay |  | x | x |  | 2020-12-20 |  |  | 2020-01-13 | 2020-01-27 | ReqSTD-2019-08-20-21-45_FORD.pdf ReqSTD-2019-08-20-21-46_LINCOLN.pdf WelcomeFarewell_Spec v2.pdf | Ford_MRD_WelcomeFarewell.docx | H22g_SYNC4_Welcome_Power_Modes_RELEASED_v1_02_MY21 | Wu, Bella (Y.) <ywu150@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Pan Juan(Juan.Pan@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-09 | 2020-01-13 | 2020-01-16 | 2020-01-16 | N.A | 12/25/2019: info new date today 12/30/2019: no new plan 1/6/2020: replan to 1/9 1/10/2020: Desay on-going 1/13/2020: MRD available today 1/16/2020: sign off |  |  | Vehicle related | Welcome/farewell | bar: 2020-05-06
9 | Vehicle Features/Interfaces | EESE/IVI(Roger) | Alerts/Chimes | Y | 90% | 10% | NA | Desay |  | x | x |  | 2019-12-15 |  |  |  |  | Alerts APIM Imp Guide v1.2 May 3, 2017.xlsx Alerts APIM SPSS v1.2 May 3, 2017.pdf RQT-001502-012992_12 Chime Sound Quality.pdf | 合并到NO84 | N/A | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/Alerts_Chime | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2019-12-24 | N.A | Desay: maiil the open questionsm 2019.12.20 12/24/2019: no open item list, confirmed with FO |  |  | Chime management | Chime management | x | bar: 2020-05-06
10 | Vehicle Features/Interfaces | EESE/System | Mykey | Y | 90% | 10% |  | Desay |  |  | x | [6 empty] | MyKey Settings In CenterStack SPSS v1.4 July 9, 2019.pdf | Mykey_Setting.docx |  | Xu, Xiao Kang (X.) <xxu71@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-20 | 2020-02-12 | 2020-02-27 | 2020-02-19 | D | 2/6/2020: supplier to provide plan date 2/12/2020: MRD send to FO 2/19/2020: sign off |  |  | Vehicle related | MyKey
11 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Ford Vehicle Settings On IVI [include: AutoHold, AutoStartStop.] | Y | 90% | 10% |  | Desay |  | x | x |  | 2019-12-15 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx FBMP APIM SPSS v1.3 May 8, 2017 Vehicle Settings APIM SPSS v1.19 Oct 30, 2019 | 【phase4-Vehicle Setting-总结】_ForDesay.xlsx | H31a_SYNC4_Settings_R_v0_40_MY21 H31k_SYNC4_Settings_R_v0_36_MY21 H31k_Supplement_SYNC4_R_v0_10_MY21 | Chen, Emma (J.) <jchen276@ford.com>/Wang, Fin | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/Ford%20Vehicle%20Settings%20On%20IVI | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2020-01-11 | N.A | briefing close. Waiting OIL Plan to frozen one version before 12.23 12/24/2019: delay to today 12/27/2019: wait feedback from Desay 12/30/2019: consolidated OIL and file not archived. 1/6/2020: OIL to be ready on 1/7 1/10/2020: plan to sign off 1/11/2020: sign off | Some HMI open; Configuration bits - to be updated and reviewed by diag/Fin |  | Vehicle related | Vehicle setting | x | bar: 2020-05-06
12 | Vehicle Features/Interfaces | EESE/DI | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | Y | 90% | 10% |  | Desay |  | x | x |  | 2019-12-15 |  |  |  |  | Climate Control CGEA 1.3 APIM Imp Guide ver1.1 Oct 30, 2014.xlsx Climate Control CGEA 1.3 APIM SPSS ver1.1 Oct 30, 2014.docx Climate Control CGEA 1.3 APIM SPSS ver1.1 Oct 30, 2014.pdf | Ford_MRD_空调_TBD_v1.7_20200222.docx 空调页面说明_v1.5.xls 空调页面说明_硬按键软按键.xlsx | H26g_SYNC4_Auto_Air_Refresh_Gen_1_Plus_RELEASED_v2_03_MY21 H26f_SYNC4_Climate_Control_RELEASED_v1_06_MY21 H26h_SYNC4_Climate_Auto_Seats_RELEASED_v1_04_MY21 | Li, Jun (J.) <jli198@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 1 | 2019-12-15 | 2019-12-19 | 2019-12-26 | 2020-02-07 | N.A | reviewed on Dec. 20th; Updated MRD to be ready before 25th. 12/24/2019: 2nd version sent to Ford FO. 12/30/2019: 2nd round meeting conducted, need HMI support for open items. 1/6/2020: Desay update and info date 1/10/2020: on-site review 1/13/2020: Desay consolidate and mail 2/4/2020: FO send out mail. arrange meeting 2/6/2020: meeting today to finalize 2/7/2020: plan to sign off; sign off |  |  | Vehicle related | HVAC | bar: 2020-05-06
13 | Vehicle Features/Interfaces | CVPP | Ford TCU Related features (Modem Reset, WiFi, WiFi Hotspot)- TCU transfer CAN data to IVI | y | 90% | 10% |  | Desay |  | x | x |  | 2019-12-15 |  |  |  |  | WiFi Hotspot OnBoardClient v2 SPSS v1.3 July 15, 2019 | WiFi Hotspot OnBoardClient v2 Imp Guide v1.3_Q&A_20200205.xlsx | H31a_SYNC4_Settings_R_v0_40_MY21 H31i_SYNC4_Vehicle_Hotspot_Settings_RELEASED_v1_02 H31i_InfoBook _Wi-Fi_Hotspot_v0_6 H31j_SYNC4_Connectivity_Settings_R_v0_08_MY21_RELEASED | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu guanghui(Guanghui.Liu@desay-svautomotive.com) & Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2019-12-23 | 2020-01-10 | 2020-01-17 | 2020-02-06 | N.A | Desay development on-going, UE/UI - based on current Desay proposal. 12/23/2019: send MRD to PanYuan 12/24/2019: delay to today 12/27/2019: wait Ford FO - 1/2 1/6/2020: Desay update after internal review 1/10/2020: MRD available, plan on-site review at Shanghai 1/13/2020: contact FO - 86-21-20322959 2/4/2020: plan to sign off 2/6/2020: sign off | to be updated | x | FNV2 | WIFI | x | bar: 2020-05-06
14 | Vehicle Features/Interfaces | EESE/IVI(Roger) | 支持与仪表盘互动/Supporting interaction with cluster（Phone/Media/Navi） | Y | 60% | 40% | NA | Desay |  | x | x |  | 2019-12-15 |  |  |  |  | folder: cluster Interaction |  |  | IVI-Chen, James (J.) <jchen303@ford.com>&IPC Cao, Helen (H.) <hcao22@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Chenxi(Chenxi.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-15 | 2019-12-15 | 2020-03-06 | 2020-03-10 | N.A | briefing close. Waiting OIL from desay 12/23/2019: 2 open items to be clarified by Ford FO. 12/24/2019: send mail to Ford FO. 12/27/2019: wait feedback from Desay 12/30/2019: no mail send to Ford FO. Delay 1/6/2020: plan to sign off 1/10/2020: Desay send out QA 1/13/2020: Desay push FO 2/10/2020: Desay review on-going, planned to be 2020/2/20 2/24/2020: updated MRD availalbe, send out tomorrow 2/28/2020: not linked to UE/UI 3/10/2020: Sign off |  |  | Vehicle related | Cluster | x | bar: 2020-05-06
15 | Vehicle Features/Interfaces | EESE/IVI(Diven) | Zone Lighting (360 Lighting) |  | 95% | 5% |  | Desay |  | x | x | [6 empty] | PRD Zone Lighting PRD v1.13.pdf | Zone Lighting APIM Imp Guide v1.4_20200228.xlsx | H31a_SYNC4_Settings_R_v0_40_MY21 (refer to Zone lighting section) | Yu, Diven (D.W.) <dyu12@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> |  |  | N | N | N | N | Y | N | N | N | ED&T | Y |  | close |  |  | 2020-01-13 | 2020-02-19 | 2020-01-20 | 2020-02-28 | N.A | 1/6/2020: Desay replan 1/13/2020: MRD avaialble today 2/12/2020: plan to close before 2/18 2/14/2020: transfer to EESE @diven 2/24/2020: open item list send out today; |  | x
16 | Vehicle Features/Interfaces | CVPP | Multi Module OTA (including: USB Update for TCU and ECG; IVI VMCU, CCPU...) |  | 90% | 10% |  | Desay |  |  | x |  | 2020-01-05 |  |  |  |  | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf 533310_C_001_In Vehicle Software Update Feature Doc v2.1.pdf 547923_A_001_IVSU Vehicle Function Download Manager v1.0.pdf 584761_A_002_Fast OTA FNV2 IVSU Requirements v1.0.docx IVSU_Cloud_Function_Diff_Generator v1.0.docx IVSU_Vehicle_Function_Diff Updater_ v1.0.docx |  | H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_8_MY21 | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Desay IOV | 文档是否包含TCU OTA？ |  | Y | Y | Y | Y | Y | Y | Y | Y |  | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/MMOTA | delay |  |  | 2020-02-14 |  |  |  | D | 1/6/2020: replan today 1/10/2020: reschedule to DCV2 2/20/2020: Suppliler not officially on board - business pending |  | x | FNV2 | OTA | x
17 | Vehicle Features/Interfaces | EESE/IVI(Diven) | Location Service （仪表指南针，etc.） | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-15 |  |  |  |  | Location Service APIM SPSS v1.10 July 10, 2019 Location Service APIM Imp Guide v1.10 July 10, 2019 | Ford_MRD_LocationService_V03.docx | No HMI UE required as onfirmed with FO. | Yu, Diven (D.W.) <dyu12@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-15 | 2019-12-23 | 2019-12-30 | 2019-01-19 | N.A | Desay prepare questions to Diven for offline check 12/23/2019: MRD send to Diven for check 12/24/2019: delay to today 12/27/2019: pending fedback from Ford FO 1/6/2020: Desay mail to Diven 1/10/2020: Desay provide OIL, plan to sign off 2/5/2020: sign off |  |  | Vehicle related | Navigation | bar: 2020-05-06
18 | Vehicle Features/Interfaces | CVPP | PaaK | Y | 95% | 5% | NA | Desay |  | x | x | [6 empty] | PRD 【更新】【Phase2林肯】PAAK智能共享手机钥匙MRD_2019_4_12-v1.5.pdf | Customer Connectivity Settings Client APIM SPSS v1.4 imp Guide v1.6_20200228.xlsx | H31m_SYNC4_Backup Ignition_R_v1.3_MY21 H31k_SYNC4_Settings_R_v0_36_MY21 | Wang, Cindy (X.J.) <xwang216@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> |  |  | N | Y | Y | Y | N | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-14 | 2020-02-13 | 2020-02-21 | 2020-02-14 | N.A | 2/12/2020: plan to close before 2/18 2/14/2020: sign off |  | x | FNV2 | PAAK | bar: 2020-05-06
19 | Vehicle Features/Interfaces | EESE/System | Ford Enhanced Memory V2 | Y | 45% | 55% |  | Baidu |  | x | x |  | 2020-12-20 |  |  |  |  | SPSS Driver profiles SYNC+ SPSS 03252019.pdf | 【福特phase4】MRD_Enhance memory_CD542_V1.2_2020_02_20 | SYNCFord HMI Requirement_Enhanced Memory_DRAFT_ v0.5 | Xu, Xiao Kang (X.) <xxu71@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | panchengdong <v_panchengdong@baidu.com> | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-13 | 2020-02-03 | 2020-01-20 | 2020-02-27 | N.A | 12/24/2019: Baidu provide new plan 1/8/2020: meeting planned this Thursday 1/10/2020: Baidu provide proposal and review on-site. 2/3/2020: pending feedback from Ford FO 2/4/2020: logic related to account will be covered in "个人账号“功能；- arrange a meeting to discuss follow up actions 2/6/2020: pending due to Ford FO 2/11/2020: MRD to be updated within this week. 2/13/2020: MRD updated and send to Ford FO. 2/25/2020: sign off for 542/625. | BU program open |  | Vehicle related | Enhanced memory |  | 账号 | bar: 2020-05-06
20 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Ford Clock Strategy | Y | 95% | 5% | NA | Desay |  | x | x |  | 2020-12-20 |  |  |  |  | Global Clock Strategy Specification Ver 1.8.docm Global Clock Strategy Specification Ver 1.8.docx Global Clock Strategy Specification Ver 1.8.pdf APIM Clock Strategy v1.4 Feb 6 2014.pdf | 合并到NO11 | H31a_SYNC4_Settings_R_v0_40_MY21 | Wang, Fin (X.Y.) <xwang65@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-25 | 2020-01-09 | 2020-01-01 | 2020-01-13 | N.A | 12/25/2019: discuss with FO today 12/30/2019: delay 1/6/2020: replan tomorrow 1/9/2020: plan to sign off 1/10/2020: re-archive by Desay, plan to sign off 1/13/2020: sign off |  |  | Vehicle related | Navigation | x | bar: 2020-05-06
21 | Vehicle Features/Interfaces | EESE/IVI(Roger) | Support Ford external DSP module by A2B | Y | 95% | 5% | NA | Desay | x | x | x |  | 2019-11-04 |  |  |  |  | Analog Devices A2B Hardware Review 000603.512 AD.doc Analog Devices A2B link Data Link and Physical Layer 000603 501 AD.doc Analog Devices A2B Link Implementation Specification V1_1.docx | Ford IVI SW Q&A_Audio&A2B.xlsx | N/A | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com | N/A |  | Xu jianjun(Jianjun.Xu@desay-svautomotive.com) | check for update |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/A2B | close | low |  | N.A | N.A | N.A | N.A | N.A | Audio_QA.xlsx |  |  | Chime management | Chime management | x | bar: 2020-03-06 to 2020-05-06
22 | Vehicle Features/Interfaces | EESE/IVI(PMT1)(Diven) | 车窗控制 Windows Control |  | 95% | 5% |  | Desay |  |  | x | [7 empty] | 合并到NO11 |  | Wang, Jingjing (J.) <jwang354@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-16 | 2020-01-17 | 2020-01-23 | 2020-01-17 | N.A | 2/6/2020: supplier to provide plan date 2/24/2020: LIN database? |  |  | Vehicle related | Vehicle setting | x
23 | Vehicle Features/Interfaces | EESE/IVI(PMT1)(Diven) | 天窗控制 Sunroof Control |  | 95% | 5% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Requirememt ready before Dec. 20th. | 合并到NO11 |  | Wang, Jingjing (J.) <jwang354@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | N | N | N | N | N | Y | ED&T | Y |  | close |  |  | 2020-02-20 | 2020-02-25 | 2020-02-27 | 2020-02-27 | N.A | 1/9/2020: need Ford FO's input. 1/10/2020: Desay push FO 1/13/2020: Ford FO provide spec 1/15 1/17/2020: spec & LIN provided, Desay FO check 1/17/2020: plan to sign off | LIN open |  |  |  | x
24 | Vehicle Features/Interfaces | EESE/IVI(PMT1)(Forrest) | 后备箱控制/Trunk Control |  | 95% | 5% |  | Desay |  | x | x |  | 2019-12-15 |  |  |  |  | Trunk_Softswitch_interfaceClient.txt | 合并到NO11 | H31a_SYNC4_Settings_R_v0_40_MY21 | Chen, Emma (J.) <jchen276@ford.com>/ Li, Xuedong (X.) <xli244@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2019-12-23 | N.A | combine to vehicle setting 12/23/2019: no open item for this function. |  |  | Vehicle related | Vehicle setting | x | bar: 2020-05-06
25 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Ford车辆系统降噪/Ford Noise reduction ANC | Y | 95% | 5% | NA | Desay | x - basic function - ANC Microphone input | x - basic function w/o calibration | x |  | 2019-11-04 |  |  |  |  | SPSS ANC SPSS v1.4 Oct 7 2013.pdf | Ford IVI SW Q&A_Audio&A2B.xlsx | N/A | Wang, Fin (X.Y.) <xwang65@ford.com>/Yao, Keita (Y.) <yyao21@ford.com> | N/A |  | Xu jianjun(Jianjun.Xu@desay-svautomotive.com) | check for update |  | Y | Y | N | N | N | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/ANC | close | low |  | N.A | N.A | N.A | N.A | N.A | Audio_QA.xlsx |  |  | Chime management | Chime management | x
26 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | 发动机声音增强/Engine Sound Enhancement | Y | 95% | 5% | NA | Desay |  | x | x |  | NA |  |  |  |  | Electrical Sound Enhancement SPSS V1.2 Oct 27, 2017.docx Electrical Sound Enhancement SPSS_Diagnostics.pdf | 不需要输出MRD | N/A | Wang, Fin (X.Y.) <xwang65@ford.com>/Yao, Keita (Y.) <yyao21@ford.com> | N/A |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | N | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2020-01-17 | N.A | Desay provide OIL 12/24/2019: no OIL, Desay follow spec, no OIL. |  |  | Chime management | Chime management | x | bar: 2020-05-06
27 | Vehicle Features/Interfaces | EESE/IVI(PMT3)(Forrest) | 驾驶模式选择/SDM(Selectable Drive Mode) | Y | 90% | 10% |  | Desay |  | x | x |  | 2019-12-15 |  |  |  |  | Selectable Drive Mode APIM Imp Guide v1.2 Aug 21, 2019.xlsx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.docx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.pdf | 不需要输出MRD |  | Gu, Zhengfu (Z.) <zgu11@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-25 | 2020-01-10 | 2020-01-01 | 2020-01-15 | N.A | HMI: Desay prepare UE 12/23/2019: SPSS is ok, while HMI need to be provided. 12/30/2019: need Desay to provide HMI 1/6/2020: Desay mail to FO/HMI 1/10/2020: Ford HMI can not accept the prospoal - open item Desay provide OIL today 1/13/2020: delay to today 1/15/2020: sign off | HMI open |  | Vehicle related | SDM | bar: 2020-05-06
28 | 驾驶辅助/Drive assist | CVPP | V2I Setting |  | 90% | 10% |  | Desay |  | x | x | [6 empty] | PRD V2I_CVPP_Ford_PRD V2.4_20191012.docx |  |  | Fan, Henry (H.) <hfan11@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Xu, Lidi <Lidi.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | on-going |  |  | 2020-03-06 | 2020-03-10 | 2020-03-11 |  | D | 1/6/2020: Desay replan 1/13/2020: replan 1/15/2020: cancel 2/28/2020: reopen- C/O phase 2, FNV2 change |  |  |  |  | x | bar: 2020-05-06
29 | 驾驶辅助/Drive assist | DAT | Off Road Front View Camera | Y | 90% | 10% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Off-road Front View Camera APIM Implementation Guide ver1_0 May 31 2013.xls Off-road Front View Camera APIM SPSS ver1_0 May 31 2013.doc Off-road Front View Camera APIM SPSS ver1_0 May 31 2013.pdf | Ford_MRD_Off-road_FrontViewCamera_V02.docx | H36k_SYNC4_Camera_Systems_R_v0_20_MY21 | Wang, Tom (X.) <xwang190@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | N | N | N | Y | Y | N | N | N | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-14 | 2020-01-17 | 2020-01-17 | N.A | 12/30/2019: replan 1/6/2020: replan 1/13/2020: desay check and feedback 2/4/2020: sign off |  |  | Driver assist | Driver assist HMI | x
30 | 驾驶辅助/Drive assist | DAT | Electronic Horizon/ADAS Horizon(Base on ADAS V2 specification) | Y | 30% | 70% |  | Baidu |  | x | x |  | 2019-12-20 |  |  |  |  | 200v2.0.4-D2.2-ADASIS_v2_Specification.0.pdf 20140602 ADAS Horizon Sensor Requirements-v93.doc 20140602 ADASISv2_Data_Dictionary_Clarification.docx 20140602 EH MPP algorithm description.doc EH data dictionary.xlsx eh_data_mux2.dbc EH_Signal_Usage.xlsx | 无MRD |  | Li, Cindy (Y.) <yli316@ford.com> | Hu, Pin (P.) <phu13@ford.com> | Zhang,Honghai(IOV) <zhanghonghai02@baidu.com> | Wang Dong <Dong.Wang@desay-svautomotive.com> Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> | C/O Phase3 |  | N | OPT | OPT | N | Y | Y | Y | Y | License | Y |  | close |  |  | 2019-01-03 | 2020-01-06 | 2019-01-10 | 2020-03-02 | N.A | 12/23/2019: MRD available today 12/24/2019: MRD delay to 12/24. 12/25/2019: arrange meeting tomorrow. 12/27/2019: Baidu check and feedback 12/30/2019: SPSS added, baidu check, meeting arranged in 1/2 1/2/2020: Baidu check and feedback today 1/6/2020: C/O phase 2; need to cascade the interface requirement to Desay 1/8/2020: Baidu contact Desay; 1/9/2020: plan to close today 1/10/2020: arrange meeting and feedback today 1/13/2020: Desay arrange a meeting 2/3/2020: arrange a meeting by Baidu 2/6/2020: pending due to Desay 2/11/2020: Discuss with FO for the change 2/17/2020: hardware change for iACC; SW share for both 32G & 64G. | open: iACC hardware issue |  |  |  |  | 地图 | bar: 2020-05-06
31 | 驾驶辅助/Drive assist | DAT | Semi Assisted Parking (SIPa, SIPe, SOPa) | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Active Park Assist V2 APIM Imp Guide v1.10 Oct 18, 2019.xlsx Active Park Assist V2 APIM SPSS v1.10 Oct 18, 2019.docx Active Park Assist V2 APIM SPSS v1.10 Oct 18, 2019.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | co phase2 requirement | Lu, Zaikai (Z.) <zlu29@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | N | N | N | N | N | N | N | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2020-01-10 | 2020-02-04 | N.A | Desay prepare UE 12/27/2019: postpone this item to Jan. 10th. 1/10/2020: on-site review 1/13/2020: MRD update? 2/4/2020: sign off | open item: startup time |  | Driver assist | Driver assist HMI | bar: 2020-05-06
32 | 驾驶辅助/Drive assist | DAT | Fully Assisted Parking (FIPa, FIPe, FOPa)/全自动泊车 | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Active Park Assist V2 APIM Imp Guide v1.10 Oct 18, 2019.xlsx Active Park Assist V2 APIM SPSS v1.10 Oct 18, 2019.docx Active Park Assist V2 APIM SPSS v1.10 Oct 18, 2019.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36m_SYNC4_APACSI_R_0_07_MY21 P36k_15P_SYNC4_Camera_R_v2_00_MY21 | Lu, Zaikai (Z.) <zlu29@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2020-01-10 | 2020-02-04 | N.A | Desay prepare UE 12/27/2019: postpone this item to Jan. 10th. 1/10/2020: on-site review 1/13/2020: MRD update? 2/4/2020: sign off | open item: startup time |  | Driver assist | Driver assist HMI | bar: 2020-05-06
33 | 驾驶辅助/Drive assist | DAT | TSR/Speed Limit and Overtaking Information Function (SLOIF) | Y | 95% | 5% |  | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Song, Amy (S.) <ssong18@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | bar: 2020-05-06
34 | 驾驶辅助/Drive assist | DAT | DAT 2.0 Base Features on IVI |  | 95% | 5% |  | Desay |  | x | x |  | 2019-12-20 | [7 empty] | Zhang, Kerry (Y.) <yzhan142@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | cancel | [7 empty] | 12/30/2019: checked, added missed items. Obsolete this one. | bar: 2020-05-06
35 | 驾驶辅助/Drive assist | DAT | DAT-High Way Assist (Active drive assist) |  | 95% | 5% |  | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx Location Service APIM Imp Guide v1.10 July 10, 2019.xlsx Location Service APIM SPSS v1.10 July 10, 2019.docx Location Service APIM SPSS v1.10 July 10, 2019.pdf | 合并到NO11 |  | Ni, Anthony (H.A.) <hni1@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | N | Y | Y | N | N | Y | N | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist setting | bar: 2020-05-06
36 | 驾驶辅助/Drive assist | DAT | Rear View Camera (RVC)-VGA&HD | Y | 95% | 5% | NA | Desay | x - HD and CVBS | x | x |  | 2019-11-04 |  |  |  |  | Stand-alone Rear View Camera APIM SPSS v2.7 Apr 26, 2019 Stand-alone Rear View Camera APIM Imp Guide v2.7 Apr 26, 2019 | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36k_SYNC4_Camera_Systems_R_v0_20_MY21 H36n_SYNC4_Camera_Shortcut_Key_R_0_02_MY21 H36q_SYNC4_Boundary_Alert_R_0_02_MY21 H36r_SYNC4_VideoOnDemand_R_0_03_MY21 | Zheng, Tina (T.) <tzheng4@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com | check for update |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 3 | 2019-12-27 | 2019-12-30 | 2020-01-03 | 2020-01-11 | N.A | 12/23/2019: re-open 12/25/2019: discuss with FO today 12/30/2019: MRD available, meeting? 1/6/2020: Desay mail 1/10/2020: on-site review, plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist HMI | bar: 2020-03-06 to 2020-05-06
37 | 驾驶辅助/Drive assist | DAT | Multi View Camera-360° | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36j SYNC GEN3 Driver Assist MultiCameraSystem RELEASED v2_5_release H36k SHMI TRG and MultiCamera System RELEASED v4_4 | Wang, Tom (X.) <xwang190@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-30 | 2020-01-06 | 2020-01-11 | N.A | 12/23/2019: re-open 12/25/2019: discuss with FO today 12/30/2019: MRD available, meeting? 1/6/2020: Desay mail 1/10/2020: on-site review, plan to sign off 1/11/2020: sign off | 2 open items: - Variant info - performance to be improved |  | Driver assist | Driver assist HMI | bar: 2020-05-06
38 | 驾驶辅助/Drive assist | DAT | LCA Lane centering assist (replace TJA) | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Ni, Anthony (H.A.) <hni1@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist setting | x | bar: 2020-05-06
39 | 驾驶辅助/Drive assist | DAT | Front&Side Parking Radar | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Visual Park Assist Graphic Client V2 APIM Imp Guide v1.6 Dec 8, 2017.xlsx Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.docx Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx |  | Lu, Zaikai (Z.) <zlu29@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-04 | N.A | 12/30/2019: replan 1/13/2020: desay check 2/4/2020: sign off |  |  | Driver assist | Driver assist setting | x | bar: 2020-05-06
40 | 驾驶辅助/Drive assist | DAT | Rear Parking Radar | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Visual Park Assist Graphic Client V2 APIM Imp Guide v1.6 Dec 8, 2017.xlsx Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.docx Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx |  | Lu, Zaikai (Z.) <zlu29@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-04 | N.A | 12/30/2019: replan 1/13/2020: desay check 2/4/2020: sign off |  |  | Driver assist | Driver assist HMI | x | bar: 2020-05-06
41 | 驾驶辅助/Drive assist | DAT | Cross Traffic Alert | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Cross Traffic Alert APIM Imp Guide v1.2 Mar 11, 2016.xlsx Cross Traffic Alert APIM SPSS v1.2 Mar 11, 2016.docx Cross Traffic Alert APIM SPSS v1.2 Mar 11, 2016.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx |  | Zhou, Wu (W.) <wzhou44@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 3 | 2019-12-27 | 2019-12-30 | 2020-01-06 | 2020-01-11 | N.A | 12/23/2019: re-open 12/25/2019: discuss with FO today 12/30/2019: MRD available, meeting? 1/6/2020: Desay mail 1/10/2020: on-site review, plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist HMI | x | bar: 2020-05-06
42 | 驾驶辅助/Drive assist | DAT | Reverse Brake Assist |  | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Reverse Brake Assist APIM Imp Guide v1.1 Feb 20, 2017.xlsx Reverse Brake Assist APIM SPSS v1.1 Feb 20, 2017.docx Reverse Brake Assist APIM SPSS v1.1 Feb 20, 2017.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx |  | Wang, Tom (X.) <xwang190@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 3 | 2019-12-27 | 2019-12-30 | 2020-01-06 | 2020-01-11 | N.A | 12/23/2019: re-open 12/25/2019: discuss with FO today 12/30/2019: MRD available, meeting? 1/6/2020: Desay mail 1/10/2020: on-site review, plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist HMI | x | bar: 2020-05-06
43 | 驾驶辅助/Drive assist | DAT | Lane Change Warning & Aid (LCWA) / Blind Spot Assist | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Zhou, Wu (W.) <wzhou44@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist setting | x | bar: 2020-05-06
44 | 驾驶辅助/Drive assist | DAT | TSR/Speed Limit and Overtaking | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 | [7 empty] | Song, Amy (S.) <ssong18@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | cancel | bar: 2020-05-06
45 | 驾驶辅助/Drive assist | DAT | Intelligent Speed Assistance | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Song, Amy (S.) <ssong18@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x | bar: 2020-05-06
46 | 驾驶辅助/Drive assist | DAT | Lane departure warning | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Zhang, Wayne (W.R.) <wzhan114@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x | bar: 2020-05-06
47 | 驾驶辅助/Drive assist | DAT | Lane keep aid | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Zhang, Wayne (W.R.) <wzhan114@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x | bar: 2020-05-06
48 | 驾驶辅助/Drive assist | DAT | Collision Mitigation (AEB) | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Wang, Lynn (X.) <xwang187@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | combine to item 11 12/30/2019: new requirement by Ford FO 1/6/2020: Desay mail to FO 1/10/2020: plan to sign off | check with FO for the new requirements - pending by Ford FO |  | Driver assist | Driver assist setting | x | bar: 2020-05-06
49 | 驾驶辅助/Drive assist | DAT | Pre Collision Assist for intersections | Y | 95% | 5% |  | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Wang, Lynn (X.) <xwang187@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | combine to item 11 12/30/2019: new requirement by Ford FO 1/6/2020: Desay mail to FO | check with FO for the new requirements - pending by Ford FO |  | Driver assist | Driver assist setting | x | bar: 2020-05-06
50 | Related to TCU features | CVPP | Vehicle locator | y | 40% | 10% | 50% | Ford CVPP/Desay |  |  | x | [6 empty] | PRD DUEROS_CVPP_Vehicle_Status_PRD_v1.1 |  |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-28 | 2020-03-06 | 2020-03-06 | 2020-03-06 | N.A | 2/6/2020: supplier to provide plan date 2/7/2020: arrange a meeting to discuss whether this function can be covered by "Location service" 2/27/2020: FO send out spec today. | open item: tbd |  | N.A | N.A |  | 硬件联动
51 | Related to TCU features | CVPP | Wi-Fi hotspot - TCU as WIFI Server (IVI provide HMI) | y | 95% | 5% | NA | Desay |  | x | x |  | NA |  |  |  |  | PRD WiFi Hotspot PRD v1.3 Feature Bundle 5.docx | WiFi Hotspot OnBoardClient v2 Imp Guide v1.3_Q&A_20200205.xlsx | H31i_SYNC4_Vehicle_Hotspot_Settings_RELEASED_v1_02 H31i_InfoBook _Wi-Fi_Hotspot_v0_6 H31j_SYNC4_Connectivity_Settings_R_v0_08_MY21_RELEASED | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Zhang Yanlan (yanlan.Zhang@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-13 | 2019-12-23 | 2019-12-30 | 2020-02-05 | N.A | 12/23/2019:combined to TCU, send to Pan yuan for check. 12/24/2019: delay to today. 12/27/2019: pending by Ford FO 1/6/2020: Desay update after internal review 1/10/2020: draft mailed to Ford FO, plan on-site review 2/5/2020: sign off | open item: | x | FNV2 | WIFI | x | bar: 2020-05-06
52 | Related to TCU features | DAT | V2V |  | 95% | 5% |  | Desay |  |  | x | [9 empty] | Shan, Susan (D.) <dshan@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  |  |  |  | N | N | N | N | N | N | N | N | ED&T | Y |  | cancel | [7 empty] | 1/15/2020: function cancelled
53 | Related to TCU features | CVPP | V2I Lite |  | 40% | 60% | NA | Baidu |  |  | x | [6 empty] | PRD V2I_CVPP_Ford_PRD V2.4_20191012.docx | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Fan, Henry (H.) <hfan11@ford.com> | Hu, Pin (P.) <phu13@ford.com> | pulijing <v_pulijing@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | on-going |  |  | 2020-03-06 | 2020-03-10 | 2020-03-11 |  | B | 1/15/2020: cancel 2/28/2020: reopen 2/28/2020: C/O phase, MRD to be updated
54 | Related to TCU features | CVPP | 用户流量统计及购买/Cellular data purchase and management |  |  | 30% | 70% | Ford CVPP/Baidu |  |  | x |  | 2020-01-23 |  |  |  |  | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf | 无MRD |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | huangqiuyue <huangqiuyue@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-13 | 2020-02-10 | N.A | 2/6/2020: Baidu provide interface only; need Ford CVPP more plan 2/7/2020: Baidu interface described in the "Launcher" MRD. Pending due to Ford FO review. 2/10/2020: sign off |  |  | CVPP | carrier |  | 第三方集成应用
55 | Ethernet SOA related features | EESE/IVI(Forrest) | Bezel Diagnostics | Y? | 90% | 10% | NA | Desay |  | x | x |  | 2019-12-25 |  |  |  |  | Diag APIM Ver 1.7 Diagnostics Logical to Physical CAN signal mapping Sep 7, 2018.docx | Ford_MRD_EngineeringMode_V02.docx |  | Wang, Fin (X.Y.) <xwang65@ford.com> | N/A |  | Chen Xiujing(Xiujing.Chen@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-14 | 2020-01-14 | 2020-01-21 | 2020-02-19 | D | 12/30/2019: no MRD/replan info 1/6/2020: replan to 1/10 1/13/2020: MRD to be available 1/14 2/12/2020: plan to sign off 2/17/2020: sign off |  | x | FNV2 | EOL | x | bar: 2020-05-06
56 | Ethernet SOA related features | CVPP | Peripheral Provisioning |  | 90% | 10% | NA | Desay |  | x | x |  | 2020-01-10 |  |  |  |  | Peripheral Module Provisioning APIM Imp Guide v1.4 July 30, 2019.xlsx Peripheral Module Provisioning SPSS v1.4 July 30, 2019.docx Peripheral Module Provisioning SPSS v1.4 July 30, 2019.pdf | 合并到NO163 | N/A | Cui, Rebecca (H.) <hcui2@ford.com> | N/A |  | Chen Xiujing(Xiujing.Chen@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-02-19 | 2020-01-17 | 2020-02-28 | D | 12/30/2019: no MRD/replan info 1/6/2020: replan to 1/10 1/13/2020: Desay push FO 2/24/2020: send out this Tuesday |  |  | Basic function | EOL | bar: 2020-05-06
57 | Ethernet SOA related features | CVPP | Embedded Modem Reset/Master reset |  | 90% | 10% |  | Desay |  | x | x |  | 2020-01-10 |  |  |  |  | PRD MasterReset-PRD.pdf | Customer Connectivity Settings Client APIM SPSS v1.4 imp Guide v1.6_20200228.xlsx | H31L_SYNC4_Reset_RELEASED_V4_02_MY21 | Ge, Haiqing (H.) <hge5@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-02-12 | 2020-01-17 | 2020-02-26 | N.A | 1/13/2020: Desay check 2/8/2020: pending by Ford FO 2/11/2020: plan to sign off on 2020/2/14 2/12/2020: MRD send to FO 2/24/2020: discussion on-going 2/26/2020: sign off |  | x | FNV2 | FNV2-basic | bar: 2020-05-06
58 | Features of IVI or Connect | EESE/IVI(Forrest) | Digital Owner's Menu(Demo Show) |  | 5% | 5% | 90% | Ford EESE |  |  | x | [6 empty] | Digital Owners Manual Client SPSS v1.0 February 9, 2018 |  |  | Geng, Dekang (D.) <dgeng1@ford.com> | Chen, Yu (Y.) <ychen372@ford.com> |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | hold-on |  |  | hold-on | hold-on | hold-on | hold-on | F | 2/6/2020: supplier to provide plan date 2/13/2020: plan date provided by in-house team 3/3/2020: inhouse team responsible |  |  | Basic function | basic
59 | Ethernet SOA related features | EESE | Web-Based HMI |  | 10% | 90% |  | Baidu |  |  | x |  | 2020-02-27 |  |  |  |  | SPSS |  |  | Chen, Yu (Y.) <ychen372@ford.com> | Chen, Yu (Y.) <ychen372@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | cancel | [7 empty] | 2/3/2020: Baidu can not support HTML5
60 | Features of IVI or Connect | CVPP | Baidu Local Harzard Information |  | 10% | 90% |  | Baidu |  |  | x | [6 empty] | Local Hazard Information Navigation v2 APIM SPSS v1.0 Jun 19, 2018 |  | embedded in Nav behaviour. | Lin, Shawn (X.) <xlin17@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | Zhang,Honghai(IOV) <zhanghonghai02@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2020-02-14 | 2020-02-24 | 2020-02-21 | 2020-02-24 | N.A | 2/12/2020: Ford FO consdier to remove this feature, discuss on-going 2/24/2020: C/O, no change. |  |  | CVPP | Message center |  | 地图
61 | Ethernet SOA related features | CVPP | IP Pass Through Client |  | 90% | 10% |  | Desay |  | x | x |  | 2020-01-10 |  |  |  |  | SPSS/PRD IP Pass Through Client Imp Guide v1.1 September 4, 2018.xlsx IP Pass Through Client SPSS v1.1 September 4, 2018.pdf | IP Pass Through Client Imp Guide v1.1 September 4, 2018 for Desay_0213.xlsx | N/A | Lin, Shawn (X.) <xlin17@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV2/IP_Pass_Through_Client | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-18 | D | 2/12/2020: MRD send to FO, plan to close before 2/21 2/18/2020: sign off |  | x | FNV2 | FNV2-basic | bar: 2020-05-06
62 | Ethernet SOA related features | CVPP/EESE | USB Update for TCU and ECG |  | 90% | 10% |  | Desay |  | x | x |  | 2020-01-10 |  |  |  |  | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf |  |  | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu guanghui(Guanghui.Liu@desay-svautomotive.com) | 可能缺少Update技术文档 |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | cancel | bar: 2020-05-06
63 | Ethernet SOA related features | CVPP | Wireless Interface Router(WIR) |  | 90% | 10% |  | Desay |  | x | x |  | 2020-01-10 |  |  |  |  | SPSS/PRD | Wireless Interface Router Client1 Imp Guide v1.3 November 22 2019 for Desay_0217.xlsx | N/A | Lin, Shawn (X.) <xlin17@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-18 | D | 2/12/2020: MRD send to FO, plan to close before 2/21 2/18/2020: sign off |  | x | FNV2 | FNV2-basic | bar: 2020-05-06
64 | Ethernet SOA related features | CVPP | FNV2 - FCI Protocol |  | 90% | 10% |  | Desay |  | x | x | [6 empty] | FNV2-FCI Protocol SPSS v1.1 August 17, 2018 | FNV2-FCI Protocol Imp Guide v1.1 August 17, 2018_20200224.xlsx | N/A | Liu, Dapeng (D.) <dliu79@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-19 | D | 2/12/2020: plan to close before 2/18 |  | x | FNV2 | FNV2-basic | bar: 2020-05-06
65 | Ethernet SOA related features | CVPP | Customer Connectivity Settings |  | 90% | 10% |  | Desay |  |  | x |  | 2019-12-20 |  |  |  |  | PRD CCS_FB5_PRD_v2.0.pdf | Customer Connectivity Settings Client APIM SPSS v1.4 imp Guide v1.2_20200214.xlsx | H31j_SYNC4_Connectivity_Settings_R_v0_08_MY21_RELEASED | Ge, Haiqing (H.) <hge5@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-14 | 2020-02-18 | 2020-02-21 | 2020-02-18 | D | 1/13/2020: move to DCV2 2/12/2020: plan to close before 2/21 2/18/2020: sign off |  | x | FNV2 | FNV2-basic
66 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Diven) | Power to Box |  | 30% | 70% | NA | Baidu |  |  | x |  | 2020-01-23 |  |  |  |  | Power to the Box SPSS v1.3 August 26, 2019 |  | H86a_SYNC4_ProPowerOnboard_RELEASED_v1_14_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> |  |  |  | Y | Y | Y | N | N | N | N | Y | ED&T | Y |  | delay |  |  | 2020-02-24 | 2020-02-27 | 2020-03-02 |  | B | 2/10/2020: CVPP feature or EESE feature? 2/24/2020: SPEC already send to Baidu | [5 empty] | 硬件联动
67 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Diven) | Power Flow Display |  | 90% | 10% | NA | DESAY |  | x | x |  | 2019-12-20 |  |  |  |  | Power Flow Display Client v3 APIM SPSS v1.0 Aug 29, 2018 Power Flow Display Client v3 APIM Imp Guide v1.0 Aug 29, 2018 | Power flow display 车型筛选_QA.xlsx | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | 单童/韩雨哲 | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | N | N | N | N | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-02-12 | 2020-01-17 | 2020-02-26 | N.A | 12/25/2019: replan 12/30/2019: no MRD/replan info 1/6/2020: replan to 1/10 1/13/2020: postpone to 1/14 2/4/2020: MRD to be updated by Desay 2/12/2020: open item list to FO 2/26/2020: sign off | bar: 2020-05-06
68 | HMI | HMI | 快捷面板/quick panel-27 only |  | 100% | 0% |  | Desay |  | x | x |  | 2020-01-17 |  |  |  |  | Design Guideline_CD542_To Supplier(11.15) compressed | Ford_MRD_27寸大屏SystemUI_20200116final.docx |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 2 | 2019-12-06 | 2019-12-13 | 2019-12-30 | 2020-03-06 | N.A | SystemUI handover to Desay Desay: 12/30 freeze 1/6/2020: plan to sign off 1/10/2020: Desay recheck and sign off 1/13/2020: meeting to discuss open item with HMI and baidu 1/17/2020: sign off for desay 2/27/2020: reopen 3/6/2020: clairfied clear, close |  |  | HMI | HMI | x | Launcher
69 | HMI | HMI | Persistant button |  | 100% | 0% |  | Desay |  | x | x |  | 2020-01-17 |  |  |  |  | Design Guideline_CD542_To Supplier(11.15) compressed | Ford_MRD_27寸大屏SystemUI_20200116final.docx | CX727 -P22h_15P_SYNC4_Dashboard_View_R_v4_00_MY21 Other programs will be aligned along with launcher design. | Liu Luisa （27inch） Xiao Yun（15.5inch 13.2inch Lincoln）Wang Lisa （13.2 Ford）Zhou Yujuan（12inch Ford） | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> | 根据新需求 |  | Y | Y | Y | Y | Y | Y | Y | Y |  | Y |  | delay |  | 2 | 2019-12-13 | 2019-12-13 | 2019-12-30 |  | D | SystemUI handover to Desay Desay: 12/30 freeze 1/6/2020: plan to sign off 1/10/2020: Desay recheck and sign off 1/13/2020: meeting to discuss open item with HMI and baidu 2/27/2020: R&R update, and reopen |  |  | HMI | HMI | x | Launcher | bar: 2020-05-06
70 | HMI | HMI | 主题更换/Theme change by User-->应用适配 |  | 30% | 40% | 30% | Baidu |  |  | x |  | 2020-01-23 | [5 empty] | phase4-福特-更换主题MRD 2020_2_15.docx |  | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | zhushiyun <v_zhushiyun01@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y |  | N |  | close |  |  | 2020-01-23 | 2020-02-03 | 2020-02-10 | 2020-02-19 | N.A | 2/3/2020: Ford FO review 2/6/2020: review on-going 2/11/2020: escalate 2/14/2020: meeting held and plan to sign off | 2 open item |  | HMI | HMI | x | 主题更换
71 | HMI | HMI | 主题更换/Theme change by User-->主题切换 |  | 90% | 10% | NA | Desay |  |  | x | [7 empty] | Ford_MRD_主题切换.docx |  | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2020-02-14 | 2020-02-25 | 2020-02-21 | 2020-03-02 | N.A | 2/6/2020: supplier to provide plan date 2/17/2020: mailed, waiting feedback from HMI 2/24/2020: MRD planned to be ready today? |  |  | HMI | HMI | x
72 | Features of IVI or Connect | CVPP | 以太网连接互联网/Connect to Internet via Ethernet |  | 90% | 10% | NA | Desay |  | x | x |  | 2020-01-10 |  |  |  |  | PRD |  | N/A | Lin, Shawn (X.) <xlin17@ford.com> / Liu, Dapeng (D.) <dliu79@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | cancel |  |  | N.A | N.A | N.A | N.A | N.A | 1/13/2020: MRD 1/14 2/11/2020: Aligned as not needed by Dapeng and Guo chengcheng |  |  | CVPP | Message center | bar: 2020-05-06
73 | Features of IVI or Connect | EESE/IVI(Diven) | 本地及在线音乐/Offline&Online Music Player | Y | 10% | 90% | NA | Baidu | x | x | x |  | 2019-11-05 |  |  |  |  | N.A | MRD-随心听多媒体V1.4.docx | H25_SYNC_4_Media_Player_RELEASED_v1_03_MY21 | Xu, Amy (X.) <xyafei@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | zhangjingyao <v_zhangjingyao@baidu.com> |  | refer to BAIDU MRD, 确认对大屏是否其他适配要求 | 福特建议本地/在线音乐和视频/，FM/AM合并，百度确认可行性 | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close | low |  | 2020-01-09 | N.A | 2020-01-16 | 2020-01-11 | N.A | 1/9/2020: feature 114 track | n.a |  | Basic function | entertainment | x | 内容生态 |  | x | bar: 2020-03-06 to 2020-05-06
74 | Features of IVI or Connect | EESE/IVI(Forrest) | 本地收音机 AM&FM/音频管理（本地+在线） | Y | 90% | 10% | NA | Desay | x | x | x |  | 2019-11-04 |  |  |  |  | SPSS AMFM Tuner of Standalone AHU SPSS v1.8.pdf Auto Store_AM FM SPSS.pdf CD539C519D568_HMI_收音机_V1.0_20180912.xlsx | DUEROS-1005-CD391&U625&CX482-随心听：个性化电台.docx 11.19DUEROS-1005-CD391&U625&CX482-随心听：个性化电台.pdf | H23_SYNC4_Radio_RELEASED_v3_03_MY21 (H22m)MY21 MIxed Preset Test Cases 20200210 | Wang, Fin (X.Y.) <xwang65@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) | 可以参照Phase1/2 MRD，但是需要在Ford SPEC基础上根据实际需求修改 |  | Y | Y | Y | Y | Y | Y | Y | Y | License | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/AM-FM | close | low |  | N.A | N.A | N.A | N.A | N.A |  | n.a |  | Basic function | entertainment | x | bar: 2020-03-06 to 2020-05-06
75 | Features of IVI or Connect | EESE/IVI(Forrest) | 在线收音机 Online Radio | Y | 10% | 90% | NA | Baidu | x | x | x |  | 2019-11-05 |  |  |  |  | N.A | Online Rideo_V1.2.docx |  | Wang, Fin (X.Y.) <xwang65@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | zhangjingyao <v_zhangjingyao@baidu.com> |  | C/O Phase1/2 |  | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close | low |  | N.A | N.A | 2019-11-20 | 2019-12-18 | N.A |  |  |  | Basic function | entertainment | x | 内容生态 |  | x | bar: 2020-03-06 to 2020-05-06
76 | Features of IVI or Connect | EESE/IVI(Diven) | 本地及在线视频播放/Video Playback | Y | 10% | 90% | NA | Baidu | x - offline USB video playback | x | x |  | 2019-11-05 |  |  |  |  | N.A | 在线视频 Online video.docx | H25b_Video_Player_Draft_v0_01 | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhangjingyao <v_zhangjingyao@baidu.com> |  | 单屏可以C/O Phase1/2 MRD， 但是27"需要重新根据Ford需求写MRD |  | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close | low |  | N.A | N.A | 2019-11-20 | 2019-12-12 | N.A |  | n.a |  | Basic function | entertainment | x | 内容生态 |  | x | bar: 2020-03-06 to 2020-05-06
77 | Features of IVI or Connect | EESE/IVI(Diven) | 视频、音乐、图片DLNA投屏到车机显示器区分主副驾/Video Playback and Video and Photo project to Display(Driver and Passenger) via DLNA |  | 70% | 30% | NA | Desay |  |  | x | [6 empty] | DLNA投屏--PRD.pdf | Ford_MRD_DLNA_20200217.docx |  | Jia, Elaine (T.) <tjia2@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  | 后期细化 | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV2/DLNA | close |  |  | 2020-02-14 | 2020-02-17 | 2020-02-21 | 2020-02-18 | N.A | 2/6/2020: supplier to provide plan date 2/17/2020: MRD avaialble, review |  |  | Basic function | entertainment | x
78 | Features of IVI or Connect | EESE/IVI(Diven) | 蓝牙音乐/Bluetooth Media | Y | 60% | 40% | NA | Desay | x - basic function only | x - complete | x |  | 2019-11-06 |  |  |  |  | SPSS BT Connectivity APIM SPSS v2.9 Jan 3, 2018.pdf DualBtSystemRequirments_V0.1.docx | Ford_MRD_蓝牙音乐_V4.0_20200218.docx | H25_SYNC_4_Media_Player_RELEASED_v1_03_MY21 H31h_SYNC4_Audio_Settings_RELEASED_v1_05_MY21 | Xu, Amy (X.) <xyafei@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） | 参考Phase1/2的MRD，根据福特新的需求更新MRD，并且27"会增加额外交互 |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/BT_Phone | close | low |  | 2019-11-10 | 2019-12-23 | 2019-12-30 | 2020-02-06 | N.A | 12/23/2019:Updated MRD avaialble 12/23. Wait confirm from Ford FO; 12/25/2019: pending by Ford FO 1/6/2020: updated MRD available, need FO check 1/9/2020: need Desay's update 1/10/2020: Desay update by 1/13 1/13/2020: Plan to sign off, consolidate info by Desay 2/6/2020: sign off | n.a |  | Basic function | BT | x | bar: 2020-03-06 to 2020-05-06
79 | Features of IVI or Connect | EESE/IVI(Diven) | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | Y | 90% | 10% | NA | Desay | x - basic function only | x - complete | x |  | 2019-11-06 |  |  |  |  | SPSS BT Phone APIM SPSS v1.9 April 24 2015.pdf Smart cockpit BT Solution.pdf | Ford_MRD_电话设置_V1.1_20200220.docx | H28a_SYNC4_Phone_RELEASED_v1_07_MY21 H28c_SYNC4_Bluetooth_Pairing_RELEASED_v1_05_MY21 | Xu, Amy (X.) <xyafei@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） | 单屏，蓝牙电话基础部分可以C/O Phase1/2，微信要重新定义 27”需要重新定义 |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/BT_Phone | close | low |  | 2019-11-10 | 2019-12-10 | 2019-12-17 | 2020-02-19 | D | 1/9/2020: reopen, 2 open items to be added; 1. BT setting missed 2. dailing button missing?... Other issues which mailed by Lisa 1/13/2020: MRD to be updated 1/14 2/8/2020: pending due to Ford FO check 2/11/2020: plan to sign off |  |  | Basic function | BT | x | bar: 2020-03-06 to 2020-05-06
80 | Features of IVI or Connect | EESE/IVI(Diven) | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) |  | 90% | 10% | NA | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | refer DCV0 (BT_Connectivity, BT_Phone) | Ford_MRD_蓝牙耳机_V1.3_20200218.docx Ford_MRD_蓝牙电话_V4.5_20200221.docx Ford_MRD_蓝牙连接设置_V4.4_20200227.docx |  | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） |  |  | N | Y | N | N | N | N | Y | Y | ED&T | Y |  | close |  |  | 2019-12-30 |  | 2020-01-06 | 2020-02-19 | D | 12/30/2019: no MRD/replan info 1/6/2020: replan to be availabel tomorrow 1/10/2020: replan after internal discussion by Desay 1/13/2020: escalate 2/11/2020: plan to sign off |  |  |  |  | x
81 | Features of IVI or Connect | EESE/IVI(Diven) | 离线及在线地图和导航/Offline&Online Map and Navigation | Y | 10% | 90% | NA | Baidu | x | x | x |  | 2019-10-28 | [5 empty] | 1.地图-产品规格说明书20200221 - ford 2.福特IOV车机地图feature list-------phase1-4通用（包含phase4变更点） | 02_Specification/05_Ford_HMI_Spec/Navigation_Ford HMI requirement.pptx | Wang, Jingjing (J.) <jwang354@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | Zhang,Honghai(IOV) <zhanghonghai02@baidu.com> |  | 单屏，可以C/O Phase1/2 MRD 27“需要重新定义 |  | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close | low |  | 2019-11-10 | 2019-12-20 | 2019-12-27 | 2020-02-27 | N.A | 12/24/2019: Ford FO在等Baidu的回复 12/25/2019: pending by Ford FO 12/27/2019: Baidu check 12/30/2019: pending by Baidu Check 1/2/2020: Baidu check 1/8/2020: Baidu provide the different list; Emma follow the 2 requirements. 1/9/2020: 3 open items: 2019/1/14 1. Baidu check the status of the "improvement" items from Diven. 2. Provide the different list between IVI & phone for Navigation 3. analysis the feasibility of new requirement 1/17/2020: baidu provided feedback 2/3/2020: organize meeting to close 2/6/2020: pending due to Ford FO 2/13/2020: meeting held 2/19/2020: final decision to be made this week, due to the change request of "trip planner" 2/24/2020: forzen this feature, tracking the changes via trip planner separately. |  |  | Basic function | Navigation | x | 地图 |  | x | bar: 2020-03-06 to 2020-05-06
82 | Features of IVI or Connect | EESE/IVI(Diven) | AR Navigation (include output to IPC) |  | 20% | 80% | NA | Baidu | x - basic video output | x - basic function | x |  | 2019-11-07 |  |  |  |  | N.A | MRD_百度车联网_项目_福特_AR导航_v1.1_20191119.docx |  | Wang, Jingjing (J.) <jwang354@ford.com>/Chen, Emma (J.) <jchen276@ford.com> | Hu, Pin (P.) <phu13@ford.com> | Zhang,Honghai(IOV) <zhanghonghai02@baidu.com> |  | new |  | N | OPT1 | N | N | N | N | N | N | License | Y |  | close | low |  | 2019-11-10 | 2019-12-20 | 2019-12-27 | 2019-12-23 | N.A | [6 empty] | 地图 |  | x
83 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Volume Setting V2 |  | 90% | 10% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Volume APIM SPSS v1.3 Jan 31, 2018 Volume APIM Imp Guide v1.3 Jan 31, 2018 Volume Logical to Physical CAN signal mapping Feb 5, 2018 | 合并到NO84 | H31a_SYNC4_Settings_R_v0_40_MY21 | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | 12/24/2019: desay check with Ford FO. 12/27：逻辑部分已经和ford audio FO澄清，界面相关合并到setting中 1/6/2020: plan to sign off 1/11/2020: sign off |  |  | Basic function | Setting | bar: 2020-05-06
84 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Audio Management | Y | 90% | 10% | NA | Desay | x | x | x |  | 2019-11-04 |  |  |  |  | Audio Management APIM Imp Guide v1.5.1 Sep 26, 2018.xlsx Audio Management Logical to Physical CAN signal mapping Sep 7, 2018.docx Audio Management SPSS v1.5 Sep 7, 2018.pdf Audio Management Supplement SYNC 4.1 July 13th, 2018.docx Audio Settings Deployment May 9th, 2019.docx Audio Settings Logical to Physical CAN signal mapping Sep 6, 2018.docx Audio Settings v2 APIM Imp Guide v1.1 May 23, 2019.xlsx Audio Settings v2 APIM SPSS v1.1 May 23, 2019.pdf | Ford_MRD_AudioSource.docx | H31a_SYNC4_Settings_R_v0_40_MY21 H31h_SYNC4_Audio_Settings_RELEASED_v1_05_MY21 | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Yu Hualin(Hualin.Yu@desay-svautomotive.com) | Phase1/2 YFV，DESAY需要重新做 |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/Audio_Management | close | low |  | N.A | N.A | N.A | N.A | N.A | Audio_QA.xlsx |  |  | Chime management | Chime management | x | bar: 2020-03-06 to 2020-05-06
85 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Power Managements | Y | 90% | 10% | NA | Desay | x | x | x |  | 2019-11-04 |  |  |  |  | Power Management Logical to Physical CAN signal mapping Sep 6, 2018.docx Power Management v2 APIM Imp Guide v1.1 May 8, 2019.xlsx Power Management v2 APIM SPSS v1.1 May 8, 2019.pdf | DUEROS-305-CX483611-电源管理.docx | H22g_SYNC4_Welcome_Power_Modes_RELEASED_v1_02_MY21 | IVI-Song, Rui (Rex.) <rsong2@ford.com>Chen James <JCHEN303@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Ding Yunrong（Yunrong.Ding@desay-svautomotive.com） | Phase1/2 YFV，DESAY需要重新做 |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/Power_Management | close | low |  | 2019-11-10 | 2019-12-06 | 2019-12-13 | 2019-12-11 | N.A | DUEROS-305-CX483611-电源管理.pdf | 2 open points by Ford FO 12/27/2019: Desay mail to FO today |  | Power management | Power management | x | bar: 2020-03-06 to 2020-05-06
86 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Illumination Requirements | Y | 90% | 10% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Illumination Management APIM SPSS ver 1_0 May 31st, 2013 folder:Illumination | illumination_QA.xlsx | H31a_SYNC4_Settings_R_v0_40_MY21 | Chen, James (J.) <jchen303@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-14 | N.A | 12/24/2019: desay check with Ford FO. 12/30/2019: setting is OK. Detail illumination requirement need Desay's hardware/software architecture check. 1/6/2020: HMI ok, need Desay provide OIL 1/10/2020: archive QA , plan to sign off 1/14/2020: sign off |  |  | Basic function | Illumination | x | bar: 2020-05-06
87 | Features of IVI or Connect | IVI | 文件浏览器/File Manager - confirmed as not needed12/25/2019 |  | 90% | 10% | NA | Desay |  | x | x |  | 43819 |  |  |  |  | File Manager.pdf |  |  | Jia, Elaine (T.) <tjia2@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Pan Juan（Juan.Pan@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | cancel | [7 empty] | upload to GitHub 12/24/2019: mailed to Ford FO 12/25/2019: meeting today | bar: 2020-05-06
88 | Features of IVI or Connect | IVI | 蓝牙文件共享/Files sharing via Bluetooth |  | 90% | 10% | NA | Desay |  | x | x |  | NA |  |  |  |  | feasibility study - ongoing |  |  | Xu, Amy (X.) <xyafei@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） |  |  | N | N | N | N | N | N | N | Y | ED&T | N |  | cancel
89 | Features of IVI or Connect | EESE/IVI(Diven) | 图片/小视频浏览器 Picture/video Viewer |  | 90% | 10% | NA | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | n.a suppliers provide the proposal and review; including HMI and data collection. | Picture_MRD.DOCX |  | Jia, Elaine (T.) <tjia2@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Dong Zhaojun<zhaojun.dong@desay-svautootive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-02-14 | D | upload to GitHub 12/24/2019: mailed to Ford FO 12/25/2019: meeting today 12/27/2019: updated MRD today 12/30/2019: updated MR mailed to Ford FO 1/6/2020: Ford FO feedback today 1/10/2020: on-site review, archive, plan to sign off 1/13/2020: MRD open item discussion. 1/19/2020: open item listed by Desay, on-hold 2/14/2020: plan to sign off |  |  | Basic function | entertainment | bar: 2020-05-06
90 | Features of IVI or Connect | EESE/IVI(Diven) | 基础及增强型语音功能/Base and Enhanced VR |  | 10% | 90% | NA | Baidu | x - basic VR function | x | x |  | 2019-10-29 |  |  |  |  | N.A | Voice recognition spec - 20191226 01 Voice recognition feature list v1.1 - 20200221 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 | H48b_Sync 3 Voice Control State Machine (DRAFT) v1.0.pdf | Wang, Jingjing (J.) <jwang354@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> |  | 基础VR可以C/O Phase1/2 增加的VR需要根据需求做 |  | Y | Y | Y | Y | Y | Y | Y | Y | License | Y |  | close | low | 5 | N.A | N.A | 2019-11-20 | 2019-12-02 | N.A |  | Open: key parameters can not meet spec. Baidu improve. 2/28/2020: 语音指令持续更新 3/30 |  | Chime management | chime management |  | 语音 |  | x | bar: 2020-03-06 to 2020-05-06
91 | Features of IVI or Connect | EESE/IVI(Diven) | 双音区语音识别/Dual Zone VR-Clarify | Y | 10% | 90% |  | Baidu |  | x | x |  | 2019-12-20 |  |  |  |  | Voice recognition spec-20191121.pdf | Voice recognition spec - 20191226 01 Voice recognition feature list v1.1 - 20200221 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 | H48b_Sync 3 Voice Control State Machine (DRAFT) v1.0.pdf | Wang, Jingjing (J.) <jwang354@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | License | Y |  | close |  |  | N.A | N.A | 2019-11-20 | 2019-12-02 | N.A | combine to 90 |  |  | Chime management | chime management |  | 语音 | bar: 2020-05-06
92 | Features of IVI or Connect | IVI | 全成员语音识别支持/Multi-zone Directional Voice Control |  | 10% | 90% | NA | Baidu |  |  | x |  | 2020-02-03 | [7 empty] | Wang, Jingjing (J.) <jwang354@ford.com> | N/A | hanyuzhe <v_hanyuzhe@baidu.com> |  |  |  | N | N | N | N | N | N | N | N | License | Y |  | cancel
93 | Features of IVI or Connect | EESE/IVI(Diven) | 人脸识别 Face ID (Registration, Recognition, Account, Personalization, Welcome) | Y | 10% | 90% | NA | Baidu | x-basic Face ID feature | x-complete | x |  | 2019-10-29 |  |  |  |  | Image Recognition Function Feature Level Specification - draft.pdf |  | SYNCFord HMI Requirement_Enhanced Memory_DRAFT_ v0.5 | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | Zhang,Lisha <zhanglisha01@baidu.com> panchengdong <v_panchengdong@baidu.com> |  | C/O Phase3 | 百度直接输出MRD | N | OPT2 | N | N | N | N | N | OPT2 | License | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/Facial%20Recognition | close | Mid |  | 2019-11-10 | 2019-12-20 | 2020-01-10 | 2020-02-19 | B | 12/23/2019: 1/10前定稿 1/2/2020: MRD status? 1/8/2020: Baidu provide updated MRD 1/9/2020: mail send to Ford FO 1/10/2020: Baidu reschedule to 1/17 2/6/2020: pending due to Baidu 2/7/2020: MRD to be updated. 2020/2/12 2/13/2020: update on-going | [5 empty] | 图像 |  | x
94 | Features of IVI or Connect | EESE/IVI(Diven) | Image recognition - Drive Status Monitor (Fatigue, Distraction, Dangers Behaviour) | Y | 10% | 90% | NA | Baidu |  | x | x |  | 2019-12-05 | [5 empty] | 福特Phase4_DMS_20200213.docx | N/A | Jia, Elaine (T.) <tjia2@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | Zhang,Lisha <zhanglisha01@baidu.com> panchengdong <v_panchengdong@baidu.com> |  |  |  | N | OPT2 | N | N | N | N | N | OPT2 | License | Y |  | close | mid |  | 2019-12-30 | 2020-01-06 | 2020-01-06 | 2020-02-19 | B | Updated MRD to be rady Dec. 30th 1/2/2020: MRD available 1/6/2020: meeting planned on 1/7 1/8/2020: Baidu provide updated MRD and open item list 1/10/2020: postpone to 1/17? 2/6/2020: pending due to Baidu 2/7/2020: MRD to be updated before 2020/2/12 2/13/2020: update on-going after meeting 2/14/2020: plan to sign off | [5 empty] | 图像
95 | Features of IVI or Connect | EESE/IVI(Diven) | Image recognition - Multi-Mode (Hand Gusture / Head / Emotion) |  | 10% | 90% | NA | Baidu |  | x | x |  | 2020-01-23 | [5 empty] | 【福特cd542】多模手势交互mrd需求文档 V2.1.2 | N/A | Jia, Elaine (T.) <tjia2@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | Zhang,Lisha <zhanglisha01@baidu.com> panchengdong <v_panchengdong@baidu.com> |  |  |  | N | OPT2 | N | N | N | N | N | OPT2 | License | Y |  | close |  |  | 2020-01-10 | 2020-01-02 | 2020-01-17 | 2020-02-20 | N.A | 12/23/2019: 多模MRD更新版本 Dec. 30th; 情绪相关内容单独输出MRD, end of Feb. 1/2/2020: MRD available 1/8/2020: Baidu provide updated MRD and open item list 1/10/2020: update on-going 2/3/2020: updated MRD avaialble, pending by Ford FO's review 2/6/2020: meeting today 2/7/2020: MRD plan to sign off 2/11/2020: Change introduced, MRD to be updated within this week. 2/20/2020: MRD updated and review closed, sign off | [5 empty] | 图像
96 | Features of IVI or Connect | EESE/IVI(Diven) | Face ID with Ford DSM module -> Image recognition with Ford DSMC module (FaceID with DSMC/Driver monitor with DSMC) |  | 10% | 90% | NA | Baidu |  |  | x | [6 empty] | Image Recognition Function Feature Level Specification - draft.pdf | 无MRD | N/A | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | Zhang,Lisha <zhanglisha01@baidu.com> panchengdong <v_panchengdong@baidu.com> |  | new | 百度直接输出MRD | N | Y | Y | N | N | N | N | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/Facial%20Recognition | open |  |  | 2020-02-14 | 2020-02-28 | 2020-02-21 |  | N.A | 2/6/2020: supplier to provide plan date 2/11/2020: Baidu provide the feasiblity study result. No MRD. 2/13/2020: Update on-going 2/20/2020: Baidu internal discussion on-going. 2/28/2020: Baidu provide technical spec to Ford FO. - open item 3/3/2020: reopen- scope not aligned between Ford FO and Baidu 3/10/2020: sign off | 2/28/2020: Baidu provide technical spec to Ford FO. - open item |  |  |  |  | 图像
97 | Features of IVI or Connect | EESE/IVI(Diven) | 随心拍/Traveling Shooting |  | 30% | 70% | NA | Baidu |  |  | x | [7 empty] | 无MRD |  | Jia, Elaine (T.) <tjia2@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhangjingyao <v_zhangjingyao@baidu.com> |  |  | 具体表现形式待确认--福特 | N | Y | N | N | N | N | N | N | ED&T | Y |  | delay |  |  | 2020-02-14 | 2020-03-10 | 2020-02-21 |  | B | 1/9/2020: not Ford develop 1/10/2020: check today 1/13/2020: Baidu send out OIL 2/6/2020: replan 2/20/2020: MRD planned to be ready before next Monday 2/24/2020: |  |  | Basic function | entertainment |  | 内容生态
98 | Features of IVI or Connect | CVPP | 车辆故障显示 / Show the vehicle Telltale Warnings |  | 30% | 70% | 0% | Desay |  |  | x | [6 empty] | PRD DUEROS_CVPP_Vehicle_Status_PRD_v1.1 | 合并到NO161 |  | Lu, Chao (C.) <clu42@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  | 福特确认 | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 2020-01-14 | 2020-01-14 | 2020-02-28 | 2020-01-21 | 2020-02-28 | N.A | 2/6/2020: supplier to provide plan date 2/10/2020: Clarify responsible 2/19/2020: R&R clear. 2/20/2020: combine to 161. |  |  | CVPP | Message center
99 | Features of IVI or Connect | HMI | 图标位置自定义/Set icon location by Customer |  | 10% | 90% | NA | Baidu |  |  | x | [9 empty] | Liu Luisa （27inch） Xiao Yun（15.5inch 13.2inch Lincoln）Wang Lisa （13.2 Ford）Zhou Yujuan（12inch Ford） | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | zhushiyun <v_zhushiyun01@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | cancel | [7 empty] | 2/4/2020: Ford FO delete this feature
100 | Features of IVI or Connect | EESE/IVI(Diven) | IVI Wi-FI, IVI Wi-Fi Hotspot-2.4GHz&5GHz - IVI provide HMI to connect other WIFI | y | 70% | 30% | NA | Desay | x - basic function | x | x |  | 2019-11-08 |  |  |  |  | Hotspot PRD v1.3 Feature Bundle 5 track changes on.docx Hotspot Server v2 SPSS v1.2 June 25, 2018.docx Hotspot TCU SPSS v1.9 Apr 28, 2017.docx Internet Gateway APIM v2 Imp Guide v1.0 March 12, 2018.xlsx Internet Gateway APIM v2 SPSS v1.0 March 12, 2018.docx Internet Gateway APIM v2 SPSS v1.0 March 12, 2018.pdf | Wifi设置_Desay_MRD_20200117.docx | H31i_InfoBook _Wi-Fi_Hotspot_v0_6 H31i_SYNC_GEN3_Wi-Fi_Settings_RELEASED_v0_35_3_MY2020 | Yu, Diven (D.W.) <dyu12@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) | SPEC有更新，需要更新 |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/WIFI%20SPSS | close | Mid |  | 2019-11-20 | 2019-12-23 | 2019-12-30 | 2020-01-15 | N.A | Link to FNV2. Ma Mei: 11-20 Diven初步认可需后续会议继续沟通（Desay 后续会根据实际讨论情况补充Q&A） 12/23/2019: Re open 1/6/2020: Mail to FO to check MRD 1/10/2020: on-site review today 1/13/2020: MRD update 1/14 1/15/2020: sign off | Diven需要确认WPS功能是否需要实现 | x | FNV2 | WIFI | bar: 2020-03-06 to 2020-05-06
101 | Features of IVI or Connect | CVPP | 账号Account |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-01-17 |  |  |  |  | PRD DUEROS_CVPP_Ford and Baidu Accoun_Phase 2_PRD_v1.4.pdf |  | Ford HMI Requirement_Account_DRAFT_ v0.5 | Wang, Johnny (J.) <jwang308@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | panchengdong <v_panchengdong@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | delay |  |  | 2019-12-27 | 2019-12-30 | 2020-01-06 |  | B | CVPP 等百度更新输入 12/24/2019: MRD available this Friday 12/30/2019: pending by Ford FO 1/8/2020: Baidu update MRD today, meeting tomorrow 1/10/2020: Baidu provide proposal 1/13, on-site review 1/13/2020: updated MRD available 2/3/2020: arrange a meeting to discuss 2/6/2020: pending due to Ford FO 2/8/2020: Baidu arrange meeting to review 2/12/2020:discussion on-going; while dealyed, and impact UE/UI, Baidu send officially mail. |  |  | CVPP | Account |  | 账号 | bar: 2020-05-06
102 | Features of IVI or Connect | CVPP | 道路救援/Road assistance | Y | 20% | 80% | NA | Baidu |  |  | x |  | 2020-01-23 | [7 empty] | Ren, Siyuan (Alex.) <sren6@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-02-03 | 2020-02-10 | 2020-03-06 | N.A | 2/3/2020: MRD available, pending 2/6/2020: pending due to Ford FO 2/11/2020: CC Stone to push 2/11/2020: Escalated, FO not aligned |  |  | CVPP | Message center |  | 道路救援
103 | Features of IVI or Connect | CVPP | Emergency Assistance/紧急救援 | y | 40% | 10% | 50% | Ford EESE/Desay |  | x | x |  | 2019-12-20 |  |  |  |  | PRD Draft Emergency Assistance APIM_DuerOS SPSS July 2nd.pdf | Ford_MRD_紧急救援_1.4.docx | H35_SHMI Global Emergency Assist (RELEASED) v1_6_CTR.pdf | Ren, Siyuan (Alex.) <sren6@ford.com> | Chen, Yu (Y.) <ychen372@ford.com> |  | zhang yanlan<yanlan.zhang@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-29 | 2020-01-10 | 2020-01-05 | 2020-02-05 | N.A | 12/24/2019: Desay check and feedback today 12/25/2019: delay to today 12/27/2019: MRD avialable 29th 1/6/2020: Desay review internal and feedback today 1/10/2020: MRD available, Ford FO check 2/3/2020: mail send again to Ford FO 2/5/2020: sign off | 3 items: 3. 当前HotSpot CAN消息中关于string的消息包含解码类型以及不同长度的说明， Ford之前项目是MCU统一转码发给SOC,所有模块统一处理会比较好【以往项目Wifi和HotSpot涉及的解码方式都是UTF16】 –Xie Jing 4. UI的设计参照H31i_SYNC4_Vehicle_Hotspot_Settings_RELEASED_v1_02.vsdx Flow Chart来出，之前百度提供的UE文档功能有缺失需要修改 –Huang Ruihao 5. WFHS-REQ-358565这一条需要实现SOA客户端需要系统那边确认可以作为Open项处理 --Ding Yunrong |  | CVPP | Message center | bar: 2020-05-06
104 | Features of IVI or Connect | CVPP | 智能家居/Intelligent Home Control | y | 20% | 80% | NA | Baidu |  |  | x |  | 2020-01-23 |  |  |  |  | PRD |  |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-01-19 | 2020-01-19 | 2020-02-06 | 2020-02-06 | N.A | 2/4/2020: plan to sign off 2/6/2020: sign off |  |  | CVPP | APP |  | 车家互联
105 | Features of IVI or Connect | CVPP | 天气/Weather |  | 10% | 90% | NA | Baidu |  |  | x |  | 2020-01-23 | [5 empty] | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Shi, Stella (J.) <jshi32@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-01-23 | 2020-01-02 | 2020-01-09 | 2020-01-19 | N.A | 12/24/2019: MRD available. Need Ford FO check 1/2/2020: list open item and mail for notification. 1/8/2020: plan to sign off 1/19/2020: sign off | AAR URL on-going/due date? |  | CVPP | APP |  | Launcher
106 | Features of IVI or Connect | CVPP | 保养及在线预约/Vehicle Maintenance and the service booking | Y | 20% | 80% | NA | Baidu |  |  | x |  | 2020-01-23 |  |  |  |  | MRD OSB MRD.pdf | 【福特Phase4】MRD_预约保养_福特车型_V1.0_20191219 |  | Wang, Johnny (J.) <jwang308@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | shantong <v_shantong@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2020-02-07 | 2020-02-10 | 2020-02-14 | 2020-02-19 | B | 2/12/2020: sign off |  |  | CVPP | APP |  | 服务生态
107 | Features of IVI or Connect | CVPP | IVI CCPU/VMCU software FOTA update (IVI自升级) |  | 90% | 10% |  | Desay |  | x | x |  | 43829 |  |  |  |  | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf |  |  | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu guanghui(Guanghui.Liu@desay-svautomotive.com) |  | 福特确认 | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | cancel | [20 empty] | X
108 | Features of IVI or Connect | CVPP | Ford VMCU Software Update (CAN or USB) |  | 90% | 10% | NA | Desay |  | x | x |  | 43826 |  |  |  |  | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf |  |  | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Pan Juan（Juan.Pan@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | cancel | [20 empty] | X
109 | Features of IVI or Connect | CVPP | CCPU&VMCU Software Update (USB) |  | 80% | 20% | NA | Desay |  | x | x |  | 43826 |  |  |  |  | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf |  |  | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Pan Juan（Juan.Pan@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | cancel | [20 empty] | X
110 | Features of IVI or Connect | EESE/IVI(Forrest) | 车机工程模式(支持车辆工厂模式)/IVI Engineering Mode |  | 90% | 10% | NA | Desay |  | x | x |  | 2019-12-27 |  |  |  |  | based on bezel diagnostic; Phase 2 mail - archive | Ford_MRD_EngineeringMode_V02.docx |  | Wang, Fin (X.Y.) <xwang65@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-27 | 2020-01-15 | 2020-01-03 | 2020-02-10 | N.A | 12/30/2019: no MRD/replan info 1/6/2020: replan today 1/10/2020: MRD on-going 1/13/2020: check status 2/6/2020: plan to sign off; 2/10/2020: sign off |  |  | Basic function | basic | x | [7 empty] | X
111 | Features of IVI or Connect | EESE/IVI(Forrest) | Log system |  | 60% | 40% | NA | DESAY |  | x | x |  | 2019-12-20 |  |  |  |  | n.a suppliers provide the proposal and review; including HMI and data collection. | Ford_MRD_Log System.docx | N/A | Chen, Emma (J.) <jchen276@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Pan Juan（Juan.Pan@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2019-12-25 | 2019-12-30 | 2020-01-01 | 2020-02-17 | N.A | 12/25/2019: need FO check 12/27/2019: wait feedback from Desay 12/30/2019: Ford FO feedback today 1/6/2020: arrange meeting today 1/10/2020: Emma check 1/13/2020: Emma feedback today 2/6/2020: pending due to Desay 2/14/2020: plan to sign off 2/17/2020: sign off |  |  | Basic function | basic | x | [7 empty] | X
112 | Passenger Feature for 27 | HMI | 对高配27"屏幕，需要支持双屏和驾驶员屏幕独占模式（超级单屏模式）-Launcher |  | 10% | 90% |  | Baidu/Desay |  | x | x |  | 2020-01-17 |  |  |  |  | Design Guideline_CD542_To Supplier(11.15) compressed | 【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> |  | 待确定--HMI | N | Y | N | N | N | N | Y | Y | ED&T | Y |  | close |  |  | 2019-12-16 | 2019-12-13 | 2019-12-30 | 2020-01-19 | N.A | 12/25/2019: sign off? 12/30/2019: update by Baidu 1/2/2020: updated MRD? 1/8/2020: plan to sign off 1/17/2020: sign off for Desay 1/19/2020: sign off for Baidu |  |  |  |  | x | Launcher
113 | Passenger Feature for 27 | HMI | 屏幕扩展显示/Extend center or passenger display content(like Navi, to show the whole path in two screens) to two display |  | 40% | 60% | NA | Baidu |  | x | x | [7 empty] | 【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  |  |  | Y | Y | N | N | N | N | Y | Y | ED&T | N |  | close |  |  | 2019-12-27 | 2019-12-30 | 2020-01-03 | 2020-01-13 | N.A | 12/25/2019: MRD available today. 12/27/2019: open item: the scope of feature not clear, mail to FO check 12/30/2019: open item closed. 1/2/2020: need Ford FO's confirm - no MRD 1/13/2020: confirmed - split to function's UE. Close |  |  |  |  | x | Launcher
114 | Passenger Feature for 27 | HMI | 27inch - 本地及在线音乐/Offline&Online Music Player & audio manager |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-01-23 | [7 empty] | Xu, Amy <XYAFEI@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhangjingyao <v_zhangjingyao@baidu.com> |  |  |  | N | Y | N | N | N | N | Y | Y | License | N | 在音乐功能里包含 | close |  |  | 2019-12-16 | 2019-12-13 | 2019-12-30 | 2020-02-19 | B | 1/9/2020: updated MRD to be available today 1/10/2020: check today with FO 1/13/2020: MRD update 2/4/2020: updated MRD to be available 2/4 2/6/2020: pending due to Baidu 2/10/2020: plan to sign off | [5 empty] | 内容生态
115 | Passenger Feature for 27 | HMI | AR Front View/360 View/BLIS View |  | 90% | 10% |  | Desay |  |  | x | [9 empty] | Chen, Emma<jchen276@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  | ED&T: ED&T; N: Y |  | cancel | [7 empty] | 2/6/2020: supplier to provide plan date 2/19/2020：FO change? 2/24/2020: MRD to be ready on this Wednesday 3/3/2020: DAT team had different view with HMI team. 3/10/2020: CD542 CPE meeting - delete this feature now.
116 | Passenger Feature for 27 | EESE/DI | 27"空调设置(climate control from passenger area) |  | 90% | 10% |  | Desay |  | x | x | [6 empty] | same with climate control | Ford_MRD_空调_TBD_v1.7_20200222.docx 空调页面说明_v1.5.xls 空调页面说明_硬按键软按键.xlsx |  | Li, Jun (J.) <jli198@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） |  |  | N | Y | N | N | N | N | Y | Y | ED&T | Y |  | close |  |  | 2020-01-09 | 2020-01-09 | 2020-01-16 | 2020-02-07 | N.A | 1/13/2020: combine with climate control 2/7/2020: plan to sign off; sign off
117 | Passenger Feature for 27 | EESE/IVI(Diven) | 副驾视频播放(支持 DLNA)/Passenger Video Playback(Support DLNA) |  | 80% | 20% | NA | Desay |  | x | x |  | 2020-01-23 | [5 empty] | Ford_MRD_DLNA_20200217.docx |  | Jia, Elaine (T.) <tjia2@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | sunying <sunying05@baidu.com> | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  | 待确定--福特 | N | Y | N | N | N | N | Y | Y | ED&T | N |  | close |  |  | 2020-02-14 | 2020-02-17 | 2020-02-21 | 2020-02-18 | N.A | 12/30/2019: new plan 2/4/2020: Baidu transfer to Desay 2/6/2020: supplier to provide plan date 2/17/2020: MRD avaialble, review
118 | Passenger Feature for 27 | EESE/IVI(Diven) | 副驾在线视频/Online Video-clarify |  | 10% | 90% | NA | Baidu |  | x | x |  | 2020-01-23 | [5 empty] | 在线视频 Online video.docx |  | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhangjingyao <v_zhangjingyao@baidu.com> |  |  |  | N | Y | N | N | N | N | Y | Y | License | N | 在视频功能里包含 | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-19 | B | 12/30/2019: new plan 1/13/2020: MRD update today 2/6/2020: pending due to Baidu |  |  |  |  | x | 内容生态
119 | Passenger Feature for 27 | EESE/IVI(Forrest) | 副驾主页/Passenger HomeScreen |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-02-03 | [5 empty] | 【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  |  |  | N | Y | N | N | N | N | Y | Y | ED&T | N |  | close |  |  | 2019-12-16 | 2019-12-13 | 2019-12-30 | 2020-01-19 | N.A | 12/25/2019: sign off? 12/30/2019: update by Baidu 1/2/2020: updated MRD? 1/8/2020: plan to sign off 1/17/2020: sign off for Desay 1/19/2020: sign off for Baidu |  |  |  |  | x | Launcher
120 | Passenger Feature for 27 | EESE/IVI(Diven) | 27"地图/including Passenger Map&Navigation |  | 10% | 90% | NA | Baidu |  | x | x |  | 2020-02-03 | [5 empty] | 【福特Phase4】MRD_27寸_地图_HMI变更_V1.2_2020_01_16-终版-已评审 |  | Wang, Jingjing (J.) <jwang354@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | Zhang,Honghai(IOV) <zhanghonghai02@baidu.com> |  |  |  | N | Y | N | N | N | N | Y | Y | License | N | 在地图功能里包含 | close |  |  | 2019-12-30 | 2019-12-30 | 2020-01-06 | 2020-02-06 | N.A | 12/30/2019: pending by Ford FO 1/9/2020: need Baidu's updated MRD 1/10/2020: meeting today 1/13/2020: Baidu check and update MRD, arrange follow up meeting 2/4/2020: plan to sign off 2/6/2020: sign off |  |  |  |  | x | 地图
121 | Passenger Feature for 27 | CVPP | 副驾天气预报/Weather forecast |  | 10% | 90% | NA | Baidu |  | x | x |  | 2020-01-23 | [5 empty] | 【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Shi, Stella (J.) <jshi32@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  |  |  | N | Y | N | N | N | N | Y | Y | License | N | 在天气功能里包含 | close |  |  | 2019-12-16 | 2019-12-13 | 2019-12-30 | 2020-01-19 | N.A | 12/24/2019: combine to 27" launcher. Baidu check and feedback 12/25/2019: confirmed, mentioned in the spec. 12/30/2019: pending by Ford FO 1/9/2020: plan to sign off 1/9/2020: detail strategy shall follow whether in driver side. TBD 1/19/2020: sign off by Baidu | [5 empty] | Launcher
122 | Passenger Feature for 27 | EESE/IVI(Forrest) | 副驾系统设置/Passenger system setting（system settings display in passenger area as well） |  | 90% | 10% | NA | Desay |  | x | x | [7 empty] | 合并到NO80 |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | N | Y | N | N | N | N | Y | Y | ED&T | N |  | close |  |  | 2020-02-20 | 2020-02-13 | 2020-02-20 | 2020-02-13 | D | 2/6/2020: supplier to provide plan date 2/13/2020: sign off |  |  |  |  | x
123 | Passenger Feature for 27 | IVI | 副驾文件浏览器／Passenger File Manager |  | 90% | 10% | NA | Desay |  | x | x | [9 empty] | Jia, Elaine (T.) <tjia2@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Dong Zhaojun<zhaojun.dong@desay-svautootive.com> |  |  | N | Y | N | N | N | N | Y | Y | ED&T | N |  | cancel | [6 empty] | N.A | 2/6/2020: supplier to provide plan date 2/17/2020: FO cancel
124 | Passenger Feature for 27 | EESE/IVI(Diven) | 副驾图片浏览器/Passenger Picture Viewer |  | 90% | 10% | NA | Desay |  | x | x | [7 empty] | Picture_MRD.DOCX |  | Jia, Elaine (T.) <tjia2@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Dong Zhaojun<zhaojun.dong@desay-svautootive.com> |  |  | N | Y | N | N | N | N | Y | Y | ED&T | N |  | close |  |  | 2020-02-14 | 2020-02-14 | 2020-02-18 | 2020-02-14 | D | 2/6/2020: supplier to provide plan date 2/14/2020: plan to sign off 2/14/2020: sign off
125 | C/O from ICA1 | IVI | features C/O from IVI ICA1（461 Phase1/2/3 features need to move to Phase4. Please refer to column "G&H" of sheet2 "461 CO Phase1&2&3 feature"） |  | 10% | 90% |  | Baidu |  |  | x |  | 2020-01-23 | [7 empty] | Yu, Yaxing (Y.) <yyu55@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | shantong <v_shantong@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | License | Y |  | cancel | [7 empty] | 2/3/2020: not needed as features already reviewed
126 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Diven) | 人物百科 Celebrity encyclopedia | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-23 | [5 empty] | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Wang, Jingjing (J.) <jwang354@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close |  |  | 2020-02-06 | 2020-02-06 | 2020-02-28 | 2020-02-28 | N.A | 1/2/2020: combined in feature 90; 在“更多”里面提供了使用说明。 2/6/2020: pending due to Ford FO 2/20/2020: postphone to 3/30 |  |  | WOW | WOW |  | 语义垂类
127 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Diven) | 世界之最 Most ** of the world | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 | [5 empty] | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Wang, Jingjing (J.) <jwang354@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close |  |  | 2020-02-06 | 2020-02-06 | 2020-02-28 | 2020-02-28 | N.A | 1/2/2020: combined in feature 90; 在“更多”里面提供了使用说明。 2/20/2020: postphone to 3/30 |  |  | WOW | WOW |  | 语义垂类
128 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 智慧停车 smart parking | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 |  |  |  |  | MRD | 【福特Phase4】MRD_ETCP_福特车型_V1.1_20200206 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | shantong <v_shantong@baidu.com> |  | Follow Baidu | [12 empty] | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-02-14 | N.A | 2/7/2020: Ford FO check 2/12/2020:plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | 服务生态 | bar: Y to ED&T
129 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 电影购票 ticket booking | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 |  |  |  |  | MRD | 【福特Phase4】MRD电影票_福特车型_V1.0_20191219 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | shantong <v_shantong@baidu.com> |  | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-02-14 | N.A | 2/7/2020: Ford FO check 2/12/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | 服务生态
130 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 酒店预定 hotel booking | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 |  |  |  |  | MRD | 【福特Phase4】MRD_酒店预订_福特车型_V1.0_20191219 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | shantong <v_shantong@baidu.com> |  | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-02-14 | N.A | 2/7/2020: Ford FO check 2/12/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | 服务生态
131 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | IVI | 车载KTV |  | 0% | 100% |  | Baidu |  |  |  |  | 2020-01-23 | [7 empty] | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | liurui <liurui18@baidu.com> |  |  | KTV麦克风作为选装件 需要按车型标定 福特确认是否需要 | N | N | N | N | N | N | N | N | License | Y |  | cancel | [7 empty] | 1/10/2020: applied in phase4? 1/13/2020: feature removed confirmed with Susan
132 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Diven) | 在线视频（爱奇艺） | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 | [5 empty] | 在线视频 Online video.docx |  | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | lijing <lijing101@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close |  |  | 2020-02-04 | 2020-02-04 | 2020-02-11 | 2020-02-06 | N.A | 2/6/2020: sign off |  |  | Basic function | entertainment |  | 内容生态
133 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 聚合支付 / aggregate payment | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 |  |  |  |  | MRD | 【phase4】MRD_支付模块_福特/林肯_V1.8_2019_05_30 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | panchengdong <v_panchengdong@baidu.com> |  | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-02-07 | 2020-02-10 | 2020-02-14 | 2020-02-14 | N.A | 2/12/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | 服务生态
134 | Passenger Feature for 27 | IVI | 27" 输入法 - 副驾输入法 / words input |  | 90% | 10% |  | Desay |  | x | x | [9 empty] | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Wu Zhengxue(Zhengxue.Wu2@desay-svautomotive.com) | 27" 由DESAY study，给出新的proposal | [12 empty] | cancel | [6 empty] | D | 2/6/2020: supplier to provide plan date 2/11/2020: Based on the info from FO, Baidu can not support. Cancel this feature | bar: Y to Y; N
135 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Forrest) | 百度输入法（包括27“主屏输入法） | Y | 10% | 90% |  | Baidu |  | x | x |  | 2019-12-20 |  |  |  |  | n.a suppliers provide the proposal and review; including HMI and data collection. | 无MRD | N/A | Chen, Emma (J.) <jchen276@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  |  | 主副驾都需要输入法的情况下，百度无法支持 Phase1/2输入法的问题，福特评估是否能接受 | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | delay |  |  | 2019-12-30 | 2019-12-30 | 2020-03-30 |  | B | 12/30输出车机输入法+语音输入可行性评估。 下周输出车机版与手机版功能点全部差异。 12/30/2019: no comments from FO; 语音输入待定 1/2/2020: c/o phase2的HMI改进需求； 1/9/2020: 2 open items to be tracked by Baidu 1. 语音输入 2. 输入法在27寸上面的浮动可行性-lusia 1/10/2020: feedback before 1/14 2/4/2020: Pending due to supplier |  |  | Basic function | basic |  | 输入法 | [6 empty] | X
136 | Vehicle Features/Interfaces | EESE/IVI(Roger) | AHUD and features (CAN bus interface) | Y | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | folder: cluster Interaction | 合并到NO14 |  | Chen, James (J.) <jchen303@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Chen Xiujing(Xiujing.Chen@desay-svautomotive.com) | [13 empty] | close |  |  | 2020-01-10 | 2020-02-14 | 2020-01-17 | 2020-02-28 | N.A | 12/30/2019: no MRD/replan info 1/6/2020: replan to 1/10 1/10/2020: Desay CAN check based on interaction spec between IVI & cluster. 1/13/2020: 1/14 desay feedback, combine to cluster feature 14. |  |  | Vehicle related | AHUD | bar: Y to Y; N
137 | Vehicle Features/Interfaces | CVPP | Auto Air Refresh |  | 30% | 70% |  | Baidu |  | x | x |  | 2019-12-30 |  |  |  |  | Draft available on Dec. 11th | 福特Phase 4_AAR_MRD 2020_0214 | H26g_SYNC4_Auto_Air_Refresh_Gen_1_Plus_RELEASED_v2_03_MY21 | Shi, Stella (J.) <jshi32@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  |  | Shi Stella | N | Y | Y | Y | Y | Y | Y | Y |  |  |  | close |  |  | 2019-12-30 | 2020-01-02 | 2020-01-06 | 2020-02-14 | N.A | 1/2/2020: MRD available 1/9/2020: status check 1/10/2020: involve HMI to confirm 1/13/2020: HMI ok, interface not clear. 1/19/2020: sign off 2/14/2020: Baidu check- change? 2/14/2020: sign off after confirm |  |  | CVPP | APP |  | 硬件联动 | [6 empty] | X
138 | BU features | EESE/IVI(PT)(Diven) | Behavior Coaching Display Client |  | 95% | 5% |  | Desay |  |  | x | [6 empty] | Behavior Coaching Display Client v2 APIM Imp Guide v1.0 Nov 19, 2018.xlsx Behavior Coaching Display Client v2 APIM SPSS v1.0 Nov 19, 2018.docx Behavior Coaching Display Client v2 APIM SPSS v1.0 Nov 19, 2018.pdf | Ford_MRD_BehaviorCoachingDisplayClient_V02.docx | H87a_SYNC4_IoD_In _SYNC_Requirements-RELEASED_v1_03_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang dong <Dong.Wang@desay-svautomotive |  | 待确定--HMI | Y | Y | Y | N | N | N | N | Y |  | Y |  | close |  |  | 2020-02-20 | 2020-02-18 | 2020-02-25 | 2020-02-19 | D | 2/6/2020: supplier to provide plan date 2/18/2020: push Diven @Emma
139 | BU features | EESE/IVI(Forrest) | Enhanced VO Test (FCPA Logging) [On hold Feature] |  | 60% | 40% |  | Desay | [11 empty] | N/A | Chen, Emma (J.) <jchen276@ford.com> | N/A |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) | [13 empty] | hold-on |  |  | hold-on | hold-on | hold-on | hold-on | F | 2/6/2020: supplier to provide plan date 2/6/2020: ON-hold till SPSS is ready |  |  | N.A | N.A | bar: Y to Y; N
140 | BU features | EESE/IVI(Roger) | Detroit Symphony Orchestra chimes |  | 100% | 0% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Alerts APIM Imp Guide v1.2 May 3, 2017.xlsx Alerts APIM SPSS v1.2 May 3, 2017.pdf RQT-001502-012992_12 Chime Sound Quality.pdf | Ford IVI SW Q&A_Audio&A2B.xlsx |  | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com | Hu, Pin (P.) <phu13@ford.com> |  | Xu Jianjun（Jianjun.Xu@desay-svautomotive.com） | [13 empty] | close |  |  | 2019-12-30 | 2019-12-27 | 2020-01-06 | 2019-12-30 | N.A | 12/27/2019: checked with FO, combined with item 9. 12/30/2019: close based on the mail confirm |  |  | Chime management | Chime management | bar: Y to Y; N
141 | BU features | EESE/IVI(Diven) | IOD - Fuel Economy |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Fuel Economy SPSS v1.1 January 31, 2019 Fuel Economy APIM Imp Guide v1.1 January 31, 2019 | Ford_MRD_IoD_FuelEconomy_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  | 细节待确定--HMI | N | N | Y | N | Y | N | N | N |  | Y |  | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open | [11 empty] | X
142 | BU features | EESE/IVI(Diven) | IOD - Pitch and Roll |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Pitch and Roll SPSS v1.0.1 Dec 18, 2018 Pitch and Roll APIM Imp Guide v1.0.1 Dec 18, 2018 | Ford_MRD_IoD-PitchandRoll_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [13 empty] | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open | [11 empty] | X | bar: 福特确认 to Y; N
143 | BU features | EESE/IVI(Diven) | IOD - SeatBelt (information on demand) |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Seatbelt IOD SPSS v1.0 Dec 19, 2018 Seatbelt IOD APIM Imp Guide v1.0 Dec 19, 2018 | Ford_MRD_IoD_SeatBelt_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [13 empty] | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open | [11 empty] | X | bar: 福特确认 to Y; N
144 | BU features | EESE/IVI(Diven) | IOD - TPMS (Information on Demand) |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | TPMS Information On Demand SPSS v1.0 March 5, 2019 TPMS Information On Demand Imp Guide v1.0 March 5, 2019 | Ford_MRD_IoD-TPMS_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [13 empty] | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open |  | vehicle related | Message center | [8 empty] | X | bar: 福特确认 to Y; N
145 | BU features | EESE/IVI(Diven) | IOD - Trip Information On Demand |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Trip Information on Demand SPSS v1.1 Nov 16, 2018 Trip Information on Demand APIM Imp Guide v1.1 Nov 16, 2018 | Ford_MRD_IoD_Trip_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [13 empty] | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open | [11 empty] | X | bar: 福特确认 to Y; N
146 | BU features | EESE/IVI(Diven) | IOD - Off Road |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Off-Road Status IOD APIM SPSS v1.0 Aug 23, 2019.pdf Off-Road Status IOD APIM Imp Guide v1.0 Aug 23, 2019.xlsx | Ford_MRD_IoD-Off-road_Status_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [12 empty] | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/Off%20Road%20Turn%20Assist | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open |  | vehicle related | Message center | bar: 福特确认 to Y; N
147 | BU features | CVPP | Backup Startup Passcode for PAAK | y | 95% | 5% | NA | Desay |  |  | x |  | 2020-02-03 |  |  |  |  | PRD 【更新】【Phase2林肯】LBI智能备用密钥_MRD_2019_7_11-v2.0.pdf | PaaK BSP (LBI) Implementation Specification 2.8 Imp Guide v1.1_20200213.xlsx | H31k_SYNC4_Settings_R_v0_36_MY21 H31m_SYNC4_Backup Ignition_R_v1.3_MY21 | Wang, Cindy (X.J.) <xwang216@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> | liu yi <Yi.Liu@desay-svautomotive.com> |  | Phase1/2百度已开发的功能，Phase4是否沿用原有的模式，由百度开发？？ | N | Y | Y | NA | NA | Y | Y | Y |  | Y |  | close |  |  | 2020-02-21 | 2020-02-13 | 2020-02-28 | 2020-02-14 | N.A | 2/4/2020: R&R to be updated? 2/6/2020: tranfer to Desay, supplier to provide plan date 2/14/2020: sign off |  |  | CVPP | PAAK
148 | Basic features | CVPP | Message Center (CVPP) | y | 5% | 95% |  | Baidu |  | x | x |  | 2019-12-27 |  |  |  |  | spec Dec. 13th | 【福特phase4】MRD_消息中心_福特CX727U725P702CD542U625ICA_V2.7_2020_02_13 【福特phase4】MRD_消息中心_林肯U554_V2.7_2020_02_13 | H22a_SYNC4_Screen_Interruption_Table_RELEASED_ v1_01_MY21 Message_Center_Display_Interface_With_Setup_and_Warnings_In_Centerstack - CGEA1.3_v1.2.docm | Wang, Johnny (J.) <jwang308@ford.com>（Harlow, Julee (J.L.) <jharlow6@ford.com>） | Pan, Jingjing (J.) <jpan35@ford.com> | panchengdong <v_panchengdong@baidu.com> | [14 empty] | close |  |  | 2019-12-27 | 2020-01-02 | 2020-01-06 | 2020-02-14 | B | 1/2/2020: MRD available. Need Ford FO check. 1/9/2020: status check 1/10/2020: MRD update by Baidu, send to Ford FO 1/13/2020: MRD available, meeting this Wednesday 2/3/2020: pending by Ford FO, baidu arrange meeting 2/10/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | Message center |  | 消息中心 | [6 empty] | X | bar: Y to Y; N
149 | Basic features | EESE/IVI(Forrest) | Message Center Client (APIM) |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-25 |  |  |  |  | Message Center Client v3 SPSS v1.1 Aug 23, 2019 Message Center Server v3 SPSS v1.1 Aug 23, 2019 | Ford_MRD_MessageCenterClient_V06.docx | CX727_Message Center Client_Interaction Spec_20200110.pdf Global_Msg_List_ver81_Released_2_4_2020.xlsx | Xu, Harriet (J.) <jxu128@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [13 empty] | close |  |  | 2020-01-10 | 2020-02-25 | 2020-01-17 | 2020-03-02 | N.A | 12/30/2019: replan 1/10/2020: Desay provide OIL 1/13/2020: check status 2/24/2020: Open item list send out by FO | [12 empty] | X | bar: Y to Y; N
150 | BU features | DAT | Multi Camera - CHMSL/AUX Camera/Rock Crawl |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36k_SYNC4_Camera_Systems_R_v0_20_MY21 H36t_SYNC4_Trailer Settings_RELEASED_1_18_MY21 P702 post J1 H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21 | Wang, Tom (X.) <xwang190@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | N | N | N | Y | N | N | N | ED&T | Y |  | close |  |  | 2020-01-08 | 2020-01-14 | 2020-01-15 | 2020-01-20 | N.A | 12/30/2019: Jan. 8th meeting/replan 1/10/2020: on-site review 1/13/2020: desay check status 2/8/2020: sign off on 1/20 |  |  | driver assist | Driver assist setting
151 | BU features | EESE/Convenience&Security Module team | Multi-Contoured Seats (Enhanced Massage Seats) |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Multi Contoured Seats Client V2 Imp Guide v1.3 June 28, 2018.xlsx Multi Contoured Seats Client V2 SPSS v1.3 June 28, 2018.docx Multi Contoured Seats Client V2 SPSS v1.3 June 28, 2018.pdf | 不需要输出MRD | H74a_SYNC4_Seat_Controls_RELEASED_0_06_MY21 | Xia,Zhiqiang<zxia13@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) | [13 empty] | close |  |  | 2020-01-08 | 2020-02-14 | 2020-01-15 | 2020-02-19 | F | 12/30/2019: Jan. 8th meeting/replan 1/10/2020: on-site review 1/13/2020: 1/14 MRD or open item list 2/14/2020: plan to sign off |  |  | driver assist | Driver assist setting | bar: Y to Y; N
152 | BU features | EESE/Convenience&Security Module team | Multi-Contoured Seats (Massage Seats) | Y | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Multi Contoured Seats APIM Imp Guide v1.2 Jun 9 2015.xlsx Multi Contoured Seats APIM SPSS v1.2 Jun 9 2015.docx Multi Contoured Seats APIM SPSS v1.2 Jun 9 2015.pdf | 不需要输出MRD | H74a_SYNC4_Seat_Controls_RELEASED_0_06_MY21 | Xia,Zhiqiang<zxia13@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) | [13 empty] | close |  |  | 2020-01-08 | 2020-01-19 | 2020-01-15 | 2020-01-19 | N.A | 12/30/2019: Jan. 8th meeting/replan 1/10/2020: on-site review 1/13/2020: 1/14 OIL by desay 1/19/2020: sign off, open item archived | 1. Do we need to support Massage pattern (Mode)? A: Yes. <Follow Multi Contoured Seats Client V2 SPSS v1.3 June 28, 2018> - Xia, Zhiqiang to double confirm 2. Initiation process During Key On, Does SYNC4 need to send initial value to SCMG/SCMH (MCS module)? - Xia, Zhiqiang 3. How many bladders for U554 MCA (7 or 11 bladder)? - Diven to check PDL 4. U554 MCA - MCS seat buttons layout and function definition | bar: Y to Y; N
153 | BU features | DAT | trail Turn Assist (Soft switch) |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | TTA_SoftSwitch_FunctionSpecification_112519.pdf | Ford_MRD_SoftSwitch_TrailTurnAssist.docx | H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21 H31c_SYNC4_InfoBook_Supplement_RELEASED_v1_17_MY21 | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [13 empty] | close |  |  | 2020-01-10 | 2020-01-10 | 2020-01-17 | 2020-01-11 | N.A | 12/30/2019: spec avaialble: TTA_SoftSwitch_FunctionSpecification_112519 1/6/2020: replan to 1/10 1/10/2020: Desay send out OIL | HMI open - menu, display info |  |  |  | x | bar: Y to Y; N
154 | BU features | EESE/IVI(PMT1)(Forrest) | Power Running Boards (PRB) |  | 90% | 10% |  | Desay |  |  | x | [6 empty] | Power Running Boards Softswitch InterfaceClient SPSS v1.0 October 5, 2018.pdf Power Running Boards Softswitch InterfaceClient Imp Guide v1.0 October 5, 2018.xlsx | 合并到NO11 | H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21 H31k_SYNC4_Settings_R_v0_36_MY21 H31c_SYNC4_InfoBook_Supplement_RELEASED_v1_17_MY21 | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [12 empty] | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/Power%20Running%20Boards%20(PRB) | close |  |  | 2020-02-20 | 2020-02-10 | 2020-02-27 | 2020-02-10 | D | 2/6/2020: supplier to provide plan date 2/10/2020: sign off |  |  | vehicle related | Vehicle setting | x | bar: Y to Y; N
155 | BU features | EESE/IVI(PMT1)(Forrest) | Power Tailgate (FordPass/SYNC); including liftgate/… |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | TailGate Softswitch InterfaceClient Imp Guide v1.3 June 25, 2019.xlsx TailGate Softswitch InterfaceClient SPSS v1.3 June 25, 2019.pdf | Ford_MRD_SoftSwitch_PowerTailgate_V02.docx | H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21 H31k_SYNC4_Settings_R_v0_36_MY21 H31c_SYNC4_InfoBook_Supplement_RELEASED_v1_17_MY21 | Chen, Emma (J.) <jchen276@ford.com>/ Li, Xuedong (X.) <xli244@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) | [13 empty] | close |  |  | 2020-01-08 | 2020-01-08 | 2020-01-15 | 2020-01-13 | N.A | 12/30/2019: Jan. 8th meeting/replan 1/8/2020: Desay send out MRD today 1/9/2020: desay provide OIL, plan to sign off 1/13/2020: sign off after archive in github and checklist update |  |  |  |  | x | bar: Y to Y; N
156 | BU features | DAT | Remote Park Assist (RePA) |  | 90% | 10% |  | Desay |  |  | x | [6 empty] | Remote Active Park Assist SPSS v1.0 Feb 4, 2020 |  | P36k_15P_SYNC4_Camera_R_v2_00_MY21 | He, Michael (X.) <xhe22@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> | [13 empty] | delay |  |  | 2020-02-20 | 2020-02-28 | 2020-02-27 |  | F | 2/6/2020: supplier to provide plan date 2/24/2020: Open item list to be provided before tomorrow |  |  | driver assist | Driver assist HMI | bar: Y to Y; N
157 | BU features | EESE/IVI(Roger) | Revel QLI 3D Audio (Audio System, settings) |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Audio Settings APIM SPSS v1.4 Nov 6, 2019 Audio Settings APIM Imp Guide v1.4 Nov 6, 2019 | 不需要输出MRD |  | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu Jianjun（Jianjun.Xu@desay-svautomotive.com） | [13 empty] | close |  |  | 2019-12-30 | 2019-12-27 | 2020-01-06 | 2020-01-14 | N.A | 12/27/2019: checked with FO, mail to FO for the OIL. 1/6/2020: plan to sign off 1/14/2020: sign off |  |  | Chime management | Chime management | x | bar: Y to Y; N
158 | BU features | EESE/IVI(PMT3)(Forrest) | SELECTABLE DRIVE MODES (different modes for each program) |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-30 |  |  |  |  | Selectable Drive Mode APIM Imp Guide v1.2 Aug 21, 2019.xlsx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.docx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.pdf | 不需要输出MRD |  | Gu, Zhengfu (Z.) <zgu11@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) | [13 empty] | close |  |  | 2019-12-30 | 2020-01-10 | 2020-01-06 | 2020-01-15 | N.A | HMI: Desay prepare UE 12/23/2019: SPSS is ok, while HMI need to be provided. 12/30/2019: need Desay to provide HMI 1/6/2020: Desay mail to FO/HMI 1/10/2020: Ford HMI can not accept the prospoal - open item Desay provide OIL today 1/13/2020: delay to today 1/15/2020: sign off | HMI open |  | Vehicle related | SDM | [8 empty] | X | bar: Y to Y; N
159 | BU features | CVPP | Stolen Vehicle Services InterfaceClient (APIM) |  | 90% | 10% |  | Desay |  | x | x | [6 empty] | PRD 2018-02-28_SVS_PRD.pdf | Stolen Vehicle Services InterfaceClient Imp Guide v1.8 August 9, 2019 for Desay_0225.xlsx | N/A | Ren, Siyuan (Alex.) <sren6@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> | [13 empty] | close |  |  | 2020-01-14 | 2020-02-14 | 2020-01-21 | 2020-02-19 | N.A | 1/6/2020: Desay replan 2/12/2020: plan to close before 2/21 |  | x | FNV2 | FNV2-basic | [8 empty] | X | bar: Y to Y
160 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(PMT4)(Forrest) | One Pedal Drive |  | 90% | 10% |  | Desay |  |  | x | [6 empty] | One-Pedal Drive APIM SPSS v1.0 May 14, 2019.pdf One-Pedal Drive APIM Imp Guide v1.0 May 14, 2019.xlsx | 合并到NO11 | H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21(TBD) | Chen, Emma (J.) <jchen276@ford.com>/ Li, Xuedong (X.) <xli244@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) | [12 empty] | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/One%20Pedal%20Drive | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2020-01-11 | D | 2/10/2020: sign off - discussed before. |  |  |  |  | x | bar: Y to Y; N
161 | Connectivity | CVPP | Vehicle Health/Alert [ include, Show the vehicle Telltale Warnings] |  | 70% | 30% | VR 可唤醒 | Desay |  | x | x | [6 empty] | PRD | Vehicle Health Alert APIM Imp Guide v1.4_20200302.xlsx |  | Lu, Chao (C.) <clu42@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> | [13 empty] | close |  |  | 2020-01-14 | 2020-02-28 | 2020-01-21 | 2020-02-28 | D | 1/6/2020: Desay replan 2/12/2020: plan to close before 2/18 2/24/2020: check the status |  | x | FNV2 | FNV2-basic | [8 empty] | X | bar: 福特确认 to N
162 | Connectivity | CVPP | TCU supply feed |  | 90% | 10% |  | Desay |  | x | x | [6 empty] | A51s_SYNC4-Supplier_Feed_Specification_214.pdf |  | N/A | Zong, Yongtao (Y.) <yzong@ford.com> | N/A |  | liu, zhiyong | [13 empty] | cancel | [6 empty] | N.A | 12/30/2019: no MRD/replan info 1/6/2020: regular tracking, provide a plan 1/13/2020: plan on-going 2/24/2020: Tracked in project meeting? 3/3/2020: 针对FNV2项目China IVI SupplyFeed，Global team策略是取消peripheral ECUs（包括IVI）的SupplyFeed requirement。  A51t FNV2-SupplyFeed Spec暂停开发，同时SupplyFeed中的Security package是独立的流程，由Security team Eric继续与Desay跟进开发；  保留前期Desay与Ford完成VPN tunnel的建立，用于Security package process； |  |  | Basic function | EOL | [8 empty] | X | bar: Y to Y
163 | Connectivity | CVPP | IVI TCU Provisioning - Baidu cloud, Ford cloud |  | 90% | 10% |  | Desay |  | x | x | [6 empty] | Peripheral Module Provisioning SPSS v1.3 Apr 10, 2019.pdf | Peripheral-Provision-MRD-v1.1.docx ford-provision-mrd-diagrams.vsdx ivi-provision-baidu-cloud-analysis-rev01.pptx | N/A | Cui, Rebecca (H.) <hcui2@ford.com> | N/A |  | Liu, Chenxi <Chenxi.Liu@desay-svautomotive.com> | [13 empty] | close |  |  | 2019-12-27 | 2020-01-06 | 2020-01-03 | 2020-03-02 | N.A | 12/30/2019: Ford FO replied. 1/6/2020: Desay provide OIL 1/10/2020: on-going 1/13/2020: Desay push FO 2/12/2020: plan to close before 2/21 3/2/2020: sign off |  | x | FNV2 | EOL | [8 empty] | X | bar: Y to Y
164 | Connectivity | CVPP | Authorization车机授权 |  | 90% | 10% |  | Desay |  | x | x |  | 2019-12-25 |  |  |  |  | PRD DUEROS_CVPP_Authorization_PRD v1.0 | 福特phase1车机端服务授权功能MRD.docx |  | Gu, Xiaosheng (X.) <xgu14@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> | [13 empty] | close |  |  | 2019-12-25 | 2020-02-13 | 2020-01-01 | 2020-03-02 | N.A | 12/25/2019: replan 12/27/2019: delay to today 1/6/2020: replan today 1/10/2020: C/O phase 2, no change. 1/13/2020: postone to 1/14 2/17/2020: FO changed, plan to close within this week. 3/2/2020: sign off based on Stone's mail |  |  | CVPP | message center | [8 empty] | X | bar: Y to Y
165 | Connectivity | CVPP | In-vehicle notification | y | 100% | 0% | NA | Desay |  |  | x |  | 2020-02-03 | [5 empty] | Customer Connectivity Settings Client APIM SPSS v1.4 imp Guide v1.2_20200214.xlsx | Ford HMI_Invehicle and T&C_Interaction Spec_DRAFT.pdf | Ge, Haiqing (H.) <hge5@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-24 | 2020-02-26 | 2020-02-28 | 2020-02-28 | N.A | 2/6/2020: pending due to Ford FO 2/11/2020: review discussion this week 2/19/2020: R&R clear 2/20/2020: combine to CCS MRD, update CCS MRD. Ford FO prepare PRD |  |  | CVPP | message center
166 | Connectivity | CVPP | T&C and Privacy Policy in HMI [Hold On] | Y | 5% | 15% | 80% | Ford CVPP |  |  | x |  | 2020-02-03 | [6 empty] | Ford HMI_Invehicle and T&C_Interaction Spec_DRAFT.pdf | Gu, Regina<QGU12@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | hold-on |  |  | hold-on | hold-on | hold-on | hold-on | F | 2/3/2020: wait feedback from FO 2/6/2020: pending due to Ford FO 2/7/2020: who development not decided? Ford solution not decided. This feature can be hold-on based on current status. |  |  | CVPP | message center
167 | Connectivity | CVPP | Take-away/美团MeiTuan | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-02-03 |  |  |  |  | MRD | 【福特Phase4】MRD_外卖_福特车型_V1.0_20191219 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | shantong <v_shantong@baidu.com> |  | Follow Baidu | [12 empty] | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-02-14 | N.A | 2/7/2020: Ford FO check 2/12/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | 服务生态 | bar: Y to Y
168 | Connectivity | CVPP | Connected Embeded Navigation | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-02-03 |  |  |  |  | PRD DUEROS_CVPP_Connected Embedded Navigation_PRD v1.0 | 【MRD】send to car &car to phone |  | Shi, Stella (J.) <jshi32@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhanghonghai <zhanghonghai02@baidu.com> | [14 empty] | close |  |  | 2020-02-11 | 2020-02-11 | 2020-02-18 | 2020-02-19 | B | 2/7/2020: can not reach FO 2/10/2020: replan 2/11/2020: plan to C/O from phase2; MRD mailed to FO |  |  | CVPP | APP |  | 地图 | bar: Y to Y
169 | Connectivity | CVPP | Real Name Register |  | 0% | 100% | No related to IVI | Baidu |  |  | x |  | 2020-02-03 |  |  |  |  | Draft |  |  | Wang, Yuran (Y.) <ywang422@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | panchengdong <v_panchengdong@baidu.com> |  | 需要百度增加RNR需求 | [12 empty] | cancel | [7 empty] | 2/3/2020: aligned as not needed. | bar: Y to Y
170 | Connectivity | CVPP | Customer Feedback | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-02-03 |  |  |  |  | PRD 福特意见反馈MRD 1129.pdf | 【福特Phase4】意见反馈_MRD_2020_01_07 |  | Wang, Johnny (J.) <jwang308@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | close |  |  | 2020-01-10 | 2020-01-10 | 2020-01-17 | 2020-01-19 | N.A | 12/30/2019: replan 1/13/2020: MRD available 1/19/2020: sign off |  |  | CVPP | APP |  | 意见反馈 | bar: Y to Y
171 | Connectivity | CVPP | Ford Finance / Lincoln Finance | Y | 0% | 20% | 80% | Ford CVPP/Baidu |  |  | x |  | 2020-02-03 |  |  |  |  | PRD DUEROS_CVPP_Ford_Finance_PRD_v1.1 | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | close |  |  | 2019-12-23 | 2019-12-24 | 2019-12-31 | 2020-01-19 | N.A | 12/30/2019: replan 1/2/2020: combine with feature 298. Ford develop ? Or baidu? 1/9/2020: plan to sign off 1/19/2020: sign off |  |  | CVPP | APP |  | 第三方集成应用 | bar: Y to Y
172 | Connectivity | EESE | Shifted GPS [merge into location service, due to V2X cancelled] | Y | 30% | 70% | need confirmed with Baidu | Baidu |  |  |  |  | 2019-10-30 |  |  |  |  | Location Service APIM SPSS v1.10 July 10, 2019 |  | N/A | Wu, Jianfei (J.) <jwu158@ford.com> | N/A | pulijing <v_pulijing@baidu.com> |  | SPEC有更新，需要更新MRD | [12 empty] | cancel | low | [6 empty] | 百度法务评审中， 12/24给出回复 12/25/2019: need Ford FO feedback 12/27/2019: Baidu check, compared with Phase 1/2, V2X addd only. 1/2/2020: Baidu check 1/9/2020: Baidu - Lu minghao check 1/10/2020: need Ford FO to sign off 1/15/2020: feature on-hold. From baidu side, c/o phase 1/2, feature merged into location service.
173 | Connectivity | CVPP | Consumer Behavior Data (IVI related)埋点 |  | 30% | 70% |  | Baidu |  |  | x | [9 empty] | Gu, Zhong Tian (Z.) <zgu10@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhanglihong <v_zhanglihong02@baidu.com> | [14 empty] | hold-on |  |  | hold-on | hold-on | hold-on | hold-on | F | 2/6/2020: supplier to provide plan date 2/11/2020: can not forzen before March. FO mail and impact discussion/FO change to be confirmed by Stone 2/19/2020: FO change to Gu zhongtian 2/24/2020: not impact UE/UI, R&R may change, meeting planned on Thursday 2/28/2020: can not forzen before end of Feb. not impact UE/UI. Start from May. |  |  | CVPP | carrier | bar: Y to Y
174 | Connectivity | IVI | IVI Module Swap 换件 |  | 30% | 70% |  | Baidu |  | x | x |  | 2019-12-30 |  |  |  |  | based on diagnostic spec + mail more spec? |  | N/A | Zhou, Hangxing (X.) <xzhou83@ford.com>/xwang65 | N/A | zhaoweilong <v_zhaoweilong01@baidu.com> | [14 empty] | cancel | [6 empty] | N.A | 1/2/2020: Baidu replan. 1/9/2020: MRD available, need Ford FO check 1/10/2020: MRD update and send out today 1/13/2020: mail to Emma 2/3/2020: FO mailed to Baidu 2/10/2020: replan 2/19/2020: 由于phase4 IVI无sim卡，不存在实名认证的迁移。百度需要关注在给用户更换完IVI之后新件的Provisioning激活和用户账号无感迁移到新件上这两个方面。 |  |  | Basic function | basic | [8 empty] | X | bar: Y to Y; N
175 | Connectivity | CVPP | Home to Car |  | 0% | 100% | No related to IVI | Baidu |  |  | x |  | 2020-02-03 |  |  |  |  | PRD DUEROS_CVPP_IOT(speaker to car)_PRD v1.0 |  | N/A | Lu, Chao (C.) <clu42@ford.com> | N/A | zhaoweilong <v_zhaoweilong01@baidu.com> | [14 empty] | close |  |  | 2020-02-07 | 2020-02-10 | 2020-02-14 | 2020-02-14 | N.A | 2/12/2020: MRD updated, Update on-going. 2/14/2020: plan to sign off; sign off |  |  | CVPP | APP |  | 车家互联 | bar: Y to Y
176 | Connectivity | CVPP | Carrier Feed | Y | 0% |  | 100% | Ford CVPP |  |  | x | [8 empty] | N/A | Wang, Yuran<ywang422@ford.com> | N/A | [15 empty] | N.A |  |  | N.A | N.A | N.A | N.A | N.A | 1/9/2020: open 1/13/2020: no impact for Baidu, Emma check with FO 2/3/2020: aligned - Ford responsible; no MRD needed. No supplier's input needed. |  |  | CVPP | carrier | bar: Y to Y
177 | 电池动力汽车相关/Electric Vehicle | CVPP | Battery SoC | y | 30% | 70% |  | Baidu |  | x | x |  | 2019-12-20 |  |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | N | N | Y | N | N | N | N | N | ED&T | Y |  | delay |  |  | 2019-12-20 | 2020-02-07 | 2020-02-14 |  | B | 12/23/2019: MRD available today 12/24/2019: Delay to today. 12/25/2019: wait Ford FO 12/27/2019: pending by Ford FO - delay to 1/2 1/9/2020: Baidu push FO to check 1/13/2020: Baidu push today 2/6/2020: combine to item 178; pending due to Baidu 2/7/2020: MRD available. Review by Ford FO 2/8/2020: Baidu arrange meeting to review | [5 empty] | xHEV | [6 empty] | X
178 | 电池动力汽车相关/Electric Vehicle | CVPP | Charge Status/Charge Time | Y | 30% | 70% |  | Baidu |  |  | x |  | 2020-01-23 |  |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | N | N | Y | N | N | N | N | N | ED&T | Y |  | delay |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 |  | B | 2/7/2020: review by Ford FO | [5 empty] | xHEV
179 | 电池动力汽车相关/Electric Vehicle | CVPP | Preferred Charge Time | Y | 30% | 70% |  | Baidu |  |  | x |  | 2020-01-23 |  |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | N | N | Y | N | N | N | N | N | ED&T | Y |  | delay |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 |  | B | 2/7/2020: review by Ford FO | [5 empty] | xHEV
180 | 电池动力汽车相关/Electric Vehicle | CVPP | Departure Time | Y | 30% | 70% |  | Baidu |  |  | x |  | 2020-01-23 |  |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | N | N | Y | N | N | N | N | N | License |  | 包含在地图里 | delay |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 |  | B | 2/6/2020: combine to 179 | [5 empty] | xHEV
181 | 电池动力汽车相关/Electric Vehicle | CVPP | Charge Station Finder | Y | 10% | 90% |  | Baidu |  |  | x |  | 2020-01-23 |  |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | embedded in Nav behaviour. | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhanghonghai <zhanghonghai02@baidu.com> | liu yi <Yi.Liu@desay-svautomotive.com> | [13 empty] | delay |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 |  | B | 2/6/2020: combine to 179 | [5 empty] | 地图 | bar: Y to Y
182 | 电池动力汽车相关/Electric Vehicle | CVPP | Trip Planner |  | 10% | 90% |  | Baidu |  |  | x |  | 2020-01-23 |  |  |  |  | PRD EV Trip Planner APIM SPSS v1.0 Mar 15, 2019.pdf |  | embedded in Nav behaviour. | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhanghonghai <zhanghonghai02@baidu.com> | liu yi <Yi.Liu@desay-svautomotive.com> | [13 empty] | open |  |  | 2020-03-01 |  | 2020-03-06 |  | B | 2/6/2020: supplier to provide plan date 2/7/2020: pending due to Ford FO 2/11/2020: Baidu Map can not support Ford's solution. Already escalated. 2/18/2020: Robert follow 2/25/2020: baidu check the changed request | [5 empty] | xHEV | bar: Y to Y
183 | 电池动力汽车相关/Electric Vehicle | CVPP | Cloud Enhanced Distance to Empty |  | 30% | 70% |  | Baidu |  | x | x |  | 2020-01-23 |  |  |  |  | PRD Cloud_Enhanced_DTE_FS_v1.1.pdf |  | N/A | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> | liu yi <Yi.Liu@desay-svautomotive.com> | [13 empty] | delay |  |  | 2020-02-14 | 2020-02-07 | 2020-02-14 |  | B |  |  | x |  |  |  | xHEV | [6 empty] | X | bar: Y to Y
184 | 电池动力汽车相关/Electric Vehicle | CVPP | Smart Charging |  | 30% | 70% |  | Baidu |  | x | x |  | 2020-01-23 |  |  |  |  | Smart Charging PRD_v1.6.pdf |  | P72d_15P_PlugAndCharge_R_v2_00_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> | liu yi <Yi.Liu@desay-svautomotive.com> | [13 empty] | delay |  |  | 2020-02-14 | 2020-02-07 | 2020-02-14 |  | F | 2/24/2020: OTA feature? |  | x |  |  |  | xHEV | [6 empty] | X | bar: Y to Y
185 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Forrest) | frunk/前备箱 |  | 95% | 5% |  | Desay |  | x | x |  | 2019-12-25 |  |  |  |  | Frunk Softswitch Interface Client SPSS v1.1 June 21 2019 | 合并到NO11 | P31b_15P_SYNC4_Controls_R_v4_00_MY21 | chen, Emma<jchen276@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) | [13 empty] | close |  |  | 2019-12-25 | 2020-01-06 | 2020-01-01 | 2020-01-11 | N.A | 12/25/2019: replan 12/27/2019: delay to today 1/6/2020: plan to sign off 1/9/2020: HMI open, desay organize open item list 1/10/2020: plan to sign off 1/11/2020: sign off |  |  |  |  | x | [7 empty] | X | bar: Y to Y
186 | 电池动力汽车相关/Electric Vehicle | CVPP | Rocket setup |  | 30% | 70% |  | Baidu |  | x | x |  | 2020-01-06 |  |  |  |  | Spec draft available Dec. 19th |  | TBD | Gu, Xiaosheng (X.) <xgu14@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | panchengdong <v_panchengdong@baidu.com> | [14 empty] | delay |  |  | 2020-01-10 | 2020-01-10 | 2020-01-17 |  | F | 12/30/2019: requirment updated, baidu check 1/9/2020: draft MRD by Baidu 1/10 1/10/2020: provide draft MRD by 1/13, on-site review on 1/15 2/3/2020: pending by Ford FO 2/6/2020: pending due to Ford FO 2/8/2020: Baidu arrange meeting to review 2/14/2020: requirement clear, open item related to account. plan to sign off 2/27/2020: re-open 2/28/2020: organize open point | [5 empty] | 账号 | [6 empty] | X | bar: Y to Y
187 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Forrest) | Charge Port Light Settings |  | 95% | 5% |  | Desay |  | x | x |  | 2019-12-25 |  |  |  |  | Vehicle Settings APIM SPSS v1.19 Oct 30, 2019 Vehicle Settings APIM Imp Guide v1.19 Oct 30, 2019 Vehicle Settings Logical to Physical CAN signal mapping Oct 30, 2019 | 不需要输出MRD | P31b_15P_SYNC4_Controls_R_v4_00_MY21 | Wang, Fin (X.Y.) (xwang65@ford.com) | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) | [13 empty] | close |  |  | 2019-12-25 | 2020-01-06 | 2020-01-01 | 2020-01-11 | N.A | 12/25/2019: replan 12/27/2019: delay to today 1/6/2020: OIL in GitHub today, Ford FO check 1/10/2020: mail to Ford FO by desay 1/11/2020: sign off | HMI open | [11 empty] | X | bar: Y to Y
188 | VPA | CVPP | Virtual Personal Assistant |  | 0% | 30% | 70% | Baidu/Ford EESE |  |  | x |  | 2020-01-23 |  |  |  |  | PRD VPA PRD - V1.3.2.pdf |  | TBD | Sophia Suo <FSUO@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> | [14 empty] | close |  |  | 2020-02-21 | 2020-03-02 | 2020-02-28 | 2020-03-02 | N.A | 2/6/2020: supplier to provide plan date 2/7/2020: adjust R&R. resource issue to be checked by in-house team. 2/11/2020: phase 3 lead 2/11/2020: Need detail plan info; Phase 3 solution not frozen, phase 4 scope not started. 2/12/2020: changes compared with Phase 3: 语音交互能力方面，会复用百度在Phase4所支持的语音交互功能，相对Phase3会有优化和新增 • 语音开放性需求增加 – 待百度对Phase4的语音接口开放性评估 • HMI设计更新，加入新的形象设计 – 福特自己Inhouse design 2/25/2020: Baidu interfaces C/O from phase3. 3/2/2020: FO sign off |  |  | vehicle related | VPA |  | 语音 | bar: Y to Y
189 | Prognostics | CVPP | Prognostics |  | 60% |  | 40% | Ford CVPP/Desay |  |  | x | [6 empty] | PRD | 合并到NO161 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> | [13 empty] | close |  | 2020-01-14 | 2020-01-14 | 2020-02-28 | 2020-01-21 | 2020-02-28 | N.A | 2/6/2020: supplier to provide plan date 2/8/2020: CVPP lead 2/25/2020: combine to feature 161. |  |  | Basic function | EOL | x | bar: Y to Y
190 | Others | EESE/IVI(Forrest) | English HMI(bezel diagnostic, etc.) |  | 10% | 90% |  | Desay |  |  | x |  | 2020-01-23 | [5 empty] | 合并到NO110 |  | Wang, Fin (X.Y.) <xwang65@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | 参考bezel diagnostic SPEC以及项目的实际需求 | [12 empty] | close |  |  | 2020-02-19 | 2020-02-21 | 2020-02-24 | 2020-02-21 | N.A | 2/6/2020: supplier to provide plan date 2/21/2020: requirement covered in feature 110. |  |  | HMI | HMI | x | bar: Y to Y; N
191 | Basic features | EESE/Wireless | HMI for wireless charging module |  | 10% | 90% |  | Baidu |  |  | x | [7 empty] | 【Phase4】HMI for wireless charging...20.docx |  | Lyu, Qingtao (Q.) <qlyu@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | close |  |  | 2020-02-27 | 2020-02-20 | 2020-02-28 | 2020-02-27 | N.A | 2/20/2020: MRD send to FO 2/27/2020: C/O, sign off |  |  | vehicle related | Wireless charge |  | Launcher | bar: Y to Y; N
192 | Passenger Feature for 27 | HMI | 27" only: Vehicle status showing in the passenger area |  | 40% | 60% |  | Baidu |  |  | x |  | 2020-01-23 | [7 empty] | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | cancel | [7 empty] | 1/9/2020: HMI study, 2020/1/15 2/6/2020: sign off 2/10/2020: requirement found not aligned 2/11/2020: HMI study on-going. 2/18/2020: combine to 161 | bar: Y to Y; N
193 | Connectivity | CVPP | Demo mode for dealers/经销商演示模式 |  | 10% | 90% |  | Baidu |  |  | x | [9 empty] | Wang, Johnny (J.) <jwang308@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | panchengdong <v_panchengdong@baidu.com> | [14 empty] | on-going |  |  | 2020-02-27 | 2020-02-27 | 2020-03-05 |  | F | 2/25/2020: pending feedback from Ford Fo 2/28/2020: solution not ready |  |  | CVPP | APP |  | 账号 | bar: Y to Y
194 | Connectivity | CVPP | Message notification pushing API for Ford backend/福特后台消息推送接口 |  | 10% | 90% |  | Baidu |  |  | x | [7 empty] | 百度消息推送相关接口 V1.1-2020.2.12 |  | Wang, Johnny (J.) <jwang308@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | panchengdong <v_panchengdong@baidu.com> | [14 empty] | close |  |  | 2020-02-14 | 2020-02-14 | 2020-02-21 | 2020-02-14 | B | 2/13/2020: update after discussion 2/14/2020: combine to 148, plan to sign off 2/14/2020: sign off |  |  | CVPP | data |  | 消息推送 | bar: Y to Y
195 | cross carline | HMI | 快速切换最近使用的APP |  | 100% | 0% |  | Desay |  |  | x | [7 empty] | Ford_MRD_27寸大屏SystemUI_20200116final.docx | HMI requirements clarified in email/meetings. | Xiao, Yun (Y.) <yxiao21@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> | [13 empty] | delay |  |  | 2020-02-27 | 2019-12-27 | 2019-12-30 |  | D | combine to item 68 1/10/2020: plan to sign off 1/17/2020: sign off for desay 2/27/2020: reOpen |  |  | HMI | HMI | x | bar: Y to Y; N
196 | cross carline | HMI | Animation Background |  | 10% | 90% |  | Baidu |  |  | x | [7 empty] | 无MRD | N/A | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> | TBD | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | on-going |  |  | 2020-02-27 | 2020-02-26 | 2020-03-05 |  | B | 2/20/2020: Baidu follow actions based on meeting discussion |  |  | HMI | HMI |  | 动效 | bar: Y to Y
197 | cross carline | HMI | Shortcut Keys (program specific) |  | 70% | 30% |  | Desay |  | x | x |  | 2019-12-25 |  |  |  |  | H36p_SYNC4_Parking_Shortcut_Key_RELEASED_v0_06_P702_Post J1_MY21 H36o_SYNC4_Drive_Assist_Shortcut_Key_R_0_04_MY21 H36n_SYNC4_Camera_Shortcut_Key_R_0_02_MY21 | Ford_MRD_Shortcut_Key.docx | A65c_SYNC4_Hard_Switch_Behavior_RELEASED_v1_10_MY21 | Xiao, Yun (Y.) <yxiao21@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> | [13 empty] | close |  |  | 2019-12-25 | 2020-01-13 | 2020-01-01 | 2020-02-28 | D | 12/30/2019: no MRD/replan info 1/6/2020: replan today 1/10/2020: MRD on-going 1/13/2020: MRD to be updated 2/24/2020: meeting planned on this Tuesday |  |  | HMI | HMI | [8 empty] | X | bar: Y to Y; N
198 | cross carline | HMI | Launcher | Y |  |  |  | Baidu | x -partly | x | x | [6 empty] | U554, 725, 702 HMI adaption from Phase 2. | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 | HMI requirements clarified in email/meetings. Status icon shall folow below specs, Header bar HMI requirement _ Ford CHN _ DRAFT HMI Interaction Spec_Header_Bar_20.02.2020 for header bar logic&flow | N.A | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  | C/O 5,6,7 | [12 empty] | close |  |  | 2019-12-23 | 2019-12-24 | 2019-12-31 | 2020-01-19 | N.A | 12/24/2019: MRD available. Need Ford FO check 1/2/2020: list open item and mail for notification. 1/8/2020: plan to sign off 1/19/2020: sign off | 天气数据区域新增点：根据当日天气情况，对应增加显示依据天气情况的人性化温馨提示语，功能研发侧基本能实现，但当前属于福特open项： A、天气数据获取来源，以及温度/天气种类的显示取舍等，需福特内部尽快给于针对phase 4车型予以确认 |  | HMI | HMI | x | Launcher |  | x |  |  |  | X | X | bar: Y to Y
199 | Connectivity | CVPP | 免密支付 payment without enterring password | Y |  |  |  | Baidu |  |  | x | [7 empty] | 【phase4】MRD_免密支付_福特/林肯_V1.0_2019_12_23 |  | Lu, Chao (C.) <clu42@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | panchengdong <v_panchengdong@baidu.com> | [14 empty] | close |  |  | 2020-02-07 | 2020-02-10 | 2020-02-14 | 2020-02-19 | B |  |  |  | CVPP | APP |  | 支付 | bar: Y to Y
200 | Connectivity | CVPP | 违章查询 Query traffic violations | Y |  |  |  | Baidu |  |  | x | [7 empty] | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Lu, Chao (C.) <clu42@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> | [14 empty] | close |  |  | 2020-02-04 | 2020-02-04 | 2020-02-11 | 2020-02-06 | N.A | 2/6/2020: sign off |  |  | CVPP | APP |  | 语义垂类 | bar: Y to Y
201 | Connectivity | CVPP | 鲜花预订 flowers ordering | Y |  |  |  | Baidu |  |  | x | [7 empty] | 【福特Phase4】MRD_外卖_福特车型_V1.0_20191219 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | shantong <v_shantong@baidu.com> | [14 empty] | close |  |  | 2020-02-04 | 2020-02-04 | 2020-02-11 | 2020-02-06 | N.A | 2/6/2020: sign off, C/O from phase 3 |  |  | CVPP | APP |  | 语义垂类 | bar: Y to Y
202 | Connectivity | CVPP | 机票查询 airplain tickets query | Y |  |  |  | Baidu |  |  | x | [7 empty] | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Wang, Jingjing (J.) <jwang354@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> | [14 empty] | close |  |  | N.A | N.A | 2019-11-20 | 2019-12-02 | N.A | 1/2/2020: combine to feature 90; 高频语音垂类 + 简单HMI入口。 |  |  | CVPP | APP |  | 语义垂类 | bar: Y to Y
203 | Connectivity | CVPP | 火车票查询 train ticket query | Y |  |  |  | Baidu |  |  | x | [7 empty] | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Wang, Jingjing (J.) <jwang354@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> | [14 empty] | close |  |  | N.A | N.A | 2019-11-20 | 2019-12-02 | N.A | 1/2/2020: combine to feature 90; 高频语音垂类 + 简单HMI入口。 |  |  | CVPP | APP |  | 语义垂类 | bar: Y to Y
204 | Connectivity | CVPP | 关于（声明）desclaimer [including, account and login in] [ 215 included: desclaimer setting] | Y |  |  |  | Baidu |  |  | x | [8 empty] | N/A | Chen, Emma | Zou, Yujuan (Y.) <yzou32@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | close |  |  | 2020-02-25 | 2020-02-26 | 2020-02-28 | 2020-02-28 | N.A | 12/30/2019: replan 1/8/2020: Emma check with CVPP 1/9/2020: contact HMI 2/3/2020: open again 2/6/2020: pending due to FO not clear 2/11/2020: list all the functions which need IVI to provide desclaimer info within this week. 2/24/2020: arrange meeting on Thursday 3/3/2020: 已确定功能上目前维持内容不变，等内容最后冻结后一次更新；基于目前U554MCA项目的开发计划，最终版本计划2021/1 之前提供内容 |  |  | CVPP | account |  | 免责声明 | bar: Y to Y
205 | cross carline | HMI | Calm Screen | Y |  |  |  | Baidu |  | x | [7 empty] | Lisa working | 【ID205】【phase 4 福特CD542&U625ICA横屏】calm screen MRD v1.4-20200107；【ID205】【phase 4 福特CX727竖屏】calm screen MRD v1.3-20200102；【ID205】【phase 4 福特U725&P702横屏】calm screen MRD v1.3-20200102；【ID205】【phase 4 林肯U554横屏】calm screen MRD v1.3-20200102 | HMI requirements clarified in email/meetings. | N.A | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-19 | N.A | 12/24/2019: wait for Ford FO mail confirm 12/30/2019: check on-going 1/8/2020: plan to sign off 1/19/2020: sign off |  |  | HMI | HMI | x | Launcher | [6 empty] | X | bar: Y to Y
206 | cross carline | HMI | Display off | Y |  |  |  | Baidu |  | x | [7 empty] | lisa checking | 【ID206】【Phase2 林肯(U554)】DisplayOff需求文档MRD_2020_01_02；【ID206】【Phase4 福特（CD542&U625ICA）（高配）】DisplayOff需求文档MRD_2020_01_06；【ID206】【Phase4 福特（CD542&U625ICA）低配】DisplayOff需求文档MRD_2020_01_02；【ID206】【Phase4 福特（CX727）】DisplayOff需求文档MRD_2020_01_02；【ID206】【Phase4 福特（U725&P702）】DisplayOff需求文档MRD_2020_01_02 | HMI requirements clarified in email/meetings. | N.A | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-19 | N.A | 12/24/2019: wait for Ford FO mail confirm 12/30/2019: check on-going 1/13/2020: plan to sign off 1/19/2020: sign off |  |  | HMI | HMI | x | Launcher | bar: Y to Y
207 | Connectivity | CVPP | 在线商城 online mall | Y |  | 20% | 80% | Ford CVPP/Baidu |  |  | x | [7 empty] | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | close |  |  | 2020-02-17 | 2020-02-17 | 2020-02-19 | 2020-02-19 | N.A | 12/24/2019: combine to item 198 1/2/2020: same with ford finance? 1/9/2020: not same. FO not clear 1/13/2020: Baidu check 1/19/2020: sign off 2/6/2020: reopen - pending by CVPP plan 2/11/2020: planned to be clarified within this week. 2/17/2020: Baidu scope clear. The content of this feature will be prepared by Ford | in-house team develop? |  | CVPP | APP |  | 第三方集成应用 | bar: Y to Y
208 | Connectivity | CVPP | Tik tok 抖音 | Y |  |  |  | Baidu |  | x | [7 empty] | DUEROS_CVPP_抖音_v1.3_20191203 | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 | N/A | Shi, Stella (J.) <jshi32@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | [14 empty] | close |  |  | 2019-12-23 | 2019-12-24 | 2019-12-30 | 2020-01-19 | N.A | 12/24/2019: combine to item 198 12/30/2019: check on-going 1/2/2020: archive file and send mail 1/19/2020: sign off |  |  | CVPP | APP |  | 第三方应用集成 | [6 empty] | X | bar: Y to Y
209 | Basic features | IVI | In-vehicle notification - a pop up notice when ignition to notify customer about data sharing policy - duplicate with 165 | Y |  |  |  | Baidu |  | x | [11 empty] | N/A | jiangting <v_jiangting@baidu.com> | [14 empty] | cancel | [20 empty] | X | bar: Y to Y
210 | Connectivity | CVPP | Carrier Backend Development 运营商后台开发 | Y |  |  |  | Baidu | [13 empty] | N/A | zhaoweilong <v_zhaoweilong01@baidu.com> | [14 empty] | cancel | bar: Y to Y
211 | Basic features | CVPP | Carrier API integration with Baidu 与百度的接口集成- Carrier Backend Development 运营商后台开发 | Y |  |  | 100% | Ford CVPP |  | x | [7 empty] | CVPP check whether needed |  |  | Wang, Yuran<ywang422@ford.com> | N/A | huangqiuyue <huangqiuyue@baidu.com> | [14 empty] | N.A |  |  | N.A | N.A | N.A | N.A | N.A | 12/24/2019: send mail to supplier for the impact 12/25/2019: need impact analysis report from Baidu 12/27/2019: Baidu check 12/30/2019: 百度需要1/15号之前定点并确认需求，安排会议讨论 1/9/2020: Baidu send mail to Emma. 1/10/2020: Baidu mail back to Emma 1/13/2020: feedback from Baidu 2/3/2020: MRD available, pending by Ford FO's reveiw 2/6/2020: Ford FO在Phase 4只保留流量预警推送和收到推送后的跳转功能，目前的流量查询和订购由嵌入车机的运营商H5完成，因为从双卡回归到单卡，所以SIM卡换件也不需要百度完成。最终的需求文档，还是得等运营商定点后才能给出。 |  |  | CVPP | carrier | [8 empty] | X | bar: Y to Y
212 | Basic features | CVPP | Carrier API integration with FORD 与福特的接口集成 -> VIN Trim Data | Y |  | 60% | 40% | Ford CVPP/Baidu |  | x | [7 empty] | CVPP check whether needed |  |  | Wang, Yuran<ywang422@ford.com> | N/A | zhaoweilong <v_zhaoweilong01@baidu.com> | [14 empty] | cancel | [7 empty] | 2/7/2020: Baidu need to provide corresponding request to Ford FO 3/6/2020： no trim data needed |  |  | CVPP | APP | [8 empty] | X | bar: Y to Y
213 | Basic features | IVI | Speed compensated volume 根据车速调整音量 | Y |  |  |  | Desay |  | x | [7 empty] | Audio Settings APIM SPSS v1.4 Nov 6, 2019 Audio Settings APIM Imp Guide v1.4 Nov 6, 2019 | [19 empty] | cancel |  |  |  |  | 1900-01-06 | [15 empty] | X | bar: Y to Y
214 | Vehicle Features/Interfaces | DAT | Rear Camera on demand | Y | 90% | 10% |  | Desay |  | x | [7 empty] | Rear Camera On Demand APIM SPSS v1.1 June 21, 2019 Rear Camera On Demand APIM Imp Guide v1.1 June 21, 2019 | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36k_SYNC4_Camera_Systems_R_v0_20_MY21 | Wang, Tom (X.) <xwang190@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-23 | 2019-12-30 | 2020-01-19 | N.A | 12/30/2019: mail discussion available, while no arhived Open item list. 1/6/2020: Desay mail to FO 1/10/2020: on-stie review 1/13/2020: plan to sign off, open item - HMI involve 1/19/2020: sign off | HMI open |  | Driver assist | Driver assist HMI | [8 empty] | X
215 | Basic features | IVI | desclaimer settings | Y |  |  |  | Desay |  | x | [7 empty] | input from HMI; to be confirmed by HMI |  |  |  | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Pan Juan（Juan.Pan@desay-svautomotive.com） | [13 empty] | cancel | [6 empty] | N.A | Emma mail Julee - done /wainting feedback from Julee 1/2/2020: feedback confirmed with HMI, FIP updated. 1/6/2020: Desay contact FO and replan 1/13/2020: replan 2/6/2020: FO not clear; combine to 204 |  |  | basic function | basic | [8 empty] | X | bar: Y to Y
216 | Basic features | EESE/IVI(Forrest) | EQ tool | Y |  |  |  | Desay |  |  | x | [9 empty] | N.A | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Zhang Li (Li.Zhang3@desay-svautomotive.com) | [13 empty] | N.A |  |  | N.A | N.A | N.A | N.A | D | 2/6/2020: supplier to provide plan date 2/11/2020: Tool, no MRD |  |  | Chime management | Chime management | bar: Y to Y
217 | Basic features | EESE/IVI(Roger) | Rear Audio Controls | Y | 90% | 10% |  | Desay |  | x | [7 empty] | Rear Audio Control APIM SPSS v1.4 Jul 1, 2017 Rear Audio Control APIM Imp Guide v1.4 Jul 1, 2017 | 不需要输出MRD |  | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com | Hu, Pin (P.) <phu13@ford.com> |  | Yu Hualin（Hualin.Yu@desay-svautomotive.com） | [13 empty] | close |  |  | 2019-12-27 | 2019-12-27 | 2020-01-03 | 2020-01-14 | N.A | 12/24/2019: desay check and feedback today. 12/25/2019: send OIL to Ford FO 1/6/2020: plan to sign off 1/13/2020: ma mei mail to sign off 1/14/2020: sign off |  |  | Chime management | Chime management | [8 empty] | X | bar: Y to Y
218 | 电池动力汽车相关/Electric Vehicle | CVPP | Charge Conflict Notification Popups | Y |  |  |  | Baidu |  |  | x | [9 empty] | Yang, Yu (Y.) <yyang158@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | zhaoweilong <v_zhaoweilong01@baidu.com> | [14 empty] | on-going |  |  | 2020-02-14 | 2020-02-25 | 2020-02-28 |  | B | 2/6/2020: supplier to provide plan date 2/18/2020: C/O feature, plan to transfer to Baidu 2/19/2020: R&R clear | bar: Y to Y
219 | Features of IVI or Connect | EESE/IVI(Forrest) | IVI interface via press physical switch 实体键IVI交互 | Y |  |  |  | Desay |  | x | [9 empty] | A65c_SYNC4_Hard_Switch_Behavior_RELEASED_v1_10_MY21 | Chen, Emma<jchen276@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [13 empty] | delay |  |  | 2019-12-26 |  | 2020-01-02 |  | D | 12/30/2019: no MRD/replan info 1/6/2020: replan today 1/10/2020: MRD on-going 1/13/2020: Desay push FO 2/24/2020: meeting planned on this Tuesday |  |  | Basic function | basic | x | [7 empty] | X | bar: Y to Y
220 | Features of IVI or Connect | CVPP | Baidu数据平台 |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-01-17 |  |  |  |  | PRD DUEROS_CVPP_Ford and Baidu Accoun_Phase 2_PRD_v1.4.pdf | 无MRD | N/A | Fan, Henry (H.) <hfan11@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | zhanglihong <v_zhanglihong02@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2020-01-03 | 2020-01-03 | 2020-01-10 | 2020-02-14 | B | 12/24/2019: Baidu check 百度提供方案？ 12/25/2019: discussion today, info tomorrow 12/27/2019: Baidu feedback before 31th 1/2/2020: MRD replan to 1/3 1/9/2020: need Ford FO check 1/10/2020: push FO check 1/13/2020: on-site review this Wednesday 2/4/2020: follow up meeting 2/14/2020: sign off; |  |  | CVPP | data |  | 数据埋点 | [6 empty] | X
221 | Features of IVI or Connect | CVPP | 个人中心 |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-01-17 |  |  |  |  | PRD DUEROS_CVPP_Ford and Baidu Accoun_Phase 2_PRD_v1.4.pdf |  | N/A | Wang, Johnny (J.) <jwang308@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | panchengdong <v_panchengdong@baidu.com> |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2020-01-10 | 2020-01-10 | 2020-01-17 | 2020-02-19 | B | 12/24/2019: Ford requirement combine to item 101 12/30/2019: replan to 2020/1/10 1/10/2020: proposal before 1/13, on-site review 1/15 2/3/2020: updated MRD available, pending by Ford FO's review comments 2/4/2020: follow up meeting 2/6/2020: pending due to Ford FO 2/14/2020: plan to sign off |  |  | CVPP | account |  | 账号 | [6 empty] | X
222 | 电池动力汽车相关/Electric Vehicle | CVPP | EV Carryover features |  | 30% | 70% |  | Baidu |  | x | x | [9 empty] | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> | [13 empty] | cancel | [6 empty] | F | 1/10/2020: Luo Minghao check on-going |  | x | [10 empty] | X
223 | 电池动力汽车相关/Electric Vehicle | CVPP | EV Plug and charge |  | 30% | 70% |  | Desay |  | x | x | [7 empty] | 不需要输出MRD（无app开发） | P72d_15P_PlugAndCharge_R_v2_00_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> | [13 empty] | close |  |  | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-03-02 | N.A | 1/10/2020: Luo Minghao check on-going 2/19/2020: 无上层应用。transfer to Desay? 2/27/2020: transfer to Desay, combine to SOA, no MRD needed.3/2/2020: development on-going, tracking separately |  | x | [10 empty] | X | bar: Y to Y
224 | 驾驶辅助/Drive assist | DAT | Auto High beam/glare free high beam | Y | 95% | 5% |  | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Song, Amy (S.) <ssong18@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x | [7 empty] | X
225 | 驾驶辅助/Drive assist | DAT | DAS: driver alert system | Y | 95% | 5% |  | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Song, Amy (S.) <ssong18@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x | [7 empty] | X
226 | 驾驶辅助/Drive assist | DAT | ACC/iACC | Y | 95% | 5% |  | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Cui, Victor (M.) <mcui5@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | ACC only | ACC only | OPT | N | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x | [7 empty] | X
227 | 驾驶辅助/Drive assist | DAT | Speed limiter/intelligent speed limiter | Y | 95% | 5% |  | Desay |  | x | x |  | 2019-12-20 |  |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Cui, Victor (M.) <mcui5@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Liu Xiaogang(Xiaogang.Liu@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x | [7 empty] | X
228 | Vehicle Features/Interfaces | EESE/system(inhouse) | Digital Scent | N | 20% | 0% | 80% | Ford EESE/Desay |  |  | x | [7 empty] | Ford_MRD_Digital_Scent_V1.3_20200228.docx |  | Zhang, Xiaojing (X.) <XZHAN247@ford.com> | TBD |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  |  | N | N | N | N | N | Y | N | Y | ED&T | Y |  | close |  |  | 2020-02-20 | 2020-02-24 | 2020-02-28 | 2020-02-28 | N.A | 1/13/2020: replan today 2/6/2020: supplier to provide plan date 2/8/2020: EESE Inhouse provide plan date 2/24/2020:
229 | Vehicle Features/Interfaces | EESE/HUD | WHUD | N | 30% | 70% |  | Baidu |  |  | x | [9 empty] | Li, Jianxin (J.) <jli294@ford.com> | TBD |  |  |  |  | N | N | N | N | N | N | N | Y | ED&T | Y |  | hold-on |  |  | hold-on | hold-on | hold-on | hold-on | B | 1/10/2020: Luo Minghao check on-going 2/6/2020: supplier to provide plan date
230 | Vehicle Features/Interfaces | EESE/System | Lincoln Embrace [hold on] | N |  |  |  | Desay |  |  | x | [9 empty] | Wu, Bella (Y.) <YWU150@ford.com> | TBD |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  |  | N | N | N | N | N | N | N | Y | ED&T | Y |  | hold-on |  |  | hold-on | hold-on | hold-on | hold-on | F | 1/13/2020: replan today 2/6/2020: supplier to provide plan date 2/14/2020: no SPSS 2/19/2020: hold on till SPSS ready
Formulas:
Planned release date = [Planned Available date]+AR1
Planned release date = [Actual available date]+AR1
Note on AR1: Author: promised to release MRD within 1 week
Note on E2: Author: "Y" 部分沿用Phase1/2/3 设计，只能作为参考，需求以Phase4需求为基准
Note on D3: Author: 包含通信部分，CAN，LIN，Ethernet，及软件架构部分，需要从Vector采购FNOS Autosar的软件基础架构。
Note on N3: Author: 需求，不需要输出MRD
Note on N5: Author: 需求，不需要输出MRD
Note on Q10: Author: studio provide animation as input
Note on D13: Author: Settings In Infotainment CenterStack : v1.17
Note on D18: Author: 通过CAN消息显示车辆OTA信息/Show the OTA status for Vehicle via CAN (FNV2)
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: function distributed in PMT1
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: function distributed in PMT1
Note on AJ27: Author: Only for Software supplier
Note on D31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: VE DAT not related
Note on D32: Author: ADAS MAP /EH; INPUT for iACC
Note on S59: Author: SPSS available, need to upload
Note on D61: Author: HTML5, flexiable HMI engine for different display
Note on D69: Author: 充电电流的显示，谁做HMI谁是lead 11/11: Studio provide animation design
Note on S71: Author: others under checking by Xiaoyun
Note on J80: Author: 不含 双蓝牙
Note on J92: Author: 基本的语音功能
Note on D99: Author: 利用AR导航摄像头拍照和视频，本地功能
Note on D102: Author: IVI: internet gateWay SPSS IVI as client
Note on D115: Author: HMI谁负责谁lead
Note on AM121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: combine to 112
Note on D139: Author: 内置
Note on D140: Author: 驾驶行为检测，从别的模块接受信号（如加速，刹车，等），对驾驶行为打分显示出来
Note on D146: Author: 胎压
Note on D152: Author: 360 camera基础上再增加一些摄像头
Note on D155: Author: 设置项
Note on D156: Author: 软开关
Note on D157: Author: 软开关
Note on D159: Author: 外置功放
Note on D160: Author: 可选驾驶模式
Note on D161: Author: 被盗车辆追踪
Note on D162: Author: setting
Note on D174: Author: 拿到GPS的原始数据做偏移
Note on D187: Author: Soft Key SYNC, Ford Pass
Note on D188: Author: When customers wait for vehicle hand-over, they can do IVI set up on FP in advance. Such as 3rd party ID linkage, wake up words, Pony related
Note on D189: Author: Improvement based on Phase II
Note on D191: Author: 诊断; 远程提醒换机油
Note on D200: Author: mapping to features
Note on D215: Author: duplicate to 157
Note on D221: Author: function already covered by the others; just reminder here

## 461 CO Phase1&2&3 feature
序号 ID | 产品功能大类 Product Suite | 客户感知型功能归集 Feature Group | 客户感知型功能单元 Feature | 工程开发用功能单元 Function | 描述 Description | [5 empty] | Lead Team |  |  | Feature Owner | Baidu/Visteon Feature Develop Engineer | Feature DV Engineer | Phrase I Ford Feature |  |  |  | Phrase II Ford Feature |  |  |  |  | Phase III Ford Feature |  |  |  | Lincoln Feature(Delete)
[6 empty] | Lineked Feature ID | required in phase 4? Y- Required N - Not required U - Required with update NA - ignore | covered in phase 4 list? | Lead Baidu/Desay | comments |  | Feature code | JIRA ID |  |  |  |  | C519C | D568C | CD391C |  | CX482C | U625C | CD391C | U540 | C/O Phase I/II Feature | CD539ICA | CX483ICA | U611ICA |  | CX483C | U611C | U540C | Comment(Feedback Deadline-10/24)
SYNC+_0001 | IVI System Function | System UI & HMI | 百度相关功能HMI的UX、UI、动效设计及开发 | 包括语音、导航、随心听、个人中心、账号登录、支付、车家互联、安全、个性化车控 |  |  | N | Y | B |  | HMI | HMI_001 | 2 | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0002 | IVI System Function | System UI & HMI | 除百度应用之外的车机功能UX、UI、功效设计及开发 | 收音机、电话、个性化车控、设置、ADAS、消息通知倒车设置等其它未列功能 |  |  | N | Y | B |  | HMI | HMI_002 | 3 | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0003 | IVI System Function | System UI & HMI | 12.8' Portrait Launcher | 12.8' Portrait Launcher -12.8' Portrait Launcher main cards | Weather, Voice command suggestion, Vehicle information | line 209,需加入feature list | Y - FOR ALL DISPLAY | N | B | main card / domain card / persistant bar | HMI | HMI_003 | 4 | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | Y |  |  |  | Y | N | N | N | N | N | N | N | N | N
SYNC+_0004 | IVI System Function | System UI & HMI | 12.8' Portrait Launcher | 12.8' Portrait Launcher -12.8' Portrait Luanch domain cards | High series - Navigation, Online music, etc. Low series - Navigation, Online music, etc. | line 209,需加入feature list | Y - FOR ALL DISPLAY | N | B |  | HMI | HMI_004 | 5 | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | Y |  |  |  | Y | N | N | N | N | N | N | N | N | N
SYNC+_0005 | IVI System Function | System UI & HMI | 12.8' Portrait Launcher | 12.8' Portrait Launcher -12.8' Portrait Luanch persisten bar | High series - Vehicle control, temperature adjuster, climate status display, 360 camera Low series - Vehicle control, temperature adjuster, climate status display, More Apps | line 209,需加入feature list | Y - FOR ALL DISPLAY | N | B |  | HMI | HMI_005 | 6 | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | Y |  |  |  | Y | N | N | N | N | N | N | N | N | N
SYNC+_0006 | IVI System Function | System UI & HMI | 12.3' Landscape Launcher | 12.3' Landscape Launcher main cards |  |  | N | N | B |  | HMI | HMI_006 | 7 | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  |  | N | N | N | N | N
SYNC+_0007 | IVI System Function | System UI & HMI | 12.3' Landscape Launcher | 12.3' Landscape Luanch domain cards |  |  | N | N | B |  | HMI | HMI_007 | 8 | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  |  | N | N | N | N | N
SYNC+_0008 | IVI System Function | System UI & HMI | 12.3' Landscape Launcher | 12.3' Landscape Luanch persisten bar |  |  | N | N | B |  | HMI | HMI_008 | 9 | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  |  | N | N | N | N | N
SYNC+_0009 | IVI System Function | System UI & HMI | 12.8' Landscape Launcher | Lincoln - 12.8' Landscape Launcher main cards |  |  | N | N | B |  | HMI | HMI_011 |  | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | N |  |  |  | Y | Y | Y | Y | Y | Y | N | Y | Y | Y
SYNC+_0010 | IVI System Function | System UI & HMI | 12.8' Landscape Launcher | Lincoln - 12.8' Landscape Luanch domain cards |  |  | N | N | B |  | HMI | HMI_012 |  | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | N |  |  |  | Y | Y | Y | Y | Y | Y | N | Y | Y | Y
SYNC+_0011 | IVI System Function | System UI & HMI | 12.8' Landscape Launcher | Lincoln - 12.8' Landscape Luanch persisten bar |  |  | N | N | B |  | HMI | HMI_013 |  | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | N |  |  |  | Y | Y | Y | Y | Y | Y | N | Y | Y | Y
SYNC+_0012 | IVI System Function | System UI & HMI | UI&UE设计规范 | UI&UE设计规范 |  |  | U | N | B |  | HMI | HMI_009 |  | Xiao, Yun (Y.) | 高建潮 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0013 | IVI System Function | System UI & HMI | Lincoln主页及开机/关机动画的设计及开发 Customized welcome prompt/animation | Lincoln主页及开机/关机动画的设计及开发 Customized welcome prompt/animation |  | Desay | U | Y | D |  | HMI | HMI_014 |  | Xiao, Yun (Y.) | 李大青 | Xiao, Yun (Y.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0014 | IVI System Function | System UI & HMI | Ford主页及开机/关机动画的设计及开发 Customized welcome prompt/animation | Ford主页及开机/关机动画的设计及开发 Customized welcome prompt/animation |  | Desay | U | Y | D |  | HMI | HMI_010 | 200 | Xiao, Yun (Y.) | 李大青 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | N
SYNC+_0015 | IVI System Function | System UI & HMI | Multi-Theme | Multi-Theme |  | feature id 71 | U | N | B |  | HMI | HMI_011 | 343 | Xiao, Yun (Y.) | 李大青 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y-C/O 482 | Y | Y | Y
SYNC+_0016 | Voice Recognition | Voice Recognition Service | 三种交互式语言3+ TTS 四种TTS播报语音 | 台湾女声（金莎语音）、情感女声、标准女声 Voice options 标准男声 |  |  | U | I | B |  | IVI | BVR_001 | 10 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0017 | Voice Recognition | Voice Recognition Service | 打断式交互barge-in | 打断式交互barge-in |  |  | U | I | B |  | IVI | BVR_002 | 11 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0018 | Voice Recognition | Voice Recognition Service | 所见即可说 All the soft bottons in touch screen support voice command, inlucding selecting listed options | 所见即可说 All the soft bottons in touch screen support voice command, inlucding selecting listed options |  |  | U | I | B |  | IVI | BVR_003 | 12 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0019 | Voice Recognition | Voice Recognition Service | 定向拾音（主驾增强）Oriented Voice recognition (Driver orientation enhancement) | 定向拾音（主驾增强）Oriented Voice recognition (Driver orientation enhancement) |  |  | U | I | B |  | IVI | BVR_004 | 13 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0020 | Voice Recognition | Voice Recognition Service | 离线指令500+ Offline comands | Roger: 需要Baidu PM列出当前的500+离线指令集， 需要让Ford VR 去review |  |  | U | I | B |  | IVI | BVR_005 | 14 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0021 | Voice Recognition | Voice Control - Wake up Words | 核心功能场景化免唤醒命令 Wake-up command is not mandatory to activate for key functions | 核心功能场景化免唤醒命令 Wake-up command is not mandatory to activate for key functions need to review all wake-up free commands |  |  | U | I | B |  | IVI | BVR_006 | 15 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0022 | Voice Recognition | Voice Control - Wake up Words | 福特的语音唤醒词“你好，福特” Ford wake-up commands | 福特的语音唤醒词“你好，福特” Ford wake-up commands | 该唤醒词“你好，福特”应该IVI里唯一有效的唤醒词。Contain one-shot feature |  | U | I | B |  | IVI | BVR_007 | 16 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | N | N | N
SYNC+_0023 | Voice Recognition | Voice Control - Wake up Words | 林肯的语音唤醒词“你好，林肯” Lincoln wake-up commands | Lincoln语音唤醒词“你好，林肯” Ford wake-up commands | 该唤醒词“你好，林肯”应该IVI里唯一有效的唤醒词。Contain one-shot feature |  | U | I | B |  | IVI | BVR_008 | 243 | Wang Jingjing | 刘建立 | Wang Jingjing | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0024 | Voice Recognition | Voice Control - Wake up Words | 自定义语音唤醒词 Customized Wake-up keyword | 自定义语音唤醒词 Customized Wake-up keyword |  |  | U | I | B |  | IVI | BVR_009 | 125 | Wang Jingjing | 刘建立 | Wang Jingjing | N |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0025 | Voice Recognition | AI Q&A General Interest Queries | 天气 Weather | 支持国内2560个城市和海外主要城市的6天内天气查询和当日生活指数查询。 Support weather info & related index search of 2560 domestic cities & main oversea cities. |  |  | U | I | B |  | IVI | AVRG_001 | 18 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0026 | Voice Recognition | AI Q&A General Interest Queries | 限行 Traffic control info - License plate restriction | 查询6个主要限行城市（北京、杭州、兰州、成都、天津、武汉）的限行信息。 Support searching 6 main cities which implemented traffic control rules |  |  | U | I | B |  | IVI | AVRG_002 | 19 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0027 | Voice Recognition | AI Q&A General Interest Queries | 人物百科 Celebrity encyclopedia | 支持娱乐明星、体育明星、历史人物等名人的重要信息（身高、体重、家乡、星座）、婚姻状况、亲属（如老婆、老公、女朋友）Support searching celebrity info |  |  | U | I | B |  | IVI | AVRG_003 | 20 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0028 | Voice Recognition | AI Q&A General Interest Queries | 股价 Share price | 支持美股、港股、沪深股市的公司市值股价和大盘指数查询 Support US/HK/Shanghai/Shenzhen share price & stock index searching |  |  | U | I | B |  | IVI | AVRG_004 | 21 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0029 | Voice Recognition | AI Q&A General Interest Queries | 笑话 Jokes | 支持文字笑话的询问与播报 Support reading literal jokes |  |  | U | I | B |  | IVI | AVRG_005 | 22 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0030 | Voice Recognition | AI Q&A General Interest Queries | 世界之最 Most ** of the world | 支持查询世界上之最、中国之最 Support searching the most ** of the world/China |  |  | U | I | B |  | IVI | AVRG_006 | 23 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0031 | Voice Recognition | AI Q&A General Interest Queries | 彩票 Lotery | 支持查询博彩类开奖结果(大乐透、七星彩、体彩、排列五、福彩、双色球）Support searching loteray info |  |  | U | I | B |  | IVI | AVRG_007 | 24 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0032 | Voice Recognition | AI Q&A General Interest Queries | 闲聊 Chat | 自由聊天，每句话都能有回应 Responding to every voice command/message |  |  | U | I | B |  | IVI | AVRG_008 | 25 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0033 | Voice Recognition | AI Q&A General Interest Queries | 诗词 Poem | 支持唐诗宋词的完整篇章或上下句、作者、出处查询。 Support China acient poem searching & related info, i.e. writer |  |  | U | I | B |  | IVI | AVRG_009 | 26 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0034 | Voice Recognition | AI Q&A General Interest Queries | 汇率 Exchange rate | 支持世界主要货币之间的兑换换算。 Support mainstreen currency exchange calculation |  |  | U | I | B |  | IVI | AVRG_010 | 27 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0035 | Voice Recognition | AI Q&A General Interest Queries | 地理 Geography | 支持查询某物的面积、长度、高度、食物的热量 Support searching something's dimension & food calorie |  |  | U | I | B |  | IVI | AVRG_011 | 28 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0036 | Voice Recognition | AI Q&A General Interest Queries | 热映电影 Popular movie | 支持电影实体查找（包括电影名、演员、类型等）Support movie searching |  |  | U | I | B |  | IVI | AVRG_012 | 29 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0037 | Voice Recognition | AI Q&A General Interest Queries | 电视剧基础属性 Episodes | 支持查询电视剧的播出时间、电影的上映时间 Episodes'airtime |  |  | U | I | B |  | IVI | AVRG_013 | 30 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0038 | Voice Recognition | AI Q&A General Interest Queries | 日历 Calendar | 支持查询节假日、节气时间 Support searching holiday date & China traditional solarterm dates |  |  | U | I | B |  | IVI | AVRG_014 | 31 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0039 | Voice Recognition | AI Q&A General Interest Queries | 电影票/外卖 movie ticket/take away | 支持购买电影票/外卖 support paying moive ticket |  |  | U | I | B |  | IVI | Wang Jingjing |  | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y
SYNC+_0040 | Voice Recognition | AI Q&A General Interest Queries | 火车票 train | 支持查询火车票 support train ticket searching |  |  | U | I | B |  | IVI | Wang Jingjing |  | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y
SYNC+_0041 | Voice Recognition | AI Q&A General Interest Queries | 机票/航班信息 air ticket/flight info | 支持查询机票/航班信息 support air ticket/flight info searching |  |  | U | I | B |  | IVI | Wang Jingjing |  | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y
SYNC+_0042 | Voice Recognition | Voice Control - Navigation | 语音发起导航 Activate NAV with Voice command | 搜索去某地地的导航路线 Search routes |  |  | U | I | B |  | IVI | AVRNAV_001 | 32 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0043 | Voice Recognition | Voice Control - Navigation | 语音发起导航 Activate NAV with Voice command | 选择PO（第X条路线）Slect a route option |  |  | U | I | B |  | IVI | AVRNAV_002 | 32 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0044 | Voice Recognition | Voice Control - Navigation | 语音发起导航 Activate NAV with Voice command | 路线规划成功语音输入“开始导航” Voice command to kick-off navigation after route is planned |  |  | U | I | B |  | IVI | AVRNAV_003 | 32 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0045 | Voice Recognition | Voice Control - Navigation | 语音发起取消导航 Activate NAV with Voice command | 路线规划成功时语音输入“取消” Voice command to cancel navigation after route is planned |  |  | U | I | B |  | IVI | AVRNAV_004 | 32 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0046 | Voice Recognition | Voice Control - Navigation | 语音结束导航 End/Cancel navigation with voice command-结束导航 End navigation | 结束导航 End navigation |  |  | U | I | B |  | IVI | AVRNAV_005 | 33 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0047 | Voice Recognition | Voice Control - Navigation | 语音打开导航APP Entry Navigation APP with voice command | 开始导航 Start navigation |  |  | U | I | B |  | IVI | AVRNAV_006 | 34 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0048 | Voice Recognition | Voice Control - Navigation | 语音打开导航APP Entry Navigation APP with voice command | 退出导航 Exit navigation |  |  | U | I | B |  | IVI | AVRNAV_007 | 34 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0049 | Voice Recognition | Voice Control - Navigation | 语音更改昼夜模式 Switch day/night mode with voice command | 白天模式/日间模式 day mode |  |  | U | I | B |  | IVI | AVRNAV_008 | 35 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0050 | Voice Recognition | Voice Control - Navigation | 语音更改昼夜模式 Switch day/night mode with voice command | 黑夜模式/夜间模式 night mode |  |  | U | I | B |  | IVI | AVRNAV_009 | 35 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0051 | Voice Recognition | Voice Control - Navigation | 语音控制地图缩放 Zoom in/out with voice command | 放大地图/地图放大 Zoom in |  |  | U | I | B |  | IVI | AVRNAV_010 | 36 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0052 | Voice Recognition | Voice Control - Navigation | 语音控制地图缩放 Zoom in/out with voice command | 缩小地图/地图缩小 Zoom out |  |  | U | I | B |  | IVI | AVRNAV_011 | 36 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0053 | Voice Recognition | Voice Control - Navigation | 语音控制导航模式切换 Navigation mode switch with voice command-查看全程/全览 Check route status overview | 查看全程/全览 Check route status overview |  |  | U | I | B |  | IVI | AVRNAV_012 | 37 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0054 | Voice Recognition | Voice Control - Navigation | 语音控制导航模式切换 Navigation mode switch with voice command-继续导航 Continue navigation | 继续导航 Continue navigation |  |  | U | I | B |  | IVI | AVRNAV_013 | 37 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0055 | Voice Recognition | Voice Control - Navigation | 语音控制地图模式切换 Map mode switch with voice command-正北模式/正北朝上 North mode/ Nav pointer oriented to north | 正北模式/正北朝上 North mode/ Nav pointer oriented to north |  |  | U | I | B |  | IVI | AVRNAV_014 | 38 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0056 | Voice Recognition | Voice Control - Navigation | 语音控制地图模式切换 Map mode switch with voice command-跟随模式/车头朝上 Follow mode/Nav pointer oriented as Vhicle orientation | 跟随模式/车头朝上 Follow mode/Nav pointer oriented as Vhicle orientation |  |  | U | I | B |  | IVI | AVRNAV_015 | 38 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0057 | Voice Recognition | Voice Control - Navigation | 路况查询 traffic query | 实时路况查询 real-time traffic query |  |  | U | I | B |  | IVI |  |  | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y
SYNC+_0058 | Voice Recognition | Voice Control - Navigation | 位置查询 location query | 实时位置查询 real-time location query |  |  | U | I | B |  | IVI |  |  | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y
SYNC+_0059 | Voice Recognition | Voice Control - Navigation | 路况打开/关闭 open/close road condition | 路况打开/关闭 open/close road condition |  |  | U | I | B |  | IVI |  |  | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y
SYNC+_0060 | Voice Recognition | Voice Control - Navigation | 添加途径点 add pass-by | 添加途径点 add pass-by |  |  | U | I | B |  | IVI |  |  | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y
SYNC+_0061 | Voice Recognition | Voice Control - Navigation | 声控电子狗 Radar detector with voice recognition function-打开电子狗/进入巡航模式 Turn on radar dector | 打开电子狗/进入巡航模式 Turn on radar dector |  |  | U | I | B |  | IVI | AVRNAV_016 | 39 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0062 | Voice Recognition | Voice Control - Navigation | 声控电子狗 Radar detector with voice recognition function-关闭电子狗/退出巡航模式 Turn off radar dector | 关闭电子狗/退出巡航模式 Turn off radar dector |  |  | U | I | B |  | IVI | AVRNAV_017 | 39 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0063 | Voice Recognition | Voice Control - Navigation | 路径规划策略调整 route planning streategy-推荐路线 Recommended route | 推荐路线 Recommended route |  |  | U | I | B |  | IVI | AVRNAV_018 | 40 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0064 | Voice Recognition | Voice Control - Navigation | 路径规划策略调整 route planning streategy-时间优先 time prioritize | 时间优先 time prioritize |  |  | U | I | B |  | IVI |  |  | Wang Jingjing | 刘建立 | Wang Jingjing | Y | Y |  |  | Y |  |  |  |  | Y | Y | Y | Y
SYNC+_0065 | Voice Recognition | Voice Control - Navigation | 路径规划策略调整 route planning streategy-高速优先 High-way prioritize | 高速优先 High-way prioritize |  |  | U | I | B |  | IVI | AVRNAV_019 | 40 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0066 | Voice Recognition | Voice Control - Navigation | 路径规划策略调整 route planning streategy-不走高速 No highway | 不走高速 No highway |  |  | U | I | B |  | IVI | AVRNAV_020 | 40 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0067 | Voice Recognition | Voice Control - Navigation | 路径规划策略调整 route planning streategy-少收费 Less charging | 少收费 Less charging |  |  | U | I | B |  | IVI | AVRNAV_021 | 40 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0068 | Voice Recognition | Voice Control - Navigation | 路径规划策略调整 route planning streategy-躲避拥堵 Avoid traffic jam roads/streets | 躲避拥堵 Avoid traffic jam roads/streets |  |  | U | I | B |  | IVI | AVRNAV_022 | 40 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0069 | Voice Recognition | Voice Control - Multimedia | 音乐 Music | 语音泛需求搜索（打开音乐、播放歌曲）fuzzy search |  |  | U | I | B |  | IVI | AVRNE_001 | 41 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0070 | Voice Recognition | Voice Control - Multimedia | 音乐 Music | 分类需求搜索(支持歌名、类别、歌手等搜索）category search |  |  | U | I | B |  | IVI | AVRNE_002 | 41 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0071 | Voice Recognition | Voice Control - Multimedia | 有声 Audio book | 语音泛需求搜索（打开有声、随便听点节目）fuzzy search |  |  | U | I | B |  | IVI | AVRNE_003 | 42 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0072 | Voice Recognition | Voice Control - Multimedia | 有声 Audio book | 分类需求搜索（支持主播、分类、专辑名等搜索）category search |  |  | U | I | B |  | IVI | AVRNE_004 | 42 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0073 | Voice Recognition | Voice Control - Multimedia | 新闻 News | 分类泛需求搜索及区域需求搜索 fuzzy search & region search |  |  | U | I | B |  | IVI | AVRNE_005 | 43 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0074 | Voice Recognition | Voice Control - Multimedia | 语音控制曲目 Voice command to control music player | 语音控制播放模式（顺序播放、单曲循环、随机播放）play mode switch with voice command |  |  | U | I | B |  | IVI | AVRNE_006 | 44 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0075 | Voice Recognition | Voice Control - Multimedia | 语音控制曲目 Voice command to control music player | 语音调整音量大小（调大音量、调小音量）Volume adjusting with voice recognition |  |  | U | I | B |  | IVI | AVRNE_007 | 44 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0076 | Voice Recognition | Voice Control - Multimedia | 我喜欢这个 like this | 标记某个喜欢内容（我喜欢听这个、点赞这个、收藏这个）Mark the favirote item |  |  | U | I | B |  | IVI | AVRNE_008 | 45 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0077 | Voice Recognition | Voice Control - Multimedia | 我不喜欢这个 dis- like | 取消之前收藏或标记为喜欢的内容内容 Mark the dislike item |  |  | U | I | B |  | IVI | AVRNE_009 | 46 | Wang Jingjing | 刘建立 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0078 | Voice Recognition | Control Vehicle - A/V | 风量控制 Air volume | 出风等级控制 Air volume-增加风量 |  |  | U | I | B |  | IVI | AVRVC_001 | 47 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0079 | Voice Recognition | Control Vehicle - A/V | 风量控制 Air volume | 出风等级控制 Air volume-风量大一点 |  |  | U | I | B |  | IVI | AVRVC_002 | 47 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0080 | Voice Recognition | Control Vehicle - A/V | 风量控制 Air volume | 出风等级控制 Air volume-减少风量 |  |  | U | I | B |  | IVI | AVRVC_003 | 47 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0081 | Voice Recognition | Control Vehicle - A/V | 风量控制 Air volume | 出风等级控制 Air volume-风量小一点 |  |  | U | I | B |  | IVI | AVRVC_004 | 47 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0082 | Voice Recognition | Control Vehicle - A/V | 风量控制 Air volume | 出风等级控制 Air volume-风量正常 |  |  | U | I | B |  | IVI | AVRVC_005 | 47 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0083 | Voice Recognition | Control Vehicle - A/V | 风量控制 Air volume | 出风等级控制 Air volume-调整风量到xx档 |  |  | U | I | B |  | IVI | AVRVC_006 | 47 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0084 | Voice Recognition | Control Vehicle - Climate | 风向系统控制 Direction control | 空气系统控制 Climate system control-调整出风方向/下一个出风方向 Air flow direction |  |  | U | I | B |  | IVI | AVRVC_007 | 48 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0085 | Voice Recognition | Control Vehicle - Climate | 风向系统控制 Direction control | 空气系统控制 Climate system control-打开/关闭自动除霜系统 defrost |  |  | U | I | B |  | IVI | AVRVC_008 | 48 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0086 | Voice Recognition | Control Vehicle - Climate | 风向系统控制 Direction control | 空气系统控制 Climate system control-打开/关闭内循环 recirc |  |  | U | I | B |  | IVI | AVRVC_009 | 48 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0087 | Voice Recognition | Control Vehicle - Climate | 风向系统控制 Direction control | 空气系统控制 Climate system control-打开/关闭空气清新系统 fresh air |  |  | U | I | B |  | IVI | AVRVC_010 | 48 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0088 | Voice Recognition | Control Vehicle - Climate | 风向系统控制 Direction control | 空气系统控制 Climate system control-打开/关闭后挡风除霜 rear deforst |  |  | U | I | B |  | IVI | AVRVC_011 | 48 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0089 | Voice Recognition | Control Vehicle - Climate | 风向系统控制 Direction control | 空气系统控制 Climate system control-打开/关闭自动模式 Auto mode |  |  | U | I | B |  | IVI | AVRVC_012 | 48 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0090 | Voice Recognition | Control Vehicle - A/C | 空调控制 AC control | 空调控制 AC control-打开/关闭空调 AC on/off |  |  | U | I | B |  | IVI | AVRVC_013 | 49 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0091 | Voice Recognition | Control Vehicle - A/C | 空调温度控制 AC control | 空调控制 AC control-设置空调温度到xx度 Temp setting |  |  | U | I | B |  | IVI | AVRVC_014 | 49 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0092 | Voice Recognition | Control Vehicle - A/C | 空调温度控制 AC control | 空调控制 AC control-提高温度 Temp up |  |  | U | I | B |  | IVI | AVRVC_015 | 49 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0093 | Voice Recognition | Control Vehicle - A/C | 空调温度控制 AC control | 空调控制 AC control-降低温度 Temp down |  |  | U | I | B |  | IVI | AVRVC_016 | 49 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0094 | Voice Recognition | Control Vehicle - A/C | 空调温度控制 AC control | 空调控制 AC control-温度最低/最低温度 LO |  |  | U | I | B |  | IVI | AVRVC_017 | 49 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0095 | Voice Recognition | Control Vehicle - A/C | 空调温度控制 AC control | 空调控制 AC control-温度最高/最高温度 HI |  |  | U | I | B |  | IVI | AVRVC_018 | 49 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0096 | Voice Recognition | Control Vehicle - Roof | 天窗控制 Roof window control | 天窗控制 Roof window control |  |  | U | I | B |  | IVI | AVRVC_023 |  |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0097 | Voice Recognition | Control Vehicle - Curtain | 遮阳帘 | 遮阳帘 |  |  | U | I | B |  | IVI | AVRVC_024 |  |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0098 | Voice Recognition | Control Vehicle - Windows | 车窗 | 车窗 |  |  | U | I | B |  | IVI | AVRVC_025 |  |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0099 | Voice Recognition | Control Vehicle - Seat | 车座控制 Seat control-打开/关闭座位加热/通风 seat heating/Cooling on/off | 车座控制 Seat control-打开/关闭座位加热/通风 seat heating/Cooling on/off |  |  | U | I | B |  | IVI | AVRVC_019 | 50 | Wang Jingjing | 陈冰 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0100 | Voice Recognition | Control Vehicle - Door | 车门控制 Door control-解锁/上锁车门 Door lock/unlock | 车门控制 Door control-解锁/上锁车门 Door lock/unlock |  |  | U | I | B |  | IVI | AVRVC_020 |  |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0101 | Voice Recognition | Control Vehicle - Lighting | 车灯控制 Lighting control-打开/关闭车灯 Lighting on/off | 车灯控制 Lighting control-打开/关闭车灯 Lighting on/off |  |  | U | I | B |  | IVI | AVRVC_021 |  |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0102 | Voice Recognition | Control Vehicle - Trunck | 车尾后备箱控制 Trunck control-打开/关闭车尾箱 Trunk on/off | 车尾后备箱控制 Trunck control-打开/关闭车尾箱 Trunk on/off |  |  | U | I | B |  | IVI | AVRVC_022 |  |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0103 | Social & Operation Services | Payment & Wallet | 停车场付费（含二维码支付） | 停车场付费（含二维码支付） | 车牌绑定支付账户 Baidu: 依赖第三方的资源，Baidu当前评估不确定J1是否一定可以满足，风险较高。 |  | Y | Y | B |  | CVPP | AVRSP_001 | 51 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0104 | Social & Operation Services | Payment & Wallet | 停车查询 Pay for parking | 搜索附近的停车场 | 搜索附近的停车场 |  | Y | Y | B |  | CVPP | AVRSP_002 | 52 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0105 | Social & Operation Services | Payment & Wallet | 停车查询 Pay for parking | 查看实时车位 | 查看实时车位 |  | Y | Y | B |  | CVPP | AVRSP_003 | 52 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0106 | Social & Operation Services | Payment & Wallet | 购买电影票（含二维码支付）Pay for movie tickets-打通百度账号 | 购买电影票（含二维码支付）Pay for movie tickets | 打通百度账号 |  | Y | Y | B |  | CVPP | AVRSP_004 | 53 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0107 | Social & Operation Services | Payment & Wallet | 购买电影票（含二维码支付）Pay for movie tickets-查看热映电影 | 购买电影票（含二维码支付）Pay for movie tickets | 查看热映电影 |  | Y | Y | B |  | CVPP | AVRSP_005 | 53 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0108 | Social & Operation Services | Payment & Wallet | 购买电影票（含二维码支付）Pay for movie tickets-选座购票 | 购买电影票（含二维码支付）Pay for movie tickets | 选座购票 |  | Y | Y | B |  | CVPP | AVRSP_006 | 53 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0109 | Social & Operation Services | Payment & Wallet | 支付功能里电影票，鲜花，餐品/外卖预定可以支持免密支付 | 支付功能里电影票，鲜花，餐品/外卖预定以及酒店可以支持免密支付 | 免密支付 | line 210,需加入feature list | Y | n | B |  | CVPP | AVRSP_006 | 53 | Lu, Chao (C.) |  | Lu, Chao (C.) | N |  |  |  | N |  |  |  |  | N | Y | Y | Y
SYNC+_0110 | Social & Operation Services | Booking & Search | 违章查询 Query traffic violations | 违章查询 Query traffic violations | Baidu: 用户终端查询是需要收费的。 | line 211,需加入feature list | Y | n | B |  | CVPP | AVRSP_007 | 248 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0111 | Social & Operation Services | Booking & Search | 餐品预定（含二维码支付）外卖预定（含二维码支付）Order food delivery | 餐品预定（含二维码支付）外卖预定（含二维码支付）Order food delivery | 餐品预定（含二维码支付）外卖预定（含二维码支付）Order food delivery | Feature id 177 | Y | n | B |  | CVPP | AVRSP_008 | 54 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0112 | Social & Operation Services | Booking & Search | 鲜花预定（含二维码支付） Order flower delivery | 鲜花预定（含二维码支付） Order flower delivery | 鲜花预定（含二维码支付） Order flower delivery | line 212,需加入feature list | Y | n | B |  | CVPP | AVRSP_009 | 55 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0113 | Social & Operation Services | Booking & Search | 机票查询 Flight search | 机票查询 Flight search | 机票查询 Flight search | line213,需加入feature list | Y | n | B |  | CVPP | AVRSP_010 | 56 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0114 | Social & Operation Services | Booking & Search | 火车票查询 Train ticket search | 火车票查询 Train ticket search | 火车票查询 Train ticket search | line214,需加入feature list | Y | n | B |  | CVPP | AVRSP_011 | 57 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0115 | Social & Operation Services | Booking & Search | 酒店预定 Hotel booking | 酒店预定 Hotel booking | 酒店预定 Hotel booking | feature id 140 | Y | n | B |  | CVPP | AVRSP_012 | 58 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0116 | Maintenance and insurance | VHA DIAGNOSTIC | 建议保养时间 | 建议保养时间 |  |  | Y | Y | B | Phase 4: Vehicle Health Alert | CVPP | AVRSP_013 | 253 | ZHU, AMY | 李大青 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0117 | Maintenance and insurance | VHA DIAGNOSTIC | 建议保养项目 | 建议保养项目 |  |  | Y | Y | B | Phase 4: Vehicle Health Alert | CVPP | AVRSP_014 | 253 | ZHU, AMY | 李大青 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0118 | Maintenance and insurance | VHA DIAGNOSTIC | 建议保养里程 | 建议保养里程 |  |  | Y | Y | B | Phase 4: Vehicle Health Alert | CVPP | AVRSP_015 | 253 | ZHU, AMY | 李大青 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0119 | Maintenance and insurance | Maintenance | 预约保养 | 预约保养 |  |  | NA | N | B |  | CVPP | AVRSP_016 | 253 | Wang, Johnny (J.) | 李大青 | Wang, Johnny (J.) | N |  |  |  | Y | [5 empty] | Y |  |  | Y |  |  |  | Duplicate, Del
SYNC+_0120 | Voice Recognition | Vehicle Status Query | 油量 Fuel status | 油量 Fuel status |  |  | Y | I | B |  | IVI | AVRVS_001 | 59 | Wang Jingjing | 李大青 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0121 | Voice Recognition | Vehicle Status Query | 胎压 Tire pressure | 胎压 Tire pressure |  |  | Y | I | B |  | IVI | AVRVS_002 | 59 | Wang Jingjing | 李大青 | Wang Jingjing | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0122 | Voice Recognition | Vehicle Status Query | 车辆总里程 mileage | 车辆总里程 mileage |  |  | Y | I | B |  | IVI | AVRVS_003 |  | Wang Jingjing | 李大青 | Wang Jingjing | N |  |  |  | N |  |  |  | N | N | N | N | N | N |  |  |  | Double check with Jingjing--Confirmed
SYNC+_0123 | Voice Recognition | Vehicle Status Query | 发动机 Engine | 发动机 Engine |  |  | Y | I | B |  | IVI | AVRVS_004 |  | Wang Jingjing | 李大青 | Wang Jingjing | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0124 | Voice Recognition | Control Vehicle - A/C | 空调 AC | 打开/关闭空调 open/close AC |  |  | Y | I | B |  | IVI | AVRVS_005 |  | Wang Jingjing | 李大青 | Wang Jingjing | Y |  |  |  | Y |  |  |  | N | Y | Y | Y | Y | N
SYNC+_0125 | IVI System Function | System Settings - Input | 百度输入法 Baidu Input | 拼音+手写+数字、符号、英文键盘 和其它 且支持联想、记忆、当前热词功能等。 |  |  | Y | Y | B |  | IVI | IME_001 | 60 | Yao, Lan (L.) | 李大青 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0126 | IVI System Function | System Settings - Input | 其它输入法 other input method | 拼音+手写+数字、符号、英文键盘 或其它 且支持联想、记忆、当前热词功能等。 |  | feature id 145 | Y | N | B |  | IVI | IME_002 |  | Yao, Lan (L.) | 李大青 | Yao, Lan (L.) | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0127 | Navigation | Navigation - Basic function | 地图基础版（见《IOV-地图功能list) Foundamental version of Map | POI检索、地点收藏 POI search & store destinations |  |  | U | Y | B |  | IVI | MAP_001 | 61 | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0128 | Navigation | Send to car | Send to car--把用户在手机APP查询的POI发送到车机 Send POI from smartphone APP to vehicle | 把用户在手机APP查询的POI发送到车机 Send POI from smartphone APP to vehicle |  |  | U | Y | B |  | CVPP | MAP_002 | 62 | Shi Stella | 陆振文 | Shi Stella | Y (need CVPP FordPass to clarify further details) |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0129 | Navigation | AR Navigation | 导航转向 | 导航转向 |  |  | NA | N | B |  | IVI | MAP_003 |  | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | N(暂无，硬件依赖) |  |  |  | N |  |  |  | N | N | N | N | N | N |  |  |  | Duplicate, Del, Refer to the AR-Navi Spec in Phase3
SYNC+_0130 | Navigation | AR Navigation | 路线标记 | 路线标记 |  |  | NA | N | B |  | IVI | MAP_004 |  | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | N(暂无，硬件依赖) |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0131 | Navigation | Navigation - Intelligent function | Pickup Riders | 定位不准的时候，用户发送实时地址，可以接到用户 |  |  | U | Y | B |  | CVPP | MAP_020 | 254 | Shi Stella | 陆振文 | Shi Stella | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0132 | Navigation | Navigation - Basic function | 限行提醒 Reminder of traffic control rules | 限行提醒 Reminder of traffic control rules |  |  | U | Y | B |  | IVI | MAP_005 | 63 | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0133 | Navigation | Navigation - Basic function | 超速提醒 Reminder of over speed | 超速提醒 Reminder of over speed |  |  | U | Y | B |  | IVI | MAP_006 | 64 | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0134 | Navigation | Navigation - Basic function | 惯性导航Inertial navi | 惯性导航Inertial navi |  |  | U | Y | B |  | IVI | MAP_007 | 65 | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0135 | Navigation | Navigation - Basic function | 实时交通播报 Real-time traffic broadcast. | 实时交通播报 Real-time traffic broadcast. | 包含在百度的“地图基础功能featurelists” |  | U | Y | B |  | IVI | MAP_008 | 66 | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0136 | Navigation | Navigation - Basic function | 明星语音包 | 明星语音包 |  | feature id 83 | Y | N | B |  | IVI | MAP_009 |  | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0137 | Navigation | Navigation - Basic function | 组队出行 | 组队出行 | Team Grouping Travelling & Talking |  | U | Y | B |  | IVI | MAP_010 | 67 | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0138 | Navigation | Navigation - Basic function | Lincoln个性化底图 | Lincoln个性化底图 | 需要福特提供Lincoln底图资源（可以提供但是没有经纬度信息） Baidu当前采用自己的数据资源. 需要Ford认可数据来源 | feature id 83 | U | N | B |  | HMI | MAP_019 | 255 | Xiao, Yun (Y.) | 李大青 | Xiao, Yun (Y.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0139 | Navigation | Navigation - Basic function | 福特个性化底图 | 福特个性化底图 | 需要福特提供底图资源（可以提供但是没有经纬度信息） Baidu当前采用自己的数据资源. 需要Ford认可数据来源 | feature id 83 | U | N | B |  | HMI | MAP_011 | 68 | Xiao, Yun (Y.) | 李大青 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  |  | Y | Y | N | N | N
SYNC+_0140 | Navigation | Navigation - Basic function | Launcher 地图 | Launcher 地图 |  |  | U | Y | B |  | IVI | MAP_012 | 69 | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0141 | Navigation | Navigation - Basic function | 无GPS信号的地下停车找车 Find my car in parking lots. | 无GPS信号的地下停车找车 Find my car in parking lots. | Baidu: 地下停车场环境下(没有GPS信号环境下)，依赖于惯性导航模块和停车场地理数据，Baidu对于J1集成有风险。当前Baidu能提供的是最近的有效的GPS位置信号。 |  | U | Y | B |  | CVPP | MAP_013 | 256 | TBD (DCR pending discussion) | 陆振文 | TBD (DCR pending discussion) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0142 | Navigation | Navigation - Basic function | 有GPS信号区域停车找车 Find my car in parking lots. | 有GPS信号区域停车找车 Find my car in parking lots. | Baidu: 地下停车场环境下(没有GPS信号环境下)，依赖于惯性导航模块和停车场地理数据，Baidu对于J1集成有风险。当前Baidu能提供的是最近的有效的GPS位置信号。 |  | U | Y | B |  | IVI | MAP_014 | 70 | Li, Alvin (L.) | 陆振文 | Li, Alvin (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0143 | Navigation | Navigation - Basic function | 路线雷达 radar detection in routes | 路线雷达 radar detection in routes |  |  | U | Y | B |  | IVI | MAP_015 | 71 | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0144 | Navigation | Navigation - Basic function | 3D地图 3D map | 3维地图 3D map |  |  | U | Y | B |  | IVI | MAP_016 | 72 | Yao, Lan (L.) | 陆振文 | Yao, Lan (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0145 | Navigation | Navigation - Basic function | 地图显示的夜间/白天模式 | 白天、夜晚自动切换地图界面的显示，减少大屏对夜间用户开车的视线干扰 和 保证地图信息对用户清晰可见。 | 1. 基于IVI 系统时间来切换白天和夜晚 2. 基于车辆自身的关系传感器及大灯状态（需要Tier1 参与提供接口） |  | U | Y | B |  | IVI | MAP_017 | 73 | Song, Rui (Rex.) | 陆振文 | Song, Rui (Rex.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0146 | Navigation | Navigation - Basic function | 地图包更新MOTA (FO不是CVPP，待定) | 地图APP更新，区域地图更新。(应用内更新数据) | 地图更新MOTA，离线数据应用中可以直接更新。地图app版本升级在整体OTA中。 |  | U | Y | B |  | IVI | MAP_018 | 74 |  | 李大青 |  | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0147 | In-Cabin Image Recognition | Facial ID - Account | 个人中心-人脸绑定入口 | 个人中心-人脸绑定入口 |  |  | NA | Y | B |  | IVI | IP_001 |  | Jia, Elaine (T.) | 李大青 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N |  |  |  | Dupilcate, Del,Refer to the Face ID Spec in Phase3
SYNC+_0148 | In-Cabin Image Recognition | Facial ID - Account | 上传照片/摄像头拍摄人脸照片 | 上传照片/摄像头拍摄人脸照片 |  |  | NA | Y | B |  | IVI | IP_002 |  | Jia, Elaine (T.) | 李大青 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | TBC |  | TBD | N
SYNC+_0149 | In-Cabin Image Recognition | Facial ID - Account | 成功绑定人脸 | 成功绑定人脸 |  |  | NA | Y | B |  | IVI | IP_003 |  | Jia, Elaine (T.) | 李大青 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0150 | In-Cabin Image Recognition | Facial ID - Account | 解绑人脸照片 | 解绑人脸照片 |  |  | NA | Y | B |  | IVI | IP_004 |  | Jia, Elaine (T.) | 李大青 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0151 | In-Cabin Image Recognition | Facial ID - Account | 多账号登录切换/对应多账号人脸绑定 | 多账号登录切换/对应多账号人脸绑定 |  |  | NA | Y | B |  | IVI | IP_005 |  | Jia, Elaine (T.) | 李大青 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0152 | In-Cabin Image Recognition | Facial ID - Login | 开机系统默认开启摄像头 | 开机系统默认开启摄像头 |  |  | NA | Y | B |  | IVI | IP_006 |  | Jia, Elaine (T.) | 李大青 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0153 | In-Cabin Image Recognition | Facial ID - Login | 人脸扫描，吊起摄像头识别 | 人脸扫描，吊起摄像头识别 |  |  | NA | Y | B |  | IVI | IP_007 |  | Jia, Elaine (T.) | 李大青 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0154 | In-Cabin Image Recognition | Facial ID - Login | 比对人脸，账号登录 | 比对人脸，账号登录 |  |  | NA | Y | B |  | IVI | IP_008 |  | Jia, Elaine (T.) | 李大青 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0155 | In-Cabin Image Recognition | Facial ID - Payment | 开机系统默认开启摄像头 | 开机系统默认开启摄像头 |  |  | NA | Y | B |  | IVI-Distribute CVPP | IP_009 |  | Jia Elaine /Lu Chao | 李大青 | Jia Elaine /Lu Chao | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0156 | In-Cabin Image Recognition | Facial ID - Payment | 人脸扫描，吊起摄像头识别 | 人脸扫描，吊起摄像头识别 |  |  | NA | Y | B |  | IVI-Distribute CVPP | IP_010 |  | Jia Elaine /Lu Chao | 李大青 | Jia Elaine /Lu Chao | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0157 | In-Cabin Image Recognition | Facial ID - Payment | 人脸校验完成，完成支付 | 人脸校验完成，完成支付 |  |  | NA | Y | B |  | IVI-Distribute CVPP | IP_011 |  | Jia Elaine /Lu Chao | 李大青 | Jia Elaine /Lu Chao | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0158 | In-Cabin Image Recognition | Gesture Recognition | 提供个性化车控功能 | 提供个性化车控功能-空气净化器 |  |  | NA | Y | B |  | IVI | IP_012 |  | Jia, Elaine (T.) | 陈冰 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | N |  | TBD | N
SYNC+_0159 | In-Cabin Image Recognition | Gesture Recognition | 提供个性化车控功能 | 提供个性化车控功能-空调温度 |  |  | NA | Y | B |  | IVI | IP_013 |  | Jia, Elaine (T.) | 陈冰 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | N |  | TBD | N
SYNC+_0160 | In-Cabin Image Recognition | Gesture Recognition | 提供个性化车控功能 | 提供个性化车控功能-空调风量 |  |  | NA | Y | B |  | IVI | IP_014 |  | Jia, Elaine (T.) | 陈冰 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | N |  | TBD | N
SYNC+_0161 | In-Cabin Image Recognition | Gesture Recognition | 提供个性化车控功能 | 提供个性化车控功能-内循环 |  |  | NA | Y | B |  | IVI | IP_015 |  | Jia, Elaine (T.) | 陈冰 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | N |  | TBD | N
SYNC+_0162 | In-Cabin Image Recognition | Gesture Recognition | 提供个性化车控功能 | 提供个性化车控功能-左右后视镜角度 |  |  | NA | Y | B |  | IVI | IP_016 |  | Jia, Elaine (T.) | 陈冰 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | N |  | TBD | N
SYNC+_0163 | In-Cabin Image Recognition | Gesture Recognition | 提供个性化车控功能 | 提供个性化车控功能-座椅角度 |  |  | NA | Y | B |  | IVI | IP_017 |  | Jia, Elaine (T.) | 陈冰 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | N |  | TBD | N
SYNC+_0164 | In-Cabin Image Recognition | Driver Monitoring System(DMS) | 疲劳驾驶监控和提醒 | 疲劳驾驶监控和提醒 |  |  | NA | Y | B |  | IVI | IP_018 |  | Jia, Elaine (T.) | 陈冰 | Jia Elaine | N（硬件依赖） |  |  |  | N |  |  |  |  | N | Y |  | TBD | N
SYNC+_0165 | Multimedia | Online Content Provider | 随心听电台：音乐，基于账号及喜好记忆进行主动推荐 Music recommended according account & preference | 随心听电台：音乐，基于账号及喜好记忆进行主动推荐 Music recommended according account & preference |  |  | U | Y | B | 本地及在线音乐/Offline&Online Music Player 在线收音机 Online Radio | IVI | NE_001 | 75 | Xiang, Zhengxi (Z.) | 张威平 | Xiang, Zhengxi (Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0166 | Multimedia | Online Content Provider | 随心听电台：新闻，基于账号及喜好记忆进行主动推荐 News recommended according account & preference | 随心听电台：新闻，基于账号及喜好记忆进行主动推荐 News recommended according account & preference |  |  | U | Y | B | 本地及在线音乐/Offline&Online Music Player 在线收音机 Online Radio | IVI | NE_002 | 75 | Xiang, Zhengxi (Z.) | 张威平 | Xiang, Zhengxi (Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0167 | Multimedia | Online Content Provider | 随心听电台：有声，基于账号及喜好记忆进行主动推荐 Audio book recommended according account & preference | 随心听电台：有声，基于账号及喜好记忆进行主动推荐 Audio book recommended according account & preference |  |  | U | Y | B |  | IVI | NE_003 | 75 | Xiang, Zhengxi (Z.) | 张威平 | Xiang, Zhengxi (Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0168 | Connected Service | User Data Burying point | 用户使用数据埋点 | 用户使用数据埋点 Phase 1 | 统计功能使用情况和用户偏好 Statistics feature usage and user preferences | feature id 183 | Y | n | B |  | CVPP | DA_002 |  | Fan Henry | 李大青 | Fan Henry | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0169 | Connected Service | User Data Burying point | 用户使用数据埋点 | 用户使用数据埋点 Phase 2 | 统计功能使用情况和用户偏好 Statistics feature usage and user preferences | feature id 183 | Y | n | B |  | CVPP | DA_003 | 257 | TBD (new hire) | 李大青 | TBD (new hire) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0170 | Connected Service | Big Data Analytics | 统计DuerOS 月度和年度激活量 Statistics monthly and annual system activation quantities | 统计DuerOS 月度和年度激活量 Statistics monthly and annual system activation quantities |  | feature id 183 | U | n | B |  | CVPP | DA_001 | 76 | TBD (new hire) | 李大青 | TBD (new hire) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0171 | Personalization & Accounts | One ID Account | 车机百度账号登录 Baidu account login | 车机百度账号登录 Baidu account login |  |  | U | y | B |  | CVPP | ACC_001 | 77 | Wang, Johnny (J.) | 李超群 | Wang, Johnny (J.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | N
SYNC+_0172 | Personalization & Accounts | One ID Account | 与Lincoln账号打通 Connected with Lincoln account | 与Lincoln账号打通 Connected with Lincoln account |  |  | U | y | B |  | CVPP | ACC_005 | 258 | Wang, Johnny (J.) | 李超群 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0173 | Personalization & Accounts | One ID Account | 与福特账号打通 connected with Ford account | 与福特账号打通 connected with Ford account |  |  | U | y | B |  | CVPP | ACC_002 | 78 | Wang, Johnny (J.) | 李超群 | Wang, Johnny (J.) | Y |  |  |  | Y |  |  |  |  | Y | Y | N | N | N
SYNC+_0174 | Personalization & Accounts | One ID Account | 手机端林肯之道&百度账号互通 Fordpass & Baidu account connection | 手机端林肯之道&百度账号互通 Fordpass & Baidu account connection |  |  | U | y | B |  | CVPP | ACC_006 | 259 | Wang, Johnny (J.) | 李超群 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0175 | Personalization & Accounts | One ID Account | 手机端福特派&百度账号互通 Fordpass & Baidu account connection | 手机端福特派&百度账号互通 Fordpass & Baidu account connection |  |  | U | y | B |  | CVPP | ACC_003 | 79 | Wang, Johnny (J.) | 李超群 | Wang, Johnny (J.) | Y |  |  |  | Y |  |  |  |  | Y | Y | N | N | N
SYNC+_0176 | Personalization & Accounts | One ID Account | 车机端多账户管理 Account management | 车机端多账户管理 Account management |  |  | U | y | B |  | CVPP | ACC_004 | 260 | Wang, Johnny (J.) | 李超群 | Wang, Johnny (J.) | N |  |  |  | N |  |  |  |  | N | Y | Y | Y | Y
SYNC+_0177 | Vehicle Function | Cluster & HUD Interface | 导航服务，转向、电子眼、ETA等信息 turn lane,radar detector & ETA | 导航服务，转向、电子眼、ETA等信息 turn lane,radar detector & ETA | CAN互动，消息协议由Ford定义 |  | Y | I | B |  | IVI | DC_001 | 80 | Chen, Jiazu (J.) | 张威平 | Chen, Jiazu (J.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0178 | Vehicle Function | Cluster & HUD Interface | 广播，专辑信息、歌名、歌手 Album info,song & singer and Radio | 广播，专辑信息、歌名、歌手 Album info,song & singer and Radio | CAN互动，消息协议由Ford定义 |  | Y | I | B |  | IVI | DC_002 | 81 | Chen, Jiazu (J.) | 张威平 | Chen, Jiazu (J.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0179 | Vehicle Function | Cluster & HUD Interface | 来电号码及名称显示，接听，挂电话 incoming caller ID display，answer call， hang-up call | 来电号码及名称显示，接听，挂电话 incoming caller ID display，answer call， hang-up call | CAN互动，消息协议由Ford定义 |  | Y | I | B |  | IVI | DC_003 | 82 | Chen, Jiazu (J.) | 李大青 | Chen, Jiazu (J.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0180 | Vehicle Function | Cluster & HUD Interface | 仪表控制导航的功能：同步目的地收藏，设置目的地途经点Cluster control IVI Navigation。 | 仪表控制导航的功能：同步目的地收藏，设置目的地途经点Cluster control IVI Navigation。 | CAN互动，消息协议由Ford定义 |  | Y | I | B |  | IVI | DC_004 | 83 | Chen, Jiazu (J.) | 李大青 | Chen, Jiazu (J.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0181 | Vehicle Function | Cluster & HUD Interface | Lincoln AHUD 信息同步 | Lincoln AHUD 信息同步 | CAN互动，消息协议由Lincoln定义 |  | Y | I | B |  | IVI | DC_006 | 261 | Chen, Jiazu (J.) | 李大青 | Chen, Jiazu (J.) | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0182 | Vehicle Function | Cluster & HUD Interface | Lincoln Rear entertainment control(Climate/Audio) - U611 | Lincoln Rear entertainment control(Climate/Audio) - U611 | CAN互动，消息协议由Lincoln定义 |  | Y | I | B |  | IVI | DC_007 | 262 | Chen, Jiazu (J.) | 李大青 | Chen, Jiazu (J.) | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0183 | Vehicle Function | Cluster & HUD Interface | 导航，里程，多媒体，电话等信息在HUD上的显示 IVI info showed in HUD | 导航，里程，多媒体，电话等信息在HUD上的显示 IVI info showed in HUD | CAN互动，消息协议由Ford定义 |  | Y | I | B |  | IVI | DC_005 | 84 | Chen, Jiazu (J.) | 李大青 | Chen, Jiazu (J.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0184 | IoT | Smart Home | 提前开空调 Turn on AC(at home) in advance | 提前开空调 Turn on AC(at home) in advance |  |  | Y | Y | B | IN PHASE 4: 智能家居/Intelligent Home Control Home to Car | CVPP | SM_001 | 85 | Lu Chao | 李大青 | Lu Chao | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0185 | IoT | Smart Home | 提前开扫地机器人 Turn on cleaning robert | 提前开扫地机器人 Turn on cleaning robert |  |  | Y | Y | B | IN PHASE 4: 智能家居/Intelligent Home Control Home to Car | CVPP | SM_002 | 86 | Lu Chao | 李大青 | Lu Chao | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0186 | IoT | Smart Home | 提前开灯 Turn on lights | 提前开灯 Turn on lights |  |  | Y | Y | B | IN PHASE 4: 智能家居/Intelligent Home Control Home to Car | CVPP | SM_003 | 87 | Lu Chao | 李大青 | Lu Chao | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0187 | IoT | Smart Home | 车机端智能硬件页面入口 smart devices' access from vehicle | 车机端智能硬件页面入口 smart devices' access from vehicle |  |  | Y | Y | B | IN PHASE 4: 智能家居/Intelligent Home Control Home to Car | CVPP | SM_004 | 88 | Lu Chao | 李大青 | Lu Chao | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0188 | Vehicle Function | Remote Control | 查询油量 fuel status query | 查询油量 fuel status query |  |  | N | N |  |  | CVPP | SM_005 |  | Lu Chao | 李大青 | Lu Chao | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0189 | Vehicle Function | Remote Control | 远程控制灯光/鸣笛 Remote control lighting/horn | 实现车辆远程灯光/鸣笛控制 |  |  | N | N |  | N | CVPP | SM_006 |  | Chen Kiefer | 李大青 | Chen Kiefer | N |  |  |  | N |  |  |  |  | N | TBD | TBD | TBD | N |  |  |  | NO WORK FOR BAIDU OR YFVE. Programs TBD. Doesn't affect MA quote.
SYNC+_0190 | Vehicle Function | Remote Control | 远程启动空调/热车 Remote start engine/AC | 远程启动空调/热车 Remote start engine/AC |  |  | N | n | D | TEST ONLY | CVPP | SM_007 |  | Chen Kiefer | 李大青 | Chen Kiefer | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0191 | Personalization & Accounts | Personalization | 用户注册/登录 register/login | 用户注册/登录 register/login |  |  | U | y | B |  | CVPP | PER_001 | 263 | Wang, Johnny (J.) | 李大青 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0192 | Vehicle Function | Personalization | 座椅位置 seat position | 座椅位置 seat position |  |  | y | Y | D | include in "Ford Vehicle Settings On IVI" | CVPP-Distribute System | PER_002 | 264 | Wang, Johnny (J.) /Xu Xiao Kang | 陈冰 | Wang, Johnny (J.) /Xu Xiao Kang | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0193 | Vehicle Function | Personalization | 氛围灯 ambient lighting | 氛围灯 ambient lighting |  |  | Y | Y | D | include in "Ford Vehicle Settings On IVI" | CVPP-Distribute System | PER_003 | 265 | Wang, Johnny (J.) /Xu Xiao Kang | 陈冰 | Wang, Johnny (J.) /Xu Xiao Kang | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0194 | Vehicle Function | Personalization | 空调面板 AC screen | 空调面板 AC screen |  |  | Y | y | B |  | CVPP-Distribute System | PER_004 | 266 | Wang, Johnny (J.) /Xu Xiao Kang | 陈冰 | Wang, Johnny (J.) /Xu Xiao Kang | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0195 | Connected Service | Security Device | 网络安全解决方案 | 网络安全解决方案 |  | feature id 5 | Y | Y | B/D |  | Cyber Security | SEC_001 | 89 | Shao, Jian (J.) | 韩宇 | Shao, Jian (J.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0196 | Multimedia | Radio/FM | 收音机 radio | 收音机 radio-基本控制(上一个/下一个) foundamental control |  |  | U | Y | B |  | IVI | RAD_001 | 90 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0197 | Multimedia | Radio/FM | 收音机 radio | 收音机 radio-输入频段 channel input |  |  | U | Y | B |  | IVI | RAD_002 |  | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y(指针形式) |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0198 | Multimedia | Radio/FM | 收音机 radio | 收音机 radio-启动/停止收音机 turn on/off |  |  | U | Y | B |  | IVI | RAD_003 | 91 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0199 | Multimedia | Radio/FM | 收音机 radio | 收音机 radio-手动调台 manual tuning |  |  | U | Y | B |  | IVI | RAD_004 | 92 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0200 | Multimedia | Radio/FM | 收音机 radio | 收音机 radio-收藏列表 collections | Baidu: 自带的随声听App音乐是具有收藏列表的。Baidu需要design 收藏列表的HMI，配合Tier1实现该功能。 |  | U | Y | B |  | IVI | RAD_005 | 93 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0201 | Multimedia | Radio/FM | 收音机 radio | 收音机 radio-更新电台列表(扫描及更新）update channels |  |  | U | Y | B |  | IVI | RAD_006 | 94 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0202 | Multimedia | Radio/FM | 收音机 radio | 收音机 radio-FM2 相关的菜单及功能 |  |  | U | Y | B |  | IVI | RAD_007 | 267 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0203 | Multimedia | Music | Music-启动/停止音乐播放器 on/off | Music-启动/停止音乐播放器 on/off |  |  | U | Y | B |  | IVI | MULT_001 | 95 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0204 | Multimedia | Music | Music-基本控制(播放/暂停/上一首/下一首) foundamental control | Music-基本控制(播放/暂停/上一首/下一首) foundamental control |  |  | U | Y | B |  | IVI | MULT_002 | 96 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0205 | Multimedia | Music | Music-播放列表 playlist | Music-播放列表 playlist |  |  | U | Y | B |  | IVI | MULT_003 | 97 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0206 | Multimedia | Music | Music-USB音乐 USB music | Music-USB音乐 USB music | 需要支持主流音频格式 |  | U | Y | B |  | IVI | MULT_004 | 98 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0207 | Multimedia | Music | Music-MTP音乐 MTP music | Music-MTP音乐 MTP music |  |  | U | Y | B |  | IVI | MULT_005 | 99 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0208 | Multimedia | Music | Music-蓝牙音乐 BT music | Music-蓝牙音乐 BT music |  |  | U | Y | B |  | IVI | MULT_006 | 100 | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0209 | Multimedia | Music | Music-IPOD音乐 IPOD music | Music-IPOD音乐 IPOD music |  |  | U | Y | B |  | IVI | MULT_007 |  | Yu, Justin (Y.Z.) | 张威平 | Yu, Justin (Y.Z.) | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0210 | Multimedia | Music | Music-音频设置入口 sound frequency setting | Music-音频设置入口 sound frequency setting |  |  | U | Y | B |  | IVI | MULT_008 | 101 | Yu, Justin (Y.Z.) Fin Wang | 张威平 | Yu, Justin (Y.Z.) Fin Wang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0211 | Multimedia | Image Reader | USB图片 USB pics | USB图片 USB pics |  |  | U | Y | B |  | IVI | MULT_009 |  |  | 于盛进 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0212 | Multimedia | Music | 本地音乐 music in local storage | 本地音乐 music in local storage |  |  | U | Y | B |  | IVI | MULT_010 | 102 | Yu, Justin (Y.Z.) Fin Wang | 于盛进 | Yu, Justin (Y.Z.) Fin Wang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0213 | Multimedia | Video | 在线视频 Online video | 在线视频 Online video |  |  | U | Y | B |  | IVI | MULT_011 | 103 | Li, Alvin (L.) | 于盛进 | Li, Alvin (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0214 | Multimedia | Video | USB视频播放 USB video | USB视频播放 USB video | 需要支持主流视频格式 |  | U | Y | B |  | IVI | MULT_012 | 104 | Li, Alvin (L.) | 于盛进 | Li, Alvin (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0215 | Multimedia | Phone | 通话记录 records | 通话记录 records |  |  | U | Y | B | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | IVI | PH_001 | 105 | Yu, Justin (Y.Z.) | 李大青 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0216 | Multimedia | Phone | 拨号 dial | 拨号 dial | 语音拨号 界面拨号 |  | U | Y | B | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | IVI | PH_002 | 106 | Yu, Justin (Y.Z.) | 李大青 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0217 | Multimedia | Phone | 通讯录搜索 | 通讯录搜索 | 语音搜索 界面搜索 |  | U | Y | B | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | IVI | PH_003 | 107 | Yu, Justin (Y.Z.) | 李大青 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0218 | Multimedia | Phone | 通讯录 contacts | 通讯录 contacts |  |  | U | Y | B | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | IVI | PH_004 | 108 | Yu, Justin (Y.Z.) | 李大青 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0219 | Multimedia | Phone | 同步通讯录和通话记录 sync contacts& records | 同步通讯录和通话记录 sync contacts& records |  |  | U | Y | B | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | IVI | PH_005 | 109 | Yu, Justin (Y.Z.) | 李大青 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0220 | Multimedia | Phone | 请勿打扰 DO NOT IDSTURB | 请勿打扰 DO NOT IDSTURB |  |  | U | Y | B | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | IVI | PH_006 | 110 | Yu, Justin (Y.Z.) | 李大青 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0221 | Multimedia | Phone | 通话界面功能 in a call screen | 通话界面功能 in a call screen |  |  | U | Y | B | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | IVI | PH_008 | 111 | Yu, Justin (Y.Z.) | 李大青 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0222 | IVI System Function | System Setting - Sound | 声音设置 sound setting | 详情请参考Ford的HMI Spec Mixed Mode Presets Autoset Preset Sound Settings - Treble/Mid/Bass Sound Settings - Balance/Fade Sound Settings - Speed Compensated Volume Sound Settings - Occupancy Mode |  |  | Y | Y | D |  | IVI | SYS_001 | 112 | Yu, Justin (Y.Z.) | 陈冰 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0223 | IVI System Function | System Setting - Wifi | wifi设置 wifi setting | 详情请参考Ford的HMI Spec |  |  | Y | y | D |  | CVPP | SYS_002 | 113 | Pan, Yuan (Y.) | 陈冰 | Pan, Yuan (Y.) | Y |  |  |  | Y |  |  |  |  | Y | Y |  |  | Y
SYNC+_0224 | IVI System Function | System Setting - Display | 显示/亮度设置 display/brightness setting | 详情请参考Ford的HMI Spec |  |  | Y | I - SETTING | D |  | IVI | SYS_004 | 115 | Song, Rui (Rex.) | 陈冰 | Song, Rui (Rex.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0225 | IVI System Function | System Setting - Language | 语言设置 language setting-仅支持中文 Chinese Mandarin | 仅支持中文 Chinese Mandarin |  |  | Y | I - SETTING | D |  | IVI |  |  | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0226 | IVI System Function | System Setting - Language | 语言设置 language setting-支持中文 Chinese Mandarin 和 英语 NA English | 支持中文 Chinese Mandarin 和 英语 NA English |  |  | Y | Y | B |  | IVI | SYS_006 |  | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0227 | IVI System Function | System Setting - Date | 日期和时间设置 date&time setting | 详情请参考Ford的HMI Spec |  |  | Y | I - SETTING | D |  | IVI | SYS_007 | 116 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0228 | IVI System Function | System Setting - Reset | 恢复出厂设置 reset（Master Reset） | 详情请参考Ford的HMI Spec |  |  | Y | I - SETTING | D |  | IVI | SYS_008 | 117 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0229 | IVI System Function | System Setting - Audio | 语音设置 audio setting |  |  |  | Y | I - SETTING | D |  | IVI | SYS_009 | 118 | Song, Rui (Rex.) | 陈冰 | Song, Rui (Rex.) | Y(百度功能） |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0230 | IVI System Function | System Setting - Others | 关于本机 | IVI sw version, VIN IVI ESN, TCU ESN… |  |  | Y | I - SETTING | D |  | IVI | SYS_010 | 119 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0231 | IVI System Function | System Setting - BT | 蓝牙连接 BT connection |  |  |  | Y | Y | B |  | IVI | CONN_001 | 120 | Yu, Justin (Y.Z.) | 陈冰 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0232 | IVI System Function | System Setting - Wifi | Wifi 热点 Wifi Hot Spot | Wifi hot spot (WHS)- SSID or password. Refer to current sync 3 |  |  | Y | Y | D |  | CVPP | CONN_002 | 121 | Pan, Yuan (Y.) | 陈冰 | Pan, Yuan (Y.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0233 | Vehicle Function | Vehicle Setting on IVI - Light | 单色氛围灯 single color ambient lighting | 单色氛围灯 single color ambient lighting | 车型只支持单色氛围灯 |  | Y | I - SETTING | D | Ford Vehicle Settings On IVI | IVI-Distributed BS | VS_002 | 131 | Xu Xiaokang | 陈冰 | Xu Xiaokang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0234 | Vehicle Function | Vehicle Setting on IVI - Light | 多色氛围灯 multi color ambient lighting | 多色氛围灯 multi color ambient lighting | 车型支持多色氛围灯 |  | Y | I - SETTING | D | Ford Vehicle Settings On IVI | IVI-Distributed BS | VS_003 | 132 | Xu Xiaokang | 陈冰 | Xu Xiaokang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0235 | Vehicle Function | Vehicle Setting on IVI - Light | Lincoln colors | Lincoln colors | different color with Ford |  | Y | I - SETTING | D | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINAL_001 | 357 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0236 | Vehicle Function | Vehicle Setting on IVI - Others | Vehicle Idle (30 mins) | Vehicle Idle (30 mins) |  |  | NA | N | B |  |  | LINVS_001 | 315 |  |  |  | N |  |  |  | N | [5 empty] | N |  |  | N |  |  |  | Del
SYNC+_0237 | Vehicle Function | Vehicle Setting on IVI - Others | Power running boards (auto, on, off) | Power running boards (auto, on, off) |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_002 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0238 | Vehicle Function | Vehicle Setting on IVI - Others | Easy access height | Easy access height |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_003 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0239 | Vehicle Function | Vehicle Setting on IVI - Others | Park Lock Control | Park Lock Control |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_004 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0240 | Vehicle Function | Vehicle Setting on IVI - Others | Silent Mode | Silent Mode |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_005 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0241 | Vehicle Function | Vehicle Setting on IVI - Others | Alarm (ask on exit ,sensor set, perimeter, all sensors active) | Alarm (ask on exit ,sensor set, perimeter, all sensors active) |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_006 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0242 | Vehicle Function | Vehicle Setting on IVI - Others | Remote start (activate, climate, auto, last setting, seats and wheels, duration) | Remote start (activate, climate, auto, last setting, seats and wheels, duration) |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_007 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0243 | Vehicle Function | Vehicle Setting on IVI - Others | Wipers | Wipers |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_008 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0244 | Vehicle Function | Vehicle Setting on IVI - Others | Windows (remote open/close) | Windows (remote open/close) |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_009 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0245 | Vehicle Function | Vehicle Setting on IVI - Others | Wipers (courtesy, rain, reverse) | Wipers (courtesy, rain, reverse) |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_010 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0246 | Vehicle Function | Vehicle Setting on IVI - Others | Air suspension | Air suspension |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute PMT3 | LINVS_011 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0247 | Vehicle Function | Vehicle Setting on IVI - Others | Active Noise Cancellation | Active Noise Cancellation |  |  | U | I - SETTING | B | JUST SETTING? | IVI | LINVS_012 | 315 | Liu, Yang (Y.) | 陈冰 | Yu, Justin (Y.Z.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0248 | Vehicle Function | Vehicle Setting on IVI - Others | Rear liftgate | Rear liftgate |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_013 | 315 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0249 | Vehicle Function | Vehicle Setting on IVI - Others | Auto Engine OFF / 30min Max Idle | Auto Engine OFF / 30min Max Idle |  |  | NA | N | B |  |  | LINVS_014 | 315 |  |  |  | N |  |  |  | N | [5 empty] | N |  |  | N |  |  |  | Del
SYNC+_0250 | Vehicle Function | Vehicle Setting on IVI - Others | Chimes | Chimes |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute DI | LINVS_015 | 315 | Cao Helen | 李大青 | Cao Helen | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0251 | Vehicle Function | Vehicle Setting on IVI - Others | Park Heater | Park Heater |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute DI | LINVS_016 | 315 | Yao, Frank/DongYa | 李大青 | NA | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0252 | Vehicle Function | Vehicle Setting on IVI - Others | Aux Heater | Aux Heater |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute DI | LINVS_017 | 315 | Yao, Frank/DongYa | 李大青 | NA | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0253 | Vehicle Function | Vehicle Setting on IVI - Others | Passenger Airbag | Passenger Airbag |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute Safty Ele | LINVS_018 | 315 | Xu Xi Hai | 李大青 | Xu Xi Hai | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0254 | Vehicle Function | Vehicle Setting on IVI - Others | Tire Mobility Kit | Tire Mobility Kit |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute PMT3 | LINVS_019 | 315 | Xue Jianhua | 李大青 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0255 | Vehicle Function | Vehicle Setting on IVI - Others | Easy Entry / Easy Exit (Seat Adjustment) | Easy Entry / Easy Exit (Seat Adjustment) |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_020 | 315 | Xu Xiaokang | 李大青 | Xu Xiaokang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0256 | Vehicle Function | Vehicle Setting on IVI - Others | Cargo Loading | Cargo Loading |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_021 | 315 | Xue Jianhua | 李大青 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0257 | Vehicle Function | Vehicle Setting on IVI - Others | MyColor | MyColor |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_022 | 315 | Xue Jianhua | 李大青 | Xue Jianhua | N |  |  |  | N |  |  |  | N | N | N | N | N | N |  |  |  | Need the confirmation from Fin Wang--Confirmed
SYNC+_0258 | Vehicle Function | Vehicle Setting on IVI - Others | Power Decklid / Liftgate | Power Decklid / Liftgate |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_023 | 315 |  | 李大青 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0259 | Vehicle Function | Vehicle Setting on IVI - Others | Trailer Brake | Trailer Brake |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINVS_024 | 315 |  | 李大青 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0260 | Vehicle Function | Vehicle Setting on IVI - Others | Exhaust Mode | Exhaust Mode |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute PMT4 | LINVS_025 | 315 |  | 李大青 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0261 | Vehicle Function | Vehicle Setting on IVI - Others | Quiet Start - Exhaust Mode | Quiet Start - Exhaust Mode |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute PMT4 | LINVS_026 | 315 |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0262 | Vehicle Function | Vehicle Setting on IVI - Others | Set Quiet Time - Exhaust Mode | Set Quiet Time - Exhaust Mode |  |  | U | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute PMT4 | LINVS_027 | 315 |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0263 | Vehicle Function | Vehicle Setting on IVI - Light | Light Setting-Glare Free lighting | Light Setting-Glare Free lighting |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute DAT | LINLIG_001 | 268 | Amy Song | 陈冰 | Amy Song | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0264 | Vehicle Function | Vehicle Setting on IVI - Light | Light Setting-Auto highbeam | Light Setting-Auto highbeam |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distribute DAT | LINLIG_002 | 268 | Amy Song | 陈冰 | Amy Song | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0265 | Vehicle Function | Vehicle Setting on IVI - Light | Light Setting-daytime lights | Light Setting-daytime lights |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLIG_003 | 268 | Xu Xiaokang | 陈冰 | Xu Xiaokang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0266 | Vehicle Function | Vehicle Setting on IVI - Light | Light Setting-welcome lights | Light Setting-welcome lights |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed System | LINLIG_004 | 268 | Bella Wu | 陈冰 | Bella Wu | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0267 | Vehicle Function | Vehicle Setting on IVI - Light | Light Setting-Adaptive headlamps | Light Setting-Adaptive headlamps |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLIG_005 | 268 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0268 | Vehicle Function | Vehicle Setting on IVI - Light | Light Setting-Autolamp delay | Light Setting-Autolamp delay |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLIG_006 | 268 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0269 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-autolock | Lock Setting-autolock |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_001 | 269 | Xu Xiaokang | 陈冰 | Xu Xiaokang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0270 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-auto unlock | Lock Setting-auto unlock |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_002 | 269 | Xu Xiaokang | 陈冰 | Xu Xiaokang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0271 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-mislock | Lock Setting-mislock |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_003 | 269 | Xu Xiaokang | 陈冰 | Xu Xiaokang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0272 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-switch inhibit | Lock Setting-switch inhibit |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_004 | 269 | Xu Xiaokang | 陈冰 | Xu Xiaokang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0273 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-Intelligent access | Lock Setting-Intelligent access |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_005 | 269 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0274 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-Key free | Lock Setting-Key free |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_006 | 269 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0275 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-Audible feedback | Lock Setting-Audible feedback |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_007 | 269 | Xu Xiaokang | 陈冰 | Xu Xiaokang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0276 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-Exterior light feedback | Lock Setting-Exterior light feedback |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_008 | 269 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0277 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-Remote unlock | Lock Setting-Remote unlock |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_009 | 269 | Xu Xiaokang | 陈冰 | Xu Xiaokang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0278 | Vehicle Function | Vehicle Setting on IVI - Lock | Lock Setting-Global unlock | Lock Setting-Global unlock |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINLOC_010 | 269 | Xu Xiaokang | 陈冰 | Xu Xiaokang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0279 | Vehicle Function | Vehicle Setting on IVI - Mirror | Mirror Setting-Autofold | Mirror Setting-Autofold |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINMIR_001 | 270 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0280 | Vehicle Function | Vehicle Setting on IVI - Mirror | Mirror Setting-Reverse tilt | Mirror Setting-Reverse tilt |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI-Distributed BS | LINMIR_002 | 270 | Xue Jianhua | 陈冰 | Xue Jianhua | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0281 | Vehicle Function | Vehicle Setting on IVI - Unit | Unit Setting-Measurement Units | Unit Setting-Measurement Units | Same as ford settings |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI | LINSET_001 | 271 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0282 | Vehicle Function | Vehicle Setting on IVI - Unit | Unit Setting-Language | Unit Setting-Language | Same as ford settings |  | U | I - SETTING | B | ENGLISH SELECTION IN BEZEL DIAGNOSTIC? BU OFFER ENGLISH CLUSTER? | IVI | LINSET_002 |  | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0283 | Vehicle Function | Vehicle Setting on IVI - Unit | Unit Setting-Temperature | Unit Setting-Temperature | Same as ford settings |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI | LINSET_003 | 271 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0284 | Vehicle Function | Vehicle Setting on IVI - Unit | Unit Setting-Tire Pressure Units | Unit Setting-Tire Pressure Units |  |  | Y | I - SETTING | B | Ford Vehicle Settings On IVI | IVI | LINSET_004 | 271 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0285 | Vehicle Function | Shortcut Keys | Auto Stop Start | Auto Stop Start |  | desay负责功能开发，baidu支持HMI页面 | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_001 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0286 | Vehicle Function | Shortcut Keys | Auto Hold | Auto Hold |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_002 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0287 | Vehicle Function | Shortcut Keys | Traction Control | Traction Control |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_003 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0288 | Vehicle Function | Shortcut Keys | Cruise control- Type (Adaptive, intelligent, normal), tolerance | Cruise control- Type (Adaptive, intelligent, normal), tolerance |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_004 | 272 | Victor Cui | 陈冰 | Victor Cui | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0289 | Vehicle Function | Shortcut Keys | Lane keeping mode (alert, aid, alert + aid), alert intensity (high, medium, low), sensitvity (normal, increased), lane keeping aid (on, off), lane keeping alert (high, medium, low, on, off) | Lane keeping mode (alert, aid, alert + aid), alert intensity (high, medium, low), sensitvity (normal, increased), lane keeping aid (on, off), lane keeping alert (high, medium, low, on, off) |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_005 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0290 | Vehicle Function | Shortcut Keys | Pre Collision Assist (pre collision assist, distance indication, active breaking, evasive steer assist, alert sensitivity (high medium low)) | Pre Collision Assist (pre collision assist, distance indication, active breaking, evasive steer assist, alert sensitivity (high medium low)) |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_006 | 272 | Lynn Wang | 陈冰 | Lynn Wang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0291 | Vehicle Function | Shortcut Keys | Blind Spot | Blind Spot |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_010 | 272 | Zhou, Wu (W.) | 陈冰 | Isaac Zhang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0292 | Vehicle Function | Shortcut Keys | Cross Traffic Alert | 倒档来车预警按键功能 |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_011 | 272 | Zhou, Wu (W.) | 陈冰 | Isaac Zhang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0293 | Vehicle Function | Shortcut Keys | Wrong Way alert | Wrong Way alert |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_012 | 272 | Amy Song | 陈冰 | Amy Song | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0294 | Vehicle Function | Shortcut Keys | Hill start assist | Hill start assist |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_013 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0295 | Vehicle Function | Shortcut Keys | Driver alert | Driver alert |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_014 | 272 | Amy Song | 陈冰 | Amy Song | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0296 | Vehicle Function | Shortcut Keys | Trailer Sway | Trailer Sway |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_015 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0297 | Vehicle Function | Shortcut Keys | Grade Assits | Grade Assits |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_016 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0298 | Vehicle Function | Shortcut Keys | PADI | PADI |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_017 | 272 | Xihai Xu | 陈冰 | Xihai Xu | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0299 | Vehicle Function | Shortcut Keys | Engine Stop Start threshold | Engine Stop Start threshold |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_018 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0300 | Vehicle Function | Shortcut Keys | Tow Haul | Tow Haul |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_019 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0301 | Vehicle Function | Shortcut Keys | Rear Park Aid | Rear Park Aid |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_020 | 272 | Michael He | 陈冰 | Michael He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0302 | Vehicle Function | Shortcut Keys | Speed Limiter | Speed Limiter |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_021 | 272 | Amy Song | 陈冰 | Amy Song | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0303 | Vehicle Function | Shortcut Keys | Traffic Sign Recognition | Traffic Sign Recognition |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_022 | 272 | Amy Song | 陈冰 | Amy Song | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0304 | Vehicle Function | Shortcut Keys | Speed Limit Information / Speed Sign Recognition | Speed Limit Information / Speed Sign Recognition |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_023 | 272 | Amy Song | 陈冰 | Amy Song | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0305 | Vehicle Function | Shortcut Keys | Hill Decent Control | Hill Decent Control |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_024 | 272 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0306 | Driver Assist | Shortcut Keys | EV+ Mode | EV+ Mode |  |  | Y | I - Shortcut | D | FO to confirm | IVI-Distribute EPE | LINDA_025 | 272 |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0307 | Vehicle Function | Shortcut Keys | BTT Light (Blind Spot Trailer Tow) | BTT Light (Blind Spot Trailer Tow) |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINDA_026 | 272 | Zhang, Isaac (S.) | 陈冰 | Issac Zhang | N |  |  |  | N |  |  |  | N | N | N | N | N | Y
SYNC+_0308 | Vehicle Function | Shortcut Keys | Adaptive Steering | Adaptive Steering |  |  | Y | I - Shortcut | D |  | IVI-Distribute PMT3 | LINDA_027 | 272 | Zhang, Isaac (S.) | 陈冰 | Issac Zhang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0309 | Driver Assist | Park related | 泊车模式 park mode | 泊车模式 park mode |  |  | Y | y | D |  | IVI-Distribute DAT | AP_001 | 133 | Michael He | 陈冰 | Michael He | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0310 | Driver Assist | Park related | 障碍物距离显示 display distance to blocks (乌龟图) | （需考虑区分高低配置) |  |  | Y | Y | B |  | IVI-Distribute DAT | PS_001 | 134 | Michael He | 陈冰 | Michael He | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0311 | Driver Assist | Image Vehicle - 360 Camera | 俯视图 plan view (Rear/Front+ Plan View 全景加前或后的单路视图) | IPMB CVBS 360, Rear/Front |  |  | Y | Y | B |  | IVI-Distribute DAT | MC_001 | 135 | Xiao, Yun (Y.) /Zheng, Tina (T.) | 陈冰 | Xiao, Yun (Y.) /Zheng, Tina (T.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0312 | Driver Assist | Image Vehicle - 360 Camera | 视角切换图 split view (Rear/Front wideangle view,单路广角视图) | IPMB CVBS split view, Rear/Front |  |  | Y | Y | B |  | IVI-Distribute DAT | MC_002 | 136 | Xiao, Yun (Y.) /Zheng, Tina (T.) | 陈冰 | Xiao, Yun (Y.) /Zheng, Tina (T.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0313 | Driver Assist | Image Vehicle - 360 Camera | 2D/3D模式 | 2D/3D模式 |  |  | NA | N | B | FO to confirm | IVI-Distribute DAT | MC_003 |  | Xiao, Yun (Y.) /Zheng, Tina (T.) | 陈冰 | Xiao, Yun (Y.) /Zheng, Tina (T.) | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0314 | Driver Assist | Image Vehicle - 360 Camera | Front/Rear view (Front/Rear/Rear Zoom 前/后的三拼图，后路放大视图) | IPMB/RVC CVBS Front/Rear/Rear Zoom |  |  | Y | Y | B |  | IVI-Distribute DAT | MC_004 | 137 | Xiao, Yun (Y.) /Zheng, Tina (T.) | 陈冰 | Xiao, Yun (Y.) /Zheng, Tina (T.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0315 | Driver Assist | Image Vehicle - 360 Camera | 360°全景影像设置 setting | 360°全景影像设置 setting |  |  | NA | N | B | FO to confirm | IVI-Distribute DAT | MC_005 |  | Zheng, Tina (T.) | 陈冰 | Zheng, Tina (T.) | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0316 | IVI System Function | OTA | U盘升级 USB drive update （SOC) | U盘升级 USB drive update （SOC) |  |  | U | Y | B |  | IVI | SW_001 | 138 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0317 | IVI System Function | OTA | IVI远程升级 remote update（FOTA) | IVI远程升级 remote update（FOTA) |  |  | U | Y | D |  | CVPP | SW_002 | 139 | Pan Yuan | 陈冰 | Pan Yuan | Y |  |  |  | Y |  |  |  |  | Y | Y |  |  | Y
SYNC+_0318 | Vehicle Function | Vehicle Control - AC | Front Row Seat Heated | Front Row Seat Heated | 前排座椅加热 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_001 | 140 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0319 | Vehicle Function | Vehicle Control - AC | Front Seat Vent | Front Seat Vent | 前排座椅吹风 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_002 | 141 | Yao, Frank/DongYa | 陈冰 | NA | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0320 | Vehicle Function | Vehicle Control - AC | Driver temp | Driver temp | 主驾温度 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_003 | 142 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0321 | Vehicle Function | Vehicle Control - AC | Fan | Fan | 风速 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_004 | 143 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0322 | Vehicle Function | Vehicle Control - AC | Passenger temp | Passenger temp | 副驾温度 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_005 | 144 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0323 | Vehicle Function | Vehicle Control - AC | Dual AC | Dual AC | 双区空调 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_006 | 145 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0324 | Vehicle Function | Vehicle Control - AC | Windshield | Windshield | 挡风玻璃 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_007 | 146 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0325 | Vehicle Function | Vehicle Control - AC | AC - face | AC - face | 空调吹脸 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_008 | 147 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0326 | Vehicle Function | Vehicle Control - AC | Recirc. | Recirc. | 车内循环 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_009 | 148 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0327 | Vehicle Function | Vehicle Control - AC | Demist | Demist | 除雾 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_010 | 149 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0328 | Vehicle Function | Vehicle Control - AC | AC - feet | AC - feet | 空调吹脚 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_011 | 150 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0329 | Vehicle Function | Vehicle Control - AC | AC on/off | AC on/off | AC开关 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_012 | 151 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0330 | Vehicle Function | Vehicle Control - AC | Auto AC | Auto AC | 自动 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_013 | 152 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0331 | Vehicle Function | Vehicle Control - AC | Max windshield | Max windshield | 挡风除霜 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_014 | 153 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0332 | Vehicle Function | Vehicle Control - AC | Max AC | Max AC | 空调最大 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_015 | 154 | Yao, Frank/DongYa | 陈冰 | Yes | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0333 | Vehicle Function | Vehicle Control - AC | Rear climate fan | Rear climate fan | 后排空调风速 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_016 | 155 | Yao, Frank/DongYa | 陈冰 | N/A | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0334 | Vehicle Function | Vehicle Control - AC | Rear climate temp | Rear climate temp | 后排空调温度 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_017 | 156 | Yao, Frank/DongYa | 陈冰 | N/A | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0335 | Vehicle Function | Vehicle Control - AC | Rear climate mode | Rear climate mode | 后排空调模式 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_018 | 157 | Yao, Frank/DongYa | 陈冰 | N/A | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0336 | Vehicle Function | Vehicle Control - AC | Steering wheel heated | Steering wheel heated | 方向盘加热 |  | Y | I | B | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | IVI-Distribute DI | AC_019 | 158 | Yao, Frank/DongYa | 陈冰 | N/A | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0337 | Connected Service | Road Side Assitance | - 拨打道路救援电话，获取道路救援服务 - 入口：车机端"道路救援"应用，其存储着固定的道路救援电话号码 - 通过蓝牙连接的手机或者车载TCU 的VoIP拨打道路救援电话 | - 拨打道路救援电话，获取道路救援服务 - 入口：车机端"道路救援"应用，其存储着固定的道路救援电话号码 - 通过蓝牙连接的手机或者车载TCU 的VoIP拨打道路救援电话 |  |  | U | y | B |  | CVPP | RSA_001 | 159 | TBD | 李大青 | Sun Serena | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | N
SYNC+_0338 | Connected Service | Emergency Assistance in RSA (Not same as Emergency Assitance feature) | - 拨打道路救援电话，获取道路救援服务 - 入口：车机端"道路救援"应用，其存储着固定的道路救援电话号码 - *通过Tbox(非Ford TCU)拨打BCALL电话* -通过蓝牙连接拨打BCALL电话（ 最终内容以PRD为准） -车辆位置数据/车辆状况数据自动上传到车企后台；车企后台发送给SP(如需要) | - 拨打道路救援电话，获取道路救援服务 - 入口：车机端"道路救援"应用，其存储着固定的道路救援电话号码 - *通过Tbox(非Ford TCU)拨打BCALL电话* -通过蓝牙连接拨打BCALL电话（ 最终内容以PRD为准） -车辆位置数据/车辆状况数据自动上传到车企后台；车企后台发送给SP(如需要) |  |  | U | y | B |  | CVPP | RSA_002 | 273 | TBD | 李大青 | Sun Serena | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0339 | Connected Service | Theft prevention | 被盗车辆追踪(SVT) |  | - 开启被盗车辆追踪功能后，用户可在手机APP追踪车辆实时位置 - 未开启该功能时，手机APP只能查看熄火前最后一次上传的车辆位置 - 被盗车辆追踪功能只能福特后台管理人员开启 |  | N | Y | D |  | CVPP | AT_001 |  | Jerry JI | 李大青 | Jerry JI | N |  |  |  | N |  |  |  |  | N | N | N | N
SYNC+_0340 | Connected Service | Theft prevention | 防盗提醒 Anti-theft reminder |  | - 用户手动按下SOS硬按键，通过Tbox拨打救援中心，同时上传车辆位置数据 - 呼叫中心根据车辆位置、通话信息组织救援 |  | N | N | B |  | CVPP | AT_002 |  | Jerry JI | 李大青 | Jerry JI | N |  |  |  | N |  |  |  |  | N | N | N | N
SYNC+_0341 | IVI System Function | System Settings - Notification | 消息&消息中心 notification & notification center | 消息： - 消息展示方式：消息体、消息中心、状态栏的消息状态提醒 - 样式定义：消息体、状态提醒的样式 - 消息展示规则、优先级与冲突机制处理 消息中心： - 各种消息的接收、存储、查看 |  |  | U | Y | B |  | IVI | NOT_001 | 160 | Wang, Fin (X.Y.) | 李大青 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0342 | Maintenance and Insurance | Reminder | 保养提醒信息推送 Voice and Message Center Push | 保养提醒信息推送 Voice and Message Center Push-主动语音推送 Active voice reminder |  |  | y | y | B | Phase 4: 保养及在线预约/Vehicle Maintenance and the service booking | CVPP | MAIN_001 | 274 | Wang, Johnny (J.) | 李大青 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0343 | Maintenance and Insurance | Reminder | 保养提醒信息推送 Voice and Message Center Push | 保养提醒信息推送 Voice and Message Center Push-消息中心推送 Push notification |  |  | y | y | B | Phase 4: 保养及在线预约/Vehicle Maintenance and the service booking | CVPP | MAIN_002 | 275 | Wang, Johnny (J.) | 李大青 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0344 | Maintenance and Insurance | Maintenance | 保养在线预约 OSB | 保养在线预约 OSB-车辆健康状况 Vehicle health rating |  |  | y | y | B | Phase 4: 保养及在线预约/Vehicle Maintenance and the service booking | CVPP | MAIN_003 | 276 | Wang, Johnny (J.) | 刘建立 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0345 | Maintenance and Insurance | Maintenance | 保养在线预约 OSB | 保养在线预约 OSB-建议保养项目 Recommended maintenance item |  |  | y | y | B | Phase 4: 保养及在线预约/Vehicle Maintenance and the service booking | CVPP | MAIN_004 | 276 | Wang, Johnny (J.) | 刘建立 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0346 | Maintenance and Insurance | Maintenance | 保养在线预约 OSB | 保养在线预约 OSB-保养预约 Service booking |  |  | y | y | B | Phase 4: 保养及在线预约/Vehicle Maintenance and the service booking | CVPP | MAIN_005 | 276 | Wang, Johnny (J.) | 刘建立 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0347 | Maintenance and Insurance | Maintenance | 保养在线预约 OSB | 保养在线预约 OSB-订单查询 order inquiry |  |  | y | y | B | Phase 4: 保养及在线预约/Vehicle Maintenance and the service booking | CVPP | MAIN_006 | 276 | Wang, Johnny (J.) | 刘建立 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0348 | Maintenance and Insurance | Maintenance | 经销商功能 Dealer function | 保养信息重置 Maintenance reset |  | feature 115 | y | n | B | Phase 4: 保养及在线预约/Vehicle Maintenance and the service booking | CVPP | MAIN_007 | 277 | Wang, Johnny (J.) | 李大青 | Wang, Johnny (J.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0349 | Personalization & Accounts | One ID Account | 登陆、注册 register & login | 登陆、注册 register & login |  |  | u | y | B |  | CVPP | SET_001 | 161 | Wang, Johnny (J.) | 李大青 | Wang, Johnny (J.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0350 | Personalization & Accounts | One ID Account | 账号互通 account binding | 账号互通 account binding |  |  | u | y | B |  | CVPP | SET_002 | 162 | Wang, Johnny (J.) | 李大青 | Wang, Johnny (J.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0351 | Personalization & Accounts | Customer Profile | 流量套餐app端流量查询购买 data plan query & oder | 流量套餐app端流量查询购买 data plan query & oder |  |  | u | y | B |  | CVPP | SET_003 | 163 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0352 | Personalization & Accounts | Customer Profile | 流量套餐对实名认证RNR的支持 | 流量套餐对实名认证RNR的支持 |  |  | u | y | B |  | CVPP | SET_003 | 163 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | N |  |  |  | N |  |  |  |  | N | Y | Y | Y
SYNC+_0353 | Personalization & Accounts | Customer Profile | 流量管理 | 流量管理 |  |  | u | y | B |  | CVPP | SET_012 | 1188 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0354 | IoT | Smart Home | 我的智能家居（入口） access to my smart home | 我的智能家居（入口） access to my smart home |  |  | U | Y | B | IN PHASE 4: 智能家居/Intelligent Home Control Home to Car | CVPP | SET_004 | 164 | Lu Chao | 李大青 | Lu Chao | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0355 | Personalization & Accounts | One ID Account | 关于（声明）desclaimer | 关于（声明）desclaimer |  | line 217，需加入feature list | u | n | B |  | CVPP | SET_005 | 165 | Wang, Johnny (J.) | 李大青 | Wang, Johnny (J.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0356 | Personalization & Accounts | One ID Account | RNR | RNR |  | Feature ID 179 | y | n | B |  | CVPP | SET_011 | 189 | Wang Yuran | 李大青 | Wang Yuran | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0357 | Social & Operation Services | Social APP | 福特/林肯金融 | 账务记录 |  |  | U | y | B |  | CVPP | SET_012 |  | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | N
SYNC+_0358 | Social & Operation Services | Online Mall | Online Mall | 在线商城 |  |  | U | y | B |  | CVPP | SET_006 |  | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | N |  |  |  | N | N | N | N | N | N | N | N | N | Y
SYNC+_0359 | Social & Operation Services | Payment & Wallet | 我的钱包 | 订单中心 order center |  |  | U | y | B |  | CVPP | SET_007 | 167 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0360 | Social & Operation Services | Payment & Wallet | 我的钱包 | 账单 |  |  | U | y | B |  | CVPP | SET_008 | 168 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0361 | Social & Operation Services | Payment & Wallet | 我的钱包 | 聚合收银台 |  |  | U | y | B |  | CVPP | SET_009 | 169 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0362 | Social & Operation Services | Payment & Wallet | 我的钱包 | 支付设置 |  |  | U | y | B |  | CVPP | SET_010 | 170 | Lu, Chao (C.) | 李大青 | Lu, Chao (C.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0363 | IVI System Function | Preset APP | 订阅管理 subscription management | 订阅管理 subscription management |  |  | NA | N | N |  | IVI | SUB_001 |  |  | 李大青 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0364 | IVI System Function | Preset APP | 安装/运行福特指定的第三方软件/VP硬件对应的软件 | Baidu: 推荐PJ1用OTA方式推一个应用程序接口。 |  |  | N | Y | B |  | IVI | 3RD_001 | 281 | Justin Li | 李大青 | Justin Li | N |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0365 | IVI System Function | Preset APP | 应用市场 APP store | 应用市场 APP store |  |  | NA | N | N |  | IVI | T1_001 |  |  | 李大青 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0366 | IVI System Function | Preset APP | 文件管理器 file manager | 文件管理器 file manager |  |  | U | Y | D |  | IVI | T1_003 |  |  | 李大青 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0367 | IVI System Function | System Setting - Others | Infotainment Diagnostic Spec- Speaker walk around 挨个喇叭发出声音（工程模式下显示） | Infotainment Diagnostic Spec- Speaker walk around 挨个喇叭发出声音（工程模式下显示） |  |  | Y | Y | D |  | IVI | VEH_001 | 318 | Wang, Fin (X.Y.) | 李大青 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0368 | Vehicle Function | IVI Support Vehicle Function | Vehicle Setting | 车辆设置 |  |  | Y | I | D | Ford Vehicle Settings On IVI | IVI | VEH_002 | 171 | Wang, Fin (X.Y.) | 李大青 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0369 | Vehicle Function | IVI Support Vehicle Function | TCS off | Soft button design（设计成软按键） |  |  | Y | I | D | Ford Vehicle Settings On IVI | IVI-Distribute DAT | VEH_003 | 172 | Tao He | 李大青 | Tao He | Y |  |  |  | Y |  |  |  | N | Y | Y | N | N | Y
SYNC+_0370 | Vehicle Function | IVI Support Vehicle Function | SDM button | (hard button only) | 正常驾驶 运动驾驶 经济驾驶 |  | Y | Y | D |  | IVI-Distribute DAT | VEH_004 | 173 | Tao He | 李大青 | Tao He | Y |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0371 | Vehicle Function | IVI Support Vehicle Function | Speed compensated volume 根据车速调整音量 | Speed compensated volume 根据车速调整音量 |  | add in Phase4 feature list line 226 | Y | N | D |  | IVI | VEH_005 | 174 | Yu, Justin (Y.Z.) | 李大青 | Yu, Justin (Y.Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0372 | Vehicle Function | IVI Support Vehicle Function | Rear view camera | 普通倒车视频 | No change, keep CVBS input |  | Y | Y | D |  | IVI-Distribute DAT | VEH_006 | 175 | Zheng, Tina (T.) | 李大青 | Zheng, Tina (T.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0373 | Vehicle Function | IVI Support Vehicle Function | Camera on demand | Camera快捷键 |  | add in Phase4 feature list line 227 | U | N | D | SHORTCUT KEY? | IVI-Distribute DAT | VEH_030 | 319 | Zheng, Tina (T.) | 李大青 | Zheng, Tina (T.) | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0374 | Vehicle Function | IVI Support Vehicle Function | Digital RVC | 数码RVC |  |  | Y | Y | D |  | IVI-Distribute DAT | VEH_029 | 282 | Zheng, Tina (T.) | 李大青 | Zheng, Tina (T.) | N |  |  |  | N |  |  |  | TBD | Y | N | N | Y | Y
SYNC+_0375 | Vehicle Function | IVI Support Vehicle Function | Park aid visual display (incl front rear and side) | 雷达显示 |  |  | Y | Y | D |  | IVI-Distribute DAT | VEH_007 | 176 | He, Michael (X.) | 李大青 | He, Michael (X.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0376 | Vehicle Function | IVI Support Vehicle Function | Rear camera delay | 倒车视频设置 |  |  | Y | I - SETTING | D | SETTING | IVI-Distribute DAT | VEH_008 | 177 | Zheng, Tina (T.) | 李大青 | Zheng, Tina (T.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0377 | Vehicle Function | IVI Support Vehicle Function | Cross Traffic Alert | 侧向来车预警HMI功能 |  |  | Y | Y | D | SETTING OR WARNING? | IVI-Distribute DAT | VEH_009 | 178 | Zhang, Isaac (S.) | 李大青 | Zhang, Isaac (S.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0378 | Vehicle Function | IVI Support Vehicle Function | Multi contour seat-Multi contour seat-Seat massage | Multi contour seat-Multi contour seat-Seat massage | 座椅按摩 |  | Y | Y | D |  | IVI-Distributed BS | VEH_010 | 179 | Xu Xiaokang | 陈冰 | Xu Xiaokang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0379 | Vehicle Function | IVI Support Vehicle Function | Multi contour seat-Custom Massage Patterns HMI for Multi-Contour Seats (U611) | Custom Massage Patterns HMI for Multi-Contour Seats (U611) |  |  | Y | Y | D |  | IVI-Distributed BS | VEH_031 | 320 | Xu Xiaokang | 陈冰 | Xu Xiaokang | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0380 | Vehicle Function | IVI Support Vehicle Function | Multi contour seat-Seat adjust | Seat adjust | 座椅调节 |  | U | Y | D |  | IVI-Distributed BS | VEH_011 | 180 | Xu Xiaokang | 陈冰 | Xu Xiaokang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0381 | IVI System Function | System Setting - Others | Disclaimer | 声明 | Content to be aligned with CVPP and baidu | add in Phase4 feature list line 228 | Y | N | D |  | IVI | VEH_012 | 181 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0382 | Vehicle Function | IVI Support Vehicle Function | Auto Dim | 自动灯光变暗 |  |  | Y | Y | D | Illumination | IVI | VEH_013 | 182 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0383 | IVI System Function | System Setting - Display | Brightness | 亮度 |  |  | Y | Y | D |  | IVI | VEH_014 | 183 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0384 | IVI System Function | System Setting - Display | Calm Screen | 精简屏幕 - 提供预置背景图片供用户选择 |  | line217需加入feature list | U | N | B |  | HMI | VEH_015 | 184 | Xiao, Yun (Y.) | 陈冰 | Xiao, Yun (Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0385 | IVI System Function | System Setting - Display | Display off | 关闭屏幕 |  | line218，需加入feature list | Y | N | B |  | IVI | VEH_016 | 185 | Wang, Fin (X.Y.) | 陈冰 | Wang, Fin (X.Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0386 | Vehicle Function | IVI Support Vehicle Function | Wireless Charging notification | 无线充电提示 |  |  | U | Y | B |  | IVI | VEH_017 | 186 | Lyu, Qingtao (Q.) | 陈冰 | Lyu, Qingtao (Q.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0387 | Vehicle Function | IVI Support Vehicle Function | UFC Lite notification | 空气净化状态提示 |  |  | Y | Y | D |  | IVI-Distribute DI | VEH_018 | 187 | Yao, Frank/DongYa | 陈冰 | N/A | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0388 | IVI System Function | System Setting - Others | Authorization. Refer to current sync 3 | Authorization. Refer to current sync 3 |  |  | U | y | D |  | CVPP | VEH_019 | 188 | Ge Grace/Luk Francis | 陈冰 | Ge Grace/Luk Francis | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0389 | IVI System Function | System Setting - Others | CCS (customer setting) around data sharing (i.e. location) | CCS (customer setting) around data sharing (i.e. location) |  |  | U | y | D |  | CVPP | VEH_021 | 190 | Ge Grace | 陈冰 | Ge Grace | Y |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
SYNC+_0390 | IVI System Function | System Setting - Others | Single account login | Single account login |  |  | U | y | B |  | CVPP | VEH_022 | 191 | Wang, Johnny (J.) | 陈冰 | Wang, Johnny (J.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0391 | IVI System Function | System Setting - Others | First Mile Navigation/Last Mile Navigation/Vehicle locator | First Mile Navigation/Last Mile Navigation/Vehicle locator |  |  | U | y | B |  | CVPP | VEH_023 | 198 | Shi Stella/Lu Chao | 陈冰 | Shi Stella/Lu Chao | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0392 | IVI System Function | System Setting - Others | Online music (tier1 proposal) | Online music (tier1 proposal) |  |  | U | Y | B |  | IVI | VEH_025 | 75 | Xiang, Zhengxi (Z.) | 陈冰 | Xiang, Zhengxi (Z.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0393 | IVI System Function | Preset APP | 在线视频播放 Online Video(aiqiyi) | 在线视频播放 Online Video(aiqiyi) | User could view the online video streaming thru apps. Meanwhile this online video feature needs to be restricted by vehicle speed. Detailed speed threshold TBD |  | U | Y | B |  | IVI | VEH_026 | 103 | Alvin Li | 陈冰 | Alvin Li | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0394 | Vehicle Function | IVI Support Vehicle Function | CAQ(Cabin Air Quality) | CAQ(Cabin Air Quality) |  | feature 147，需加入feature list | Y | N | B |  | CVPP-Distributed DI | VEH_027 | 199 | Tong Tian | 陈冰 | Tong Tian | Y |  |  |  | Y |  |  |  |  | N | N | N | N | Y |  |  |  | Phase3, Refer to AAR
SYNC+_0395 | IVI System Function | System Setting - Others | Driving restriction | Driving restriction | To Stop/cancel video playing when condition not correct. | 涵盖在功能中？ | U | N | B |  | IVI | VEH_028 | 328 | Li, Alvin (L.) | 陈冰 | Li, Alvin (L.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0396 | IVI System Function | Audio System | Active Noise Cancellationg (ANC) Tuning | Active Noise Cancellationg (ANC) Tuning | ANC/ESE Tuning |  | Y | Y | D |  | IVI | TUNE_001 | 283 | Tian, Chen (C.) / Song, Rui (Rex.) | 陈冰 | Tian, Chen (C.) / Song, Rui (Rex.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0397 | IVI System Function | Audio System | Engine Sound Enhancement (ESE) | Engine Sound Enhancement (ESE) | ESE Tuning |  | Y | Y | D |  | IVI | TUNE_006 | 284 | Tian, Chen (C.) / Song, Rui (Rex.) | 陈冰 | Tian, Chen (C.) / Song, Rui (Rex.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0398 | IVI System Function | Audio System | A2B Functional | A2B Functional |  |  | Y | Y | D |  | IVI | TUNE_002 | 329 | Tian, Chen (C.) / Song, Rui (Rex.) | 陈冰 | Tian, Chen (C.) / Song, Rui (Rex.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0399 | IVI System Function | Audio System | Brand Audio | Brand Audio |  |  | U | Y(include in "Revel QLI 3D Audio (Audio System, ANC/ESE tuning)") | D |  | IVI | TUNE_007 |  | Tian, Chen (C.) / Song, Rui (Rex.) | 陈冰 | Tian, Chen (C.) / Song, Rui (Rex.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0400 | IVI System Function | Audio System | Noise cancellation for Baidu VR | Noise cancellation for Baidu VR |  |  | N | Y | B |  | IVI | TUNE_003 |  | Gao, Yue (Y.) | 陈冰 | Gao, Yue (Y.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0401 | IVI System Function | Audio System | Radio reception test | Radio reception test |  |  | N | Y | D |  | IVI | TUNE_004 |  | Wu, Andy (Z.J.) | 陈冰 | Wu, Andy (Z.J.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0402 | IVI System Function | Audio System | EQ tool | EQ tool |  | add in Phase4 feature list line 229 | Y | N | D | banlence and fade? | IVI | TUNE_005 | 330 | Pan, Donghai (Paul.) | 陈冰 | Pan, Donghai (Paul.) | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0403 | IVI System Function | MCU features | FNOS | FNOS |  |  | U | Y | D |  | IVI-Distributed System | MCU_001 | 192 | Zhu, Jing Yuan (J.) /Fin Wang | 陈冰 | Zhu, Jing Yuan (J.) /Fin Wang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0404 | Vehicle Function | MCU features | Illumination | Illumination |  |  | Y | Y | D |  | IVI-Distributed System | MCU_002 | 193 | Wu Bella/ Justin Yu | 陈冰 | Wu Bella/ Justin Yu | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0405 | IVI System Function | MCU features | Infotainment Diagnostic Spec | Infotainment Diagnostic Spec |  |  | U | Y | D |  | IVI-Distributed System | MCU_003 |  | Zhu, Jing Yuan (J.) /Fin Wang | 陈冰 | Zhu, Jing Yuan (J.) /Fin Wang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0406 | IVI System Function | MCU features | MCU software download (via CAN) | MCU software download (via CAN) |  |  | N | U | D |  | IVI-Distributed System | MCU_004 | 194 | Zhu, Jing Yuan (J.) /Fin Wang | 陈冰 | Zhu, Jing Yuan (J.) /Fin Wang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0407 | IVI System Function | MCU features | RNR | RNR |  |  | U | Y(include in"Real Name Register") | B |  | IVI-Distributed System | MCU_005 | 195 | Zhu, Jing Yuan (J.) /Fin Wang | 陈冰 | Zhu, Jing Yuan (J.) /Fin Wang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0408 | IVI System Function | MCU features | Power management | Power management |  |  | U | Y | D |  | IVI-Distributed System | MCU_006 | 196 | Zhu, Jing Yuan (J.) /Fin Wang | 陈冰 | Zhu, Jing Yuan (J.) /Fin Wang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0409 | IVI System Function | MCU features | CAN signals （contain carry over signals） | CAN signals （contain carry over signals） |  |  | N | Y | D |  | IVI-Distributed System | MCU_007 | 197 | Zhu, Jing Yuan (J.) /Fin Wang | 陈冰 | Zhu, Jing Yuan (J.) /Fin Wang | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0410 | Maintenance and Insurance | User Manual & Guidance | Digital user tuturial which customer could view and interact with IVI screen content directly.(from paper to IVI screen) | 在线可更新. |  | line 219，需加入feature list | y | n | B | IVI manual or vehicle manual? | CVPP | DOM_001 | 201 | Zhou Calvin | 陈冰 | Zhou Calvin | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0411 | Connected Service | Carrier | SIM Management SIM卡管理 | SIM卡数据，账号，通信能力和连接性，Rate Plan，data packages等 |  | line 223-226，需加入feature list | U | n | B |  | CVPP | TEL_001 |  | Wang, Yuran | 李大青 | Wang, Yuran | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0412 | Connected Service | Carrier | RNR | RNR |  |  | U | y | B |  | CVPP | TEL_002 |  | Pan Yuan | 李大青 | Pan Yuan | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0413 | Connected Service | Carrier | Carrier Backend Development 运营商后台开发 | associate 1 VIN with 2 SIMs; RNR platform; Online Mall; Jasper/M2M portal; Per APP billing, etc. |  |  | U | n | B |  | CVPP | TEL_003 |  | Wang, Yuran | 李大青 | Wang, Yuran | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0414 | Connected Service | Carrier | API integration with Baidu 与百度的接口集成 | retail data plan API, data usage query API, order API, payment API, invoice API, usage notification API, etc. |  |  | U | n | B |  | CVPP | TEL_004 |  | Wang, Yuran | 李大青 | Wang, Yuran | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0415 | Connected Service | Carrier | API integration with FORD 与福特的接口集成 | retail data plan API, data usage query API, order API, payment API, usage notification API, etc. |  |  | U | n | B |  | CVPP | TEL_005 |  | Wang, Yuran | 李大青 | Wang, Yuran | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0416 | Maintenance and Insurance | User Report & Feedback | 用户反馈Customer Feedback | [产品阶段] |  |  | y | y | B | Phase 4: 保养及在线预约/Vehicle Maintenance and the service booking | CVPP | CUST_002 | 285 | Wang, Johnny (J.) | 李大青 | Wang, Johnny (J.) | Y |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0417 | IVI System Function | Preset APP | 网页浏览器 Internet Brower | Internet browser presents customer the ability to surf the internet. The browser should preload some popular websites for customer to easily get access to. Customer is also able to type in the web address or use voice command to navigate to the webpages he / she wants to browse. The browser should support multi-tab view mode and be associated with other IVI features like phone, media player, navigation…etc. Driving restrictions should be considered for this feature |  |  | N | N | N |  | IVI | BRO_001 |  |  | 李大青 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N
SYNC+_0418 | Vehicle Function | Mykey | Settings-Volume limiter | Settings-Volume limiter |  |  | Y | I - SETTING | D |  | IVI-Distributed System | LINMK_001 | 287 | Xu Xiao Kang | 陈冰 | Xu Xiao Kang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0419 | Vehicle Function | Mykey | Settings-My key status | Settings-My key status |  |  | Y | I - SETTING | D |  | IVI-Distributed System | LINMK_002 | 287 | Xu Xiao Kang | 陈冰 | Xu Xiao Kang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0420 | Vehicle Function | Mykey | Settings-Create my key | Settings-Create my key |  |  | Y | I - SETTING | D |  | IVI-Distributed System | LINMK_003 | 287 | Xu Xiao Kang | 陈冰 | Xu Xiao Kang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0421 | Vehicle Function | Mykey | Settings-Clear my keys | Settings-Clear my keys |  |  | Y | I - SETTING | D |  | IVI-Distributed System | LINMK_004 | 287 | Xu Xiao Kang | 陈冰 | Xu Xiao Kang | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0422 | Vehicle Function | Shortcut Keys | Lincoln Park Assist Shortcut key | Lincoln Park Assist Shortcut key-Park aid on off | hard button trigger LPA screen | desay负责功能开发，baidu支持HMI页面 | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINPA_001 | 288 | He, Michael (X.) | 陈冰 | He, Michael (X.) | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0423 | Vehicle Function | Shortcut Keys | Lincoln Park Assist Shortcut key | Lincoln Park Assist Shortcut key-Autoparking |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINPA_002 | 288 | He, Michael (X.) | 陈冰 | He, Michael (X.) | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0424 | Vehicle Function | Shortcut Keys | U625 Park Assist Shortcut key-PA button in U625 | U625 Park Assist Shortcut key-PA button in U625 | Trigger front BPA from short cut key in HMI |  | NA | NA | N |  |  | FORDPA_001 |  |  | 陈冰 |  | N |  |  |  | N |  |  |  | N | N | N | N | N | N |  |  |  | Del
SYNC+_0425 | Vehicle Function | Shortcut Keys | Lincoln Camera Shortcut key | Lincoln Camera Shortcut key-360, standard rear, etc, Includes all HMI views |  |  | Y | I - Shortcut | D |  | IVI-Distribute DAT | LINCAM_001 | 290 | Zheng, Tina (T.) | 陈冰 | Zheng, Tina (T.) | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0426 | Vehicle Function | Shortcut Keys | Lincoln Seats shortcut key | Lincoln Seats shortcut key-4 or 2 way lumbar |  |  | Y | I - Shortcut | D |  | IVI-Distributed BS | LINSEAT_001 | 322 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0427 | Vehicle Function | Shortcut Keys | Lincoln Seats shortcut key | Lincoln Seats shortcut key-Lincoln unique MCS seats and seat adjustment |  |  | Y | I - Shortcut | D |  | IVI-Distributed BS | LINSEAT_002 | 322 | Zhu, Jing Yuan (J.) | 陈冰 | Tao He | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0428 | Vehicle Function | Shortcut Keys | Climate (menu and rear shortcut keys) | Climate (menu and rear shortcut keys)-Rear- Tri or Quad Zone climate |  |  | Y | I - Shortcut | D |  | IVI-Distribute DI | LINCLI_001 | 291 | Yao, Frank/DongYa | 陈冰 | N/A | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0429 | Vehicle Function | Shortcut Keys | Climate (menu and rear shortcut keys) | Climate (menu and rear shortcut keys)-Auto Air Refresh (AAR) |  |  | Y | I - Shortcut | D |  | IVI-Distribute DI | LINCLI_002 | 292 | Yao, Frank/DongYa | 陈冰 | N/A | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0430 | Vehicle Function | Shortcut Keys | Climate (menu and rear shortcut keys) | Climate (menu and rear shortcut keys)-climate in rear display |  |  | Y | I - Shortcut | D |  | IVI-Distribute DI | LINCLI_003 | 293 | Yao, Frank/DongYa | 陈冰 | N/A | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0431 | Lincoln Features | Lincoln Audio | Speakers Config | Up to 14 speakers. | Up to 14 speakers. Revel with QLI |  | Y | Y | D |  | IVI | LINAUD_001 | 294 | Rex Song | 陈冰 | Rex Song | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0432 | Lincoln Features | Lincoln Audio | Speakers Config | Lincoln more speakers audio & ANC tuning. | Lincoln more speakers audio & ANC tuning. Revel QLI |  | Y | Y | D |  | IVI | LINAUD_004 | 295 | Rex Song | 陈冰 | Rex Song | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0433 | Lincoln Features | Lincoln Audio | Rear Audio Controls | Rear Audio Controls | Touch screen U611 | add in Phase4 feature list line 230 | U | N | D | ??? | IVI | LINAUD_002 | 296 | Rex Song | 陈冰 | Rex Song | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0434 | Lincoln Features | Lincoln Audio | Branded HMI | Branded HMI | Lincoln Branded Audio |  | N | N | B |  | HMI | LINAUD_003 | 297 | Xiao, Yun (Y.) | 陈冰 | Xiao, Yun (Y.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0435 | Lincoln Features | Lincoln Parking | Fully automated park assist (hard button/HMI) | Fully automated park assist (hard button/HMI) |  |  | Y | Y | D |  | DAT | LINP_001 | 298 | He, Michael (X.) | 陈冰 | He, Michael (X.) | N |  |  |  | N |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0436 | Personalization & Accounts | Customer Profile | Enhanced memory-Memory and Profile | Enhanced memory-Memory and Profile |  |  | y | y | D |  | CVPP-Distribute System | LINEM_001 | 299 | Wang, Johnny (J.) /Xu Xiao Kang | 陈冰 | Wang, Johnny (J.) /Xu Xiao Kang | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0437 | Personalization & Accounts | Customer Profile | Enhanced memory-Seat settings, etc tied to profile | Enhanced memory-Seat settings, etc tied to profile |  |  | y | y | D |  | CVPP-Distribute System | LINEM_002 | 300 | Wang, Johnny (J.) /Xu Xiao Kang | 陈冰 | Wang, Johnny (J.) /Xu Xiao Kang | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0438 | Vehicle Function | Remote Control | Phone as key(PaaK) | Phone as key(PaaK) | Regular PAAK |  | y | Y | B |  | CVPP-Distribute System | LINKL_001 | 302 | Wang, Cindy (X.J.) /Joey Chen | 陈冰 | Wang, Cindy (X.J.) /Joey Chen | N |  |  |  | Y |  |  |  |  | Y | N | Y | Y | Y
SYNC+_0439 | Vehicle Function | Remote Control | Phone as key(PaaK) | Phone as key(PaaK) | Lite Version for CD539ICA |  | u | Y | B |  | CVPP-Distribute System | LINKL_001 | 302 | Wang, Cindy (X.J.) /Joey Chen | 陈冰 | Wang, Cindy (X.J.) /Joey Chen | N |  |  |  | N |  |  |  |  | N | Y | N | N | Y
SYNC+_0440 | Vehicle Function | Remote Control | Temporary key（Valet Mode） | Temporary key（Valet Mode） | Valet Mode与Temporary key是同一功能，在DuerOS中更名为智能临时密钥 Temporary key | 德赛 | y | y | D | include in "PaaK" | CVPP-Distribute System | LINKL_002 | 377 | Daniel Li | 陈冰 | Daniel Li | N |  |  |  | N | N |  |  | N | N | N | N | N | Y
SYNC+_0441 | Lincoln Features | Lincoln Chimes | Lincoln Chimes | Detroit Symphony Orchestra chimes |  |  | Y | Y | D |  | IVI | LINSOU_001 | 304 | TBD Daniel Li | 陈冰 | Daniel Li | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0442 | Vehicle Function | IVI Support Vehicle Function | Welcome and farewell | Coorindated animations with rear display & Cluster |  |  | Y | Y | B |  | IVI-Distributed System | LINEMB_001 | 305 | Bella Wu | 陈冰 | Bella Wu | Y |  |  |  | Y |  |  |  | Y | Y | Y | Y | Y | Y
SYNC+_0443 | Electric Vehicle | PHEV Setting | Charge Settings | Charge Status, Charge Time Settings, Departure Time Settings |  |  | Y | Y | B |  | EPE | PHEV_001 | 306 | Dean Wu | 陈冰 | Dean Wu | N |  |  |  | Y |  |  |  | N | Y | N | Y | N | N
SYNC+_0444 | Electric Vehicle | PHEV Setting | Charge Location | Charge Location |  |  | Y | Y | B |  | EPE | PHEV_002 | 306 | Dean Wu | 陈冰 | Dean Wu | N |  |  |  | Y |  |  |  | N | Y | N | Y | N | N
SYNC+_0445 | Electric Vehicle | PHEV Setting | Preferred Charge Time | Preferred Charge Time |  |  | Y | Y | B |  | EPE | PHEV_003 | 306 | Dean Wu | 陈冰 | Dean Wu | N |  |  |  | Y |  |  |  | N | Y | N | Y | N | N
SYNC+_0446 | Electric Vehicle | PHEV Setting | Departure Time | Departure Time |  |  | Y | Y | B |  | EPE | PHEV_004 | 306 | Dean Wu | 陈冰 | Dean Wu | N |  |  |  | Y |  |  |  | N | Y | N | Y | N | N
SYNC+_0447 | Electric Vehicle | PHEV Setting | Station Finder | 在地图上寻找充电地方 |  |  | Y | Y | B |  | EPE | PHEV_005 | 306 | Dean Wu | 陈冰 | Dean Wu | N |  |  |  | Y |  |  |  | N | Y | N | Y | N | N
SYNC+_0448 | Electric Vehicle | PHEV Setting | Power Flow | Power Flow |  |  | Y | Y | D |  | EPE | PHEV_006 | 306 | Dean Wu | 陈冰 | Dean Wu | N |  |  |  | Y |  |  |  | N | Y | N | Y | N | N
SYNC+_0449 | Electric Vehicle | PHEV Setting | Charge Port Light Settings | On：Illuminates when plugging in，opening doors， pressing the unlock button on your remote and while charging. Off：Does not illuminate. Limited：Illuminates only when plugging in，opening doors，or pressing the unlock button on your remote. CD391PHEV 有三个选项 : “ on, off & Limited” U6xx只有两个选项“on，off” |  | add in Phase4 feature list line 231 | Y | N | D | EV feature | CVPP/EPE | PHEV_008 | 306 | Dean Wu | 陈冰 | Dean Wu | N |  |  |  | Y |  |  |  | N | Y | N | Y | N | N
SYNC+_0450 | Electric Vehicle | PHEV Setting | Charge Conflict Notification Popups | Charge Conflict Notification Popups |  | add in Phase4 feature list line 232 | Y | N | D | EV feature | CVPP/EPE | PHEV_010 | 306 | Dean Wu | 陈冰 | Dean Wu | N |  |  |  | Y |  |  |  | N | Y | N | Y | N | N
SYNC+_0451 | Electric Vehicle | PHEV Setting | Range Ring-Nav Screen | Range Ring-Nav Screen |  |  | Y | N | B |  | EPE | PHEV_011 | 306 | Dean Wu | 陈冰 | Dean Wu | N |  |  |  | Y |  |  |  | N | Y | N | N | N | N
SYNC+_0452 | Driver Assist | Reverse Brake Assist (RBA) | Reverse brake assist | Reverse brake assist |  |  | Y | Y | D |  | IVI-Distribute DAT | RBA_001 | 307 | Zheng, Tina (T.) | 陈冰 | Zheng, Tina (T.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0453 | Lincoln Features | Lincoln HMI | A few lincoln sepcific animations | A few lincoln sepcific animations |  |  | N | N | B |  | HMI | LINANI_001 | 308 | Xiao, Yun (Y.) | 陈冰 | Xiao, Yun (Y.) | N |  |  |  | Y |  |  |  | Y | Y | N | Y | Y | Y
SYNC+_0454 | Navigation | Navigation - Intelligent function | EH | TSR Fusion/ADAS MAP |  |  | Y | Y | B |  | DAT | EH_001 | 309 | Cindy Li | 陈冰 | Cindy Li | N |  |  |  | Y-u611 |  |  |  | N | Y | N | N | Y | N
SYNC+_0455 | Social & Operation Services | Online Mall | Online Mall 在线商城 | 在线商城支付的功能。 |  | line 220，需加入feature list | U | n | B |  | CVPP | OM_001 | 310 | Lu, Chao (C.) | 陈冰 | Lu, Chao (C.) | N |  |  |  | N | N | N | N | N | N | N | N | N | Y
SYNC+_0456 | Navigation | Navigation - Intelligent function | LHI (Local Hazard Information) | LHI (Local Hazard Information) | 危险事件上报及播报 |  | Y | Y | B |  | CVPP | LHI_001 | 379 | Lin Shawn | 陈冰 | Lin Shawn | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y | Y
SYNC+_0457 | Navigation | AR navigation | AR navigation |  |  |  | Y | Y | B |  | IVI |  |  | Gao, Yue (Y.) | [11 empty] | N | N | N | Y
SYNC+_0458 | In-Cabin Image Recognition | Face ID | Canbin Image Recognition |  |  |  | NA | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y |  |  |  |  | Duplicate,Del,Refer to the Face ID spec in Phase3
SYNC+_0459 | IVI System Function | Preset APP | Digital scent |  |  | add in Phase4 feature list line 233 | Y | N | D | Lincoln only,Ford development ,DESAY integrate | PMT5 |  |  | Zhang XiaoJiang | [11 empty] | N | N | Y | Y
SYNC+_0460 | IVI System Function | Preset APP | E-Manual Book |  |  |  | U | Y | D | Ford development ,DESAY integrate | IVI |  |  | Geng DeKang |  |  | N |  |  |  | Y |  |  |  |  | Y | Y | Y | Y
SYNC+_0461 | Voice Recognition | Voice Recognition Service | Multi Zone |  |  |  | N | Y | B |  | IVI |  |  | Wang Jingjing | [11 empty] | N | N | N | Y
SYNC+_0462 | IVI System Function | System UI & HMI | 13.2 inch Landscape HMI | 13.2' Landscape Launcher main cards |  | line 209，需加入feature list | Y | n | B |  | HMI | [14 empty] | N | Y | N | N
SYNC+_0463 | IVI System Function | System UI & HMI | 13.2 inch Landscape HMI | 13.2' Landscape Luanch domain cards |  |  | Y | n | B |  | HMI | [14 empty] | N | Y | N | N
SYNC+_0464 | IVI System Function | System UI & HMI | 13.2 inch Landscape HMI | 13.2' Landscape Luanch persisten bar |  |  | Y | n | B |  | HMI |  |  | Xiao, Yun (Y.) | [11 empty] | N | Y | N | N
SYNC+_0465 | IoT | V2X | V2I Funcion |  |  |  | U | Y | B |  | CVPP |  |  | Henry Fan |  |  | N |  |  |  | N |  |  |  |  | N | Y | Y | Y |  |  |  |  | Yes for PHASE 3. Explained feature in meetings. Three parties will review detail PRD documents later.
SYNC+_0466 | Voice Recognition | VPA | VPA Function |  |  |  | U | Y | B |  | CVPP |  |  | Ren SiYuan(Alex) |  |  | N |  |  |  | N |  |  |  |  | N | Y | Y | Y |  |  |  |  | Yes for PHASE 3. Explained feature in meetings. Three parties will review detail PRD documents later.
SYNC+_0467 | IVI System Function | Preset APP | TikTok on DuerOS |  |  | line 221，需加入feature list | Y | N | B |  | CVPP |  |  | Shi Stella |  |  | N |  |  |  | N |  |  |  |  | N | Y | Y | Y
SYNC+_0468 | IoT | Smart Home | Home to Vehicle Software platform, including 1. fuel status query 2. Remote Control lighting/horn 3. Remote start engine/AC |  |  |  | U | y | B | IN PHASE 4: 智能家居/Intelligent Home Control Home to Car | CVPP |  |  | Lu Chao |  |  | N |  |  |  | Y(Delayed) |  |  |  |  | Y | Y | Y | Y |  |  |  |  | This feature is covered in phase 2 signed MA doc as attached feature list.
SYNC+_0469 | MCU OTA | MCU features |  |  |  |  | U | Y | D |  | CVPP |  |  | Pan, Yuan (Y.) | [6 empty] | Y | Y |  |  | Y | Y | Y | Y | Y
SYNC+_0470 | Driver Assist | RVC | IVI 绘制动态辅助线 |  |  |  | U | Y | D | new request should c/o to phase 4 | [15 empty] | N | Y | Y | Y
SYNC+_0471 | Driver Assist | RVC | RVC 叠加AR BPA |  |  |  | U | Y | D | new request should c/o to phase 4 | [15 empty] | N | Y | Y | Y |  |  |  |  | Ford releases the detailed Spec to YFVE/Baidu--Fin
SYNC+_0472 | In-Cabin Image Recognition | Multimode interaction | 随心听场景-OK手势-开始播放DuMedia scene-OK Gesture-start to play |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0473 | In-Cabin Image Recognition | Multimode interaction | 随心听场景-比嘘手势-暂停播放DuMedia scene-Slience Gesture-pause to play |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0474 | In-Cabin Image Recognition | Multimode interaction | 随心听场景-点赞手势-收藏音乐DuMedia scene-thumbs up gesture-save music |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | N | N | Y
SYNC+_0475 | In-Cabin Image Recognition | Multimode interaction | 导航场景-OK手势-开始导航Navi scene-OK gesture-start to navi |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | N | N | Y
SYNC+_0476 | In-Cabin Image Recognition | Multimode interaction | 导航场景-点赞手势-收藏POI点Navi scene-thumbs up gesture-save POI |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | N | N | Y
SYNC+_0477 | In-Cabin Image Recognition | Multimode interaction | 导航场景-点头/摇头-回应弹框问询Navi scene-nod/shake-answer the popup |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | N | N | Y
SYNC+_0478 | In-Cabin Image Recognition | Multimode interaction | 导航场景-比嘘手势-静音TTS播放Navi scene-slience Gesture-shut down navi TTS |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | N | N | Y
SYNC+_0479 | In-Cabin Image Recognition | Multimode interaction | 导航场景-OK手势-取消TTS静音Navi scene-OK gesture-open navi TTS |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | N | N | Y
SYNC+_0480 | In-Cabin Image Recognition | Multimode interaction | 主动推荐-点头/摇头-代表确认/取消Active recommendation-nod/shake-confirm/cancel |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0481 | In-Cabin Image Recognition | Multimode interaction | 语音场景-挥手手势-唤醒语音Voice interaction-wave Gesture-wake up gesture |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0482 | In-Cabin Image Recognition | Multimode interaction | 语音场景-比嘘手势-退出语音Voice interaction-Slience Gesture-quit voice interaction |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0483 | In-Cabin Image Recognition | Multimode interaction | 复杂动作冲突策略升级Complex Action Conflict Strategy |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0484 | In-Cabin Image Recognition | 疲劳行为监测长闭眼 | 长闭眼Closed eyes for a long time |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0485 | In-Cabin Image Recognition | 疲劳行为监测长闭眼 | 打哈欠yawn |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0486 | In-Cabin Image Recognition | 疲劳行为监测长闭眼 | 打电话make phone call |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0487 | In-Cabin Image Recognition | 疲劳行为监测长闭眼 | 喝饮料drink |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0488 | In-Cabin Image Recognition | 疲劳行为监测长闭眼 | 常规抽烟smoke |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0489 | In-Cabin Image Recognition | 注意力行为监测Attention detect | 视线偏移Line of sight offset |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0490 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 图标提醒icon warn |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0491 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 图标提醒icon warn |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0492 | In-Cabin Image Recognition | 提醒策略Reminder strategy | TTS预警TTS warn |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0493 | In-Cabin Image Recognition | 提醒策略Reminder strategy | TTS预警TTS warn |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0494 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 预警策略warn strategy |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0495 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 优先预警策略warn priority strategy |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0496 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 优化预警方式Optimized warning method |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0497 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 驾驶行为监测偏好设置Driving behavior monitoring preferences |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0498 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 打哈欠20秒策略Yawning 20 second strategy |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0499 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 打哈欠结合主动推荐预警Yawning combined with active recommendation warning |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0500 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 优化视线偏移预警Optimized line of sight offset warning |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0501 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 30分钟问询30 minute inquiry |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0502 | In-Cabin Image Recognition | 提醒策略Reminder strategy | 优化闭眼策略Optimized closed eye strategy |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0503 | In-Cabin Image Recognition | 人脸注册Face registration | 百度帐号与人脸进行绑定Baidu account is bound to the face |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0504 | In-Cabin Image Recognition | 人脸登录face login | 开机启动摄像头识别登录对应帐号Start the camera to identify the login account |  |  |  | Y | Y | B |  | CVPP |  |  | Wang, Johnny (J.) | [11 empty] | N | Y | N | Y
SYNC+_0505 | In-Cabin Image Recognition | 人脸解绑Untied face | 解除人脸与百度帐号绑定关系Dispel the binding between the face and the Baidu account |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0506 | In-Cabin Image Recognition | 人脸打招呼say hello | 可以根据早上、中午、下午时间段区分打招呼，如“早上好”xiaodu can distinguish greetings according to the morning, noon, and afternoon time periods, such as "Good morning." |  |  |  | Y | Y | B |  | IVI |  |  | Jia, Elaine (T.) | [11 empty] | N | Y | N | Y
SYNC+_0507 | In-Cabin Image Recognition | Face ID | 人脸支付 Face id payment |  | 支付宝 |  | Y | Y | B |  | CVPP |  |  | clu42@ford.com | [11 empty] | N | Y | N | Y
SYNC+_0508 | IVI System Function | In-vehicle notification | a pop up notice when ignition to notify customer about data sharing policy | a pop up notice when ignition to notify customer about data sharing policy |  | line 222，需加入feature list | U | N | B |  | CVPP |  |  | Ge, Haiqing (H.) |  |  | N | N | N | N | N | Y | Y | Y | Y | N | Y | Y | Y |  |  |  |  | FO propose to add in phase 1-3, phase 1&2 will be covered by DCR
SYNC+_0509 | IVI System Function | T&C and Privacy Policy in HMI | Terms & Conditions consent in IVI before activation SYNC+ system | Terms & Conditions consent in IVI before activation SYNC+ system |  | feature id 176 | U | N | B |  | CVPP |  |  | Ge, Haiqing (H.) |  |  | N | N | N | N | N | Y | Y | Y | Y | N | Y | Y | Y |  |  |  |  | FO propose to add in phase 1-3, phase 1&2 will be covered by DCR
SYNC+_0510 | Connected Service | Emergency assistance feature | Emergency Assistance will be triggered when airbag pump out or oil pipe line cut off. An emergency call will be placed to China call center by customer's phone connected with Sync+ by bluetooth, and after line open, call center will provide corresponding services per customer's needs. | Emergency Assistance will be triggered when airbag pump out or oil pipe line cut off. An emergency call will be placed to China call center by customer's phone connected with Sync+ by bluetooth, and after line open, call center will provide corresponding services per customer's needs. |  |  | U | Y | D |  | CVPP |  |  | ALEX Ren |  |  | N |  |  |  | N |  |  |  |  | N | Y | Y | Y
Note on D128: Author: 除了百度之外的输入法
Note on D138: Author: 百度VR里面，不仅仅是地图里面的语音提示
Note on R398: Author: Phase-I C519 supports ESE.
Note on D412: Author: E-Manual, ID 59
Note on D453: Author: BAIDU地图里面的内容

## Settings_Menu
Setting Title | SPSS Title | sub-Setting type | Lead FNV2 Program | Direct Interface with Source Modules or Using Cluster as Middleman | HMI Spec | Note | enhanced memory
Auto Hitch | Auto Hitch |  | P702 | Direct
1-Pedal Drive | One-Pedal Drive |  | CX727 | Direct
APA-assist park aid | APA |  | P702 | Direct | H36m
Auto EPB | Auto EPB |  | P702 | Direct | H36K | trailer hitching process only
Auto Hold | Auto Hold |  | P702 (Carryover from SYNC3) | Direct | H31K & H36o
Auto Start Stop | Auto Start Stop |  | P702 | Direct | H31K & H36o
Boundary Alert | Boundary Alert |  |  | Direct | H36q | Police feature
Cross Traffic Alert | Cross Traffic Alert |  |  | Direct | H36k
Dark Mode | Dark Mode |  |  | Direct | H31K | Police Feature
Digital RVC | Digital RVC |  |  | Direct | H36k | FBMP, simple CAN signals are used and LIN protocol.
Fuel Economy | Fuel Economy |  | P702 | IPC
Multicamera | Multicamera |  | P702 | Direct | H36k | FBMP and simple CAN signals are used
Pitch and Roll | Pitch and Roll |  | P702 | Direct
Rear Camera On Demand | Rear Camera On Demand |  |  | Direct | H36n/ Latest Draft of H36k
Rear View Camera | Rear View Camera |  |  | Direct | H36k | FBMP included in communication scheme
Reverse Brake Assist | Reverse Brake Assist |  |  | Direct | H36k
Seatbelt IOD | Seatbelt IOD |  | Cx727 | Direct
Select Drive Mode | Select Drive Mode |  | Cx727 | Direct
Shortcut Key Driver Assist | Shortcut Key Driver Assist |  |  | Direct | H36o
Snow Plow | Snow Plow |  | P702 | Direct |  | confirmed as not needed for China
TBA2 | TBA2 |  | P702 | Direct | H36s | FBMP included in communication scheme
Trailer Settings | Trailer Settings |  | P702 | Hybrid. Multiple protocols involved communication. | H36t | Feature communications with IPC through TP and also through FBMP for passthrough data .
Video On Demand | Video On Demand |  |  | Direct | H36r | Police feature
VPA | Supplier's spec |  | P702 | Direct | H36k
Zone Lighting/360 | Zone Lighting |  | P702 | Direct | H31a
Frunk | Frunk Softswitch Interface Client SPSS |  | CX727 | Direct (for status info) BCM middleman to RGTM (for request) |  | Feature operation request, not Setting
Liftgate | LiftGate Softswitch Interface Client SPSS |  | P702 | BCM middleman to RGTM (for request) |  | Feature operation request, not Setting
Power to the Box | Power to the Box SPSS |  | P702 | Direct
TPMS IOD | TPMS Information On Demand SPSS |  | CX727 | Direct (Cluster > SYNC)
Feature Resets | Embedded Modem Reset InterfaceClient v2 SPSS |  | P702 | Initiated on SYNC, although ECG is middleman to BLEM, TCU, HPCM |  | Includes Brand Connect Reset, WifiHotspot Reset, PaaK Reset
Fuel Economy IOD | Fuel Economy SPSS |  | P702 | Direct (Cluster > SYNC)
Power Running Boards | Power Running Boards Softswitch InterfaceClient SPSS |  | P702 | Direct (DSM > SYNC)
Power Tailgate | TailGate Softswitch InterfaceClient SPSS |  | P702 | Direct (RGTM > SYNC)
Engine Oil Temp | Settings in the Centerstack SPSS | dedicated FBMP | CD542 | Direct Cluster
Power Gauge | Settings in the Centerstack SPSS | dedicated FBMP | CD542 | Direct Cluster
Tachometer | Settings in the Centerstack SPSS | dedicated FBMP | CD542 | Direct Cluster
Oil Life percentage | Settings in the Centerstack SPSS | dedicated FBMP | CD542 | Direct ECM
Oil Life Reset | Settings in the Centerstack SPSS | dedicated FBMP | CD542 | Cluster Middleman
Cluster IoD settings (18 settings) | Settings in the Centerstack SPSS | dedicated FBMP | CD542 | Direct Cluster
Cluster Trip 1 menu | Settings in the Centerstack SPSS | dedicated FBMP | CD542 | Direct Cluster
Cluster Speedo view | Settings in the Centerstack SPSS | dedicated FBMP | CD542 | Direct Cluster
Cluster Trip 2 menu | Settings in the Centerstack SPSS | dedicated FBMP | CD542 | Direct Cluster
Launch Control Assist Settings (TBD) | Settings in the Centerstack SPSS |  | C519ST (TBD) | Cluster middleman to PCM | H31k | TBD
Rev Match setting | Settings in the Centerstack SPSS | vehicle setting | U725, C519ST | Cluster middleman to PCM | H31k
Quiet Start Enable - Exhaust Mode | Vehicle Settings |  | P702 Raptor | Direct PCM | H31k
Set Quiet Time - Exhaust Mode | Vehicle Settings |  | P702 Raptor | Direct PCM | H31k
Clear Exit Assist - Setting | Vehicle Settings SPSS |  | MY22 U55X | Direct ADAS | H31k
Clear Exit Assist - Warning and Power Mode | Vehicle Settings SPSS |  | MY22 U55X | Direct ADAS | H31k
ToneTouch | Audio Settings SPSS |  | TBD SYNC 3, C519 MCA SYNC 4 | Direct DSP AMP | H31a
Eco-Idle | Vehicle Settings SPSS |  | P702 | Direct PCM | H31k
Walk away lock | Settings in the Centerstack SPSS | vehicle setting | CX727 (post job 1?) | Direct BCM | P31A
Walk away lock reminder | Settings in the Centerstack SPSS | vehicle setting | CX727 (post job 1?) | Direct BCM | P31A
double lock | Settings in the Centerstack SPSS | vehicle setting | CX727 (post job 1?) | Direct BCM | P31A
Propulsion Sound Setting | Vehicle Settings SPSS |  | CX727 | Direct AHU | P31A
Drive History | Vehicle Settings SPSS |  | CX727 | Direct PCM | P31A
Low Battery Alert | Vehicle Settings SPSS |  | CX727 | Direct PCM | P31A
Auto/Manual Drive Mode Ambient Lighting | Vehicle Settings SPSS |  | CX727 | Direct BCM | TBD Menlo/Dashcard HMI spec number - H31k feeds Menlo HMI for settings
7 Digit Keypad | Vehicle Settings SPSS |  | CX727 | Direct BCM | TBD Menlo/Dashcard HMI spec number - H31k feeds Menlo HMI for settings
Trip IoD (CX727 - non EV portion) | Trip IoD SPSS |  | CX727 | Direct Cluster | TBD Menlo/Dashcard HMI version of H87a spec
Trip IoD (P702) | Trip IoD SPSS |  | P702 | Direct Cluster | H87a
Bezel Diagnostics (SOA interface) | Bezel Diagnostic SPSS |  | P702 | Direct (TCU, ECG) | H39
Speed Limit - Variant 2 settings | Settings in the Centerstack SPSS | Driver assistance setting | P702 | Direct (ADAS) | H31k | Variant 2 of TSR, SLI and Speed Limiter
Cruise Control - Variant 2 settings (include Highway Assist) | Settings in the Centerstack SPSS | Driver assistance setting | P702 | Direct (ADAS) | H31k
Alarm setting update (motion sensors) | Settings in the Centerstack SPSS | vehicle setting | P702 | Cluster middleman (BCM) | H31k | Update to existing Alarm setting (update to SYNC 3 setting)
Hands Free Liftgate | Settings in the Centerstack SPSS | vehicle setting | P702 | Direct (BCM) | H31k
Long Term Front Park Aid | Settings in the Centerstack SPSS | Driver assistance setting | P702 | Cluster middleman to park aid module | H31k
Long Term Rear Park Aid | Settings in the Centerstack SPSS | Driver assistance setting | P702 | Cluster middleman to park aid module | H31k
Tire Monitor / Tire Pressure Reset | Settings in the Centerstack SPSS | FBMP based | CX727, CD542 | Cluster Middleman | P31A
Border Crossing / Considerate Prompts | Settings in the Centerstack SPSS | FBMP based | CX727, CD542 | Direct Cluster | P31A | Post Job 1 change
EcoCoach Settings (multiple settings) | Settings in the Centerstack SPSS | FBMP based | CX727 | Direct Cluster | P31A
Speedometer setting | Settings in the Centerstack SPSS | FBMP based | CX727 | Direct Cluster | P31A
Brake Coach | Settings in the Centerstack SPSS | FBMP based | CX727 | Direct Cluster | P31A
Neutral Tow | Settings in the Centerstack SPSS | FBMP based | CX727 | Cluster middleman to PCM | P31A
Nav Repeater in Cluster | Settings in the Centerstack SPSS | FBMP based | CX727 | Direct Cluster | P31A
Maps in the Cluster | Settings in the Centerstack SPSS | FBMP based | CX727 | Direct Cluster | P31A
Adjustable chime settings | Alerts SPSS |  | TBD FNV2, SYNC 4.2 | Direct Cluster | H31a | It appears the AHU, DSP AMP and Cluster might not implement and if so SYNC won't finish their software
Adjustable prompt volume setting - TBD | HMI only (system requirements there) |  | SYNC CC approved for P702 post job 1 | Direct (SYNC internal) | H31a | Not implemented yet. TBD if implement
Sound Immersion | Audio Settings SPSS |  | carryover from SYNC 3 (U611/U625) | Direct DSP AMP | H31a
Cruise Control - Variant 1 | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Direct IPMA | H31k
Speed Limiter | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Cluster middleman | H31k
Traffic Sign Recognition | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Direct ADAS (IPMA pre FNV2) | H31k
Speed Limit Information / Speed Sign Recognition | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Direct ADAS (IPMA pre FNV2) | H31k
Lane Keeping System | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Direct ADAS/IPMA | H31k
Pre-Collision Assist | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Direct for most of feature Pre-Collision Assist features (IPMA/ADAS) Cluster Middleman for PSCM-Power Steering Control Module - Evasive Steering | H31k
Blind Spot Detection | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman | H31k
BTT Lite (Blind Spot Trailer Tow) | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman | H31k
Cross Traffic Alert | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman | H31k
Wrong Way Alert | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (TBD U611/U625) | Direct (IPMA/ADAS) | H31k
Driver Alert | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (TBD U611/U625) | Direct (IPMA/ADAS) | H31k
Trailer Sway | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (TBD U611/U625) | Cluster Middleman (ABS) | H31k
Park Aid (ie short term) | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman | H31k
Traction Control | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman (ABS) | H31k
Hill Decent Control | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (TBD U611/U625) | Cluster Middleman (ABS) | H31k
Hill Start Assist | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (TBD U611/U625) | Cluster Middleman (ABS) | H31k
Tow Haul | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (TBD U611/U625) | Cluster Middleman (PCM) | H31k
Grade Assist | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (TBD U611/U625) | Cluster Middleman | H31k
Adaptive steering | Settings in the Centerstack SPSS | Driver assistance setting
Engine Start/Stop Speed Threshold (Auto Start/Stop Speed Threshold) | Settings in the Centerstack SPSS | Driver assistance setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman | H31k
Tire Pressure Units | Settings in the Centerstack SPSS | General setting | carryover from SYNC 3 (U611/U625) | Direct Cluster | H31k
Measure Units | Settings in the Centerstack SPSS | General setting | carryover from SYNC 3 (U611/U625) | Direct Cluster | H31k
Auto Engine OFF / 30 min max idle | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman (PCM) | H31k
Park Lock Control | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (TBD U611/U625) | Direct BCM | H31k
Silent Mode | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (TBD U611/U625) | Direct BCM | H31k
Chime settings | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Direct Cluster | H31k
Remote Start settings | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Direct BCM, FCIM | H31k
Window settings | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Direct BCM | H31k
Wiper settings | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Direct SCCM | H31k
Power Liftgate | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman | H31k
Power Decklid | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman | H31k
Lighting settings | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Direct BCM, IPMA, HCM | H31k
Lock settings | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Direct BCM | H31k
Mirror settings | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Direct DDM | H31k
Park Heater | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (CX482 lead?) | Cluster Middleman | H31k
Aux Heater | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 | Cluster Middleman | H31k
Passenger Airbag | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Cluster Middleman (RCM) | H31k
Tire Mobility Kit | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (TBD U611/U625) | Direct Cluster | H31k
Easy Entery / Easy Exit (seat adjustment) | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (U611/U625) | Direct Cluster | H31k
Auto Entry / Exit Height (Easy Access Height) | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (TBD U611/U625) | Direct SUMA | H31k
Cargo Loading | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (TBD U611/U625) | Direct SUMA | H31k
Air Suspension | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (TBD U611/U625) | Direct SUMA | H31k
My Color | Settings in the Centerstack SPSS | vehicle setting
Auto Regen | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (TBD U611/U625) | Cluster Middleman (PCM) | H31k
Trailer Brake (Effort and Mode) | Settings in the Centerstack SPSS | vehicle setting | carryover from SYNC 3 (TBD U611/U625) | Cluster Middleman | H31k
5 Digit Keypad | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct BCM | H31k
Ambient Lighting - Variant 2 | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct BCM | H31k | Always used with Enhanced Memory. Used 100% on CX727 regardless of EM, to support Auto/Man Drive Modes.
Ambient Lighting - Variant 1 | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct BCM | H31k
Valet Mode | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct (SYNC internal, BCM TBD) | H31a
Master Reset | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct (SYNC internal, AHU, DSP AMP, TCU) | H31k, H31L
Charge Cord Unlock | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct | H31k
Charge Port Light Ring | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct | H31k
12/24 mode | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct Cluster | H31a
Touch Panel Beep settings | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct | H31k
Tempature Units | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct Cluster | H31k
Language | Vehicle Settings SPSS |  | Carryover from SYNC 3 | Direct Cluster | H31k
Surround Sound | Audio Settings SPSS |  | Carryover from SYNC 3 | Direct DSP AMP | H31a
Audio Demonstration Mode | Audio Settings SPSS |  | Carryover from SYNC 3 | Direct DSP AMP | H31a
Convertible Auto-EQ Occupancy Mode | Audio Settings SPSS |  | Carryover from SYNC 3 | Direct | H31a | for convertible car only
Occupancy Mode | Audio Settings SPSS |  | Carryover from SYNC 3 | Direct | H31a
Speed Compensated Volume | Audio Settings SPSS |  | Carryover from SYNC 3 | Direct | H31a
Bass, Treble, Balance, Mid-Range, Fade settings | Audio Settings SPSS |  | Carryover from SYNC 3 | Direct | H31a

## MRD_Review_Overview
Totally 119 requirements of features need to aligned and frozen before Feb. 14th. | [34 empty] | Status | # of features | Responsible |  | Comments
13 of them planned as no supplier requirement spec needed. Q&A list provided to prove that all the Ford requests had been accepted by supplier. | [30 empty] | Status | # of features | Follow up action responsible |  | Close | 141 | Baidu | 52 | 8 items shared responsibility
Review Status |  | MRD or QA list Planned Available date | Desay | Desay/Baidu | QA-planned | QA-delayed | planned | delay | close | on-going | [20 empty] | Delay | 17 | Baidu | 12 |  |  | Desay | 94
[33 empty] | Desay | 5 |  |  | Ford EESE | 1
[33 empty] | Ford |  |  |  | Ford CVPP | 3
[31 empty] | On-going | 5 | Baidu | 4 | Cancel | 33
open | 2 | 2019-11-20 | 1 |  |  | 1 |  |  |  |  | Overview |  | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 | 2020-01-17 | 2020-01-24 | 2020-01-31 | [12 empty] | Desay | 1 | onhold | 3
QA | 0 | 2019-12-05 | 1 | [6 empty] | 1 | Plan | MRD Out put | 11 | 46 | 68 | 79 | 112 | 120 | 123 | 123 | [10 empty] | Open | 2 | Baidu | 2
Desay
on-going | 5 | 2019-12-10 |  | 2 |  | 2 | [26 empty] | Ford EESE
Ford CVPP
delay | 17 | 2019-12-13 | 1 |  | 1 | [25 empty] | Planned |  | Baidu | 1
[33 empty] | Desay | 2
Ford EESE
close | 167 | 2019-12-15 | 9 |  | 1 |  | 8 | [5 empty] | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 | 2020-01-17 | 2020-01-24 | 2020-01-31 | [12 empty] | Ford CVPP
|  | 2019-12-16 | [8 empty] | Plan | MRD approval | 9 | 10 | 36 | 65 | 84 | 117 | 125 | 125 | [10 empty] | Close | 167
|  | 2019-12-20 | 29 |  |  |  | 29 |  |  |  | Actual | MRD approval | 7 | 8 | 11 | 13 | 21 | 56 | 70 | 70
|  | 2019-12-25 | 6 |  |  |  | 6
|  | 2019-12-27 | 1 |  |  |  | 1 | [23 empty] | Cancel | 27
|  | 2019-12-30 | 18 |  |  |  | 18 | [23 empty] | onhold | 6
|  | 2020-01-05 | 1 |  |  |  | 1 | [23 empty] | N.A | 4
2020-01-06
|  | 2020-01-10 | 9 |  | 1 |  | 8
|  | 2020-01-17 | [8 empty] | Desay
|  | total | [10 empty] | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 | 2020-01-17 | 2020-01-24 | 2020-01-31 | 2020-02-07 | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27
[11 empty] | Plan | MRD Out put | 20 | 48 | 64 | 68 | 94 | 100 | 100 | 100 | 100 | 107 | 115 | 116 | 117 | 117 | 117
[11 empty] | Actual | MRD Out put | 4 | 29 | 39 | 53 | 69 | 81 | 82 | 82 | 83 | 95 | 102 | 109 | 109 | 110
|  | MRD or QA list Planned Available date |  | Baidu | QA-planned | QA-delayed | planned | delay | close | on-going |  |  | 2019-12-27: 25
2019-11-20
|  | 2019-12-05 | [10 empty] | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 | 2020-01-17 | 2020-01-24 | 2020-01-31 | 2020-02-07 | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27 | 2020-04-03 | 2020-04-10
|  | 2019-12-06 |  | 2 |  | 2 |  |  |  |  | Plan | MRD approval | 15 | 10 | 32 | 53 | 62 | 89 | 95 | 97 | 100 | 100 | 107 | 114 | 115 | 116 | 116
|  | 2019-12-10 | [8 empty] | Actual | MRD approval | 2 | 2 | 4 | 18 | 26 | 59 | 63 | 63 | 72 | 79 | 94 | 102 | 109 | 110
|  | 2019-12-13 |  | 4 |  |  |  | 4 |  |  |  |  | 2019-12-27: 28
2019-12-15
|  | 2019-12-16 |  | 1 |  |  | 1
|  | 2019-12-20 |  | 7 |  |  | 7
|  | 2019-12-25 | [8 empty] | Baidu
|  | 2019-12-27 |  | 1 |  |  | 1 | [5 empty] | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 | 2020-01-17 | 2020-01-24 | 2020-01-31 | 2020-02-07 | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27 | 2020-04-03 | 2020-04-10
|  | 2019-12-30 |  | 3 |  |  | 3 |  |  |  | Plan | MRD Out put | 4 | 10 | 15 | 20 | 27 | 28 | 31 | 46 | 63 | 71 | 71 | 76 | 78 | 78 | 78
|  | 2020-01-05 | [8 empty] | Actual | MRD Out put | 3 | 8 | 10 | 19 | 24 | 25 | 26 | 37 | 56 | 62 | 63 | 70 | 70 | 72
|  | 2020-01-06 |  | 1 |  |  | 1 | [5 empty] | 2019-12-27: 5
2020-01-10
|  | 2020-01-17 |  | 1 | [5 empty] | 1 |  |  | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 | 2020-01-17 | 2020-01-24 | 2020-01-31 | 2020-02-07 | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27 | 2020-04-03 | 2020-04-10
|  | total | [8 empty] | Plan | MRD approval | 7 | 7 | 11 | 17 | 25 | 31 | 32 | 38 | 39 | 59 | 64 | 69 | 73 | 74 | 74
[11 empty] | Actual | MRD approval | 5 | 6 | 7 | 7 | 7 | 9 | 17 | 22 | 27 | 37 | 47 | 54 | 56 | 56
4

## Change Log
date | version | author | change content | open item
2019-10-14 | 1.65 | Diven Yu | Deleted: 多屏背景同步/Multi-display wallpaper synchornization 紧急呼叫时静音/Mute for eCall 电子罗盘/Compass on IPC and IVI Emergency call Multi-Display, drive up to 3 display and 1 Video output Multi-Display animation 行车记录仪/Dash Camera(Driving Recording)---TBD 副驾收音机（和主驾相同）-New 副驾音频AUX输出/Passenger Audio AUX Output Deleted Lower Display features | need to sort out EV features with CVPP, key words: EV, power, Charge
| 2.3 | Susan Zhang | Update based on kick off meeting
2019-11-22 | 2.4 | Emma Chen | Update based on the FIP review with Fin and Diven. - change the sheet name "Phase4 Master feature list V2.0" to "Phase4 Master feature list V2.x" - adjust the format: font size - update the column "ID" to minimize confusion. - add column "AJ" as "file location"; - update column "S", add spec name for the features assigned to me. - mark cells in column "S" after checking the files in GitHub. Green means files available. - add file location link for DCV0 available files 11/28/2019: migrate FO info from input from Ma Mei.
2019-12-04 | 2.5 | Susan Zhang | remove some features. update Face ID items update option items
2019-12-05 | 2.6 | Emma Chen | Update after "MRD plan" meeting: column S, T; 2019/12/9: Add columns to record MRD review status. Add sheet “MRD_Review_Overview" Update regularly based on daily meeting Minor revision history are recorded in the sharepoint history

## QA
NO | Question | Baidu Response | Ford Response
1 | 对于该表格中约定的以ED&T形式定制开发的功能，需要支持通过配置去启用或禁用该功能，在不同配置中启用或禁用该类功能，不影响其配置对应的license费用 | 不影响license费用我方认可，但烦请此处确认“配置”的准确定义指的是什么(拿CD542举例，是否指的就是CD542-LOW, CD542-HIGH）？另外所有我方的license报价均基于feature list功能全集，此feature list未涉及到的功能的license需要重新评估。
2 | 对于列表中所列Baidu提供的亮点功能，可以由Ford选择是否使用，无Cost(ED&T及License)的变化。 | 根据今晚会议沟通，明天我方技术团队架构师 @方胜 与南京REC针对于此需求，即需要支持通过配置去启用或者禁用该功能的实现细则，待双方技术工程团队沟通后，我方再update相关反馈。
3 | 功能OPT1-4单独给出ED&T及License成本。 | 我方澄清如下：表格中所列亮点功能，其中智慧停车我方目前报价中包含的仅有相关查询功能，不含支付功能，由于我方智慧停车后面的资源方为ETCP，我方和ETCP的结算成本过高，我方无法在此版报价中包含智慧停车相关支付功能，如需使用此功能，建议可以采取C端付费的形式，其余亮点功能我方均可支持，且包含在报价中。
4 | CX727的Med/High中包含AR导航（OPT1）、人脸识别基础功能（OPT2）及FOTA（OPT4）等功能。 | 百度之前报价版本中已经输出，无异议。
5 | CD542所有车型共用一版软件，通过MCU中配置的形式区分不同车型的功能配置 如果后期采用两版/多版软件，则在所有版本软中同样实现所有以ED&T形式开发的功能，Ford会采用EOL的配置去实现功能配置。
6 | 跨车型之间的功能移植，进按照功能移植来计算Cost，无重新开发的cost
7 | 所有以ED&T开发的功能(目前feature list中已经确认部分需要部署功能配置的要求，后期可能在ED&T类型功能范围内增减，增减无COST的影响)，需要支持EOL 中的可配置，即功能的Enable/Disable
8 | 对于部分以License方式开发的功能（以feature list中EOL Configuration列为准），需要支持EOL 中的可配置，即功能的Enable/Disable
9 | 功能内部也存在配置，去选择其表现形式，如空调可能是自动、手动、有无座椅加热等。
10 | 双音区/多音区VR标定：对于CD542高低配车型分别选择双音区或多音区作为其唯一功能配置，且同配置的音频环境相同（麦克风、麦克风装配、Speaker类型、Speaker数量、功放类型、和声音标定有关的内饰）
Display 变更： 1. Background a. 高配Display 从13.2*2改为27寸，4032*756，PPI 152 b. 低配继续维持单13.2"(2348*1080)屏幕, PPI 196，Ratio：13：6 c. DuerOS ICA1 PPI-167 d. 高配的Lower display整体删除，其功能均不再需要 2. Functions a. 新增/澄清 i. 针对高配27"屏幕，增加双屏和驾驶员屏幕独占模式（超级单屏模式） 澄清 i. 之前的高配双屏部分功能均保留。 ii. 双屏模式下依然有内容或app拖拽/复制模式。 1) 地图 2) 音乐/视频/图片 3) 其他副屏和主屏都有的功能 3. HMI Redesign a. 确认高配双屏模式能复用多少13.2寸的设计 b. Baidu确认27"带来的HMI上相对于13.2*2的变化。 4. RFQ a. Baidu和Ford HMI在7.23确认HMI侧的变更。 b. Baidu在本周五前提供具体变更Cost 5. 屏幕样件采购 a. 27寸屏幕由德赛代Baidu采购或Baidu独立采购？ 13.2寸采购保持原来的方式。
澄清由福特in-house开发的功能

## Mgt.
| CD542 | CX727
Y | 0 | 0
N | N | Y
OPT | Y | Y
#VALUE!
COMMON | 172 |  |  | CD542 |  | CX727 | Function team | Feature number | Comments
|  |  | 1 | 天窗控制 Sunroof Control | 1 | Off Road Front View Camera | CVPP | 69
CD542 specific | 21 | [5 empty] | DAT | 27 | 20 of them already aligned with VE DAT team, they will support validation from their side.
|  |  | 2 | Ford车辆系统降噪/Ford Noise reduction ANC | 2 | IOD - Fuel Economy | EESE/Convenience&Security Module team | 2 | massage seats
[6 empty] | IOD - Pitch and Roll | EESE/DI | 1
|  |  | 3 | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) |  | IOD - SeatBelt (information on demand) | EESE/HUD | 1
CX727 | 0 |  |  |  |  | IOD - TPMS (Information on Demand) | EESE/system/IVI - Diven team | 37
C/O from Phase 1/2/3 | 43.56% | 98 | 4 | #REF! |  | IOD - Trip Information On Demand | EESE/IVI - Forrest team | 26
CX727 specific | #DIV/0! | 9 |  | AR Navigation (include output to IPC) |  | Message Center Client (APIM) | EESE/system/inHouse | 2 | Dekang cover 1
Comon new | #DIV/0! | -107 |  | AR Front View/360 View/BLIS View |  |  | EESE/IVI - Roger team | 11
[5 empty] | 3 | front trunk/前引擎盖 | EESE/System | 10
[7 empty] | EESE/Wireless | 1
[5 empty] | 4 | Rocket setup | HMI | 13
|  |  | 5 | 对高配27"屏幕，需要支持双屏和驾驶员屏幕独占模式（超级单屏模式）-Launcher
屏幕扩展显示/Extend center or passenger display content(like Navi, to show the whole path in two screens) to two display
27inch - 本地及在线音乐/Offline&Online Music Player & audio manager
27"空调设置(climate control from passenger area)
副驾视频播放(支持 DLNA)/Passenger Video Playback(Support DLNA)
副驾系统设置/Passenger system setting（system settings display in passenger area as well）
副驾文件浏览器／Passenger File Manager
副驾图片浏览器/Passenger Picture Viewer
27" only: Vehicle status showing in the passenger area
副驾主页/Passenger HomeScreen
#REF!
27"地图/including Passenger Map&Navigation
27" 输入法 - 副驾输入法 / words input
副驾在线视频/Online Video-clarify
副驾天气预报/Weather forecast
|  |  | OPT | PAAK (phone as a key)
Backup Startup Passcode for PAAK
Emotion Recognition-New
Note on G20: Author: When customers wait for vehicle hand-over, they can do IVI set up on FP in advance. Such as 3rd party ID linkage, wake up words, Pony related

## vehicleTest
|  |  | HIL instead | Total days
|  |  | 55.025 | 105
|  |  | 52.4% | 49.975
Baidu | Functional Test | 音源模块测试 （BT/Tuner/USB音源等） | x | 10
|  | 实车音效测试 (音效、Pop声测试、音量) |  | 4
|  | VR（与蓝牙/收音交互测试等） |  | 6
|  | RVC/360 | x | 6
|  | 实车点火测试 |  | 6
|  | 蓝牙通话质量 | partly | 4
|  | 收音路试（AM/FM） |  | 3
|  | OTA |  | 7
|  | System Setting&Vehicle Setting （my key/Vehicle Lighting control/Selectable Drive Mode/泊车辅助等与车身相关设置。） | x | 4
|  | HVAC (Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR) | x | 4
|  | Welcome&Farewell | x | 4
|  | 问题复现 | partly | 15
|  | 问题验证 | partly | 15
Desay | 语音 | 1. 基本功能的自测验证，每个业务垂类，尤其与车相关的主动提醒模块 | partly | 1.75
|  | 2. dsp调参，包括声源抑制，噪音、回声消除，对应功能是唤醒率、识别率 |  | 9.5
|  | 3. 车控指令调试 |  | 1.5
|  | 4. 音频焦点调试与随心听、随心看、地图等模块的调试 | partly | 0.45
|  | 5. mic焦点调试，录音功能 |  | 0.45
|  | 6. 主副驾声源定位RD测试 |  | 0.45
|  | 7. 物理按键唤醒、取消 | partly | 0.45
|  | 8. 激活需要设备id和vin码，联调下激活，语音是否可以正常使用 |  | 0.45
| 物理按键 | 1. 物理按键控制 | x | 0.6
|  | 2. 多屏互动反控 |  | 0.6
|  | 3. 语音控制 |  | 0.6
|  | 4. 本地播放：USB |  | 0.6
|  | 5. 基本功能自测验证，与各垂类APP完整交互验证 |  | 0.6
| 地图 | 1. 道路试验中定位特性的验证、自适应与验证 |  | 9
|  | 2.道路试验中巡航模式的验证、自适应和验证特性 |  | 8
|  | 3. 道路试验中制导方式的验证、自适应与验证特性 |  | 8
|  | 4. 道路试验中路径规划的验证、自适应与验证特性 |  | 4
|  | 5. 道路试验检索的验证、自适应与验证特性 |  | 4
|  | 6. 道路试验中mapview、离线数据、vr功能的验证与验证 |  | 4
|  | 7. 验证tts的有效性和可验证性，在道路测试中实现了音频聚焦相关功能 |  | 4
|  | 8.地图内部的路测团队需进行全功能测试，验证达标成度，保证交付质量 |  | 8
| ETCP 智慧停车 | 1. 进出场实车验证 |  | 1.5
|  | 2. 车辆相关信息vin、车牌绑定验证 |  | 0.5
| 其他 | 与定位服务相关的APP模块 |  | 6
| QA | 系统集成路测 | partly | 9
| 安全 | 1. 车机IVI |  | 0.6
|  | 2. T-BOX | x | 1.8
|  | 3. 业务评估(控车功能) |  | 1.8
|  | 4. Gateway/ECU | x | 1.8

## Variant
[13 empty] | 32G | 64G
|  | CD542 |  | CX727 | U725 | P702 | U554MCA | U625ICA | CD764 |  | SW-A: | 12''&13.2''Ford | SW-A1 | SW-A2
| display " | 13.2 | 27 | 15.5 | 12 | 12 | 13.2 | 27 | 27 |  | SW-B: | 27''Ford | SW-B1 | SW-B2
| SW variant | SW-A | SW-B | SW-C | SW-A | SW-A | SW-D | SW-B | SW-E |  | SW-C: | 15.5" Ford | SW-C1 | SW-C2
| iACC | N | N | OPT | N | Y | Y | OPT | OPT |  | SW-D: | 13.2''Lincoln |  | SW-D
| eMMC |  |  | 32G/64G |  | 64G | 64G | 32G/64G | 32G/64G
| SW variant-updated | SW-A1 | SW-B1 | SW-C1 SW-C2 | SW-A1 | SW-A2 | SW-D | SW-B1 SW-B2 | SW-E1 SW-E2
| iACC: open item:; OPT: software variants increase; OPT: software variants increase | software variants increase |  | SW-E: | 27''Lincoln | SW-E1 | SW-E2
HW variant
iACC take rate | OPT: 60%; OPT: 39% | 35%
|  | CD542 | CX727 | U725 | P702 | U554MCA | U625ICA | CD764
| SDM | Y | Y | Y | Y | Y | Y | Y |  | 1. Phase4每个车型都有三套主题，切换方式如下，
| SDM hard switch | N | N | Y | Y | Y | Y | Y
| SDM soft switch | Y | Y | N | N | N | N | N |  | 1) U554/P702/U725由用户在系统设置里的更换主题选项进行设置
| Theme change based on SDM mode | Y | Y | N | N | N | TBD | TBD |  | 2) CX727/CD542不提供更换主题的设置项，主题会跟随驾驶模式，即在用户切换驾驶模式后自动切换至对应主题
| Theme change based on HMI menu selection | N | N | Y | Y | Y | TBD | TBD
| HMI mis-match with Cluster | Not issue | Not issue | C/O phase 2 design | C/O phase 2 design | C/O phase 2 design | TBD | TBD |  | 3) CD764/U625ICA 待确认
| Mode detail | 3 modes – eco, normal, sport | 4 modes – normal, sport, eco-comfort, Track mode (GT variant ONLY) | 8 modes – normal, sport, eco, Low Mu Mode 湿滑模式, Mud/Rute Mode, Sand Mode, Rock Crawl Mode, Baja Mode (Repter variant ONLY) | 10 modes – normal, sport, eco, Low Mu Mode 湿滑模式, Tow Haul Mode, Mud/Rute Mode, Sand Mode, Rock Crawl Mode, Rough Road mode, Baja Mode (Repter variant ONLY) | 8 modes – sport, eco, low mu mode, mud/rute mode, sand mode, normal 2H mode, normal 4A mode, normal 4L mode | 7 modes – normal, sport, eco, low mu mode, tow haul mode, sand mode, rough road mode

## 服务功能列表 (hidden)
一期预计实现的功能 The Features to be achived in A project
功能模块 Functional Module | 主功能 Main Features | 一期预计实现功能 The Features to be achived in A project | 功能备注 Features Remarks | 斑马建议 Suggestions from BANMA | Ford工程反馈 Feedback from EESE | 2/2 confirmation | 建议备注 Remarks | 需要长安福特的支持 Supports from CAF
养车模块 Maintenance Module | 车况分析 Vehicle Condition Analysis | 故障监测 Vehicle Fault Monitoring | 01. 获取车辆故障码 01. Get the vehicle fault code | 可支持 | TCU在info CAN上，TCU故障码可支持；BCM，仪表，ECM等其他模块在整车CAN上，没法传；整车故障码显示无法实现。（Leo确认后续SOP可以支持哪些？） | N
|  |  | 02. 图形显示故障部件 02. Graphical display of defective parts | 可支持（有ICON） |  | N
|  |  | 03. 图形显示故障原因 03. Graphical display of fault reason | 只能文字描述收到的故障内容 |  | N |  | 需收到对应的故障码及故障信息
|  | 车辆状态监控 Vehicle Conditon Monitoring （实时行车数据流采集 静态车辆数据采集） （Real-time vehicle driving data acquisition & Static vehicle data collection) | 01. 胎压监测 01. Tire pressure monitoring | 可支持 | 胎压在HS CAN，没法传。Info CAN没有这条信号，做不到。 | N |  | 需收到胎压信号
|  |  | 02. 电池电压监测与预警 02. Battery voltage monitoring and warning | 可以故障显示，没有实时监测及显示 | 检测：电压值可以实时获取。斑马后续和Leo进一步确认如何使用以上数值。 预警：CAF服务部要求斑马增加预警策略，设定某一条件，电池需要更换。电池寿命有无数值？仪表上有此数据。 | N |  | 需收到对应的故障码及故障信息 3/6 赵亮：C520无故障码输出给AHU，此功能取消
|  |  | 03. 轮胎磨损角度监测 03. Tire wear angle monitoring | NOK |  | N |  | 目前无信号可使用
|  |  | 04. 油液夜位监测 04. Oil & fluid level detection monitoring | 可以故障显示，没有实时监测及显示 | 有燃油%，其他油液不确定。 | N |  | 需收到对应的故障码及故障信息 跟REC确认仪表可以提供油量报警信号-赵亮 3/6 赵亮：C520无故障码输出给AHU，此功能取消
|  |  | 05. 车内空气质量监测 05. Air quality monitoring in car | 斑马制定的智能硬件空气净化器可以显示 |  | Y |  | 需用户购买安装空气净化器（斑马已完成适配开发） | 不兼容其他后装的空气净化器。 IVI的屏幕显示出OEM前装的集成在空调内的空净的PM2.5数据。 Tong Tian Offline和斑马及EESE讨论。
|  |  | 06. 车速监测 06. Speed monitoring | 车速在仪表显示，斑马有超速提醒 | 可以收到车速。 | Y |  | 需收到车速信号
|  |  | 07. 瞬时油耗监测 07. Instantaneous fuel consumption monitoring |  |  |  |  | 第一期不需要
|  |  | 08. 平均油耗计算 08. Average fuel consumption monitoring |  |  |  |  | 第一期不需要
|  |  | 09. 燃油花费预测 09. Fuel cost forcast | 暂时没有花费预测，可以有油量低通知（来自仪表信号） | 有燃油%，有里程，但没有直接的百公里油耗，没有续航里程。 需求改为：油量低的信号。 | Y |  | 需收到仪表的油量低信号
|  |  | 10. 行车时间记录 10. Driving time record | 不支持 |  | N
|  |  | 11. 其他车辆状态参数监测 （去掉） 11. Other vehicle conditions monitoring |  |  | N
|  | 车况综合打分 Vehicle condition comprehensive score | 01. 以颜色代表各等级车况得分 01. Using defferent colors represent ech grade condition score | 可支持 斑马给车况打分，核心的输入是保养时间，拿到福特的保养时间和保养逻辑。输入由售后服务提供，每个零件的保养周期及要求。客户的更换情况和更换时间，经销商操作保养复位。经销商工程U盘。权限仅开放给经销商。不支持在其他处保养。 | Risk：此非Raido的功能范畴。是否考虑客户仪表上特殊操作，清理保养纪录？ | Y w/Risk |  | 工程U盘+工程账号进入工程模式进行重置， OEM将 这些东西发放给4S店 2018.2.13：CAF确认权限只给4S店
|  |  | 02. 分3-4个等级 02. Using 3~4 grads to display conditon score | 可支持 |  | Y w/Risk
| 保养提醒 Maintenance Reminder | 耗材保养提醒 Consumables maintenance reminder | 01. 显示需要保养的耗材名称 01. Display name of consumables to be maintained | 可支持 |  | Y
|  |  | 02. 显示何时需要保养 02. Display when to take maintenance | 可支持 |  | Y
|  |  | 03. 显示如何保养 03. Display how to take maintenance | 可支持 |  | Y | 保养更换配件范围
|  |  | 04. 显示该去何处保养 04. Display where to take maintenance | 可支持 |  | Y
|  |  | 05. 保养提醒重置功能 05. The funciton to reset Maintenance Reminder | 可支持 告诉用户需要更换的零件。在用户未实施保养时，有提醒保养过期。 | Risk：此非Raido的功能范畴。播放音乐，导航等时候，是否弹出保养提醒？对用户体验的影响？要求允许用户选择“已经完成保养”。 | Y w/Risk
| 服务预约 Service Booking | 电话预约 Telephone booking | 01. 展示经销商信息 01. Show dealers information(telephone, address and so on) | 可支持 |  | Y
|  |  | 02. 车机蓝牙拨号 02. dial-up with car bluetooth phone | 可支持 |  | Y
|  | 在线预约 Online booking | 对接预约中心在线预约 Docking appointment center & booking online | 需确认双方系统打通的可行性 |  | N |  | 需确认系统开发的负责人跟斑马对接，一起确认可行性及计划 2018.2.13：斑马跟CAF就实现范围达成一致，待PD超超整理后发出 2018.3.6：2018.7月份无法完成，需双方评估新的时间点。
| 活动推广 Activities Promotion | 活动内容投放 Activity content post | 01. 服务市场活动展示 01. Show activity content | [5 empty] | 提醒内容的维护谁负责？操作流程？ Ford/CAF对接斑马活动运营团队，拟定好后，斑马推送消息给指定车主。目前不开放给OEM，未来系统打通后，可以直接下发。
|  |  | a. 全客户群活动通知推送 a. Push notification to all customers | 可支持 |  | Y
|  |  | b. 目标客户群精准通知推送 b. Push notification to target customers | 可支持 |  | Y
|  |  | 02. 客户关怀活动展示（视频） 02. Show customer care activities ( video ) | 不支持 |  | N
|  |  | 03. 技术服务活动展示 03. Show technical activities | 可支持 |  | Y | 推送消息
| 服务进展 Services Progress Monitoring | [6 empty] | 第一期不需要
道路救援 Road Assistance | 原厂救援 OEM Assistance | 救援电话展示 Show road assistance telephone | 车机蓝牙拨号 Dial-up with care bluetooth phone | 可支持 |  | Y
|  | 救援公司平台集成 Dock road assistance company's platform | 01. 车机拨号 01. Car machine call road assistance telephone | NOK | 是否可以放在手机APP上直接打电话，APP发出车辆位置，第三方请求车辆位置和车辆数据。 手机打电话，车机上显示服务码，告知服务码，服务器端获取车辆位置？斑马评估。Leo评估下TCU增加B-Call放在SOP2时间可能性，以及其他车型的可能性。 | N | TCU没有B-Call功能，不能通过Tbox拨打电话同时将故障车辆位置发给救援公司平台 | 建议未来TCU增加B-Call功能
|  |  | 02. 推送客户位置信息给救援公司 02. Push customer's address to road assistance company' platform |  |  | N
|  |  | 03. 车机上获得救援车辆实时位置信息 03. Car machine get real-time address of road assistance vehicle |  |  | N
保险 Insurance | 场景险 Scenes insurance | 保险介绍 Introduce Insurance products | 01. H5链接保险产品信息 01. H5 Link insurance products informaiton | 可支持推送消息 |  | Y | 仅推送消息，不显示保险信息
|  |  | 02. 车机上推送保险产品介绍 02. Show insurance products | 可支持推送消息 |  | Y | 仅推送消息，不显示保险信息
|  | 投保功能（是否为长安福特产品？） Buy insurance | 01. 恶劣天气自驾险 01. F.P.G. for self-driving in bad weather | 可支持 | 产品下线时是否支持可配置？福特需要具备可Disable能力。 | N |  | 2018.2.13：CAF确认2018.7月份不上
|  |  | 02. 长距离自驾险 02. F.P.G. for selft-driving long distances | 可支持 | 产品下线时是否支持可配置？福特需要具备可Disable能力。 | N
在线销售模式 Sales Online | 销售平台 Sale platform | 产品介绍 Introduce products | 01. 产品宣传 01. Products introduction | CAF可以上线天猫或者淘宝店铺，斑马可支持在车主手机淘宝中通过车主卡片作为入口，推广销售对应车型的商品，服务。 |  | N |  | 1. CAF上线淘宝或天猫店铺，并上架对应产品 2. 店铺开一个淘客活动给到斑马 2018.2.13：CAF确认2018.7月份不上
|  |  | 02. 目标客户产品信息推送 02. Show products information |  |  | N
|  | 产品销售 Sale proudcts | 01. 销售ESB产品 01. Sale ESB products |  |  | N
|  |  | 02. 销售原厂附件 02. Sale OEM Accessories |  |  | N
|  |  | 03. 销售原厂重要耗材 03. Sale OEM consumables |  |  | N
|  | 在线结算 Settle accounts online | 01. 资金流处理 01. Settle accounts |  |  | N
|  |  | 02. 发票推送 03. Push invoicement |  |  | N
二期预计实现的功能 The Features to be achived in B project
功能模块 Functional Module | 主功能 Main Features | 一期预计实现功能 The Features to be achived in A project | 功能备注 Features Remarks | 斑马建议 Suggestions from BANMA |  |  | 建议备注 Remarks | 需要长安福特的支持 Supports from CAF
养车模块 Maintenance Module | 车况分析 Vehicle Condition Analysis | 远程诊断 Remote diagnosis | 01. 车主远程诊断申请功能 01. One key to apply remote diagnosis
02. 远程诊断受理反馈 02. Feedback remote diagnosis accepted
03. 技术人员远程登录车机 03. Technician log in marchine remotly
04. 远程故障诊断 04. Diagnose fault remotly
05. 生成故障诊断报告与维修方案 05. Generate diagnosis report and repair program
06. 维修方案费用预算报告 06. Generate repair cost report
07. 推送车主信息与维修方案至4S店平台 07. Post customer information and repair proposal to dealer
08. 故障案例存入中心知识库
| 保养提醒 Maintenance Reminder | 智能保养 Intelligent Maintenance | 引入“保养顾问”概念，为车辆定制保养 Create new concept - 'Maintenance Advisor', to customize maintenance program for customer.
01. 基于客户消费习惯，用车习惯，车辆综合车况定制常规保养方案 01. Customize general maintenance proposal base on customer spending habits, driving habits, vehicle conditions, and so on.
02. 定制车辆临时保养方案(如长距离行驶，极端环境行车) 02. Customize temporary maintenance proposal
03. 人机互动与人文关怀 04. Human-Computer interaction and Humanistic care
| 服务预约 Service Booking | 预约互动 Interaction of service boooking | 01. 经销商预约资源推送 01. Post Booking source
02. 生成在线预约报价单 02. Generate online booking quote
03.客户报价信息推送给经销商 03. Post online booking information to dealer
| 活动推广 Activities Promotion | 互动与闭环管理 Interaction and close loop management | 01. 活动提醒与查询 01. Activities reminder and inquiry
02. 客户在线互动咨询 02. Online advisory and interaction
03. 预约并引导客户回厂 03. Guide customer to dealer
04. 购买，使用与核销 04. Purchase, use and settle acounts
| 服务进展 Services Progress Monitoring | 维修进度实时查询 Inquire real-time repair schedule | 平台需要开发维修进度实时接收端口和实时输出端口
|  | 电子车辆检查报告 Electric vehicle inspection report | 平台需要开发维修报告实时接收端口和实时输出端口
|  | 车辆到店提醒 Vehicle arriving reminder | 车辆到店后提醒经销商接待车主
|  | 车辆检测在线查询 Inquire vehicle inspecion online | IPAD接车与电子检查报告反馈
|  | 维修结果在线反馈 Feed back repair result online | 反馈客户维修结果与维修费用
道路救援 Road Assistance | 原厂救援 OEM Assistance | 客户自费救援 Customers pay road assistance | 救援服务零售 Retail road assistance service
保险 Insurance | 保险 insurance | 车险 Vehicle insurance | 01. 一键投保 01. One key to buy vehicle insurance
02. 报案理赔 02. Report claims
03. 基于客户特征的数据分析 03. Data analysis base on customer features
04. 事故车辆返厂监控 05. Monitor return data of accident vehicle
在线销售模式 Sales Online | 销售平台 Sale platform | 目标客户画像 Target customer figure
多场景的消费引导 Multi-scene guiding to spend