## Phase4 Master feature list
[26 empty] | 27 | 28 | 29 | 30 | 29 | 30 | 31 | 31 | 32 | [11 empty] | 31
[5 empty] | Effort Estimation | [16 empty] | FO/Interface |  |  |  | 29: CD542; 29: CD542 ICA; 31: CX727; 31: CX727ICA; 32: U725 (cancel) | P702 | P702(MCA) | U725C ICA | U554 MCA | U625ICA | CD764 | CD764 ICA | S650 | CDX706 | CDX706 | CX483 MCA | CX771 | Cost Type | EOL Configuration |  | MRD review |  |  |  |  | 7 |  | Next Resp. | [11 empty] | CD542L |  | CD542H |  | CX727 |  | P702 | U554 MCA | U625ICA | CD764 | S650 | CDX706 | CDX706 | CX483 MCA
ID | Category | Function | Feature | Feature carried from Phase 1/2/3 | Desay | Baidu | Ford SW | R&R | DCV0 MRD before 2019-11-20 | DCV1 60% MRD before 2020-02-14 | 100% MRD Before 2020-03-1 | EOL bit | MRD planned Delivery Time | U554 UE File | CX727 UE File | UE Sign Off Time | UI Delivery Time | UI Sign Off Time | Ford SPSS/PRD | Supplier's output (MRD, Q&A, RD…) | HMI interaction Spec | Ford Feature owner | Ford HMI Lead | BAIDU FO | DESAY FO | Comments | KO Meeting | Ambient/Trend | Titanium/ST Line | Ambient/Trend | Titanium/ST Line | Mid/High | Mid/High | Ford Bronco SUV | Ford Raptor F-150 Pickup truck | Ford Raptor F-150 Pickup truck |  | Lincoln Navigator Large SUV (3 row seat) | Explorer | Lincoln Sedan | Lincoln Sedan | Ford Mustang | Ford SUV 13.2 | Ford Suv 27 | Lincoln Suv 27 | Ford BEV | License/ED&T |  | File Location | Review status | risk | # of review | Planned Available date | Actual available date | Planned release date | Actual release date |  | Comments | Open item | FNV2 | Category | sub-function | IVI validate | FNV2 related featuers | 供应商模块 | report-dimension | Auto Test |  | Plan | Actual | Plan | Actual | Plan | Actual | Ford Raptor F-150 Pickup truck | Lincoln Navigator Large SUV (3 row seat) | Explorer | Lincoln Sedan | Ford Mustang | Ford SUV 13.2 | Ford Suv 27 | Lincoln Suv 27
1 | Basic features | EESE/System | Autosar |  | 100% | 0% | NA | Desay | x | x | x | n.a | N/A | N/A | N/A |  |  |  | AUTOSAR SOW_2019.0-WGC1NJ5520MQ2-2.zip AUTOSAR\AUTOSAR SOW_2019.0-WGC1NJ5520MQ2.zip AUTOSAR\AUTOSAR SOW_2019.0.zip | 不需要输出MRD | N/A | Jian, Ashley (Yao.) <yjian@ford.com> / Song, Robert (J.) <jsong30@ford.com> | N/A | [11 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close | Mid |  | N.A | N.A | N.A | N.A | N.A | Desay Fully meet. No QA |  |  | Basic function | basic |  |  | General | core | N |  |  |  | DCV0 | DCV0 | DCV1.1 | DCV1.1 | bar: 29 to 32
2 | Basic features | EESE/System | Ford Ethernet |  | 90% | 0% | 10% | Desay | x - IP function | x | x | n.a | 2019-11-08 | N/A | N/A |  |  |  | AutomotiveEthernetHardwareReviewTestMethod-00.06.03.400-AB.docx AutomotiveEthernetLinkImplementationSpecification-00.06.01.001-AC.docx AutomotiveEthernetModuleLevelDesignVerificationMethod-00.06.01.301-AB.docx AutomotiveEthernetPhysicalLayerSpecification-00.06.03.003-AB.docx AutomotiveEthernetSoftwareReviewChecklist-00.06.01.402-AB.docx AutomotiveEthernetSwitchChecklist-00.06.01.403-AA.docx AutomotiveEthernetSwitchImplementationSpecification-00.06.01.002-AA.docx AutomotiveEthernetSystemLevelDesignVerificationMethod-00.06.01.313-AB.docx | Ford_MRD_Ethernet_V02.docx | N/A | Guo, Cheng Cheng (C.) <cguo12@ford.com> | N/A |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close | Mid |  | 2020-01-10 | 2020-02-04 | 2020-01-17 | 2020-01-20 | N.A | 1/13/2020: FO info clear, MRD to be available 1/14 2/5/2020: sign off |  |  | Basic function | basic |  | x | Ethernet | core | N |  |  |  | DCV0 | DCV0 | DCV1.1 | DCV1.1 | bar: 29 to 32
3 | Basic features | EESE/System | FPD LINK III |  | 100% | 0% | NA | Desay | x | x | x | n.a | N/A | N/A | N/A |  |  |  | FPDLinkIIICableandConnectorAssemblyDesignVerficationChecklist-00.06.01.306-AA.docx FPDLinkIIICableandConnectorAssemblySpecification-00.06.01.005-AA.docx FPDLinkIIIImplementationReviewChecklist-00.06.01.405-AA.docx FPDLinkIIILinkImplementationSpecification-00.0 | 不需要输出MRD | N/A | Guo, Cheng Cheng (C.) <cguo12@ford.com> | N/A |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close | Mid |  | N.A | N.A | N.A | N.A | N.A |  | 27" not ready, open item list will be provided after migrating this screen. / Feb. 2020 12/24/2019: ask Desay to fill checklist |  | Basic function | basic |  |  | General | core | N |  |  |  | DCV0 | DCV0 | DCV1.1 | DCV1.1 | bar: 29 to 32
4 | Basic features | EESE/System | Fully Ford ECU Diagnostic&EOL | Y | 90% | 10% | NA | Desay |  | x | x | n.a | 2020-01-10 | N/A | N/A |  |  |  | Phase4 Diag Req Sheet.xlsx | 合并到NO110 | N/A | Tian, Yuan (EESE.) <ytian22@ford.com> &Wang, Fin (X.Y.) <xwang65@ford.com> | N/A |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | CDD是由DESAY做 SPEC由Ford提供 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  | 1 | 2019-12-23 | 2019-12-23 | 2019-12-30 | 2019-12-30 | N.A | Mamei: check when able to finalize the requriements. 12/24/2019: QA upload today 12/27/2019: wait feedback from Desay 12/30/2019: desay FO confirmed, GitHub updated.Close |  |  | Basic function | EOL | x | x | Diagnostic | core | N |  |  |  | DCV1 | DCV2 | DCV3 | DCV3
5 | Basic features | EESE/System | Ford Cyber Security Requirements | Y | 50% | 50% | NA | Desay/Baidu |  | x | x | n.a | NA | 【林肯U554】_ID5_车机管家_V1.31_20200423.pdf | 【福特CX727】_ID5_车机管家_V1.31_20200423 |  |  |  | App_signing_requirements_ver 1.3.pdf Bluetooth_Security_Spec_1.0.docx C.13 Ford_CyberAssurance-SOW_ReleaseV1.3(EE).doc FESN Generation Spec_V0.6.pdf IVI Security Requirements v7.docx Key Material Requirements.docx Key Packaging Spec_V0.72.pdf Operating_Systems_Security_Requirements_RC3.docx Phase4 Security RR_20191024 .xlsx S26_Secure_Channel_v1_04_Release.doc Vehicle and Mobility Security Data Logging Standard.pdf Vehicle-Mobility-Security-Data-Logging_Standard_v06-04Apr18.pdf Vehicle_HotSpot_and_AP_Client_Specification_v.2_final.pdf Vehicle_to_Cloud_Security_Spec_1.1.pdf | Desay -不需要输出MRD Baidu - 车机管家MRD | N/A | Ding, Dean (W.) <wding14@ford.com> / Huang, Eric (E.H.) <chuang98@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 朴文军 piaowenjun@baidu.com | Ding Yunrong(Yunrong.Ding@desay-svautomotive.com) | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2019-12-30 | 2020-01-06 | 2020-01-06 | 2020-03-03 | F | Desay: Security_QA.xlsx Baidu: 1/2/2020: MRD available, Ford FO check 1/8/2020: Baidu mail FO to push the feedback 1/9/2020: send today 1/10/2020: postpone to today 1/13/2020: SunYing mail 2/6/2020: sign off for CD542 3/3/2020: scope change: key package process migrated from Supply feed. - confrmed with FO. | 2/6/2020: other program status not clear |  | Basic function | Cyber security |  | x | 安全 | core | N |  |  |  | R00 | ? | DCV3 | R00 | bar: 29 to 32
6 | Basic features | EESE/System | Ford Software development Requirements |  | 50% | 50% | NA | Desay |  | x | x | n.a | NA | N/A | N/A |  |  |  | 2018_1_Release_of_Generic_eSOW_SW_Attachment.zip |  | N/A | Jian, Ashley (Yao.) <yjian@ford.com> | N/A |  | Liu Xiaogang | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | N.A |  |  | N.A | N.A | N.A | N.A | N.A | Output: regular TDR meeting minutes |  |  | N.A | N.A |  |  | N/A | bar: 29 to 32
7 | Basic features | EC Inhouse | Implement/Integrate Ford SOA Structure |  | 90% | 10% |  | Desay |  | x | x | n.a | 2020-01-10 | N/A | N/A |  |  |  | pending by Dapeng's input | SOAGateway MRD-v0.2.docx | N/A | Liu, Dapeng (D.) <dliu79@ford.com> | N/A |  | Ding Yunrong(Yunrong.Ding@desay-svautomotive.com) | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2020-01-10 | 2020-02-28 | 2020-01-17 | 2020-03-02 | D | 1/13/2020: Desay check today 2/12/2020: plan to close this before 2020/2/28: not linked to UE/UI, requirements are clear, send mail to close 3/2/2020: development on-going, tracking separately |  | x | FNV2 | FNV2-basic |  | x | General | core | N |  |  |  | DCV0 | DCV0 | DCV1.1 | DCV1.1 | bar: 29 to 32
8 | Vehicle Features/Interfaces | EESE/System | Welcome&Farewell | Y | 90% | 10% | NA | Desay |  | x | x | tbd - animation (DE00 reserve) | 2020-12-20 | N/A, HMI involve | N/A, HMI involve |  | 2020-01-13 | 2020-01-27 | ReqSTD-2019-08-20-21-45_FORD.pdf ReqSTD-2019-08-20-21-46_LINCOLN.pdf WelcomeFarewell_Spec v2.pdf | Ford_MRD_WelcomeFarewell.docx | H22g_SYNC4_Welcome_Power_Modes_RELEASED_v1_02_MY21 | Chen Huizhen HCHEN188@ford.com | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Pan Juan(Juan.Pan@desay-svautomotive.com) | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-09 | 2020-01-13 | 2020-01-16 | 2020-01-16 | N.A | 12/25/2019: info new date today 12/30/2019: no new plan 1/6/2020: replan to 1/9 1/10/2020: Desay on-going 1/13/2020: MRD available today 1/16/2020: sign off |  |  | Vehicle related | Welcome/farewell |  |  | Power | basic | Y |  |  |  | DCV3 | DCV4 | DCV3 | R00 | bar: 29 to 32
9 | Vehicle Features/Interfaces | EESE/IVI(Roger) | Alerts/Chimes | Y | 90% | 10% | NA | Desay |  | x | x | DE05 Byte 3, bit 3(DSO or normal) | 2019-12-15 | N/A | N/A |  |  |  | Alerts APIM Imp Guide v1.2 May 3, 2017.xlsx Alerts APIM SPSS v1.2 May 3, 2017.pdf RQT-001502-012992_12 Chime Sound Quality.pdf | 合并到NO84 | N/A | Li Xuedong XLI244@ford.com | N/A |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/Alerts_Chime | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2019-12-24 | N.A | Desay: maiil the open questionsm 2019.12.20 12/24/2019: no open item list, confirmed with FO |  |  | Chime management | Chime management | x |  | Audio | core | Y |  |  |  | DCV0 | DCV0 | DCV1.1 | R00 | bar: 29 to 32
10 | Vehicle Features/Interfaces | EESE/System | Mykey | Y | 90% | 10% |  | Desay |  |  | x | yes |  | pending- to be cancelled | N/A |  |  |  | MyKey Settings In CenterStack SPSS v1.4 July 9, 2019.pdf | Mykey_Setting.docx |  | Xu, Xiao Kang (X.) <xxu71@ford.com>/Sun, Evan (Yi.) <ysun15@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [9 empty] | N | N | N | N | N | N | N | N | N | N | N | N | ED&T | Y |  | close |  |  | 2020-02-20 | 2020-02-12 | 2020-02-27 | 2020-02-19 | D | 2/6/2020: supplier to provide plan date 2/12/2020: MRD send to FO 2/19/2020: sign off |  |  | Vehicle related | MyKey |  |  | setting | bar: 29 to 32
11 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Ford Vehicle Settings On IVI [include: AutoHold, AutoStartStop.] | Y | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-15 | 【林肯554】车辆设置_车门解锁密码_ID11_V1.5_20200417 【林肯U554】系统设置一级菜单_ID11_V1.4_20200508 【林肯U554】车辆控制_ID11_V2.1_ 20200331 | 【CX727】车辆设置_车门解锁密码_ID11_V1.2_20200429 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx FBMP APIM SPSS v1.3 May 8, 2017 Vehicle Settings APIM SPSS v1.19 Oct 30, 2019 Auto Hold APIM SPSS v1.1 Feb 20, 2017 Auto Start Stop SPSS v1.1 Oct 25, 2018 | 【phase4-Vehicle Setting-总结】_ForDesay.xlsx | H31a_SYNC4_Settings_R_v0_40_MY21 H31k_SYNC4_Settings_R_v0_36_MY21 H31k_Supplement_SYNC4_R_v0_10_MY21 | Chen, Emma (J.) <jchen276@ford.com>/Wang, Fin | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/Ford%20Vehicle%20Settings%20On%20IVI | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2020-01-11 | N.A | briefing close. Waiting OIL Plan to frozen one version before 12.23 12/24/2019: delay to today 12/27/2019: wait feedback from Desay 12/30/2019: consolidated OIL and file not archived. 1/6/2020: OIL to be ready on 1/7 1/10/2020: plan to sign off 1/11/2020: sign off | Some HMI open; Configuration bits - to be updated and reviewed by diag/Fin |  | Vehicle related | Vehicle setting | x |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | R00 | bar: 29 to 32
12 | Vehicle Features/Interfaces | EESE/DI | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | Y | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-15 | 林肯U554MCA空调设置_ID12_v1.8_20200418 | 【福特727】空调设置_ID12_V1.6_20200314 |  |  |  | Climate Control CGEA 1.3 APIM Imp Guide ver1.1 Oct 30, 2014.xlsx Climate Control CGEA 1.3 APIM SPSS ver1.1 Oct 30, 2014.docx Climate Control CGEA 1.3 APIM SPSS ver1.1 Oct 30, 2014.pdf | Ford_MRD_空调_TBD_v1.7_20200222.docx 空调页面说明_v1.5.xls 空调页面说明_硬按键软按键.xlsx | H26g_SYNC4_Auto_Air_Refresh_Gen_1_Plus_RELEASED_v2_03_MY21 H26f_SYNC4_Climate_Control_RELEASED_v1_06_MY21 H26h_SYNC4_Climate_Auto_Seats_RELEASED_v1_04_MY21 | Li, Jun (J.) <jli198@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 1 | 2019-12-15 | 2019-12-19 | 2019-12-26 | 2020-02-07 | N.A | reviewed on Dec. 20th; Updated MRD to be ready before 25th. 12/24/2019: 2nd version sent to Ford FO. 12/30/2019: 2nd round meeting conducted, need HMI support for open items. 1/6/2020: Desay update and info date 1/10/2020: on-site review 1/13/2020: Desay consolidate and mail 2/4/2020: FO send out mail. arrange meeting 2/6/2020: meeting today to finalize 2/7/2020: plan to sign off; sign off |  |  | Vehicle related | HVAC |  | x | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV2.1 | bar: 29 to 32
13 | Vehicle Features/Interfaces | CVPP | Ford TCU Related features (Modem Reset, WiFi, WiFi Hotspot)- TCU transfer CAN data to IVI | y | 90% | 10% |  | Desay |  | x | x | always enable | 2019-12-15 | 【林肯U554】IOD实时车况_ID138&141&142&143&144&145&146_V1.4_20200416 【林肯U554】Wi-Fi 设置_ID13&100_V1.2_20200309 【林肯U554】WiFi热点_ID13&51&100_V1.7_20200310 | 【福特727】Wi-Fi热点_ID 13&51&100_V1.2_20200017 【福特727】WIFI设置_ID13&100_V1.4_20200318 |  |  |  | WiFi Hotspot OnBoardClient v2 SPSS v1.3 July 15, 2019 | WiFi Hotspot OnBoardClient v2 Imp Guide v1.3_Q&A_20200205.xlsx | H31a_SYNC4_Settings_R_v0_40_MY21 H31i_SYNC4_Vehicle_Hotspot_Settings_RELEASED_v1_02 H31i_InfoBook _Wi-Fi_Hotspot_v0_6 H31j_SYNC4_Connectivity_Settings_R_v0_08_MY21_RELEASED | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu guanghui(Guanghui.Liu@desay-svautomotive.com) & Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2019-12-23 | 2020-01-10 | 2020-01-17 | 2020-02-06 | N.A | Desay development on-going, UE/UI - based on current Desay proposal. 12/23/2019: send MRD to PanYuan 12/24/2019: delay to today 12/27/2019: wait Ford FO - 1/2 1/6/2020: Desay update after internal review 1/10/2020: MRD available, plan on-site review at Shanghai 1/13/2020: contact FO - 86-21-20322959 2/4/2020: plan to sign off 2/6/2020: sign off | to be updated | x | FNV2 | WIFI | x | x | WI-FI | CVPP |  |  |  |  | DCV1 | DCV3 | DCV2 | DCV3 | bar: 29 to 32
14 | Vehicle Features/Interfaces | EESE/IVI(Roger) | 支持与仪表盘互动/Supporting interaction with cluster（Phone/Media/Navi） | Y | 60% | 40% | NA | Desay |  | x | x | yes | 2019-12-15 | N/A | N/A |  |  |  | folder: cluster Interaction |  |  | IVI-Chen, James (J.) <jchen303@ford.com>&IPC Cao, Helen (H.) <hcao22@ford.com> | N/A | 原翼 yuanyi13@baidu.com/穆仁萍 v_murenping@baidu.com | Liu Chenxi(Chenxi.Liu@desay-svautomotive.com) | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-15 | 2019-12-15 | 2020-03-06 | 2020-03-10 | N.A | briefing close. Waiting OIL from desay 12/23/2019: 2 open items to be clarified by Ford FO. 12/24/2019: send mail to Ford FO. 12/27/2019: wait feedback from Desay 12/30/2019: no mail send to Ford FO. Delay 1/6/2020: plan to sign off 1/10/2020: Desay send out QA 1/13/2020: Desay push FO 2/10/2020: Desay review on-going, planned to be 2020/2/20 2/24/2020: updated MRD availalbe, send out tomorrow 2/28/2020: not linked to UE/UI 3/10/2020: Sign off |  |  | Vehicle related | Cluster | x |  | cluster interaction | basic | N |  |  |  | DCV2 | R00 | DCV3 | R00 | bar: 29 to 32
15 | Vehicle Features/Interfaces | EESE/IVI(Diven) | Zone Lighting (360 Lighting) |  | 95% | 5% |  | Desay |  | x | x | yes | [6 empty] | PRD Zone Lighting PRD v1.13.pdf | Zone Lighting APIM Imp Guide v1.4_20200228.xlsx | H31a_SYNC4_Settings_R_v0_40_MY21 (refer to Zone lighting section) | Ding, Xiaoyu (X.) <xding15@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> | [9 empty] | N | N | Y | N | N | N | N | N | N | N | N | N | ED&T | Y |  | close |  |  | 2020-01-13 | 2020-02-19 | 2020-01-20 | 2020-02-28 | N.A | 1/6/2020: Desay replan 1/13/2020: MRD avaialble today 2/12/2020: plan to close before 2/18 2/14/2020: transfer to EESE @diven 2/24/2020: open item list send out today; 4/21/2020: cancel this feature based on the program's decision |  | x |  |  |  |  | zone lighting | bar: 29 to 32
16 | Vehicle Features/Interfaces | CVPP | Multi Module OTA (including: USB Update for TCU and ECG; IVI VMCU, CCPU...) |  | 90% | 10% |  | Desay |  |  | x | always enable | 2020-01-05 | 【福特U554】MMOTA升级_ID16_v1.8_20200422 | 福特CX727_MMOTA升级_ID16_v1.3_20200513 |  |  |  | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf 533310_C_001_In Vehicle Software Update Feature Doc v2.1.pdf 547923_A_001_IVSU Vehicle Function Download Manager v1.0.pdf 584761_A_002_Fast OTA FNV2 IVSU Requirements v1.0.docx IVSU_Cloud_Function_Diff_Generator v1.0.docx IVSU_Vehicle_Function_Diff Updater_ v1.0.docx |  | H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_8_MY21 | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Desay IOV | 文档是否包含TCU OTA？ |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y |  | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/MMOTA | close |  |  | 2020-02-14 |  |  |  | D | 1/6/2020: replan today 1/10/2020: reschedule to DCV2 2/20/2020: Suppliler not officially on board - business pending |  | x | FNV2 | OTA | x | x | OTA | CVPP |  |  |  |  | R05 | R06? | R06 | R05
17 | Vehicle Features/Interfaces | EESE/IVI(Diven) | Location Service （仪表指南针，etc.） | Y | 95% | 5% | NA | Desay |  | x | x | always enable | 2019-12-15 | N/A | N/A |  |  |  | Location Service APIM SPSS v1.10 July 10, 2019 Location Service APIM Imp Guide v1.10 July 10, 2019 | Ford_MRD_LocationService_V03.docx | No HMI UE required as onfirmed with FO. | Yu, Diven (D.W.) <dyu12@ford.com> | N/A |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [9 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-15 | 2019-12-23 | 2019-12-30 | 2019-01-19 | N.A | Desay prepare questions to Diven for offline check 12/23/2019: MRD send to Diven for check 12/24/2019: delay to today 12/27/2019: pending fedback from Ford FO 1/6/2020: Desay mail to Diven 1/10/2020: Desay provide OIL, plan to sign off 2/5/2020: sign off |  |  | Vehicle related | Navigation |  |  | Location service | core | N |  |  |  | DCV1 | DCV1 | DCV2 | DCV3 | bar: 29 to 32
18 | Vehicle Features/Interfaces | CVPP | PaaK | Y | 95% | 5% | NA | Desay |  | x | x | yes |  | 【林肯U554】系统复位&连接复位_ID57_V1.4_20200325.pdf | 【福特727】系统复位&互联复位_ID18&57_v1.2_20200422 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | PRD 【更新】【Phase2林肯】PAAK智能共享手机钥匙MRD_2019_4_12-v1.5.pdf | Customer Connectivity Settings Client APIM SPSS v1.4 imp Guide v1.6_20200228.xlsx | H31m_SYNC4_Backup Ignition_R_v1.3_MY21 H31k_SYNC4_Settings_R_v0_36_MY21 | Zhang, Yan (Y.) <YZHAN481@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> | [9 empty] | N | N | N | Y | Y | Y | Y | N | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-14 | 2020-02-13 | 2020-02-21 | 2020-02-14 | N.A | 2/12/2020: plan to close before 2/18 2/14/2020: sign off |  | x | FNV2 | PAAK |  | x | setting | CVPP |  |  |  |  | DCV1 | DCV3 | DCV2 | DCV3 | bar: 29 to 32
19 | Vehicle Features/Interfaces | EESE/System | Ford Enhanced Memory V2 | Y | 45% | 55% |  | Baidu |  | x | x | DE04 B4b7 | 2020-12-20 | check with FO | check with FO |  |  |  | SPSS Driver profiles SYNC+ SPSS 03252019.pdf | 【福特phase4】MRD_Enhance memory_CD542_V1.2_2020_02_20 | SYNCFord HMI Requirement_Enhanced Memory_DRAFT_ v0.5 | Xu, Xiao Kang (X.) <xxu71@ford.com>/Sun, Evan (Yi.) <ysun15@ford.com> Xu, Andy (X.) <XXU71@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | 苏争 _suzheng01@baidu.com | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | OPT | Y | Y | Y | N | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-13 | 2020-02-03 | 2020-01-20 |  | N.A | 12/24/2019: Baidu provide new plan 1/8/2020: meeting planned this Thursday 1/10/2020: Baidu provide proposal and review on-site. 2/3/2020: pending feedback from Ford FO 2/4/2020: logic related to account will be covered in "个人账号“功能；- arrange a meeting to discuss follow up actions 2/6/2020: pending due to Ford FO 2/11/2020: MRD to be updated within this week. 2/13/2020: MRD updated and send to Ford FO. 2/25/2020: sign off for 542/625. 4/15/2020: reopen for BU programs 4/23/2020: MRD avaiable, to be reviwed this week. | BU program open |  | Vehicle related | Enhanced memory |  | x | 账号 | basic | N |  |  |  | R04 |  | DCV3 | R04
20 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Ford Clock Strategy | Y | 95% | 5% | NA | Desay |  | x | x | always enable | 2020-12-20 | 【林肯U554】车辆控制_ID20&24&27&33&35&38&43&45_V1.6_ 20200316 | lisa wang |  |  |  | Global Clock Strategy Specification Ver 1.8.docm Global Clock Strategy Specification Ver 1.8.docx Global Clock Strategy Specification Ver 1.8.pdf APIM Clock Strategy v1.4 Feb 6 2014.pdf | 合并到NO11 | H31a_SYNC4_Settings_R_v0_40_MY21 | Wang, Fin (X.Y.) <xwang65@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-25 | 2020-01-09 | 2020-01-01 | 2020-01-13 | N.A | 12/25/2019: discuss with FO today 12/30/2019: delay 1/6/2020: replan tomorrow 1/9/2020: plan to sign off 1/10/2020: re-archive by Desay, plan to sign off 1/13/2020: sign off |  |  | Vehicle related | Navigation | x |  | clock | core | N |  |  |  | DCV1 | DCV1 | DCV2 | DCV3
21 | Vehicle Features/Interfaces | EESE/IVI(Roger) | Support Ford external DSP module by A2B | Y | 95% | 5% | NA | Desay | x | x | x | yes | 2019-11-04 | N/A | N/A |  |  |  | Analog Devices A2B Hardware Review 000603.512 AD.doc Analog Devices A2B link Data Link and Physical Layer 000603 501 AD.doc Analog Devices A2B Link Implementation Specification V1_1.docx | Ford IVI SW Q&A_Audio&A2B.xlsx | N/A | Li Xuedong XLI244@ford.com | N/A |  | Xu jianjun(Jianjun.Xu@desay-svautomotive.com) | check for update |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/A2B | close | low |  | N.A | N.A | N.A | N.A | N.A | Audio_QA.xlsx |  |  | Chime management | Chime management | x |  | audio | basic | N |  |  |  | DCV0 | DCV0 | DCV1.1 | R00
22 | Vehicle Features/Interfaces | EESE/IVI(PMT1)(Forrest) | 车窗控制设置 Windows Control setting only |  | 95% | 5% |  | Desay |  |  | x | yes |  | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  |  | 合并到NO11 |  | chen, Emma <jchen276@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-16 | 2020-01-17 | 2020-01-23 | 2020-01-17 | N.A | 2/6/2020: supplier to provide plan date 2/24/2020: LIN database? |  |  | Vehicle related | Vehicle setting | x |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
23 | Vehicle Features/Interfaces | EESE/IVI(Diven) | 天窗控制 Sunroof Control |  | 95% | 5% |  | Desay |  | x | x | yes - missed? | 2019-12-30 | N/A | N/A |  |  |  | Requirememt ready before Dec. 20th. | 合并到NO11 |  | Qi, Xuliang<xqi14@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | 刘韧 v_liuren@baidu.com（语音） | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | N | N | N | N | N | N | N | N | Y | Y | Y | Y | Y | N | N | ED&T | Y |  | close |  |  | 2020-02-20 | 2020-02-25 | 2020-02-27 | 2020-02-27 | N.A | 1/9/2020: need Ford FO's input. 1/10/2020: Desay push FO 1/13/2020: Ford FO provide spec 1/15 1/17/2020: spec & LIN provided, Desay FO check 1/17/2020: plan to sign off | LIN open |  |  |  | x |  | setting | basic | Y |  |  |  | DCV2 | R00
24 | Vehicle Features/Interfaces | EESE/IVI(PMT1)(Forrest) | 后备箱控制/Trunk Control including liftgate/… |  | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-15 | 【林肯U554】车辆控制_ID20&24&27&33&35&38&43&45_V1.6_ 20200316 | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  | Trunk_Softswitch_interfaceClient.txt LiftGate Softswitch Interface Client SPSS v1.2 June 21 2019 | 合并到NO11 | H31a_SYNC4_Settings_R_v0_40_MY21 | Chen, Emma (J.) <jchen276@ford.com>/ Li, Xuedong (X.) <xli244@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | 刘韧 v_liuren@baidu.com（语音） | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2019-12-23 | N.A | combine to vehicle setting 12/23/2019: no open item for this function. |  |  | Vehicle related | Vehicle setting | x |  | setting | basic | Y |  |  |  | DCV2 | DCV3 | DCV2 | DCV3
25 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Ford车辆系统降噪/Ford Noise reduction ANC | Y | 95% | 5% | NA | Desay | x - basic function - ANC Microphone input | x - basic function w/o calibration | x | yes | 2019-11-04 | N/A | N/A |  |  |  | SPSS ANC SPSS v1.4 Oct 7 2013.pdf | Ford IVI SW Q&A_Audio&A2B.xlsx | N/A | Wang, Fin (X.Y.) <xwang65@ford.com>/Yao, Keita (Y.) <yyao21@ford.com> | N/A |  | Xu jianjun(Jianjun.Xu@desay-svautomotive.com) | check for update |  | N | N | N | N | N | N | N | N | N | N | Y | N | Y | Y | Y | Option | Option | Option | N | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/ANC | close | low |  | N.A | N.A | N.A | N.A | N.A | Audio_QA.xlsx |  |  | Chime management | Chime management | x |  | Audio | extend | Y
26 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | 发动机声音增强/Engine Sound Enhancement | Y | 95% | 5% | NA | Desay |  | x | x | yes | NA | N/A | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  | Electrical Sound Enhancement SPSS V1.2 Oct 27, 2017.docx Electrical Sound Enhancement SPSS_Diagnostics.pdf | 不需要输出MRD | N/A | Wang, Fin (X.Y.) <xwang65@ford.com>/Yao, Keita (Y.) <yyao21@ford.com> | N/A |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | N | Y | Y | Y | Y | N | Y(opt) | Y(opt) | Y | Option | Option | Option | Y | ED&T | Y |  | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2020-01-17 | N.A | Desay provide OIL 12/24/2019: no OIL, Desay follow spec, no OIL. |  |  | Chime management | Chime management | x |  | Audio | extend | Y |  |  |  | DCV4 | R00 | R00 | R00
27 | Vehicle Features/Interfaces | EESE/IVI(PMT3)(Forrest) | 驾驶模式选择/SDM(Selectable Drive Mode) | Y | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-15 | 【林肯U554】车辆控制_ID20&24&27&33&35&38&43&45_V1.6_ 20200316 | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  | Selectable Drive Mode APIM Imp Guide v1.2 Aug 21, 2019.xlsx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.docx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.pdf | 不需要输出MRD |  | Zhang Spring JZHAN136@ford.com | Hu, Pin (P.) <phu13@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-25 | 2020-01-10 | 2020-01-01 | 2020-01-15 | N.A | HMI: Desay prepare UE 12/23/2019: SPSS is ok, while HMI need to be provided. 12/30/2019: need Desay to provide HMI 1/6/2020: Desay mail to FO/HMI 1/10/2020: Ford HMI can not accept the prospoal - open item Desay provide OIL today 1/13/2020: delay to today 1/15/2020: sign off | HMI open |  | Vehicle related | SDM |  |  | setting | core | Y |  |  |  | DCV2 | DCV3 | DCV2 | R00
28 | 驾驶辅助/Drive assist | CVPP | V2I Setting |  | 90% | 10% |  | Desay |  | x | x | yes |  | 【林肯U554】车辆控制_V2I设置_ID28_V1.1_20200424 | lisa wang |  |  |  | PRD V2I_CVPP_Ford_PRD V2.4_20191012.docx |  |  | Fan, Henry (H.) <hfan11@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-03-06 | 2020-03-10 | 2020-03-11 | 2020-04-10 | F | 1/6/2020: Desay replan 1/13/2020: replan 1/15/2020: cancel 2/28/2020: reopen- C/O phase 2, FNV2 change 3/22/2020: FO feedback next Monday |  |  |  |  | x | x | setting | CVPP |  |  |  |  | R04 | R05 | DCV2 | R05
29 | 驾驶辅助/Drive assist | DAT | Off Road Front View Camera | Y | 90% | 10% | NA | Desay |  | x | x | yes | 2019-12-20 | N/A | N/A |  |  |  | Off-road Front View Camera APIM Implementation Guide ver1_0 May 31 2013.xls Off-road Front View Camera APIM SPSS ver1_0 May 31 2013.doc Off-road Front View Camera APIM SPSS ver1_0 May 31 2013.pdf | Ford_MRD_Off-road_FrontViewCamera_V02.docx | H36k_SYNC4_Camera_Systems_R_v0_20_MY21 | Li, Xin<xli268@ford.com>/Wang, Tom (X.) <xwang190@ford.com>/Zheng, Tina (T.) <tzheng4@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | N | N | N | N | N | N | Y | Y | Y | Y | N | N | N | N | N | N | N | N | N | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-14 | 2020-01-17 | 2020-01-17 | N.A | 12/30/2019: replan 1/6/2020: replan 1/13/2020: desay check and feedback 2/4/2020: sign off |  |  | Driver assist | Driver assist HMI | x |  | camera | basic | Y
30 | 驾驶辅助/Drive assist | DAT | Electronic Horizon/ADAS Horizon(Base on ADAS V2 specification) | Y | 30% | 70% |  | Baidu |  | x | x | DE04 B6b7 | 2019-12-20 | N/A | N/A |  |  |  | 200v2.0.4-D2.2-ADASIS_v2_Specification.0.pdf 20140602 ADAS Horizon Sensor Requirements-v93.doc 20140602 ADASISv2_Data_Dictionary_Clarification.docx 20140602 EH MPP algorithm description.doc EH data dictionary.xlsx eh_data_mux2.dbc EH_Signal_Usage.xlsx | 无MRD |  | Li, Cindy (Y.) <yli316@ford.com> | N/A | 原翼 yuanyi13@baidu.com | Wang Dong <Dong.Wang@desay-svautomotive.com> Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> | C/O Phase3 |  | N | Y | N | Y | Y | Y | N | Y | Y | Y | Y | Y | Y | Y | N | TBC | Y | Y | Y | License | Y |  | close |  |  | 2019-01-03 | 2020-01-06 | 2019-01-10 | 2020-03-02 | N.A | 12/23/2019: MRD available today 12/24/2019: MRD delay to 12/24. 12/25/2019: arrange meeting tomorrow. 12/27/2019: Baidu check and feedback 12/30/2019: SPSS added, baidu check, meeting arranged in 1/2 1/2/2020: Baidu check and feedback today 1/6/2020: C/O phase 2; need to cascade the interface requirement to Desay 1/8/2020: Baidu contact Desay; 1/9/2020: plan to close today 1/10/2020: arrange meeting and feedback today 1/13/2020: Desay arrange a meeting 2/3/2020: arrange a meeting by Baidu 2/6/2020: pending due to Desay 2/11/2020: Discuss with FO for the change 2/17/2020: hardware change for iACC; SW share for both 32G & 64G. | open: iACC hardware issue |  |  |  |  | x - iACC | 地图 | basic | N |  |  |  | DCV0 | DCV0 | DCV2 | DCV3
31 | 驾驶辅助/Drive assist | DAT | Semi Assisted Parking (SIPa, SIPe, SOPa) | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 | [5 empty] | Active Park Assist V2 APIM Imp Guide v1.10 Oct 18, 2019.xlsx Active Park Assist V2 APIM SPSS v1.10 Oct 18, 2019.docx Active Park Assist V2 APIM SPSS v1.10 Oct 18, 2019.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | co phase2 requirement | Lu, Zaikai (Z.) <zlu29@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | ED&T | Y |  | cancel | [6 empty] | N.A | Desay prepare UE 12/27/2019: postpone this item to Jan. 10th. 1/10/2020: on-site review 1/13/2020: MRD update? 2/4/2020: sign off 3/26/2020: cancel based on DAT input |  |  | Driver assist | Driver assist HMI
32 | 驾驶辅助/Drive assist | DAT | Fully Assisted Parking (FIPa, FIPe, FOPa)/全自动泊车 | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | N/A | 【CX727】自动泊车_ID32_V2.0_2020511 |  |  |  | Active Park Assist V2 APIM Imp Guide v1.10 Oct 18, 2019.xlsx Active Park Assist V2 APIM SPSS v1.10 Oct 18, 2019.docx Active Park Assist V2 APIM SPSS v1.10 Oct 18, 2019.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36m_SYNC4_APACSI_R_0_07_MY21 P36k_15P_SYNC4_Camera_R_v2_00_MY21 | Lu, Zaikai (Z.) <zlu29@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | Y | N | Y | Y | Y | Y | N | N | N | Y | Y | Y | Y | N | N | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2020-01-10 | 2020-02-04 | N.A | Desay prepare UE 12/27/2019: postpone this item to Jan. 10th. 1/10/2020: on-site review 1/13/2020: MRD update? 2/4/2020: sign off | open item: startup time |  | Driver assist | Driver assist HMI |  |  | camera | extend | Y |  |  |  | DCV3 | R05 | DCV3 | R00
33 | 驾驶辅助/Drive assist | DAT | TSR/Speed Limit and Overtaking Information Function (SLOIF) | Y | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID20&24&27&33&35&38&43&45_V1.6_ 20200316 | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Song, Amy (S.) <ssong18@ford.com> Cui, Victor (M.) <MCUI5@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting |  |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
34 | 驾驶辅助/Drive assist | DAT | DAT 2.0 Base Features on IVI |  | 95% | 5% |  | Desay |  | x | x |  | 2019-12-20 | [8 empty] | Zhang, Kerry (Y.) <yzhan142@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | N | N | N | Y | ED&T | Y |  | cancel | [7 empty] | 12/30/2019: checked, added missed items. Obsolete this one.
35 | 驾驶辅助/Drive assist | DAT | DAT-High Way Assist (Active drive assist) |  | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID20&24&27&33&35&38&43&45_V1.6_ 20200316 | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx Location Service APIM Imp Guide v1.10 July 10, 2019.xlsx Location Service APIM SPSS v1.10 July 10, 2019.docx Location Service APIM SPSS v1.10 July 10, 2019.pdf | 合并到NO11 |  | Ni, Anthony (H.A.) <hni1@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | N | N | N | N | Y | N | Y | Y | N | N | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist setting |  | x | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
36 | 驾驶辅助/Drive assist | DAT | Rear View Camera (RVC) | Y | 95% | 5% | NA | Desay | x - HD and CVBS | x | x | yes | 2019-11-04 | 【林肯U554交互】倒车影像&CTA&RBA_ID36&37&39&40&41&42&214_V1.4_20200324 【林肯U554交互】RVC倒车影像_ID36_V1.2_20191228 【林肯U554交互】车影像CTA-RBA_ID36&37&39&40&41&42&214_V1.4_20200318 | 【福特727】RVC倒车影像_ID36&37&41&42&214_V1.9_20200430 |  |  |  | Stand-alone Rear View Camera APIM SPSS v2.7 Apr 26, 2019 Stand-alone Rear View Camera APIM Imp Guide v2.7 Apr 26, 2019 Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36k_SYNC4_Camera_Systems_R_v0_20_MY21 H36n_SYNC4_Camera_Shortcut_Key_R_0_02_MY21 H36q_SYNC4_Boundary_Alert_R_0_02_MY21 H36r_SYNC4_VideoOnDemand_R_0_03_MY21 | Chen Xuan <XCHEN161@ford.com>/Zheng, Tina (T.) <tzheng4@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com | check for update |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 3 | 2019-12-27 | 2019-12-30 | 2020-01-03 | 2020-01-11 | N.A | 12/23/2019: re-open 12/25/2019: discuss with FO today 12/30/2019: MRD available, meeting? 1/6/2020: Desay mail 1/10/2020: on-site review, plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist HMI |  |  | camera | basic | N |  |  |  | DCV2 | R00 | DCV3 | DCV3
37 | 驾驶辅助/Drive assist | DAT | Multi View Camera-360° | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554交互】倒车影像&CTA&RBA_ID36&37&39&40&41&42&214_V1.4_20200324 【林肯U554交互】车影像CTA-RBA_ID36&37&39&40&41&42&214_V1.4_20200318 | 【福特727】RVC倒车影像_ID36&37&41&42&214_V1.9_20200430 |  |  |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36j SYNC GEN3 Driver Assist MultiCameraSystem RELEASED v2_5_release H36k SHMI TRG and MultiCamera System RELEASED v4_4 | Chen Xuan <XCHEN161@ford.com>/Wang, Tom (X.) <xwang190@ford.com>/Zheng, Tina (T.) <tzheng4@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | N | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-30 | 2020-01-06 | 2020-01-11 | N.A | 12/23/2019: re-open 12/25/2019: discuss with FO today 12/30/2019: MRD available, meeting? 1/6/2020: Desay mail 1/10/2020: on-site review, plan to sign off 1/11/2020: sign off | 2 open items: - Variant info - performance to be improved |  | Driver assist | Driver assist HMI |  |  | camera | extend | N |  |  |  | DCV2 | R00 | DCV3 | R00
38 | 驾驶辅助/Drive assist | DAT | LCA Lane centering assist (replace TJA) | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID20&24&27&33&35&38&43&45_V1.6_ 20200316 | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Ni, Anthony (H.A.) <hni1@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
39 | 驾驶辅助/Drive assist | DAT | Front&Side Parking Radar | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554交互】倒车影像&CTA&RBA_ID36&37&39&40&41&42&214_V1.4_20200324 【林肯U554交互】车影像CTA-RBA_ID36&37&39&40&41&42&214_V1.4_20200318 | 【U554&702&725&542&727】雷达图_ID39&40_V1.5_20200410 |  |  |  | Visual Park Assist Graphic Client V2 APIM Imp Guide v1.6 Dec 8, 2017.xlsx Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.docx Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx |  | Lu, Zaikai (Z.) <zlu29@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-04 | N.A | 12/30/2019: replan 1/13/2020: desay check 2/4/2020: sign off |  |  | Driver assist | Driver assist setting | x |  | camera | core | Y |  |  |  | DCV1 | R00 | DCV2 | DCV3
40 | 驾驶辅助/Drive assist | DAT | Rear Parking Radar | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554交互】倒车影像&CTA&RBA_ID36&37&39&40&41&42&214_V1.4_20200324 【林肯U554交互】车影像CTA-RBA_ID36&37&39&40&41&42&214_V1.4_20200318 | 【U554&702&725&542&727】雷达图_ID39&40_V1.5_20200410 |  |  |  | Visual Park Assist Graphic Client V2 APIM Imp Guide v1.6 Dec 8, 2017.xlsx Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.docx Visual Park Assist Graphic Client V2 APIM SPSS v1.6 Dec 8, 2017.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx |  | Lu, Zaikai (Z.) <zlu29@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-04 | N.A | 12/30/2019: replan 1/13/2020: desay check 2/4/2020: sign off |  |  | Driver assist | Driver assist HMI | x |  | camera | core | Y |  |  |  | DCV1 | R00 | DCV2 | DCV3
41 | 驾驶辅助/Drive assist | DAT | Cross Traffic Alert | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554交互】倒车影像&CTA&RBA_ID36&37&39&40&41&42&214_V1.4_20200324 【林肯U554交互】车影像CTA-RBA_ID36&37&39&40&41&42&214_V1.4_20200318 | 【福特727】RVC倒车影像_ID36&37&41&42&214_V1.9_20200430 |  |  |  | Cross Traffic Alert APIM Imp Guide v1.2 Mar 11, 2016.xlsx Cross Traffic Alert APIM SPSS v1.2 Mar 11, 2016.docx Cross Traffic Alert APIM SPSS v1.2 Mar 11, 2016.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx |  | Zhou, Wu (W.) <wzhou44@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 3 | 2019-12-27 | 2019-12-30 | 2020-01-06 | 2020-01-11 | N.A | 12/23/2019: re-open 12/25/2019: discuss with FO today 12/30/2019: MRD available, meeting? 1/6/2020: Desay mail 1/10/2020: on-site review, plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist HMI | x |  | camera | basic | Y |  |  |  | DCV1 | R04 | DCV2 | DCV3
42 | 驾驶辅助/Drive assist | DAT | Reverse Brake Assist |  | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554交互】倒车影像&CTA&RBA_ID36&37&39&40&41&42&214_V1.4_20200324 【林肯U554交互】车影像CTA-RBA_ID36&37&39&40&41&42&214_V1.4_20200318 | 【福特727】RVC倒车影像_ID36&37&41&42&214_V1.9_20200430 |  |  |  | Reverse Brake Assist APIM Imp Guide v1.1 Feb 20, 2017.xlsx Reverse Brake Assist APIM SPSS v1.1 Feb 20, 2017.docx Reverse Brake Assist APIM SPSS v1.1 Feb 20, 2017.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx |  | Chen Xuan <XCHEN161@ford.com>/Wang, Tom (X.) <xwang190@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 3 | 2019-12-27 | 2019-12-30 | 2020-01-06 | 2020-01-11 | N.A | 12/23/2019: re-open 12/25/2019: discuss with FO today 12/30/2019: MRD available, meeting? 1/6/2020: Desay mail 1/10/2020: on-site review, plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist HMI | x |  | camera | core | Y |  |  |  | DCV1 | R00 | DCV2 | DCV3
43 | 驾驶辅助/Drive assist | DAT | Lane Change Warning & Aid (LCWA) / Blind Spot Assist | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID20&24&27&33&35&38&43&45_V1.6_ 20200316 | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Zhou, Wu (W.) <wzhou44@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off 1/11/2020: sign off |  |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
44 | 驾驶辅助/Drive assist | DAT | TSR/Speed Limit and Overtaking | Y | 95% | 5% | NA | Desay |  | x | x |  | 2019-12-20 | [8 empty] | Song, Amy (S.) <ssong18@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T | Y |  | cancel | [7 empty] | covered in setting
45 | 驾驶辅助/Drive assist | DAT | Intelligent Speed Assistance | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID20&24&27&33&35&38&43&45_V1.6_ 20200316 | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Song, Amy (S.) <ssong18@ford.com> Cui, Victor (M.) <MCUI5@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
46 | 驾驶辅助/Drive assist | DAT | Lane departure warning | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Zhang, Wayne (W.R.) <wzhan114@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
47 | 驾驶辅助/Drive assist | DAT | Lane keep aid | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Zhang, Wayne (W.R.) <wzhan114@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
48 | 驾驶辅助/Drive assist | DAT | Collision Mitigation (AEB) | Y | 95% | 5% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Zhu Jinpeng JZHU85@ford.com ??? | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | combine to item 11 12/30/2019: new requirement by Ford FO 1/6/2020: Desay mail to FO 1/10/2020: plan to sign off | check with FO for the new requirements - pending by Ford FO |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
49 | 驾驶辅助/Drive assist | DAT | Pre Collision Assist for intersections | Y | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Zhu Jinpeng JZHU86@ford.com ??? | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | combine to item 11 12/30/2019: new requirement by Ford FO 1/6/2020: Desay mail to FO | check with FO for the new requirements - pending by Ford FO |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | R00 | DCV2 | DCV3
50 | Related to TCU features | CVPP | Vehicle locator | y | 40% | 10% | 50% | Ford CVPP/Desay |  |  | x | always enable |  | N/A | N/A |  |  |  | PRD DUEROS_CVPP_Vehicle_Status_PRD_v1.1 |  |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-28 | 2020-03-06 | 2020-03-06 | 2020-03-06 | N.A | 2/6/2020: supplier to provide plan date 2/7/2020: arrange a meeting to discuss whether this function can be covered by "Location service" 2/27/2020: FO send out spec today. | open item: tbd |  | N.A | N.A |  | x | vehicle information | CVPP |  |  |  |  | DCV1 | DCV3 | DCV2 | DCV3
51 | Related to TCU features | CVPP | Wi-Fi hotspot - TCU as WIFI Server (IVI provide HMI) | y | 95% | 5% | NA | Desay |  | x | x | always enable | NA | 【林肯U554】WiFi热点_ID13&51&100_V1.7_20200310 | 【福特727】Wi-Fi热点_ID 13&51&100_V1.2_20200017 |  |  |  | PRD WiFi Hotspot PRD v1.3 Feature Bundle 5.docx | WiFi Hotspot OnBoardClient v2 Imp Guide v1.3_Q&A_20200205.xlsx | H31i_SYNC4_Vehicle_Hotspot_Settings_RELEASED_v1_02 H31i_InfoBook _Wi-Fi_Hotspot_v0_6 H31j_SYNC4_Connectivity_Settings_R_v0_08_MY21_RELEASED | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Zhang Yanlan (yanlan.Zhang@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-13 | 2019-12-23 | 2019-12-30 | 2020-02-05 | N.A | 12/23/2019:combined to TCU, send to Pan yuan for check. 12/24/2019: delay to today. 12/27/2019: pending by Ford FO 1/6/2020: Desay update after internal review 1/10/2020: draft mailed to Ford FO, plan on-site review 2/5/2020: sign off | open item: | x | FNV2 | WIFI | x | x | WI-Fi | CVPP |  |  |  |  | DCV1 | DCV3 | DCV2 | DCV3
52 | Related to TCU features | DAT | V2V |  | 95% | 5% |  | Desay |  |  | x | [10 empty] | Shan, Susan (D.) <dshan@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  |  |  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | ED&T | Y |  | cancel | [7 empty] | 1/15/2020: function cancelled
53 | Related to TCU features | CVPP | V2I Lite |  | 40% | 60% | NA | Baidu |  |  | x |  |  | check with Yaozhu/FO: | check with Yaozhu/FO: |  |  |  | PRD V2I_CVPP_Ford_PRD V2.4_20191012.docx | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Fan, Henry (H.) <hfan11@ford.com> Zhang, Wei (W.) | Sun, Xiao (X.) <xsun36@ford.com> | 原翼 yuanyi13@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-03-06 | 2020-03-10 | 2020-03-11 | 2020-03-30 | N.A | 1/15/2020: cancel 2/28/2020: reopen 2/28/2020: C/O phase, MRD to be updated 3/22/2020: 下周释放，没有风险 3/30/2020: sign off | [5 empty] | x | 百度地图 | CVPP |  |  |  |  | R04 |  | R04 | R05
54 | Related to TCU features | CVPP | 用户流量统计及购买/Cellular data purchase and management |  |  | 30% | 70% | Ford CVPP/Baidu |  |  | x |  | 2020-01-23 | UE developed by CVPP - check with FO | UE developed by CVPP - check with FO |  |  |  | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf | 无MRD |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-13 | 2020-02-10 | N.A | 2/6/2020: Baidu provide interface only; need Ford CVPP more plan 2/7/2020: Baidu interface described in the "Launcher" MRD. Pending due to Ford FO review. 2/10/2020: sign off |  |  | CVPP | carrier |  | x | 第三方集成应用 | CVPP |  |  |  |  | R00 | R00 | R05 | R04
55 | Ethernet SOA related features | EESE/IVI(Forrest) | Bezel Diagnostics | Y? | 90% | 10% | NA | Desay |  | x | x | always enable | 2019-12-25 | N/A | N/A |  |  |  | Diag APIM Ver 1.7 Diagnostics Logical to Physical CAN signal mapping Sep 7, 2018.docx | Ford_MRD_EngineeringMode_V02.docx |  | Wang, Fin (X.Y.) <xwang65@ford.com> | N/A |  | Chen Xiujing(Xiujing.Chen@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-14 | 2020-01-14 | 2020-01-21 | 2020-02-19 | D | 12/30/2019: no MRD/replan info 1/6/2020: replan to 1/10 1/13/2020: MRD to be available 1/14 2/12/2020: plan to sign off 2/17/2020: sign off |  | x | FNV2 | EOL | x | x | Diagnostic | core | N |  |  |  | DCV1 | DCV3 | DCV2 | DCV3
56 | Ethernet SOA related features | CVPP | Peripheral Provisioning |  | 90% | 10% | NA | Desay |  | x | x | always enable | 2020-01-10 | N/A | N/A |  |  |  | Peripheral Module Provisioning APIM Imp Guide v1.4 July 30, 2019.xlsx Peripheral Module Provisioning SPSS v1.4 July 30, 2019.docx Peripheral Module Provisioning SPSS v1.4 July 30, 2019.pdf | 合并到NO163 | N/A | Cui, Rebecca (H.) <hcui2@ford.com> | N/A |  | Chen Xiujing(Xiujing.Chen@desay-svautomotive.com) |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-02-19 | 2020-01-17 | 2020-02-28 | D | 12/30/2019: no MRD/replan info 1/6/2020: replan to 1/10 1/13/2020: Desay push FO 2/24/2020: send out this Tuesday |  |  | Basic function | EOL |  | x | Peripheral Module provisioning | CVPP |  |  |  |  | DCV1 | DCV3 | DCV2 | DCV3
57 | Ethernet SOA related features | CVPP | Embedded Modem Reset/Master reset |  | 90% | 10% |  | Desay |  | x | x | always enable | 2020-01-10 | 【林肯U554】系统复位&连接复位_ID57_V1.4_20200325 | 【福特727】系统复位&互联复位_ID18&57_v1.2_20200422 |  |  |  | PRD MasterReset-PRD.pdf | Customer Connectivity Settings Client APIM SPSS v1.4 imp Guide v1.6_20200228.xlsx | H31L_SYNC4_Reset_RELEASED_V4_02_MY21 | Ge, Haiqing (H.) <hge5@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-02-12 | 2020-01-17 | 2020-02-26 | N.A | 1/13/2020: Desay check 2/8/2020: pending by Ford FO 2/11/2020: plan to sign off on 2020/2/14 2/12/2020: MRD send to FO 2/24/2020: discussion on-going 2/26/2020: sign off |  | x | FNV2 | FNV2-basic |  | x | setting | CVPP |  |  |  |  | DCV2 | DCV3 | DCV2 | DCV3
58 | Features of IVI or Connect | EC Inhouse | Digital Owner's Manual(Demo Show) |  | 5% | 5% | 90% | Ford EESE |  |  | x |  |  | entrance clear. check with FO | entrance clear. check with FO |  |  |  | Digital Owners Manual Client SPSS v1.0 February 9, 2018 |  |  | Jiang, Wei (W.) <WJIANG33@ford.com> | Nong, Green (G.)< gnong@ford.com> |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | hold-on | hold-on | hold-on | hold-on | F | 2/6/2020: supplier to provide plan date 2/13/2020: plan date provided by in-house team 3/3/2020: inhouse team responsible |  |  | Basic function | basic |  |  | User manual | extend | N |  |  |  | R00 | R00 | R06 | R05
59 | Ethernet SOA related features | EESE | Web-Based HMI |  | 10% | 90% |  | Baidu |  |  | x |  | 2020-02-27 | [5 empty] | SPSS |  |  | Chen, Yu (Y.) <ychen372@ford.com> | Chen, Yu (Y.) <ychen372@ford.com> |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T | Y |  | cancel | [7 empty] | 2/3/2020: Baidu can not support HTML5
60 | Features of IVI or Connect | CVPP | Baidu Local Harzard Information |  | 10% | 90% |  | Baidu |  |  | x |  |  | no UE delivered Baidu: combined into map by Baidu internal review | no UE delivered Baidu: combined into map by Baidu internal review |  |  |  | Local Hazard Information Navigation v2 APIM SPSS v1.0 Jun 19, 2018 |  | embedded in Nav behaviour. | Lin, Shawn (X.) <xlin17@ford.com> Li, Yifei (Y.) <nli26@ford.com>-725 | Xiao, Yun (Y.) <yxiao21@ford.com> | 原翼 yuanyi13@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2020-02-14 | 2020-02-24 | 2020-02-21 | 2020-02-24 | N.A | 2/12/2020: Ford FO consdier to remove this feature, discuss on-going 2/24/2020: C/O, no change. |  |  | CVPP | Message center |  | x | 地图 | CVPP |  |  |  |  | DCV0 | DCV0 | DCV2 | DCV3
61 | Ethernet SOA related features | CVPP | IP Pass Through Client |  | 90% | 10% |  | Desay |  | x | x | always enable | 2020-01-10 | N/A | N/A |  |  |  | SPSS/PRD IP Pass Through Client Imp Guide v1.1 September 4, 2018.xlsx IP Pass Through Client SPSS v1.1 September 4, 2018.pdf | IP Pass Through Client Imp Guide v1.1 September 4, 2018 for Desay_0213.xlsx | N/A | Lin, Shawn (X.) <xlin17@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV2/IP_Pass_Through_Client | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-18 | D | 2/12/2020: MRD send to FO, plan to close before 2/21 2/18/2020: sign off |  | x | FNV2 | FNV2-basic |  | x | IPPT | CVPP |  |  |  |  | DCV1 | DCV1 | DCV2 | DCV3
62 | Ethernet SOA related features | CVPP | USB Update for TCU and ECG |  | 90% | 10% |  | Desay |  | x | x |  | 2020-01-10 | [5 empty] | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf |  |  | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu guanghui(Guanghui.Liu@desay-svautomotive.com) | 可能缺少Update技术文档 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T | Y |  | cancel | [7 empty] | merged into MMOTA
63 | Ethernet SOA related features | CVPP | Wireless Interface Router(WIR) |  | 90% | 10% |  | Desay |  | x | x | always enable | 2020-01-10 | N/A | N/A |  |  |  | SPSS/PRD | Wireless Interface Router Client1 Imp Guide v1.3 November 22 2019 for Desay_0217.xlsx | N/A | Lin, Shawn (X.) <xlin17@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-18 | D | 2/12/2020: MRD send to FO, plan to close before 2/21 2/18/2020: sign off |  | x | FNV2 | FNV2-basic |  | x | Wi-FI | CVPP |  |  |  |  | DCV3 | R00 | DCV2.1 | R00
64 | Ethernet SOA related features | EC Inhouse | FNV2 - FCI Protocol |  | 90% | 10% |  | Desay |  | x | x | always enable |  | N/A | N/A |  |  |  | FNV2-FCI Protocol SPSS v1.1 August 17, 2018 | FNV2-FCI Protocol Imp Guide v1.1 August 17, 2018_20200224.xlsx | N/A | Liu, Dapeng (D.) <dliu79@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-19 | D | 2/12/2020: plan to close before 2/18 |  | x | FNV2 | FNV2-basic |  | x | FNV2-FCI | extend | N |  |  |  | R00 | R00 | R06 | R05
65 | Ethernet SOA related features | CVPP | Customer Connectivity Settings |  | 90% | 10% |  | Desay |  |  | x | always enable | 2019-12-20 | 【林肯U554】ID_65&165_CCS_V2.1_20200430.pdf | 【福特727】CCS_ID65&165_V1.3_20200430 |  |  |  | PRD CCS_FB5_PRD_v2.0.pdf | Customer Connectivity Settings Client APIM SPSS v1.4 imp Guide v1.2_20200214.xlsx | H31j_SYNC4_Connectivity_Settings_R_v0_08_MY21_RELEASED | Ge, Haiqing (H.) <hge5@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-14 | 2020-02-18 | 2020-02-21 | 2020-02-18 | D | 1/13/2020: move to DCV2 2/12/2020: plan to close before 2/21 2/18/2020: sign off |  | x | FNV2 | FNV2-basic |  | x | Setting | CVPP |  |  |  |  | DCV2 | R00 | DCV2 | DCV3
66 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Diven) | Power to Box |  | 30% | 70% | NA | Baidu |  |  | x | DE06 B3b7 | 2020-01-23 | [5 empty] | Power to the Box SPSS v1.3 August 26, 2019 |  | H86a_SYNC4_ProPowerOnboard_RELEASED_v1_14_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | v_fengyunzhou@baidu.com |  |  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | ED&T | Y |  | cancel |  |  | 2020-02-24 | 2020-02-27 | 2020-03-02 |  | B | 2/10/2020: CVPP feature or EESE feature? 2/24/2020: SPEC already send to Baidu 3/22/2020: MRD继续delay，但是没有开发风险 4/10/2020: 2 open issues - waiting for feedback from FNA 4/21/2020: cancel confirmed with NA team. | [6 empty] | 硬件联动
67 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Diven) | Power Flow Display |  | 90% | 10% | NA | DESAY |  | x | x | yes | 2019-12-20 | N/A | N/A |  |  |  | Power Flow Display Client v3 APIM SPSS v1.0 Aug 29, 2018 Power Flow Display Client v3 APIM Imp Guide v1.0 Aug 29, 2018 | Power flow display 车型筛选_QA.xlsx | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | N | N | N | N | N | N | N | N | Y | Y | N | Y | Y | Y | N | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-02-12 | 2020-01-17 | 2020-02-26 | N.A | 12/25/2019: replan 12/30/2019: no MRD/replan info 1/6/2020: replan to 1/10 1/13/2020: postpone to 1/14 2/4/2020: MRD to be updated by Desay 2/12/2020: open item list to FO 2/26/2020: sign off | [6 empty] | power flow | extend | Y |  |  |  | DCV2 | DCV2
68 | HMI | HMI | 快捷面板/quick panel-27 only |  | 100% | 0% |  | Desay |  | x | x | 27" specific | 2020-01-17 | N/A | N/A |  |  |  | Design Guideline_CD542_To Supplier(11.15) compressed | Ford_MRD_27寸大屏SystemUI_20200116final.docx |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | ED&T | Y |  | close |  | 2 | 2019-12-06 | 2019-12-13 | 2019-12-30 | 2020-03-06 | N.A | SystemUI handover to Desay Desay: 12/30 freeze 1/6/2020: plan to sign off 1/10/2020: Desay recheck and sign off 1/13/2020: meeting to discuss open item with HMI and baidu 1/17/2020: sign off for desay 2/27/2020: reopen 3/6/2020: clairfied clear, close |  |  | HMI | HMI | x |  | HMI | extend | N |  |  |  | DCV2 | DCV2
69 | HMI | HMI | Persistant button |  | 100% | 0% |  | Desay |  | x | x | always enable | 2020-01-17 | 【林肯U554】Launcher&system UI_ID69&195&144&146_V1.9_20200414 | 【福特XC727】Launcher&SystemUI_ID69&195_V2.5_20200416 |  |  |  | Design Guideline_CD542_To Supplier(11.15) compressed | Ford_MRD_27寸大屏SystemUI_20200116final.docx | CX727 -P22h_15P_SYNC4_Dashboard_View_R_v4_00_MY21 Other programs will be aligned along with launcher design. | Liu Luisa （27inch） Xiao Yun（15.5inch 13.2inch Lincoln）Wang Lisa （13.2 Ford）Zhou Yujuan（12inch Ford） | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> | 根据新需求 | [23 empty] | close |  | 2 | 2019-12-13 | 2019-12-13 | 2019-12-30 | 2020-03-25 | N.A | SystemUI handover to Desay Desay: 12/30 freeze 1/6/2020: plan to sign off 1/10/2020: Desay recheck and sign off 1/13/2020: meeting to discuss open item with HMI and baidu 2/27/2020: R&R update, and reopen 3/25/2020: SIGN OFF |  |  | HMI | HMI | x |  | HMI | core | N |  |  |  | DCV2 | DCV2 | DCV2 | DCV3 | bar: N to Y; Y
70 | HMI | HMI | 主题更换/Theme change by User-->应用适配 |  | 30% | 40% | 30% | Baidu |  |  | x |  | 2020-01-23 | Theme change setting: if no UE, how desay develop? @baidu | Theme change setting: if no UE, how desay develop? @baidu |  |  |  |  | phase4-福特-更换主题MRD 2020_2_15.docx |  | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | UI | [25 empty] | close |  |  | 2020-01-23 | 2020-02-03 | 2020-02-10 | 2020-02-19 | N.A | 2/3/2020: Ford FO review 2/6/2020: review on-going 2/11/2020: escalate 2/14/2020: meeting held and plan to sign off | 2 open item |  | HMI | HMI | x |  | 主题更换 | extend | N |  |  |  | DCV4 | R00 | DCV3 | DCV3 | bar: N to Y; Y
71 | HMI | HMI | 主题更换/Theme change by User-->主题切换 |  | 90% | 10% | NA | Desay |  |  | x | feature 70 config - baidu lead/Desay follow |  | c/o UE, only UI | c/o UE, only UI |  |  |  |  | Ford_MRD_主题切换.docx |  | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | UI | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2020-02-14 | 2020-02-25 | 2020-02-21 | 2020-03-02 | N.A | 2/6/2020: supplier to provide plan date 2/17/2020: mailed, waiting feedback from HMI 2/24/2020: MRD planned to be ready today? |  |  | HMI | HMI | x |  | HMI | extend | N |  |  |  | DCV4 | R00 | DCV3 | R00
72 | Features of IVI or Connect | CVPP | 以太网连接互联网/Connect to Internet via Ethernet |  | 90% | 10% | NA | Desay |  | x | x |  | 2020-01-10 | [5 empty] | PRD |  | N/A | Lin, Shawn (X.) <xlin17@ford.com> / Liu, Dapeng (D.) <dliu79@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T |  |  | cancel |  |  | N.A | N.A | N.A | N.A | N.A | 1/13/2020: MRD 1/14 2/11/2020: Aligned as not needed by Dapeng and Guo chengcheng |  |  | CVPP | Message center
73 | Features of IVI or Connect | EESE/IVI(Diven) | 本地及在线音乐/Offline&Online Music Player | Y | 10% | 90% | NA | Baidu | x | x | x |  | 2019-11-05 | U554在线及本地音乐_ID73_V1.5 For DCV1 | CX727 在线及本地音乐_ID73_V1.4_For DCV1 |  |  |  | N.A | MRD-随心听多媒体V1.4.docx | H25_SYNC_4_Media_Player_RELEASED_v1_03_MY21 | Xu, Amy (X.) <xyafei@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | 穆仁萍 v_murenping@baidu.com |  | refer to BAIDU MRD, 确认对大屏是否其他适配要求 | 福特建议本地/在线音乐和视频/，FM/AM合并，百度确认可行性 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close | low |  | 2020-01-09 | N.A | 2020-01-16 | 2020-01-11 | N.A | 1/9/2020: feature 114 track | n.a |  | Basic function | entertainment | x | x | 内容生态 | core | Y |  |  |  | DCV4 | DCV4 | R00 | R00
74 | Features of IVI or Connect | EESE/IVI(Forrest) | 本地收音机 AM&FM/音频管理（本地+在线） | Y | 90% | 10% | NA | Desay | x | x | x | always enable | 2019-11-04 | 【林肯U554】本地收音机_ID74_V1.3-20200203 | 【福特 727】本地收音机_ID74_V1.6-20200303 |  |  |  | SPSS AMFM Tuner of Standalone AHU SPSS v1.8.pdf Auto Store_AM FM SPSS.pdf CD539C519D568_HMI_收音机_V1.0_20180912.xlsx | DUEROS-1005-CD391&U625&CX482-随心听：个性化电台.docx 11.19DUEROS-1005-CD391&U625&CX482-随心听：个性化电台.pdf | H23_SYNC4_Radio_RELEASED_v3_03_MY21 (H22m)MY21 MIxed Preset Test Cases 20200210 | Wang, Fin (X.Y.) <xwang65@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | 可以参照Phase1/2 MRD，但是需要在Ford SPEC基础上根据实际需求修改 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/AM-FM | close | low |  | N.A | N.A | N.A | N.A | N.A |  | n.a |  | Basic function | entertainment | x |  | Tuner | core | Y |  |  |  | DCV1 | DCV1 | DCV1.1 | DCV3
75 | Features of IVI or Connect | EESE/IVI(Forrest) | 在线收音机 Online Radio | Y | 10% | 90% | NA | Baidu | x | x | x |  | 2019-11-05 | U554 在线收音机_ID75_v1.5_20200430 | 【福特CX727】在线收音机_ID75_ v1.6_20200430 |  |  |  | N.A | Online Rideo_V1.2.docx |  | Wang, Fin (X.Y.) <xwang65@ford.com> Xiang, Zhengxi (Z.) <ZXIANG6@ford.com> - 725? | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | 穆仁萍 v_murenping@baidu.com |  | C/O Phase1/2 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close | low |  | N.A | N.A | 2019-11-20 | 2019-12-18 | N.A |  |  |  | Basic function | entertainment | x | x | 内容生态 | core | Y |  |  |  | DCV0 | DCV0 | DCV2 | DCV3
76 | Features of IVI or Connect | EESE/IVI(Diven) | 本地及在线视频播放/Video Playback | Y | 10% | 90% | NA | Baidu | x - offline USB video playback | x | x |  | 2019-11-05 | 【林肯U554】爱奇艺_本地视频_ID76、132_V2.1_202000310 | 【福特CX727】爱奇艺_本地视频_ID76_V2.3_20200213 |  |  |  | N.A | 在线视频 Online video.docx | H25b_Video_Player_Draft_v0_01 | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 穆仁萍 v_murenping@baidu.com |  | 单屏可以C/O Phase1/2 MRD， 但是27"需要重新根据Ford需求写MRD |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close | low |  | N.A | N.A | 2019-11-20 | 2019-12-12 | N.A |  | n.a |  | Basic function | entertainment | x | x | 内容生态 | basic | Y |  |  |  | DCV0 | DCV0 | DCV2 | DCV3
77 | Features of IVI or Connect | EESE/IVI(Diven) | 视频、音乐、图片DLNA投屏到车机显示器/Video Playback and Video and Photo project to Display via DLNA |  | 70% | 30% | NA | Desay |  |  | x | always enable |  | 【林肯U554】 DLNA投屏功能_ID77_v1.4_20200408 | 【福特727】DLAN投屏功能_ID77_v1.6_20200428 |  |  |  | DLNA投屏--PRD.pdf | Ford_MRD_DLNA_20200217.docx |  | Jia, Elaine (T.) <tjia2@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  | 后期细化 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV2/DLNA | close |  |  | 2020-02-14 | 2020-02-17 | 2020-02-21 | 2020-02-18 | N.A | 2/6/2020: supplier to provide plan date 2/17/2020: MRD avaialble, review |  |  | Basic function | entertainment | x | x | DLNA display | basic | TBD |  |  |  | R00 | R00 | DCV1.1 | R05
78 | Features of IVI or Connect | EESE/IVI(Diven) | 蓝牙音乐/Bluetooth Media | Y | 60% | 40% | NA | Desay | x - basic function only | x - complete | x | always enable | 2019-11-06 | 【林肯U554】蓝牙设置_ID78&79_V1.7_20200220 【林肯U554交互】蓝牙音乐_ID78_v2.0_20200213 | 【福特727】蓝牙设置_ID78&79_v1.2_20200220 【福特727】蓝牙音乐_ID78_v1.2_20200213 |  |  |  | SPSS BT Connectivity APIM SPSS v2.9 Jan 3, 2018.pdf DualBtSystemRequirments_V0.1.docx | Ford_MRD_蓝牙音乐_V4.0_20200218.docx | H25_SYNC_4_Media_Player_RELEASED_v1_03_MY21 H31h_SYNC4_Audio_Settings_RELEASED_v1_05_MY21 | Xu, Amy (X.) <xyafei@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） | 参考Phase1/2的MRD，根据福特新的需求更新MRD，并且27"会增加额外交互 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/BT_Phone | close | low |  | 2019-11-10 | 2019-12-23 | 2019-12-30 | 2020-02-06 | N.A | 12/23/2019:Updated MRD avaialble 12/23. Wait confirm from Ford FO; 12/25/2019: pending by Ford FO 1/6/2020: updated MRD available, need FO check 1/9/2020: need Desay's update 1/10/2020: Desay update by 1/13 1/13/2020: Plan to sign off, consolidate info by Desay 2/6/2020: sign off | n.a |  | Basic function | BT | x |  | BT | core | Y |  |  |  | DCV1 | DCV1 | DCV1.1 | DCV3
79 | Features of IVI or Connect | EESE/IVI(Diven) | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | Y | 90% | 10% | NA | Desay | x - basic function only | x - complete | x | always enable | 2019-11-06 | 【林肯U554】多连接通话_ID79_V1.6_20200316 【林肯U554】电话设置_ID79_V1.4_20200324 【林肯U554】蓝牙电话（不含多连接通话）_ID79_V2.0_20200304 【林肯U554】蓝牙设置_ID78&79_V1.7_20200220 | 【福特727】多连接通话_ID79_V1.0_20200404 【福特727】电话设置_ID79_V1.0_20200315 【福特727】蓝牙设置_ID78&79_v1.2_20200220 【福特727交互】蓝牙电话（不含多连接通话）_ID79_V1.4_20200311 |  |  |  | SPSS BT Phone APIM SPSS v1.9 April 24 2015.pdf Smart cockpit BT Solution.pdf | Ford_MRD_电话设置_V1.1_20200220.docx | H28a_SYNC4_Phone_RELEASED_v1_07_MY21 H28c_SYNC4_Bluetooth_Pairing_RELEASED_v1_05_MY21 | Xu, Amy (X.) <xyafei@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） | 单屏，蓝牙电话基础部分可以C/O Phase1/2，微信要重新定义 27”需要重新定义 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/BT_Phone | close | low |  | 2019-11-10 | 2019-12-10 | 2019-12-17 | 2020-02-19 | D | 1/9/2020: reopen, 2 open items to be added; 1. BT setting missed 2. dailing button missing?... Other issues which mailed by Lisa 1/13/2020: MRD to be updated 1/14 2/8/2020: pending due to Ford FO check 2/11/2020: plan to sign off |  |  | Basic function | BT | x |  | BT | core | Y |  |  |  | DCV1 | DCV1 | DCV2 | DCV3
80 | Features of IVI or Connect | EESE/IVI(Diven) | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) |  | 90% | 10% | NA | Desay |  | x | x | 27" specific | 2019-12-30 | N/A | N/A |  |  |  | refer DCV0 (BT_Connectivity, BT_Phone) | Ford_MRD_蓝牙耳机_V1.3_20200218.docx Ford_MRD_蓝牙电话_V4.5_20200221.docx Ford_MRD_蓝牙连接设置_V4.4_20200227.docx |  | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | ED&T | Y |  | close |  |  | 2019-12-30 |  | 2020-01-06 | 2020-02-19 | D | 12/30/2019: no MRD/replan info 1/6/2020: replan to be availabel tomorrow 1/10/2020: replan after internal discussion by Desay 1/13/2020: escalate 2/11/2020: plan to sign off |  |  |  |  | x |  | BT | extend | Y |  |  |  | R00 | R00
81 | Features of IVI or Connect | EESE/IVI(Diven) | 离线及在线地图和导航/Offline&Online Map and Navigation | Y | 10% | 90% | NA | Baidu | x | x | x |  | 2019-10-28 | no UE delivered Baidu: combined into map by Baidu internal review | no UE delivered Baidu: combined into map by Baidu internal review |  |  |  |  | 1.地图-产品规格说明书20200221 - ford 2.福特IOV车机地图feature list-------phase1-4通用（包含phase4变更点） | 02_Specification/05_Ford_HMI_Spec/Navigation_Ford HMI requirement.pptx | Yao, Tristan (Lan) <LYAO17@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | 原翼 yuanyi13@baidu.com |  | 单屏，可以C/O Phase1/2 MRD 27“需要重新定义 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close | low |  | 2019-11-10 | 2019-12-20 | 2019-12-27 | 2020-02-27 | N.A | 12/24/2019: Ford FO在等Baidu的回复 12/25/2019: pending by Ford FO 12/27/2019: Baidu check 12/30/2019: pending by Baidu Check 1/2/2020: Baidu check 1/8/2020: Baidu provide the different list; Emma follow the 2 requirements. 1/9/2020: 3 open items: 2019/1/14 1. Baidu check the status of the "improvement" items from Diven. 2. Provide the different list between IVI & phone for Navigation 3. analysis the feasibility of new requirement 1/17/2020: baidu provided feedback 2/3/2020: organize meeting to close 2/6/2020: pending due to Ford FO 2/13/2020: meeting held 2/19/2020: final decision to be made this week, due to the change request of "trip planner" 2/24/2020: forzen this feature, tracking the changes via trip planner separately. |  |  | Basic function | Navigation | x | x | 地图 | core | Y |  |  |  | DCV0 | DCV0 | DCV2 | DCV3
82 | Features of IVI or Connect | EESE/IVI(Diven) | AR Navigation (include output to IPC) |  | 20% | 80% | NA | Baidu | x - basic video output | x - basic function | x | DE04 B5b7 DE07 B4b0 | 2019-11-07 | N/A | N/A |  |  |  | N.A | MRD_百度车联网_项目_福特_AR导航_v1.1_20191119.docx |  | Ding, Xiaojing (X.) <XDING13@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 原翼 yuanyi13@baidu.com |  | new |  | N | OPT1 | N | OPT1 | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | License | Y |  | close | low |  | 2019-11-10 | 2019-12-20 | 2019-12-27 | 2019-12-23 | N.A | [6 empty] | x | 地图 | basic | N |  |  |  | DCV0 | R00
83 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Volume Setting V2 |  | 90% | 10% | NA | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】音效设置_ID83&84&157_V1.3_20200303 | 【福特727】音效设置_ID83&84_V1.4_20200323 |  |  |  | Volume APIM SPSS v1.3 Jan 31, 2018 Volume APIM Imp Guide v1.3 Jan 31, 2018 Volume Logical to Physical CAN signal mapping Feb 5, 2018 | 合并到NO84 | H31a_SYNC4_Settings_R_v0_40_MY21 | Li Xuedong XLI244@ford.com | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-11 | N.A | 12/24/2019: desay check with Ford FO. 12/27：逻辑部分已经和ford audio FO澄清，界面相关合并到setting中 1/6/2020: plan to sign off 1/11/2020: sign off |  |  | Basic function | Setting |  |  | Audio | core | N |  |  |  | DCV1 | DCV1 | DCV1.1 | DCV3
84 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Audio Management | Y | 90% | 10% | NA | Desay | x | x | x | yes? audio setting | 2019-11-04 | 【林肯U554】音效设置_ID83&84&157_V1.3_20200303 | 【福特727】音效设置_ID83&84_V1.4_20200323 |  |  |  | Audio Management APIM Imp Guide v1.5.1 Sep 26, 2018.xlsx Audio Management Logical to Physical CAN signal mapping Sep 7, 2018.docx Audio Management SPSS v1.5 Sep 7, 2018.pdf Audio Management Supplement SYNC 4.1 July 13th, 2018.docx Audio Settings Deployment May 9th, 2019.docx Audio Settings Logical to Physical CAN signal mapping Sep 6, 2018.docx Audio Settings v2 APIM Imp Guide v1.1 May 23, 2019.xlsx Audio Settings v2 APIM SPSS v1.1 May 23, 2019.pdf | Ford_MRD_AudioSource.docx | H31a_SYNC4_Settings_R_v0_40_MY21 H31h_SYNC4_Audio_Settings_RELEASED_v1_05_MY21 | Li Xuedong XLI244@ford.com | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Yu Hualin(Hualin.Yu@desay-svautomotive.com) | Phase1/2 YFV，DESAY需要重新做 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/Audio_Management | close | low |  | N.A | N.A | N.A | N.A | N.A | Audio_QA.xlsx |  |  | Chime management | Chime management | x |  | Audio | core | Y |  |  |  | DCV0 | DCV0 | DCV1.1 | DCV3
85 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Power Managements | Y | 90% | 10% | NA | Desay | x | x | x | n.a | 2019-11-04 | UE missed, @desay | UE missed, @desay |  |  |  | Power Management Logical to Physical CAN signal mapping Sep 6, 2018.docx Power Management v2 APIM Imp Guide v1.1 May 8, 2019.xlsx Power Management v2 APIM SPSS v1.1 May 8, 2019.pdf | DUEROS-305-CX483611-电源管理.docx | H22g_SYNC4_Welcome_Power_Modes_RELEASED_v1_02_MY21 | IVI-Song, Rui (Rex.) <rsong2@ford.com>Chen James <JCHEN303@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Ding Yunrong（Yunrong.Ding@desay-svautomotive.com） | Phase1/2 YFV，DESAY需要重新做 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/Power_Management | close | low |  | 2019-11-10 | 2019-12-06 | 2019-12-13 | 2019-12-11 | N.A | DUEROS-305-CX483611-电源管理.pdf | 2 open points by Ford FO 12/27/2019: Desay mail to FO today |  | Power management | Power management | x |  | power | core | Y |  |  |  | DCV1 | DCV1 | DCV2 | DCV3
86 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Illumination Requirements | Y | 90% | 10% | NA | Desay |  | x | x | n.a | 2019-12-20 | c/o UE, only UI [system setting - dislay setting] desay check whether OK for development | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  | Illumination Management APIM SPSS ver 1_0 May 31st, 2013 folder:Illumination | illumination_QA.xlsx | H31a_SYNC4_Settings_R_v0_40_MY21 | Chen, James (J.) <jchen303@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-14 | N.A | 12/24/2019: desay check with Ford FO. 12/30/2019: setting is OK. Detail illumination requirement need Desay's hardware/software architecture check. 1/6/2020: HMI ok, need Desay provide OIL 1/10/2020: archive QA , plan to sign off 1/14/2020: sign off |  |  | Basic function | Illumination | x |  | illumination | core | N |  |  |  | DCV1 | DCV1 | DCV1.1 | DCV3
87 | Features of IVI or Connect | IVI(removed) | 文件浏览器/File Manager - confirmed as not needed12/25/2019 |  | 90% | 10% | NA | Desay |  | x | x |  | 43819 | [5 empty] | File Manager.pdf |  |  | Jia, Elaine (T.) <tjia2@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Pan Juan（Juan.Pan@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T | N |  | cancel | [7 empty] | upload to GitHub 12/24/2019: mailed to Ford FO 12/25/2019: meeting today
88 | Features of IVI or Connect | IVI(removed) | 蓝牙文件共享/Files sharing via Bluetooth |  | 90% | 10% | NA | Desay |  | x | x |  | NA | [5 empty] | feasibility study - ongoing |  |  | Xu, Amy (X.) <xyafei@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） |  |  | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | N | N | N | N | N | ED&T | N |  | cancel | [7 empty] | cancelled due to request by FO
89 | Features of IVI or Connect | EESE/IVI(Diven) | 图片/小视频浏览器 Picture/video Viewer |  | 90% | 10% | NA | Desay |  | x | x | always enable | 2019-12-20 | 【林肯U554】图片视频浏览器_ID89_V1.7_20200410 | 【福特727】图片视频浏览器_ID89_V1.4_20200424 |  |  |  | n.a suppliers provide the proposal and review; including HMI and data collection. | Picture_MRD.DOCX |  | Jia, Elaine (T.) <tjia2@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Dong Zhaojun<zhaojun.dong@desay-svautootive.com> |  |  | N | Y | N | Y | N | N | Y | N | N | N | N | N | N | N | N | N | N | N | N | ED&T | N |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-02-14 | D | upload to GitHub 12/24/2019: mailed to Ford FO 12/25/2019: meeting today 12/27/2019: updated MRD today 12/30/2019: updated MR mailed to Ford FO 1/6/2020: Ford FO feedback today 1/10/2020: on-site review, archive, plan to sign off 1/13/2020: MRD open item discussion. 1/19/2020: open item listed by Desay, on-hold 2/14/2020: plan to sign off |  |  | Basic function | entertainment |  | x | PicMgr | basic | Y |  |  |  | DCV1 | DCV1 | DCV2 | DCV3
90 | Features of IVI or Connect | EESE/IVI(Diven) | 基础及增强型语音功能/Base and Enhanced VR |  | 10% | 90% | NA | Baidu | x - basic VR function | x | x |  | 2019-10-29 | 【林肯U554】系统设置-语音设置【ID90】_V1.8_20200302 | 【福特CX727】系统设置-语音设置【ID90】_V1.9_20200413 |  |  |  | N.A | Voice recognition spec - 20191226 01 Voice recognition feature list v1.1 - 20200221 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 | H48b_Sync 3 Voice Control State Machine (DRAFT) v1.0.pdf | Qi, Xuliang<xqi14@ford.com> Zhang, Meijuan (M.) <MZHAN102@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | 刘韧 v_liuren@baidu.com |  | 基础VR可以C/O Phase1/2 增加的VR需要根据需求做 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | Y |  | close | low | 5 | N.A | N.A | 2019-11-20 | 2019-12-02 | N.A |  | Open: key parameters can not meet spec. Baidu improve. 2/28/2020: 语音指令持续更新 3/30 |  | Chime management | chime management |  | x | 语音 | basic | Y |  |  |  | DCV0 | DCV0 | DCV2 | DCV3
91 | Features of IVI or Connect | EESE/IVI(Diven) | 双音区语音识别/Dual Zone VR-Clarify | Y | 10% | 90% |  | Baidu |  | x | x |  | 2019-12-20 | UE c/o from phase2, UI updated | UE c/o from phase2, UI updated |  |  |  | Voice recognition spec-20191121.pdf | Voice recognition spec - 20191226 01 Voice recognition feature list v1.1 - 20200221 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 | H48b_Sync 3 Voice Control State Machine (DRAFT) v1.0.pdf | Qi, Xuliang<xqi14@ford.com> Zhang, Meijuan (M.) <MZHAN102@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | 刘韧 v_liuren@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | Y |  | close |  |  | N.A | N.A | 2019-11-20 | 2019-12-02 | N.A | combine to 90 |  |  | Chime management | chime management |  | x | 语音 | basic | Y |  |  |  | DCV0 | DCV0 | DCV2 | DCV3
92 | Features of IVI or Connect | IVI(removed) | 全成员语音识别支持/Multi-zone Directional Voice Control |  | 10% | 90% | NA | Baidu |  |  | x |  | 2020-02-03 | [8 empty] | Wang, Jingjing (J.) <jwang354@ford.com> | N/A |  |  |  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | License | Y |  | cancel | [7 empty] | cancelled due to request by FO | [13 empty] | DCV3
93 | Features of IVI or Connect | EESE/IVI(Diven) | 百度人脸识别 Face ID (Registration, Recognition, Account, Personalization, Welcome) | Y | 10% | 90% | NA | Baidu | x-basic Face ID feature | x-complete | x | DE06 B5b7 | 2019-10-29 | N/A | N/A |  |  |  | Image Recognition Function Feature Level Specification - draft.pdf |  | SYNCFord HMI Requirement_Enhanced Memory_DRAFT_ v0.5 | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | 潘中举 panzhongju@baidu.com |  | C/O Phase3 | 百度直接输出MRD | N | OPT2 | N | OPT2 | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | License | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/Facial%20Recognition | close | Mid |  | 2019-11-10 | 2019-12-20 | 2020-01-10 | 2020-02-19 | B | 12/23/2019: 1/10前定稿 1/2/2020: MRD status? 1/8/2020: Baidu provide updated MRD 1/9/2020: mail send to Ford FO 1/10/2020: Baidu reschedule to 1/17 2/6/2020: pending due to Baidu 2/7/2020: MRD to be updated. 2020/2/12 2/13/2020: update on-going | [5 empty] | x | 图像 | basic | N |  |  |  | DCV3 | DCV3
94 | Features of IVI or Connect | EESE/IVI(Diven) | Image recognition - Drive Status Monitor (Fatigue, Distraction, Dangers Behaviour) | Y | 10% | 90% | NA | Baidu |  | x | x | DE06 B5b7 | 2019-12-05 | N/A | N/A |  |  |  |  | 福特Phase4_DMS_20200213.docx | N/A | Jia, Elaine (T.) <tjia2@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | 潘中举 panzhongju@baidu.com |  |  |  | N | OPT2 | N | OPT2 | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | License | Y |  | close | mid |  | 2019-12-30 | 2020-01-06 | 2020-01-06 | 2020-02-19 | B | Updated MRD to be rady Dec. 30th 1/2/2020: MRD available 1/6/2020: meeting planned on 1/7 1/8/2020: Baidu provide updated MRD and open item list 1/10/2020: postpone to 1/17? 2/6/2020: pending due to Baidu 2/7/2020: MRD to be updated before 2020/2/12 2/13/2020: update on-going after meeting 2/14/2020: plan to sign off | [5 empty] | x | 图像 | basic | N |  |  |  | DCV1 | R00
95 | Features of IVI or Connect | EESE/IVI(Diven) | Image recognition - Multi-Mode (Hand Gusture / Head / Emotion) |  | 10% | 90% | NA | Baidu |  | x | x | DE06 B5b7 | 2020-01-23 | N/A | N/A |  |  |  |  | 【福特cd542】多模手势交互mrd需求文档 V2.1.2 | N/A | Jia, Elaine (T.) <tjia2@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | 潘中举 panzhongju@baidu.com |  |  |  | N | OPT2 | N | OPT2 | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | License | Y |  | close |  |  | 2020-01-10 | 2020-01-02 | 2020-01-17 | 2020-02-20 | N.A | 12/23/2019: 多模MRD更新版本 Dec. 30th; 情绪相关内容单独输出MRD, end of Feb. 1/2/2020: MRD available 1/8/2020: Baidu provide updated MRD and open item list 1/10/2020: update on-going 2/3/2020: updated MRD avaialble, pending by Ford FO's review 2/6/2020: meeting today 2/7/2020: MRD plan to sign off 2/11/2020: Change introduced, MRD to be updated within this week. 2/20/2020: MRD updated and review closed, sign off | [5 empty] | x | 图像 | basic | N |  |  |  | DCV1 | R00
96 | Features of IVI or Connect | EESE/IVI(Diven) | Image recognition with DSMC module (FaceID with DSMC/Driver monitor with DSMC) |  | 10% | 90% | NA | Baidu |  |  | x | DE06 B5b7 DE07 B4b1 |  | N/A | N/A |  |  |  | Image Recognition Function Feature Level Specification - draft.pdf | 无MRD | N/A | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> Li, Cindy (Y.) <YLI316@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | 潘中举 panzhongju@baidu.com |  | new | 百度直接输出MRD | N | OPT1 | N | OPT1 | Y | Y | N | N | N | N | N | N | Y | Y | N | N | Y | Y | Y | ED&T | Y | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/Facial%20Recognition | close |  |  | 2020-02-14 |  | 2020-02-21 |  | F | 2/6/2020: supplier to provide plan date 2/11/2020: Baidu provide the feasiblity study result. No MRD. 2/13/2020: Update on-going 2/20/2020: Baidu internal discussion on-going. 2/28/2020: Baidu provide technical spec to Ford FO. - open item 3/3/2020: reopen- scope not aligned between Ford FO and Baidu 3/10/2020: sign off 3/22/2020： 基于Ford FO的排期计划，百度排期 | 2/28/2020: Baidu provide technical spec to Ford FO. - open item |  |  |  |  | x | 图像 | extend | N |  |  |  | R07 |  | R07.01 | tbd
97 | Features of IVI or Connect | EESE/IVI(Diven) | 随心拍/Traveling Shooting |  | 30% | 70% | NA | Baidu |  |  | x | DE06 B5b7 |  | N/A | N/A |  |  |  |  | 无MRD |  | Jia, Elaine (T.) <tjia2@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 段家仪 v_duanjiayi@baidu.com |  |  |  | N | Y | N | Y | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | ED&T | Y |  | close |  |  | 2020-02-14 | 2020-03-10 | 2020-02-21 | 2020-04-10 | N.A | 1/9/2020: not Ford develop 1/10/2020: check today 1/13/2020: Baidu send out OIL 2/6/2020: replan 2/20/2020: MRD planned to be ready before next Monday 3/22/2020：有open项，但是不影响开发 4/10/2020: sign off |  |  | Basic function | entertainment |  | x | 内容生态 | extend | N |  |  |  | DCV0 | R00
98 | Features of IVI or Connect | CVPP | 车辆故障显示 / Show the vehicle Telltale Warnings |  | 30% | 70% | 0% | Desay |  |  | x | always enable |  | 【林肯U554】车辆状态_ID98&161&189__V1.5-20200324 | 【福特727】车辆状况_ID98&161&189_V1.5_20200428 |  |  |  | PRD DUEROS_CVPP_Vehicle_Status_PRD_v1.1 | 合并到NO161 |  | Lu, Chao (C.) <clu42@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  | 2020-01-14 | 2020-01-14 | 2020-02-28 | 2020-01-21 | 2020-02-28 | N.A | 2/6/2020: supplier to provide plan date 2/10/2020: Clarify responsible 2/19/2020: R&R clear. 2/20/2020: combine to 161. |  |  | CVPP | Message center |  | x | Vehicle Information | CVPP |  |  |  |  | DCV1 | DCV3 | DCV2 | DCV3
99 | Features of IVI or Connect | HMI | 图标位置自定义/Set icon location by Customer |  | 10% | 90% | NA | Baidu |  |  | x | [10 empty] | Liu Luisa （27inch） Xiao Yun（15.5inch 13.2inch Lincoln）Wang Lisa （13.2 Ford）Zhou Yujuan（12inch Ford） | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T | N |  | cancel | [7 empty] | 2/4/2020: Ford FO delete this feature
100 | Features of IVI or Connect | EESE/IVI(Diven) | IVI Wi-FI, IVI Wi-Fi Hotspot-2.4GHz&5GHz - IVI provide HMI to connect other WIFI | y | 70% | 30% | NA | Desay | x - basic function | x | x | always enable | 2019-11-08 | 【林肯U554】WiFi热点_ID13&51&100_V1.7_20200310.pdf | 【福特727】Wi-Fi热点_ID 13&51&100_V1.2_20200017 【福特727】WIFI设置_ID13&100_V1.4_20200318 |  |  |  | Hotspot PRD v1.3 Feature Bundle 5 track changes on.docx Hotspot Server v2 SPSS v1.2 June 25, 2018.docx Hotspot TCU SPSS v1.9 Apr 28, 2017.docx Internet Gateway APIM v2 Imp Guide v1.0 March 12, 2018.xlsx Internet Gateway APIM v2 SPSS v1.0 March 12, 2018.docx Internet Gateway APIM v2 SPSS v1.0 March 12, 2018.pdf | Wifi设置_Desay_MRD_20200117.docx | H31i_InfoBook _Wi-Fi_Hotspot_v0_6 H31i_SYNC_GEN3_Wi-Fi_Settings_RELEASED_v0_35_3_MY2020 | Yu, Diven (D.W.) <dyu12@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | SPEC有更新，需要更新 |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV0/WIFI%20SPSS | close | Mid |  | 2019-11-20 | 2019-12-23 | 2019-12-30 | 2020-01-15 | N.A | Link to FNV2. Ma Mei: 11-20 Diven初步认可需后续会议继续沟通（Desay 后续会根据实际讨论情况补充Q&A） 12/23/2019: Re open 1/6/2020: Mail to FO to check MRD 1/10/2020: on-site review today 1/13/2020: MRD update 1/14 1/15/2020: sign off | Diven需要确认WPS功能是否需要实现 | x | FNV2 | WIFI |  | x | Wi-Fi | core | N |  |  |  | DCV2 | DCV3 | DCV2 | DCV3
101 | Features of IVI or Connect | CVPP | 账号Account? |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-01-17 | U554 帐号 ID101 ID186 V1.5 20200426 |  |  |  |  | PRD DUEROS_CVPP_Ford and Baidu Accoun_Phase 2_PRD_v1.4.pdf |  | Ford HMI Requirement_Account_DRAFT_ v0.5 | Wang, Johnny (J.) <jwang308@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | 潘承栋 v_panchengdong@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2019-12-27 | 2019-12-30 | 2020-01-06 | 2020-03-20 | B | CVPP 等百度更新输入 12/24/2019: MRD available this Friday 12/30/2019: pending by Ford FO 1/8/2020: Baidu update MRD today, meeting tomorrow 1/10/2020: Baidu provide proposal 1/13, on-site review 1/13/2020: updated MRD available 2/3/2020: arrange a meeting to discuss 2/6/2020: pending due to Ford FO 2/8/2020: Baidu arrange meeting to review 2/12/2020:discussion on-going; while dealyed, and impact UE/UI, Baidu send officially mail. |  |  | CVPP | Account |  | x | 账号 | CVPP |  |  |  |  | DCV0 | R04 | R00 | R04
102 | Features of IVI or Connect | CVPP | 道路救援/Road assistance | Y | 30% | 70% | NA | Baidu |  |  | x |  | 2020-01-23 | c/o UE, only UI | c/o UE, only UI | [6 empty] | Ren, Siyuan (Alex.) <sren6@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-01-10 | 2020-02-03 | 2020-02-10 | 2020-03-06 | N.A | 2/3/2020: MRD available, pending 2/6/2020: pending due to Ford FO 2/11/2020: CC Stone to push 2/11/2020: Escalated, FO not aligned |  |  | CVPP | Message center |  | x | 道路救援 | CVPP |  |  |  |  | DCV0 | DCV3 | DCV2 | DCV3
103 | Features of IVI or Connect | CVPP | Emergency Assistance/紧急救援 | y | 40% | 10% | 50% | Ford EESE/Desay |  | x | x | always enable | 2019-12-20 | 【林肯U554】紧急救援_ID103_V1.6_20200221 | 【福特727交互】紧急救援_ID103_V1.2_20200427 |  |  |  | PRD Draft Emergency Assistance APIM_DuerOS SPSS July 2nd.pdf | Ford_MRD_紧急救援_1.4.docx | H35_SHMI Global Emergency Assist (RELEASED) v1_6_CTR.pdf | Ren, Siyuan (Alex.) <sren6@ford.com> | Li, Jessie (J.) <jli316@ford.com> |  | zhang yanlan<yanlan.zhang@desay-svautomotive.com> |  |  | N | N | N | N | Y | Y | Y | Y | Y | N | Y | Y | N | N | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-29 | 2020-01-10 | 2020-01-05 | 2020-02-05 | N.A | 12/24/2019: Desay check and feedback today 12/25/2019: delay to today 12/27/2019: MRD avialable 29th 1/6/2020: Desay review internal and feedback today 1/10/2020: MRD available, Ford FO check 2/3/2020: mail send again to Ford FO 2/5/2020: sign off | 3 items: 3. 当前HotSpot CAN消息中关于string的消息包含解码类型以及不同长度的说明， Ford之前项目是MCU统一转码发给SOC,所有模块统一处理会比较好【以往项目Wifi和HotSpot涉及的解码方式都是UTF16】 –Xie Jing 4. UI的设计参照H31i_SYNC4_Vehicle_Hotspot_Settings_RELEASED_v1_02.vsdx Flow Chart来出，之前百度提供的UE文档功能有缺失需要修改 –Huang Ruihao 5. WFHS-REQ-358565这一条需要实现SOA客户端需要系统那边确认可以作为Open项处理 --Ding Yunrong |  | CVPP | Message center |  | x | Emergency assistance | CVPP | [6 empty] | DCV2 | DCV3
104 | Features of IVI or Connect | CVPP | 智能家居/Intelligent Home Control | y | 20% | 80% | NA | Baidu |  |  | x |  | 2020-01-23 | 【林肯U554】_ID104_智能家居_V1.4_20200414 | 【福特CX727】_ID104_智能家居_V1.2_20200414 |  |  |  | PRD |  |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 刘韧 v_liuren@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-01-19 | 2020-01-19 | 2020-02-06 | 2020-02-06 | N.A | 2/4/2020: plan to sign off 2/6/2020: sign off |  |  | CVPP | APP |  | x | 车家互联 | CVPP |  |  |  |  | DCV0 | DCV3 | DCV2 | DCV3
105 | Features of IVI or Connect | CVPP | 天气/Weather |  | 10% | 90% | NA | Baidu |  |  | x |  | 2020-01-23 | 【福特 P702&U725】ID_198&105&171_Launcher_V1.4_20200315 | 【福特XC727】Launcher&SystemUI_ID69&195_V2.5_20200416 |  |  |  |  | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Shi, Stella (J.) <jshi32@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 杨萍 v_yangping03@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-01-23 | 2020-01-02 | 2020-01-09 | 2020-01-19 | N.A | 12/24/2019: MRD available. Need Ford FO check 1/2/2020: list open item and mail for notification. 1/8/2020: plan to sign off 1/19/2020: sign off | AAR URL on-going/due date? |  | CVPP | APP |  | x | Launcher | CVPP |  |  |  |  | DCV0 | DCV3 | DCV2 | DCV3
106 | Features of IVI or Connect | CVPP | 保养及在线预约/Vehicle Maintenance and the service booking [open in CX727] | Y | 20% | 80% | NA | Baidu |  |  | x |  | 2020-01-23 | 【林肯U554】车场景预约保养【ID106】V2.0_20200415 |  |  |  |  | MRD OSB MRD.pdf | 【福特Phase4】MRD_预约保养_福特车型_V1.0_20191219 |  | Wang, Johnny (J.) <jwang308@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 段家仪 v_duanjiayi@baidu.com |  |  |  | Y | Y | Y | Y | N | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | ED&T |  |  | open-727 |  |  | 2020-02-07 | 2020-02-10 | 2020-02-14 | 2020-02-19 | B | 2/12/2020: sign off |  |  | CVPP | APP |  | x | 服务生态 | CVPP |  |  |  |  | DCV0 | DCV3
107 | Features of IVI or Connect | CVPP | IVI CCPU/VMCU software FOTA update (IVI自升级) |  | 90% | 10% |  | Desay |  | x | x |  | 43829 | [5 empty] | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf |  |  | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Liu guanghui(Guanghui.Liu@desay-svautomotive.com) |  | 福特确认 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T | N |  | cancel | [7 empty] | merged into MMOTA
108 | Features of IVI or Connect | CVPP | Ford VMCU Software Update (CAN or USB) |  | 90% | 10% | NA | Desay |  | x | x |  | 43826 | [5 empty] | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf |  |  | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Pan Juan（Juan.Pan@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T | Y |  | cancel | [7 empty] | merged into MMOTA
109 | Features of IVI or Connect | CVPP | CCPU&VMCU Software Update (USB) |  | 80% | 20% | NA | Desay |  | x | x |  | 43826 | [5 empty] | PRD 548171_F_002_IVSU_Vehicle_Function_HMI_v3.7.pdf H33_SYNC4_SHMI_General_Info_and_App_Install_RELEASED_v1_11_6_MY21.pdf 547912_A_001_IVSU Vehilce Function VIL Client v1.0.pdf |  |  | Pan, Yuan (Y.) <ypan23@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Pan Juan（Juan.Pan@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T | Y |  | cancel | [7 empty] | merged into MMOTA
110 | Features of IVI or Connect | EESE/IVI(Forrest) | 车机工程模式(支持车辆工厂模式)/IVI Engineering Mode |  | 90% | 10% | NA | Desay |  | x | x | always enable | 2019-12-27 | FO check, function work only | FO check, function work only |  |  |  | based on bezel diagnostic; Phase 2 mail - archive | Ford_MRD_EngineeringMode_V02.docx |  | Wang, Fin (X.Y.) <xwang65@ford.com> | N/A |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-27 | 2020-01-15 | 2020-01-03 | 2020-02-10 | N.A | 12/30/2019: no MRD/replan info 1/6/2020: replan today 1/10/2020: MRD on-going 1/13/2020: check status 2/6/2020: plan to sign off; 2/10/2020: sign off |  |  | Basic function | basic | x |  | Diagnostic | core | N |  |  |  | DCV0 | DCV3 | DCV2 | DCV3
111 | Features of IVI or Connect | EESE/IVI(Forrest) | Log system |  | 60% | 40% | NA | DESAY |  | x | x | always enable | 2019-12-20 | FO check, function work only | FO check, function work only |  |  |  | n.a suppliers provide the proposal and review; including HMI and data collection. | Ford_MRD_Log System.docx | N/A | Chen, Emma (J.) <jchen276@ford.com> | N/A | RD | Pan Juan（Juan.Pan@desay-svautomotive.com） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | N |  | close |  |  | 2019-12-25 | 2019-12-30 | 2020-01-01 | 2020-02-17 | N.A | 12/25/2019: need FO check 12/27/2019: wait feedback from Desay 12/30/2019: Ford FO feedback today 1/6/2020: arrange meeting today 1/10/2020: Emma check 1/13/2020: Emma feedback today 2/6/2020: pending due to Desay 2/14/2020: plan to sign off 2/17/2020: sign off |  |  | Basic function | basic | x |  | log system | core | N |  |  |  | DCV0 | DCV3 | DCV2 | DCV3
112 | Passenger Feature for 27 | HMI | 对高配27"屏幕，需要支持双屏和驾驶员屏幕独占模式（超级单屏模式）-Launcher |  | 10% | 90% |  | Baidu/Desay |  | x | x | 27" specific | 2020-01-17 | N/A | N/A |  |  |  | Design Guideline_CD542_To Supplier(11.15) compressed | 【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 杨萍 v_yangping03@baidu.com | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> |  | 待确定--HMI | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | ED&T | Y |  | close |  |  | 2019-12-16 | 2019-12-13 | 2019-12-30 | 2020-01-19 | N.A | 12/25/2019: sign off? 12/30/2019: update by Baidu 1/2/2020: updated MRD? 1/8/2020: plan to sign off 1/17/2020: sign off for Desay 1/19/2020: sign off for Baidu |  |  |  |  | x | x | Launcher | extend | Y |  |  |  | DCV1 | R04
113 | Passenger Feature for 27 | HMI | 屏幕扩展显示/Extend center or passenger display content(like Navi, to show the whole path in two screens) to two display |  | 40% | 60% | NA | Baidu |  | x | x |  |  | N/A | N/A |  |  |  |  | 【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  |  | Y | Y | Y | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | ED&T | N |  | close |  |  | 2019-12-27 | 2019-12-30 | 2020-01-03 | 2020-01-13 | N.A | 12/25/2019: MRD available today. 12/27/2019: open item: the scope of feature not clear, mail to FO check 12/30/2019: open item closed. 1/2/2020: need Ford FO's confirm - no MRD 1/13/2020: confirmed - split to function's UE. Close |  |  |  |  | x | x | Launcher | extend | Y |  |  |  | DCV1 | R04
114 | Passenger Feature for 27 | HMI | 27inch - 本地及在线音乐/Offline&Online Music Player & audio manager |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-01-23 | N/A | N/A | [6 empty] | Xu, Amy <XYAFEI@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 穆仁萍 v_murenping@baidu.com |  |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | License | N | 在音乐功能里包含 | close |  |  | 2019-12-16 | 2019-12-13 | 2019-12-30 | 2020-02-19 | B | 1/9/2020: updated MRD to be available today 1/10/2020: check today with FO 1/13/2020: MRD update 2/4/2020: updated MRD to be available 2/4 2/6/2020: pending due to Baidu 2/10/2020: plan to sign off | [5 empty] | x | 内容生态 | extend | Y |  |  |  | DCV1 | R00
115 | Passenger Feature for 27 | HMI | AR Front View/360 View/BLIS View |  | 90% | 10% |  | Desay |  |  | x | [10 empty] | Chen, Emma<jchen276@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  | N: N; ED&T: ED&T; N: Y |  | cancel | [7 empty] | 2/6/2020: supplier to provide plan date 2/19/2020：FO change? 2/24/2020: MRD to be ready on this Wednesday 3/3/2020: DAT team had different view with HMI team. 3/10/2020: CD542 CPE meeting - delete this feature now.
116 | Passenger Feature for 27 | EESE/DI | 27"空调设置(climate control from passenger area) |  | 90% | 10% |  | Desay |  | x | x | 27" specific |  | N/A | N/A |  |  |  | same with climate control | Ford_MRD_空调_TBD_v1.7_20200222.docx 空调页面说明_v1.5.xls 空调页面说明_硬按键软按键.xlsx |  | Li, Jun (J.) <jli198@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Wang Ziyan（Ziyan.Wang@desay-svautomotive.com） |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | ED&T | Y |  | close |  |  | 2020-01-09 | 2020-01-09 | 2020-01-16 | 2020-02-07 | N.A | 1/13/2020: combine with climate control 2/7/2020: plan to sign off; sign off | [5 empty] | x | setting | extend | Y |  |  |  | DCV2 | R00
117 | Passenger Feature for 27 | EESE/IVI(Diven) | 副驾视频播放(支持 DLNA)/Passenger Video Playback(Support DLNA) |  | 80% | 20% | NA | Desay |  | x | x | always enable | 2020-01-23 | N/A | N/A |  |  |  |  | Ford_MRD_DLNA_20200217.docx |  | Jia, Elaine (T.) <tjia2@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  | 待确定--福特 | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | ED&T | N |  | close |  |  | 2020-02-14 | 2020-02-17 | 2020-02-21 | 2020-02-18 | N.A | 12/30/2019: new plan 2/4/2020: Baidu transfer to Desay 2/6/2020: supplier to provide plan date 2/17/2020: MRD avaialble, review | [5 empty] | x | DLNA display | extend | N |  |  |  | R00 | ?
118 | Passenger Feature for 27 | EESE/IVI(Diven) | 副驾在线视频/Online Video-clarify |  | 10% | 90% | NA | Baidu |  | x | x |  | 2020-01-23 | N/A | N/A |  |  |  |  | 在线视频 Online video.docx |  | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 穆仁萍 v_murenping@baidu.com |  |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | License | N | 在视频功能里包含 | close |  |  | 2020-01-10 | 2020-01-13 | 2020-01-17 | 2020-02-19 | B | 12/30/2019: new plan 1/13/2020: MRD update today 2/6/2020: pending due to Baidu |  |  |  |  | x | x | 内容生态 | extend | Y |  |  |  | DCV1 | R04
119 | Passenger Feature for 27 | EESE/IVI(Forrest) | 副驾主页/Passenger HomeScreen |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-02-03 | N/A | N/A |  |  |  |  | 【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 杨萍 v_yangping03@baidu.com |  |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | ED&T | N |  | close |  |  | 2019-12-16 | 2019-12-13 | 2019-12-30 | 2020-01-19 | N.A | 12/25/2019: sign off? 12/30/2019: update by Baidu 1/2/2020: updated MRD? 1/8/2020: plan to sign off 1/17/2020: sign off for Desay 1/19/2020: sign off for Baidu |  |  |  |  | x | x | Launcher | extend | Y |  |  |  | DCV1 | R04
120 | Passenger Feature for 27 | EESE/IVI(Diven) | 27"地图/including Passenger Map&Navigation |  | 10% | 90% | NA | Baidu |  | x | x |  | 2020-02-03 | N/A | N/A |  |  |  |  | 【福特Phase4】MRD_27寸_地图_HMI变更_V1.2_2020_01_16-终版-已评审 |  | Yao, Tristan (Lan) <LYAO17@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 原翼 yuanyi13@baidu.com |  |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | License | N | 在地图功能里包含 | close |  |  | 2019-12-30 | 2019-12-30 | 2020-01-06 | 2020-02-06 | N.A | 12/30/2019: pending by Ford FO 1/9/2020: need Baidu's updated MRD 1/10/2020: meeting today 1/13/2020: Baidu check and update MRD, arrange follow up meeting 2/4/2020: plan to sign off 2/6/2020: sign off |  |  |  |  | x | x | 地图 | extend | Y |  |  |  | DCV0 | R04
121 | Passenger Feature for 27 | CVPP | 副驾天气预报/Weather forecast |  | 10% | 90% | NA | Baidu |  | x | x |  | 2020-01-23 | N/A | N/A |  |  |  |  | 【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Shi, Stella (J.) <jshi32@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 杨萍 v_yangping03@baidu.com |  |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | License | N | 在天气功能里包含 | close |  |  | 2019-12-16 | 2019-12-13 | 2019-12-30 | 2020-01-19 | N.A | 12/24/2019: combine to 27" launcher. Baidu check and feedback 12/25/2019: confirmed, mentioned in the spec. 12/30/2019: pending by Ford FO 1/9/2020: plan to sign off 1/9/2020: detail strategy shall follow whether in driver side. TBD 1/19/2020: sign off by Baidu | [5 empty] | x | Launcher | CVPP |  |  |  |  | DCV0 | R04
122 | Passenger Feature for 27 | EESE/IVI(Forrest) | 副驾系统设置/Passenger system setting（system settings display in passenger area as well） |  | 90% | 10% | NA | Desay |  | x | x | 27" specific |  | N/A | N/A |  |  |  |  | 合并到NO80 |  | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | ED&T | N |  | close |  |  | 2020-02-20 | 2020-02-13 | 2020-02-20 | 2020-02-13 | D | 2/6/2020: supplier to provide plan date 2/13/2020: sign off |  |  |  |  | x | x | setting | extend | Y |  |  |  | DCV2 | ?
123 | Passenger Feature for 27 | IVI(removed) | 副驾文件浏览器／Passenger File Manager |  | 90% | 10% | NA | Desay |  | x | x | [10 empty] | Jia, Elaine (T.) <tjia2@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Dong Zhaojun<zhaojun.dong@desay-svautootive.com> |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | N | N | N | ED&T | N |  | cancel | [6 empty] | N.A | 2/6/2020: supplier to provide plan date 2/17/2020: FO cancel
124 | Passenger Feature for 27 | EESE/IVI(Diven) | 副驾图片浏览器/Passenger Picture Viewer |  | 90% | 10% | NA | Desay |  | x | x | 27" specific |  | N/A | N/A |  |  |  |  | Picture_MRD.DOCX |  | Jia, Elaine (T.) <tjia2@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Dong Zhaojun<zhaojun.dong@desay-svautootive.com> |  |  | N | Y | N | Y | N | N | N | N | N | N | N | Y | Y | Y | N | N | Y | Y | N | ED&T | N |  | close |  |  | 2020-02-14 | 2020-02-14 | 2020-02-18 | 2020-02-14 | D | 2/6/2020: supplier to provide plan date 2/14/2020: plan to sign off 2/14/2020: sign off | [5 empty] | x | PicMgr | extend | Y |  |  |  | DCV1 | ?
125 | C/O from ICA1 | IVI(removed) | features C/O from IVI ICA1（461 Phase1/2/3 features need to move to Phase4. Please refer to column "G&H" of sheet2 "461 CO Phase1&2&3 feature"） |  | 10% | 90% |  | Baidu |  |  | x |  | 2020-01-23 | [8 empty] | Yu, Yaxing (Y.) <yyu55@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | License | Y |  | cancel | [7 empty] | 2/3/2020: not needed as features already reviewed
126 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Diven) | 人物百科 Celebrity encyclopedia | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-23 | 【福特U554&P702&U725&542低配】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316.pdf 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.002 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.001 | 【福特CX727】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316 |  |  |  |  | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Qi, Xuliang<xqi14@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 刘韧 v_liuren@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close |  |  | 2020-02-06 | 2020-02-06 | 2020-02-28 | 2020-02-28 | N.A | 1/2/2020: combined in feature 90; 在“更多”里面提供了使用说明。 2/6/2020: pending due to Ford FO 2/20/2020: postphone to 3/30 |  |  | WOW | WOW |  | x | 语义垂类 | extend | Y |  |  |  | DCV0 | DCV0 | DCV2 | DCV3
127 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Diven) | 世界之最 Most ** of the world | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 | 【福特U554&P702&U725&542低配】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316.pdf 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.002 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.001 | 【福特CX727】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316 |  |  |  |  | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Qi, Xuliang<xqi14@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 刘韧 v_liuren@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close |  |  | 2020-02-06 | 2020-02-06 | 2020-02-28 | 2020-02-28 | N.A | 1/2/2020: combined in feature 90; 在“更多”里面提供了使用说明。 2/20/2020: postphone to 3/30 |  |  | WOW | WOW |  | x | 语义垂类 | extend | Y |  |  |  | DCV0 | DCV0 | DCV2 | DCV3
128 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 智慧停车 smart parking | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 | 【林肯U554】智慧停车场_【ID128】_V1.4_20200415 【林肯U554】智慧停车场_车辆解绑【ID128】_V1.1_20200415 | 【福特CX727】智慧停车场_【ID128】_V1.5_20200415 【福特CX727】智慧停车场_个人中心【ID128】_V1.4_20200408 【福特CX727】智慧停车场_车辆解绑【ID128】_V1.5_20200415 |  |  |  | MRD | 【福特Phase4】MRD_ETCP_福特车型_V1.1_20200206 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 段家仪 v_duanjiayi@baidu.com |  | Follow Baidu | [23 empty] | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-02-14 | N.A | 2/7/2020: Ford FO check 2/12/2020:plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | x | 服务生态 | CVPP |  |  |  |  | DCV1 | DCV1 | DCV2 | DCV3 | bar: Y to N
129 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 电影购票 ticket booking | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 | UE c/o from phase2, UI only | UE c/o from phase2, UI only |  |  |  | MRD | 【福特Phase4】MRD电影票_福特车型_V1.0_20191219 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 段家仪 v_duanjiayi@baidu.com |  | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-02-14 | N.A | 2/7/2020: Ford FO check 2/12/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | x | 服务生态 | CVPP |  |  |  |  | DCV1 | DCV1 | DCV2 | DCV3
130 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 酒店预定 hotel booking | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 | UE c/o from phase2, UI only | UE c/o from phase2, UI only |  |  |  | MRD | 【福特Phase4】MRD_酒店预订_福特车型_V1.0_20191219 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 段家仪 v_duanjiayi@baidu.com |  | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-02-14 | N.A | 2/7/2020: Ford FO check 2/12/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | x | 服务生态 | CVPP |  |  |  |  | DCV1 | DCV1 | DCV2 | DCV3
131 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | IVI(removed) | 车载KTV |  | 0% | 100% |  | Baidu |  |  |  |  | 2020-01-23 | [8 empty] | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  |  | KTV麦克风作为选装件 需要按车型标定 福特确认是否需要 | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | License | Y |  | cancel | [7 empty] | 1/10/2020: applied in phase4? 1/13/2020: feature removed confirmed with Susan | [13 empty] | DCV1
132 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Diven) | 在线视频（爱奇艺） | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 | 【林肯U554】爱奇艺_本地视频_ID76、132_V2.1_202000310 | [5 empty] | 在线视频 Online video.docx |  | Xu, Amy (X.) <xyafei@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 穆仁萍 v_murenping@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close |  |  | 2020-02-04 | 2020-02-04 | 2020-02-11 | 2020-02-06 | N.A | 2/6/2020: sign off |  |  | Basic function | entertainment |  | x | 内容生态 | extend | Y |  |  |  | DCV1 | DCV1 | DCV2 | DCV3
133 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 聚合支付 / aggregate payment | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-01-15 | 【林肯U554】_ID133_聚合支付_V1.34_20200421 | 【福特CX727】_ID133聚合支付_V1.25_20200421 |  |  |  | MRD | 【phase4】MRD_支付模块_福特/林肯_V1.8_2019_05_30 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 潘承栋 v_panchengdong@baidu.com |  | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License |  |  | close |  |  | 2020-02-07 | 2020-02-10 | 2020-02-14 | 2020-02-14 | N.A | 2/12/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | x | 服务生态 | CVPP |  |  |  |  | DCV1 | DCV1 | DCV2 | DCV3
134 | Passenger Feature for 27 | IVI(removed) | 27" 输入法 - 副驾输入法 / words input |  | 90% | 10% |  | Desay |  | x | x | [10 empty] | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Wu Zhengxue(Zhengxue.Wu2@desay-svautomotive.com) | 27" 由DESAY study，给出新的proposal | [23 empty] | cancel | [6 empty] | D | 2/6/2020: supplier to provide plan date 2/11/2020: Based on the info from FO, Baidu can not support. Cancel this feature | bar: Y to Y; N
135 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Forrest) | 百度输入法（包括27“主屏输入法） | Y | 10% | 90% |  | Baidu |  | x | x |  | 2019-12-20 | UE missed, @baidu | UE missed, @baidu |  |  |  | n.a suppliers provide the proposal and review; including HMI and data collection. | 无MRD | N/A | Chen, Emma (J.) <jchen276@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | 杨萍 v_yangping03@baidu.com |  |  | 主副驾都需要输入法的情况下，百度无法支持 Phase1/2输入法的问题，福特评估是否能接受 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | License | N |  | close |  |  | 2019-12-30 | 2019-12-30 | 2020-03-30 |  | B | 12/30输出车机输入法+语音输入可行性评估。 下周输出车机版与手机版功能点全部差异。 12/30/2019: no comments from FO; 语音输入待定 1/2/2020: c/o phase2的HMI改进需求； 1/9/2020: 2 open items to be tracked by Baidu 1. 语音输入 2. 输入法在27寸上面的浮动可行性-lusia 1/10/2020: feedback before 1/14 2/4/2020: Pending due to supplier 4/20/2020: pending by CAF approve. Baidu need 2 months to develop this function. backup plan: use the previous SDK. |  |  | Basic function | basic |  |  | 输入法 | basic | N |  |  |  | R04 |  | R06 | R05.01
136 | Vehicle Features/Interfaces | EESE/IVI(Roger) | AHUD and features (CAN bus interface) | Y | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | N/A | N/A |  |  |  | folder: cluster Interaction | 合并到NO14 |  | Chen, James (J.) <jchen303@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Chen Xiujing(Xiujing.Chen@desay-svautomotive.com) | [24 empty] | close |  |  | 2020-01-10 | 2020-02-14 | 2020-01-17 | 2020-02-28 | N.A | 12/30/2019: no MRD/replan info 1/6/2020: replan to 1/10 1/10/2020: Desay CAN check based on interaction spec between IVI & cluster. 1/13/2020: 1/14 desay feedback, combine to cluster feature 14. |  |  | Vehicle related | AHUD |  |  | AHUD interaction | extend | N | bar: Y to Y; N
137 | Vehicle Features/Interfaces | CVPP | Auto Air Refresh |  | 30% | 70% |  | Baidu |  | x | x | DE03 B3b7 | 2019-12-30 | U554 AAR_ID137_v3.9_20200424 | CX727 AAR_ID137_v2.4_20200424 |  |  |  | Draft available on Dec. 11th | 福特Phase 4_AAR_MRD 2020_0214 | H26g_SYNC4_Auto_Air_Refresh_Gen_1_Plus_RELEASED_v2_03_MY21 | Shi, Stella (J.) <jshi32@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> | 苏静 v_sujing01@baidu.com |  |  | Shi Stella | N | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y |  |  |  | close |  |  | 2019-12-30 | 2020-01-02 | 2020-01-06 | 2020-02-14 | N.A | 1/2/2020: MRD available 1/9/2020: status check 1/10/2020: involve HMI to confirm 1/13/2020: HMI ok, interface not clear. 1/19/2020: sign off 2/14/2020: Baidu check- change? 2/14/2020: sign off after confirm |  |  | CVPP | APP |  | x | 硬件联动 | CVPP |  |  |  |  | DCV3 | DCV4 | DCV2 | R00
138 | BU features | EESE/IVI(Diven) | IOD- Behavior Coaching Display Client |  | 95% | 5% |  | Desay |  |  | x | yes |  | 【林肯U554】IOD实时车况_ID138&141&142&143&144&145&146_V1.4_20200416 | 【福特727】IOD_ID138&141&142&143&144&145_V1.6_20200410 |  |  |  | Behavior Coaching Display Client v2 APIM Imp Guide v1.0 Nov 19, 2018.xlsx Behavior Coaching Display Client v2 APIM SPSS v1.0 Nov 19, 2018.docx Behavior Coaching Display Client v2 APIM SPSS v1.0 Nov 19, 2018.pdf | Ford_MRD_BehaviorCoachingDisplayClient_V02.docx | H87a_SYNC4_IoD_In _SYNC_Requirements-RELEASED_v1_03_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang dong <Dong.Wang@desay-svautomotive |  | 待确定--HMI | N | N | N | N | Y | Y | N | N | N | N | N | N | N | N | N | N | N | N | Y |  | Y |  | reopen |  |  | 2020-02-20 | 2020-02-18 | 2020-02-25 | 2020-02-19 | Desay | 2/6/2020: supplier to provide plan date 2/18/2020: push Diven @Emma 7/3/2020: CD542 SAR cancel this feature 2020/10/23: UE/UI | [6 empty] | IOD | basic | Y | [5 empty] | DCV2 | DCV3
139 | BU features | EESE/IVI(Forrest) | Enhanced VO Test (FCPA Logging) [On hold Feature] |  | 60% | 40% |  | Desay |  |  |  | n.a | [8 empty] | N/A | Chen, Emma (J.) <jchen276@ford.com> | N/A |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) | [24 empty] | cancel |  |  | hold-on | hold-on | hold-on | hold-on | N.A | 2/6/2020: supplier to provide plan date 2/6/2020: ON-hold till SPSS is ready 4/15/2020: 把VOCF的测试log同步到福特云，中国不适用。 |  |  | N.A | N.A |  |  | hold on | bar: Y to Y; N
140 | BU features | EESE/IVI(Roger) | Detroit Symphony Orchestra chimes |  | 100% | 0% |  | Desay |  | x | x | yes | 2019-12-30 | N/A | N/A |  |  |  | Alerts APIM Imp Guide v1.2 May 3, 2017.xlsx Alerts APIM SPSS v1.2 May 3, 2017.pdf RQT-001502-012992_12 Chime Sound Quality.pdf | Ford IVI SW Q&A_Audio&A2B.xlsx |  | Li Xuedong XLI244@ford.com | N/A |  | Xu Jianjun（Jianjun.Xu@desay-svautomotive.com） | [24 empty] | close |  |  | 2019-12-30 | 2019-12-27 | 2020-01-06 | 2019-12-30 | N.A | 12/27/2019: checked with FO, combined with item 9. 12/30/2019: close based on the mail confirm |  |  | Chime management | Chime management |  |  | audio | extend | N | bar: Y to Y; N
141 | BU features | EESE/IVI(Diven) | IOD - Fuel Economy |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】IOD实时车况_ID138&141&142&143&144&145&146_V1.4_20200416 | 【福特727】IOD_ID138&141&142&143&144&145_V1.6_20200410 |  |  |  | Fuel Economy SPSS v1.1 January 31, 2019 Fuel Economy APIM Imp Guide v1.1 January 31, 2019 | Ford_MRD_IoD_FuelEconomy_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> |  | 细节待确定--HMI | N | N | N | N | Y | Y | N | N | N | N | N | N | N | N | N | N | N | N | Y |  | Y |  | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open | [5 empty] | IOD | basic | Y | [5 empty] | DCV2 | DCV3
142 | BU features | EESE/IVI(Diven) | IOD - Pitch and Roll |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】IOD实时车况_ID138&141&142&143&144&145&146_V1.4_20200416 | 【福特727】IOD_ID138&141&142&143&144&145_V1.6_20200410 |  |  |  | Pitch and Roll SPSS v1.0.1 Dec 18, 2018 Pitch and Roll APIM Imp Guide v1.0.1 Dec 18, 2018 | Ford_MRD_IoD-PitchandRoll_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open | [5 empty] | IOD | basic | bar: Y to Y; N
143 | BU features | EESE/IVI(Diven) | IOD - SeatBelt (information on demand) |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】IOD实时车况_ID138&141&142&143&144&145&146_V1.4_20200416 | 【福特727】IOD_ID138&141&142&143&144&145_V1.6_20200410 |  |  |  | Seatbelt IOD SPSS v1.0 Dec 19, 2018 Seatbelt IOD APIM Imp Guide v1.0 Dec 19, 2018 | Ford_MRD_IoD_SeatBelt_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open | [5 empty] | IOD | basic | Y | [5 empty] | DCV2 | DCV3 | bar: Y to Y; N
144 | BU features | EESE/IVI(Diven) | IOD - TPMS (Information on Demand) |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】IOD实时车况_ID138&141&142&143&144&145&146_V1.4_20200416 【林肯U554】Launcher&system UI_ID69&195&144&146_V1.9_20200414 | 【福特727】IOD_ID138&141&142&143&144&145_V1.6_20200410 |  |  |  | TPMS Information On Demand SPSS v1.0 March 5, 2019 TPMS Information On Demand Imp Guide v1.0 March 5, 2019 | Ford_MRD_IoD-TPMS_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open |  | vehicle related | Message center |  |  | IOD | basic | Y | [5 empty] | DCV2 | DCV3 | bar: Y to Y; N
145 | BU features | EESE/IVI(Diven) | IOD - Trip Information On Demand |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】IOD实时车况_ID138&141&142&143&144&145&146_V1.4_20200416.pdf | 【福特727】IOD_ID138&141&142&143&144&145_V1.6_20200410 |  |  |  | Trip Information on Demand SPSS v1.1 Nov 16, 2018 Trip Information on Demand APIM Imp Guide v1.1 Nov 16, 2018 | Ford_MRD_IoD_Trip_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open | [5 empty] | IOD | basic | Y | [5 empty] | DCV2 | DCV3 | bar: Y to Y; N
146 | BU features | EESE/IVI(Diven) | IOD - Off Road |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】IOD实时车况_ID138&141&142&143&144&145&146_V1.4_20200416 【林肯U554】Launcher&system UI_ID69&195&144&146_V1.9_20200414 | N/A |  |  |  | Off-Road Status IOD APIM SPSS v1.0 Aug 23, 2019.pdf Off-Road Status IOD APIM Imp Guide v1.0 Aug 23, 2019.xlsx | Ford_MRD_IoD-Off-road_Status_V02.docx | P87_15P_Vehicle_IODs_R_v1_00_MY21 H87_SYNC4_InformationOnDemand-RELEASED_V1_13_MY21 | Yu, Diven (D.W.) <dyu12@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [23 empty] | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/Off%20Road%20Turn%20Assist | close |  |  | 2020-01-06 | 2020-01-10 | 2020-01-13 | 2020-01-11 | N.A | 12/30/2019: replan; HMI missing 1/10/2020: plan to sign off 1/11/2020: sign off | archive and HMI open |  | vehicle related | Message center |  |  | IOD | basic | Y | bar: Y to Y; N
147 | BU features | CVPP | Backup Startup Passcode for PAAK | y | 95% | 5% | NA | Desay |  |  | x | yes | 2020-02-03 | 林肯U554MCA空调设置_ID12_v1.8_20200418 | 【福特 727】智能备用密钥_ID147_V1.7_20200508 |  |  |  | PRD 【更新】【Phase2林肯】LBI智能备用密钥_MRD_2019_7_11-v2.0.pdf | PaaK BSP (LBI) Implementation Specification 2.8 Imp Guide v1.1_20200213.xlsx | H31k_SYNC4_Settings_R_v0_36_MY21 H31m_SYNC4_Backup Ignition_R_v1.3_MY21 | Zhang, Yan (Y.) <YZHAN481@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  | Phase1/2百度已开发的功能，Phase4是否沿用原有的模式，由百度开发？？ | N | N | N | N | N | N | N | N | N | N | Y | N | N | N | N | Y | Y | N | N |  | Y |  | close |  |  | 2020-02-21 | 2020-02-13 | 2020-02-28 | 2020-02-14 | N.A | 2/4/2020: R&R to be updated? 2/6/2020: tranfer to Desay, supplier to provide plan date 2/14/2020: sign off |  |  | CVPP | PAAK |  | x | PAAK | CVPP
148 | Basic features | CVPP | Message Center (CVPP) | y | 5% | 95% |  | Baidu |  | x | x |  | 2019-12-27 | 【林肯_U554】消息中心_ID148_V2.1_20200401 | 【福特CX727】消息中心_ID148__V2.3_20200401 |  |  |  | spec Dec. 13th | 【福特phase4】MRD_消息中心_福特CX727U725P702CD542U625ICA_V2.7_2020_02_13 【福特phase4】MRD_消息中心_林肯U554_V2.7_2020_02_13 | H22a_SYNC4_Screen_Interruption_Table_RELEASED_ v1_01_MY21 Message_Center_Display_Interface_With_Setup_and_Warnings_In_Centerstack - CGEA1.3_v1.2.docm | Wang, Johnny (J.) <jwang308@ford.com>（Harlow, Julee (J.L.) <jharlow6@ford.com>） | Pan, Jingjing (J.) <jpan35@ford.com> | 苏争 _suzheng01@baidu.com | [25 empty] | close |  |  | 2019-12-27 | 2020-01-02 | 2020-01-06 | 2020-02-14 | B | 1/2/2020: MRD available. Need Ford FO check. 1/9/2020: status check 1/10/2020: MRD update by Baidu, send to Ford FO 1/13/2020: MRD available, meeting this Wednesday 2/3/2020: pending by Ford FO, baidu arrange meeting 2/10/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | Message center |  |  | 消息中心 | CVPP |  |  |  |  | DCV0 | DCV0 | DCV2 | DCV3 | bar: Y to Y; N
149 | Basic features | EESE/IVI(Forrest) | Message Center Client (APIM) |  | 90% | 10% |  | Desay |  | x | x | yes - missed? | 2019-12-25 | N/A | N/A |  |  |  | Message Center Client v3 SPSS v1.1 Aug 23, 2019 Message Center Server v3 SPSS v1.1 Aug 23, 2019 | Ford_MRD_MessageCenterClient_V06.docx | CX727_Message Center Client_Interaction Spec_20200110.pdf Global_Msg_List_ver81_Released_2_4_2020.xlsx | Xu, Harriet (J.) <jxu128@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-10 | 2020-02-25 | 2020-01-17 | 2020-03-02 | N.A | 12/30/2019: replan 1/10/2020: Desay provide OIL 1/13/2020: check status 2/24/2020: Open item list send out by FO | [6 empty] | Message center | core | Y | [5 empty] | DCV2 | DCV3 | bar: Y to Y; N
150 | BU features | DAT | Multi Camera - CHMSL/AUX Camera/Rock Crawl |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | N/A | N/A |  |  |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36k_SYNC4_Camera_Systems_R_v0_20_MY21 H36t_SYNC4_Trailer Settings_RELEASED_1_18_MY21 P702 post J1 H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21 | Li, Xin<xli268@ford.com>/Zheng, Tina (T.) <tzheng4@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | N | N | N | N | N | N | Y | Y | Y | N | N | N | N | N | N | N | N | N | ED&T | Y |  | close |  |  | 2020-01-08 | 2020-01-14 | 2020-01-15 | 2020-01-20 | N.A | 12/30/2019: Jan. 8th meeting/replan 1/10/2020: on-site review 1/13/2020: desay check status 2/8/2020: sign off on 1/20 |  |  | driver assist | Driver assist setting |  |  | camera | basic | Y
151 | BU features | EESE/Body Security | Multi-Contoured Seats (Enhanced Massage Seats) |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】座椅设置_ID151&152_v1.3_20200309 | N/A |  |  |  | Multi Contoured Seats Client V2 Imp Guide v1.3 June 28, 2018.xlsx Multi Contoured Seats Client V2 SPSS v1.3 June 28, 2018.docx Multi Contoured Seats Client V2 SPSS v1.3 June 28, 2018.pdf | 不需要输出MRD | H74a_SYNC4_Seat_Controls_RELEASED_0_06_MY21 | Xia,Zhiqiang<zxia13@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-08 | 2020-02-14 | 2020-01-15 | 2020-02-19 | F | 12/30/2019: Jan. 8th meeting/replan 1/10/2020: on-site review 1/13/2020: 1/14 MRD or open item list 2/14/2020: plan to sign off |  |  | driver assist | Driver assist setting |  |  | setting | basic | Y | bar: Y to Y; N
152 | BU features | EESE/Body Security | Multi-Contoured Seats (Massage Seats) | Y | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】座椅设置_ID151&152_v1.3_20200309 | N/A |  |  |  | Multi Contoured Seats APIM Imp Guide v1.2 Jun 9 2015.xlsx Multi Contoured Seats APIM SPSS v1.2 Jun 9 2015.docx Multi Contoured Seats APIM SPSS v1.2 Jun 9 2015.pdf | 不需要输出MRD | H74a_SYNC4_Seat_Controls_RELEASED_0_06_MY21 | Xia,Zhiqiang<zxia13@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-08 | 2020-01-19 | 2020-01-15 | 2020-01-19 | N.A | 12/30/2019: Jan. 8th meeting/replan 1/10/2020: on-site review 1/13/2020: 1/14 OIL by desay 1/19/2020: sign off, open item archived | 1. Do we need to support Massage pattern (Mode)? A: Yes. <Follow Multi Contoured Seats Client V2 SPSS v1.3 June 28, 2018> - Xia, Zhiqiang to double confirm 2. Initiation process During Key On, Does SYNC4 need to send initial value to SCMG/SCMH (MCS module)? - Xia, Zhiqiang 3. How many bladders for U554 MCA (7 or 11 bladder)? - Diven to check PDL 4. U554 MCA - MCS seat buttons layout and function definition | [5 empty] | setting | basic | Y | bar: Y to Y; N
153 | BU features | EESE/IVI(Forrest) | Trail Turn Assist (Soft switch) |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | N/A | N/A |  |  |  | TTA_SoftSwitch_FunctionSpecification_112519.pdf | Ford_MRD_SoftSwitch_TrailTurnAssist.docx | H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21 H31c_SYNC4_InfoBook_Supplement_RELEASED_v1_17_MY21 | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-10 | 2020-01-10 | 2020-01-17 | 2020-01-11 | N.A | 12/30/2019: spec avaialble: TTA_SoftSwitch_FunctionSpecification_112519 1/6/2020: replan to 1/10 1/10/2020: Desay send out OIL | HMI open - menu, display info |  |  |  | x |  | soft switch | basic | Y | bar: Y to Y; N
154 | BU features | EESE/IVI(PMT1)(Forrest) | Power Running Boards (PRB) |  | 90% | 10% |  | Desay |  |  | x | yes |  | 【林肯U554】电动踏板PRB_ID154_V1.4_20200330 | N/A |  |  |  | Power Running Boards Softswitch InterfaceClient SPSS v1.0 October 5, 2018.pdf Power Running Boards Softswitch InterfaceClient Imp Guide v1.0 October 5, 2018.xlsx | 合并到NO11 | H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21 H31k_SYNC4_Settings_R_v0_36_MY21 H31c_SYNC4_InfoBook_Supplement_RELEASED_v1_17_MY21 | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [23 empty] | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/Power%20Running%20Boards%20(PRB) | close |  |  | 2020-02-20 | 2020-02-10 | 2020-02-27 | 2020-02-10 | D | 2/6/2020: supplier to provide plan date 2/10/2020: sign off |  |  | vehicle related | Vehicle setting | x |  | soft switch | basic | Y | bar: Y to Y; N
155 | BU features | EESE/IVI(PMT1)(Forrest) | Power Tailgate (FordPass/SYNC); |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | N/A | N/A |  |  |  | TailGate Softswitch InterfaceClient Imp Guide v1.3 June 25, 2019.xlsx TailGate Softswitch InterfaceClient SPSS v1.3 June 25, 2019.pdf | Ford_MRD_SoftSwitch_PowerTailgate_V02.docx | H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21 H31k_SYNC4_Settings_R_v0_36_MY21 H31c_SYNC4_InfoBook_Supplement_RELEASED_v1_17_MY21 | Chen, Emma (J.) <jchen276@ford.com>/ Li, Xuedong (X.) <xli244@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-08 | 2020-01-08 | 2020-01-15 | 2020-01-13 | N.A | 12/30/2019: Jan. 8th meeting/replan 1/8/2020: Desay send out MRD today 1/9/2020: desay provide OIL, plan to sign off 1/13/2020: sign off after archive in github and checklist update |  |  |  |  | x |  | soft switch | core | Y | bar: Y to Y; N
156 | BU features | DAT | Remote Park Assist (RePA) |  | 90% | 10% |  | Desay |  |  | x | yes | [6 empty] | Remote Active Park Assist SPSS v1.0 Feb 4, 2020 |  | P36k_15P_SYNC4_Camera_R_v2_00_MY21 | He, Michael (X.) <xhe22@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> | [24 empty] | new |  |  | 2020-02-20 | 2020-02-28 | 2020-02-27 |  | F | 2/6/2020: supplier to provide plan date 2/24/2020: Open item list to be provided before tomorrow 5/14/2020: cancelled based on info from program and FO |  |  | driver assist | Driver assist HMI |  |  | camera | bar: Y to Y; N
157 | BU features | EESE/IVI(Roger) | Revel QLI 3D Audio (Audio System, settings) |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】音效设置_ID83&84&157_V1.3_20200303 | N/A |  |  |  | Audio Settings APIM SPSS v1.4 Nov 6, 2019 Audio Settings APIM Imp Guide v1.4 Nov 6, 2019 | 不需要输出MRD |  | Li Xuedong XLI244@ford.com | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Xu Jianjun（Jianjun.Xu@desay-svautomotive.com） | [24 empty] | close |  |  | 2019-12-30 | 2019-12-27 | 2020-01-06 | 2020-01-14 | N.A | 12/27/2019: checked with FO, mail to FO for the OIL. 1/6/2020: plan to sign off 1/14/2020: sign off |  |  | Chime management | Chime management | x |  | audio | extend | Y | bar: Y to Y; N
158 | BU features | EESE/IVI(PMT3)(Forrest) | SELECTABLE DRIVE MODES (different modes for each program) |  | 90% | 10% |  | Desay |  | x | x | yes | 2019-12-30 | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  | Selectable Drive Mode APIM Imp Guide v1.2 Aug 21, 2019.xlsx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.docx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.pdf | 不需要输出MRD |  | Zhang Spring JZHAN136@ford.com | Hu, Pin (P.) <phu13@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [24 empty] | close |  |  | 2019-12-30 | 2020-01-10 | 2020-01-06 | 2020-01-15 | N.A | HMI: Desay prepare UE 12/23/2019: SPSS is ok, while HMI need to be provided. 12/30/2019: need Desay to provide HMI 1/6/2020: Desay mail to FO/HMI 1/10/2020: Ford HMI can not accept the prospoal - open item Desay provide OIL today 1/13/2020: delay to today 1/15/2020: sign off | HMI open |  | Vehicle related | SDM |  |  | setting | core | Y |  |  |  | DCV2 | DCV3 | DCV2 | DCV3 | bar: Y to Y; N
159 | BU features | CVPP | Stolen Vehicle Services InterfaceClient (APIM) |  | 90% | 10% |  | Desay |  | x | x | always enable | [6 empty] | PRD 2018-02-28_SVS_PRD.pdf | Stolen Vehicle Services InterfaceClient Imp Guide v1.8 August 9, 2019 for Desay_0225.xlsx | N/A | Ren, Siyuan (Alex.) <sren6@ford.com> | N/A |  | Ding, Yunrong <Yunrong.Ding@desay-svautomotive.com> | [24 empty] | cancel |  |  | 2020-01-14 | 2020-02-14 | 2020-01-21 | 2020-02-19 | N.A | 1/6/2020: Desay replan 2/12/2020: plan to close before 2/21 3/31/2020: hold on 4/15/2020: officially cancelled |  | x | FNV2 | FNV2-basic |  |  | SVS | bar: Y to Y
160 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(PMT4)(Forrest) | One Pedal Drive |  | 90% | 10% |  | Desay |  |  | x | yes |  | N/A | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  | One-Pedal Drive APIM SPSS v1.0 May 14, 2019.pdf One-Pedal Drive APIM Imp Guide v1.0 May 14, 2019.xlsx | 合并到NO11 | H31n_SYNC4_Features_Domain_RELEASED_V1_04_MY21(TBD) | Chen, Emma (J.) <jchen276@ford.com>/ Li, Xuedong (X.) <xli244@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [23 empty] | https://github.ford.com/APIMCIS/APIMCIS/tree/master/02_Specification/01_Ford_SPEC/DCV1/One%20Pedal%20Drive | close |  |  | 2019-12-15 | 2019-12-15 | 2019-12-22 | 2020-01-11 | D | 2/10/2020: sign off - discussed before. |  |  |  |  | x |  | setting | basic | Y | [5 empty] | DCV2 | DCV3 | bar: Y to Y; N
| Connectivity | CVPP | Vehicle Health/Alert [ include, Show the vehicle Telltale Warnings] |  | 70% | 30% | VR 可唤醒 | Desay |  | x | x | yes |  | 【林肯U554】车辆状态_ID98&161&189__V1.5-20200324 | 【福特727】车辆状况_ID98&161&189_V1.5_20200428 |  |  |  | PRD | Vehicle Health Alert APIM Imp Guide v1.4_20200302.xlsx |  | Lu, Chao (C.) <clu42@ford.com> Chen, Wei (W.) <WCHEN160@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-01-14 | 2020-02-28 | 2020-01-21 | 2020-02-28 | D | 1/6/2020: Desay replan 2/12/2020: plan to close before 2/18 2/24/2020: check the status |  | x | FNV2 | FNV2-basic |  | x | vehicle information | CVPP |  |  |  |  | DCV1 | DCV3 | DCV2 | DCV3 | bar: Y to Y
162 | Connectivity | CVPP | TCU supply feed |  | 90% | 10% |  | Desay |  | x | x | [7 empty] | A51s_SYNC4-Supplier_Feed_Specification_214.pdf |  | N/A | Zong, Yongtao (Y.) <yzong@ford.com> | N/A |  | liu, zhiyong | [24 empty] | cancel | [6 empty] | N.A | 12/30/2019: no MRD/replan info 1/6/2020: regular tracking, provide a plan 1/13/2020: plan on-going 2/24/2020: Tracked in project meeting? 3/3/2020: 针对FNV2项目China IVI SupplyFeed，Global team策略是取消peripheral ECUs（包括IVI）的SupplyFeed requirement。  A51t FNV2-SupplyFeed Spec暂停开发，同时SupplyFeed中的Security package是独立的流程，由Security team Eric继续与Desay跟进开发；  保留前期Desay与Ford完成VPN tunnel的建立，用于Security package process； |  |  | Basic function | EOL | bar: Y to Y
163 | Connectivity | CVPP | IVI TCU Provisioning - Baidu cloud, Ford cloud |  | 90% | 10% |  | Desay |  | x | x | always enable |  | N/A | N/A |  |  |  | Peripheral Module Provisioning SPSS v1.3 Apr 10, 2019.pdf | Peripheral-Provision-MRD-v1.1.docx ford-provision-mrd-diagrams.vsdx ivi-provision-baidu-cloud-analysis-rev01.pptx | N/A | Cui, Rebecca (H.) <hcui2@ford.com> | N/A |  | Liu, Chenxi <Chenxi.Liu@desay-svautomotive.com> | [24 empty] | close |  |  | 2019-12-27 | 2020-01-06 | 2020-01-03 | 2020-03-02 | N.A | 12/30/2019: Ford FO replied. 1/6/2020: Desay provide OIL 1/10/2020: on-going 1/13/2020: Desay push FO 2/12/2020: plan to close before 2/21 3/2/2020: sign off |  | x | FNV2 | EOL |  | x | Peripheral Module Provisioning | CVPP |  |  |  |  | R00 | R00 | DCV2 | R05 | bar: Y to Y
164 | Connectivity | CVPP | Authorization车机授权 |  | 90% | 10% |  | Desay |  | x | x | always enable | 2019-12-25 | 【U554&702&725&542&727】车机授权_ID164_V1.1_20200323 | 【U554&702&725&542&727】车机授权_ID164_V1.1_20200323 |  |  |  | PRD DUEROS_CVPP_Authorization_PRD v1.0 | 福特phase1车机端服务授权功能MRD.docx |  | Gu, Xiaosheng (X.) <xgu14@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | Liu, Yi NJ_Vision <Yi.Liu@desay-svautomotive.com> | [24 empty] | close |  |  | 2019-12-25 | 2020-02-13 | 2020-01-01 | 2020-03-02 | N.A | 12/25/2019: replan 12/27/2019: delay to today 1/6/2020: replan today 1/10/2020: C/O phase 2, no change. 1/13/2020: postone to 1/14 2/17/2020: FO changed, plan to close within this week. 3/2/2020: sign off based on Stone's mail |  |  | CVPP | message center |  | x | setting | CVPP |  |  |  |  | DCV2 | DCV3 | DCV2 | DCV3 | bar: Y to Y
165 | Connectivity | CVPP | In-vehicle notification | y | 100% | 0% | NA | Desay |  |  | x | always enable | 2020-02-03 | 【林肯U554】ID_65&165_CCS_V2.1_20200430.pdf | 【福特727】CCS_ID65&165_V1.3_20200430 |  |  |  |  | Customer Connectivity Settings Client APIM SPSS v1.4 imp Guide v1.2_20200214.xlsx | Ford HMI_Invehicle and T&C_Interaction Spec_DRAFT.pdf | Ge, Haiqing (H.) <hge5@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2020-02-24 | 2020-02-26 | 2020-02-28 | 2020-02-28 | N.A | 2/6/2020: pending due to Ford FO 2/11/2020: review discussion this week 2/19/2020: R&R clear 2/20/2020: combine to CCS MRD, update CCS MRD. Ford FO prepare PRD |  |  | CVPP | message center |  | x | Vehicle information | CVPP |  |  |  |  | DCV1 | DCV3 | DCV2 | DCV3
166 | Connectivity | CVPP | T&C and Privacy Policy in HMI [Hold On] | Y | 5% | 15% | 80% | Ford CVPP |  |  | x |  | 2020-02-03 | 【林肯U554】ID_65&165_CCS_V2.1_20200430.pdf | [6 empty] | Ford HMI_Invehicle and T&C_Interaction Spec_DRAFT.pdf | Gu, Regina<QGU12@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> |  |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | ED&T | Y |  | cancel |  |  | hold-on | hold-on | hold-on | hold-on | F | 2/3/2020: wait feedback from FO 2/6/2020: pending due to Ford FO 2/7/2020: who development not decided? Ford solution not decided. This feature can be hold-on based on current status. 2020/9/2: remove this feature based on FO's mail |  |  | CVPP | message center |  | x | 其他 | CVPP
167 | Connectivity | CVPP | Take-away/美团MeiTuan | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-02-03 | UE c/o from phase2, UI only | UE c/o from phase2, UI only |  |  |  | MRD | 【福特Phase4】MRD_外卖_福特车型_V1.0_20191219 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 段家仪 v_duanjiayi@baidu.com |  | Follow Baidu | [23 empty] | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-02-14 | N.A | 2/7/2020: Ford FO check 2/12/2020: plan to sign off 2/14/2020: sign off |  |  | CVPP | APP |  | x | 服务生态 | CVPP |  |  |  |  | DCV0 | DCV3 | DCV2 | DCV3 | bar: Y to Y
168 | Connectivity | CVPP | Connected Embeded Navigation | Y | 0% | 100% |  | Baidu |  |  | x |  | 2020-02-03 | no UE delivered Baidu: combined into map by Baidu internal review | no UE delivered Baidu: combined into map by Baidu internal review |  |  |  | PRD DUEROS_CVPP_Connected Embedded Navigation_PRD v1.0 | 【MRD】send to car &car to phone |  | Shi, Stella (J.) <jshi32@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 原翼 yuanyi13@baidu.com | [25 empty] | close |  |  | 2020-02-11 | 2020-02-11 | 2020-02-18 | 2020-02-19 | B | 2/7/2020: can not reach FO 2/10/2020: replan 2/11/2020: plan to C/O from phase2; MRD mailed to FO |  |  | CVPP | APP |  | x | 地图 | CVPP |  |  |  |  | R00 | R00 | DCV2 | DCV3 | bar: Y to Y
169 | Connectivity | CVPP | Real Name Register |  | 0% | 100% | No related to IVI | Baidu |  |  | x |  | 2020-02-03 | [5 empty] | Draft |  |  | Wang, Yuran (Y.) <ywang422@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | 需要百度增加RNR需求 | [23 empty] | cancel | [7 empty] | 2/3/2020: aligned as not needed. | bar: Y to Y
170 | Connectivity | CVPP | Customer Feedback | Y | 30% | 70% |  | Baidu |  |  | x |  | 2020-02-03 | c/o UE, UI only | c/o UE, UI only |  |  |  | PRD 福特意见反馈MRD 1129.pdf | 【福特Phase4】意见反馈_MRD_2020_01_07 |  | Wang, Johnny (J.) <jwang308@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 苏静 v_sujing01@baidu.com | [25 empty] | close |  |  | 2020-01-10 | 2020-01-10 | 2020-01-17 | 2020-01-19 | N.A | 12/30/2019: replan 1/13/2020: MRD available 1/19/2020: sign off |  |  | CVPP | APP |  | x | 意见反馈 | CVPP |  |  |  |  | DCV4 | DCV4 | DCV2 | DCV3 | bar: Y to Y
171 | Connectivity | CVPP | Ford Finance / Lincoln Finance | Y | 0% | 20% | 80% | Ford CVPP/Baidu |  |  | x |  | 2020-02-03 | c/o phase 1/2/3, no UE | c/o phase 1/2/3, no UE |  |  |  | PRD DUEROS_CVPP_Ford_Finance_PRD_v1.1 | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | [26 empty] | close |  |  | 2019-12-23 | 2019-12-24 | 2019-12-31 | 2020-01-19 | N.A | 12/30/2019: replan 1/2/2020: combine with feature 298. Ford develop ? Or baidu? 1/9/2020: plan to sign off 1/19/2020: sign off |  |  | CVPP | APP |  | x | 第三方集成应用 | CVPP |  |  |  |  | DCV0 | DCV3 | DCV2 | DCV3 | bar: Y to Y
172 | Connectivity | EESE | Shifted GPS [merge into location service, due to V2X cancelled] | Y | 30% | 70% | need confirmed with Baidu | Baidu |  |  |  |  | 2019-10-30 | [5 empty] | Location Service APIM SPSS v1.10 July 10, 2019 |  | N/A | Wu, Jianfei (J.) <jwu158@ford.com> | N/A |  |  | SPEC有更新，需要更新MRD | [23 empty] | cancel | low | [6 empty] | 百度法务评审中， 12/24给出回复 12/25/2019: need Ford FO feedback 12/27/2019: Baidu check, compared with Phase 1/2, V2X addd only. 1/2/2020: Baidu check 1/9/2020: Baidu - Lu minghao check 1/10/2020: need Ford FO to sign off 1/15/2020: feature on-hold. From baidu side, c/o phase 1/2, feature merged into location service. | bar: N
173 | Connectivity | EESE/IVI(Tony) | Consumer Behavior Data (IVI related)埋点 |  | 30% | 70% |  | Baidu |  |  | x |  |  | HMI involve, no UE | HMI involve, no UE | [6 empty] | Gu, Zhong Tian (Z.) <zgu10@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | 徐静怡 v_xujingyi@baidu.com | [25 empty] | on-going |  |  | hold-on | hold-on | hold-on | hold-on | F | 2/6/2020: supplier to provide plan date 2/11/2020: can not forzen before March. FO mail and impact discussion/FO change to be confirmed by Stone 2/19/2020: FO change to Gu zhongtian 2/24/2020: not impact UE/UI, R&R may change, meeting planned on Thursday 2/28/2020: can not forzen before end of Feb. not impact UE/UI. Start from May. 4/9/2020: hold on to end of Aug. |  |  | CVPP | carrier |  |  | 埋点 | extend | N |  |  |  | R05 |  | R05 | R05 | bar: Y to Y
174 | Connectivity | IVI(removed) | IVI Module Swap 换件 |  | 30% | 70% |  | Baidu |  | x | x |  | 2019-12-30 | [5 empty] | based on diagnostic spec + mail more spec? |  | N/A | Zhou, Hangxing (X.) <xzhou83@ford.com>/xwang65 | N/A | [26 empty] | cancel | [6 empty] | N.A | 1/2/2020: Baidu replan. 1/9/2020: MRD available, need Ford FO check 1/10/2020: MRD update and send out today 1/13/2020: mail to Emma 2/3/2020: FO mailed to Baidu 2/10/2020: replan 2/19/2020: 由于phase4 IVI无sim卡，不存在实名认证的迁移。百度需要关注在给用户更换完IVI之后新件的Provisioning激活和用户账号无感迁移到新件上这两个方面。 |  |  | Basic function | basic | bar: Y to Y; N
175 | Connectivity | CVPP | Home to Car [on hold] |  | 0% | 100% | No related to IVI | Baidu |  |  | x |  | 2020-02-03 | hold on - FO | hold on - FO |  |  |  | PRD DUEROS_CVPP_IOT(speaker to car)_PRD v1.0 |  | N/A | Lu, Chao (C.) <clu42@ford.com> Kan, Bing (B.) <BKAN@ford.com>-725 | N/A | 刘韧 v_liuren@baidu.com |  |  |  | Y | Y | Y | Y | Y-onhold | Y-onhold | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y-onhold |  |  |  | hold |  |  | 2020-02-07 | 2020-02-10 | 2020-02-14 | 2020-02-14 | N.A | 2/12/2020: MRD updated, Update on-going. 2/14/2020: plan to sign off; sign off 2020/9/2: remove based on mail from FO |  |  | CVPP | APP |  | x | 车家互联 | [5 empty] | ? | ? | ? | ?
176 | Connectivity | CVPP | Carrier Feed | Y | 0% |  | 100% | Ford CVPP |  |  | x |  |  | N/A | N/A | [5 empty] | N/A | Wang, Yuran<ywang422@ford.com> | N/A | [26 empty] | N.A |  |  | N.A | N.A | N.A | N.A | N.A | 1/9/2020: open 1/13/2020: no impact for Baidu, Emma check with FO 2/3/2020: aligned - Ford responsible; no MRD needed. No supplier's input needed. |  |  | CVPP | carrier |  | x |  | CVPP |  |  |  |  | R00 | DCV4 | R05 | R00 | bar: Y to Y
177 | 电池动力汽车相关/Electric Vehicle | CVPP | Battery SoC | y | 30% | 70% |  | Baidu |  | x | x | DE04 B3b7 | 2019-12-20 | N/A | 【福特CX727】_ID177&178&179&180&218_charge status&charge preference&departure &comfort_V2.6_20200512 |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | N | N | N | N | N | N | N | N | N | N | N | N | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2020-02-07 | 2020-02-14 | 2020-04-23 | N.A | 12/23/2019: MRD available today 12/24/2019: Delay to today. 12/25/2019: wait Ford FO 12/27/2019: pending by Ford FO - delay to 1/2 1/9/2020: Baidu push FO to check 1/13/2020: Baidu push today 2/6/2020: combine to item 178; pending due to Baidu 2/7/2020: MRD available. Review by Ford FO 2/8/2020: Baidu arrange meeting to review 3/22/2020: Battery SoC, Charge Status/Charge Time, Preferred Charge Time, Departure Time, Charge Conflict Notification Popups - one MRD cover 3/31/2020: MRD最新版本提交，福特FO在评审 4/10/2020: Baidu FO update MRD and send out review. replan to release on Apr. 15th. 4/23/2020: sign off | [6 empty] | xHEV | CVPP |  |  |  |  | protected | protected | DCV2.1 | DCV3
178 | 电池动力汽车相关/Electric Vehicle | CVPP | Charge Status/Charge Time | Y | 30% | 70% |  | Baidu |  |  | x | DE04 B3b7 | 2020-01-23 | N/A | 【福特CX727】_ID177&178&179&180&218_charge status&charge preference&departure &comfort_V2.6_20200512 |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | N | N | N | N | N | N | N | N | N | N | N | N | Y | ED&T | Y |  | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-04-23 | N.A | 2/7/2020: review by Ford FO 4/1/2020: combine to 177 | [5 empty] | x | xHEV | CVPP |  |  |  |  | protected | protected | DCV2.1 | DCV3
179 | 电池动力汽车相关/Electric Vehicle | CVPP | Preferred Charge Time | Y | 30% | 70% |  | Baidu |  |  | x | DE04 B3b7 | 2020-01-23 | N/A | 【福特CX727】_ID177&178&179&180&218_charge status&charge preference&departure &comfort_V2.6_20200512 |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | N | N | N | N | N | N | N | N | N | N | N | N | Y | ED&T | Y |  | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-04-23 | N.A | 2/7/2020: review by Ford FO 4/1/2020: combine to 177 | [5 empty] | x | xHEV | CVPP |  |  |  |  | protected | protected | DCV2.1 | DCV3
180 | 电池动力汽车相关/Electric Vehicle | CVPP | Departure Time | Y | 30% | 70% |  | Baidu |  |  | x | DE04 B3b7 | 2020-01-23 | N/A | 【福特CX727】_ID177&178&179&180&218_charge status&charge preference&departure &comfort_V2.6_20200512 |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | H72c_SYNC4_Electrification_RELEASED_v1_5_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | N | Y | N | Y | Y | Y | N | N | N | N | N | N | N | N | N | N | N | N | Y | License |  | 包含在地图里 | close |  |  | 2020-02-07 | 2020-02-07 | 2020-02-14 | 2020-04-23 | N.A | 2/6/2020: combine to 179 4/1/2020: combine to 177 | [5 empty] | x | xHEV | CVPP |  |  |  |  | protected | protected | DCV2.1 | DCV3
181 | 电池动力汽车相关/Electric Vehicle | CVPP | Charge Station Finder | Y | 10% | 90% |  | Baidu |  |  | x | DE04 B3b7 | 2020-01-23 | N/A | N/A |  |  |  | PRD xEV PRD_EVCS_B5_v1.3 (05-16-2018).docx |  | embedded in Nav behaviour. | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | 原翼 yuanyi13@baidu.com | liu yi <Yi.Liu@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-02-07 | 2020-04-10 | 2020-04-10 | 2020-04-23 | N.A | 2/6/2020: combine to 179 3/22/2020: separate MRD, 下周MRD更新，有额外的cost 4/8/2020: plan to sign off this week. 4/10/2020: POI data to be updated in next Monday, planned to be released before next Wednesday 4/23/2020: sign off | [5 empty] | x | 地图 | CVPP |  |  |  |  | protected | protected | DCV3 | DCV3 | bar: Y to Y
182 | 电池动力汽车相关/Electric Vehicle | CVPP | Trip Planner - BEV only |  | 10% | 90% |  | Baidu |  |  | x | DE04 B3b7 | 2020-01-23 | N/A | N/A |  |  |  | PRD EV Trip Planner APIM SPSS v1.0 Mar 15, 2019.pdf |  | embedded in Nav behaviour. | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | 原翼 yuanyi13@baidu.com | liu yi <Yi.Liu@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-03-01 | 2020-04-23 | 2020-05-08 | 2020-04-27 | N.A | 2/6/2020: supplier to provide plan date 2/7/2020: pending due to Ford FO 2/11/2020: Baidu Map can not support Ford's solution. Already escalated. 2/18/2020: Robert follow 2/25/2020: baidu check the changed request 3/22/2020: 高风险，可能会OTA 3/31/2020: on hold 4/10/2020: Baidu preparing MRD, plan to be released next week. 4/23/2020: MRD already available. 4/27/2020: Sign off | [5 empty] | x | xHEV | CVPP | [6 empty] | DCV3 | DCV3 | bar: Y to Y
183 | 电池动力汽车相关/Electric Vehicle | CVPP | Cloud Enhanced Distance to Empty - BEV only |  | 30% | 70% |  | Baidu |  | x | x | DE04 B6b3 | 2020-01-23 | N/A | N/A |  |  |  | PRD Cloud_Enhanced_DTE_FS_v1.1.pdf |  | N/A | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-02-14 | 2020-02-07 | 2020-02-14 | 2020-03-30 | N.A | 3/22/2020: plan to sign off on 3/20 3/30/2020: sign off |  | x |  |  |  | x | xHEV | CVPP | [6 empty] | DCV3 | DCV3 | bar: Y to Y
184 | 电池动力汽车相关/Electric Vehicle | CVPP | Smart Charging - BEV only [on hold] |  | 30% | 70% |  | Baidu |  | x | x | DE04 B3b7 | 2020-01-23 | N/A | N/A |  |  |  | Smart Charging PRD_v1.6.pdf |  | P72d_15P_PlugAndCharge_R_v2_00_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> |  |  | N | N | N | N | Y-onhold | Y-onhold | N | N | N | N | N | N | N | N | N | N | N | N | Y-onhold |  |  |  | holdon till J1 |  |  | hold-on | hold-on | hold-on | hold-on | F | 2/24/2020: OTA feature? 3/22/2020: pending, OTA apply 3/31/2020: pending, 运营商关联，后期OTA |  | x |  |  |  | x | xHEV | CVPP | [6 empty] | ? | ?
185 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Forrest) | frunk/前备箱 - BEV only |  | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-25 | N/A | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  | Frunk Softswitch Interface Client SPSS v1.1 June 21 2019 | 合并到NO11 | P31b_15P_SYNC4_Controls_R_v4_00_MY21 | chen, Emma<jchen276@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [24 empty] | close |  |  | 2019-12-25 | 2020-01-06 | 2020-01-01 | 2020-01-11 | N.A | 12/25/2019: replan 12/27/2019: delay to today 1/6/2020: plan to sign off 1/9/2020: HMI open, desay organize open item list 1/10/2020: plan to sign off 1/11/2020: sign off |  |  |  |  | x |  | soft switch | core | Y | [5 empty] | DCV2 | R06 | bar: Y to Y
186 | 电池动力汽车相关/Electric Vehicle | CVPP | Rocket setup |  | 30% | 70% |  | Baidu |  | x | x | DE04 B3b7 (No Rocket setup config bit) | 2020-01-06 | U554 帐号 ID101 ID186 V1.5 20200426 |  |  |  |  | Spec draft available Dec. 19th |  | TBD | Gu, Xiaosheng (X.) <xgu14@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | 苏争 _suzheng01@baidu.com | [25 empty] | close |  |  | 2020-01-10 | 2020-01-10 | 2020-01-17 | 2020-04-03 | N.A | 12/30/2019: requirment updated, baidu check 1/9/2020: draft MRD by Baidu 1/10 1/10/2020: provide draft MRD by 1/13, on-site review on 1/15 2/3/2020: pending by Ford FO 2/6/2020: pending due to Ford FO 2/8/2020: Baidu arrange meeting to review 2/14/2020: requirement clear, open item related to account. plan to sign off 2/27/2020: re-open 2/28/2020: organize open point 3/22/2020: 后台评审，27号释放不影响开发 3/31/2020: 昨天评审结束，可以sign off； 百度内部在评估，今天给出结论。 | [5 empty] | x | 账号 | CVPP |  |  |  |  | R04 |  | R04 | R05 | bar: Y to Y
187 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Forrest) | Charge Port Light Settings |  | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-25 | N/A | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  | Vehicle Settings APIM SPSS v1.19 Oct 30, 2019 Vehicle Settings APIM Imp Guide v1.19 Oct 30, 2019 Vehicle Settings Logical to Physical CAN signal mapping Oct 30, 2019 | 不需要输出MRD | P31b_15P_SYNC4_Controls_R_v4_00_MY21 | Wang, Fin (X.Y.) (xwang65@ford.com) | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> | [24 empty] | close |  |  | 2019-12-25 | 2020-01-06 | 2020-01-01 | 2020-01-11 | N.A | 12/25/2019: replan 12/27/2019: delay to today 1/6/2020: OIL in GitHub today, Ford FO check 1/10/2020: mail to Ford FO by desay 1/11/2020: sign off | HMI open | [5 empty] | setting | basic | Y |  |  |  | DCV2 | DCV3 | DCV2 | DCV3 | bar: Y to Y
188 | VPA | CVPP | Virtual Personal Assistant |  | 0% | 30% | 70% | Baidu/Ford EESE |  |  | x |  | 2020-01-23 | pending - outsourcing (FO) | pending - outsourcing (FO) |  |  |  | PRD VPA PRD - V1.3.2.pdf |  | TBD | Sophia Suo <FSUO@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | 刘韧 v_liuren@baidu.com | [25 empty] | close |  |  | 2020-02-21 | 2020-03-02 | 2020-02-28 | 2020-03-02 | N.A | 2/6/2020: supplier to provide plan date 2/7/2020: adjust R&R. resource issue to be checked by in-house team. 2/11/2020: phase 3 lead 2/11/2020: Need detail plan info; Phase 3 solution not frozen, phase 4 scope not started. 2/12/2020: changes compared with Phase 3: 语音交互能力方面，会复用百度在Phase4所支持的语音交互功能，相对Phase3会有优化和新增 • 语音开放性需求增加 – 待百度对Phase4的语音接口开放性评估 • HMI设计更新，加入新的形象设计 – 福特自己Inhouse design 2/25/2020: Baidu interfaces C/O from phase3. 3/2/2020: FO sign off |  |  | vehicle related | VPA |  | x | 语音 | CVPP |  |  |  |  | R05 | R05 | R06 | R05.01 | bar: Y to Y
189 | Prognostics | CVPP | Prognostics |  | 60% |  | 40% | Ford CVPP/Desay |  |  | x | yes |  | 【林肯U554】车辆状态_ID98&161&189__V1.5-20200324 | 【福特727】车辆状况_ID98&161&189_V1.5_20200428 |  |  |  | PRD | 合并到NO161 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> | [24 empty] | close |  | 2020-01-14 | 2020-01-14 | 2020-02-28 | 2020-01-21 | 2020-02-28 | N.A | 2/6/2020: supplier to provide plan date 2/8/2020: CVPP lead 2/25/2020: combine to feature 161. |  |  | Basic function | EOL | x | x | prognostics | CVPP |  |  |  |  | DCV2 | DCV3 | bar: Y to Y
190 | Others | EESE/IVI(Forrest) | English HMI(bezel diagnostic, etc.) |  | 10% | 90% |  | Desay |  |  | x | always enable | 2020-01-23 | N/A | N/A |  |  |  |  | 合并到NO110 |  | Wang, Fin (X.Y.) <xwang65@ford.com> | N/A |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | 参考bezel diagnostic SPEC以及项目的实际需求 | [23 empty] | close |  |  | 2020-02-19 | 2020-02-21 | 2020-02-24 | 2020-02-21 | N.A | 2/6/2020: supplier to provide plan date 2/21/2020: requirement covered in feature 110. |  |  | HMI | HMI | x |  | HMI | basic | N |  |  |  | DCV1 | DCV3 | DCV2 | DCV3 | bar: Y to Y; N
191 | Basic features | EESE/IVI(Jack) | HMI for wireless charging module |  | 10% | 90% |  | Baidu |  |  | x |  |  | c/o UE, UI only | c/o UE, UI only |  |  |  |  | 【Phase4】HMI for wireless charging...20.docx |  | Lyu, Qingtao (Q.) <qlyu@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | [26 empty] | close |  |  | 2020-02-27 | 2020-02-20 | 2020-02-28 | 2020-02-27 | N.A | 2/20/2020: MRD send to FO 2/27/2020: C/O, sign off |  |  | vehicle related | Wireless charge |  |  | 其他 | extend | Y |  |  |  | DCV3 | DCV3 | DCV2 | DCV3 | bar: Y to Y; N
192 | Passenger Feature for 27 | HMI | 27" only: Vehicle status showing in the passenger area |  | 40% | 60% |  | Baidu |  |  | x |  | 2020-01-23 | [8 empty] | Liu, Luisa (Fan.) <fliu43@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | [26 empty] | cancel | [7 empty] | 1/9/2020: HMI study, 2020/1/15 2/6/2020: sign off 2/10/2020: requirement found not aligned 2/11/2020: HMI study on-going. 2/18/2020: combine to 161 | bar: Y to Y; N
193 | Connectivity | CVPP | Demo mode for dealers/经销商演示模式 |  | 10% | 90% |  | Baidu |  |  | x | [10 empty] | Wang, Johnny (J.) <jwang308@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | [26 empty] | cancel |  |  | 2020-02-27 | 2020-02-27 | 2020-03-05 |  | F | 2/25/2020: pending feedback from Ford Fo 2/28/2020: solution not ready |  |  | CVPP | APP |  |  | 账号 | bar: Y to Y
194 | Connectivity | CVPP | Message notification pushing API for Ford backend/福特后台消息推送接口 |  | 10% | 90% |  | Baidu |  |  | x |  |  | N/A | N/A |  |  |  |  | 百度消息推送相关接口 V1.1-2020.2.12 |  | Wang, Johnny (J.) <jwang308@ford.com> | N/A | 苏争 _suzheng01@baidu.com | [25 empty] | close |  |  | 2020-02-14 | 2020-02-14 | 2020-02-21 | 2020-02-14 | B | 2/13/2020: update after discussion 2/14/2020: combine to 148, plan to sign off 2/14/2020: sign off |  |  | CVPP | data |  |  | 消息推送 | CVPP |  |  |  |  | DCV0 | DCV3 | DCV2 | DCV3 | bar: Y to Y
195 | cross carline | HMI | 快速切换最近使用的APP |  | 100% | 0% |  | Desay |  |  | x | always enable |  | 【林肯U554】Launcher&system UI_ID69&195&144&146_V1.9_20200414 | 【福特XC727】Launcher&SystemUI_ID69&195_V2.5_20200416 |  |  |  |  | Ford_MRD_27寸大屏SystemUI_20200116final.docx | HMI requirements clarified in email/meetings. | Xiao, Yun (Y.) <yxiao21@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-02-27 | 2019-12-27 | 2019-12-30 | 2020-03-25 | N.A | combine to item 68 1/10/2020: plan to sign off 1/17/2020: sign off for desay 2/27/2020: reOpen 3/25/2020: sign off |  |  | HMI | HMI | x |  | HMI | extend | N |  |  |  | DCV1 | DCV1 | DCV2 | DCV3 | bar: Y to Y; N
196 | cross carline | HMI | Animation [Background, others] |  | 10% | 90% |  | Baidu |  |  | x |  |  | N/A | N/A |  |  |  |  | 无MRD | N/A | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> | N/A | UI | [25 empty] | close |  |  | 2020-02-27 | 2020-02-26 | 2020-03-05 | 2020-04-23 | N.A | 2/20/2020: Baidu follow actions based on meeting discussion 4/23/2020: all animiation requirements concurred by digital studio and Suppliers |  |  | HMI | HMI |  |  | 动效 | extend | N |  |  |  | DCV4 | ? | DCV2 | DCV3 | bar: Y to Y
197 | cross carline | HMI | Shortcut Keys (program specific) |  | 70% | 30% |  | Desay |  | x | x | yes - missed? | 2019-12-25 | 【林肯U554】实体键 _ID197&219_V1.5 _20200408 | 【福特 727】实体键_ID197&219_V1.5_20200423 |  |  |  | H36p_SYNC4_Parking_Shortcut_Key_RELEASED_v0_06_P702_Post J1_MY21 H36o_SYNC4_Drive_Assist_Shortcut_Key_R_0_04_MY21 H36n_SYNC4_Camera_Shortcut_Key_R_0_02_MY21 | Ford_MRD_Shortcut_Key.docx | A65c_SYNC4_Hard_Switch_Behavior_RELEASED_v1_10_MY21 | Xiao, Yun (Y.) <yxiao21@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Xie, Jun NJ_RN1 <Jun.Xie2@desay-svautomotive.com> | [24 empty] | close |  |  | 2019-12-25 | 2020-01-13 | 2020-01-01 | 2020-02-28 | D | 12/30/2019: no MRD/replan info 1/6/2020: replan today 1/10/2020: MRD on-going 1/13/2020: MRD to be updated 2/24/2020: meeting planned on this Tuesday |  |  | HMI | HMI |  |  | HMI | core | N |  |  |  | DCV1 | R00 | DCV2 | DCV3 | bar: Y to Y; N
198 | cross carline | HMI | Launcher | Y |  |  |  | Baidu | x -partly | x | x |  |  | 【福特 P702&U725】ID_198&105&171_Launcher_V1.4_20200315 | 【福特XC727】Launcher&SystemUI_ID69&195_V2.5_20200416 |  |  |  | U554, 725, 702 HMI adaption from Phase 2. | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 | HMI requirements clarified in email/meetings. Status icon shall folow below specs, Header bar HMI requirement _ Ford CHN _ DRAFT HMI Interaction Spec_Header_Bar_20.02.2020 for header bar logic&flow | N.A | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> |  | C/O 5,6,7 | [23 empty] | close |  |  | 2019-12-23 | 2019-12-24 | 2019-12-31 | 2020-01-19 | N.A | 12/24/2019: MRD available. Need Ford FO check 1/2/2020: list open item and mail for notification. 1/8/2020: plan to sign off 1/19/2020: sign off | 天气数据区域新增点：根据当日天气情况，对应增加显示依据天气情况的人性化温馨提示语，功能研发侧基本能实现，但当前属于福特open项： A、天气数据获取来源，以及温度/天气种类的显示取舍等，需福特内部尽快给于针对phase 4车型予以确认 |  | HMI | HMI | x | x | Launcher | core | Y |  |  |  | DCV4 | DCV4 | DCV2 | R00 | bar: Y to Y
199 | Connectivity | CVPP | 免密支付 payment without enterring password | Y |  |  |  | Baidu |  |  | x |  |  | 【林肯U554】_ID199_免密支付_V1.0_20200404 | 【福特CX727】_ID199_免密支付_V1.0_20200404 |  |  |  |  | 【phase4】MRD_免密支付_福特/林肯_V1.0_2019_12_23 |  | Lu, Chao (C.) <clu42@ford.com> | Wang, Wei Hua (Lisa.) (wwang96@ford.com) | panchengdong <v_panchengdong@baidu.com> | [25 empty] | close |  |  | 2020-02-07 | 2020-02-10 | 2020-02-14 | 2020-02-19 | B |  |  |  | CVPP | APP |  | x | 支付 | CVPP |  |  |  |  | DCV3 | DCV3 | DCV2 | DCV3 | bar: Y to Y
200 | Connectivity | CVPP | 违章查询 Query traffic violations | Y |  |  |  | Baidu |  |  | x |  |  | 【福特U554&P702&U725&542低配】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316.pdf 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.002 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.001 | 【福特U554&P702&U725&542低配】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316.pdf 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.002 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.001 |  |  |  |  | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Lu, Chao (C.) <clu42@ford.com> Xie, Jie (J.) <JXIE49@ford.com> - 725 | Pan, Jingjing (J.) <jpan35@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> | [25 empty] | close |  |  | 2020-02-04 | 2020-02-04 | 2020-02-11 | 2020-02-06 | N.A | 2/6/2020: sign off |  |  | CVPP | APP |  | x | 语义垂类 | CVPP |  |  |  |  | DCV0 | DCV0 | DCV2 | DCV3 | bar: Y to Y
201 | Connectivity | CVPP | 鲜花预订 flowers ordering | Y |  |  |  | Baidu |  |  | x |  |  | c/o 167 UE, UI only | c/o 167 UE, UI only |  |  |  |  | 【福特Phase4】MRD_外卖_福特车型_V1.0_20191219 |  | Lu, Chao (C.) <clu42@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | shantong <v_shantong@baidu.com> | [25 empty] | close |  |  | 2020-02-04 | 2020-02-04 | 2020-02-11 | 2020-02-06 | N.A | 2/6/2020: sign off, C/O from phase 3 |  |  | CVPP | APP |  | x | 语义垂类 | CVPP |  |  |  |  | DCV0 | DCV0 | DCV2 | DCV3 | bar: Y to Y
202 | Connectivity | CVPP | 机票查询 airplain tickets query | Y |  |  |  | Baidu |  |  | x |  |  | 【福特U554&P702&U725&542低配】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316.pdf 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.002 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.001 | 【福特CX727】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316 |  |  |  |  | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> | [25 empty] | close |  |  | N.A | N.A | 2019-11-20 | 2019-12-02 | N.A | 1/2/2020: combine to feature 90; 高频语音垂类 + 简单HMI入口。 |  |  | CVPP | APP |  | x | 语义垂类 | CVPP |  |  |  |  | DCV0 | DCV0 | DCV2 | DCV3 | bar: Y to Y
203 | Connectivity | CVPP | 火车票查询 train ticket query | Y |  |  |  | Baidu |  |  | x |  |  | 【福特U554&P702&U725&542低配】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316.pdf 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.002 【福特P702&U725】语音语义垂直类_ID126、127、202、203_V1.11_20200213.zip.001 | 【福特CX727】语音语义垂直类_图片搜索_ID126、127、202、203_V1.10_20200316 |  |  |  |  | 【附表】语音各垂类指令集-phase3&phase4 v1.1-20200123 |  | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | hanyuzhe <v_hanyuzhe@baidu.com> | [25 empty] | close |  |  | N.A | N.A | 2019-11-20 | 2019-12-02 | N.A | 1/2/2020: combine to feature 90; 高频语音垂类 + 简单HMI入口。 |  |  | CVPP | APP |  | x | 语义垂类 | CVPP |  |  |  |  | DCV0 | DCV0 | DCV2 | DCV3 | bar: Y to Y
204 | Connectivity | CVPP | 关于（声明）desclaimer [including, account and login in] [ 215 included: desclaimer setting] | Y | 30% | 70% |  | Baidu |  |  | x |  |  | c/o UE, only UI desay check whether OK for development | c/o UE, only UI desay check whether OK for development | [5 empty] | N/A | chen, Emma <jchen276@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | [26 empty] | close |  |  | 2020-02-25 | 2020-02-26 | 2020-02-28 | 2020-02-28 | N.A | 12/30/2019: replan 1/8/2020: Emma check with CVPP 1/9/2020: contact HMI 2/3/2020: open again 2/6/2020: pending due to FO not clear 2/11/2020: list all the functions which need IVI to provide desclaimer info within this week. 2/24/2020: arrange meeting on Thursday 3/3/2020: 已确定功能上目前维持内容不变，等内容最后冻结后一次更新；基于目前U554MCA项目的开发计划，最终版本计划2021/1 之前提供内容 |  |  | CVPP | account |  | x | 免责声明 | CVPP |  |  |  |  | DCV0 | DCV0 | DCV2 | DCV3 | bar: Y to Y
205 | cross carline | HMI | Calm Screen | Y | 30% | 70% |  | Baidu |  | x |  |  |  | 【林肯U554】ID205_CalmScreen_V1.2_20200226 | 【福特CX727】ID205_CalmScreen_V1.3_20200227 |  |  |  | Lisa working | 【ID205】【phase 4 福特CD542&U625ICA横屏】calm screen MRD v1.4-20200107；【ID205】【phase 4 福特CX727竖屏】calm screen MRD v1.3-20200102；【ID205】【phase 4 福特U725&P702横屏】calm screen MRD v1.3-20200102；【ID205】【phase 4 林肯U554横屏】calm screen MRD v1.3-20200102 | HMI requirements clarified in email/meetings. | N.A | Xiao, Yun (Y.) <yxiao21@ford.com> | [26 empty] | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-19 | N.A | 12/24/2019: wait for Ford FO mail confirm 12/30/2019: check on-going 1/8/2020: plan to sign off 1/19/2020: sign off |  |  | HMI | HMI | x |  | setting | extend | Y |  |  |  | DCV0 | DCV0 | DCV2 | DCV3 | bar: Y to Y
206 | cross carline | HMI | Display off | Y | 30% | 70% |  | Baidu |  | x |  |  |  | c/o UE, UI only | c/o UE, UI only |  |  |  | lisa checking | 【ID206】【Phase2 林肯(U554)】DisplayOff需求文档MRD_2020_01_02；【ID206】【Phase4 福特（CD542&U625ICA）（高配）】DisplayOff需求文档MRD_2020_01_06；【ID206】【Phase4 福特（CD542&U625ICA）低配】DisplayOff需求文档MRD_2020_01_02；【ID206】【Phase4 福特（CX727）】DisplayOff需求文档MRD_2020_01_02；【ID206】【Phase4 福特（U725&P702）】DisplayOff需求文档MRD_2020_01_02 | HMI requirements clarified in email/meetings. | N.A | Xiao, Yun (Y.) <yxiao21@ford.com> | [26 empty] | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-19 | N.A | 12/24/2019: wait for Ford FO mail confirm 12/30/2019: check on-going 1/13/2020: plan to sign off 1/19/2020: sign off |  |  | HMI | HMI | x |  | setting | basic | Y |  |  |  | DCV0 | DCV0 | bar: Y to Y
207 | Connectivity | CVPP | 在线商城 online mall | Y |  | 20% | 80% | Ford CVPP/Baidu |  |  | x | EOL? | [7 empty] | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 |  | Gu, Xiaosheng (X.) <xgu14@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> | [26 empty] | cancel |  |  | 2020-02-17 | 2020-02-17 | 2020-02-19 | 2020-02-19 | N.A | 12/24/2019: combine to item 198 1/2/2020: same with ford finance? 1/9/2020: not same. FO not clear 1/13/2020: Baidu check 1/19/2020: sign off 2/6/2020: reopen - pending by CVPP plan 2/11/2020: planned to be clarified within this week. 2/17/2020: Baidu scope clear. The content of this feature will be prepared by Ford 4/28/2020: cancle based on management's decision | in-house team develop? |  | CVPP | APP |  |  | 第三方集成应用 | bar: Y to Y
208 | Connectivity | CVPP | Tik tok 抖音 | Y |  |  |  | Baidu |  | x |  |  |  | 【福特 P702&U725】ID_198&105&171_Launcher_V1.4_20200315 | 【福特XC727】Launcher&SystemUI_ID69&195_V2.5_20200416 |  |  |  | DUEROS_CVPP_抖音_v1.3_20191203 | 【Phase4】CD542低配_Launcher_MRD 2020_02_06；【Phase4】CX727__Launcher_MRD 2019_01_02；【Phase4】P702&U725_Launcher_MRD 2020_01_06；【Phase4】U554__Launcher_MRD 2020_01_03；【终版】【福特Phase4】MRD_27寸主副驾屏Launcher_CD542高配&U625ICA_V1.5_2019_01_20 | N/A | Shi, Stella (J.) <jshi32@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> | zhushiyun <v_zhushiyun01@baidu.com> | [25 empty] | cancel |  |  | 2019-12-23 | 2019-12-24 | 2019-12-30 | 2020-01-19 | N.A | 12/24/2019: combine to item 198 12/30/2019: check on-going 1/2/2020: archive file and send mail 1/19/2020: sign off | 7/13/2020: Tik tok cancelled based on program's mail |  | CVPP | APP |  | x | 第三方集成应用 | bar: Y to Y
209 | Basic features | IVI(removed) | In-vehicle notification - a pop up notice when ignition to notify customer about data sharing policy - duplicate with 165 | Y |  |  |  | Baidu |  | x | [12 empty] | N/A | jiangting <v_jiangting@baidu.com> | [25 empty] | cancel | [7 empty] | duplicate with 165 | bar: Y to Y
210 | Connectivity | CVPP | Carrier Backend Development 运营商后台开发 | Y |  |  |  | Baidu | [14 empty] | N/A | zhaoweilong <v_zhaoweilong01@baidu.com> | [25 empty] | cancel | [7 empty] | cancelled due to request by FO | bar: Y to Y
211 | Basic features | CVPP | Carrier API integration with Baidu 与百度的接口集成- Carrier Backend Development 运营商后台开发 | Y |  |  | 100% | Ford CVPP |  | x |  |  |  | N/A | N/A | [6 empty] | Wang, Yuran<ywang422@ford.com> | N/A | huangqiuyue <huangqiuyue@baidu.com> | [25 empty] | N.A |  |  | N.A | N.A | N.A | N.A | N.A | 12/24/2019: send mail to supplier for the impact 12/25/2019: need impact analysis report from Baidu 12/27/2019: Baidu check 12/30/2019: 百度需要1/15号之前定点并确认需求，安排会议讨论 1/9/2020: Baidu send mail to Emma. 1/10/2020: Baidu mail back to Emma 1/13/2020: feedback from Baidu 2/3/2020: MRD available, pending by Ford FO's reveiw 2/6/2020: Ford FO在Phase 4只保留流量预警推送和收到推送后的跳转功能，目前的流量查询和订购由嵌入车机的运营商H5完成，因为从双卡回归到单卡，所以SIM卡换件也不需要百度完成。最终的需求文档，还是得等运营商定点后才能给出。 |  |  | CVPP | carrier |  | x |  | CVPP |  |  |  |  | R00 | R00 | R05 | R04 | bar: Y to Y
212 | Basic features | CVPP | Carrier API integration with FORD 与福特的接口集成 -> VIN Trim Data | Y |  | 60% | 40% | Ford CVPP/Baidu |  | x | [8 empty] | CVPP check whether needed |  |  | Wang, Yuran<ywang422@ford.com> | N/A | [26 empty] | cancel | [7 empty] | 2/7/2020: Baidu need to provide corresponding request to Ford FO 3/6/2020： no trim data needed |  |  | CVPP | APP | bar: Y to Y
213 | Basic features | IVI(removed) | Speed compensated volume 根据车速调整音量 | Y |  |  |  | Desay |  | x | [8 empty] | Audio Settings APIM SPSS v1.4 Nov 6, 2019 Audio Settings APIM Imp Guide v1.4 Nov 6, 2019 | [30 empty] | cancel |  |  |  |  | 1900-01-06 |  |  | duplicate with 157 | bar: Y to Y
214 | Vehicle Features/Interfaces | DAT | Rear Camera on demand | Y | 90% | 10% |  | Desay |  | x |  | yes - missed? |  | 【林肯U554交互】倒车影像&CTA&RBA_ID36&37&39&40&41&42&214_V1.4_20200324 【林肯U554交互】车影像CTA-RBA_ID36&37&39&40&41&42&214_V1.4_20200318 | 【福特727】RVC倒车影像_ID36&37&41&42&214_V1.9_20200430 |  |  |  | Rear Camera On Demand APIM SPSS v1.1 June 21, 2019 Rear Camera On Demand APIM Imp Guide v1.1 June 21, 2019 | Ford_MRD_RVC_RCOD_MultiCamera_CTA_RBA_APA_Radar.docx | H36k_SYNC4_Camera_Systems_R_v0_20_MY21 | Chen Xuan <XCHEN161@ford.com>/Wang, Tom (X.) <xwang190@ford.com>/Zheng, Tina (T.) <tzheng4@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> |  | Li Xiaojie（Xiaojie.Li@desay-svautomotive.com） |  |  | N | N | N | N | N | N | Y | N | N | N | N | N | N | N | Y | N | N | N | N | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-23 | 2019-12-30 | 2020-01-19 | N.A | 12/30/2019: mail discussion available, while no arhived Open item list. 1/6/2020: Desay mail to FO 1/10/2020: on-stie review 1/13/2020: plan to sign off, open item - HMI involve 1/19/2020: sign off | HMI open |  | Driver assist | Driver assist HMI |  |  | Camera | basic | TBD
215 | Basic features | IVI(removed) | desclaimer settings | Y |  |  |  | Desay |  | x | [8 empty] | input from HMI; to be confirmed by HMI |  |  |  | Wang, Wei Hua (Lisa.) (wwang96@ford.com) |  | Pan Juan（Juan.Pan@desay-svautomotive.com） | [24 empty] | cancel | [6 empty] | N.A | Emma mail Julee - done /wainting feedback from Julee 1/2/2020: feedback confirmed with HMI, FIP updated. 1/6/2020: Desay contact FO and replan 1/13/2020: replan 2/6/2020: FO not clear; combine to 204 |  |  | basic function | basic | bar: Y to Y
216 | Basic features | EESE/IVI(Forrest) | EQ tool | Y |  |  |  | Desay |  |  | x | n.a |  | N/A | N/A | [6 empty] | N.A | N/A |  | Zhang Li (Li.Zhang3@desay-svautomotive.com) | [24 empty] | N.A |  |  | N.A | N.A | N.A | N.A | D | 2/6/2020: supplier to provide plan date 2/11/2020: Tool, no MRD |  |  | Chime management | Chime management |  |  | audio | core | N |  |  |  | DCV3 | ? | DCV2 | DCV3 | bar: Y to Y
217 | Basic features | EESE/IVI(Roger) | Rear Audio Controls | Y | 90% | 10% |  | Desay |  | x |  | yes |  | 【林肯U554】实体键 _ID197&219_V1.5 _20200408.pdf | 【福特 727】实体键_ID197&219_V1.5_20200423 |  |  |  | Rear Audio Control APIM SPSS v1.4 Jul 1, 2017 Rear Audio Control APIM Imp Guide v1.4 Jul 1, 2017 | 不需要输出MRD |  | Li Xuedong XLI244@ford.com | N/A |  | Yu Hualin（Hualin.Yu@desay-svautomotive.com） | [24 empty] | close |  |  | 2019-12-27 | 2019-12-27 | 2020-01-03 | 2020-01-14 | N.A | 12/24/2019: desay check and feedback today. 12/25/2019: send OIL to Ford FO 1/6/2020: plan to sign off 1/13/2020: ma mei mail to sign off 1/14/2020: sign off |  |  | Chime management | Chime management |  |  | audio | basic | TBD | bar: Y to Y
218 | 电池动力汽车相关/Electric Vehicle | CVPP | Charge Conflict Notification Popups | Y |  | 100% |  | Baidu |  |  | x |  |  | N/A | 【福特CX727】_ID177&178&179&180&218_charge status&charge preference&departure &comfort_V2.6_20200512 | [6 empty] | Yang, Yu (Y.) <yyang158@ford.com> | Pan, Jingjing (J.) <jpan35@ford.com> | [26 empty] | close |  |  | 2020-02-14 | 2020-02-25 | 2020-02-28 | 2020-04-23 | B | 2/6/2020: supplier to provide plan date 2/18/2020: C/O feature, plan to transfer to Baidu 2/19/2020: R&R clear 4/1/2020: combine to 177 | [6 empty] | EV | CVPP |  |  |  |  | protected | protected | DCV2.1 | DCV3 | bar: Y to Y
219 | Features of IVI or Connect | EESE/IVI(Forrest) | IVI interface via press physical switch 实体键IVI交互 | Y | 100% |  |  | Desay |  | x |  | yes - missed? |  | 【林肯U554】实体键 _ID197&219_V1.5 _20200408 | 【福特 727】实体键_ID197&219_V1.5_20200423 | [5 empty] | A65c_SYNC4_Hard_Switch_Behavior_RELEASED_v1_10_MY21 | Chen, Emma<jchen276@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | Wang Dong <Dong.Wang@desay-svautomotive.com> | [24 empty] | close |  |  | 2019-12-26 | 2020-03-22 | 2020-01-02 | 2020-04-03 | N.A | 12/30/2019: no MRD/replan info 1/6/2020: replan today 1/10/2020: MRD on-going 1/13/2020: Desay push FO 2/24/2020: meeting planned on this Tuesday 3/22/2020: 2 rounds of update, some open items left. |  |  | Basic function | basic | x |  | HMI | core | Y |  |  |  | DCV1 | DCV3 | DCV1.1 | DCV3 | bar: Y to Y
220 | Features of IVI or Connect | CVPP | Baidu数据平台 |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-01-17 | N/A | N/A |  |  |  | PRD DUEROS_CVPP_Ford and Baidu Accoun_Phase 2_PRD_v1.4.pdf | 无MRD | N/A | Fan, Henry (H.) <hfan11@ford.com> | N/A | 徐静怡 v_xujingyi@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2020-01-03 | 2020-01-03 | 2020-01-10 | 2020-02-14 | B | 12/24/2019: Baidu check 百度提供方案？ 12/25/2019: discussion today, info tomorrow 12/27/2019: Baidu feedback before 31th 1/2/2020: MRD replan to 1/3 1/9/2020: need Ford FO check 1/10/2020: push FO check 1/13/2020: on-site review this Wednesday 2/4/2020: follow up meeting 2/14/2020: sign off; |  |  | CVPP | data |  | x | 数据埋点 | CVPP |  |  |  |  | DCV4 | DCV4 | R05 | ?
221 | Features of IVI or Connect | CVPP | 个人中心 |  | 20% | 80% | NA | Baidu |  | x | x |  | 2020-01-17 | 【林肯U554】_ID221_个人中心_V1.4_20200415 | 【福特CX727】_ID221_个人中心_V1.5_20200415 |  |  |  | PRD DUEROS_CVPP_Ford and Baidu Accoun_Phase 2_PRD_v1.4.pdf |  | N/A | Wang, Johnny (J.) <jwang308@ford.com> | Zou, Yujuan (Y.) <yzou32@ford.com> | 潘承栋 v_panchengdong@baidu.com |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T |  |  | close |  |  | 2020-01-10 | 2020-01-10 | 2020-01-17 | 2020-02-19 | B | 12/24/2019: Ford requirement combine to item 101 12/30/2019: replan to 2020/1/10 1/10/2020: proposal before 1/13, on-site review 1/15 2/3/2020: updated MRD available, pending by Ford FO's review comments 2/4/2020: follow up meeting 2/6/2020: pending due to Ford FO 2/14/2020: plan to sign off |  |  | CVPP | account |  | x | 账号 | CVPP |  |  |  |  | R04 |  | DCV2 | DCV3
222 | 电池动力汽车相关/Electric Vehicle | CVPP | EV Carryover features |  | 30% | 70% |  | Baidu |  | x | x | [10 empty] | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> | [24 empty] | cancel | [6 empty] | F | 1/10/2020: Luo Minghao check on-going feature duplicated. |  | x | bar: Y to Y
223 | 电池动力汽车相关/Electric Vehicle | CVPP | EV Plug and charge |  | 30% | 70% |  | Desay |  | x | x | DE04 B7b3 |  | N/A | N/A |  |  |  |  | 不需要输出MRD（无app开发） | P72d_15P_PlugAndCharge_R_v2_00_MY21 | Ji, Jerry (Y.) <yji9@ford.com> | Xiao, Yun (Y.) <yxiao21@ford.com> |  | liu yi <Yi.Liu@desay-svautomotive.com> | [24 empty] | close |  |  | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-03-02 | N.A | 1/10/2020: Luo Minghao check on-going 2/19/2020: 无上层应用。transfer to Desay? 2/27/2020: transfer to Desay, combine to SOA, no MRD needed.3/2/2020: development on-going, tracking separately |  | x |  |  |  | x |  | CVPP |  |  |  |  | DCV0 | DCV0 | DCV1.1 | DCV3 | bar: Y to Y
224 | 驾驶辅助/Drive assist | DAT | Auto High beam/glare free high beam | Y | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Song, Amy (S.) <ssong18@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | DCV2 | DCV2 | DCV3
225 | 驾驶辅助/Drive assist | DAT | DAS: driver alert system | Y | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Song, Amy (S.) <ssong18@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | DCV2 | DCV2 | DCV3
226 | 驾驶辅助/Drive assist | DAT | ACC/iACC (Setting/HMI) | Y | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Cui, Victor (M.) <mcui5@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | ACC only | ACC only | ACC only | ACC only | Y | Y | N | Y | Y | Y | Y | OPT | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | DCV2 | DCV2 | DCV3
227 | 驾驶辅助/Drive assist | DAT | Speed limiter/intelligent speed limiter | Y | 95% | 5% |  | Desay |  | x | x | yes | 2019-12-20 | 【林肯U554】车辆控制_ID11_V2.1_ 20200331.pdf | 【福特727】车辆设置_ID11&20&33&35&38&43&45&46&47&48&49&67&224&225&226&227_v3.4_20200427 |  |  |  | Settings In Infotainment CenterStack SPSS v1.17 May 28, 2019.pdf Settings in Centerstack Logical to Physical CAN signal mapping Feb 5, 2019.docx Settings In Infotainment CenterStack APIM ImpGuide v1.17 May 28, 2019.xlsx | 合并到NO11 |  | Cui, Victor (M.) <mcui5@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | close |  |  | 2019-12-20 | 2019-12-20 | 2019-12-27 | 2020-01-08 | N.A | corresponding setting functions combine to item 11 1/6/2020: plan to sign off |  |  | Driver assist | Driver assist setting | x |  | setting | core | Y |  |  |  | DCV2 | DCV2 | DCV2 | DCV3
228 | Vehicle Features/Interfaces | PMT2 | Digital Scent | N | 85% | 15% |  | DEsay |  |  | x | yes |  | pending - tbd (FO) - program scope - open | N/A |  |  |  |  | Ford_MRD_Digital_Scent_V1.3_20200228.docx |  | Wang, Yisheng (Y.) <ywang440@ford.com> Chen, Minghui <MCHEN122@ford.com> | New NSPS |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  |  | N | N | N | N | N | N | N | N | N | N | tbd | N | Y | Y | N | N | N | Y | N | ED&T | Y |  | reopen |  |  | 2020-02-20 | 2020-02-24 | 2020-02-28 | 2020-02-28 | Ford | 1/13/2020: replan today 2/6/2020: supplier to provide plan date 2/8/2020: EESE Inhouse provide plan date 2/24/2020: 2020/10/23: MRD shared to Ford FO, pending by Ma shuhan's comments | [6 empty] | digital scent | extend | TBD
229 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | TFT HUD - setting | N |  |  |  | Desay |  |  | x | DE07 B2b2 |  | N/A | N/A | [6 empty] | Li, Jianxin (J.) <jli294@ford.com> | Liu, Luisa (Fan.) <fliu43@ford.com> |  | liu, xiao gang |  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | ED&T | Y |  | reopen | [6 empty] | Ford | 1/10/2020: Luo Minghao check on-going 2/6/2020: supplier to provide plan date 3/22/2020: not related to SW, cancel 4/13/2020: change feature name to "AHUD setting" 2020/10/23: Discussion held months ago, while no further final request shared to Desay. | [7 empty] | basic | TBD
230 | Vehicle Features/Interfaces | EESE/System | Lincoln Embrace (vehicle setting: 3-mode selection) | N | 90% | 10% |  | Desay |  |  |  | yes - tbd |  | N/A | N/A | [6 empty] | Wu, Bella (Y.) <YWU150@ford.com> | Wang, Wei Hua (Lisa.) <wwang96@ford.com> |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  |  | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | N | N | N | Y | N | ED&T | Y |  | reopen |  |  | hold-on | hold-on | hold-on | hold-on | Ford | 1/13/2020: replan today 2/6/2020: supplier to provide plan date 2/14/2020: no SPSS 2/19/2020: hold on till SPSS ready 2020/10/23: no offical request send to Desay | [7 empty] | extend | TBD
231 | Vehicle Features/Interfaces | EESE/DI | Multi-Function Knob |  | 90% | 10% |  | Desay |  |  |  | n.a |  | N/A | N/A | [6 empty] | Yao, Frank (F.) <FYAO2@ford.com> |  |  | Wang dong <Dong.Wang@desay-svautomotive |  |  | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | N | N | N | Y | N | ED&T | Y |  | reopen | [6 empty] | Ford | 2020/10/23: only feasibiliity study held, need more official input | [7 empty] | basic | TBD
232 | Vehicle Features/Interfaces | EESE/DI | modified mini ICP |  | 90% | 10% |  | Desay |  |  |  | n.a |  | N/A | N/A | [6 empty] | Yao, Frank (F.) <FYAO2@ford.com> - 764 Chen, Huizhen (H.) <hchen188@ford.com> - 625ICA |  |  | Wang dong <Dong.Wang@desay-svautomotive |  |  | N | N | N | N | N | N | N | N | N | N | N | Y - Variant2 | Y | Y | N | Y | Y | Y | N | ED&T | Y |  | reopen | [6 empty] | Ford | 2020/10/23: only feasibiliity study held, need more official input | [7 empty] | basic | TBD
233 | Vehicle Features/Interfaces | PMT2 | Ambient Lighting - Music Visualizer, specific color settings |  | 90% | 10% |  | Desay |  |  |  | yes |  | N/A | N/A | [6 empty] | Fu, Theo (X.) <XFU7@ford.com> Sun, Qiming (Q.) <qsun31@ford.com> |  |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  |  | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | N | N | N | N | N | ED&T | Y |  | reopen | [6 empty] | Desay | 2020/10/23: UE on-going | [6 empty] | setting | basic | TBD
234 | Vehicle Features/Interfaces | PMT2 | Ambient Lighting - Breath Control (setting: on/off) |  | 90% | 10% |  | Desay |  |  |  | yes |  | N/A | N/A | [6 empty] | Fu, Theo (X.) <XFU7@ford.com> Sun, Qiming (Q.) <qsun31@ford.com> |  |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  |  | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | ED&T | Y |  | reopen | [6 empty] | Desay | 2020/10/23: UE on-going; duplicated with 233 | [6 empty] | setting | basic | TBD
235 | 驾驶辅助/Drive assist | DAT | Clear Exit Assist （DAT204） | Y | 90% | 10% | NA | Desay |  |  | x | yes |  | N/A | N/A |  |  |  | Vehicle Settings APIM SPSS v1.22 Feb 25, 2020 |  |  | Zhou, Wu (W.) <wzhou44@ford.com> | Sun, Xiao (X.) <xsun36@ford.com> |  | liu, xiao gang |  |  | N | N | N | Y | N | N | N | N | N | N | N | N | Y | Y | N | N | Y | Y | N | ED&T | Y |  | reopen |  | 3 |  |  |  |  | Desay | 2020/10/23: Desay UE check whether update needed |  |  | Driver assist | Driver assist HMI | x |  | setting | basic | TBD
236 | 驾驶辅助/Drive assist | DAT | Digital RVC (stand alone RVC with I2C) |  | 90% | 10% |  | Desay |  |  | x | yes |  | N/A | N/A |  |  |  | Digital RVC SPSS v1.4 April 26, 2019 I2C Over LVDS Com Protocol for Camera SPSS v1.0 Jun 2, 2017 |  |  | Chen Xuan <XCHEN161@ford.com>/Wang, Tom (X.) <XWANG190@ford.com> |  |  | li, xiaojie |  |  | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | Y | Y | Y | Y | N | ED&T | Y |  | reopen | [6 empty] | Ford | 2020/10/23: only feasibiliity study held, need more official input | [6 empty] | camera | core | TBD
237 | Vehicle Features/Interfaces | EESE/IVI(Diven) | 3D Map in Cluster |  | 20% | 80% |  | Baidu |  |  |  | yes |  | N/A | N/A | [6 empty] | Ding, Xiaojing (X.) <XDING13@ford.com> |  | 原翼 yuanyi13@baidu.com |  |  |  | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | N | N | N | N | N | ED&T | Y |  | reopen | [6 empty] | Ford | 2020/10/23: only feasibiliity study held, need more official input | [5 empty] | x | 地图 | extend | TBD
238 | Vehicle Features/Interfaces | Fordpass | Smart Scene | N | 20% | 0% | 80% | Ford EESE |  |  |  | yes |  | N/A | N/A | [6 empty] | Meng, Sheena (M.) <MXIA10@ford.com>/Liu, Zichao (Tony.) <zliu83@ford.com> |  |  | XU LIDI(Lidi.Xu@desay-svautomotive.com) |  |  | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | Y | Y | Y | Y | N | ED&T | Y |  | reopen | [6 empty] | Ford | 2020/10/23: only feasibiliity study held, need more official input | [7 empty] | extend | TBD
239 | Vehicle Features/Interfaces | EESE/IVI(Diven) | Auto EPB |  | 90% | 0% |  | Desay |  |  |  | yes |  | N/A | N/A |  |  |  | Auto EPB SPSS v1.0 Oct 11, 2018.pdf |  |  | Ding, Xiaojing | [5 empty] | N | N | N | N | N | N | N | Y | Y | Y | N | N | N | N | N | N | N | N | N | ED&T | Y |  | close | [15 empty] | basic | TBD
240 | Features of IVI or Connect | CVPP | E-CALL |  | 95% | 5% |  | desay |  |  |  | yes | [9 empty] | Ren, Siyuan (Alex.) <SREN6@ford.com> | [5 empty] | Y | Y | Y | Y | N | N | N | N | N | Y | N | N | Y | Y | Y | Y | Y | Y | Y_New | ED&T | Y |  | on-going | [6 empty] | Ford | 2020/10/23: MRD review by Ford FO | [7 empty] | basic |  |  |  |  | DCV4 | DCV4
241 | Features of IVI or Connect | EESE/IVI(Diven) | BT Child Seat |  | 95% | 5% |  | Desay |  |  |  | yes | [9 empty] | Xu, Amy (X.) <XYAFEI@ford.com> | [5 empty] | Y | Y | Y | Y | N | N | N | N | N | N | N | Y | Y | Y | Y | Y | Y | Y | N | ED&T | Y |  | on-going | [6 empty] | Desay | 2020/10/23: Desay review PRD, provide OIL and close | [7 empty] | extend | TBD |  |  |  | R04
242 | Vehicle Features/Interfaces | EC Inhouse | Relax (At-ease) | N | 15% | 15% | 70% | Ford EESE |  |  | x | yes |  |  | N/A |  |  |  |  | Ford_MRD_Digital_Scent_V1.3_20200228.docx |  | Zhang, Xiaojing (X.) <XZHAN247@ford.com> | New NSPS | 刘韧 v_liuren@baidu.com（语音） |  |  |  | Y | Y | Y | Y | N | N | N | N | N | N | N | N | Y | Y | Y | Y | Y | Y | N | ED&T | Y |  | new |  |  | 2020-02-20 | 2020-02-24 | 2020-02-28 | 2020-02-28 | in House | 1/13/2020: replan today 2/6/2020: supplier to provide plan date 2/8/2020: EESE Inhouse provide plan date | [6 empty] | digital scent | extend | TBD |  |  |  | R00 | R00
243 | Vehicle Features/Interfaces | EC Inhouse | Surprise message | N | 15% | 15% | 70% | Ford EESE |  |  |  | yes | [9 empty] | Bao, Jianming (J.) <JBAO8@ford.com> | [5 empty] | Y | Y | Y | Y | N | N | N | N | N | N | N | N | N | N | Y | Y | Y | N | N | ED&T | Y |  | new | [6 empty] | in House | [8 empty] | extend | TBD |  |  |  | DCV3 | DCV3
244 | Vehicle Features/Interfaces | EESE/IVI(Roger) | Digital chime | N | 100% |  |  | Desay |  |  |  | yes | [9 empty] | Liu, Yang (Y.) <YLIU307@ford.com> | [5 empty] | N | N | N | N | Y | Y | N | N | N | N | N | N | N | N | N | N | N | N | Y | ED&T | Y |  | on-going | [6 empty] | Ford | 2020/10/23: Ford FO double confirm the requirement spec | [7 empty] | extend | [6 empty] | R06 | R05.01
245 | Vehicle Features/Interfaces | EC Inhouse | Demo Mode | N | 15% | 15% | 70% | Ford EESE |  |  |  | yes | [9 empty] | Bao, Jianming (J.) <JBAO8@ford.com> | [5 empty] | N | Y | N | Y | N | N | N | N | N | N | N | N | Y | Y | Y | Y | Y | N | N | ED&T | Y |  | new | [6 empty] | in House | [8 empty] | extend | TBD |  |  |  | R00 | R00
246 | Vehicle Features/Interfaces | EC Inhouse | Co-driver | N | 15% | 15% | 70% | Ford EESE |  |  |  | yes | [9 empty] | Bao, Jianming (J.) <JBAO8@ford.com> | [5 empty] | N | Y | N | Y | N | N | N | N | N | N | N | N | N | N | N | N | Y | N | N | ED&T | Y |  | new | [6 empty] | in House | [8 empty] | extend | TBD |  |  |  | R07
247 | Vehicle Features/Interfaces | EC Inhouse | Phase4 FNV2_Diagnostics_Analytics | N | 100% |  |  | Desay |  |  |  | n.a | [9 empty] | Liu, Dapeng (D.) <DLIU79@ford.com> | [5 empty] | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | ED&T | Y |  | on-going | [6 empty] | Baidu | 2020/10/23: pending by UI | [7 empty] | basic |  |  |  |  | R04 | R04 | R06 | R05
248 | 驾驶辅助/Drive assist | CVPP/EESE | 5G V2X (V2I + V2V) (requirement to be confirmed) | N |  |  |  | TBD | [13 empty] | Shan, Susan (D.) <DSHAN@ford.com> CVPP | [5 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | N | N | ED&T | Y |  | new
249 | Basic features | EESE/IVI(Diven) | New CAN Database (FNV2.1, FNV3) | N | 90% | 10% |  | Desay | [13 empty] | Ding, Sunny (X.) <XDING13@ford.com> | [5 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | Y | N | N | N | N | ED&T | Y
250 | Vehicle Features/Interfaces | EESE | My Mustang: Pony Screen, Track Apps, Gauges, Exaust Mode, Heritage, Custom Mode | N | 90% | 10% |  | Desay | [19 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | Y | N | N | N | N | ED&T | Y
251 | Vehicle Features/Interfaces | EESE | Mustang Settings | N | 90% | 10% |  | Desay | [19 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | Y | N | N | N | N | ED&T | Y
252 | HMI | EESE | My Color (setting, new theme) | N | 55% | 45% |  | Desay | [19 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | Y | N | N | N | N | ED&T | Y
253 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Continuously Controlled Damping (Setting) | N | 90% | 10% |  | Desay | [10 empty] | Settings In Infotainment CenterStack SPSS v1.19 Jun 18, 2020 | [8 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | Y | N | ED&T | Y
254 | HMI | EESE | 3D Real-time Render & Animation | N | 50% | 50% |  | Desay/Baidu | [19 empty] | N | N | N | N | N | N |  | N | N | N | N | N | Y | Y | N | N | N? | N | N | ED&T | N
255 | Vehicle Features/Interfaces | EC Inhouse | IVI Calendar | N | 5% | 15% | 80% | Ford EESE | [13 empty] | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  | 刘韧 v_liuren@baidu.com（语音） |  |  |  | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | N | N | N | Y | N | ED&T | N
256 | Vehicle Features/Interfaces | EESE/IVI(Roger) | Baidu Map 5.0 - new engine | N |  | 100% |  | Baidu | [13 empty] | Yao Lan |  | 原翼 yuanyi13@baidu.com |  |  |  | N | N | N | N | N | N | N | N | N | N | N | N | Y | Y | Y | Y | Y | Y | N | ED&T | N
257 | Vehicle Features/Interfaces | EESE/IVI(Roger) | KTV | N | 10% | 90% |  | Baidu | [15 empty] | 穆仁萍 v_murenping@baidu.com |  |  |  | N | Y | N | Y | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | ED&T & license | N | [22 empty] | ?
258 | Vehicle Features/Interfaces | EESE/System | Rear power seat adjustment | N | 90% | 10% |  | Desay | [13 empty] | He, Tao (T.) <the8@ford.com>/Ruan, Guansheng (G.) <gruan1@ford.com> | [5 empty] | N | N | N | N | N | N | N | N | N | N | N | Y | N | N | N | N | N | N | N | ED&T | Y
259 | 驾驶辅助/Drive assist | DAT | Lane Biasing (On/Off Setting) （DAT204） | N | 90% | 10% |  | Desay | [10 empty] | Vehicle Settings APIM SPSS v1.29 Oct 7, 2021 |  |  | Song, Amy (S.) <ssong18@ford.com> | QXU35@ford.com |  |  |  |  | N | N | N | Y | N | Y | N | N | N | N | N | N | Y | Y | N | N | Y | N | Y_ICA | ED&T | Y
260 | 驾驶辅助/Drive assist | DAT | Assisted Lane Change (On/Off Setting)(DAT204) | N | 90% | 10% |  | Desay | [10 empty] | Vehicle Settings APIM SPSS v1.29 Oct 7, 2021 |  |  | Song, Amy (S.) <ssong18@ford.com> | QXU35@ford.com |  |  |  |  | N | N | N | Y | N | Y | N | N | N | N | N | N | Y | Y | N | N | Y | N | Y_ICA | ED&T | Y
261 | Vehicle Features/Interfaces | EESE | Door Keypad Code (Setting/HMI) | N | 90% | 10% |  | Desay | [10 empty] | Vehicle Settings APIM SPSS v1.29 Oct 7, 2021 | [8 empty] | N | N | N | N | N | N | N | Y | Y | Y | Y | N | N | N | N | N | N | Y | N | ED&T | Y
262 | Vehicle Features/Interfaces | EESE | Custom Drive Mode | N | 90% | 10% |  | Desay | [12 empty] | Wang, Wei Hua (Lisa) <wwang96@ford.com> | CDM FO Aleid, Ehab (E.) <ealeid@ford.com>/ IVI System: Cui, Junzhi (J.) <JCUI17@ford.com> | [5 empty] | N | N | N | N | N | N |  | N | N | N | N | N | N | N | Y | N | N | N | N | ED&T | Y
263 | Vehicle Features/Interfaces | EESE | S650 3D APP (Setting/HMI) | N | 90% | 10% |  | Desay | [12 empty] | Wang, Wei Hua (Lisa) <wwang96@ford.com> | Jam.Leung(展钊)<zliang7@ford.com> | [5 empty] | N | N | N | N | N | N |  | N | N | N | N | N | N | N | Y | N | N | N | N | ED&T | Y
264 | Vehicle Features/Interfaces | EESE | Passenger Airbag Deactivation(TBD) | N | 90% | 10% |  | Desay | [19 empty] | N | N | N | N | N | N |  | N | N | N | N | N | N | N | Y | N | N | N | N | ED&T | Y
265 | 驾驶辅助/Drive assist | EESE | predictive speed assist menu-Active Drive Assist 1.5 I ACC 2.0(DAT204) | N | 90% | 10% |  | Desay | [10 empty] | Settings In Infotainment CenterStack SPSS v1.24 Oct 7, 2021 |  |  | Cui, Victor (M.) <MCUI5@ford.com> | QXU35@ford.com |  |  |  |  | N | N | N | Y | Y | N |  | N | N | N | N | N | Y | Y | Y | Y | Y | N | N | ED&T | Y
266 | 驾驶辅助/Drive assist | EESE | 360 cross traffic alert triggered split view(CTASV)(DAT204) | [15 empty] | Vehicle Settings APIM SPSS v1.29 Oct 7, 2021 |  |  | Chen, Xuan (X.) <XCHEN161@ford.com> | [5 empty] | N | N | N | Y | N | Y | N | N | N | N | N | N | Y | Y | N | N | Y | N | Y_ICA | ED&T | Y
267 | 驾驶辅助/Drive assist | EESE | Intersection Assist 2.0 (交叉口辅助)(DAT204) | [15 empty] | Vehicle Settings APIM SPSS v1.29 Oct 7, 2021 |  |  | Zhu, Jinpeng (J.) <jzhu85@ford.com> | [5 empty] | N | N | N | Y | N | Y | N | N | N | N | N | N | Y | Y | N | Y | Y | N | Y_ICA | ED&T | Y
268 | Vehicle Features/Interfaces | EESE/IVI(PMT3)(Forrest) | 驾驶模式选择/SDM(Selectable Drive Mode) from Hotkey | Y | 90% | 10% |  | Desay |  |  |  |  | 2019-12-15 | 【林肯U554】车辆控制_ID20&24&27&33&35&38&43&45_V1.6_ 20200316 | 【福特727】车辆控制_ID11&22&24&26&27&86&158&160&185&187_V2.8_20200427 |  |  |  | Selectable Drive Mode APIM Imp Guide v1.2 Aug 21, 2019.xlsx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.docx Selectable Drive Mode SPSS v1.2 Aug 21, 2019.pdf | 不需要输出MRD |  | Yang, Yi (Y.) <YYANG130@ford.com> | Hu, Pin (P.) <phu13@ford.com> |  | Xu, Kangkang <Kangkang.Xu@desay-svautomotive.com> |  |  | N | N | Y | Y | N | N | N | N | N | N | N | N | N | N | N | Y | Y | Y | N | Y | ED&T | Y |  | close |  |  | 2019-12-25 | 2020-01-10 | 2019-12-25 | 2020-01-15 | N.A | HMI: Desay prepare UE 12/23/2019: SPSS is ok, while HMI need to be provided. 12/30/2019: need Desay to provide HMI 1/6/2020: Desay mail to FO/HMI 1/10/2020: Ford HMI can not accept the prospoal - open item Desay provide OIL today 1/13/2020: delay to today 1/15/2020: sign off | HMI open |  | Vehicle related | SDM |  |  | setting | core | Y |  |  |  | DCV2 | DCV3 | DCV2 | R00
268 | Vehicle Features/Interfaces | EESE/IVI | Electronic Locking Differential (eLD / eLocker) |  | 90% | 10% |  | Desay | [13 empty] | Kshavarz, Mahmoud (M.) | bar: N N to N N
269 | IPC only | EESE/IVI | Oil Minder/ Level (P702 MCA) |  | 90% | 10% | [15 empty] | McCliment, Greg (G.A.) | bar: N N to Y Y; N N to Y_ICA Y_ICA
270 | Vehicle setting | EESE/IVI | Active Exhaust Valve (P702 MCA) |  | 90% | 10% |  | Desay | [13 empty] | Kainz, Laura (L.L.) | bar: N N to Y Y; N N to Y_ICA Y_ICA
271 | IPC only |  | Trail 1-Pedal Driving (P702 MCA) | [18 empty] | Zhang, Jason (Pin) <pzhang11@ford.com> Yu, Hugo (G.)<GYU18@ford.com> | [5 empty] | N | N | N | N | N | N |  | N | Y | Y? | N | N | N | N | N | N | N | N | N
272 | Vehicle Features/Interfaces | EESE/IVI | Trailer Brake Control (P702 MCA) |  | 90% | 10% |  | Desay | [13 empty] | Jones, Drew (A.T.) | bar: N N to Y Y; N N to Y_ICA Y_ICA
273 | IPC only |  | 1st Row Seat Position (P702 MCA) | [18 empty] | Schutt, Sarah (S.) | bar: N N to Y Y; N N to Y_ICA Y_ICA
274 | Vehicle Features/Interfaces | EESE/IVI | Fob Free Entry and Ignition (NFC) 2024 (P702 MCA) |  | 90% | 10% |  | Desay | [13 empty] | Bonnell-Kangas, Aaron (A.) | bar: N N to Y Y; N N to Y_ICA Y_ICA
275 | Vehicle setting | EESE/IVI | Neutral Flat Tow (Recreational Tow) (P702 MCA) |  | 90% | 10% |  | Desay | [13 empty] | Piovano, Francisco (F.) | bar: N N to Y Y; N N to Y_ICA Y_ICA
276 | Vehicle Features/Interfaces | EESE/IVI | Trailer Profiles and Settings (P702 MCA) |  | 90% | 10% |  | Desay | [13 empty] | Rodriguez-flores, Raul (R.) | bar: N N to Y Y; N N to Y_ICA Y_ICA
277 | IPC only | EESE/IVI | Engine Starting (Stationary) (P702 MCA) |  | 90% | 10% | [15 empty] | Barrueta, Cesar (C.) Zhang, Jian (Ben.) <JZHAN263@ford.com> | [5 empty] | N N: N; N N: Y; N N: Y?; N N: N; N N: N; Y Y: N; Y Y: N; N N: N; N Y: N; Y Y: N; N N: N; Y_ICA Y_ICA: N
278 | Vehicle Features/Interfaces | EESE/IVI | Enhanced Active Driver Assist (P702 MCA) |  | 90% | 10% |  | Desay | [13 empty] | Gotadki, Shruti (S. P.) | bar: N N to Y_ICA Y_ICA
279 | Vehicle Features/Interfaces | EESE/IVI | Trailer Light Check (FNV3) (MY24 P702 MCA) |  | 90% | 10% |  | Desay | [13 empty] | Antunes, Mauricio (M.C.) | bar: N N to Y_ICA Y_ICA
280 | Vehicle setting | EESE/IVI | TPMS |  | 90% | 10% |  | Desay | [13 empty] | Baldi, Valter (V. Z.) | bar: N N to Y_ICA Y_ICA
281 | Features of IVI or Connect | CVPP | 语音助手1.5/2.0 VPA 1.5/2.0 (融合贯通生态的智能化的语音助手） |  | 10% | 90% |  | Baidu | [13 empty] | Xie, Jie (J.) <JXIE49@ford.com> | bar: N N to Y_ICA Y_ICA
| P702 MCA (FNV3) |  | 基于云端的用户档案Project Aspire_Personal Portable Profiles (PPP) | bar: N N to Y_ICA Y_ICA
282 | Features of IVI or Connect | CVPP | 最新版领先市场的地图导航能力 Leading Connected Map/Navi （百度地图5.0） |  | 10% | 90% |  | Baidu | [13 empty] | Yao, Tristan (Lan) <LYAO17@ford.com> | bar: N N to Y_ICA Y_ICA
283 | Features of IVI or Connect | CVPP | FNOS (CNECDMPORT-114 - Oil Life Prediction / China SYNC+ IVI) |  | 5% | 5% | 90% | Ford | [13 empty] | Chen, Wei (W.) <WCHEN160@ford.com> | bar: N N to Y_ICA Y_ICA
284 | Features of IVI or Connect | CVPP | (百度小程序) 加油 - Oil Service |  | 10% | 90% | [15 empty] | Xie, Jie (J.) <JXIE49@ford.com> | bar: N N to Y_ICA Y_ICA
285 | Features of IVI or Connect | CVPP | (百度小程序) 洗车 - Car wash |  | 10% | 90% | [15 empty] | Xie, Jie (J.) <JXIE49@ford.com> | bar: N N to Y_ICA Y_ICA
286 | Features of IVI or Connect | CVPP | 4G/5G Entertainment Connectivity Subscription |  | 5% | 5% | 90% | Ford | [13 empty] | Qi, Xingyu | bar: N N to Y_ICA Y_ICA
287 | Features of IVI or Connect | CVPP | Show car mode - CX（Account 账号和个人设置） |  | 5% | 5% | 90% | Ford | [13 empty] | Sheng Ling | bar: N N to Y_ICA Y_ICA
288 | Features of IVI or Connect | CVPP | CCS (Customer Connectivity Setting)---中国SYNC+ IVI端没有专门固定的设置界面。(global 版是一直有的）。中国采用用户授权 (手机端触发），允许后台获取用户数据（TCU） |  | 5% | 5% | 90% | Ford | [13 empty] | Gu, Regina (Q.) <QGU12@ford.com> | bar: N N to Y_ICA Y_ICA
289 | Features of IVI or Connect | CVPP | 用户反馈2.0 (voice Customer Feedback 2.0) |  | 10% | 90% | [15 empty] | Xie, Jie (J.) <JXIE49@ford.com> | [27 empty] | cancel | bar: N N to N N
|  | EESE/IVI | 地图基础版（见《IOV-地图功能list) Foundamental version of Map | [18 empty] | Yao, Tristan (Lan) <LYAO17@ford.com> | bar: N N
|  | EESE/IVI | 开始导航倒计时/导航结束卡片 Starting/Ending Count Down | [18 empty] | Yao, Tristan (Lan) <LYAO17@ford.com> | bar: N N
|  | EESE/IVI | 个性化底图-4S店POI显示 4S Dealer POI on Map | [18 empty] | Yao, Tristan (Lan) <LYAO17@ford.com> | bar: N N
|  | EESE/IVI | 组队出行 Team Travel | [18 empty] | Yao, Tristan (Lan) <LYAO17@ford.com> | bar: N N
|  | EESE/IVI | 微信地址分享 WeChat Send To Car | [18 empty] | Yao, Tristan (Lan) <LYAO17@ford.com> | bar: N N
|  | CVPP | 福特派/林肯之道地址分享 FordPass/LincolnWay Send to car | [18 empty] | Shi, Stella (J.) <jshi32@ford.com> | bar: N N
|  | PMT2 | AWD / 4WD: Torque Transfer for Handling & Traction (FWD or RWD) (disconnect is sub-system) | [18 empty] | Gao Jiliang | bar: N N
|  | PMT5 | Trail Control (TRAIL) | [18 empty] | Yu, Hugo (G.)<GYU18@ford.com> | bar: N N
|  | EESE | Trailer Lights and Charging | [18 empty] | Travis Zhou | bar: N N
|  | ECDX | Road Book | [18 empty] | Yang, Yi (Y.) <YYANG184@ford.com> | bar: N N
Formulas:
Planned release date = [Planned Available date]+BD2
Planned release date = [Actual available date]+BD2
Actual release date = [Actual available date]+BE2
Note on BD2: Author: promised to release MRD within 1 week
Note on E3: Author: "Y" 部分沿用Phase1/2/3 设计，只能作为参考，需求以Phase4需求为基准
Note on D4: Author: 包含通信部分，CAN，LIN，Ethernet，及软件架构部分，需要从Vector采购FNOS Autosar的软件基础架构。
Note on N4: Author: 需求，不需要输出MRD
Note on N6: Author: 需求，不需要输出MRD
Note on R11: Author: studio provide animation as input
Note on AL11: Welcome & farewell animation surrogate U725 NA
Note on D14: Author: Settings In Infotainment CenterStack : v1.17
Note on D19: Author: 通过CAN消息显示车辆OTA信息/Show the OTA status for Vehicle via CAN (FNV2)
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: function distributed in PMT1
Note on AV28: Author: Only for Software supplier
Note on D32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: VE DAT not related
Note on D33: Author: ADAS MAP /EH; INPUT for iACC
Note on T60: Author: SPSS available, need to upload
Note on D62: Author: HTML5, flexiable HMI engine for different display
Note on D70: Author: 充电电流的显示，谁做HMI谁是lead 11/11: Studio provide animation design
Note on T72: Author: others under checking by Xiaoyun
Note on AL73: 2D rendering updates for U725 CN exterior and interior (how many exterior colors TBC)
Note on AL78: 资源能力提升. 资源涵盖不受传统radio 的地域限制。支持节目名称搜索，和收藏。 资源提供方：蜻蜓FM。 取决于电台是否做了online radio (有单独的license, 涵盖在phase 4 license 里面) Enhanced Online Radio (resource: 蜻蜓FM - 公版). with more radio programs without geograph constrains. Support voice command of "open online Radio" " Previouse one" " Next one" " Save". Availible for Phase 4 programs. Currently booked on CD542;U554;U725:P702;CX727. Other programs will need to book application cost if have display size differences. Attention: Keep pay attention to customer feedback and see opportunity of replace Traditional FM/AM using it. Things been called out by team - Data Consumption & Support 流量影响 - Online Radio's Resources & UE Improvement
Note on J81: Author: 不含 双蓝牙
Note on AL82: 接听挂断；通话记录 records；拨号 dial；通讯录搜索；通讯录 contacts；同步通讯录和通话记录 sync contacts& records；请勿打扰 DO NOT IDSTURB
Note on J93: Author: 基本的语音功能
Note on D100: Author: 利用AR导航摄像头拍照和视频，本地功能
Note on D103: Author: IVI: internet gateWay SPSS IVI as client
Note on AL104: 车机端用户显示二维码， 用户通过福特派/林肯之道APP扫描二维码实现林肯/福特和百度账号互通。车机端会同时登陆福特/林肯账号和百度账号。 目前支持8个。
Note on D116: Author: HMI谁负责谁lead
Note on AY122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: combine to 112
Note on D140: Author: 内置
Note on D141: Author: 驾驶行为检测，从别的模块接受信号（如加速，刹车，等），对驾驶行为打分显示出来
Note on D147: Author: 胎压
Note on D153: Author: 360 camera基础上再增加一些摄像头
Note on D156: Author: 设置项
Note on D157: Author: 软开关
Note on D158: Author: 软开关
Note on D160: Author: 外置功放
Note on D161: Author: 可选驾驶模式
Note on D162: Author: 被盗车辆追踪
Note on D163: Author: setting
Note on D175: Author: 拿到GPS的原始数据做偏移
Note on D188: Author: Soft Key SYNC, Ford Pass
Note on D189: Author: When customers wait for vehicle hand-over, they can do IVI set up on FP in advance. Such as 3rd party ID linkage, wake up words, Pony related
Note on D190: Author: Improvement based on Phase II
Note on D192: Author: 诊断; 远程提醒换机油
Note on D201: Author: mapping to features
Note on D216: Author: duplicate to 157
Note on D222: Author: function already covered by the others; just reminder here
Note on D295: 见《IOV-地图功能list)。 支持地图包更新MOTA。 POI检索、地点收藏 POI search & store destinations 3D地图 3D Map 首页地图 Launcher Map 地图显示的夜间/白天模式 Night/Day Mode 实时交通播报 Real-time Traffic Broadcast 惯性导航 Inertial Navigation 超速提醒 Reminder of over speed 路线雷达 radar detection in routes 限行提醒 Reminder of traffic control rules
Note on D297: 福特品牌显示福特标，林肯品牌显示林肯标，野马显示野马标
Note on D298: 分享地址，支持Ford/Lincoln 车型间 语音对讲
Note on D299: 微信中收到的地址可以长按选择百度地图，地址会同步给相同百度地图账号的车机端。首次需微信扫描车机二维码，关联账号 （又被叫做：微信互联）
Note on D300: Send to car--把用户在FordPass 内置的地图查询的POI发送到车机 Send POI from smartphone APP to vehicle
Note on D304: Collect the point cloud data of underground parking lot back to the cloud by crowdsourcing through AR technology, analyze and provide parking POI information services, and provide advanced vehicle search services through indoor positioning technology.

## Change Log
date | version | author | change content | open item
2019-10-14 | 1.65 | Diven Yu | Deleted: 多屏背景同步/Multi-display wallpaper synchornization 紧急呼叫时静音/Mute for eCall 电子罗盘/Compass on IPC and IVI Emergency call Multi-Display, drive up to 3 display and 1 Video output Multi-Display animation 行车记录仪/Dash Camera(Driving Recording)---TBD 副驾收音机（和主驾相同）-New 副驾音频AUX输出/Passenger Audio AUX Output Deleted Lower Display features | need to sort out EV features with CVPP, key words: EV, power, Charge
| 2.3 | Susan Zhang | Update based on kick off meeting
2019-11-22 | 2.4 | Emma Chen | Update based on the FIP review with Fin and Diven. - change the sheet name "Phase4 Master feature list V2.0" to "Phase4 Master feature list V2.x" - adjust the format: font size - update the column "ID" to minimize confusion. - add column "AJ" as "file location"; - update column "S", add spec name for the features assigned to me. - mark cells in column "S" after checking the files in GitHub. Green means files available. - add file location link for DCV0 available files 11/28/2019: migrate FO info from input from Ma Mei.
2019-12-04 | 2.5 | Susan Zhang | remove some features. update Face ID items update option items
2019-12-05 | 2.6 | Emma Chen | Update after "MRD plan" meeting: column S, T; 2019/12/9: Add columns to record MRD review status. Add sheet “MRD_Review_Overview" Update regularly based on daily meeting Minor revision history are recorded in the sharepoint history
2020-04-08 | 2.8 | Emma Chen | • update FO info based on request from Diven, HMI team, DAT team @Yu, Diven (D.W.) @Zhu, Julia (L.) @Xu, Lidi @Jiang, Wenyan • MyKey cancelled in CD542, U725; @Sun, Evan (Yi.) @Xu, Andy (X.) • BSP cancelled in some programs based on FO’ input; @Wang, Cindy (X.J.) • ANC/ESE feature cancelled for some programs @Xu, Lidi @Wang, Fin (X.Y.) • reserve PHEV features(feature 177, 178, 179,180, 181, 187, 218, 223) for CD542 MY23 @Yu, Diven (D.W.) @Wang, Fin (X.Y.) @Ji, Jerry (Y.) @Liu, Luisa (Fan.) @Sun,Ying(IOV) • revert feature 229 due to the finding that AHUD setting missed in IVI for CD764. @Xu, Lidi • Features which need support from security team collected. • add supplier module info based feedback from Desay • add planned software releases, and percentage for DCV1 based on supplier’s input.
2020-06-01 | 2.8.1 | Emma Chen | 6/1/2020: rename file, remove revision index add sheets "U554MCA_FIP_Maturity", "CX727_FIP_Maturity", "P702_FIP_Maturity" after aligning with the detail software development for each feature; - update sheet "Phase4 Master feature list V2.x": cancel myKey feature; remove planning info for U554MCA, CX727, P702
2020-06-02 | 2.8.2 | Emma Chen | add charts for U554MCA, CX727, P702; update UE status for CX727 UE.
2020-06-04 | 2.8.3 | Emma Chen | - update sheet "Phase4 Master Feature list V2.x": Remove feature CEA in U554MCA. Remove feature "Eco behavior" in CD542, CD764
2020-06-08 | 2.8.4 | Emma Chen | add acutal maturity data for U554MCA, CX727, P702 after radom validation Add back feature "Eco behavior" in CD542, CD764
2020-06-09 | 2.8.5 | Emma Chen | HUD setting removed in U625ICA.
2020-07-03 | 2.8.6 | Emma Chen | feature 138 eco coach- cancelled in CD542 based on program's CPE meeting decision
2020-07-06 | 2.8.7 | Emma Chen | Update Feature status after weekly meeting
2020-07-13 | 2.8.8 | Emma Chen | 1. Cancel "tik toc" based on program's direction 2. Feature 217: RAC only applied in U554MCA and U625ICA based on PDL and hardware status 3. add DCV2 validation info
2020-07-14 | 2.8.9 | Emma Chen | 1. Cancel "Home to car" feature
2020-07-28 | 2.8.10 | Emma Chen | 1. cancel "IOD - Pitch and roll" in CX727; no program will have this feature. 2. add "home to car" back
2020-07-31 | 2.8.11 | Emma Chen | 1. add 4 new features: Relax E-CALL BT Child set Surprise Message 2. change FO of "Digital Scent", remove this feature in U554MCA.
2020-08-05 | 2.8.12 | Emma Chen | 1. Remove feature 147 - BSP for paak in CX727, 764 based on info from FO.
2020-08-21 | 2.8.13 | Emma Chen | Power running board: not applied in U625ICA
2020-09-01 | 2.8.14 | Emma Chen | 1. remove feature 189 Prognostics in CX727 2. remove feature 106 保养及在线预约 in CX727
2020-09-02 | 2.8.15 | Emma Chen | 1. remove feature 166 T&C and Privacy Policy in HMI for all programs 2. hold on feature 199 免密支付 for all programs 3. remove feature 175 home to car for all programs
2020-09-14 | 2.8.16 | Emma Chen | 1. add feature 140 DSO for CX727 based on the feedback from FNA CX727 team 2. Remove feature 27, 158 SDM in U554MCA (backup feature)
2020-09-18 | 2.9.17 | Emma Chen | 1. add back feature 175 home to car for all programs based on program governement change meeting. - hold on, need FO's further plan info 2. add back feature 106 保养及在线预约 in CX727 as "tbd" 3. add feature 228 - digital scent in 554MCA - tbd
2020-09-27 | 2.9.18 | Emma Chen | 1. remove feature 26 - ESE for P702 program based on program's confirmation mail 2. add feature 244 - digital chime for CX727; remove feature 140 DSO for CX727 3. add "Y" for feature 232 in U625ICA 4. change feature 199 免密支付 from onhold to Y
2020-09-29 | 2.9.19 | Emma Chen | 1. rename feature 242: from Relax to "Relax (At-ease)" 2. add new features: 245 - demo mode, 246 - co-driver based on CD542 action TIB 60 3. add feature 247 - Phase4 FNV2_Diagnostics_Analytics
2020-10-10 | 3 | Emma Chen | Add program "S650"
2020-10-15 | 3.1 | Emma Chen | Remove EA feature in CD542 based on the input from FO
2020-10-19 | 3.2 | Emma Chen | add Desay/baidu FO for CD764 - add ESE back for CD764 for high series only
2020-10-23 | 3.3 | Emma Chen | update new feature status after reviewing with desay
2020-10-26 | 3.4 | Emma Chen | Update Feature 214- rear camera on demand for CX727, U554MCA, CD764, CD542, P702, U625ICA
2020-10-30 | 3.4.1 | Yu Diven | Add S650, CDX706
2020-11-24 | 3.5 | Emma Chen | Update HMI FO for feature ID 58, 103;
2021/1/xx | 3.6 | Yu Diven | Update FIP for CX483
2021-01-27 | 3.7 | Emma Chen | Add feature: 254 3D Real-time Render & Animation for CD764； Change feature 237: from 2D to 3D, add feature: E-call in CD764, add feature: IVI Calendar, Baidu Map 4.0 - new engine, kala ok
2021-02-23 | 3.8 | Emma Chen | remove HUD setting in CD764 IVI; add rear power seat adjustment in U625ICA
2021-02-27 | 3.9 | Emma Chen | add feature implemtaion status for CD542, CX727;
2021-04-07 | 3.1 | Emma Chen | remove feature 234 based on the input from FO - Sun, Qiming (Q.)
2021-04-20 | 3.11 | Emma Chen | Update FO name for feature 29, 150,37,42,214,236,36
2021-04-26 | 3.12 | Emma Chen | remove feature 103 in CD764
2021-05-12 | 3.13 | Emma Chen | add ESE back for P702
2021-05-25 | 3.14 | Emma Chen | Add "Demo mode" in CD764
2021-05-26 | 3.15 | Emma Chen | Remove Li Alvin, replaced by Li Xuedong
2021-06-03 | 3.16 | Emma Chen | add feature 82 - AR in CD764
2021-06-15 | 3.17 | Emma Chen | change "variant" info: all
2021-06-16 | 3.18 | Diven Yu | Remove below features on CX483MCA, due to no Photo Shooting feature, no picture/video to be viewed: - 图片/小视频浏览器 Picture/video Viewer - 副驾图片浏览器/Passenger Picture Viewer Added below feature on CX483MCA, carry over CDX764: - IVI Calendar
2021-06-17 | 3.19 | Diven Yu | Remove below features on CX483MCA, due to deleted in IVI PDL: - Surprise message - Demo Mode - Co-driver - "Image recognition - Drive Status Monitor (Fatigue, Distraction, Dangers Behaviour)" - "Image recognition - Multi-Mode (Hand Gusture / Head / Emotion)" - 天窗控制 Sunroof Control - Ambient Lighting - Music Visualizer, specific color settings - Ambient Lighting - Breath Control (setting: on/off) - Rocket Setup
2021-07-01 | 3.20. | Diven Yu | Remove below features on CX483MCA and CDX706, due to deleted by Feature Owner: - TFT HUD - setting Added below feature on CX727 for CX727 ICA DAT204 update - Lane Biasing (On/Off Setting) - Assisted Lane Change (On/Off Setting)
2021-07-13 | 3.21 | Geng Dekang | Update Alert&Chime FO Update SDM FO Update Collision Mitigation (AEB) & Pre Collision Assist for intersections FO Update Welcome&Farewell FO
2021-08-06 | 3.22 | Geng Dekang | Update Camera variant for S650/CDX706/CX483MCA Update FIP ID 237 -Digital RVC (Modify S650 from "N" to "Y")
2021-09-06 | 3.23 | Diven Yu | Create new column for CX771, per RTO assumtion, all feature c/o CX727 and add E-Call. Remove 图片/小视频浏览器 Picture/video Viewer on all programs except CD542 High. This feature requires AR Camera, so it is bundled with AR Navigation. Remove IOD- Behavior Coaching Display Client from CD764 and CX483MCA due to the feature is not required. Add Door Keypad Code (Setting/HMI) to U554MCA, P702, CX483MCA
2021-11-10 | 3.24 | Chen Emma | - remove feature 93/94/95 based on FO-Elaine Jia's comment - add feature 124 for CX483MCA
2021-11-15 | 3.25 | Chen Emma | - add 4 new features for S650 Custom Drive Mode S650 3D APP (Setting/HMI) Passenger Airbag Deactivation(TBD) predictive speed assist menu-Active Drive Assist 1.5 I ACC 2.0
2021-12-01 | 3.26 | Zhang Daorong | add feature 93/96 for CDX706 add DAT204 feature 239/259/260/265/266/267
2021-12-18 | 3.27 | Zhang Daorong | Update baidu FO contact Update CX483/CD706 ADAS Variant
2022-02-18 | 3.28 | Zhang Daorong | Update Ford FO contact Update CX483 for 237 3D Map in Cluster
2022-02-23 | 3.29 | Cui Junzhi Zhang Daorong | Add feature 269-291 for P702MCA
22/3/2022 | 3.3 | Cui Junzhi | delete:IPC only feature（P702MCA） Oil -Minder/ Level Trail 1-Pedal Driving 1st Row Seat Position Engine Starting (Stationary) delete feature（P702MCA） : (百度小程序) 加油/洗车
30/3/2022 | 3.31 | Shen Haomin | Update DAT204 feature 265/267 for CDX706L
2022-05-23 | 3.32 | Wuchengbo | Add U725C ICA Feature List
2022-05-23 | 3.32 | Geng Dekang | Add CD764ICA & DAT 204 for CD764 & CD764 ICA
2022-05-29 | 3.32 | Wuchengbo | Adjust U725C ICA Feature
2022-06-06 | 3.33 | wuchengbo | Adjust U725C ICA Feature

## Variant
|  | J1 | [10 empty] | FNV2.1
|  |  | MY21 | MY21 |  | MY22 | MY22 | MY22 | MY21 |  |  | MY23 | MY23 | MY23 |  |  | 32G | 64G
|  | CD542 CD542ICA |  | CX727 | U725 | P702 | U554MCA | U625ICA | CD764 |  | CD706 |  | S650 | CX483MCA | SW-A: | 12''&13.2''Ford | SW-A1 | SW-A2
| display " | 13.2 | 27 | 15.5 | 12 | 12L | 13.2 | 27 | 27 |  | 13.2 | 27 | 13.2 | 27 | SW-B: | 27''Ford | SW-B1 | SW-B2
| SW variant | SW-A | SW-B | SW-C | SW-A | SW-A | SW-D | SW-B | SW-E |  | SW-G | SW-F | SW-H | SW-K | SW-C: | 15.5" Mustang |  | SW-C
| iACC | N | N | OPT | N | Y | Y | OPT | OPT |  | N |  |  |  | SW-D: | 13.2''Lincoln |  | SW-D
| eMMC | 64G | 64G | 64G |  | 64G | 64G | 64G | 64G |  | 64G | 64G | 64G | 64G
| ECG | 1.3 | 1.3 | 1.3 |  | 1.4 | 1.4 | 1.3 | 1.5 | 1.4 | ECG2 | ECG2 | ECG2 | ECG2
| SW variant-updated | SW-A1 | SW-B1 | SW-C | SW-A1 | SW-A2 | SW-D | SW-B2 | SW-E |  | SW-A3 | SW-B3 | SW-A4 | SW-E2
| iACC: open item:; SW-C OPT: software variants increase; SW-B OPT: software variants increase; SW-E OPT: software variants increase |  |  | CD542 base |  | CD764 base | SW-E: | 27''Lincoln | SW-E1 | SW-E2
| iACC: HW variant | [5 empty] | SW-F: | 13.2" Mustang |  | SW-F
iACC take rate | SW-C OPT: 100%; SW-B OPT: 39%; SW-E OPT: 35%
| Theme | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 |  | 3 | 3 | 1 | 3
|  | CD542 | CX727 | U725 | P702 | U554MCA | U625ICA | CD764 | CDX706 |  | S650 | CX483MCA
| SDM function | Y | Y | Y | Y | Y | Y | Y | Y
| SDM hard switch | N | N | Y | Y | Y | Y | Y | Y_13.2
| SDM soft switch | Y | Y | N | N | N | N | N | Y
| Theme change based on SDM mode | N | Y | N | N | N | N | LINK (optional) +ambinent lighting | N
| Theme change based on HMI menu selection | Y | N | Y | Y | Y | Y | Y | Y |  | 一套主题
| HMI mis-match with Cluster | 仪表和中控之间主题联动 | Not issue | C/O phase 2 design | C/O phase 2 design | C/O phase 2 design | 仪表和中控之间主题联动 | 仪表和中控之间主题联动
| Mode detail | 3 modes – eco, normal, sport | 4 modes – normal, sport, eco-comfort, Track mode (GT variant ONLY) | 8 modes – normal, sport, eco, Low Mu Mode 湿滑模式, Mud/Rute Mode, Sand Mode, Rock Crawl Mode, Baja Mode (Repter variant ONLY) | 10 modes – normal, sport, eco, Low Mu Mode 湿滑模式, Tow Haul Mode, Mud/Rute Mode, Sand Mode, Rock Crawl Mode, Rough Road mode, Baja Mode (Repter variant ONLY) | 8 modes – sport, eco, low mu mode, mud/rute mode, sand mode, normal 2H mode, normal 4A mode, normal 4L mode | 7 modes – normal, sport, eco, low mu mode, tow haul mode, sand mode, rough road mode
| Program | Job1 Date | Screen size | ADAS ECU/PAM | Channel | feature | Hard switch? | Camera | Note | IVI SPSS | D&R
| S650 |  | 13.2 | ? | ? | ? | / | RVC | Standalone RVC Digital Camera (1280X800) | Digital RVC SPSS v1.4 April 26, 2019 I2C Over LVDS Com Protocol for Camera SPSS v1.0 Jun 2, 2017 | Ren Qingying
| CD706 |  | 13.2 | FHEV SPORT 5P ST line Low |  | RBA |  | RVC | Standalone RVC Digital Camera (1280X800) | Digital RVC SPSS v1.4 April 26, 2019 I2C Over LVDS Com Protocol for Camera SPSS v1.0 Jun 2, 2017 | Li,YiFan
| CD706 |  | 27 | FHEV SPORT 5P ST line Low |  | RBA | Hotkey? | RVC | Standalone RVC Digital Camera (1280X800) | Digital RVC SPSS v1.4 April 26, 2019 I2C Over LVDS Com Protocol for Camera SPSS v1.0 Jun 2, 2017 | Li,YiFan
| SW-C OPT: ADAS ECU; SW-A Y: RPA+FPA; SW-D Y: Hotkey; SW-B OPT: RVC; SW-E OPT: Standalone RVC Digital Camera (1280X800) | Digital RVC SPSS v1.4 April 26, 2019 I2C Over LVDS Com Protocol for Camera SPSS v1.0 Jun 2, 2017 | Li,YiFan
| SW-C OPT: ADAS ECU; SW-A Y: RPA+FPA+FAPA; SW-D Y: Hotkey; SW-B OPT: 360; SW-E OPT: Titanium Digital Camera (1280X800) | Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx | Li,YiFan
| CX483MCA |  | 27 | PAM |  | RPA | Hotkey? | RVC | Standalone RVC Digital Camera (1280X800) | Digital RVC SPSS v1.4 April 26, 2019 I2C Over LVDS Com Protocol for Camera SPSS v1.0 Jun 2, 2017 | Cui Wei
| SW-C OPT: ADAS ECU; SW-A Y: RPA+FPA; SW-D Y: Hotkey; SW-B OPT: 360; SW-E OPT: 102A(optional),103A Digital Camera (1280X800) | Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx | Cui Wei
| SW-C OPT: ADAS ECU; SW-A Y: RPA+FPA+FAPA; SW-D Y: Hotkey; SW-B OPT: 360; SW-E OPT: 102A(optional),103A Digital Camera (1280X800) | Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx | Cui Wei
| P702 | 2021-04-05 | Landscape 12.3 | ADAS ECU -C Level | 4 | RPA | Hotkey | non-camera | 801A Standard |  | Lu,Zaikai
[5 empty] | 8 | RPA+FPA | Hotkey | 360 | 801A optional A
[5 empty] | 12 | RPA+FPA+FAPA | Hotkey | 360 | 801A optional B
| U554MCA | 2021-06-12 | Landscape 13.2 | DAT2.1 ADAS ECU Gen8 APA | 12 | RPA+FPA+FAPA | Hotkey | 360 |  |  | He, Michael
| CX727 | 2021-08-04 | Portrait 15.5 | DAT2.0 ADAS ECU Gen7 APA | 12 | RPA+FPA+FAPA | Hotkey | RVC |  |  | Zhang,Wenguang
360
| CD542 | 2021-08-18 | Landscape 13.2 | N/A | 0 | non-RPA | N/A | RVC | Ambient only |  | Lu,Zaikai
|  |  | Landscape 27 | ADAS ECU | 4 | RPA | no hard switch | RVC
[5 empty] | 8 | RPA+FPA | BPA hard switch with text off and LED indicator. | RVC
[5 empty] | 12 | RPA+FPA+FAPA | hotkey | 360
| U725 | 2021-11-08 | Landscape 12.3 | SA PAM or ADAS ECU??? | 8 | RPA+FPA | BPA hard switch with text off and LED indicator. | 360 |  |  | Lu,Zaikai
| CD764 | 2021-12-24 | Landscape 27 | DAT2.1 ADAS ECU | 4 | RPA | N/A or Hotkey??? | RVC-SA | 100A |  | He, Michael
[5 empty] | 8 | RPA+FPA | Hotkey | RVC-SA | 101A
[8 empty] | RVC-ADAS ECU RVC | 102A
[5 empty] | 12 | RPA+FPA+FAPA | Hotkey | 360 | 103A
| U625ICA | 2022-01-19 | Landscape 27 | SA PAM LU5T-CD, HP sensor | 4 | RPA | N/A or Hotkey??? | RVC |  |  | Zhu,jinpeng
|  |  |  | IPMB | 12 | RPA+FPA+FAPA | Hotkey | 360
| 360 feature相关的摄像头： |  |  |  | RVC feature相关的摄像头：
|  | variant 1. ADAS 360 digital output |  |  |  | variant 4. Analog RVC
|  | variant 2. IPMB 360 digital output |  |  |  | variant 5. ADAS RVC
|  | variant 3. IPMB 360 analog output |  |  |  | variant 6. IPMB RVC
variant 7. Standalone digital RVC – IIC
| Program | Job1 Date | Screen size | PAM | Channel | feature | PA hotkey ¦P¦ | Camera variant | camera说明 |  | IVI SPSS
| P702 | 2021-04-05 | Landscape 12.3 | ADAS ECU -C Level | 4CH | RPA | softbutton only | non-camera
| SW-A N: 8CH; SW-A Y: RPA+FPA; SW-D Y: BPA(OFF) switch; SW-B OPT: Variant 1; SW-E OPT: 4个高清摄像头接到ADAS盒子 |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf
| U554MCA | 2021-06-12 | Landscape 13.2 | DAT2.1 ADAS ECU Gen8 APA | 12CH | RPA+FPA+REPA | Hotkey | Variant 1 | 4个高清摄像头接到ADAS盒子 |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx
| SW-E OPT: [带RBA功能 - warning message, ON/OFF menu] |  | Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf
| CX727 | 2021-08-04 | Portrait 15.5 | DAT2.0 ADAS ECU Gen7 APA | 12CH | RPA+FPA+FAPA | Hotkey | Variant 5 | 广角RVC |  | Open:
| SW-E OPT: （1个高清摄像头连接到ADAS盒子） |  | 1. SPSS用哪份？
2. HMI单独的UE？
Emma: refer to Multi-Camera SPSS
| SW-B OPT: Variant 1; SW-E OPT: 4个高清摄像头接到ADAS盒子 |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf
| CD542 | 2021-08-18 | Landscape 13.2 | N/A | 0CH | non-RPA | N/A | Variant 4 | 模拟摄像头，非高清 |  | Stand-alone Rear View Camera APIM SPSS v2.7 Apr 26, 2019
|  |  | Landscape 27 | ADAS ECU | 4CH | RPA | softbutton only | Variant 4 |  |  | Stand-alone Rear View Camera APIM Imp Guide v2.7 Apr 26, 2019
[5 empty] | 8CH | RPA+FPA | hotkey | Variant 4
| SW-A N: 12CH; SW-A Y: RPA+FPA+FAPA; SW-D Y: hotkey; SW-B OPT: Variant 1; SW-E OPT: 4个高清摄像头接到ADAS盒子 |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf
|  | 2021-11-08 | Landscape 12.3 |  | 4CH | RPA |  | Variant 6 | 1个高清摄像头连接到IPMB盒子 |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf
U725
|  | 2021-11-08 | Landscape 12.3 |  | 8CH | RPA+FPA |  | Variant 2 | 4个高清摄像头接到IPMB盒子 |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf
| CD764 | 2021-12-24 | Landscape 27 | DAT2.1 ADAS ECU | 4CH | RPA | Hotkey | Variant 7 | standalone的高清摄像头 |  | Digital RVC SPSS v1.4 April 26, 2019
| SW-A N: 8CH; SW-A Y: RPA+FPA; SW-B OPT: Variant 7 |  | I2C Over LVDS Com Protocol for Camera SPSS v1.0 Jun 2, 2017
| SW-B OPT: Variant 5; SW-E OPT: 广角RVC |  | Open:
| SW-E OPT: （1个高清摄像头连接到ADAS盒子） |  | 1. SPSS用哪份？
2. HMI单独的UE？
Emma: refer to Multi-Camera SPSS
| SW-A N: 12; SW-A Y: RPA+FPA+FAPA; SW-B OPT: Variant 1; SW-E OPT: 4个高清摄像头接到ADAS盒子 |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx
Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf
| U625ICA | 2022-01-19 | Landscape 27 | SA PAM LU5T-CD, HP sensor | 4CH | RPA | Hotkey | Variant 4 | 模拟摄像头，非高清 |  | Stand-alone Rear View Camera APIM SPSS v2.7 Apr 26, 2019
Stand-alone Rear View Camera APIM Imp Guide v2.7 Apr 26, 2019
| SW-C OPT: IPMB; SW-A N: 12CH; SW-A Y: RPA+FPA+FAPA; SW-B OPT: Variant 6; SW-E OPT: 4个高清摄像头接到IPMB， |  | Multi-Camera Client APIM Imp Guide v1.11 Oct 2, 2019.xlsx
| SW-E OPT: 输出是模拟的 |  | Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.docx
| SW-E OPT: [不带RBA】 |  | Multi-Camera Client APIM SPSS v1.11 Oct 2, 2019.pdf