## About
Created on: | 12 Oct 23 02:49 UTC
Jira Site: | https://ford.atlassian.net
Jira Query: | project in (APIMCIS, APIMCIM) AND issuetype = Bug AND status in (Approval, "In Progress", Monitor, Reopened, Test, "To Do") AND component in ("System Performance", "System Stability") AND labels in (CD542H, CD542H_R12, CD542H_R13, CD542_R09, CD764, cd764, CD764_R11, CD764_R10.3, CD764_R11.HF2, CD764_R11.HF3, CD764_R11.HF4, CD764_R12, "CD764,", U625, u625, U625ICA) order by created DESC

## Your Jira Issues
状态类别 | 密钥 | 已解决 | 摘要 | 组件 | 经办人 | 报告人 | 优先级 | 状态 | 解决方案 | 已创建 | 已更新 | 事务类型 | Category | External Reference ID
待办 | APIMCIS-34031 |  | Phase 4：【必现】【Performance】【CD764】【随心听】R11.HF2版本Launcher显示到音乐首次启动时间较长(实车7.1s,Target_6s) | System Performance | Wenjie Shu | Wenjie Shu | P2 | 待办 |  | 2023-07-20 03:40 | 2023-07-21 00:02 | 缺陷
待办 | APIMCIS-34008 |  | [CD764][1%]monkey test,com.ford.sync.fordcalendar happens ANR. | System Performance | Wenting Huang | lijuan jia | P2 | 待办 |  | 2023-07-18 05:09 | 2023-10-09 22:15 | 缺陷
正在进行 | APIMCIS-34004 |  | [CD764][1%]monkey test,com.desay.setting happens ANR. | System Performance | Kaige Guan | lijuan jia | P2 | Test |  | 2023-07-18 04:40 | 2023-07-20 03:28 | 缺陷
待办 | APIMCIS-33932 |  | CD764场景二账号进程一直消耗cpu资源 | System Performance | LinYuzhang | Huaifu Xue | P2 | 待办 |  | 2023-07-06 03:13 | 2023-07-20 04:56 | 缺陷
待办 | APIMCIS-33928 |  | CD764场景二部分进程cpu资源异常 | System Performance | LinYuzhang | Huaifu Xue | P2 | 待办 |  | 2023-07-05 04:20 | 2023-07-20 05:48 | 缺陷
正在进行 | APIMCIS-33911 |  | CD542H R12 HF2并发场景AR导航资源消耗高于CD542H ICA R07，测试十分钟多出20%cpu资源 | System Performance | LinYuzhang | Huaifu Xue | P2 | Test |  | 2023-06-28 22:23 | 2023-07-16 22:31 | 缺陷
待办 | APIMCIS-33853 |  | [CD542H][Performance]1次ANR in com.baidu.xiaoduos.launcher | System Performance | LinYuzhang | Zhujin Gao | P2 | 待办 |  | 2023-06-20 03:41 | 2023-07-03 02:16 | 缺陷
待办 | APIMCIS-33851 |  | [CD542H][Performance]2次ANR in com.baidu.naviauto | System Performance | LinYuzhang | Zhujin Gao | P2 | 待办 |  | 2023-06-20 03:41 | 2023-07-03 02:19 | 缺陷
待办 | APIMCIS-33850 |  | [CD542H][Performance]1次ANR in com.baidu.iov.dueros.hotel | System Performance | LinYuzhang | Zhujin Gao | P2 | 待办 |  | 2023-06-20 03:41 | 2023-07-03 02:20 | 缺陷
待办 | APIMCIS-33849 |  | [CD542H][Performance]1次CRASH in com.baidu.iov.dueros.hotel | System Performance | Ying Sun | Zhujin Gao | P2 | 待办 |  | 2023-06-20 03:41 | 2023-06-20 23:38 | 缺陷
待办 | APIMCIS-33848 |  | [CD542H][Performance]1次ANR in com.baidu.che.maintenance:remote | System Performance | Ying Sun | Zhujin Gao | P2 | 待办 |  | 2023-06-20 03:41 | 2023-07-16 23:28 | 缺陷
正在进行 | APIMCIS-33847 |  | [CD542H][Performance]1次CRASH in com.baidu.car.radio | System Performance | Zhujin Gao | Zhujin Gao | P2 | 审批 |  | 2023-06-20 03:41 | 2023-09-12 01:47 | 缺陷
正在进行 | APIMCIS-33845 |  | [CD542H][Performance]1次ANR in com.desay_svautomotive.svhvac | System Performance | Zhujin Gao | Zhujin Gao | P2 | 审批 |  | 2023-06-20 03:41 | 2023-09-12 01:48 | 缺陷
正在进行 | APIMCIS-33844 |  | [CD542H][Performance]1次ANR in com.desay.setting | System Performance | Zhujin Gao | Zhujin Gao | P2 | 审批 |  | 2023-06-20 03:41 | 2023-09-12 01:48 | 缺陷
正在进行 | APIMCIS-33843 |  | [CD542H][Performance]Launcher模块卡顿超10s | System Performance | Zhujin Gao | Zhujin Gao | P2 | 审批 |  | 2023-06-20 03:41 | 2023-10-08 03:08 | 缺陷
待办 | APIMCIS-33828 |  | [CD542H][偶现][System Stability]播放QQ音乐时点击车控图标系统自动重启一次 | System Stability |  | Ying Liu | P2 | 待办 |  | 2023-06-19 22:51 | 2023-08-31 04:46 | 缺陷
正在进行 | APIMCIS-33777 |  | [CD764][Performance]13次CRASH in com.ford.sync.surprisemessage | System Performance | Zhujin Gao | Zhujin Gao | P1 | Monitor |  | 2023-06-16 02:01 | 2023-07-23 23:52 | 缺陷
正在进行 | APIMCIS-33733 |  | [CD764][Performance]Monkey中1次CRASH com.baidu.xiaoduos.launcher导致冻屏+分屏黑屏+车模消失 | System Performance | Zhujin Gao | Zhujin Gao | P1 | Monitor |  | 2023-06-14 04:43 | 2023-07-18 21:30 | 缺陷
正在进行 | APIMCIS-33732 |  | [CD764][Performance]Monkey中1次ANR com.android.systemuiscreenshot导致黑屏超5s | System Performance | Zhujin Gao | Zhujin Gao | P1 | Monitor |  | 2023-06-14 04:43 | 2023-07-18 21:31 | 缺陷
正在进行 | APIMCIS-33731 |  | [CD764][Performance]Monkey中1次ANR com.desay.setting导致黑屏超5s | System Performance | Zhujin Gao | Zhujin Gao | P1 | Monitor |  | 2023-06-14 04:43 | 2023-07-18 21:32 | 缺陷
正在进行 | APIMCIS-33730 |  | [CD764][Performance]电影票模块加载时间超30s | System Performance | Zhujin Gao | Zhujin Gao | P1 | Monitor |  | 2023-06-14 04:43 | 2023-07-18 21:32 | 缺陷
正在进行 | APIMCIS-33728 |  | [CD764][Performance]Monkey中1次ANR com.baidu.naviauto导致背景黑屏 | System Performance | Zhujin Gao | Zhujin Gao | P1 | Monitor |  | 2023-06-14 04:43 | 2023-07-11 06:54 | 缺陷
正在进行 | APIMCIS-33726 |  | [CD764][Performance]Monkey中1次ANR in com.baidu.xiaoduos.launcher导致背景黑屏 | System Performance | Zhujin Gao | Zhujin Gao | P1 | Monitor |  | 2023-06-14 04:43 | 2023-07-18 21:33 | 缺陷
待办 | APIMCIS-33700 |  | Phase 4：【必现】【Performance】【CD764】【地图】R11.HF1版本导航搜索框下拉时间较长（实车测试4.8s，Target 1s） | System Performance;百度-地图 | Sun, Ying (Y.) | Wenjie Shu | P1 | 已重新打开 |  | 2023-06-13 22:37 | 2023-08-17 23:18 | 缺陷
正在进行 | APIMCIS-33595 |  | [CD542H][1/15H]monkey test,com.baidu.naviauto:remote happens 1 times anr | System Performance | Wang XiaoLei | Wang XiaoLei | P2 | 审批 |  | 2023-06-06 00:46 | 2023-09-12 01:49 | 缺陷
正在进行 | APIMCIS-33594 |  | [CD542H][1/15H]monkey test,com.ford.sync.codriver happens 1 times crash | System Performance | Qian Yang | Wang XiaoLei | P2 | Test |  | 2023-06-06 00:42 | 2023-08-21 04:46 | 缺陷
正在进行 | APIMCIS-33593 |  | [CD542H][2/15H]monkey test,com.desay.setting happens 2 times crash | System Performance | Wang XiaoLei | Wang XiaoLei | P2 | 审批 |  | 2023-06-05 23:09 | 2023-09-13 04:12 | 缺陷
正在进行 | APIMCIS-33515 |  | [CD542H][1/15H]monkey test,com.desay.picture happens 1 times anr | System Performance | Wang XiaoLei | Wang XiaoLei | P2 | 审批 |  | 2023-05-31 01:38 | 2023-09-12 01:49 | 缺陷
正在进行 | APIMCIS-33514 |  | [CD542H][1/15H]monkey test,com.baidu.iov.dueros.videoplayer happens 1 times anr | System Performance | LinYuzhang | Wang XiaoLei | P2 | Monitor |  | 2023-05-31 01:34 | 2023-09-21 03:58 | 缺陷
正在进行 | APIMCIS-33447 |  | [CD542_H][100%]power on start settings test result is not up to standard. | System Performance | Huaifu Xue | Wang XiaoLei | P2 | Monitor |  | 2023-05-24 01:53 | 2023-08-29 04:07 | 缺陷
正在进行 | APIMCIS-33386 |  | 【CD542H】【售后2】[logmanager][logic][黑屏log打印机制] | System Performance | Tang Manman | Sen Shi | P1 | Monitor |  | 2023-05-16 07:39 | 2023-06-21 02:43 | 缺陷
正在进行 | APIMCIS-33252 |  | Phase 4：【必现】【Performance】【CD542H】【Launcher】Power on Launcher界面可见耗时较长，且较R11有所回退（R12_25.2s;R11_22.6;Target_22.5s) | System Performance | Leo Jiang | Zhichao Zhang | P2 | Monitor |  | 2023-04-03 04:37 | 2023-09-05 22:05 | 缺陷
正在进行 | APIMCIS-33225 |  | [CD764][100%]The idle CPU is too low in the road test. | System Performance;百度-地图 | lijuan jia | lijuan jia | P1 | 审批 |  | 2023-03-24 08:43 | 2023-08-22 23:13 | 缺陷
正在进行 | APIMCIS-33218 |  | [CD764][100%]In scenario 3, the display of V2I is inconsistent between the instrument and the IVI during the test. | System Performance;V2I | Kaige Guan | lijuan jia | P1 | 审批 |  | 2023-03-23 03:11 | 2023-10-10 08:03 | 缺陷
正在进行 | APIMCIS-33178 |  | Phase 4：【Performance】【CD764】外卖冷启动时间较长(实车测试8.1s，Target 4.6s） | System Performance | Wenjie Shu | Wenjie Shu | P2 | 审批 |  | 2023-03-19 22:21 | 2023-07-19 05:08 | 缺陷
正在进行 | APIMCIS-33177 |  | Phase 4：【Performance】【CD764】电影票冷启动时间较长(实车测试6.8s，Target 4.6s） | System Performance | Wenjie Shu | Wenjie Shu | P2 | 审批 |  | 2023-03-19 22:19 | 2023-07-19 05:08 | 缺陷
正在进行 | APIMCIS-33108 |  | Phase 4：【Performance】【CD764】【CPU】路试过程中进程存在高CPU占用，导致系统可用不足(Target：剩余>60%，实际47%） | System Performance | Kaige Guan | Wenjie Shu | P1 | Monitor |  | 2023-03-12 23:11 | 2023-07-21 02:54 | 缺陷
正在进行 | APIMCIS-33056 |  | [CD764][Performance]1次ANR in com.ford.sync.vpa | System Performance | LinYuzhang | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:34 | 缺陷
正在进行 | APIMCIS-33055 |  | [CD764][Performance]4次CRASH in com.ford.sync.surprisemessage | System Performance | Zhujin Gao | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:35 | 缺陷
正在进行 | APIMCIS-33054 |  | [CD764][Performance]1次ANR in com.ford.sync.guestmode | System Performance | Yun Li | Zhujin Gao | P2 | Test |  | 2023-03-06 03:17 | 2023-07-18 21:13 | 缺陷
正在进行 | APIMCIS-33053 |  | [CD764][Performance]1次ANR in com.ford.sync.fordcalendar | System Performance | LinYuzhang | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:35 | 缺陷
正在进行 | APIMCIS-33051 |  | [CD764][Performance]1次ANR in com.baidu.xiaoduos.messageserver | System Performance | LinYuzhang | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:36 | 缺陷
正在进行 | APIMCIS-33049 |  | [CD764][Performance]3次ANR in com.baidu.naviauto | System Performance | LinYuzhang | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:37 | 缺陷
正在进行 | APIMCIS-33048 |  | [CD764][Performance]1次ANR in com.baidu.iov.faceos | System Performance | LinYuzhang | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:38 | 缺陷
正在进行 | APIMCIS-33046 |  | [CD764][Performance]1次ANR in com.baidu.car.input | System Performance | LinYuzhang | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:39 | 缺陷
正在进行 | APIMCIS-33045 |  | [CD764][Performance]1次ANR in com.desay.calmScreen | System Performance | LinYuzhang | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:40 | 缺陷
正在进行 | APIMCIS-33044 |  | [CD764][Performance]1次ANR in com.desaysv.mediaplayer | System Performance | LinYuzhang | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:41 | 缺陷
正在进行 | APIMCIS-33042 |  | [CD764][Performance]3次ANR in com.desay.setting | System Performance | Zhujin Gao | Zhujin Gao | P2 | Monitor |  | 2023-03-06 03:17 | 2023-07-18 21:41 | 缺陷
正在进行 | APIMCIM-17872 |  | Phase 5【AutoTest】Monkey测试期间，出现包名为 com.baidu.car.radio2 的 crash异常 | Radio;System Stability | Zihao Qiu | Ying Xiao | P2 | 审批 |  | 2023-02-10 01:38 | 2023-09-11 05:36 | 缺陷
正在进行 | APIMCIM-17861 |  | Phase 5【AutoTest】Monkey测试期间，出现包名为 com.baidu.car.radio 的crash异常 | System Stability | Zihao Qiu | Ying Xiao | P2 | 审批 |  | 2023-02-10 00:56 | 2023-09-11 05:39 | 缺陷
正在进行 | APIMCIM-17859 |  | Phase 5【AutoTest】Monkey测试期间，出现包名为 com.android.systemui 的crash异常 | System Stability;System UI | Zihao Qiu | Ying Xiao | P2 | 审批 |  | 2023-02-10 00:46 | 2023-09-11 05:40 | 缺陷
待办 | APIMCIM-17845 |  | Phase 5【AutoTest】Monkey测试期间，出现包名为 com.ford.sync.electronicmanual 的crash异常 | System Stability | chunbo Yang | Ying Xiao | P2 | 待办 |  | 2023-02-09 21:19 | 2023-08-22 04:57 | 缺陷
正在进行 | APIMCIS-32806 |  | [CD542H][2/15H]monkey test,com.baidu.iov.dueros.hotel happens 2 times crash | System Stability | Wang XiaoLei | Wang XiaoLei | P2 | 审批 |  | 2023-02-03 00:45 | 2023-09-05 07:26 | 缺陷
正在进行 | APIMCIS-32804 |  | [CD542H][10/15H]monkey test,com.baidu.xiaoduos.launcher happens 10 times crash | System Stability | Wang XiaoLei | Wang XiaoLei | P2 | Test |  | 2023-02-03 00:14 | 2023-08-21 02:59 | 缺陷
正在进行 | APIMCIS-32131 |  | 【CD764&CX483MCA】【必现】【性能】Launcher的滑动速度明显低于Setting | System Performance | LinYuzhang | Xuliang Qi | P2 | Monitor |  | 2022-10-31 01:46 | 2023-08-17 23:57 | 缺陷
正在进行 | APIMCIS-32130 |  | 【CD764】【必现】【Setting】Setting中有两个页面可以向左滑出一个空白窗口 | System Performance | Kaige Guan | Xuliang Qi | P0 | Monitor |  | 2022-10-31 01:45 | 2023-07-13 22:45 | 缺陷
正在进行 | APIMCIS-32122 |  | [U625ICA][Performance][Stability]monkey test,5 hours later,monkey has no inject,monkey process still running | System Performance | Wang XiaoLei | Lu Lu Wang | P0 | Monitor |  | 2022-10-27 00:51 | 2022-12-08 04:11 | 缺陷
待办 | APIMCIS-32105 |  | [U625ICA][Performance]1次ANR in com.baidu.iov.faceos | System Performance | Sun, Ying (Y.) | Zhujin Gao | P2 | 待办 |  | 2022-10-25 22:25 | 2023-07-11 03:20 | 缺陷
正在进行 | APIMCIS-31497 |  | 【CD764】com.baidu.iov.dueros.videoplayer、com.baidu.bodyguard crash | System Performance | Mao, Yuyan (Y.) | Xu, Lidi (L.) | P0 | Monitor |  | 2022-08-18 05:40 | 2023-07-18 22:06 | 缺陷
正在进行 | APIMCIS-31467 |  | 【CD764】【偶现】【system performance】车机发生自动重启，开机动画跳闪 | System Performance | Kaige Guan | Zijia Shi | P1 | Monitor |  | 2022-08-16 21:06 | 2023-07-09 23:02 | 缺陷
正在进行 | APIMCIS-31452 |  | [U625ICA][1/15h] monkey test,com.baidu.che.parking have suspected happened memory leak | System Performance | Mao, Yuyan (Y.) | lijuan jia | P0 | 审批 |  | 2022-08-16 02:53 | 2023-08-30 04:44 | 缺陷
正在进行 | APIMCIS-31451 |  | [U625ICA][1/15h] monkey test，Ford processes have happened anr | System Performance | Kaige Guan | Wang XiaoLei | P0 | Test |  | 2022-08-16 02:46 | 2023-09-07 00:37 | 缺陷
正在进行 | APIMCIS-31450 |  | [U625ICA][1/15h] monkey test,Desay processes have happened anr | System Performance | lijuan jia | lijuan jia | P0 | Test |  | 2022-08-16 02:42 | 2023-07-20 01:02 | 缺陷
正在进行 | APIMCIS-31449 |  | [U625ICA][1/15H] monkey test,Baidu processes have happened anr | System Performance | Sun, Ying (Y.) | lijuan jia | P0 | Test |  | 2022-08-16 02:39 | 2023-08-30 04:15 | 缺陷
正在进行 | APIMCIS-31457 |  | [U625ICA][1/15h] monkey test,Ford processes have happened crash | System Performance | Hailang Liu | lijuan jia | P2 | Test |  | 2022-08-16 02:31 | 2023-09-11 03:26 | 缺陷
正在进行 | APIMCIS-31446 |  | [U625ICA][1/15H] monkey test,desay process have happened once crash | System Performance | lijuan jia | lijuan jia | P2 | 审批 |  | 2022-08-16 02:23 | 2023-07-20 01:06 | 缺陷
正在进行 | APIMCIS-31447 |  | [U625ICA][2/15H] monkey test,Baidu processes have happened crash | System Performance | Mao, Yuyan (Y.) | lijuan jia | P2 | Test |  | 2022-08-16 02:17 | 2023-07-24 21:29 | 缺陷
正在进行 | APIMCIS-31448 |  | [U625ICA][1/15H] monkey test, system happened reboot | System Performance | lijuan jia | Wang XiaoLei | P0 | Monitor |  | 2022-08-16 01:39 | 2023-07-20 01:26 | 缺陷
正在进行 | APIMCIS-31428 |  | Phase4_【CD542H】【Performance】【随心看】【必现】R11版本随心看冷启动性能测试结果不及预期(随心看冷启动时间_7.41s_偏差196%） | System Performance | Chen Wang | Zhichao Zhang | P2 | 审批 |  | 2022-08-15 01:33 | 2023-06-20 23:40 | 缺陷
待办 | APIMCIS-31426 |  | Phase4_【CD542H】【Performance】【QQ音乐】【必现】R11版本qq音乐性能测试结果不及预期(power on qq音乐启动_5.89s_偏差47%；power on qq音乐选择歌曲_3.10s_偏差107%；系统稳定状态下qq音乐首次启动_3.81s_偏差91%；系统稳定状态下qq音乐选择歌曲_2.10s_偏差110%） | Media;System Performance | Sun, Ying (Y.) | Zhichao Zhang | P2 | 待办 |  | 2022-08-15 01:24 | 2023-06-20 23:31 | 缺陷
待办 | APIMCIS-31339 |  | [U625ICA][Performance]4次ANR in com.baidu.bodyguard | System Performance | Ying Sun | Zhujin Gao | P2 | 待办 |  | 2022-08-10 02:36 | 2023-01-04 03:33 | 缺陷
正在进行 | APIMCIS-31329 |  | 【CD764】【Performance】R10版本monkey测试launcher一直Crash | System Performance | Mao, Yuyan (Y.) | Kaige Guan | P0 | Monitor |  | 2022-08-09 21:32 | 2023-07-18 22:07 | 缺陷
正在进行 | APIMCIS-31197 |  | 【U625ICA】【Performance】Monkey test 中导航一直Crash | System Performance | Mao, Yuyan (Y.) | Kaige Guan | P0 | 审批 |  | 2022-08-01 02:33 | 2023-09-04 08:31 | 缺陷
正在进行 | APIMCIS-31067 |  | [CD764][1%]IVI crash during network compress testing | System Performance;System Stability;Wireless Interface Router | mingguang shang | Zhang zhen | P0 | Monitor |  | 2022-07-19 22:08 | 2023-07-24 09:01 | 缺陷
正在进行 | APIMCIS-29031 |  | 【CD764】【偶发】IVI睡眠后，QQ音乐音源大概率不记忆恢复 | System Performance | Kaige Guan | Kaige Guan | P1 | Monitor |  | 2022-04-08 04:03 | 2023-07-03 23:07 | 缺陷
正在进行 | APIMCIS-27711 |  | Phase4 CD542H 大屏：中央大屏，副屏，QQ音乐，设置，主屏从主界面到自由秘境界面 | System Performance | Ma, Bin (B.) [X] | Ma, Bin (B.) [X] | P0 | 审批 |  | 2022-02-15 09:42 | 2022-04-12 03:28 | 缺陷
正在进行 | APIMCIS-27531 |  | Phase4 U625 点击紧急救援和系统更新下的说明时，无法通过点击空白处退出说明。其他功能说明可以 | System Performance | Shen, Siyu (S.) [X] | Shen, Siyu (S.) [X] | P0 | 审批 |  | 2022-02-10 01:57 | 2023-08-02 04:55 | 缺陷
正在进行 | APIMCIS-26987 |  | [P702][Performace]CRASH: com.desaysv.svadapter | System Performance | Kaige Guan | Zhujin Gao | P2 | Monitor |  | 2022-01-21 05:30 | 2023-06-05 23:15 | 缺陷
正在进行 | APIMCIS-10495 |  | 【必现】【性能】【CD542H】优化com.baidu.che.codriver性能 | System Performance;百度-语音 | Xuliang Qi | Xuliang Qi | P0 | 审批 |  | 2021-06-05 07:27 | 2022-06-25 06:09 | 缺陷