## 测试报告
一、测试报告总论
1.质量标准基础指标达成情况：
基础质量 | 指标项 | 通过标准 | 实测结果 | 测试结论
功能完备度 | 提测需求项/计划交付项 | 100% | 100% | PASS
存量BUG | P0/P1 BUG数量 | 无P0/P1 BUG | P0 1个，P1 15个 | FAIL
| ALL | 未修复BUG数量<50个 | 46 | PASS
2.版本稳定性及性能指标达成情况：
稳定性及性能 | 指标项 | 通过标准 | 实测结果 | 测试结论
版本稳定性 | Monkey | 7*12无crash、无ANR | 地图出现1次crash | FAIL
3.质量标准效果类指标达成情况
AI能力 | 指标项 | 通过标准 | 实测结果 | 测试结论
4、流程质量符合情况：功能清单、产品指标、MRD、技术文档、单云测试、CodeReview各环节交付物是否缺失及评审是否通过情况概述
流程环节 | 通过情况
功能清单 | 评审通过
产品指标 | 缺失
MRD | 评审通过
技术文档 | 缺失
单元测试报告 | 缺失
Codereview结论 | 评审通过
二、Bug解决情况
icafe未解决46个（其中P0 1个，P1 13个）
Jira未解决67个（其中IG 4个，Gating 28个）
三、版本已知风险/遗留问题
1.严重问题
【台架】【CX727ICA 8155】【随心听】【必现】播放USB音乐时拔U盘没有恢复上个音源播放
【实车】【CX727ICA 8155】【智慧停车场】【必现】打开智慧停车场，显示绑定失败后，联系客服直接返回主界面
【台架】【CX727ICA 8155】【随心听】【必现】重启车机，USB音乐lastsource不能恢复播放
【台架】【CX727ICA 8155】【随心听】【必现】车机插入两个U盘，不能识别第二个U盘的歌曲
【台架】【CX727ICA 8155】【随心听】【必现】从蓝牙音源、FM页面切换至随心听、USB、在线收音机页面，播放列表被清空（playbar显示未在播放）
【台架】【CX727ICA 8155】【地图】【偶现】monkey crash java.lang.IllegalArgumentException: Invalid stream type 11
【台架】【CX727ICA 8155】【车家互联】【必现】语音『发现设备』，返回结果不正确
2.项目风险（阻塞项、进度风险、功能需求未实现、质量风险、依赖实车、依赖环境、成熟度/通过率低的原因）
激活模块（1）因安全双向验证未联调，激活失败，阻塞75条用例执行
图像模块（1）实车无人脸环境，阻塞356条用例执行
车家互联模块（1） 云端服务连接失败，阻塞17条用例执行
EM模块（1） 无测试环境，阻塞3条用例执行
地图模块（1）台架测试，定位和导航部分未进行实车测试，阻塞77条用例执行
四、测试用例执行情况及遗留bug数
模块名称 |  |  | 用例总数 | 测试执行数 | 测试执行率 | 执行通过数 | 执行通过率 (执行成功数/测试执行数） | DCV1.ENG4版本成熟度 | 未测/漏测原因和分析
EV |  |  | 224 | 224 | 100% | 222 | 99.11% | 99.11%
账号&支付&个人中心 |  |  | 316 | 316 | 100% | 314 | 99.37% | 99.37%
地图 |  |  | 968 | 891 | 92.05% | 885 | 99.33% | 91.43% | 1.台架测试，定位和导航部分未进行实车测试
随心看 |  |  | 94 | 94 | 100% | 91 | 96.81% | 96.81%
车家互联 |  |  | 42 | 25 | 59.52% | 23 | 92% | 54.76% | 1.云端服务连接失败，目前已经修复，计划17号重新验证
launcher+AAR |  |  | 162 | 162 | 100% | 160 | 98.77% | 98.77%
激活 |  |  | 76 | 1 | 1.316% | 0 | 0% | 0% | 1.因安全双向验证未联调，激活失败，计划DCV1 ENG PRO版本组入
语音 |  |  | 1196 | 1196 | 100% | 1182 | 98.83% | 98.83%
消息中心 |  |  | 94 | 94 | 100% | 94 | 100% | 100%
随心听 |  |  | 303 | 303 | 100% | 293 | 96.7% | 96.7%
安全 |  |  | 63 | 63 | 100% | 60 | 95.24% | 95.24%
图像 |  |  | 356 | 0 | 0% | 0 | 0% | 0% | 实车无人脸环境阻塞测试，计划17号更新测试报告
EM+RS |  |  | 152 | 149 | 98.03% | 148 | 99.33% | 97.37% | 1.无测试环境
输入法 |  |  | 50 | 50 | 100% | 50 | 100% | 100%
电影票 |  |  | 46 | 46 | 100% | 45 | 97.83% | 97.83%
智慧停车场 |  |  | 24 | 24 | 100% | 23 | 95.83% | 95.83%
酒店 |  |  | 57 | 57 | 100% | 57 | 100% | 100%
外卖 |  |  | 196 | 196 | 100% | 195 | 99.49% | 99.49%
项目整体测试覆盖率 |  |  | 全部模块用例总执行数/全部模块用例总数=88% |  |  | 执行通过率(执行成功数/测试执行数）=99% |  | 总体成熟度(执行成功数/用例总数）=87%
六、测试环境及版本说明
SOC版本 |  |  | 20221110_0010_LF15_DCV1.ENG
MCU版本 |  |  | 20221105_015_PRO
屏幕尺寸 |  |  | 15.5

## icafe遗留buglist
编号 | 标题 | 类型 | 流程状态 | 负责人 | 创建时间 | 所属模块 | 优先级 | 修复版本
FordPhase4Scrum-35768 | 【台架】【CX727ICA 8155】【随心听】【必现】从USB页面切到在线收音机，提示播放失败 | Bug | 新建 | 袁洪烈(yuanhonglie) | 2022-10-13 14:39 | 随心听 | P2-Middle
FordPhase4Scrum-35789 | 【台架】【CX727ICA 8155】【电影票】【必现】未开启授权时，点击确认选座按钮没有弹出授权弹窗 | Bug | 新建 | 王杰(v_wangjie16) | 2022-10-13 17:19 | 电影票 | P2-Middle
FordPhase4Scrum-35955 | 【实车】【CX727ICA 8155】【语音】【必现】点击对话流的帮助按钮，直接关闭了对话流 | Bug | 新建 | 马龙(malong03) | 2022-10-13 20:00 | 语音 | P2-Middle
FordPhase4Scrum-37183 | 【台架】【CX727ICA 8155】【随心听】【必现】USB音乐，本地搜索结果，歌名和歌手较长时会重叠 | Bug | 新建 | 袁洪烈(yuanhonglie) | 2022-10-19 15:49 | 随心听 | P2-Middle
FordPhase4Scrum-37199 | 【台架】【CX727ICA 8155】【随心听】【必现】在线收音机首页、在线收音机搜索页面，点击输入框左侧的放大镜图标是搜索按钮 | Bug | 新建 | 袁洪烈(yuanhonglie) | 2022-10-19 17:20 | 随心听 | P2-Middle
FordPhase4Scrum-37283 | 【台架】【CX727ICA 8155】【随心听】【必现】从USB切到随心听，不能恢复随心听播放 | Bug | 新建 | 袁洪烈(yuanhonglie) | 2022-10-20 15:09 | 随心听 | P2-Middle
FordPhase4Scrum-37902 | 【实车】【CX727ICA-8155】【图像】【必现】未注册人脸点击打开Face ID开关，未弹出引导弹窗引导用户注册 | Bug | 新建 | 王二松(v_wangersong) | 2022-10-25 11:48 | 图像 | P2-Middle
FordPhase4Scrum-37903 | 【实车】【CX727ICA-8155】【图像】【必现】已注册过Face ID信息，长按IVI power键重启后，系统未调起人脸识别 | Bug | 新建 | 王二松(v_wangersong) | 2022-10-25 11:58 | 图像 | P2-Middle
FordPhase4Scrum-37898 | 【台架】【7278155】【地图】【必现】语音导航到附近加油站失败 | Bug | 新建 | 李安敏(lianmin) | 2022-10-25 11:12 | 地图 | P1-High
FordPhase4Scrum-39604 | 【台架】【CX727ICA 8155】【安全】【必现】删除1000_USRCERT_bidu_https+^global文件，重新导入证书失败 | Bug | 已分析 | 毛宇航(maoyuhang) | 2022-11-08 19:23 | 安全 | P2-Middle
FordPhase4Scrum-39582 | 【台架】【CX727ica 8155】【安全】【必现】U盘导入证书失败 | Bug | 已分析 | 毛宇航(maoyuhang) | 2022-11-08 17:33 | 安全 | P1-High
FordPhase4Scrum-40085 | 【台架】【CX727ica_8155】【安全】【必现】安全日志目录及下级文件权限不对 | Bug | 新建 | 赵亚军(v_zhaoyajun) | 2022-11-11 15:15 | 安全 | P2-Middle
FordPhase4Scrum-40220 | 【实车】【727-8155】【账号】【必现】未登录账号，开机启动 账号二维码未加载出来 | Bug | 新建 | 贾卫卫(jiaweiwei),杨旺(v_yangwang) | 2022-11-14 10:33 | 账号支付 | P2-Middle
FordPhase4Scrum-39965 | 【台架】【CX727ICA8155】【车家互联】【必现】语音『发现设备』，返回结果不正确 | Bug | 新建 | 王杰(v_wangjie16) | 2022-11-10 18:46 | 车家互联 | P1-High
FordPhase4Scrum-40298 | 【台架】【727-8155】【地图】【必现】离线下载U盘提示错误 | Bug | 新建 | 胡金广(hujinguang) | 2022-11-14 16:38 | 地图 | P2-Middle
FordPhase4Scrum-40294 | 【台架】【727-8155】【地图】【必现】离线下载取消按钮热区问题 | Bug | 新建 | 胡金广(hujinguang) | 2022-11-14 16:30 | 地图 | P2-Middle
FordPhase4Scrum-40222 | 【台架】【CX727ICA 8155】【随心听】【偶现】adb reboot命令重启车机，偶现重启之后自动退出QQ音乐帐号 | Bug | 新建 | 徐俊兵(v_xujunbing) | 2022-11-14 10:58 | 随心听 | P1-High
FordPhase4Scrum-40356 | 【实车】【8155 CX727IAC】【EM】【必现】语音设置不随着个性化档案变化而变化 | Bug | 新建 | 宋龙(songlong),王锦鹏(v_wangjinpeng01) | 2022-11-15 14:10 | EM | P2-Middle
FordPhase4Scrum-40366 | 【台架】【CX727ICA 8155】【随心听】【必现】USB页面，显示U盘名称与在电脑中显示U盘实际名称不一致 | Bug | 新建 | 袁洪烈(yuanhonglie) | 2022-11-15 14:56 | 随心听 | P2-Middle
FordPhase4Scrum-40423 | 【实车】【cx727-8155】【外卖】【必现】搜索框默认记录20条，实际显示6条 | Bug | 新建 | 王杰(v_wangjie16) | 2022-11-15 17:00 | 外卖 | P2-Middle
FordPhase4Scrum-40422 | 【实车】【CX727-8155】【账号】【必现】客户端更新账号头像，个人中心未更新 | Bug | 新建 | 贾卫卫(jiaweiwei),杨旺(v_yangwang),方月龙(v_fangyuelong) | 2022-11-15 16:58 | 账号支付 | P2-Middle
FordPhase4Scrum-40426 | 【实车】【cx727-8155】【电影票】【偶现】打开定位权限，点击电影票模块，进入后定位成功仍提示定位失败 | Bug | 新建 | 王杰(v_wangjie16) | 2022-11-15 17:21 | 电影票 | P2-Middle
FordPhase4Scrum-40441 | 【实车】【8155 CX727ICA】【EV】【偶现】按时出发时间添加失败，且按时出发时间列表依然会出现保存失败的时间 | Bug | 新建 | 宋龙(songlong),王锦鹏(v_wangjinpeng01) | 2022-11-15 18:18 | EV | P2-Middle
FordPhase4Scrum-40447 | 【实车】【8155 727ICA】【EV】【必现】续航里程和系统设置不一致 | Bug | 新建 | 宋龙(songlong),王锦鹏(v_wangjinpeng01) | 2022-11-15 19:51 | EV | P2-Middle
FordPhase4Scrum-40449 | 【实车】【8155 CX727ICA】【EV】【必现】按时出发infobook展示不完全 | Bug | 新建 | 宋龙(songlong),王锦鹏(v_wangjinpeng01) | 2022-11-15 19:58 | EV | P2-Middle
FordPhase4Scrum-40360 | 【实车】【8155 CX727ICA】【EM】【必现】个性化档案infobook 文字排版没有对齐 | Bug | 新建 | 王锦鹏(v_wangjinpeng01),宋龙(songlong) | 2022-11-15 14:22 | EM | P2-Middle
FordPhase4Scrum-40453 | 【实车】【8155 727】【launcher】【必现】禁用状态下重启车机，状态是禁用，歌曲是播放状态 | Bug | 新建 | 黄辉平(huanghuiping) | 2022-11-15 21:42 | Launcher&AAR | P2-Middle
FordPhase4Scrum-40459 | 【实车】【8155 727】【launcher】【必现】智能馨风详情页底部>250展示不正确 | Bug | 新建 | 黄辉平(huanghuiping) | 2022-11-15 22:56 | Launcher&AAR | P2-Middle
FordPhase4Scrum-40460 | 【实车】【8155 727 】【AAR】【必现】 无网络/弱网，点击详细数据页面刷新按钮，按钮一直旋转停不下来 | Bug | 新建 | 黄辉平(huanghuiping) | 2022-11-15 23:00 | Launcher&AAR | P2-Middle
FordPhase4Scrum-40310 | 【台架】【727-8155】【地图】【偶现】monkey crash java.lang.IllegalArgumentException: Invalid stream type 11 | Bug | 已分析 | 胡金广(hujinguang) | 2022-11-14 18:21 | 地图 | P1-High
FordPhase4Scrum-40285 | 【台架】【727-8155】【地图】【必现】导航设置音量加减按键无效 | Bug | 已分析 | 胡金广(hujinguang) | 2022-11-14 15:43 | 地图 | P2-Middle
FordPhase4Scrum-40466 | 【实车】【8155 CX727ICA】【EV】【必现】开关按钮打开关闭加载颜色与主题不一致 | Bug | 新建 | 王锦鹏(v_wangjinpeng01),宋龙(songlong) | 2022-11-16 10:18 | EV | P2-Middle
FordPhase4Scrum-37185 | 【台架】【CX727ICA 8155】【随心听】【必现】车机插入两个U盘，不能识别第二个U盘的歌曲 | Bug | 已分配 | 袁洪烈(yuanhonglie) | 2022-10-19 16:02 | 随心听 | P1-High
FordPhase4Scrum-40372 | 【台架】【CX727ICA 8155】【随心听】【必现】从蓝牙音源、FM页面切换至随心听、USB、在线收音机页面，播放列表被清空（playbar显示未在播放） | Bug | 新建 | 袁洪烈(yuanhonglie) | 2022-11-15 15:09 | 随心听 | P1-High
FordPhase4Scrum-40416 | 【台架】【CX727ICA 8155】【随心听】【必现】通过发送can信号更换主题，更换后随心听暂停播放 | Bug | 新建 | 袁洪烈(yuanhonglie) | 2022-11-15 16:36 | 随心听 | P1-High
FordPhase4Scrum-40433 | 【实车】【cx727-8155】【智慧停车场】【必现】打开智慧停车场，选择需要去的停车场点击导航，提示百度地图导航失败 | Bug | 新建 | 王杰(v_wangjie16) | 2022-11-15 17:48 | 智慧停车场 | P1-High
FordPhase4Scrum-40439 | 【实车】【cx727-8155】【语音】【必现】主界面语音喊话小度或电马调起失败 | Bug | 新建 | 马龙(malong03) | 2022-11-15 18:02 | 语音 | P1-High
FordPhase4Scrum-40454 | 【实车】【8155 727】【launcher】【必现】蓝牙音乐播放中，切换主题，launcher展示的不是蓝牙音乐播放的歌曲 | Bug | 已分配 | 袁洪烈(yuanhonglie) | 2022-11-15 21:52 | 随心听 | P1-High
FordPhase4Scrum-40451 | 【实车】【8155 727 】【launcher】【必现】qq音乐播放中，更换主题后播放按钮状态，及歌曲内容都不正确 | Bug | 已分配 | 袁洪烈(yuanhonglie) | 2022-11-15 21:34 | 随心听 | P1-High
FordPhase4Scrum-40450 | 【实车】【8155 727】【launcher】【必现】导航中，查看地图大卡片，诱导卡片是灰色 | Bug | 已分配 | 胡金广(hujinguang) | 2022-11-15 21:30 | 地图 | P1-High
FordPhase4Scrum-40319 | 【台架】【727-8155】【地图】【必现】冷启动后消息中心消息启动地图导航失败 | Bug | 已分析 | 胡金广(hujinguang) | 2022-11-14 19:24 | 地图 | P2-Middle
FordPhase4Scrum-40501 | 【台架】【CX727ICA_8155】【安全】【必现】launcher小卡片点击一键优化无反应 | Bug | 新建 | 王志鑫(wangzhixin02) | 2022-11-16 14:35 | 安全 | P2-Middle
FordPhase4Scrum-40306 | 【台架】【727ica 8155】【随心看】【必现】选集页面，语音下一页，提示语字体太小 | Bug | 已分配 | 周王伟(v_zhouwangwei) | 2022-11-14 17:56 | 随心看 | P2-Middle
FordPhase4Scrum-40125 | 【台架】【CX727ICA 8155】【随心听】【必现】重启车机，USB音乐lastsource不能恢复播放 | Bug | 新建 | 徐俊兵(v_xujunbing) | 2022-11-11 17:29 | 随心听 | P0-Highest
FordPhase4Scrum-40389 | 【台架】【CX727ICA 8155】【随心听】【必现】播放USB音乐时拔U盘没有恢复上个音源播放 | Bug | 新建 | 袁洪烈(yuanhonglie) | 2022-11-15 15:36 | 随心听 | P1-High
FordPhase4Scrum-40429 | 【实车】【cx727-8155】【智慧停车场】【必现】打开智慧停车场，显示绑定失败后，联系客服直接返回主界面 | Bug | 新建 | 王杰(v_wangjie16) | 2022-11-15 17:35 | 智慧停车场 | P1-High

## Jira遗留buglist
FORD JIRA
Displaying 67 issues at 16/Nov/22 2:58 AM.
Issue Type | Summary | Reporter | Status | Fix Version/s | Affects Version/s | Assignee | Component/s | Supplier. | Labels | Priority | Key
Bug | Phase4:[EV][Trip Planner] The colour for the POI of charge station along the trip is wrong | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, EV, Phase4_CVPPTst, Trip_Planner, 百度-地图 | High | AW2-9116
Bug | Phase4:[EV][Trip Planner] The charge station along the trip is showed as green but it should showed as red | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, EV, Phase4_CVPPTst, Trip_Planner, 百度-地图 | High | AW2-9112
Bug | Phase4:[EV][100%][home page]Infobook prompt MustangMach-E APP | li, qijian (q.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, EV, EV_Charge_Programming, Phase4_CVPPTst | High | AW2-8989
Bug | [CX727ICA8155][语音][必现]语音“关闭蓝牙音乐”后不返回至Launcher首页 | Ma, tingting (t.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-语音 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8377
Bug | [CX727ICA8155][必现][输入法]可用网络中选择一个网络，未自动弹出输入法 | Fan, Yang (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-百度输入法 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8367
Bug | [CX727ICA8155][必现][输入法]输入“虹桥”没有智能联想到“机场、火车站” | Zhang, Yunrong (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-百度输入法 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITest | High | AW2-8495
Bug | [CX727ICA8155][偶现][百度-随心看]爱奇艺在播放电视剧，点击选集无反应 | Ye, Yunyun (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-随心看 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8499
Bug | [CX727ICA8155][必现][输入法]输入“zhuqingting”未匹配到“竹蜻蜓” | Zhang, Yunrong (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-百度输入法 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITest | High | AW2-8492
Bug | [CX727ICA8155][必现][地图]限行输入车牌后，地图设置页面无法关闭 | Zhang, Yunrong (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-地图 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITest | Gating | AW2-8489
Bug | [CX727ICA8155][随机][百度-随心看]爱奇艺进入搜索界面，点击返回键未进入上一层界面 | Ye, Yunyun (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-随心看 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8498
Bug | Phase4: [CX727ICA_8155][100%]The alert icon not show after select EV tab | liu, baoyan (b.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Vehicle Health Alert | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, Phase4_CVPPTst | High | AW2-8512
Bug | Phase4:[CX727ICA8155] [100%]Launcher voice interface prompt "试试说'你好，福特'" | Chen, Hao (H.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Virtual Personal Assistant | Baidu | APIMCIS_WAVE2, CX727ICA_8155, Phase4_CVPPTst | High | AW2-8448
Bug | [CX727ICA8155][必现]地图]在导航界面使用双指旋转，底图无法响应旋转操作 | Fan, Yang (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-地图 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | Gating | AW2-8627
Bug | [CX727ICA8155][必现]地图]车机无网络时，开始导航，网络不畅界面提示显示异常 | Fan, Yang (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-地图 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8626
Bug | [CX727ICA8155][必现][百度-地图]切换电马账号后地图头像未更新 | Liu, Ying (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-地图 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8976
Bug | [CX727ICA8155][Launcher][必现]Launcher语音界面提示请试试说“你好，福特” | Ma, tingting (t.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-Launcher |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8196
Bug | 【CX727ICA8155】【必现】【launcher】点击更多服务里的应用搜索，会有一个过渡动画 | Ye, Yunyun (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-Launcher |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | Medium | AW2-8769
Bug | 【CX727ICA8155】【偶现】【百度地图】Pow on导航启动点击无反应 | Shu, Wenjie (W.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-地图 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | Gating | AW2-8830
Bug | [CX727ICA8155][必现][地图]导航设置里调节播报音异常 | Zhang, Yunrong (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-地图 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | Gating | AW2-8799
Bug | [CX727ICA8155][地图][必现]恢复默认设置后，点击左上角叉号无法退出设置界面 | Ma, tingting (t.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-地图 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | Gating | AW2-8222
Bug | [CX727ICA8155][必现]地图]进入地图，点击“清空历史记录”，提示无法删除历史记录 | Fan, Yang (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-地图 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | Gating | AW2-8632
Bug | [CX727ICA8155][必现]地图]车机无法接收到小度接人的位置信息 | Fan, Yang (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-地图 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | Gating | AW2-8634
Bug | [CX727ICA8155][必现][百度-随心听]界面显示“正在自动搜索频道”，页面最多可展示17个自动存储电台 | Ye, Yunyun (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-随心听 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8698
Bug | 【CX727ICA 8155】【必现】切换驾驶模式后，lancher/充电页面颜色无改变 | Guan, Kaige (K.) | New |  | LF15_DCV1.ENG1 | Sun, Ying (Y.) |  |  | Baidu, CX727ICA_8155, Desaytest, Wave2 | High | AW2-9034
Bug | Phase4:[EV][100%][Preferred Charge Time] The last number will disappear when the name of preferred charge time is more than 20 symbols | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, EV_Charge_Programming, Phase4_CVPPTst | High | AW2-9190
Bug | Phase4:[CX727ICA_8155][100%]The takeaway shows that the positioning failed | liu, baoyan (b.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | 百度-外卖 | Baidu | APIMCIS_WAVE2, CX727ICA_8155, Phase4_CVPPTst, 百度-外卖 | High | AW2-9536
Bug | Phase4:[CX727ICA8155] [偶现]Cabin fresh air is automatically highlighted and turned on | zhang, xinyuan (z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Auto Air Refresh | Baidu | APIMCIS_WAVE2, CX727ICA_8155, Phase4_CVPPTst | High | AW2-9456
Bug | Phase4:[CX727ICA8155] [必现]The time display is not complete under the history record | zhang, xinyuan (z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Auto Air Refresh | Baidu | APIMCIS_WAVE2, CX727ICA_8155, Phase4_CVPPTst | High | AW2-9219
Bug | Phase4:[EV][100%]All infobook prompts on the charging page slide down | li, qijian (q.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, EV, EV_Charge_Programming, Phase4_CVPPTst | High | AW2-8990
Bug | [CX727ICA8155][必现][百度-随心看]本地视频播放时，选集button与清晰度界面重合 | Ye, Yunyun (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-随心看 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8503
Bug | [CX727ICA8155][必现][百度-随心听]自动搜台时，收藏电台按钮和列表按钮可操作不置灰 | Ye, Yunyun (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) |  |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | High | AW2-8697
Bug | Phase4:[CX727ICA_8155][100%]Voice control feedback error when disconnected from smart home device network | deyuan, Wang (W.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | IOT | Baidu | APIMCIS_WAVE2, CX727ICA_8155, Phase4_CVPPTst | High | AW2-8770
Bug | Phase4:[727ICA_8155][100%]ETCP Navigation Parking Lot Prompts Guidance Failed | liu, baoyan (b.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | 百度-智慧停车场 | Baidu | APIMCIS_WAVE2, APIMCIS_WAVE2,, CX727ICA_8155, DCV1.PRO_Mustfix, ETCP, Phase4_CVPPTst | Gating | AW2-9533
Bug | Phase4:[EV][Station Finder] The station list for around charge station is wrong | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, APIM_CIS, CX727ICA_8155, EV, Phase4_CVPPTst, Station_Finder | Immediate Gating | AW2-8431
Bug | Phase4:[EV][100%]The mileage display on the overview page does not match the settings | li, qijian (q.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, EV, EV_Charge_Programming, Phase4_CVPPTst | Gating | AW2-8995
Bug | Phase4:[EV][100%][Station Finder]Station Finder feature not available | li, qijian (q.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, Phase4_CVPPTst, Station_Finder | Immediate Gating | AW2-9627
Bug | Phase4:[EV][100%][Home Page]The overview page switch status is grayed out under Run status | li, qijian (q.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, EV_Charge_Programming, Phase4_CVPPTst | Gating | AW2-9395
Bug | Phase4:[EV][100%]The battery on the overview page is red and the battery level is 100% | li, qijian (q.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, EV, EV_Charge_Programming, Phase4_CVPPTst | High | AW2-4141
Bug | Phase4:[EV][100%][home page]The charging overview page displays PM | li, qijian (q.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, EV, EV_Charge_Programming, Phase4_CVPPTst | Gating | AW2-8992
Bug | Phase4:[CX727ICA_8155][100%]Movie tickets, hotel location failed | liu, baoyan (b.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-电影票, 百度-酒店 | baidu | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, Phase4_CVPPTst, 百度-酒店 | Gating | AW2-9060
Bug | Phase4:[EV][100%][Trip Planner] 通勤场景，返程电量不足时，弹框提示与设计稿不一致 | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, Phase4_CVPPTst, Trip_Planner | High | AW2-9684
Bug | Phase4:[EV][100%][Trip planner]Prompt box text is missing "目的地" | li, qijian (q.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, Phase4_CVPPTst, Trip_Planner | High | AW2-9657
Bug | Phase4：[EV][Trip Planner]导航中电量不足时的弹框显示错误 | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, Phase4_CVPPTst, Trip_Planner | High | AW2-9718
Bug | Phase4：[EV][Trip Planner]一键添加小于3个充电站途径点时，途径点不显示详情 | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, Phase4_CVPPTst, Trip_Planner | High | AW2-9712
Bug | Phase4:[EV][100%][Preferred Charge Time] The charge window page showed is wrong when the user doesn't choose any charge window | li, qijian (q.) | New | JF15_R07.PRO | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIM_CIS, CX727ICA_8155, EV, EV_Charge_Programming, Phase4_CVPPTst | High | AW2-6162
Bug | Phase4:[727ICA_8155][100%]The ETCP parameter uuid does not exist and does not conform to the specification | liu, baoyan (b.) | Developing |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Payment | Baidu | APIMCIS_WAVE2, APIMCIS_WAVE2,, CX727ICA_8155, DCV1.PRO_Mustfix, ETCP, Phase4_CVPPTst | Gating | AW2-9535
Bug | Phase4:[EV][100%][Trip Planner] 充电偏好的title错误 | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, Phase4_CVPPTst, Trip_Planner | High | AW2-9679
Bug | Phase4:[EV][100%][Preferred Charge Times]Input characters can be saved on preferred charge time name | li, qijian (q.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, EV, EV_Charge_Programming, Phase4_CVPPTst | Gating | AW2-9187
Bug | [Phase4][CX727ICA8155] [VPA][必现]查看图片时，缩略图不会显示，选择查看某个图片时，无法沉浸式查看大图 | Xia, Feixiang (F.) | Developing |  | LF15_DCV1.ENG1 | Sun, Ying (Y.) | Virtual Personal Assistant | Baidu | APIMCIS_WAVE2, CX727ICA_8155, Phase4_CVPPTst, 百度-语义 | High | AW2-9741
Bug | [Phase4][CX727ICA8155] [VPA][必现]POI导航时，查询导航途径充电站后，选择其中一个，播报暂无选项 | Xia, Feixiang (F.) | New |  | LF15_DCV1.ENG1 | Sun, Ying (Y.) | Virtual Personal Assistant | Baidu | APIMCIS_WAVE2, CX727ICA_8155, Phase4_CVPPTst | High | AW2-9732
Bug | [Phase4][CX727ICA8155] [VPA][必现]成语接龙答错时，田字格无变红抖动动画效果提示 | Xia, Feixiang (F.) | New |  | LF15_DCV1.ENG1 | Sun, Ying (Y.) | Virtual Personal Assistant | Baidu | APIMCIS_WAVE2, CX727ICA_8155, Phase4_CVPPTst | High | AW2-9739
Bug | Phase4:[EV][100%]The obvious switching effect of switching to EV page | li, qijian (q.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, EV, EV_Charge_Programming, Phase4_CVPPTst | Gating | AW2-8994
Bug | Phase4：[EV][Trip Planner]添加和删除途径点时，地址栏显示异常 | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, EV, Phase4_CVPPTst, Trip_Planner | Gating | AW2-9686
Bug | Phase4:[EV][Trip Planner] No flitter icon after click charge station icon | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, EV, Phase4_CVPPTst, Trip_Planner, 百度-地图 | Gating | AW2-9119
Bug | Phase4:[EV][Trip Planner] The Map still has pop up when Automatically recommend charging pile is closed | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Electric Vehicle |  | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, EV, Phase4_CVPPTst, Trip_Planner, 百度-地图 | Gating | AW2-9117
Bug | Phase4:[727ICA_8155][10%]ETCP shows that positioning is not enabled | liu, baoyan (b.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | 百度-智慧停车场 | Baidu | APIMCIS_WAVE2, APIMCIS_WAVE2,, CX727ICA_8155, DCV1.PRO_Mustfix, ETCP, Phase4_CVPPTst | Gating | AW2-9532
Bug | Phase4:[CX727ICA_8155][100%]No response to hotel calls | liu, baoyan (b.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-酒店 | baidu | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, Phase4_CVPPTst, 百度-酒店 | Gating | AW2-8757
Bug | Phase4:[CX727ICA_8155][100%]Entering the hotel does not display the service authorization pop-up box | liu, baoyan (b.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-酒店 | baidu | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, Phase4_CVPPTst, 百度-酒店 | Gating | AW2-8699
Bug | Phase4:[CX727ICA_8155]The response speed is too slow after the button is clicked in location service list | Wang, Zhou (Z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | System Performance |  | APIMCIS_WAVE2, CX727ICA_8155, Phase4_CVPPTst | Gating | AW2-8901
Bug | Phase4:[EV][100%]Low battery mileage reminder IVI screen has no prompt and no voice prompt | li, qijian (q.) | New |  | LF15_DCV1.ENG2, LF15_DCV1.ENG3 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, EV, Phase4_CVPPTst, low_range_alert | Gating | AW2-9417
Bug | 【CX727ICA】8155 百度地图在导航或巡航模式均不显示V2I的红绿灯信息 | Zhang, Yuan Yan (Y.) | Developing | LF15_DCV1.PRO | LF15_DCV1.ENG1 | Sun, Ying (Y.) | V2I |  | APIMCIS_WAVE2, Baidu_Map_5.0, CX727ICA_8155, Phase4_CVPPTst | Immediate Gating | AW2-8514
Bug | Phase4:[CX727ICA_8155]The greeting beside the avatar does not match the actual time after IVI restart | Wang, Zhou (Z.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Account | Baidu | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, Phase4_CVPPTst | Gating | AW2-9396
Bug | Phase4：[EV][Trip Planner]已有3个途径点时，有推荐充电站，但是无一键添加按钮 | lu, zhoujie (z.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Electric Vehicle | Baidu | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, EV, Phase4_CVPPTst, Trip_Planner | Gating | AW2-9690
Bug | Phase4:[CX727ICA_8155]Face recognition detects a face other than the current login account. After the account is successfully switched, the text prompts an error | Wang, Zhou (Z.) | New |  | LF15_DCV1.ENG3 | Sun, Ying (Y.) | Account, 百度-图像-FaceID | Baidu | APIMCIS_WAVE2, CX727ICA_8155, DCV1.PRO_Mustfix, Phase4_CVPPTst | Gating | AW2-9675
Bug | Phase4:[CX727ICA_8155][100%]The last 1 km function cannot be realized | liu, baoyan (b.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | Connected Embedded Navigation | Baidu | APIMCIS_WAVE2, APIMCIS_WAVE2,, BEV1.9.0, CX727ICA_8155, Ford_Brand, Phase4_CVPPTst, bd-prcs | Immediate Gating | AW2-9051
Bug | [CX727ICA8155][必现][百度-语音]语音关闭座椅加热无效 | Liu, Ying (Y.) | New |  | LF15_DCV1.ENG2 | Sun, Ying (Y.) | 百度-语音 |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | Gating | AW2-9855
Bug | [CX727ICA8155][必现][EV]大屏提示充电设置冲突 | Liu, Ying (Y.) | New |  | LF15_DCV1.ENG4 | Sun, Ying (Y.) |  |  | APIMCIS_WAVE2, Baidu, CX727ICA_8155, Phase4_IVITst | Gating | AW2-9856
Generated at Wed Nov 16 02:58:18 EST 2022 by Mao, Yuyan (Y.) using Jira 8.13.22#813022-sha1:0bfa32aeac99337fb4121989dd25167b6f869653.