## RL-Revision-History
Release Note Change Record History
Version Number | Release Date | Author & Email | Reviewer & Email | Approver & Email | Content Changes
1 | 2023-12-28 | Zhang Bin | Pang Hongyu | Tian Niu | R06.2

## Release Content
Software Release Information List |  |  |  | 1. 各方需要提供该格式的release note； 2. 集成方需要整合各方的release content，Fixed Bug list Open Bug List 的内容； 3. Release note的内容准确性由各个开发方的PM&SWQ来保证，Ford方的System Integration Manager&SWQ 来检查 4. Release note 版本号： After Integration Completed 1.* After Supplier Test Completed 2.* REC(End To End) Test Completed 3.*
Software Release Information Description
Prepared By |  | Baidu | Reviewed By:
Date |  | 2023-12-28 | Tian Niu
Software Version Information
SOC SW Version
General Info |  | SOC SW P/N
Main board HW Version
MCU SW Version
MCU SW P/N
Checksum
Software Release Content
Release Content | 新增功能
完善功能
| BUG修复 | Launcher修复闪烁问题： AW2-37293 【CX727_8155】【Base Retrofit 8155 Polit OTA】【Display】【偶现】早上homepage 闪屏，无法使用，program屏幕无法打开，设置和CarPlay 界面正常，音乐播放开车都没问题，之前没有碰到过。快速重启电源无法解决，再关闭电源，静止一分钟后启动，问题解决了。 AW2-36970 【CX727_8155】【Base Retrofit 8155 Polit OTA】【Display】【偶现】早上启动时，出现闪屏现象。一直闪，熄火了也闪。直到重启后才恢复。
设计调整
| 遗留问题 | 见Open Bug List
Software Release Conclusion

## Fixed Bug List
Key | Summary | Priority | Fixed Version | Suppliers
AW2-37293 | 【CX727_8155】【Base Retrofit 8155 Polit OTA】【Display】【偶现】早上homepage 闪屏，无法使用，program屏幕无法打开，设置和CarPlay 界面正常，音乐播放开车都没问题，之前没有碰到过。快速重启电源无法解决，再关闭电源，静止一分钟后启动，问题解决了。 | P1 | R06.2 | 百度
AW2-36970 | 【CX727_8155】【Base Retrofit 8155 Polit OTA】【Display】【偶现】早上启动时，出现闪屏现象。一直闪，熄火了也闪。直到重启后才恢复。 | P1 | R06.2 | 百度

## Open Bug List
CIA (Customer Impact Assessment)
Key | Supplier | Summery | Priority | Repeat step | Frequency | Affects Version | Issue Analysis |  |  | ICA | PCA | Planned Fix Version | Data Tagging Analysis | Customer Complain
[7 empty] | Risk assessment （Need FO Confirmation） | XCL Evaluation | Root cause

## Metrics
Process | Proposed KPI | Target / Norm | Operational Definition | Achievement Time | Week/Month | Comments
SWE.1.Software Requirements Analysis | Software Requirements Reviewed Rate % | 100% | Number of approved(reviewed) Software Requirements/ Number of Software Requirements | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.2.Software Architectural Design | SW Architectural to SW Requirement Coverage Rate | 100% | Jira Traceability/Excel Traceability | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.3 Software Detailed Design and Unit Construction | Traceable Software requirements(Jira Story) to the code | 100% | All Jira requirements should have a corresponding software unit in GIT | SOP: All requirement Formal release scope : The requirements planned to be released in this version. |  | Using Traceability From Code to Requirement&Change_Template to show the evidence.
SWE.3 Software Detailed Design and Unit Construction | SW detail design to SW Architectural Coverage | 100% | Jira Traceability/Excel Traceability | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.4 Software Unit Verification | Unit test（Code） coverage | >= 80 % | (Conditions True + Conditions False + Covered Lines)/(2*Conditions + Executable Lines) | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.4 Software Unit Verification | Static Code Analysis Number of Critical Bugs | 0 | Static Code result in Sonar. | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Planned Integration Test cases vs. actual executed integration test cases | 100% | Percentage of SW integration Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Software Integration Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Software Integration Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Software Integration Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | SW architecture design test coverage (HLD with Ready State test cases) | 100% | (Number of HLD SQD have integration test Case + Number of Interface have integration test case)/(Number of HLD SQD + Number of interface) | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.5 Software Integration Test | Count of Software Integration Test defects | 0 | Count of Integration Defects | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Planned Qualification test cases vs. actual executed Qualification test cases | 100% | Percentage of SW Qualification Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | SW requirement test coverage | 100% | Percentage of Requirements in Jira that has corresponding test cases in TestRail | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Software Qualification Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SWE.6 Software Qualification Test | Count of Software Qualification test defects | 0 | Count of Defects raised in the SW Qualification Testing Phase | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.1 Quality Assurance | NC closure rate | 90% | Closed NC/Total NC | Monthly
SUP.1 Quality Assurance | Process Audit compliance | 100% | Percentage of audits completed on time | Monthly
SUP.8 Configuration Management | Nightly builds have a success rate | 100% | Percentage of compliance as defined in the process audit checklist | Every Sprint
SUP.8 Configuration Management | Baseline completed Rate | 100% | Count of of actually baseline CI Item number/ Count of Planned baseline CI item Number | Monthly
SUP.8 Configuration Management | CM Audit Pass rate | 100% | Pass rate of CM Audit Checklist: Count of passed Number in CM Audit Checklist/total planned CM Audit Checklist | Monthly
SUP.9 Problem Resolution Management | Immediate Gating/Gating （Critical） defects for release | 0 | All urgent defects actioned on high priority, | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.9 Problem Resolution Management | Problem closure adherence | 100% | No. of defects closed against no. of defects planned for closure in this release （Include Project deviation issue and Defect） | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.9 Problem Resolution Management | Defect fix time | <40 | Defect fix time | Every Sprint
SUP.9 Problem Resolution Management | Count of IG&G defect @current version | <1 | Count of IG&G defect @current version | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
SUP.10 Change Request Management | Change Request status closure % | 100% | No. of Change Requests completed / Total number of change requests raised in the version | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
MAN.3 Project Management | Requirement Completion Rate for sprint/Milestone | > 85% | No. of requirements delivered / No. of requirements committed for this sprint/Milestone | Every Sprint/Milestone
MAN.3 Project Management | Commitment Adherence for All Requirement | 100% | No. of requirements delivered / No of requirements Committed for all requirement | SOP: All requirement Formal release scope : The requirements planned to be released in this version.
Software Metrics Conclusion
Metrics Summary:

## Sign off Evidence
截图必须包含 ： 版本号 发起sign off 的名字 Approve 者的名字 Sign off的时间 Note： 1. Sign off的版本以供应商测试完的时间点; 2. Milestone release 副总签字,OKTB 要求总经理签字； Inhouse： Milestone release LL5, OKTB/OTA: LL4;