## RL-Revision-History
Release Note Change Record History
Version Number | Release Date | Author | Reviewer | Approver | Content Changes
1 | 2023-07-12 | Zhang Bin | Lin Yuzhang | Tian Niu | MY24 P702 版本发布

## Release Content
Software Release Information List
Software Release Information Description
Prepared By |  | Baidu/Desay/Inhouse | Reviewed By:
Date |  | 2023-05-16 | 2023-05-16
Software Version Information
SOC SW Version |  | SOC Debug：20230710_0943_A4F12_R05.PRO
General Info |  | SOC SW P/N
Main board HW Version
|  | MCU SW Version | 20230703_659_PRO
MCU SW P/N
Checksum
Software Release Content
Release Content | 新增功能 | NA
| 完善功能 | 更换地图主线版本为PL26。
| BUG修复 | Baidu： 见Fixed Bug List
| 设计调整 | NA
| 遗留问题 | 见Open Bug List
Software Release Conlusion

## Fixed Bug List
Key | Summary | Priority | fixed version | 归属
AW2-22051 | [P702MCA][Performance]7次CRASH: com.baidu.xiaoduos.launcher | Gating | A4F12_R05.PRO | Baidu
AW2-22050 | [P702MCA][Performance]12次CRASH: com.baidu.xiaoduos.launcher | Gating | A4F12_R05.PRO | Baidu
AW2-22048 | [P702MCA][Performance]39次ANR: com.baidu.iov.dueros.videoplayer | Gating | A4F12_R05.ENG2 | Baidu
AW2-21771 | 【P702MCA】【必现】【个性化档案】点击创建时提示失败 | Gating | A4F12_R05.ENG1 | Baidu
AW2-21665 | [MY24P702][5/5]AAR can not get TLS location. | Gating | A4F12_R05.ENG1 | Baidu
AW2-21518 | 【P702MCA】【偶现】【百度地图】组队导航中修改用户名超过七位，等待提醒弹窗消失后继续输入，昵称修改界面自动退出 | Gating | A4F12_R05.PRO | Baidu
AW2-21270 | 【P702MCA】【必现】【随心看】爱奇艺搜索记录最大时继续发起任意搜索，搜索结果出现后点击返回按钮，界面闪黑屏 | Gating | A4F12_R05.PRO | Baidu
AW2-15183 | 【P702MCA】【必现】【map】偏航时未出现"叮"的声音 | Gating | A4F12_R05.PRO | Baidu
AW2-14612 | 【P702MCA】【必现】【地图】地图静音，语音“导航音量调整到5”，音量值调整到了7 | Gating | A4F12_R05.PRO | Baidu
AW2-14580 | 【P702MCA】【必现】【map】微信互联从手机端发到车机端位置信息显示异常 | Gating | A4F12_R05.PRO | Baidu

## Open Bug List
Key | Summery | Frequency | Priority | Planned Fix Version | 1. Must Include Ford & Supplier Open Issue. 2. For the Priority P0/P1, must fill G-K line. 3. For P2/P3/P4, G-K are not mandatory to fill.
AW2-22603 | Phase 4：【必现】【Performance】【P702MCA】【地图】R04版本导航启动时间较长(Launcher显示到地图打开_16.7s，taeget_13s，偏差上限13.65。稳定状态_8.5s，target_3.3s，偏差上限3.79) | 必现 | Gating | R06
AW2-22594 | Phase 4：【必现】【Performance】【P702MCA】【地图】语音导航路线规划时间较长(R04_32.2s；target_13s) | 必现 | Gating | R06
AW2-22496 | Phase 4：【偶现】【P702MCA】【地图】车机重启后，语音导航路线规划地图无法正常打开 | 偶现 | Gating | R06
AW2-21969 | 【P702MCA】【必现】【仪表】开启导航时N和NE反复交替闪烁 | 必现 | Gating | NA
AW2-21495 | 【P702MCA】【偶现】【Map】地图不显示比例尺 | 偶现 | Gating | R06
AW2-21491 | 【P702MCA】【必现】【Map】小度接人无途径点 | 偶现 | Gating | NA
AW2-19818 | 【P702MCA】【必现】【地图】地图速度比仪表车速快2km/h | 必现 | Gating | R06
AW2-16879 | Phase 4：【Performance】【MY24P702】【随心看】随心看冷启动时间较长(实车测试9.6s，允许上限偏差7s） | 必现 | Gating | R06
AW2-14559 | 【P702MCA】【必现】【map】打开地图默认比例尺为200米 | 必现 | Gating | R06

## Metrics
Process | Proposed KPI | Target / Norm | Operational Definition | Archivement Time | Week/Month | Comments
SWE.1.Software Requirements Analysis | Software Requirements Reviewed Rate % | 100% | Number of approved(reviewed) Software Requirements/ Number of Software Requirements | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.2.Software Architectural Design | SW Architectural to SW Requirement Coverage Rate | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.3 Software Detailed Design and Unit Construction | Traceable Software requirements(Jira Story) to the code | 100% | All Jira requirements should have a corresponding software unit in GIT | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA | Using Traceability From Code to Requirement&Change_Template to show the evidence.
SWE.3 Software Detailed Design and Unit Construction | SW detail design to SW Architectural Coverage | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Unit test（Code） coverage | >= 80 % | (Conditions True + Conditions False + Covered Lines)/(2*Conditions + Executable Lines) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Static Code Analysis Number of Critical Bugs | 0 | Static Code result in Sonar. | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Planned Integration Test cases vs. actual executed integration test cases | 100% | Percentage of SW integration Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | SW architecture design test coverage (HLD with Ready State test cases) | 100% | (Number of HLD SQD have integraton test Case + Number of Interface have integration test case)/(Number of HLD SQD + Number of interface) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Count of Software Integration Test defects | 0 | Count of Integration Defects | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.6 Software Qualification Test | Planned Qualification test cases vs. actual executed Qualification test cases | 100% | Percentage of SW Qualification Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.6 Software Qualification Test | SW requirement test coverage | 100% | Percentage of Requirements in Jira that has corresponding test cases in TestRail | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.6 Software Qualification Test | Software Qualification Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 99%
SWE.6 Software Qualification Test | Software Qualification Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 1%
SWE.6 Software Qualification Test | Software Qualification Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0%
SWE.6 Software Qualification Test | Count of Software Qualification test defects | 0 | Count of Defects raised in the SW Qualification Testing Phase | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 4
SUP.1 Quality Assurance | NC closure rate | 90% | Closed NC/Total NC | Monthly | NA
SUP.1 Quality Assurance | Process Audit compliance | 100% | Percentage of audits completed on time | Monthly | NA
SUP.8 Configuration Management | Nightly builds have a success rate | 100% | Percentage of compliance as defined in the process audit checklist | Every Sprint | NA
SUP.8 Configuration Management | Ba'seline completed Rate | 100% | Count of of actually baseline CI Item number/ Count of Planned baseline CI item Number | Monthly | NA
SUP.8 Configuration Management | CM Audit Passrate | 100% | Passrate of CM Audit Checklist: Count of passed Number in CM Audit Checklist/total planned CM Audit Checklist | Monthly | NA
SUP.9 Problem Resolution Management | Immediate Gating/Gating （Critical） defects for release | 0 | All urgent defects actioned on high priority, | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.9 Problem Resolution Management | Problem closure adherence | 100% | No. of defects closed against no. of defects planned for closure in this release （Include Project deviation issue and Defect） | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.9 Problem Resolution Management | Defect fix time | <40 | Defect fix time | Every Sprint | NA
SUP.9 Problem Resolution Management | Count of IG&G defect @current version | <1 | Count of IG&G defect @current version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.10 Change Request Management | Change Request status closure % | 100% | No. of Change Requests completed / Total number of change requests raised in the version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
MAN.3 Project Management | Requirement Completion Rate for sprint/Milestone | > 85% | No. of requirements delivered / No. of requirements committed for this sprint/Milestone | Every Sprint/Milestone | 100%
MAN.3 Project Management | Commitment Adherencen for All Requirement | 100% | No. of requirements delivered / No of requirements Committed for all requirement | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
Software Metrics Conlusion
Metrics Summary: 1.交付周期完成了所有了优化需求与测试 2.测试整体通过率99%，符合整体98%要求 3.依旧留存6个G bug未修复

## Sign off Evidence
截图必须包含 ： 版本号 发起sign off 的名字 Approve 者的名字 Sign off的时间 Note： 1. Sign off的版本以供应商测试完的时间点; 2. Milestone release 副总签字,OKTB 要求总经理签字； Inhouse： Milestone release LL5, OKTB/OTA: LL4;

## sha256
apkname | version | sha256
FCS_APK_CD542H_U625ICA_v1.13.1-prd_20230515_release.apk | 1.13.1 | 29c5063a37567b8f9a72382ac70ccce7be1bf0b5db7df3f40798a3118a376612
EManual.apk | 1.6.2 | 741925311343a0d5e1d0b6f6d0b571e70f55224e204afee8d4653ed989e33266
EManualGoldenTheme.apk | 1.6.2 | 4e2757d1f1e2a035832a978805d9223159208f1d315e24aadcac51aff79595b7
EManualGreenTheme.apk | 1.6.2 | 1b5472b85ab134d28689b0c498136d2c30de0fe9bc2d0ce739396588a7a5f838
SurpriseMessage.apk | 1.5.1 | a4499bf8c0a2feb93ae4fef97d6179f0be83e796e8d23ee94e551a34fc2ad460
VoiceControlService.apk | 1.0.0 | 36d028592138341d9c11819734be8239a404f511f7510420490e3f91cd03dcec