## RL-Revision-History
Release Note Change Record History
Version Number | Release Date | Author | Reviewer | Approver | Content Changes
1 | 2023-07-12 | Zhang Bin | Lin Yuzhang | Tian Niu | MY24 P702 版本发布

## Release Content
Software Release Information List
Software Release Information Description
Prepared By |  | Baidu/Desay/Inhouse | Reviewed By:
Date |  | 2023-05-16 | 2023-05-16
Software Version Information
SOC SW Version |  | SOC Debug：20230710_0943_A4F12_R05.PRO
General Info |  | SOC SW P/N
Main board HW Version
|  | MCU SW Version | 20230703_659_PRO
MCU SW P/N
Checksum
Software Release Content
Release Content | 新增功能 | NA
| 完善功能 | 更换地图主线版本为PL26。
| BUG修复 | Baidu： 见Fixed Bug List
| 设计调整 | NA
| 遗留问题 | 见Open Bug List
Software Release Conlusion

## Fixed Bug List
Key | Summary | Priority | fixed version | 归属
AW2-22051 | [P702MCA][Performance]7次CRASH: com.baidu.xiaoduos.launcher | Gating | A4F12_R05.PRO | Baidu
AW2-22050 | [P702MCA][Performance]12次CRASH: com.baidu.xiaoduos.launcher | Gating | A4F12_R05.PRO | Baidu
AW2-22048 | [P702MCA][Performance]39次ANR: com.baidu.iov.dueros.videoplayer | Gating | A4F12_R05.ENG2 | Baidu
AW2-21771 | 【P702MCA】【必现】【个性化档案】点击创建时提示失败 | Gating | A4F12_R05.ENG1 | Baidu
AW2-21665 | [MY24P702][5/5]AAR can not get TLS location. | Gating | A4F12_R05.ENG1 | Baidu
AW2-21518 | 【P702MCA】【偶现】【百度地图】组队导航中修改用户名超过七位，等待提醒弹窗消失后继续输入，昵称修改界面自动退出 | Gating | A4F12_R05.PRO | Baidu
AW2-21270 | 【P702MCA】【必现】【随心看】爱奇艺搜索记录最大时继续发起任意搜索，搜索结果出现后点击返回按钮，界面闪黑屏 | Gating | A4F12_R05.PRO | Baidu
AW2-15183 | 【P702MCA】【必现】【map】偏航时未出现"叮"的声音 | Gating | A4F12_R05.PRO | Baidu
AW2-14612 | 【P702MCA】【必现】【地图】地图静音，语音“导航音量调整到5”，音量值调整到了7 | Gating | A4F12_R05.PRO | Baidu
AW2-14580 | 【P702MCA】【必现】【map】微信互联从手机端发到车机端位置信息显示异常 | Gating | A4F12_R05.PRO | Baidu

## Open Bug List
Key | Summery | Frequency | Priority | Affects Version | Repeat step | Risk assessment | Root cause | PCA | ICA | Fix version | Comment | CIA
AW2-26372 | 【P702MCA】【必现】【map】GPS未完全Ready | 必现 | Gating | R05 PRO以及以前的版本 | 完全Ready后关闭此问题 | SOA方案，R05阶段开发中。 | GPS方案改造，按计划R06阶段组入。 | NA | NA | R06 PRO |  | NA
AW2-26060 | [MY24P702][必现][随心听]QQ音乐编辑最近播放后自动跳转到最后 | 必现 | Gating | R05 PRO以及以前的版本 | Step1: 进入QQ音乐最近播放 Step2: 点击编辑-删除任意记录 期待结果:退出编辑状态，停留在当前内容 实际结果:跳转到最后 | 已修复待集成，风险较小 | 去除有声最近播放的删除动作后的滑动 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-26058 | [MY24P702][必现][随心听]QQ音乐编辑我的收藏时点击全选后不显示取消全选按钮 | 必现 | Gating | R05 PRO以及以前的版本 | Step1: 进入QQ音乐我的收藏 Step2: 点击编辑-全选 期待结果:全选按钮变成取消全选 实际结果:仍显示全选按钮，无法取消全选 | 已修复待集成，风险较小 | 6.7.14号之前的老版本问题，50首资源限制导致 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-25899 | [MY24P702][100%]V2I voice alert announces abnormalities | 必现 | Gating | R05 PRO以及以前的版本 | 1.触发绿波、闯红灯提醒、绿灯起步，检查TTS播报 期待结果: tts正常播报 实际结果: 播报异常，结尾有ttsxxx一串播报 | 播报后播放TTSXXX，用户体验较差。已修复，下个版本可以合入，低风险。 | 因本地开发新需求adas-voice 复用该接口导致 原有功能tts带了分割符号 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-25593 | [P702MCA][Performance]Monkey过程中出现Launcher崩溃超2min后自动恢复 | 偶现 | Gating | R05 PRO以及以前的版本 | 1. Launcher崩溃超过2min（伴随com.baidu.xiaoduos.launcher CRASH） 是否可恢复:后续自动恢复 | 已修复待集成，不影响用户，风险较小 | 获取上下文的Context为null，导致出现了空指针 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-25527 | 【P702MCA】【必现】【map】 地图导航语音无个性化语音包 | 必现 | Gating | R05 PRO以及以前的版本 | 1.b+/acc/ig on 2. 网络正常 3.手机地图中有个性化语音包 复现步骤 1.打开地图设置-导航语音 2.查看显示 期待结果: 2.有个性化语音包 实际结果 2.无个性化语音包 | 手机新录制的上传成功，历史录制未第一时间上传。需要澄清同步策略。 | 手图与车机端同步策略原因，无法登陆后第一时间同步至车机端，正在与云端协商解决方案。 | 云端修复 | NA | R06 PRO |  | NA
AW2-25459 | 【P702MCA】【必现】【语音】语音唤醒率低，有时要喊两三声才会调起语音 | 必现 | Gating | R05 PRO以及以前的版本 | 复现步骤 1.语音：你好，福特 2.查看显示 3. 期待结果: 2.语音唤醒率高 实际结果 2.语音唤醒率低，有时要喊两三声才会调起语音 | 整车语音调参工作尚未开始。 | 整车语音调参工作尚未开始。调参后可修复。 | R07完成优化 | NA | R07 PRO |  | NA
AW2-25349 | Launcher显示到导航界面点击输入框出现下拉框R05测试值不达标 | 必现 | Gating | R05 PRO以及以前的版本 | Launcher显示到导航界面点击输入框出现下拉框R05测试值不达标，Target 1.2s，偏差上限1.44s，R05实测值3.12 | 启动1S内打开地图存在输入框下拉慢，20s后操作地图则符合指标。 | 地图引擎引入性能回退 | 地图引擎LTS版本优化 | 等待系统稳定后（约20S）打开地图 | R07 PRO |  | NA
AW2-25332 | 【P702MCA】【必现】【Launcher】Launcher页面地图挂入D挡后不是车头朝上 | 必现 | Gating | R05 PRO以及以前的版本 | 1.挂入D挡 2.查看Launcher地图显示 期待结果: 2.一直是车头朝上 实际结果 2.不是车头朝上 | 已修复待集成，风险较小 | 没有处理D档档相关逻辑导致 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-22603 | Phase 4：【必现】【Performance】【P702MCA】【地图】R04版本导航启动时间较长(Launcher显示到地图打开_16.7s，taeget_13s，偏差上限13.65。稳定状态_8.5s，target_3.3s，偏差上限3.79) | 必现 | Gating | R05 PRO以及以前的版本 | 复现步骤： Launcher显示到导航启动时间： Step1：Launcher显示后1s内，点击导航图标 Step2：计时从手部离开点击开始第一帧到导航地图搜索框显示时间 稳定状态下导航首次启动： Step1：测试时处于播放QQ音乐状态 Step2：Launcher出来以后等待3分钟，点击导航按钮 Step3：计时从手指抬起动作到导航地图搜索框显示时间 期待结果：Launcher显示到导航启动target 13s，允许上限偏差13.7s 稳定状态下导航首次启动target 3.3s，允许上限偏差3.8s 实际结果：实车测试Launcher16.7s，稳定状态下8.5s | 启动1S内打开导航，启动时长比预期多3S；系统稳定下启动8.5S | 地图引擎引入性能回退，当前R05版本存在一个1.5s的延迟（原先为了避免底图闪白屏的问题，目前已优化此逻辑） | 地图引擎LTS版本优化 | 等待系统稳定后（约20S）打开地图 | R07 PRO |  | NA
AW2-22594 | Phase 4：【必现】【Performance】【P702MCA】【地图】语音导航路线规划时间较长(R04_32.2s；target_13s) | 必现 | Gating | R05 PRO以及以前的版本 | Step1：IVI开机，发送adb reboot命令 Step2：Launcher显示后1s内，尝试福特定制唤醒词唤醒 Step3：语音"导航到xxx" Step4：语音“第一条 期待结果：target 13s，允许上限偏差13.7s 实际结果：实车测试 32.2s | R05性能测试报告17.82s，仍然达标，需要继续优化 | 地图引擎引入性能回退 | 地图引擎LTS版本优化 | 等待系统稳定后（约20S）语音发起导航 | R07 PRO |  | NA
AW2-22496 | Phase 4：【偶现】【P702MCA】【地图】车机重启后，语音导航路线规划地图无法正常打开 | 偶现 | Gating | R05 PRO以及以前的版本 | Step1：IVI开机，发送adb reboot命令 Step2：Launcher显示后1s内，尝试福特定制唤醒词唤醒 Step3：语音"导航到xxx" Step4：语音“第一条” 期待结果：打开地图并规划路线 实际结果：语音"第一条"后，没有打开地图 | 同AW2-22594，均为地图性能问题 | 地图引擎引入性能回退 | 地图引擎LTS版本优化 | 等待系统稳定后（约20S）语音发起导航 | R07 PRO |  | NA
AW2-22117 | [MY24P702][100%]Account not logged in, clicking on the CEN message did not redirect to the login page | 必现 | Gating | R05 PRO以及以前的版本 | 前提条件：车辆点火，车机未登陆账号 复现步骤： 1.打开福特派，向车机端发送一个CEN消息 2.车机端收到CEN消息后，点击CEN消息，查看车机端显示 *期待结果:*未登录账号的情况下点击CEN消息，车机跳转到账号登陆页面 实际结果: 未登录账号的情况下点击CEN消息，车机跳转到百度地图页面 | 已修复，待集成至R06，风险较小 | 新需求开发，前期无此交互 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-21969 | 【P702MCA】【必现】【仪表】开启导航时N和NE反复交替闪烁 | 必现 | Gating | R05 PRO以及以前的版本 | 复现步骤 1.开启导航 2.查看仪表显示 3. 期待结果: 2.有反馈音 实际结果: 2.无反馈音 | 闪烁对用户体验较差，已修复待集成，风险较小 | carangle数据处理异常导致 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-21787 | 【P702MCA】【必现】【map】使用我的语音包设置失败并且无法再次点击 | 仅一次 | Gating | R05 PRO以及以前的版本 | 1.进入地图设置-导航语音 2.点击使用我的语音包 3.查看显示 期待结果: 3.设置成功 | 仅复现一次，R05版本没有再复现。 | 怀疑和云端有关，缺少引擎日志，无法确认根因。 | NA | NA | NA | 百度跟踪3个百度未复现。 | NA
AW2-21665 | [MY24P702][100%]AAR can not get TLS location. | 必现 | Gating | R05 PRO以及以前的版本 | 1.台架上电 2.车机安装调试好TLS 复现步骤（必填）： 1.使用TLS 模拟一个GPS位置 2.定位成功后,观察AAR,百度地图以及天气的GPS信息 预期结果： 可以获取到模拟的位置信息 实际结果： AAR没有定位信息 | 已修复待集成，风险较小 | 因launcher比车机管家启动快导致，刚开机获取不到权限，打断了gps初始化 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-21498 | 【P702MCA】【必现】【Map】语音退出地图后仪表依然显示在导航中 | 必现 | Gating | R05 PRO以及以前的版本 | 1.b+/acc/ig on 2. 网络正常 3.正在组队 复现步骤 1.导航中 2.语音退出地图 3.查看仪表显示 期待结果: 3.仪表退出地图 实际结果: 3.仪表还在导航中 | 已修复待集成，风险较小 | 导航结束时，需要发送导航结束信息传给德赛侧 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-21495 | 【P702MCA】【偶现】【Map】地图不显示比例尺 | 偶现 | Gating | R05 PRO以及以前的版本 | 复现步骤 1.进入导航页面 2.查看比例尺显示 期待结果: 2.比例尺显示正常 实际结果: 2.无比例尺 | 已修复待集成，风险较小 | 日间模式比例尺文字颜色太淡 | 已修复，R06合入 | 可使用日间模式 | R06 PRO |  | NA
AW2-21144 | 【P702MCA】【必现】【随心听】QQ音乐进度条无法划到底 | 必现 | Gating | R05 PRO以及以前的版本 | 1.进入QQ音乐 2.播放音乐后把进度条划到底 3.查看显示 期待结果: 3.可以划到底 实际结果: 3.无法划到底 | 已修复待集成，风险较小 | 背景图片适配问题 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-19818 | 【P702MCA】【必现】【地图】地图速度比仪表车速快2km/h | 必现 | Gating | R05 PRO以及以前的版本 | 1.开始导航到南京南 2.车辆行驶 3.查看显示 期待结果: 3.仪表速度和地图速度一致 实际结果: 3.地图速度比仪表速度快2km/h | 已修复待集成，风险较小 | 百度地图的车速转换规则与北美仪表不一致导致 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-14580 | 【P702MCA】【必现】【map】微信互联从手机端发到车机端位置信息显示异常 | 必现 | Gating | R05 PRO以及以前的版本 | 复现步骤 1.正在导航页面 2.手机发送一个位置给车机 3.查看显示 期待结果: 3.正常显示 实际结果: 3.显示异常 | 已修复待集成，风险较小 | UI适配问题 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-14559 | 【P702MCA】【必现】【map】打开地图默认比例尺为200米 | 必现 | Gating | R05 PRO以及以前的版本 | 1.打开地图 2.查看默认比例尺显示 期待结果: 2.默认为一公里 | 不影响用户使用，已修复待集成，风险较小 | 未按MRD执行 | 已修复，R06合入 | NA | R06 PRO |  | NA
AW2-14207 | [MY24P702][100%]账号登录和“如何注册福特派”页面UI未合入，与UI设计不符 | 必现 | Gating | R05 PRO以及以前的版本 | 1.进入个人中心-账号登录页面&如何注册福特派页面 2.检查页面 Actual Result： 2.账号登录和“如何注册福特派”页面UI未合入，与UI设计不符 Expect Result： 2.页面与UI设计一致 | 已修复待集成，风险较小 | 福特账号未集成最新版本 | 已修复，R06合入 | NA | R06 PRO |  | NA

## Metrics
Process | Proposed KPI | Target / Norm | Operational Definition | Archivement Time | Week/Month | Comments
SWE.1.Software Requirements Analysis | Software Requirements Reviewed Rate % | 100% | Number of approved(reviewed) Software Requirements/ Number of Software Requirements | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.2.Software Architectural Design | SW Architectural to SW Requirement Coverage Rate | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.3 Software Detailed Design and Unit Construction | Traceable Software requirements(Jira Story) to the code | 100% | All Jira requirements should have a corresponding software unit in GIT | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA | Using Traceability From Code to Requirement&Change_Template to show the evidence.
SWE.3 Software Detailed Design and Unit Construction | SW detail design to SW Architectural Coverage | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Unit test（Code） coverage | >= 80 % | (Conditions True + Conditions False + Covered Lines)/(2*Conditions + Executable Lines) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Static Code Analysis Number of Critical Bugs | 0 | Static Code result in Sonar. | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Planned Integration Test cases vs. actual executed integration test cases | 100% | Percentage of SW integration Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | SW architecture design test coverage (HLD with Ready State test cases) | 100% | (Number of HLD SQD have integraton test Case + Number of Interface have integration test case)/(Number of HLD SQD + Number of interface) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Count of Software Integration Test defects | 0 | Count of Integration Defects | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.6 Software Qualification Test | Planned Qualification test cases vs. actual executed Qualification test cases | 100% | Percentage of SW Qualification Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.6 Software Qualification Test | SW requirement test coverage | 100% | Percentage of Requirements in Jira that has corresponding test cases in TestRail | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.6 Software Qualification Test | Software Qualification Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 99%
SWE.6 Software Qualification Test | Software Qualification Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 1%
SWE.6 Software Qualification Test | Software Qualification Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0%
SWE.6 Software Qualification Test | Count of Software Qualification test defects | 0 | Count of Defects raised in the SW Qualification Testing Phase | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 4
SUP.1 Quality Assurance | NC closure rate | 90% | Closed NC/Total NC | Monthly | NA
SUP.1 Quality Assurance | Process Audit compliance | 100% | Percentage of audits completed on time | Monthly | NA
SUP.8 Configuration Management | Nightly builds have a success rate | 100% | Percentage of compliance as defined in the process audit checklist | Every Sprint | NA
SUP.8 Configuration Management | Ba'seline completed Rate | 100% | Count of of actually baseline CI Item number/ Count of Planned baseline CI item Number | Monthly | NA
SUP.8 Configuration Management | CM Audit Passrate | 100% | Passrate of CM Audit Checklist: Count of passed Number in CM Audit Checklist/total planned CM Audit Checklist | Monthly | NA
SUP.9 Problem Resolution Management | Immediate Gating/Gating （Critical） defects for release | 0 | All urgent defects actioned on high priority, | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.9 Problem Resolution Management | Problem closure adherence | 100% | No. of defects closed against no. of defects planned for closure in this release （Include Project deviation issue and Defect） | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.9 Problem Resolution Management | Defect fix time | <40 | Defect fix time | Every Sprint | NA
SUP.9 Problem Resolution Management | Count of IG&G defect @current version | <1 | Count of IG&G defect @current version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.10 Change Request Management | Change Request status closure % | 100% | No. of Change Requests completed / Total number of change requests raised in the version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
MAN.3 Project Management | Requirement Completion Rate for sprint/Milestone | > 85% | No. of requirements delivered / No. of requirements committed for this sprint/Milestone | Every Sprint/Milestone | 100%
MAN.3 Project Management | Commitment Adherencen for All Requirement | 100% | No. of requirements delivered / No of requirements Committed for all requirement | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
Software Metrics Conlusion
Metrics Summary: 1.交付周期完成了所有了优化需求与测试 2.测试整体通过率99%，符合整体98%要求 3.依旧留存6个G bug未修复

## Sign off Evidence
截图必须包含 ： 版本号 发起sign off 的名字 Approve 者的名字 Sign off的时间 Note： 1. Sign off的版本以供应商测试完的时间点; 2. Milestone release 副总签字,OKTB 要求总经理签字； Inhouse： Milestone release LL5, OKTB/OTA: LL4;

## sha256
apkname | version | sha256
FCS_APK_CD542H_U625ICA_v1.13.1-prd_20230515_release.apk | 1.13.1 | 29c5063a37567b8f9a72382ac70ccce7be1bf0b5db7df3f40798a3118a376612
EManual.apk | 1.6.2 | 741925311343a0d5e1d0b6f6d0b571e70f55224e204afee8d4653ed989e33266
EManualGoldenTheme.apk | 1.6.2 | 4e2757d1f1e2a035832a978805d9223159208f1d315e24aadcac51aff79595b7
EManualGreenTheme.apk | 1.6.2 | 1b5472b85ab134d28689b0c498136d2c30de0fe9bc2d0ce739396588a7a5f838
SurpriseMessage.apk | 1.5.1 | a4499bf8c0a2feb93ae4fef97d6179f0be83e796e8d23ee94e551a34fc2ad460
VoiceControlService.apk | 1.0.0 | 36d028592138341d9c11819734be8239a404f511f7510420490e3f91cd03dcec