## RL-Revision-History
Release Note Change Record History
Version Number | Release Date | Author | Reviewer | Approver | Content Changes
1 | 2023-11-21 | Zhang Bin | Lin Yuzhang | Tian Niu | MY24 P702 R06.1版本发布

## Release Content
Software Release Information List
Software Release Information Description
Prepared By |  | Baidu/Desay/Inhouse | Reviewed By:
Date |  | 2023-11-21 | 2023-11-21
Software Version Information
SOC SW Version |  | SOC User：20231121_1007_A4F12_R06.1.PRO_User SOC Debug：20231121_1007_A4F12_R06.1.PRO_Debug MCU：20231120_709_PRO FNV：dueros_EX2.4_A8.1-bin-2.0.4.1019_20230816
General Info |  | SOC SW P/N | Desay
|  | Main board HW Version | Desay
|  | MCU SW Version | Desay
|  | MCU SW P/N | Desay
|  | Checksum | Desay
Software Release Content
Release Content | 新增功能 | NA
| 完善功能 | NA
| BUG修复 | 见Fixed Bug List
| 设计调整 | NA
| 遗留问题 | 见Open Bug List
Software Release Conlusion

## Fixed Bug List
Key | 影响模块 | Summary | Priority | fixed version | 归属
AW2-32132 | Launcher | Scrolling quickly through DUER settings will display truck animation | P1 | R06.1 | Baidu

## Open Bug List
Key | Summery | Frequency | Priority | Affects Version | Repeat step | Risk assessment | Root cause | PCA | ICA | Fix version | Comment | CIA
AW2-32831 | [P702MCA][必现][百度-语音]在语音设置中无法设置自定义唤醒词 | 必现 | P1 | R06 PRO以及以前的版本 | Pre-condition:更新软件后未设置过自定义唤醒词，也未语音设置过唤醒词 复现步骤 Step1：进入语音设置 Step2：打开自定义唤醒词开关 Step3：输入“大白”，点击确定 期待结果:唤醒词设置成功，自定义唤醒词开关被打开 实际结果:唤醒词设置失败，自定义唤醒词开关仍关闭状态，语音可以设置唤醒词 | 无法使用自定义唤醒词，已修复，R07合入 | 语音模块判断车型逻辑有误，导致P702MCA判断唤醒词开关方法有问题，无法生效。。 | R07完成优化 | NA | R07 PRO |  | NA
AW2-25349 | Launcher显示到导航界面点击输入框出现下拉框R05测试值不达标 | 必现 | P1 | R06 PRO以及以前的版本 | Launcher显示到导航界面点击输入框出现下拉框R05测试值不达标，Target 1.2s，偏差上限1.44s，R05实测值3.12 | R06HF2实车测试2.7S，与820A现有车型持平。 | 地图引擎安全修复引入性能回退。 | 地图引擎LTS版本优化 | NA | R07 PRO |  | NA
AW2-22603 | Phase 4：【必现】【Performance】【P702MCA】【地图】R04版本导航启动时间较长(Launcher显示到地图打开_16.7s，taeget_13s，偏差上限13.65。稳定状态_8.5s，target_3.3s，偏差上限3.79) | 必现 | P1 | R06 PRO以及以前的版本 | 复现步骤： Launcher显示到导航启动时间： Step1：Launcher显示后1s内，点击导航图标 Step2：计时从手部离开点击开始第一帧到导航地图搜索框显示时间 稳定状态下导航首次启动： Step1：测试时处于播放QQ音乐状态 Step2：Launcher出来以后等待3分钟，点击导航按钮 Step3：计时从手指抬起动作到导航地图搜索框显示时间 期待结果：Launcher显示到导航启动target 13s，允许上限偏差13.7s 稳定状态下导航首次启动target 3.3s，允许上限偏差3.8s 实际结果：实车测试Launcher16.7s，稳定状态下8.5s | 启动1S内打开导航，启动时长比预期多3S；系统稳定下启动5.7S | P702MCA车机6G内存，低于指标车型727/S650的8G。地图需要进一步优化。 | 地图引擎LTS版本优化 | NA | R07 PRO |  | NA
AW2-16867 | Phase 4：【Performance】【MY24P702】【地图】系统稳定状态Navigation首次启动较长(实车测试：6s，允许上限偏差3.8s） | 必现 | P1 | R06 PRO以及以前的版本 | Step1：执行”系统稳定状态下Navigation首次启动“case Step2：计时从手指抬起动作到导航地图搜索框显示时间 期待结果： Target：3.3s，允许上限偏差3.8s | 系统稳态首次启动地图5.7s | 启动分析中，将达标的S650 APK安装在P702，启动6S。 | 优化地图性能 | NA | R07 PRO | R07计划修复 | NA
AW2-32815 | [用户体验][P702MCA][导航][高频]地图使用过程出现页面响应卡顿和语音播报卡顿 | 高频 | P1 | R06 PRO以及以前的版本 | Steps: 1.发起导航，后台播放QQ音乐 2.偏航 Expected result： 2.语音正常提示偏航信息，播报新的路线 Actual result: 2.语音播报卡顿 Rates: 1/3 | 需要进行性能优化 | CPU Idle空间不足，最低4%，导致播报卡顿。需要基于HF2版本复测日志进行优化 | 优化版本性能 | NA | R07 PRO | R07计划修复 | NA
AW2-22594 | Phase 4：【必现】【Performance】【P702MCA】【地图】语音导航路线规划时间较长(R04_32.2s；target_13s) | 必现 | P1 | R06 PRO以及以前的版本 | Step1：IVI开机，发送adb reboot命令 Step2：Launcher显示后1s内，尝试福特定制唤醒词唤醒 Step3：语音"导航到xxx" Step4：语音“第一条 期待结果：target 13s，允许上限偏差13.7s 实际结果：实车测试 32.2s | 需要进行性能优化 | P702MCA车机6G内存，低于指标车型727/S650的8G。地图需要进一步优化。 | 优化版本性能 | NA | R07 PRO | R07计划修复 | NA

## Metrics
Process | Proposed KPI | Target / Norm | Operational Definition | Archivement Time | Week/Month | Comments
SWE.1.Software Requirements Analysis | Software Requirements Reviewed Rate % | 100% | Number of approved(reviewed) Software Requirements/ Number of Software Requirements | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.2.Software Architectural Design | SW Architectural to SW Requirement Coverage Rate | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.3 Software Detailed Design and Unit Construction | Traceable Software requirements(Jira Story) to the code | 100% | All Jira requirements should have a corresponding software unit in GIT | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA | Using Traceability From Code to Requirement&Change_Template to show the evidence.
SWE.3 Software Detailed Design and Unit Construction | SW detail design to SW Architectural Coverage | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Unit test（Code） coverage | >= 80 % | (Conditions True + Conditions False + Covered Lines)/(2*Conditions + Executable Lines) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Static Code Analysis Number of Critical Bugs | 0 | Static Code result in Sonar. | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Planned Integration Test cases vs. actual executed integration test cases | 100% | Percentage of SW integration Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | SW architecture design test coverage (HLD with Ready State test cases) | 100% | (Number of HLD SQD have integraton test Case + Number of Interface have integration test case)/(Number of HLD SQD + Number of interface) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Count of Software Integration Test defects | 0 | Count of Integration Defects | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.6 Software Qualification Test | Planned Qualification test cases vs. actual executed Qualification test cases | 100% | Percentage of SW Qualification Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.6 Software Qualification Test | SW requirement test coverage | 100% | Percentage of Requirements in Jira that has corresponding test cases in TestRail | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.6 Software Qualification Test | Software Qualification Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 99%
SWE.6 Software Qualification Test | Software Qualification Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 1%
SWE.6 Software Qualification Test | Software Qualification Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0%
SWE.6 Software Qualification Test | Count of Software Qualification test defects | 0 | Count of Defects raised in the SW Qualification Testing Phase | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 4
SUP.1 Quality Assurance | NC closure rate | 90% | Closed NC/Total NC | Monthly | NA
SUP.1 Quality Assurance | Process Audit compliance | 100% | Percentage of audits completed on time | Monthly | NA
SUP.8 Configuration Management | Nightly builds have a success rate | 100% | Percentage of compliance as defined in the process audit checklist | Every Sprint | NA
SUP.8 Configuration Management | Ba'seline completed Rate | 100% | Count of of actually baseline CI Item number/ Count of Planned baseline CI item Number | Monthly | NA
SUP.8 Configuration Management | CM Audit Passrate | 100% | Passrate of CM Audit Checklist: Count of passed Number in CM Audit Checklist/total planned CM Audit Checklist | Monthly | NA
SUP.9 Problem Resolution Management | Immediate Gating/Gating （Critical） defects for release | 0 | All urgent defects actioned on high priority, | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.9 Problem Resolution Management | Problem closure adherence | 100% | No. of defects closed against no. of defects planned for closure in this release （Include Project deviation issue and Defect） | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.9 Problem Resolution Management | Defect fix time | <40 | Defect fix time | Every Sprint | NA
SUP.9 Problem Resolution Management | Count of IG&G defect @current version | <1 | Count of IG&G defect @current version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.10 Change Request Management | Change Request status closure % | 100% | No. of Change Requests completed / Total number of change requests raised in the version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
MAN.3 Project Management | Requirement Completion Rate for sprint/Milestone | > 85% | No. of requirements delivered / No. of requirements committed for this sprint/Milestone | Every Sprint/Milestone | 100%
MAN.3 Project Management | Commitment Adherencen for All Requirement | 100% | No. of requirements delivered / No of requirements Committed for all requirement | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
Software Metrics Conlusion
Metrics Summary: 1.交付周期完成了所有了优化需求与测试 2.测试整体通过率99%，符合整体98%要求 3.依旧留存6个G bug未修复

## Sign off Evidence
截图必须包含 ： 版本号 发起sign off 的名字 Approve 者的名字 Sign off的时间 Note： 1. Sign off的版本以供应商测试完的时间点; 2. Milestone release 副总签字,OKTB 要求总经理签字； Inhouse： Milestone release LL5, OKTB/OTA: LL4;

## sha256
apkname | version | sha256
FordVPA/FordVPA.apk | 1.0.8 | 2dd367fe03fae30e962221dd8b78cd39aca620a4ead76b95c2b0609edc7f5283
FordCloudService/FordCloudService.apk | 1.14.1 | a0056f67a9a775916341529c95575eb6fefd332dfdd7dddf60a4c641be3be1e2