## RL-Revision-History
Release Note Change Record History
Version Number | Release Date | Author | Reviewer | Approver | Content Changes
1 | 2023-06-12 | zhangbin | linyuzhang | tianniu | MY24 U554 R05 PRO版本

## Release Content
Software Release Information List
Software Release Information Description
Prepared By |  | Baidu | Reviewed By:
Date |  | 2023-06-12 | 2023-06-12
Software Version Information
SOC SW Version |  | 20230520_0920_D3L13_R05.ENG 20230607_0924_D3L13_R05.PRO
General Info |  | SOC SW P/N | NA
|  | Main board HW Version | NA
|  | MCU SW Version | 20230511_623_PRO 20230607_649_PRO
MCU SW P/N
Checksum
Software Release Content
Release Content | 新增功能 | NA
| 完善功能 | NA
| BUG修复 | Baidu： 见Fixed Bug List 特殊说明： 埋点修复： 激活（1.2.8.28）： 【ACT10006激活失败原因】频繁上报 地图（3.0.4.117）： NAV10014语音发起AR导航埋点修复。 图像（27.0.0.1）： 【图像-账号】【必现】(百度算法)开关车门后台人脸成功，但未弹出切换弹窗
| 设计调整 | NA
| 遗留问题 | 见Open Bug List
Software Release Conlusion
1.交付周期完成了所有了优化需求与测试 2.测试整体通过率98%，符合整体98%要求 3.依旧留存8个IG/G bug未修复

## Fixed Bug List
Key | Summary | Priority | fixed version | 归属
AW2-19769 | Phase4:[MY23 U554][100%][AAR]The history shows an error. | Gating | R05 Pro | Baidu
AW2-19535 | [My23 U554][偶现][随心听]首次进入QQ音乐，微信登录成功后，歌曲名显示未知，但显示播放进度与时间 | Gating | R05 Pro | Baidu
AW2-19533 | [My23 U554][必现][地图]导航音量设置为静音，点击详细/简洁/提示音取消了静音模式，但导航音量依然显示为静音 | Gating | R05 Pro | Baidu
AW2-9256 | Phase4:[MY23 U554][必现]最近应用图标显示原生态，并且名称还有英文 | Gating | R05 Pro | Baidu
AW2-8173 | Phase4:[MY23 U554][必现]智能新风车模内饰不正确 | Gating | R05 Pro | Baidu
AW2-7421 | [My23 U554][偶现][Lanuncher]Launcher第三页显示“当前无网络，请稍后重试”，点击功能也无法使用 | Gating | R05 Pro | Baidu
AW2-7098 | Phase4:The launcher page Himalaya pause key click is invalid | Gating | R05 Pro | Baidu
AW2-6875 | Phase4:[MY23 U554][100%][AAR] Smart Loop State 1 to State 3 and State 3 to State 4 Error | Gating | R05 Pro | Baidu
AW2-6873 | Phase4:[MY23 U554][100%]【AAR】Strategy disabled or any of the following conditions are not met,Auto Recirc Control Strategy is still available | Gating | R05 Pro | Baidu
AW2-6860 | Phase4:[100%]Submit an OSB order under the weak network, it will crash | Gating | R05 Pro | Baidu
AW2-6816 | [My23 U554][必现][Media]插入U盘进入本地视频，本地视频界面显示空白，无法加载出U盘视频 | Gating | R05 Pro | Baidu
AW2-6815 | [My23 U554][必现][media]播放一个之前未播放结束的音频，已经开始续播，但界面还显示续播提示 | Gating | R05 Pro | Baidu

## Open Bug List
Key | Summery | Frequency | Priority | Affects Version | Repeat step | Risk assessment | Root cause | PCA | ICA | Fix version | Comment | CIA | 归属 | 1. Must Include Ford & Supplier Open Issue. 2. For the Priority P0/P1, must fill G-K line. 3. For P2/P3/P4, G-K are not mandatory to fill.

## Metrics
Process | Proposed KPI | Target / Norm | Operational Definition | Archivement Time | Week/Month | Comments
SWE.1.Software Requirements Analysis | Software Requirements Reviewed Rate % | 100% | Number of approved(reviewed) Software Requirements/ Number of Software Requirements | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.2.Software Architectural Design | SW Architectural to SW Requirement Coverage Rate | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.3 Software Detailed Design and Unit Construction | Traceable Software requirements(Jira Story) to the code | 100% | All Jira requirements should have a corresponding software unit in GIT | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100% | Using Traceability From Code to Requirement&Change_Template to show the evidence.
SWE.3 Software Detailed Design and Unit Construction | SW detail design to SW Architectural Coverage | 100% | Jira Tracibility/Excel Tracibility | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Unit test（Code） coverage | >= 80 % | (Conditions True + Conditions False + Covered Lines)/(2*Conditions + Executable Lines) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Static Code Analysis Number of Critical Bugs | 0 | Static Code result in Sonar. | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0
SWE.5 Software IntegrationTest | Planned Integration Test cases vs. actual executed integration test cases | 100% | Percentage of SW integration Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Software Integration Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | SW architecture design test coverage (HLD with Ready State test cases) | 100% | (Number of HLD SQD have integraton test Case + Number of Interface have integration test case)/(Number of HLD SQD + Number of interface) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software IntegrationTest | Count of Software Integration Test defects | 0 | Count of Integration Defects | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.6 Software Qualification Test | Planned Qualification test cases vs. actual executed Qualification test cases | 100% | Percentage of SW Qualification Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 99.13% | 5730/5780=99.13%
SWE.6 Software Qualification Test | SW requirement test coverage | 100% | Percentage of Requirements in Jira that has corresponding test cases in TestRail | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
SWE.6 Software Qualification Test | Software Qualification Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 98.3% | 5682/5780=98.30%
SWE.6 Software Qualification Test | Software Qualification Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0.83% | 48/5780=0.83%
SWE.6 Software Qualification Test | Software Qualification Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0% | 50/5780=0.87%
SWE.6 Software Qualification Test | Count of Software Qualification test defects | 0 | Count of Defects raised in the SW Qualification Testing Phase | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0
SUP.1 Quality Assurance | NC closure rate | 90% | Closed NC/Total NC | Monthly | NA
SUP.1 Quality Assurance | Process Audit compliance | 100% | Percentage of audits completed on time | Monthly | NA
SUP.8 Configuration Management | Nightly builds have a success rate | 100% | Percentage of compliance as defined in the process audit checklist | Every Sprint | NA
SUP.8 Configuration Management | Ba'seline completed Rate | 100% | Count of of actually baseline CI Item number/ Count of Planned baseline CI item Number | Monthly | 100%
SUP.8 Configuration Management | CM Audit Passrate | 100% | Passrate of CM Audit Checklist: Count of passed Number in CM Audit Checklist/total planned CM Audit Checklist | Monthly | 100%
SUP.9 Problem Resolution Management | Immediate Gating/Gating （Critical） defects for release | 0 | All urgent defects actioned on high priority, | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 8
SUP.9 Problem Resolution Management | Problem closure adherence | 100% | No. of defects closed against no. of defects planned for closure in this release （Include Project deviation issue and Defect） | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SUP.9 Problem Resolution Management | Defect fix time | <40 | Defect fix time | Every Sprint | NA
SUP.9 Problem Resolution Management | Count of IG&G defect @current version | <1 | Count of IG&G defect @current version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 8
SUP.10 Change Request Management | Change Request status closure % | 100% | No. of Change Requests completed / Total number of change requests raised in the version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
MAN.3 Project Management | Requirement Completion Rate for sprint/Milestone | > 85% | No. of requirements delivered / No. of requirements committed for this sprint/Milestone | Every Sprint/Milestone | NA
MAN.3 Project Management | Commitment Adherencen for All Requirement | 100% | No. of requirements delivered / No of requirements Committed for all requirement | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100%
Software Metrics Conlusion
Metrics Summary: 1.交付周期完成了所有了优化需求与测试 2.测试整体通过率99%，符合整体98%要求 3.依旧留存8个IG/G bug未修复

## Sign off Evidence
截图必须包含 ： 版本号 发起sign off 的名字 Approve 者的名字 Sign off的时间 Note： 1. Sign off的版本以供应商测试完的时间点; 2. Milestone release 副总签字,OKTB 要求总经理签字； Inhouse： Milestone release LL5, OKTB/OTA: LL4;