## RL-Revision-History
Release Note Change Record History
Version Number | Release Date | Author & Email | Reviewer & Email | Approver & Email | Content Changes
V1.0 | 2023-10-23 | Zhang Bin | Lin Yuzhang | Tian niu | U625ICA R13 Release Note First version
V1.1 | 2023-11-13 | Zhang Bin | Lin Yuzhang | Tian niu | 使用V1.3模版
V1.2 | 2023-12-01 | Zhang Bin | Lin Yuzhang | Tian niu | R13HF1
V1.3 | 2023-12-05 | Zhang Bin | Lin Yuzhang | Tian niu | R13HF1 按需修改
V1.4 | 2023-12-05 | Zhang Bin | Tian niu | Bu Junfei | R13HF1 更新遗留问题清单
V1.5 | 2023-12-17 | Zhang Bin | Tian niu | Bu Junfei | R13HF2 更新遗留问题清单

## Release Content
Software Release Information List |  |  |  | 1. 各方需要提供该格式的release note； 2. 集成方需要整合各方的release content，Fixed Bug list Open Bug List 的内容； 3. Release note的内容准确性由各个开发方的PM&SWQ来保证，Ford方的System Integration Manager&SWQ 来检查 4. Release note 版本号： After Integration Completed 1.* After Supplier Test Completed 2.* REC(End To End) Test Completed 3.*
Software Release Information Description
Prepared By |  | Zhang Bin | Reviewed By:
Date |  | 2023.12.17 | Bu Junfei
Software Version Information
SOC SW Version |  | Desay
General Info |  | SOC SW P/N | Desay
|  | Main board HW Version | Desay
|  | MCU SW Version | Desay
|  | MCU SW P/N | Desay
|  | Checksum | Desay
Software Release Content
Release Content | 新增功能 | 【Baidu】 1、APIMCIS-34150 U625ICA Map 3.0升级到Map 5.1 ---L24版本 修改模块：地图：BaiduMapAuto_5.2-U625ICA-R13-9.1-PL24_HF2_27_20230925185843 2、APIMCIS-33944 U625ICA 合入QQ VIP功能 修改模块：随心听：CarRadio2_CD542H_6.9.23.1916 3、APIMCIS-34151 语音控制打开360 修改模块：语音：DuerOSVPA_1.5.6.5 4、APIMCIS-34153 语音控制后视镜加热 修改模块：语音：DuerOSVPA_1.5.6.5 5、APIMCIS-34022 [U625ICA]sync+2.0生态软件隐私条款合规满足国家法规要求整改_地图 修改模块：语音（DuerOSVPA_1.5.6.5）、Launcher（CarLauncher_2.5.8.1）、地图（BaiduMapAuto_5.2-U625ICA-R13-9.1-PL24_HF2_27_20230925185843）、随心听（CarRadio2_CD542H_6.9.23.1916）、随心看（DuerOSVideoPlayer_1.5.92）、输入法（BaiduInput_sprint_34.0.0.1） 6、APIMCIS-33647 【U625ICA】【DCR】【随心听】Phase4 QQ 音乐合入Phase3的OTA 功能 修改模块：随心听：CarRadio2_CD542H_6.9.23.1916
| 完善功能 | 【Baidu】 1、APIMCIS-33372 FM混源 修改模块：随心听：CarRadio2_CD542H_6.9.23.1916 2、APIMCIS-34156 QQ音乐随机播放歌曲重复率高 修改模块：随心听：CarRadio2_CD542H_6.9.23.1916 3、APIMCIS-34154 下架应用：美团，电影票、酒店预定,智慧停车厂（ETCP） 修改模块：语音（DuerOSVPA_1.5.6.5）、Launcher（CarLauncher_2.5.8.1） 4、APIMCIS-33957 【U625ICA】【R13】【QQVIP】【埋点】QQVIP对应埋点开发 修改模块：随心听：CarRadio2_CD542H_6.9.23.1916
| BUG修复 | 【Baidu】 见Fixed Bug List
| 设计调整 | 【Baidu】 暂无
| 遗留问题 | 【内容】 对版本没有解决的问题做简单说明，指当前发布的成果的遗留问题，生成列表放在<Open Bug List>，并在此备注见<Open Bug List> 如无，可为空。
Software Release Conclusion
针对该版本发布的结论： 1、需求完整度100% 2、测试结论有条件通过，遗留问题影响较小。

## Fixed Bug List
Key | Summary | Priority | Fixed Version | Suppliers | Component | Test steps | Test result
APIMCIS-34396 | 【实车】【U625ICA】【地图】【必现】导航结束卡片滑动列表主副驾驶不同步 | P1 | B1F27_R13.PRO | Baidu
APIMCIS-34346 | 【phase4_U625ICA】天气界面字体重叠 | P1 | B1F27_R13.PRO | Baidu
APIMCIS-34345 | 【phase4_U625ICA】【VT202302282143】智能馨风的天气预报和当前地区PM2.5不显示。 | P1 | B1F27_R13.PRO | Baidu
APIMCIS-34341 | 【U625ICA-R13】【埋点】【验收】百度侧问题汇总 | P1 | B1F27_R13.PRO | Baidu
APIMCIS-33947 | 【U625ICA】【R13】【埋点】【地图】Map 5.1埋点优化 | P1 | B1F27_R13.PRO | Baidu
APIMCIS-31509 | Phase4:[必现]27寸长屏，消息中心内的消息卡片无法滑动到最左侧 | P0 | B1F27_R13.PRO | Baidu
APIMCIS-31344 | [U625ICA][Performance]6次CRASH: com.baidu.car.radio | P0 | B1F27_R13.PRO | Baidu
APIMCIS-30942 | 【台架】【U625】【随心听】【必现】U盘音乐播放中唤醒语音更换主题，主题换完点击音效按钮无反应 | P1 | B1F27_R13.PRO | Baidu
APIMCIS-30796 | 【点检】【高频】副屏播放蓝牙音乐或FM，主屏首页随心听依旧显示Usb音乐在播放状态 | P0 | B1F27_R13.PRO | Baidu
APIMCIS-30404 | [U625ICA][偶现][音频双开]随心听主副驾双开，主驾launcher卡片显示默认信息 | P0 | B1F27_R13.PRO | Baidu
APIMCIS-30269 | CLONE - Phase4：[U625ICA]The intelligent startup pop-up window closes abnormally | P0 | B1F27_R13.PRO | Baidu
APIMCIS-30101 | 【必现】【语音】【U625】唤醒语音，当展开全屏时，点击语音软按键退出，再次唤醒语音，有之前界面残留 | P0 | B1F27_R13.PRO | Baidu
APIMCIS-26783 | Phase4:Click on the subscribe prompt to display unsubscribe | P0 | B1F27_R13.PRO | Baidu
APIMCIS-24078 | 【U625】【随心听】【必现】主驾随心看播放中点击返回按钮，副驾QQ音乐跳转到了在线收音机界面 | P0 | B1F27_R13.PRO | Baidu
APIMCIS-22757 | [U625ICA][Performace]18次ANR in com.desay.setting | P0 | B1F27_R13.PRO | Baidu
APIMCIS-22302 | [U625ICA][必现][地图]合作模式，导航中，副驾点击分屏，主驾闪现副驾诱导信息 | P0 | B1F27_R13.PRO | Baidu
FordPhase4Scrum-73503 | 【实车】【U625ICA】【地图】【必现】语音进入算路页面，缺失路径规划卡片，无法进入导航态 | P0 | B1F27_R13.PRO | Baidu | 地图 | 语音进入算路页面，缺失路径规划卡片，无法进入导航态 | Pass
FordPhase4Scrum-76317 | 【高优】【台架】【U625ICA】【地图】【必现】点击搜索‘福特4S店’，主驾屏正常显示搜索结果，副驾屏显示异常 | P1 | B1F27_R13.PRO | Baidu | 地图 | 点击搜索‘福特4S店’，主驾屏正常显示搜索结果，副驾屏显示异常 | Pass
FordPhase4Scrum-76311 | 【高优】【台架】【U625ICA】【地图】【必现】地图首页点击搜索框没有调起键盘 | P1 | B1F27_R13.PRO | Baidu | 地图 | 地图首页点击搜索框没有调起键盘 | Pass
FordPhase4Scrum-75874 | 【高优】【实车】【U625ICA】【地图】【必现】【客户反馈】进入导航设置，两侧比例尺和组队控件无法点击 | P1 | B1F27_R13.PRO | Baidu | 地图 | 进入导航设置，两侧比例尺和组队控件无法点击 | Pass
FordPhase4Scrum-75804 | 【高优】【实车】【U625ICA】【地图】【必现】【客户体验】语音上报少了一个事件类型 | P1 | B1F27_R13.PRO | Baidu | 地图 | 语音上报少了一个事件类型 | Pass
FordPhase4Scrum-75588 | 【高优】【实车】【U625ICA】【地图】【客户反馈】【必现】1535 当前导航中，语音设置播报模式为简洁，再静音，在增高导航音量，播报模式变为详细 | P1 | B1F27_R13.PRO | Baidu | 地图 | 当前导航中，语音设置播报模式为简洁，再静音，在增高导航音量，播报模式变为详细 | Pass
FordPhase4Scrum-74443 | 【实车】【CD542H】【随心听】【必现】Launcher显示到在线电台音源恢复的响应时间超过taget值 | P1 | B1F27_R13.PRO | Baidu | 随心听 | Launcher显示到在线电台音源恢复 | Pass
FordPhase4Scrum-71350 | 【台架】【CD542H】【随心听】【必现】播放USB音乐，长按HOME键清除随心听，再进入随心听后USB页面不显示歌词 | P1 | B1F27_R13.PRO | Baidu | 随心听 | 播放USB音乐，长按HOME键清除随心听，再进入随心听后USB页面不显示歌词 | Pass
FordPhase4Scrum-71344 | 【台架】【CD542H】【随心听签约管理】【必现】独立模式，连接蓝牙耳机，副驾随心听前台时取消签约授权，副驾随心听没有自动停止播放并退出 | P1 | B1F27_R13.PRO | Baidu | 随心听 | 独立模式，连接蓝牙耳机，副驾随心听前台时取消签约授权，副驾随心听没有自动停止播放并退出 | Pass
FordPhase4Scrum-71343 | 【台架】【CD542H】【随心听签约管理】【必现】独立模式，副驾点击随心听，主驾调起签约页面后关闭分屏，同意签约后，再点击随心听无法打开 | P1 | B1F27_R13.PRO | Baidu | 随心听 | 独立模式，副驾点击随心听，主驾调起签约页面后关闭分屏，同意签约后，再点击随心听无法打开 | Pass
FordPhase4Scrum-71151 | 【台架】【CD542H】【随心听签约管理】【必现】进入随心听，访客签约同意后没有自动进入随心听页面 | P1 | B1F27_R13.PRO | Baidu | 随心听 | 进入随心听，访客签约同意后没有自动进入随心听页面 | Pass
FordPhase4Scrum-74397 | 【实车】【U625ICA】【地图】【必现】语音获取当前位置失败 | P1 | B1F27_R13.PRO | Baidu | 语音 | 语音获取当前位置失败 | Pass
FordPhase4Scrum-73523 | 【台架】【CD542H】【语音】【必现】随心听模块签约整车隐私协议后，语音设置依旧显示去授权按钮，且此时唤醒词无法唤醒 | P1 | B1F27_R13.PRO | Baidu | 语音 | 随心听模块签约整车隐私协议后，语音设置依旧显示去授权按钮，且此时唤醒词无法唤醒 | Pass
FordPhase4Scrum-73500 | 【实车】【U625ICA】【语音】【必现】导航中，语音添加途经点，允许语音唤醒开关关闭 | P1 | B1F27_R13.PRO | Baidu | 语音 | 导航中，语音添加途经点，允许语音唤醒开关关闭 | Pass
FordPhase4Scrum-72980 | 【台架】【CD542h/U625ICA】【语音】【必现】首次全部授权成功后，语音设置页面允许语音唤醒按钮默认关闭状态 | P1 | B1F27_R13.PRO | Baidu | 语音 | 首次全部授权成功后，语音设置页面允许语音唤醒按钮默认关闭状态 | Pass
FordPhase4Scrum-71365 | 【台架】【U625ICA】【语音】【必现】关闭车机管家语音麦克风权限后，语音设置页面显示去授权（其他授权均已开启） | P1 | B1F27_R13.PRO | Baidu | 语音 | 关闭车机管家语音麦克风权限后，语音设置页面显示去授权（其他授权均已开启） | Pass
FordPhase4Scrum-71364 | 【台架】【U625ICA】【语音】【必现】取消隐私授权协议后，语音设置页面未显示去授权 | P1 | B1F27_R13.PRO | Baidu | 语音 | 取消隐私授权协议后，语音设置页面未显示去授权 | Pass
APIMCIS-34856 | 【U625ICA】【偶现】车机重启后点击随心听签署全部协议后出现蓝屏 | P1 | B2F27_R13.PRO.HF1 | Baidu | 随心听 |  | Pass
APIMCIS-34779 | [U625ICA][必现][百度-安全]未签约全部协议时清空后台可以直接进入爱奇艺本地视频 | P1 | B2F27_R13.PRO.HF1 | Baidu | 随心看 |  | Pass
APIMCIS-34665 | [U625ICA][地图][必现]断开车机网络，地图家和公司无法同步 | P1 | B2F27_R13.PRO.HF1 | Baidu | 地图 |  | Pass
APIMCIS-34647 | [U625ICA][地图][必现]点击仪表导航，大屏调起地图，仪表导航菜单项显示空白 | P1 | B2F27_R13.PRO.HF1 | Baidu | 地图 |  | Pass
APIMCIS-34635 | 【实车】【U625ICA】【地图】【必现】我的队伍和队伍管理界面语音继续导航卡片未消失 | P1 | B2F27_R13.PRO.HF1 | Baidu | 地图 |  | Pass
APIMCIS-34634 | 【实车】【U625ICA】【地图】【必现】周边搜任意位置，进入全屏/分屏，poi图标被隐藏 | P1 | B2F27_R13.PRO.HF1 | Baidu | 地图 |  | Pass
APIMCIS-34625 | 【U625ICA】【必现】【仪表】只设置公司地址，仪表导航菜单显示"找不到匹配结果" | P1 | B2F27_R13.PRO.HF1 | Baidu | 地图 |  | Pass
APIMCIS-34399 | 【实车】【U625ICA】【地图】【必现】进入导航，点击设置车牌，未进入操作态，左右两侧控件显示异常 | P1 | B2F27_R13.PRO.HF1 | Baidu | 地图 |  | Pass
APIMCIS-32849 | 【U625ICA】【语音】【必现】语音拨打蓝牙电话，无法匹配纯拼音的用户 | P1 | B2F27_R13.PRO.HF1 | Baidu | 语音 |  | Pass | 1. Must Include Ford & Supplier Fixed Bug List. 2.For Supplier Bug List, should include component, test steps, test result.
APIMCIS-31451 | [U625ICA][1/15h] monkey test，Ford processes have happened anr | P1 | B2F27_R13.PRO.HF1 | Baidu | 车家互联 |  | Pass
APIMCIS-31449 | [U625ICA][1/15H] monkey test,Baidu processes have happened anr | P1 | B2F27_R13.PRO.HF1 | Baidu | 车家互联 |  | Pass
APIMCIS-26716 | [U625ICA][必现][语音]语音设置“重置”字体不适配主题颜色 | P2 | B1F27_R13.PRO | Baidu | 语音 |  | Pass
APIMCIS-27488 | [U625ICA][542L][100%]Traffic consumption prompt stays at 20% | P2 | B1F27_R13.PRO | Baidu | 地图 |  | Pass
APIMCIS-31136 | [Phase4][U625ICA][VPA][必现] 查询股票时切换查询阿里巴巴呢语音提示请先登录QQ音乐 | P2 | B1F27_R13.PRO | Baidu | 语音 |  | Pass
APIMCIS-31137 | [Phase4][U625ICA][VPA][偶现] 看一下杭州明天天气怎么样提示请先登录QQ音乐 | P2 | B1F27_R13.PRO | Baidu | 语音 |  | Pass
APIMCIS-31197 | 【U625ICA】【Performance】Monkey test 中导航一直Crash | P0 | B1F27_R13.PRO | Baidu | 地图 |  | Pass
APIMCIS-31415 | [U625ICA][100%]ETCP WeChat unbinding password-free payment prompt error | P2 | B1F27_R13.PRO | Baidu | ETCP |  | Pass
APIMCIS-31418 | [U625ICA][100%]No voice broadcast when wake up VPA and then simulate crash event. | P1 | B1F27_R13.PRO | Baidu | 语音 |  | Pass
APIMCIS-31452 | [U625ICA][1/15h] monkey test,com.baidu.che.parking have suspected happened memory leak | P0 | B1F27_R13.PRO | Baidu | ETCP |  | Pass
APIMCIS-31453 | [U625ICA][100%] monkey稳定性测试，com.baidu.iov.dueros.car2home发生内存泄漏。 | P0 | B1F27_R13.PRO | Baidu | 车家互联 |  | Pass
APIMCIS-31555 | [U625ICA][必现][地图]经过路口时，地图提示转弯距离和实际距离有误差 | P0 | B1F27_R13.PRO | Baidu | 地图 |  | Pass
APIMCIS-32006 | [U625ICA][100%]The price display of the product detail is unchanged after the specification is modified | P1 | B1F27_R13.PRO | Baidu | 外卖 |  | Pass
APIMCIS-32107 | Phase 4：【必现】【Performance】【U625】【Account】R12版本power on 账号登录较慢（launcher到账号登录10.4s） | P0 | B1F27_R13.PRO | Baidu | 账号 |  | Pass
APIMCIS-32176 | [U625ICA][50%]Select a new city on the movie ticket homepage and refresh it to return to the location of the city | P2 | B1F27_R13.PRO | Baidu | 电影票 |  | Pass
APIMCIS-32561 | [U625ICA][100%]Movie ticket cannot be submitted Order text prompt error | P1 | B1F27_R13.PRO | Baidu | 电影票 |  | Pass
APIMCIS-33203 | 车机无网络，百度地图无法加载正常显示 | P1 | B1F27_R13.PRO | Baidu | 地图 |  | Pass
APIMCIS-33985 | 【U625ICA】【语音】【必现】分屏模式下，副驾无法通过语音打开WIFI | P1 | B1F27_R13.PRO | Baidu | 语音 |  | Pass
APIMCIS-34308 | 【U625ICA】车机休眠或重启后‘’允许语音唤醒’‘的开关不记忆 | P1 | B1F27_R13.PRO | Baidu | 语音 |  | Pass
APIMCIS-34759 | [U625ICA][必现][radio]播放在线视频时来电，车机铃声和FM同时播放 | P2 | B1F27_R13.PRO | Baidu | 随心听 |  | Pass
APIMCIS-35188 | CLONE - 【Phase4 XCL MAP5.1】U625ICA导航静音模式不记忆 | P1 | B1F27_R13.PRO.HF2 | Baidu | 地图 |  | Pass

## Open Bug List
CIA (Customer Impact Assessment)
Key | Supplier | Summery | Priority | Repeat step | Frequency | Affects Version | Issue Analysis |  |  | ICA | PCA | Planned Fix Version | Data Tagging Analysis | Customer Complain
[7 empty] | Risk assessment （Need FO Confirmation） | XCL Evaluation | Root cause
1. Must Include Ford & Supplier Open Issue. 2. For the Priority P0/P1, must fill H-O line. 3. For P2/P3/P4,H-O are not mandatory to fill.

## Metrics
Process | Proposed KPI | Target / Norm | Operational Definition | Achievement Time | R13 | Comments
SWE.1.Software Requirements Analysis | Software Requirements Reviewed Rate % | 100% | Number of approved(reviewed) Software Requirements/ Number of Software Requirements | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100% | 新增/变更需求5 个，已完成
SWE.2.Software Architectural Design | SW Architectural to SW Requirement Coverage Rate | 100% | Jira Traceability/Excel Traceability | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.3 Software Detailed Design and Unit Construction | Traceable Software requirements(Jira Story) to the code | 100% | All Jira requirements should have a corresponding software unit in GIT | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100% | Using Traceability From Code to Requirement&Change_Template to show the evidence.
SWE.3 Software Detailed Design and Unit Construction | SW detail design to SW Architectural Coverage | 100% | Jira Traceability/Excel Traceability | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Unit test（Code） coverage | >= 80 % | (Conditions True + Conditions False + Covered Lines)/(2*Conditions + Executable Lines) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.4 Software Unit Verification | Static Code Analysis Number of Critical Bugs | 0 | Static Code result in Sonar. | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0
SWE.5 Software Integration Test | Planned Integration Test cases vs. actual executed integration test cases | 100% | Percentage of SW integration Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software Integration Test | Software Integration Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software Integration Test | Software Integration Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software Integration Test | Software Integration Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software Integration Test | SW architecture design test coverage (HLD with Ready State test cases) | 100% | (Number of HLD SQD have integration test Case + Number of Interface have integration test case)/(Number of HLD SQD + Number of interface) | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.5 Software Integration Test | Count of Software Integration Test defects | 0 | Count of Integration Defects | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | NA
SWE.6 Software Qualification Test | Planned Qualification test cases vs. actual executed Qualification test cases | 100% | Percentage of SW Qualification Test cases executed against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 99.65% | 阻塞21 总数6138，执行6117 6117/6138=99.65%
SWE.6 Software Qualification Test | SW requirement test coverage | 100% | Percentage of Requirements in Jira that has corresponding test cases in TestRail | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100% | 需求卡片&testcase关联
SWE.6 Software Qualification Test | Software Qualification Test Pass % | 100% | Percentage of Passed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 99.14% | 成功6085 总数6138 6085/6138=99.14%
SWE.6 Software Qualification Test | Software Qualification Test Fail % | 0% | Percentage of Failed test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0.52% | 失败32 总数6138 32/6138=0.52%
SWE.6 Software Qualification Test | Software Qualification Test Blocked % | 0% | Percentage of Blocked test cases against total planned test cases | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0.34% | 阻塞21 总数6138 21/6138=0.34%
SWE.6 Software Qualification Test | Count of Software Qualification test defects | 0 | Count of Defects raised in the SW Qualification Testing Phase | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 0 | 软件测试过程中高危bug 0个
SUP.1 Quality Assurance | NC closure rate | 90% | Closed NC/Total NC | Monthly | NA
SUP.1 Quality Assurance | Process Audit compliance | 100% | Percentage of audits completed on time | Monthly | NA
SUP.8 Configuration Management | Nightly builds have a success rate | 100% | Percentage of compliance as defined in the process audit checklist | Every Sprint | NA
SUP.8 Configuration Management | Baseline completed Rate | 100% | Count of of actually baseline CI Item number/ Count of Planned baseline CI item Number | Monthly | NA
SUP.8 Configuration Management | CM Audit Pass rate | 100% | Pass rate of CM Audit Checklist: Count of passed Number in CM Audit Checklist/total planned CM Audit Checklist | Monthly | NA
SUP.9 Problem Resolution Management | Immediate Gating/Gating （Critical） defects for release | 0 | All urgent defects actioned on high priority, | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 9 | P1 遗留 9 个
SUP.9 Problem Resolution Management | Problem closure adherence | 100% | No. of defects closed against no. of defects planned for closure in this release （Include Project deviation issue and Defect） | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 95.58% | P0提交8个，已解决8个，未解决0个，P0Bug解决率：100%；P1提交196个，已解决187个，未解决9个，P1Bug解决率：95.4%； 总计bug 解决率：195/204=95.58%
SUP.9 Problem Resolution Management | Defect fix time | <40 | Defect fix time | Every Sprint | NA
SUP.9 Problem Resolution Management | Count of IG&G defect @current version | <1 | Count of IG&G defect @current version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 9 | P1 遗留 9 个
SUP.10 Change Request Management | Change Request status closure % | 100% | No. of Change Requests completed / Total number of change requests raised in the version | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100% | 新增/变更需求5 个已完成，见release content-新增功能
MAN.3 Project Management | Requirement Completion Rate for sprint/Milestone | > 85% | No. of requirements delivered / No. of requirements committed for this sprint/Milestone | Every Sprint/Milestone | NA
MAN.3 Project Management | Commitment Adherence for All Requirement | 100% | No. of requirements delivered / No of requirements Committed for all requirement | SOP: All requirement Formal release scope : The requirements planned to be released in this version. | 100% | 当前R13版本目前需求提测率100%（5/5）
Software Metrics Conclusion
Metrics Summary: 1.未修复P1 bug数 9 个，遗留问题影响较小 2.新增/变更需求均已完成，提测率 100% 3.未走基线审核

## Sign off Evidence
截图必须包含 ： 版本号 发起sign off 的名字 Approve 者的名字 Sign off的时间 Note： 1. Sign off的版本以供应商测试完的时间点; 2. Milestone release 副总签字,OKTB 要求总经理签字； Inhouse： Milestone release LL5, OKTB/OTA: LL4;