## Phase4 Master feature list V2.x
ID | Category | Function | Feature |  | Effort Estimation | [6 empty] | FO/Interface |  |  | CD542 |  | CX727 | U725 | P702 | U554 MCA | U625ICA | CD764 | Delivery Plan | File Location | 备注
|  |  |  | Feature carried from Phase 1/2/3 | Desay | Baidu | Ford SW | R&R | DCV0 MRD before 2019-11-20 | DCV1 60% MRD before 2020-02-14 | 100% MRD Before 2020-03-1 | Ford Feature owner | Comments | KO Meeting | Ambient/Trend | Titanium/ST Line | Mid/High | Ford Bronco SUV | Ford Raptor F-150 Pickup truck | Lincoln Navigator Large SUV (3 row seat) | Explorer | Lincoln Sedan
2 | Basic features | EESE/System | Ford Ethernet |  | 90% | 0% | 10% | Desay | x - IP function | x | x | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-22 | 已上传
3 | Basic features | EESE/System | FPD LINK III |  | 100% | 0% | NA | Desay | x | x | x | Guo, Cheng Cheng (C.) <cguo12@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | NA
4 | Basic features | EESE/System | Fully Ford ECU Diagnostic&EOL | Y | 90% | 10% | NA | Desay |  | x | x | Tian, Yuan (EESE.) <ytian22@ford.com> &Wang, Fin (X.Y.) <xwang65@ford.com> | CDD是由DESAY做 SPEC由Ford提供 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-24
5 | Basic features | EESE/System | Ford Cyber Security Requirements | Y | 50% | 50% | NA | Desay/Baidu |  | x | x | Ding, Dean (W.) <wding14@ford.com> / Huang, Eric (E.H.) <chuang98@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Desay：4/14/2020 Baidu：6/1/2020 | 安全
6 | Basic features | EESE/System | Ford Software development Requirements |  | 50% | 50% | NA | Desay |  | x | x | Jian, Ashley (Yao.) <yjian@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | NA
7 | Basic features | EESE/system(inhouse) | Implement/Integrate Ford SOA Structure |  | 90% | 10% |  | Desay |  | x | x | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | NA
8 | Vehicle Features/Interfaces | EESE/System | Welcome&Farewell | Y | 90% | 10% | NA | Desay |  | x | x | Wu, Bella (Y.) <ywu150@ford.com>/Sun, Evan (Yi.) <ysun15@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
9 | Vehicle Features/Interfaces | EESE/IVI(Roger) | Alerts/Chimes | Y | 90% | 10% | NA | Desay |  | x | x | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
10 | Vehicle Features/Interfaces | EESE/System | Mykey | Y | 90% | 10% |  | Desay |  |  | x | Xu, Xiao Kang (X.) <xxu71@ford.com>/Sun, Evan (Yi.) <ysun15@ford.com> |  |  | N | N | Y | N | Y | Y | Y | Y | 2020-05-25
11 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Ford Vehicle Settings On IVI [include: AutoHold, AutoStartStop.] | Y | 90% | 10% |  | Desay |  | x | x | Chen, Emma (J.) <jchen276@ford.com>/Wang, Fin |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
12 | Vehicle Features/Interfaces | EESE/DI | Climate Control (SATC, DATC, Outside Air Temperature, auto air refersh, Heated Steering Wheel) on IVI by HMI and VR | Y | 90% | 10% |  | Desay |  | x | x | Li, Jun (J.) <jli198@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
13 | Vehicle Features/Interfaces | CVPP | Ford TCU Related features (Modem Reset, WiFi, WiFi Hotspot)- TCU transfer CAN data to IVI | y | 90% | 10% |  | Desay |  | x | x | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-24
14 | Vehicle Features/Interfaces | EESE/IVI(Roger) | 支持与仪表盘互动/Supporting interaction with cluster（Phone/Media/Navi） | Y | 60% | 40% | NA | Desay |  | x | x | IVI-Chen, James (J.) <jchen303@ford.com>&IPC Cao, Helen (H.) <hcao22@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
15 | Vehicle Features/Interfaces | EESE/IVI(Diven) | Zone Lighting (360 Lighting) |  | 95% | 5% |  | Desay |  | x | x | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | N | N | N | N | Y | N | N | N | 2020-04-23 | 已上传
16 | Vehicle Features/Interfaces | CVPP | Multi Module OTA (including: USB Update for TCU and ECG; IVI VMCU, CCPU...) |  | 90% | 10% |  | Desay |  |  | x | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-24
17 | Vehicle Features/Interfaces | EESE/IVI(Diven) | Location Service （仪表指南针，etc.） | Y | 95% | 5% | NA | Desay |  | x | x | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
19 | Vehicle Features/Interfaces | EESE/System | Ford Enhanced Memory V2 | Y | 45% | 55% |  | Baidu |  | x | x | Xu, Xiao Kang (X.) <xxu71@ford.com>/Sun, Evan (Yi.) <ysun15@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | TBD | 账号
20 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Ford Clock Strategy | Y | 95% | 5% | NA | Desay |  | x | x | Wang, Fin (X.Y.) <xwang65@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25 | A部分上传 B部分4/25
21 | Vehicle Features/Interfaces | EESE/IVI(Roger) | Support Ford external DSP module by A2B | Y | 95% | 5% | NA | Desay | x | x | x | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com | check for update |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-30 | Link
22 | Vehicle Features/Interfaces | EESE/IVI(PMT1)(Diven) | 车窗控制 Windows Control |  | 95% | 5% |  | Desay |  |  | x | chen, Emma <jchen276@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-30
23 | Vehicle Features/Interfaces | EESE/IVI(PMT1)(Diven) | 天窗控制 Sunroof Control |  | 95% | 5% |  | Desay |  | x | x | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> |  |  | Y | Y | N | N | N | N | N | Y | 2020-05-14
24 | Vehicle Features/Interfaces | EESE/IVI(PMT1)(Forrest) | 后备箱控制/Trunk Control including liftgate/… |  | 95% | 5% |  | Desay |  | x | x | Chen, Emma (J.) <jchen276@ford.com>/ Li, Xuedong (X.) <xli244@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
25 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | Ford车辆系统降噪/Ford Noise reduction ANC | Y | 95% | 5% | NA | Desay | x - basic function - ANC Microphone input | x - basic function w/o calibration | x | Wang, Fin (X.Y.) <xwang65@ford.com>/Yao, Keita (Y.) <yyao21@ford.com> | check for update |  | N | N | N | N | N | Y | N | Y | TBD
26 | Vehicle Features/Interfaces | EESE/IVI(Forrest) | 发动机声音增强/Engine Sound Enhancement | Y | 95% | 5% | NA | Desay |  | x | x | Wang, Fin (X.Y.) <xwang65@ford.com>/Yao, Keita (Y.) <yyao21@ford.com> |  |  | N | Y | Y | N | Y | Y | N | Y | TBD
27 | Vehicle Features/Interfaces | EESE/IVI(PMT3)(Forrest) | 驾驶模式选择/SDM(Selectable Drive Mode) | Y | 90% | 10% |  | Desay |  | x | x | Gu, Zhengfu (Z.) <zgu11@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
28 | 驾驶辅助/Drive assist | DAT | V2I Setting |  | 90% | 10% | NA | Desay |  | x | x | Fan, Henry (H.) <hfan11@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
29 | 驾驶辅助/Drive assist | DAT | Off Road Front View Camera | Y | 90% | 10% | NA | Desay |  | x | x | Wang, Tom (X.) <xwang190@ford.com>/Zheng, Tina (T.) <tzheng4@ford.com> |  |  | N | N | N | Y | Y | N | N | N | 2020-04-24 | 已完成并上传
30 | 驾驶辅助/Drive assist | DAT | Electronic Horizon/ADAS Horizon(Base on ADAS V2 specification) | Y | 30% | 70% |  | Baidu |  | x | x | Li, Cindy (Y.) <yli316@ford.com> | C/O Phase3 |  | N | Y | Y | N | Y | Y | Y | Y | 2020-04-23 | 地图
32 | 驾驶辅助/Drive assist | DAT | Fully Assisted Parking (FIPa, FIPe, FOPa)/全自动泊车 | Y | 95% | 5% | NA | Desay |  | x | x | Lu, Zaikai (Z.) <zlu29@ford.com> |  |  | N | Y | Y | Y | Y | N | Y | Y | 2020-04-25
33 | 驾驶辅助/Drive assist | DAT | TSR/Speed Limit and Overtaking Information Function (SLOIF) | Y | 95% | 5% |  | Desay |  | x | x | Song, Amy (S.) <ssong18@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
35 | 驾驶辅助/Drive assist | DAT | DAT-High Way Assist (Active drive assist) |  | 95% | 5% |  | Desay |  | x | x | Ni, Anthony (H.A.) <hni1@ford.com> |  |  | N | Y | Y | N | N | Y | N | Y | 2020-04-25
36 | 驾驶辅助/Drive assist | DAT | Rear View Camera (RVC)-VGA | Y | 95% | 5% | NA | Desay | x - HD and CVBS | x | x | Zheng, Tina (T.) <tzheng4@ford.com> | check for update |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
37 | 驾驶辅助/Drive assist | DAT | Multi View Camera-360° | Y | 95% | 5% | NA | Desay |  | x | x | Wang, Tom (X.) <xwang190@ford.com>/Zheng, Tina (T.) <tzheng4@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-28
38 | 驾驶辅助/Drive assist | DAT | LCA Lane centering assist (replace TJA) | Y | 95% | 5% | NA | Desay |  | x | x | Ni, Anthony (H.A.) <hni1@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
39 | 驾驶辅助/Drive assist | DAT | Front&Side Parking Radar | Y | 95% | 5% | NA | Desay |  | x | x | Lu, Zaikai (Z.) <zlu29@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25 | A部分上传 B部分4/25
40 | 驾驶辅助/Drive assist | DAT | Rear Parking Radar | Y | 95% | 5% | NA | Desay |  | x | x | Lu, Zaikai (Z.) <zlu29@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25 | A部分上传 B部分4/25
41 | 驾驶辅助/Drive assist | DAT | Cross Traffic Alert | Y | 95% | 5% | NA | Desay |  | x | x | Zhou, Wu (W.) <wzhou44@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25 | A部分上传 B部分4/25
42 | 驾驶辅助/Drive assist | DAT | Reverse Brake Assist |  | 95% | 5% | NA | Desay |  | x | x | Wang, Tom (X.) <xwang190@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25 | A部分上传 B部分4/25
43 | 驾驶辅助/Drive assist | DAT | Lane Change Warning & Aid (LCWA) / Blind Spot Assist | Y | 95% | 5% | NA | Desay |  | x | x | Zhou, Wu (W.) <wzhou44@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
45 | 驾驶辅助/Drive assist | DAT | Intelligent Speed Assistance | Y | 95% | 5% | NA | Desay |  | x | x | Song, Amy (S.) <ssong18@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
46 | 驾驶辅助/Drive assist | DAT | Lane departure warning | Y | 95% | 5% | NA | Desay |  | x | x | Zhang, Wayne (W.R.) <wzhan114@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
47 | 驾驶辅助/Drive assist | DAT | Lane keep aid | Y | 95% | 5% | NA | Desay |  | x | x | Zhang, Wayne (W.R.) <wzhan114@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
48 | 驾驶辅助/Drive assist | DAT | Collision Mitigation (AEB) | Y | 95% | 5% | NA | Desay |  | x | x | Wang, Lynn (X.) <xwang187@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
49 | 驾驶辅助/Drive assist | DAT | Pre Collision Assist for intersections | Y | 95% | 5% |  | Desay |  | x | x | Wang, Lynn (X.) <xwang187@ford.com> |  |  | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
50 | Related to TCU features | CVPP | Vehicle locator | y | 40% | 10% | 50% | Ford CVPP/Desay |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-24
51 | Related to TCU features | CVPP | Wi-Fi hotspot - TCU as WIFI Server (IVI provide HMI) | y | 95% | 5% | NA | Desay |  | x | x | Pan, Yuan (Y.) <ypan23@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
53 | Related to TCU features | CVPP | V2I Lite |  | 40% | 60% | NA | Baidu |  |  | x | Fan, Henry (H.) <hfan11@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | ? | pending on confirm
54 | Related to TCU features | CVPP | 用户流量统计及购买/Cellular data purchase and management |  |  | 30% | 70% | Ford CVPP/Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | Launcher
55 | Ethernet SOA related features | EESE/IVI(Forrest) | Bezel Diagnostics | Y? | 90% | 10% | NA | Desay |  | x | x | Wang, Fin (X.Y.) <xwang65@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-24
56 | Ethernet SOA related features | CVPP | Peripheral Provisioning |  | 90% | 10% | NA | Desay |  | x | x | Cui, Rebecca (H.) <hcui2@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
57 | Ethernet SOA related features | CVPP | Embedded Modem Reset/Master reset |  | 90% | 10% |  | Desay |  | x | x | Ge, Haiqing (H.) <hge5@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
58 | Features of IVI or Connect | EESE/IVI(Forrest) | Digital Owner's Menu(Demo Show) |  | 5% | 5% | 90% | Ford EESE |  |  | x | Geng, Dekang (D.) <dgeng1@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y
60 | Features of IVI or Connect | CVPP | Baidu Local Harzard Information |  | 10% | 90% |  | Baidu |  |  | x | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-06 | 地图
61 | Ethernet SOA related features | CVPP | IP Pass Through Client |  | 90% | 10% |  | Desay |  | x | x | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
63 | Ethernet SOA related features | CVPP | Wireless Interface Router(WIR) |  | 90% | 10% |  | Desay |  | x | x | Lin, Shawn (X.) <xlin17@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
64 | Ethernet SOA related features | EESE/system(inhouse) | FNV2 - FCI Protocol |  | 90% | 10% |  | Desay |  | x | x | Liu, Dapeng (D.) <dliu79@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
65 | Ethernet SOA related features | CVPP | Customer Connectivity Settings |  | 90% | 10% |  | Desay |  |  | x | Ge, Haiqing (H.) <hge5@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-20
67 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Diven) | Power Flow Display |  | 90% | 10% | NA | DESAY |  | x | x | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | Y | Y | N | N | N | N | N | Y | 2020-04-23 | 已上传
68 | HMI | HMI | 快捷面板/quick panel-27 only |  | 100% | 0% |  | Desay |  | x | x | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-04-15 | 已上传
69 | HMI | HMI | Persistant button |  | 100% | 0% |  | Desay |  | x | x | Liu Luisa （27inch） Xiao Yun（15.5inch 13.2inch Lincoln）Wang Lisa （13.2 Ford）Zhou Yujuan（12inch Ford） | 根据新需求 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
70 | HMI | HMI | 主题更换/Theme change by User-->应用适配 |  | 30% | 40% | 30% | Baidu |  |  | x | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 转德赛负责
71 | HMI | HMI | 主题更换/Theme change by User-->主题切换 |  | 90% | 10% | NA | Desay |  |  | x | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-27
73 | Features of IVI or Connect | EESE/IVI(Diven) | 本地及在线音乐/Offline&Online Music Player | Y | 10% | 90% | NA | Baidu | x | x | x | Xu, Amy (X.) <xyafei@ford.com> | refer to BAIDU MRD, 确认对大屏是否其他适配要求 | 福特建议本地/在线音乐和视频/，FM/AM合并，百度确认可行性 | Y | Y | Y | Y | Y | Y | Y | Y | 2020-02-28 | 随心听
74 | Features of IVI or Connect | EESE/IVI(Forrest) | 本地收音机 AM&FM/音频管理（本地+在线） | Y | 90% | 10% | NA | Desay | x | x | x | Wang, Fin (X.Y.) <xwang65@ford.com> | 可以参照Phase1/2 MRD，但是需要在Ford SPEC基础上根据实际需求修改 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
75 | Features of IVI or Connect | EESE/IVI(Forrest) | 在线收音机 Online Radio | Y | 10% | 90% | NA | Baidu | x | x | x | Wang, Fin (X.Y.) <xwang65@ford.com> | C/O Phase1/2 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-06 | 随心听
76 | Features of IVI or Connect | EESE/IVI(Diven) | 本地及在线视频播放/Video Playback | Y | 10% | 90% | NA | Baidu | x - offline USB video playback | x | x | Xu, Amy (X.) <xyafei@ford.com> | 单屏可以C/O Phase1/2 MRD， 但是27"需要重新根据Ford需求写MRD |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-02-28 | 随心听
77 | Features of IVI or Connect | EESE/IVI(Diven) | 视频、音乐、图片DLNA投屏到车机显示器区分主副驾/Video Playback and Video and Photo project to Display(Driver and Passenger) via DLNA |  | 70% | 30% | NA | Desay |  |  | x | Jia, Elaine (T.) <tjia2@ford.com> |  | 后期细化 | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-25
78 | Features of IVI or Connect | EESE/IVI(Diven) | 蓝牙音乐/Bluetooth Media | Y | 60% | 40% | NA | Desay | x - basic function only | x - complete | x | Xu, Amy (X.) <xyafei@ford.com> | 参考Phase1/2的MRD，根据福特新的需求更新MRD，并且27"会增加额外交互 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23
79 | Features of IVI or Connect | EESE/IVI(Diven) | 蓝牙电话（包含微信）/Bluetooth Phone(including Wechat) | Y | 90% | 10% | NA | Desay | x - basic function only | x - complete | x | Xu, Amy (X.) <xyafei@ford.com> | 单屏，蓝牙电话基础部分可以C/O Phase1/2，微信要重新定义 27”需要重新定义 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
80 | Features of IVI or Connect | EESE/IVI(Diven) | 主副驾独立蓝牙系统 V5.0/Driver and passenger Independent Bluetooth service V5.0 (主芯片支持多路HFP，副芯片工作在蓝牙source模式) |  | 90% | 10% | NA | Desay |  | x | x | Xu, Amy (X.) <xyafei@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-04-25
81 | Features of IVI or Connect | EESE/IVI(Diven) | 离线及在线地图和导航/Offline&Online Map and Navigation | Y | 10% | 90% | NA | Baidu | x | x | x | Wang, Jingjing (J.) <jwang354@ford.com> Ding, Xiaojing (X.) <XDING13@ford.com> | 单屏，可以C/O Phase1/2 MRD 27“需要重新定义 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-13 | 地图
82 | Features of IVI or Connect | EESE/IVI(Diven) | AR Navigation (include output to IPC) |  | 20% | 80% | NA | Baidu | x - basic video output | x - basic function | x | Wang, Jingjing (J.) <jwang354@ford.com> Ding, Xiaojing (X.) <XDING13@ford.com> | new |  | N | OPT1 | N | N | N | N | N | N | 2020-02-08 | 地图
83 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Volume Setting V2 |  | 90% | 10% | NA | Desay |  | x | x | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
84 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Audio Management | Y | 90% | 10% | NA | Desay | x | x | x | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com | Phase1/2 YFV，DESAY需要重新做 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
85 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Power Managements | Y | 90% | 10% | NA | Desay | x | x | x | IVI-Song, Rui (Rex.) <rsong2@ford.com>Chen James <JCHEN303@ford.com> | Phase1/2 YFV，DESAY需要重新做 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | A部分上传 B部分4/28
86 | Features of IVI or Connect | EESE/IVI(Roger) | Ford Illumination Requirements | Y | 90% | 10% | NA | Desay |  | x | x | Chen, James (J.) <jchen303@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-31 | 已上传
89 | Features of IVI or Connect | EESE/IVI(Diven) | 图片/小视频浏览器 Picture/video Viewer |  | 90% | 10% | NA | Desay |  | x | x | Jia, Elaine (T.) <tjia2@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
90 | Features of IVI or Connect | EESE/IVI(Diven) | 基础及增强型语音功能/Base and Enhanced VR |  | 10% | 90% | NA | Baidu | x - basic VR function | x | x | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> | 基础VR可以C/O Phase1/2 增加的VR需要根据需求做 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-02-28 | 语音
91 | Features of IVI or Connect | EESE/IVI(Diven) | 双音区语音识别/Dual Zone VR-Clarify | Y | 10% | 90% |  | Baidu |  | x | x | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-06 | 语音
93 | Features of IVI or Connect | EESE/IVI(Diven) | 人脸识别 Face ID (Registration, Recognition, Account, Personalization, Welcome) | Y | 10% | 90% | NA | Baidu | x-basic Face ID feature | x-complete | x | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> | C/O Phase3 | 百度直接输出MRD | N | OPT2 | N | N | N | N | N | OPT2 | 2020-05-14 | 图像 | 时间：待定 原因：因需求需求在5月11日进行变更，且最新的UX同步变更中尚未评审，待按照最新需求的UE评审后2周后输出测试用例
94 | Features of IVI or Connect | EESE/IVI(Diven) | Image recognition - Drive Status Monitor (Fatigue, Distraction, Dangers Behaviour) | Y | 10% | 90% | NA | Baidu |  | x | x | Jia, Elaine (T.) <tjia2@ford.com> |  |  | N | OPT2 | N | N | N | N | N | OPT2 | 2020-05-14 | 图像 | 时间：待定 原因：因需求需求在5月11日进行变更，且最新的UX同步变更中尚未评审，待按照最新需求的UE评审后2周后输出测试用例
95 | Features of IVI or Connect | EESE/IVI(Diven) | Image recognition - Multi-Mode (Hand Gusture / Head / Emotion) |  | 10% | 90% | NA | Baidu |  | x | x | Jia, Elaine (T.) <tjia2@ford.com> |  |  | N | OPT2 | N | N | N | N | N | OPT2 | 2020-05-14 | 图像 | 情绪现在还没有出策略
96 | Features of IVI or Connect | EESE/IVI(Diven) | Face ID with Ford DSM module -> Image recognition with Ford DSMC module (FaceID with DSMC/Driver monitor with DSMC) |  | 10% | 90% | NA | Baidu |  |  | x | Jia, Elaine (T.) <tjia2@ford.com>/ Wang, Johnny (J.) <jwang308@ford.com> Li, Cindy (Y.) <YLI316@ford.com> | new | 百度直接输出MRD | N | Y | Y | N | N | N | N | Y | 2020-05-14 | 图像 | 时间：待定 原因：因需求需求在5月11日进行变更，且最新的UX同步变更中尚未评审，待按照最新需求的UE评审后2周后输出测试用例
97 | Features of IVI or Connect | EESE/IVI(Diven) | 随心拍/Traveling Shooting |  | 30% | 70% | NA | Baidu |  |  | x | Jia, Elaine (T.) <tjia2@ford.com> |  |  | N | Y | N | N | N | N | N | N | 2020-05-14 | 图像 | 已完成
98 | Features of IVI or Connect | CVPP | 车辆故障显示 / Show the vehicle Telltale Warnings |  | 30% | 70% | 0% | Desay |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-25
100 | Features of IVI or Connect | EESE/IVI(Diven) | IVI Wi-FI, IVI Wi-Fi Hotspot-2.4GHz&5GHz - IVI provide HMI to connect other WIFI | y | 70% | 30% | NA | Desay | x - basic function | x | x | Yu, Diven (D.W.) <dyu12@ford.com> | SPEC有更新，需要更新 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
101 | Features of IVI or Connect | CVPP | 账号Account |  | 20% | 80% | NA | Baidu |  | x | x | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 已完成
102 | Features of IVI or Connect | CVPP | 道路救援/Road assistance | Y | 30% | 70% | NA | Baidu |  |  | x | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 转德赛负责
103 | Features of IVI or Connect | CVPP | Emergency Assistance/紧急救援 | y | 40% | 10% | 50% | Ford EESE/Desay |  | x | x | Ren, Siyuan (Alex.) <sren6@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25 | A部分上传 B部分4/25
104 | Features of IVI or Connect | CVPP | 智能家居/Intelligent Home Control | y | 20% | 80% | NA | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 已完成
105 | Features of IVI or Connect | CVPP | 天气/Weather |  | 10% | 90% | NA | Baidu |  |  | x | Shi, Stella (J.) <jshi32@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 已完成
106 | Features of IVI or Connect | CVPP | 保养及在线预约/Vehicle Maintenance and the service booking | Y | 20% | 80% | NA | Baidu |  |  | x | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-06-22
110 | Features of IVI or Connect | EESE/IVI(Forrest) | 车机工程模式(支持车辆工厂模式)/IVI Engineering Mode |  | 90% | 10% | NA | Desay |  | x | x | Wang, Fin (X.Y.) <xwang65@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-07 | 已上传
111 | Features of IVI or Connect | EESE/IVI(Forrest) | Log system |  | 60% | 40% | NA | DESAY |  | x | x | Chen, Emma (J.) <jchen276@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-10 | 已上传
112 | Passenger Feature for 27 | HMI | 对高配27"屏幕，需要支持双屏和驾驶员屏幕独占模式（超级单屏模式）-Launcher |  | 10% | 90% |  | Baidu/Desay |  | x | x | Liu, Luisa (Fan.) <fliu43@ford.com> |  | 待确定--HMI | N | Y | N | N | N | N | Y | Y | 2020-04-01 | Launcher
113 | Passenger Feature for 27 | HMI | 屏幕扩展显示/Extend center or passenger display content(like Navi, to show the whole path in two screens) to two display |  | 40% | 60% | NA | Baidu |  | x | x | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | Y | Y | N | N | N | N | Y | Y | 2020-05-14 |  | 已完成
114 | Passenger Feature for 27 | HMI | 27inch - 本地及在线音乐/Offline&Online Music Player & audio manager |  | 20% | 80% | NA | Baidu |  | x | x | Xu, Amy <XYAFEI@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-05-14 |  | 已完成
116 | Passenger Feature for 27 | EESE/DI | 27"空调设置(climate control from passenger area) |  | 90% | 10% |  | Desay |  | x | x | Li, Jun (J.) <jli198@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-05-10
117 | Passenger Feature for 27 | EESE/IVI(Diven) | 副驾视频播放(支持 DLNA)/Passenger Video Playback(Support DLNA) |  | 80% | 20% | NA | Desay |  | x | x | Jia, Elaine (T.) <tjia2@ford.com> |  | 待确定--福特 | N | Y | N | N | N | N | Y | Y | 2020-05-10
118 | Passenger Feature for 27 | EESE/IVI(Diven) | 副驾在线视频/Online Video-clarify |  | 10% | 90% | NA | Baidu |  | x | x | Xu, Amy (X.) <xyafei@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-04-23 | 随心看
119 | Passenger Feature for 27 | EESE/IVI(Forrest) | 副驾主页/Passenger HomeScreen |  | 20% | 80% | NA | Baidu |  | x | x | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-04-23 | Launcher
120 | Passenger Feature for 27 | EESE/IVI(Diven) | 27"地图/including Passenger Map&Navigation |  | 10% | 90% | NA | Baidu |  | x | x | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-04-23 | 地图
121 | Passenger Feature for 27 | CVPP | 副驾天气预报/Weather forecast |  | 10% | 90% | NA | Baidu |  | x | x | Shi, Stella (J.) <jshi32@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-05-14 |  | 已完成
122 | Passenger Feature for 27 | EESE/IVI(Forrest) | 副驾系统设置/Passenger system setting（system settings display in passenger area as well） |  | 90% | 10% | NA | Desay |  | x | x | Liu, Luisa (Fan.) <fliu43@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-05-10
124 | Passenger Feature for 27 | EESE/IVI(Diven) | 副驾图片浏览器/Passenger Picture Viewer |  | 90% | 10% | NA | Desay |  | x | x | Jia, Elaine (T.) <tjia2@ford.com> |  |  | N | Y | N | N | N | N | Y | Y | 2020-05-10
126 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Diven) | 人物百科 Celebrity encyclopedia | Y | 0% | 100% |  | Baidu |  |  | x | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 语音
127 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Diven) | 世界之最 Most ** of the world | Y | 0% | 100% |  | Baidu |  |  | x | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 语音
128 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 智慧停车 smart parking | Y | 0% | 100% |  | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | offline confirm
129 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 电影购票 ticket booking | Y | 0% | 100% |  | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | offline confirm
130 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 酒店预定 hotel booking | Y | 0% | 100% |  | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | offline confirm
132 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Diven) | 在线视频（爱奇艺） | Y | 0% | 100% |  | Baidu |  |  | x | Xu, Amy (X.) <xyafei@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 随心看
133 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | CVPP | 聚合支付 / aggregate payment | Y | 0% | 100% |  | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | offline confirm
135 | 亮点功能，可以提供在福特产品上的/Software tier1's outstanding features, can be available on Ford IVI. | EESE/IVI(Forrest) | 百度输入法（包括27“主屏输入法） | Y | 10% | 90% |  | Baidu |  | x | x | Chen, Emma (J.) <jchen276@ford.com> |  | 主副驾都需要输入法的情况下，百度无法支持 Phase1/2输入法的问题，福特评估是否能接受 | Y | Y | Y | Y | Y | Y | Y | Y | TBD
136 | Vehicle Features/Interfaces | EESE/IVI(Roger) | AHUD and features (CAN bus interface) | Y | 90% | 10% |  | Desay |  | x | x | Chen, James (J.) <jchen303@ford.com> |  |  | N | N | N | N | N | Y | Y | Y | 2020-04-25 | A部分上传 B部分4/25
137 | Vehicle Features/Interfaces | CVPP | Auto Air Refresh |  | 30% | 70% |  | Baidu |  | x | x | Shi, Stella (J.) <jshi32@ford.com> |  | Shi Stella | N | Y | Y | Y | Y | Y | Y | Y | 2020-04-24
138 | BU features | EESE/IVI(PT)(Diven) | IOD- Behavior Coaching Display Client |  | 95% | 5% |  | Desay |  |  | x | Yu, Diven (D.W.) <dyu12@ford.com> |  | 待确定--HMI | Y | Y | Y | N | N | N | N | Y | 2020-05-24
140 | BU features | EESE/IVI(Roger) | Detroit Symphony Orchestra chimes |  | 100% | 0% |  | Desay |  | x | x | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com |  |  | N | N | N | N | N | Y | N | Y | 2020-04-28
141 | BU features | EESE/IVI(Diven) | IOD - Fuel Economy |  | 90% | 10% |  | Desay |  | x | x | Yu, Diven (D.W.) <dyu12@ford.com> |  | 细节待确定--HMI | N | N | Y | N | Y | N | N | N | 2020-03-31 | 已上传
142 | BU features | EESE/IVI(Diven) | IOD - Pitch and Roll |  | 90% | 10% |  | Desay |  | x | x | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | N | N | Y | Y | Y - aka: off road | N | N | N | 2020-03-31 | 已上传
143 | BU features | EESE/IVI(Diven) | IOD - SeatBelt (information on demand) |  | 90% | 10% |  | Desay |  | x | x | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | N | N | Y | N | Y | N | N | N | 2020-03-31 | 已上传
144 | BU features | EESE/IVI(Diven) | IOD - TPMS (Information on Demand) |  | 90% | 10% |  | Desay |  | x | x | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | N | N | Y | N | N | Y | N | N | 2020-03-31 | 已上传
145 | BU features | EESE/IVI(Diven) | IOD - Trip Information On Demand |  | 90% | 10% |  | Desay |  | x | x | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | N | N | Y | N | Y | N | N | N | 2020-03-31 | 已上传
146 | BU features | EESE/IVI(Diven) | IOD - Off Road |  | 90% | 10% |  | Desay |  | x | x | Yu, Diven (D.W.) <dyu12@ford.com> |  |  | N | N | N | Y | N | Y | N | N | 2020-03-31 | 已上传
147 | BU features | CVPP | Backup Startup Passcode for PAAK | y | 95% | 5% | NA | Desay |  |  | x | Wang, Cindy (X.J.) <xwang216@ford.com> |  | Phase1/2百度已开发的功能，Phase4是否沿用原有的模式，由百度开发？？ | N | N | Y | N | N | Y | N | Y | 2020-05-20
148 | Basic features | CVPP | Message Center (CVPP) | y | 5% | 95% |  | Baidu |  | x | x | Wang, Johnny (J.) <jwang308@ford.com>（Harlow, Julee (J.L.) <jharlow6@ford.com>） |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-17 | 消息中心
149 | Basic features | EESE/IVI(Forrest) | Message Center Client (APIM) |  | 90% | 10% |  | Desay |  | x | x | Xu, Harriet (J.) <jxu128@ford.com> |  |  | N | N | Y | N | N | N | N | N | 2020-04-24
150 | BU features | DAT | Multi Camera - CHMSL/AUX Camera/Rock Crawl |  | 90% | 10% |  | Desay |  | x | x | Zheng, Tina (T.) <tzheng4@ford.com> |  |  | N | N | N | N | Y | N | N | N | 2020-04-24 | A部分上传 B部分4/28
151 | BU features | EESE/Convenience&Security Module team | Multi-Contoured Seats (Enhanced Massage Seats) |  | 90% | 10% |  | Desay |  | x | x | Xia,Zhiqiang<zxia13@ford.com> |  |  | N | N | N | N | N | Y | Y | Y | 2020-04-25
152 | BU features | EESE/Convenience&Security Module team | Multi-Contoured Seats (Massage Seats) | Y | 90% | 10% |  | Desay |  | x | x | Xia,Zhiqiang<zxia13@ford.com> |  |  | N | N | N | N | N | Y | Y | Y | 2020-04-25
153 | BU features | DAT | trail Turn Assist (Soft switch) |  | 90% | 10% |  | Desay |  | x | x | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  |  | N | N | N | N | Y | N | N | N | 2020-04-27 | A部分上传 B部分4/27
154 | BU features | EESE/IVI(PMT1)(Forrest) | Power Running Boards (PRB) |  | 90% | 10% |  | Desay |  |  | x | Chen, Emma (J.) <jchen276@ford.com>/Li, Xuedong (X.) <xli244@ford.com> |  |  | N | N | N | N | Y | Y | Y | N | 2020-05-24 | A部分上传 B部分5/24
155 | BU features | EESE/IVI(PMT1)(Forrest) | Power Tailgate (FordPass/SYNC); |  | 90% | 10% |  | Desay |  | x | x | Chen, Emma (J.) <jchen276@ford.com>/ Li, Xuedong (X.) <xli244@ford.com> |  |  | N | N | N | N | Y | N | N | N | 2020-04-23 | A部分上传 B部分4/27
156 | BU features | DAT | Remote Park Assist (RePA) |  | 90% | 10% |  | Desay |  |  | x | He, Michael (X.) <xhe22@ford.com> |  |  | N | N | N | N | N | Y | N | Y | 2020-05-17
157 | BU features | EESE/IVI(Roger) | Revel QLI 3D Audio (Audio System, settings) |  | 90% | 10% |  | Desay |  | x | x | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com |  |  | N | N | N | N | N | Y | N | Y | 2020-04-28
158 | BU features | EESE/IVI(PMT3)(Forrest) | SELECTABLE DRIVE MODES (different modes for each program) |  | 90% | 10% |  | Desay |  | x | x | Gu, Zhengfu (Z.) <zgu11@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-27 | A部分上传 B部分4/27
163 | Connectivity | CVPP | IVI TCU Provisioning - Baidu cloud, Ford cloud |  | 90% | 10% |  | Desay |  | x | x | Cui, Rebecca (H.) <hcui2@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-31 | 已上传
164 | Connectivity | CVPP | Authorization车机授权 |  | 90% | 10% |  | Desay |  | x | x | Gu, Xiaosheng (X.) <xgu14@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
165 | Connectivity | CVPP | In-vehicle notification | y | 100% | 0% | NA | Desay |  |  | x | Ge, Haiqing (H.) <hge5@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-24
167 | Connectivity | CVPP | Take-away/美团MeiTuan | Y | 0% | 100% |  | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> | Follow Baidu |  | Y | Y | Y | Y | Y | Y | Y | Y | offline confirm
168 | Connectivity | CVPP | Connected Embeded Navigation | Y | 0% | 100% |  | Baidu |  |  | x | Shi, Stella (J.) <jshi32@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-01 | 地图
170 | Connectivity | CVPP | Customer Feedback | Y | 30% | 70% |  | Baidu |  |  | x | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 转德赛负责
171 | Connectivity | CVPP | Ford Finance / Lincoln Finance | Y | 0% | 20% | 80% | Ford CVPP/Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | offline confirm
175 | Connectivity | CVPP | Home to Car |  | 0% | 100% | No related to IVI | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-31
176 | Connectivity | CVPP | Carrier Feed | Y | 0% |  | 100% | Ford CVPP |  |  | x | Wang, Yuran<ywang422@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y
177 | 电池动力汽车相关/Electric Vehicle | CVPP | Battery SoC | y | 30% | 70% |  | Baidu |  | x | x | Ji, Jerry (Y.) <yji9@ford.com> |  |  | N | Y | Y | N | N | N | N | N | TBD | Launcher：3/17
178 | 电池动力汽车相关/Electric Vehicle | CVPP | Charge Status/Charge Time | Y | 30% | 70% |  | Baidu |  |  | x | Ji, Jerry (Y.) <yji9@ford.com> |  |  | N | Y | Y | N | N | N | N | N | 2020-05-14 |  | 交互设计在05月13日锁定，case需要重新写
180 | 电池动力汽车相关/Electric Vehicle | CVPP | Departure Time | Y | 30% | 70% |  | Baidu |  |  | x | Ji, Jerry (Y.) <yji9@ford.com> |  |  | N | Y | Y | N | N | N | N | N | 2020-05-14 |  | 交互设计在05月13日锁定，case需要重新写
181 | 电池动力汽车相关/Electric Vehicle | CVPP | Charge Station Finder | Y | 10% | 90% |  | Baidu |  |  | x | Ji, Jerry (Y.) <yji9@ford.com> |  |  | N | Y | Y | N | N | N | N | N | 2020-05-14 |  | 交互设计在05月13日锁定，case需要重新写
182 | 电池动力汽车相关/Electric Vehicle | CVPP | Trip Planner - BEV only |  | 10% | 90% |  | Baidu |  |  | x | Ji, Jerry (Y.) <yji9@ford.com> |  |  | N | N | Y | N | N | N | N | N | 2020-05-14 |  | 交互设计在05月13日锁定，case需要重新写
183 | 电池动力汽车相关/Electric Vehicle | CVPP | Cloud Enhanced Distance to Empty - BEV only |  | 30% | 70% |  | Baidu |  | x | x | Ji, Jerry (Y.) <yji9@ford.com> |  |  | N | N | Y | N | N | N | N | N | 2020-05-14 |  | 交互设计在05月13日锁定，case需要重新写
184 | 电池动力汽车相关/Electric Vehicle | CVPP | Smart Charging - BEV only |  | 30% | 70% |  | Baidu |  | x | x | Ji, Jerry (Y.) <yji9@ford.com> |  |  | N | N | Y | N | N | N | N | N | 2020-05-14 |  | 交互设计在05月13日锁定，case需要重新写
185 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Forrest) | frunk/前备箱 - BEV only |  | 95% | 5% |  | Desay |  | x | x | chen, Emma<jchen276@ford.com> |  |  | N | N | Y | N | N | N | N | N | 2020-04-27 | A部分上传 B部分4/27
186 | 电池动力汽车相关/Electric Vehicle | CVPP | Rocket setup |  | 30% | 70% |  | Baidu |  | x | x | Gu, Xiaosheng (X.) <xgu14@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 | 账号 | 已完成
187 | 电池动力汽车相关/Electric Vehicle | EESE/IVI(Forrest) | Charge Port Light Settings |  | 95% | 5% |  | Desay |  | x | x | Wang, Fin (X.Y.) (xwang65@ford.com) |  |  | N | Y | Y | N | N | N | N | N | 2020-04-23 | 已上传
188 | VPA | CVPP | Virtual Personal Assistant |  | 0% | 30% | 70% | Baidu/Ford EESE |  |  | x | Sophia Suo <FSUO@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-20 | 语音
189 | Prognostics | CVPP | Prognostics |  | 60% |  | 40% | Ford CVPP/Desay |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-23 | 已上传
190 | Others | EESE/IVI(Forrest) | English HMI(bezel diagnostic, etc.) |  | 10% | 90% |  | Desay |  |  | x | Wang, Fin (X.Y.) <xwang65@ford.com> | 参考bezel diagnostic SPEC以及项目的实际需求 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-30
191 | Basic features | EESE/Wireless | HMI for wireless charging module |  | 10% | 90% |  | Baidu |  |  | x | Lyu, Qingtao (Q.) <qlyu@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 转德赛负责
194 | Connectivity | CVPP | Message notification pushing API for Ford backend/福特后台消息推送接口 |  | 10% | 90% |  | Baidu |  |  | x | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-31
195 | cross carline | HMI | 快速切换最近使用的APP |  | 100% | 0% |  | Desay |  |  | x | Xiao, Yun (Y.) <yxiao21@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-20
196 | cross carline | HMI | Animation [Background, others] |  | 10% | 90% |  | Baidu |  |  | x | Low, Scott (S.) <slow@ford.com>/Han, Lisa (L.) <lhan23@ford.com>/Zou, Emma (E.) <ezou1@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-06-01
197 | cross carline | HMI | Shortcut Keys (program specific) |  | 70% | 30% |  | Desay |  | x | x | Xiao, Yun (Y.) <yxiao21@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-31 | 已上传
198 | cross carline | HMI | Launcher | Y |  |  |  | Baidu | x -partly | x | x | N.A | C/O 5,6,7 |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-06 | Launcher
199 | Connectivity | CVPP | 免密支付 payment without enterring password | Y |  |  |  | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 已完成
200 | Connectivity | CVPP | 违章查询 Query traffic violations | Y |  |  |  | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 之前交付测试中已包含
201 | Connectivity | CVPP | 鲜花预订 flowers ordering | Y |  |  |  | Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 之前交付测试中已包含
202 | Connectivity | CVPP | 机票查询 airplain tickets query | Y |  |  |  | Baidu |  |  | x | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 之前交付测试中已包含
203 | Connectivity | CVPP | 火车票查询 train ticket query | Y |  |  |  | Baidu |  |  | x | Wang, Jingjing (J.) <jwang354@ford.com> Qi, Xuliang<xqi14@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-14 |  | 之前交付测试中已包含
204 | Connectivity | CVPP | 关于（声明）desclaimer [including, account and login in] [ 215 included: desclaimer setting] | Y | 30% | 70% |  | Baidu |  |  | x | chen, Emma <jchen276@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-20 |  | 转德赛负责
205 | cross carline | HMI | Calm Screen | Y | 30% | 70% |  | Baidu |  | x |  | N.A |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-06 | Launcher
206 | cross carline | HMI | Display off | Y | 30% | 70% |  | Baidu |  | x |  | N.A |  |  | Y | Y | N | Y | Y | Y | Y | Y | 2020-03-06 | Launcher
207 | Connectivity | CVPP | 在线商城 online mall | Y |  | 20% | 80% | Ford CVPP/Baidu |  |  | x | Lu, Chao (C.) <clu42@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-06-01
208 | Connectivity | CVPP | Tik tok 抖音 | Y |  |  |  | Baidu |  | x |  | Shi, Stella (J.) <jshi32@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | TBD
211 | Basic features | CVPP | Carrier API integration with Baidu 与百度的接口集成- Carrier Backend Development 运营商后台开发 | Y |  |  | 100% | Ford CVPP |  | x |  | Wang, Yuran<ywang422@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y
214 | Vehicle Features/Interfaces | DAT | Rear Camera on demand | Y | 90% | 10% |  | Desay |  | x |  | Wang, Tom (X.) <xwang190@ford.com>/Zheng, Tina (T.) <tzheng4@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-28 | A部分上传 B部分4/28
216 | Basic features | EESE/IVI(Forrest) | EQ tool | Y |  |  |  | Desay |  |  | x | N.A |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-05-25
217 | Basic features | EESE/IVI(Roger) | Rear Audio Controls | Y | 90% | 10% |  | Desay |  | x |  | IVI-Song, Rui (Rex.) <rsong2@ford.com> Li Alvin LLI156@ford.com |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-03-31 | 已上传
218 | 电池动力汽车相关/Electric Vehicle | CVPP | Charge Conflict Notification Popups | Y |  | 100% |  | Baidu |  |  | x | Yang, Yu (Y.) <yyang158@ford.com> |  |  | N | Y | Y | N | N | N | N | N | TBD
219 | Features of IVI or Connect | EESE/IVI(Forrest) | IVI interface via press physical switch 实体键IVI交互 | Y | 100% |  |  | Desay |  | x |  | Chen, Emma<jchen276@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-28
220 | Features of IVI or Connect | CVPP | Baidu数据平台 |  | 20% | 80% | NA | Baidu |  | x | x | Fan, Henry (H.) <hfan11@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | TBD | 数据埋点
221 | Features of IVI or Connect | CVPP | 个人中心 |  | 20% | 80% | NA | Baidu |  | x | x | Wang, Johnny (J.) <jwang308@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | TBD | 账号
223 | 电池动力汽车相关/Electric Vehicle | CVPP | EV Plug and charge |  | 30% | 70% |  | Desay |  | x | x | Ji, Jerry (Y.) <yji9@ford.com> |  |  | N | Y | Y | N | N | N | N | N | 2020-04-28
224 | 驾驶辅助/Drive assist | DAT | Auto High beam/glare free high beam | Y | 95% | 5% |  | Desay |  | x | x | Song, Amy (S.) <ssong18@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
225 | 驾驶辅助/Drive assist | DAT | DAS: driver alert system | Y | 95% | 5% |  | Desay |  | x | x | Song, Amy (S.) <ssong18@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-25
226 | 驾驶辅助/Drive assist | DAT | ACC/iACC (Setting/HMI) | Y | 95% | 5% |  | Desay |  | x | x | Cui, Victor (M.) <mcui5@ford.com> |  |  | ACC only | ACC only | OPT | N | Y | Y | Y | Y | 2020-04-28
227 | 驾驶辅助/Drive assist | DAT | Speed limiter/intelligent speed limiter | Y | 95% | 5% |  | Desay |  | x | x | Cui, Victor (M.) <mcui5@ford.com> |  |  | Y | Y | Y | Y | Y | Y | Y | Y | 2020-04-28
228 | Vehicle Features/Interfaces | EESE/system(inhouse) | Digital Scent | N | 20% | 0% | 80% | Ford EESE/Desay |  |  | x | Zhang, Xiaojing (X.) <XZHAN247@ford.com> |  |  | N | N | N | N | N | Y | N | Y | TBD
229 | Vehicle Features/Interfaces | EESE/HUD | TFT HUD - setting | N |  |  |  | Desay |  |  | x | Li, Jianxin (J.) <jli294@ford.com> |  |  | N | N | N | N | N | N | Y | Y | ?
230 | Vehicle Features/Interfaces | EESE/System | Lincoln Embrace (vehicle setting: 3-mode selection) | N | 90% | 10% |  | Desay |  |  |  | Wu, Bella (Y.) <YWU150@ford.com> |  |  | N | N | N | N | N | N | N | Y | TBD
231 | Vehicle Features/Interfaces | EESE/DI | Multi-Function Knob |  | 90% | 10% |  | Desay |  |  |  | Yao, Frank (F.) <FYAO2@ford.com> |  |  | N | N | N | N | N | N | N | Y | TBD
232 | Vehicle Features/Interfaces | EESE/DI | modified mini ICP |  | 90% | 10% |  | Desay |  |  |  | Yao, Frank (F.) <FYAO2@ford.com> |  |  | N | N | N | N | N | N | N | Y | TBD
233 | Vehicle Features/Interfaces | PMT2 | Ambient Lighting - Music Visualizer |  | 90% | 10% |  | Desay |  |  |  | Fu, Theo (X.) <XFU7@ford.com> |  |  | N | N | N | N | N | N | N | Y | TBD
234 | Vehicle Features/Interfaces | PMT2 | Ambient Lighting - Breath Control (setting: on/off) |  | 90% | 10% |  | Desay |  |  |  | Fu, Theo (X.) <XFU7@ford.com> |  |  | N | N | N | N | N | N | N | Y | TBD
235 | 驾驶辅助/Drive assist | DAT | Clear Exit Assist | Y | 90% | 10% | NA | Desay |  |  | x | Zhou, Wu (W.) <wzhou44@ford.com> |  |  | N | N | N | N | N | Y | N | Y | TBD
236 | 驾驶辅助/Drive assist | DAT | Digital RVC (stand alone RVC with I2C) |  | 90% | 10% |  | Desay |  |  | x | Wang, Tom (X.) <XWANG190@ford.com> |  |  | N | N | N | N | N | N | N | Y | 2020-05-30
237 | Vehicle Features/Interfaces | EESE/IVI(Diven) | 2D Map in Cluster (study) |  | 20% | 80% |  | Baidu |  |  |  | Wang, Jingjing (J.) <jwang354@ford.com> Ding, Xiaojing (X.) <XDING13@ford.com> |  |  | N | N | N | N | N | N | N | Y | TBD
238 | Vehicle Features/Interfaces | Fordpass | Smart Scene | N | 20% | 0% | 80% | Ford EESE/Desay |  |  |  | Meng, Sheena (M.) <MXIA10@ford.com> |  |  | N | N | N | N | N | N | N | Y | ?
Note on E2: 作者: "Y" 部分沿用Phase1/2/3 设计，只能作为参考，需求以Phase4需求为基准
Note on X6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: other interface
Note on X7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NA
Note on D12: 作者: Settings In Infotainment CenterStack : v1.17
Note on D17: 作者: 通过CAN消息显示车辆OTA信息/Show the OTA status for Vehicle via CAN (FNV2)
Note on X18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GNSS数据传输到车辆系统接口，供车辆其他系统使用。涉及到Sevice层，应覆盖到功能，不建议单独测试。
Note on X19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 因为MRD变更重新排期，DCV1不交付，配合其他模块集成
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: function distributed in PMT1
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: function distributed in PMT1
Note on X25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: confirm with FO
Note on X26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: confirm with FO ?
Note on D29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: VE DAT not related
Note on D30: 作者: ADAS MAP /EH; INPUT for iACC
Note on D60: 作者: 充电电流的显示，谁做HMI谁是lead 11/11: Studio provide animation design
Note on X65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DCV1
Note on X67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DCV1
Note on X68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DCV1
Note on J70: 作者: 不含 双蓝牙
Note on X73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DCV1
Note on X74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DCV1
Note on J80: 作者: 基本的语音功能
Note on X82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MRD delay
Note on D86: 作者: 利用AR导航摄像头拍照和视频，本地功能
Note on D88: 作者: IVI: internet gateWay SPSS IVI as client
Note on X89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MRD delay
Note on X94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6/22提供初版 7/1提供定版
Note on X97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baidu lead
Note on D98: 作者: HMI谁负责谁lead
Note on X102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Full Test Case
Note on X103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Full Test Case
Note on X104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Full Test Case
Note on X105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 独立Case
Note on X108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Full Test Case
Note on X109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Full Test Case
Note on X115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending on 商务
Note on D117: 作者: 内置
Note on D118: 作者: 驾驶行为检测，从别的模块接受信号（如加速，刹车，等），对驾驶行为打分显示出来
Note on D123: 作者: 胎压
Note on X127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MRD已评审，UE时间待定
Note on D129: 作者: 360 camera基础上再增加一些摄像头
Note on D132: 作者: 设置项
Note on D133: 作者: 软开关
Note on D134: 作者: 软开关
Note on D136: 作者: 外置功放
Note on D137: 作者: 可选驾驶模式
Note on X145: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 无HMI
Note on X147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MRD锁定时间未定，MRD更新中，可能有变更，只有727 车型，DCV1不交
Note on D154: 作者: Soft Key SYNC, Ford Pass
Note on D155: 作者: When customers wait for vehicle hand-over, they can do IVI set up on FP in advance. Such as 3rd party ID linkage, wake up words, Pony related
Note on D156: 作者: Improvement based on Phase II
Note on D158: 作者: 诊断; 远程提醒换机油
Note on D165: 作者: mapping to features
Note on X174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wang，Amber确认测试范围
Note on X175: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 因目前福特内部pending在商务某些层面，故DCV1不交付抖音测试用例（2020.04.07）
Note on X180: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 百度反馈已经转给德赛
Note on D181: 作者: function already covered by the others; just reminder here
Note on X182: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BI平台新需求等复工之后忠天和 herry 对齐一下统一给百度提需求，TSP 平台答疑内容整理中，完成后输出给 herry
Note on X183: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 因为MRD变更重新排期，DCV1不交付，配合其他模块集成
Note on X198: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: confirm new feature ?

## 服务功能列表 (hidden)
一期预计实现的功能 The Features to be achived in A project
功能模块 Functional Module | 主功能 Main Features | 一期预计实现功能 The Features to be achived in A project | 功能备注 Features Remarks | 斑马建议 Suggestions from BANMA | Ford工程反馈 Feedback from EESE | 2/2 confirmation | 建议备注 Remarks | 需要长安福特的支持 Supports from CAF
养车模块 Maintenance Module | 车况分析 Vehicle Condition Analysis | 故障监测 Vehicle Fault Monitoring | 01. 获取车辆故障码 01. Get the vehicle fault code | 可支持 | TCU在info CAN上，TCU故障码可支持；BCM，仪表，ECM等其他模块在整车CAN上，没法传；整车故障码显示无法实现。（Leo确认后续SOP可以支持哪些？） | N
|  |  | 02. 图形显示故障部件 02. Graphical display of defective parts | 可支持（有ICON） |  | N
|  |  | 03. 图形显示故障原因 03. Graphical display of fault reason | 只能文字描述收到的故障内容 |  | N |  | 需收到对应的故障码及故障信息
|  | 车辆状态监控 Vehicle Conditon Monitoring （实时行车数据流采集 静态车辆数据采集） （Real-time vehicle driving data acquisition & Static vehicle data collection) | 01. 胎压监测 01. Tire pressure monitoring | 可支持 | 胎压在HS CAN，没法传。Info CAN没有这条信号，做不到。 | N |  | 需收到胎压信号
|  |  | 02. 电池电压监测与预警 02. Battery voltage monitoring and warning | 可以故障显示，没有实时监测及显示 | 检测：电压值可以实时获取。斑马后续和Leo进一步确认如何使用以上数值。 预警：CAF服务部要求斑马增加预警策略，设定某一条件，电池需要更换。电池寿命有无数值？仪表上有此数据。 | N |  | 需收到对应的故障码及故障信息 3/6 赵亮：C520无故障码输出给AHU，此功能取消
|  |  | 03. 轮胎磨损角度监测 03. Tire wear angle monitoring | NOK |  | N |  | 目前无信号可使用
|  |  | 04. 油液夜位监测 04. Oil & fluid level detection monitoring | 可以故障显示，没有实时监测及显示 | 有燃油%，其他油液不确定。 | N |  | 需收到对应的故障码及故障信息 跟REC确认仪表可以提供油量报警信号-赵亮 3/6 赵亮：C520无故障码输出给AHU，此功能取消
|  |  | 05. 车内空气质量监测 05. Air quality monitoring in car | 斑马制定的智能硬件空气净化器可以显示 |  | Y |  | 需用户购买安装空气净化器（斑马已完成适配开发） | 不兼容其他后装的空气净化器。 IVI的屏幕显示出OEM前装的集成在空调内的空净的PM2.5数据。 Tong Tian Offline和斑马及EESE讨论。
|  |  | 06. 车速监测 06. Speed monitoring | 车速在仪表显示，斑马有超速提醒 | 可以收到车速。 | Y |  | 需收到车速信号
|  |  | 07. 瞬时油耗监测 07. Instantaneous fuel consumption monitoring |  |  |  |  | 第一期不需要
|  |  | 08. 平均油耗计算 08. Average fuel consumption monitoring |  |  |  |  | 第一期不需要
|  |  | 09. 燃油花费预测 09. Fuel cost forcast | 暂时没有花费预测，可以有油量低通知（来自仪表信号） | 有燃油%，有里程，但没有直接的百公里油耗，没有续航里程。 需求改为：油量低的信号。 | Y |  | 需收到仪表的油量低信号
|  |  | 10. 行车时间记录 10. Driving time record | 不支持 |  | N
|  |  | 11. 其他车辆状态参数监测 （去掉） 11. Other vehicle conditions monitoring |  |  | N
|  | 车况综合打分 Vehicle condition comprehensive score | 01. 以颜色代表各等级车况得分 01. Using defferent colors represent ech grade condition score | 可支持 斑马给车况打分，核心的输入是保养时间，拿到福特的保养时间和保养逻辑。输入由售后服务提供，每个零件的保养周期及要求。客户的更换情况和更换时间，经销商操作保养复位。经销商工程U盘。权限仅开放给经销商。不支持在其他处保养。 | Risk：此非Raido的功能范畴。是否考虑客户仪表上特殊操作，清理保养纪录？ | Y w/Risk |  | 工程U盘+工程账号进入工程模式进行重置， OEM将 这些东西发放给4S店 2018.2.13：CAF确认权限只给4S店
|  |  | 02. 分3-4个等级 02. Using 3~4 grads to display conditon score | 可支持 |  | Y w/Risk
| 保养提醒 Maintenance Reminder | 耗材保养提醒 Consumables maintenance reminder | 01. 显示需要保养的耗材名称 01. Display name of consumables to be maintained | 可支持 |  | Y
|  |  | 02. 显示何时需要保养 02. Display when to take maintenance | 可支持 |  | Y
|  |  | 03. 显示如何保养 03. Display how to take maintenance | 可支持 |  | Y | 保养更换配件范围
|  |  | 04. 显示该去何处保养 04. Display where to take maintenance | 可支持 |  | Y
|  |  | 05. 保养提醒重置功能 05. The funciton to reset Maintenance Reminder | 可支持 告诉用户需要更换的零件。在用户未实施保养时，有提醒保养过期。 | Risk：此非Raido的功能范畴。播放音乐，导航等时候，是否弹出保养提醒？对用户体验的影响？要求允许用户选择“已经完成保养”。 | Y w/Risk
| 服务预约 Service Booking | 电话预约 Telephone booking | 01. 展示经销商信息 01. Show dealers information(telephone, address and so on) | 可支持 |  | Y
|  |  | 02. 车机蓝牙拨号 02. dial-up with car bluetooth phone | 可支持 |  | Y
|  | 在线预约 Online booking | 对接预约中心在线预约 Docking appointment center & booking online | 需确认双方系统打通的可行性 |  | N |  | 需确认系统开发的负责人跟斑马对接，一起确认可行性及计划 2018.2.13：斑马跟CAF就实现范围达成一致，待PD超超整理后发出 2018.3.6：2018.7月份无法完成，需双方评估新的时间点。
| 活动推广 Activities Promotion | 活动内容投放 Activity content post | 01. 服务市场活动展示 01. Show activity content | [5 empty] | 提醒内容的维护谁负责？操作流程？ Ford/CAF对接斑马活动运营团队，拟定好后，斑马推送消息给指定车主。目前不开放给OEM，未来系统打通后，可以直接下发。
|  |  | a. 全客户群活动通知推送 a. Push notification to all customers | 可支持 |  | Y
|  |  | b. 目标客户群精准通知推送 b. Push notification to target customers | 可支持 |  | Y
|  |  | 02. 客户关怀活动展示（视频） 02. Show customer care activities ( video ) | 不支持 |  | N
|  |  | 03. 技术服务活动展示 03. Show technical activities | 可支持 |  | Y | 推送消息
| 服务进展 Services Progress Monitoring | [6 empty] | 第一期不需要
道路救援 Road Assistance | 原厂救援 OEM Assistance | 救援电话展示 Show road assistance telephone | 车机蓝牙拨号 Dial-up with care bluetooth phone | 可支持 |  | Y
|  | 救援公司平台集成 Dock road assistance company's platform | 01. 车机拨号 01. Car machine call road assistance telephone | NOK | 是否可以放在手机APP上直接打电话，APP发出车辆位置，第三方请求车辆位置和车辆数据。 手机打电话，车机上显示服务码，告知服务码，服务器端获取车辆位置？斑马评估。Leo评估下TCU增加B-Call放在SOP2时间可能性，以及其他车型的可能性。 | N | TCU没有B-Call功能，不能通过Tbox拨打电话同时将故障车辆位置发给救援公司平台 | 建议未来TCU增加B-Call功能
|  |  | 02. 推送客户位置信息给救援公司 02. Push customer's address to road assistance company' platform |  |  | N
|  |  | 03. 车机上获得救援车辆实时位置信息 03. Car machine get real-time address of road assistance vehicle |  |  | N
保险 Insurance | 场景险 Scenes insurance | 保险介绍 Introduce Insurance products | 01. H5链接保险产品信息 01. H5 Link insurance products informaiton | 可支持推送消息 |  | Y | 仅推送消息，不显示保险信息
|  |  | 02. 车机上推送保险产品介绍 02. Show insurance products | 可支持推送消息 |  | Y | 仅推送消息，不显示保险信息
|  | 投保功能（是否为长安福特产品？） Buy insurance | 01. 恶劣天气自驾险 01. F.P.G. for self-driving in bad weather | 可支持 | 产品下线时是否支持可配置？福特需要具备可Disable能力。 | N |  | 2018.2.13：CAF确认2018.7月份不上
|  |  | 02. 长距离自驾险 02. F.P.G. for selft-driving long distances | 可支持 | 产品下线时是否支持可配置？福特需要具备可Disable能力。 | N
在线销售模式 Sales Online | 销售平台 Sale platform | 产品介绍 Introduce products | 01. 产品宣传 01. Products introduction | CAF可以上线天猫或者淘宝店铺，斑马可支持在车主手机淘宝中通过车主卡片作为入口，推广销售对应车型的商品，服务。 |  | N |  | 1. CAF上线淘宝或天猫店铺，并上架对应产品 2. 店铺开一个淘客活动给到斑马 2018.2.13：CAF确认2018.7月份不上
|  |  | 02. 目标客户产品信息推送 02. Show products information |  |  | N
|  | 产品销售 Sale proudcts | 01. 销售ESB产品 01. Sale ESB products |  |  | N
|  |  | 02. 销售原厂附件 02. Sale OEM Accessories |  |  | N
|  |  | 03. 销售原厂重要耗材 03. Sale OEM consumables |  |  | N
|  | 在线结算 Settle accounts online | 01. 资金流处理 01. Settle accounts |  |  | N
|  |  | 02. 发票推送 03. Push invoicement |  |  | N
二期预计实现的功能 The Features to be achived in B project
功能模块 Functional Module | 主功能 Main Features | 一期预计实现功能 The Features to be achived in A project | 功能备注 Features Remarks | 斑马建议 Suggestions from BANMA |  |  | 建议备注 Remarks | 需要长安福特的支持 Supports from CAF
养车模块 Maintenance Module | 车况分析 Vehicle Condition Analysis | 远程诊断 Remote diagnosis | 01. 车主远程诊断申请功能 01. One key to apply remote diagnosis
02. 远程诊断受理反馈 02. Feedback remote diagnosis accepted
03. 技术人员远程登录车机 03. Technician log in marchine remotly
04. 远程故障诊断 04. Diagnose fault remotly
05. 生成故障诊断报告与维修方案 05. Generate diagnosis report and repair program
06. 维修方案费用预算报告 06. Generate repair cost report
07. 推送车主信息与维修方案至4S店平台 07. Post customer information and repair proposal to dealer
08. 故障案例存入中心知识库
| 保养提醒 Maintenance Reminder | 智能保养 Intelligent Maintenance | 引入“保养顾问”概念，为车辆定制保养 Create new concept - 'Maintenance Advisor', to customize maintenance program for customer.
01. 基于客户消费习惯，用车习惯，车辆综合车况定制常规保养方案 01. Customize general maintenance proposal base on customer spending habits, driving habits, vehicle conditions, and so on.
02. 定制车辆临时保养方案(如长距离行驶，极端环境行车) 02. Customize temporary maintenance proposal
03. 人机互动与人文关怀 04. Human-Computer interaction and Humanistic care
| 服务预约 Service Booking | 预约互动 Interaction of service boooking | 01. 经销商预约资源推送 01. Post Booking source
02. 生成在线预约报价单 02. Generate online booking quote
03.客户报价信息推送给经销商 03. Post online booking information to dealer
| 活动推广 Activities Promotion | 互动与闭环管理 Interaction and close loop management | 01. 活动提醒与查询 01. Activities reminder and inquiry
02. 客户在线互动咨询 02. Online advisory and interaction
03. 预约并引导客户回厂 03. Guide customer to dealer
04. 购买，使用与核销 04. Purchase, use and settle acounts
| 服务进展 Services Progress Monitoring | 维修进度实时查询 Inquire real-time repair schedule | 平台需要开发维修进度实时接收端口和实时输出端口
|  | 电子车辆检查报告 Electric vehicle inspection report | 平台需要开发维修报告实时接收端口和实时输出端口
|  | 车辆到店提醒 Vehicle arriving reminder | 车辆到店后提醒经销商接待车主
|  | 车辆检测在线查询 Inquire vehicle inspecion online | IPAD接车与电子检查报告反馈
|  | 维修结果在线反馈 Feed back repair result online | 反馈客户维修结果与维修费用
道路救援 Road Assistance | 原厂救援 OEM Assistance | 客户自费救援 Customers pay road assistance | 救援服务零售 Retail road assistance service
保险 Insurance | 保险 insurance | 车险 Vehicle insurance | 01. 一键投保 01. One key to buy vehicle insurance
02. 报案理赔 02. Report claims
03. 基于客户特征的数据分析 03. Data analysis base on customer features
04. 事故车辆返厂监控 05. Monitor return data of accident vehicle
在线销售模式 Sales Online | 销售平台 Sale platform | 目标客户画像 Target customer figure
多场景的消费引导 Multi-scene guiding to spend