## Security
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Source 问题来源 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
0 |  | Security | Customer | Q: Does FordDuerOS project need to follow A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document? | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
1 |  | Security | Customer | Q:Please provide the TCU Hardware Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: about Ford part number for the TCU module hardware. The part number is generated by Ford and given to the supplier. | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
2 |  | Security | Customer | Q:Please provide the TCU Assembly Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: about Ford Assembly Part Number for the TCU module hardware. The part number is generated by Ford and given to the supplier. | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
3 |  | Security | Customer | Q:Please provide the TCU Assembly Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: about Ford Assembly Part Number for the TCU module hardware. The part number is generated by Ford and given to the supplier. | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
4 |  | Security | Customer | Q:Please provide the Destination Region Code In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
5 |  | Security | Customer | Q:Please provide the Main/Host Processor Strategy Software Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
6 |  | Security | Customer | Q:Please provide theMain/Host Processor Config Software Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: . | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
7 |  | Security | Customer | Q:Please provide the Secondary Processor Strategy Software Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: . | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
8 |  | Security | Customer | Q:Please provide the Key Rotation and Rekeying Security Specification. In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: . | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
9 |  | Security | Customer | Q:Please provide S13b Security Specification. In Key Material Requirements.pdf document: . | YangHui | 2019-05-22 | Medium | 应该不适用 ----再确认 | Xu, Jinchi | 2019-06-05 | Open
10 |  | Security | Customer | Q:Please provide a Ford root CA. In Key Material Requirements.pdf document: .Unless otherwise noted, all certificates used shall be derived from a Ford root CA. | YangHui | 2019-05-22 | Medium | Cert/Key由Ford 提供的为：Code signing 以及Secure Boot | Xu, Jinchi | 2019-06-05 | Open
11 |  | Security | Customer | Q:Please provide ESN prefix generation (3 characters) shall be determined by Ford. In Key Material Requirements.pdf document: provide ESN prefix generation (3 characters) shall be determined by Ford. | YangHui | 2019-05-22 | Medium
12 |  | Security | Customer | Q: Does FordDuerOS project need to follow Connected Vehicle Mobile Applications Standard.pdf document? | YangHui | 2019-05-22 | Medium | 适用于Mobile APP不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
13 |  | Security | Customer | Q:Please provide App signing RSA keys from Ford In App_signing_requirements_ver 1.3 | YangHui | 2019-05-22 | Medium | Cert/Key由Ford 提供的为：Code signing 以及Secure Boot | Xu, Jinchi | 2019-06-05 | Open
14 |  | Security | Customer | Q:Please provide S26, S25, and S23 series requirements.. In In App_signing_requirements_ver 1.3 . | YangHui | 2019-05-22 | Medium
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## Sheet1 (hidden)
Req Type 需求类型 | Feasibility 可行性分析 | Verification Phase 验证阶段
Functional 功能需求 | Feasible 可行 | System Test 系统测试
Non-Functional 非功能需求 | Under disscussion 待讨论 | Vehicle Test 实车测试
Interface 接口需求 | Not Feasible 不可行 | Sys IT 系统集成测试
根据需求描述分析：
可行性
可验证性
分析结论：
Accept
Under disscussion
Reject
需要讨论的需求需要在Q&A中创建一个问题，与之对应
分析结论作为Q&A的输入
如果发现风险需要在创建一个风险，与之对应

## Tuner
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Models 模块 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
16 |  | Software Req | Customer | 自动存储---切换到预设列表，列表区域更新为自动存储的电台，当前播放频率不跟随切换 比如： 当前在FM，是不是值需要自动存储FM，不需要存储AM。 当前在AM，是不是值需要自动存储AM，不需要存储FM。 | Wen Yaojun | 2019-05-22 | Medium | 是的 | Yu Justin | 2019-06-13 | Close
17 |  | Software Req | Customer | 自动更新站点的场景有哪些？ | Wen Yaojun | 2019-05-22 | Medium | 顾客手动点 Autostore 选项，IVI会自动更新radio station | Yu Justin | 2019-06-13 | Close
Note on B4: 问题溯源到的需求ID
Note on C4: 来源(系统需求、软件需求)
Note on D4: 问题类型(客户、供应商、内部)
Note on H4: 高中低
Note on L4: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## CAN
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Models 模块 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
19 |  | Netcom | Customer | 什么时候释放ARXML/CDD/MDX数据文件？ | Chen Xiujing | 2019-05-22 | Medium | Ford发送CDD文件给desay，进行诊断（Part4 已提供，在诊断文件夹） | Leo Wang | 2019-06-13 | Close
20 |  | Netcom | Customer | 什么时候释放ECU Function需求文件？ | Chen Xiujing | 2019-05-22 | Medium | Part4 已提供，工具需要weihao要权限下载 | Leo Wang | 2019-06-13 | Close
21 |  | Netcom | Customer | 会议沟通了解到，Ford会提供以下测试工具，计划什么时候释放？ MUX testing SW： MAVS Diagnostic Part1 test： Diagnostic Script Player；Diagnostic Script Setup tool。 | Chen Xiujing | 2019-05-22 | Medium | Part4 已提供，工具需要weihao要权限下载 | Leo Wang | 2019-06-13 | Close
39 | NA | Diagnostic | Customer | 文档： Phase4 Diag Req Sheet 问题： Config bits DE07 Byte8 Bit7-4相关的配置参数，长度（Length）描述有错误，本来占1Bit，Sheet里写8Bit。然后剩下的Bit3-0没有参数，也没有描述。 | ChenYun | 2019-12-23 | High | 是1bit，会更新。没有定义的bit用reserved补齐 | Fin Wang | 2019-12-15 | Close
40 | NA | Diagnostic | Customer | 文档： DS-LJ7T-14H158-FB 问题： Extended Data Record used for Aging Counter (0x02)：对应GGDS哪个命令？ | ChenYun | 2019-12-23 | medium | 请参考GGSD 4.2.1.3 | Fin Wang | 2019-12-15 | Close
41 | NA | Diagnostic | Customer | 文档： DS-LJ7T-14H158-FB 问题： Extended Data Records Supported (0x02,0x10)：对应GGDS哪个命令，具体什么意思？ | ChenYun | 2019-12-23 | medium | 请参考GGSD table 4.13和4.14里02和10 | Fin Wang | 2019-12-15 | Close
42 | NA | Diagnostic | Customer | 文档： DS-LJ7T-14H158-FB 问题： Monitoring Cycle：Ignition ON->OFF和Operation-Cycle RUN有什么区别？ | ChenYun | 2019-12-23 | medium | operation cycle是针对continous DTC来说符合条件的时间，与ign cycle不同 | Fin Wang | 2019-12-15 | Close
Note on B5: 问题溯源到的需求ID
Note on C5: 来源(系统需求、软件需求)
Note on D5: 问题类型(客户、供应商、内部)
Note on H5: 高中低
Note on L5: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## BT
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Models 模块 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
c |  | Software Req | Internal | 蓝牙开启需要几秒？ | fangzewen |  | Medium | 不超过1s | xuyafei
23 |  | Software Req | Customer | 蓝牙耳机是否支持mic | xuyafei |  | Medium | 可以支持
24 |  | Software Req | Internal | SPSS文档上2.17要求可配置，具体配置什么？ | wanglei | 2019-05-17 | Medium
25 |  | Software Req | Internal | SPSS文档上2.12 - BRSF Value - CHLD Capabilities 是指什么？？ | wanglei | 2019-05-17 | Medium
26 |  | Software Req | Internal | SPSS文档上3.1.4的iAP是指什么？ | wanglei | 2019-05-17 | Medium
27 |  | Software Req | Customer | 微信语音及视频的支持？ |  |  | Medium
28 |  | Software Req | Customer | LDAC音频编码是否可配置为可选项？ | wanglei | 2019-05-17 | Medium | 可以支持
29 |  | Software Req | Customer | 可以支持headset profile么？ | xuyafei | 2019-05-10 | Medium | 可以支持，目前推荐副驾的BT 支持蓝牙耳机，耳机也是连接A2DP , 所有的HFP （4部手机都连接主驾的BT HFP协议） | chendingzhu | 2019-05-10
30 |  | Software Req | Customer | 同一时刻，可以连接多少台设备，（BT corev5.0可支持同时连接的设备是7个）？ | xuyafei | 2019-05-10 | Medium | 主驾的BT 可以连接最多4个手机 的HFP ，采用仲裁机制 ， 那个优先来电接通那个电话， 通话过程中的其他手机来电，有用户自己在界面选择是否接听 | chendingzhu | 2019-05-10
|  | Software Req | Customer | 同一时刻，HFP可以建立多少条链路，A2DP可以建立多少条，HSP可以建立多少条？ | xuyafei | 2019-05-10 | Medium | HFP 见上面的回复， A2DP 我们目前建议只保持一路连接 。 | chendingzhu | 2019-05-10
|  | Software Req | Customer | 同一时刻，可以做source的角色 又可以做sink的角色（即连接手机设备的时候同时连接蓝牙耳机设备） | xuyafei | 2019-05-10 | Medium | 目前评估只有个别的BT Stack 供应商能够实现， 在支持LDAC 990K 高音质连接的时候， UART 的带宽是一个比较大的挑战 ， 我们担心系统稳定性。 其实从用户的使用场景看，用处并不大。下午的会议可以细谈。 | chendingzhu | 2019-05-10
|  | Software Req | Customer | 主驾的蓝牙作为sink，连接手机设备或者多媒体设备；副驾的蓝牙作为source，连接耳机设备 | xuyafei | 2019-05-10 | Medium | 确认ok | chendingzhu | 2019-05-15
|  | Software Req | Customer | 主驾的蓝牙，同一时刻至少能够连接4个设备，同一时刻需要能够支持，4条HFP链路，4条A2DP链路 | xuyafei | 2019-05-10 | Medium | 跟BT协议栈供应商确认可以实现 | chendingzhu | 2019-05-15
|  | Software Req | Customer | 主驾蓝牙，同时连接Driver和passenger的手机设备，driver在播放蓝牙音乐过程中，passenger播放蓝牙音乐，需要能自动抢占音源 | xuyafei | 2019-05-10 | Medium | 这个是逻辑控制层的需求， 评估可以实现 | chendingzhu | 2019-05-15
|  | Software Req | Customer | 需要支持的场景：主驾蓝牙，同时连接Driver和passenger的手机设备，driver在通话过程中，passenger接到来电，（可以在界面提醒用户是挂断driver的电话，还是driver的电话保持or其他选项）。如果passenger接通电话，选择在车机端接听，driver的电话应该自动切换到私密模式 | xuyafei | 2019-05-10 | Medium | 确认可以实现， 但是用户体验是否好，还需要福特推敲，个人觉得不是很合理， 开车的过程中把电话转成私密，驾驶员是没有办法接听的，还涉嫌违章 | chendingzhu | 2019-05-15
|  | Software Req | Customer | 1） 蓝牙App功能，不能出现卡顿的情况，德赛需要清楚协议栈的负载能力，看情况是否需要对用户行为做出限制。(4路HFP同时active，是否有性能问题) | xuyafei | 2019-05-21 | Medium | 参照刚才转给你的邮件的问题1， 同一时间只能有一个手机处于通话中， 关于一个手机的多方通话不要跟HFP的连接混于一谈， 四路HFP同时连接是没有问题的， 同一时间只有一个手机处于连接状态，因此带宽不是问题。有问题的是我们的控制逻辑。 | chendingzhu | 2019-05-21
|  | Software Req | Customer | 2） 需要支持基本的微信通话功，同时，微信语音是否采用A2DP传输，微信语音音源是否可以抢占？ | xuyafei | 2019-05-21 |  | 是的，必须抢占
|  | Software Req | Customer | 3)微信外设协议 | leo | 2019-05-21
|  | Software Req | Customer | 4） 主副驾都需要有LDAC开关。需要了解协议栈供应商是否支持4路A2DP的LDAC开关选项，每路LDAC 都要支持990kbps和660kbps两个选择 | xuyafei | 2019-05-21 | Medium | 可以支持 | chendingzhu | 2019-05-21
|  | Software Req | Customer | 5） 主屏只有一个设置界面，显示主屏蓝牙芯片的连接列表。副屏有两个设置界面，除了显示主屏芯片的蓝牙连接，还要显示副屏蓝牙芯片的连接状态。 | xuyafei | 2019-05-21 | Medium | 可以支持
|  | Software Req | Customer | 6） 不需要支持邮箱和短信，但是要支持OPP文件传输，协议栈是否支持 | xuyafei | 2019-05-21 | Medium | 可以支持 | chendingzhu | 2019-05-21
|  | Software Req | Customer | 7） 副驾蓝牙耳机是否有mic可支持微信通话 | xuyafei | 2019-05-21 | Medium
|  | Software Req | Customer | 1） 耳机控制的基本功能需要实现，AV2CP； | xuyafei | 2019-05-21 | Medium | 应该是AVRCP 吧，可以支持 | chendingzhu | 2019-05-21
|  | Software Req | Internal | 4路HFP的场景非常复杂，是否可以先限制2路HFP？ | liudaxin | 2019-05-22 | Medium
|  | Software Req | Customer | 双蓝牙系统，方案以及蓝牙芯片，协议栈的选型，以及协议栈能够提供的能力 | xuyafei | 2019-05-22 | Medium | 正在确定方案中
|  | Software Req | Customer | 微信语音的兼容性：目前微信语音和手机型号有关，部分手机，微信语音通过A2DP，部分手机，通过HFP 支持通过HFP传输的手机，必须支持任何时候，用户点击微信语音，都能够通过车机播放微信语音消息 支持通过A2DP传输的手机，在当前音源是蓝牙源的情况下，用户点击微信语音，都能够通过车机播放微信语音消息 | xuyafei | 2019-05-22 | Medium | 除部分手机兼容性问题，可以支持
|  | Software Req | Customer | A2DP协议的编码，主副屏都要支持LDAC, AAC ,SBC 编码 | xuyafei | 2019-05-22 | Medium | AAC/LDAC的产品化阶段需要购买License，请Desaysv直接与AAC LDAC原厂沟通采购。是否解码也需要这三种格式
|  | Software Req | Internal | 邮件功能是否需要支持 | wanglei | 2019-05-16 | Medium | 短信/电子邮件功能不需要实现 | xuyafei | 2019-05-16
|  | Software Req | Internal | 主/副屏是否可以分开点亮控制 | wanglei | 2019-05-16 | Medium | 主/副屏可以分开点亮控制 | xuyafei | 2019-05-16
|  | Software Req | Internal | 主屏是否需要支持耳机设备 | wanglei | 2019-05-16 | Medium | 主屏不需要支持耳机设备 | xuyafei | 2019-05-16
|  | Software Req | [5 empty] | A2DP协议需要支持的编码格式：SBC AAC LDAC | xuyafei | 2019-05-16
|  | Software Req | Customer | 目前一个手机可以存在3路电话，我们可以接入 4个HFP的手机设备，接入的电话数量可以做限 制，最少支持8路电话 | xuyafei | 2019-05-16 | Medium | 可以支持
|  | Software Req | Customer | 主驾蓝牙支持的协议：除基本协议之外，需要支 持HFP ,A2DP, AVRCP,PBAP,OPP | xuyafei | 2019-05-16 | Medium | 可以支持
|  | Software Req | Customer | 副驾蓝牙支持的协议：除基本协议之外，需要支 持A2DP，AVRCP,HSP（蓝牙耳机，蓝牙音箱 等设备），如果连接的蓝牙耳机有MIC，需要 支持MIC的使用，为后续扩展，视频会议，车 载微信等app服务 | xuyafei | 2019-05-16 | Medium | MIC可以支持，微信会议我要继续调研
|  | Software Req | Customer | 主/副屏上显示电话dialog一样，如果存在多路 电话，可以在屏幕上弹出提示框，由用户选择 每路电话音频的输入/出 |  |  |  | 可以支持
|  | Software Req | Customer | 副屏的蓝牙一直工作在不可被发现模式(主驾 蓝牙不可以检测到蓝牙), 但可以在连接模式时 检测到SINK设备（比如耳机）并完成配对，同 时可以和已配对蓝牙设备自动连接 | xuyafei | 2019-05-16 | Medium | 可以支持
|  | Software Req | Customer | 主屏蓝牙和副屏蓝牙同时打开时：副驾蓝牙的 搜索列表中显示SOURCE（如手机）设备和sink 设备，当点击SOURCE（如手机）设备的时候， 连接是主驾的蓝牙，当点击sink设备的时候， 连接的是副驾的蓝牙； 主屏蓝牙关闭，副驾蓝牙打开，副驾蓝牙只能 搜索到的是sink设备 | xuyafei | 2019-05-16 | Medium | 可以支持
|  | Software Req | Customer | 导航界面，来电时，弹出的是来电的缩略框，方便接听电话，又能看导航界面 | xuyafei | 2019-05-16 | Medium | 可以支持
|  | Software Req | 协议栈供应商 | 目前一个手机可以存在3路电话，我们可以接入4个HFP的手机设备，接入的电话数量可以做限制，最少支持8路电话 | 协议栈供应商 | 2019-05-23 | Medium | 是指每路HFP都要支持三方通话（2*4 = 8）， 具体哪路通话通过车机扬声器输出，可以由用户选择 | xuyafei | 2019-05-24
|  | Software Req | 协议栈供应商 | 车机中的SIM卡是否有电话动作 | 协议栈供应商 | 2019-05-23 | Medium | 不做电话动作 | xuyafei | 2019-05-24
|  | Software Req | 协议栈供应商 | A2DP协议的编码，是否主副屏都要支持LDAC, AAC ,SBC 编码 | 协议栈供应商 | 2019-05-23 | Medium | 主屏蓝牙芯片不做src，只需要做解码，如手机传送LDAC音频， 主频需要根据LDAC的设置，做出解码 | xuyafei | 2019-05-24
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.1 MD-REQ-273358/B-HMIAudioMode About the "HMIAudioMode“, what's the difference between Inactive and OFF? What does the "Load Shed Active" mean, any different from the ON mode? | Jiang Lixiao | 2019-05-22 | Medium | inactive 是为不激活状态，即初始状态。 Off是关闭状态。 Load Shed Active：被动进入低功耗模式，电池保护，某些节点在电池电压低时不需要供电 |  |  | Closed | 出差与Leo确认
Note on B5: 问题溯源到的需求ID
Note on C5: 来源(系统需求、软件需求)
Note on D5: 问题类型(客户、供应商、内部)
Note on H5: 高中低
Note on L5: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## Power
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注 | Question Status | Remark 备注
No. | Req ID 需求ID | Models 模块 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态 |  | Status 问题状态
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.1 MD-REQ-273358/B-HMIAudioMode About the "HMIAudioMode“, what's the difference between Inactive and OFF? What does the "Load Shed Active" mean, any different from the ON mode? | Jiang Lixiao | 2019-05-22 | Medium | inactive 是为不激活状态，即初始状态。 Off是关闭状态。 Load Shed Active：被动进入低功耗模式，电池保护，某些节点在电池电压低时不需要供电 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.1 MD-REQ-273358/B-HMIAudioMode What's the "System Master"? What does the "Infotainment modules" include? | Jiang Lixiao | 2019-05-22 | Medium | 我们主机就是System Master。 这条消息是主机进入某种状态后，发出去的，告诉别人我处于什么状态。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.5 MD-REQ-273721/B-CarMode Any more requirments for the Carmode? | Jiang Lixiao |  | High | Carmode是状态图中最外面那个圈。 [2019-5-24,JLX]Carmode问题，细节另起QA，关闭此条内容。 |  |  | Closed
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.6 MD-REQ-273722/A-_Battery_Mgmt_2 What's the "load shed event"? | Jiang Lixiao | 2019-05-22 | Medium | "load shed event"是HU被动进入低功耗模式的消息。 [2019-5-20, JLX]参考“1.1.1.6 MD-REQ-273722/A-_Battery_Mgmt_2” ，另外，load shed的优先级最高，如果HMIAudioMode的逻辑遇到需要设置load shed，优先设load shed。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.7 MD-REQ-273727/A-ActvNse_B_Actv What's the "ANC status" and "ANC Server"? | Jiang Lixiao | 2019-05-22 | Low | 我们主机有做ANC功能，因此我理解"ANC Server"是主机，"ANC status"是指ANC工作或不工作。 [2019-5-21, JLX]Power只需从ANC模块获取信息，并将信息转发给CAN即可，不做逻辑处理（逻辑在ANC模块处理）。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.11 MD-REQ-273750/A-Ignition_Status Any more requirments for the "ignition status "? | Jiang Lixiao | 2019-05-22 | High | Accessory, Run, Start可以当成一种情况来处理。 [2019-5-22, JLX]并与Delay_ACC做或的关系处理。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.16 MD-REQ-295417/A-KeyOffPwMde_D_Stat 1.1.1.17 MD-REQ-295418/A-InfoSysMasterPw_D_Stat Any more information about the "KeyOffPwMde_D_Stat" and "InfoSysMasterPw_D_Stat"? | Jiang Lixiao | 2019-05-24 | High | power可能不需要处理，待定。 |  | Leo review会后回复 | Open
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 3.1.1 PWRMANv3-SR-REQ-033881/D-System Master Power Moding (TcSE ROIN-289984-3) I found that, when the network inactive, the power mode will change to OFF(Sleep) mode. I want to know any other conditions can let power mode change to OFF, like B+ < 10V or lower? | Jiang Lixiao |  | High | B+ < 10V，是进入standby mode，要看下从standby 有没有timeout到off的。 可以看下： 3.4.1.2， HMI上可以选择off 3.4.1.3，1小时模式后进入off [2019-5-22, JLX]暂定小于6.5V或大于24V可立马睡眠，这俩电压值可根据实际情况调整。关闭此问题。 |  |  | Closed
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.11 MD-REQ-273750/A-Ignition_Status The "Ignition_Status" seem's use bit mask for the value, I mean I want to know does the status can happened in the same time? Eg. Ignition_Status = 0x06, does it mean the Ignition_Status = Accessory and Run? Or are these values incompatible? | Jiang Lixiao |  | Medium | [2019-6-13,JLX]Leo确认，不会有状态组合，状态值都是固定的，如有其它值，就当非法值处理。 |  |  | Closed | 2019-06-13
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.12 MD-REQ-273762/A-Delay_Acc 3 Functional Definition The "Delay_Acc" and "Delay_Accy" are the same thing? | Jiang Lixiao | 2019-05-22 | Low | [2019-5-21, JLX]同一个东西。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.1.1.3 MD-REQ-273497/A-DriverDoorStatus 3.1.4 PWRMAN-REQ-033882/B-MMInactive_Sleep Power Mode Diagram (TcSE ROIN-289985-2) 状态图中的“[DoorStatus = Closed &&Veh_Lock_Status = Locked]”中的DoorStatus是指所有门，还是任意一个门？ 如"DriverDoorStatus" 和"PassengerDoorStatus"? | Jiang Lixiao | 2019-05-22 | Medium | [2019-6-13,JLX] 3.1.4 PWRMANv2-SR-REQ-093960/C-MMInactive_Sleep_Standby Power Mode Diagram 中的“[DoorStatus = Closed &&Veh_Lock_Status = Locked”的DoorStatus = Closed是指所有门closed。 而“Welcome HMI Supported && [(DoorStatus = Closed)--> (DoorStatus = Ajar)]”指的是任意一个门从Closed变为Ajar. |  |  | Closed | 2019-06-13
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 3.1.3 PWRMANv2-SR-REQ-031239/C-Phone Mode Power Moding (TcSE ROIN-275203-1) After exiting the "Phone Mode", if the conditions evaluate to FALSE(eg. Ignition_Status == Start), how is the state transformation? | Jiang Lixiao |  | Medium | [2019-6-13,JLX] 具体case具体分析，如： 1. Ignition_Status == OFF && Delay_Accy == OFF && EPTimer >= EPLimit && HMIAudioMode == ON，这种case就直接跳转到Inactive mode； 2. 如果Ignition_Status == UNKNOWN或者INVALID值，就要先处理这些非法值（这些非法值有专门的处理逻辑），再做条件判断和状态跳转。 其它case详细另起一个QA讨论，关闭此问题。 |  |  | Closed
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 3.1 PWRMANv3-FUN-REQ-033880/B-System Master Power Moding (TcSE ROIN-289928-1) In state "MM Active", if Power key pressed event happens, how is the state transformation? | Jiang Lixiao | 2019-05-24 | Medium | audio off，或者goto home scree，细节后期还要讨论，长按可能做成reset。 [2019-5-21,JLX]关于button的内容，会有专题讨论。暂关闭此问题。 |  |  | Closed
|  | Power | Customer | Refer to: Voltage Curve RQT-002600-000443 ARL FS-0000-00001-AB Rev 2 Master.pdf China AHU Hardware Spec V1.3.pdf 确认电压范围和各临界点的处理，还有“冷启动”的voltage curve是怎样的？如何区分cold crank和warm crank | Jiang Lixiao | 2019-05-22 | Medium | [2019-6-13,JLX]软件不用关心这个内容，硬件EE处理。 |  |  | Closed | 2019-06-13
|  | Power | Customer | Refer to: Voltage Curve RQT-002600-000443 ARL FS-0000-00001-AB Rev 2 Master.pdf 什么是“VQM(Voltage Quality Module)”？ | Jiang Lixiao |  | Medium | [2019-5-21,JLX]待确认。 [2019-6-13,JLX]Leo确认再回复。 |  |  | Open
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf China AHU Hardware Spec V1.3.pdf “Normal operation shall be supported between 9.0 – 16.0V, although below 10V audio performance cannot be guaranteed. ”和“To enter Functional Power Mode states from Standby the voltage at the system master shall be 10v < B+ < 16v.”是否矛盾？ | Jiang Lixiao |  | Medium | "10v < B+ < 16v"是软件功能要求范围 [2019-5-24,JLX]电压问题，另起QA确认，关闭此问题。 |  |  | Closed
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf Acc和Delay_Acc的关系？有没有优先？例如，一个是ON另一个是OFF的情况下，应该以哪个为准？ | Jiang Lixiao | 2019-05-22 | Medium | [2019-5-21,JLX]只有delay_acc，Ignition_Status的Accessory就是ACC，他们关系见#19. |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf Ignition_Status和Delay_Acc的关系？ | Jiang Lixiao | 2019-05-22 | Medium | [2019-5-21,JLX]Ignition_Status的ON，Accessory，RUN和Delay_ACC的ON是或的关系，另一方面，Ignition_Status的OFF和Delay_ACC的OFF是与的关系。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 3.1.1 PWRMANv3-SR-REQ-033881/D-System Master Power Moding (TcSE ROIN-289984-3) 在状态图里面的phone inactive后的条件里面的“HMIAudioMode = OFF”是set HMIAudioMode = OFF？还是只是判断？ | Jiang Lixiao | 2019-05-22 | Medium | [2019-5-21,JLX]指的是set HMIAudioMode = OFF，状态图中的其他关于HMIAudioMode的内容，都是指Set，不是判断。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf HMIAudioMode这是一个事件还是一个状态，是HU Power模块设置的吗？ | Jiang Lixiao | 2019-05-22 | Medium | [2019-5-21,JLX]是MCU power管理的一个状态，初始值为inactive，（详见文档的状态图逻辑）有变化需要通知CAN往外发通知其他节点 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf "- Extended Play Activation / Deactivation events defined in HMI specification. (ex. Power Button Press)"中的HMI Specification是哪个？有哪些事件？ | Jiang Lixiao |  | Medium | [2019-5-21,JLX]对于Active Event目前只有power button这一个，对于Deactive Event，有power button press和EP timeout两个。 另，Button内容会有专题讨论。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | Refer to: Power Management APIM SPSS v1.8 Apr 6, 2018.pdf 1.4.1 PWRMAN-REQ-031235/B-APIM Deep Sleep Mode during Transport Mode (TcSE ROIN-282927-2) 文档提到““APIM(SYNC) KOL Transport requirement.doc” (will become an SDS requirement in future) ”，目前我们Desay没有收到这份文档 | Jiang Lixiao | 2019-05-24 | Medium | [2019-6-13,JLX]Leo确认再回复。 |  |  | Open
|  | Power | Customer | 关于“熄屏模式” | Jiang Lixiao | 2019-05-22 | Medium | [2019-5-20,JLX]熄屏模式是SOC APP应用的行为，属于functional的功能，处于power的active状态中，和power的standby，inactive等没有关系，也不影响power状态逻辑。 在屏幕界面上会有“熄屏”或“屏保”的功能按钮。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | 关于BT电话、RVC唤醒问题 | Jiang Lixiao | 2019-05-22 | Medium | [2019-5-21,JLX]在Power的Standby模式下，BT电话和RVC不可唤醒HU。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | 关于在cold start期间的mute问题 | Jiang Lixiao | 2019-05-22 | High | [2019-5-24,JLX]在cold start期间，电压会有跌落，此时需要mute，这个判断条件是Ignition_Status == Start（MCU会在电压降低之前收到该消息）。如果有电压跌落，而没有Ignition_Status == Start消息，可以不关注这个mute逻辑。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | 关于Standby中的SOC是否启动或关闭问题 | Jiang Lixiao | 2019-05-22 | High | [2019-5-24,JLX]初步确定以下内容： 1. MCU从Sleep到Standby（假设电压是稳定的，10V~16V），可有条件地（例如Veh_Lock_Status和DoorStatus等状态）唤醒SOC。Leo（在2019-5-24前？）会给出全部条件细节（有另外的说明文档）。 2. 从Active（functional)dao Standby,假设电压为10V~16V，SOC不断电。 3. 如果因为过压或欠压（小于10V或大于16V）进入Standby，SOC断电。 [2019-6-13,JLX]EE再确认，到时候发出邮件。 |  |  | Open
|  | Power | Customer | 出差Ford时，Leo提到如果在Carmode的Transport mode跳到Standby，需要马上进入Sleep。其他case和细节需Leo提供。 | Jiang Lixiao | 2019-05-22 | Medium | [2019-6-13,JLX]详细case再另起QA讨论。 |  |  | Closed
|  | Power | Customer | 关于系统的电压范围问题 | Jiang Lixiao | 2019-05-22 | High | [2019-5-24,JLX]初步确定以下内容： 1. < 6.5V： CAN不工作，Power紧急进入睡眠 2. 6.5V ~ 10V： 系统需要坚持10S，然后进入Standby，SOC断电 3. 10V ~ 16V： 这个是系统的要求保证能有功能的电压，如果这个区间进入standby，SOC不断电 4. 16V ~ 24V： 系统需要坚持10S，然后进入Standby，SOC断电 5. > 24V： CAN不工作，Power紧急进入睡眠 其中6.5V和24V这俩值可以根据实际做调整。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | LIN和CAN唤醒后，根据实际情况睡眠问题 | Jiang Lixiao | 2019-05-22 | High | [2019-5-24,JLX]power按键消息是通过LIN传来，LIN和CAN都可唤醒MCU。 在LIN或CAN唤醒MCU后，MCU可根据实际情况在10S内（暂定2s或5s，不应该是ms级，除非是紧急掉电）睡下去。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | 关于Audio Off | Jiang Lixiao | 2019-05-22 | Medium | [2019-5-24,JLX]Audio Off只mute声音，不关屏，不影响power模式，SOC应用自己管理。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | 关于通过power button press进入或退出Extended Play模式问题 | Jiang Lixiao | 2019-05-22 | High | [2019-5-24,JLX]在Ignition_Status == Off的情况下，短按Power button，进入EP模式，长按Power Button（5s或3S）进入Standby模式。 |  |  | Closed | 出差与Leo确认
|  | Power | Customer | 关于通过power button press复位问题， 出差Ford时，Leo提到组合按键power button+Other button（待定），可Reset系统。 1. Other button是哪个？ 2. 长按还是短按？ | Jiang Lixiao | 2019-05-22 | High | [2019-6-13,JLX] 1. Other button待定； 2. 长按10s |  |  | Open
|  | Power | Customer | 出差Ford时，Leo提需要对power进行优化，Ford需要提供Power需求的补充文档 | Jiang Lixiao | 2019-05-22 | High | [2019-6-13,JLX]Leo会近期回复。 |  |  | Open
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清
Note on N3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## FNV2_WIR&IPPT
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Models 模块 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
1 | WIR-CLD-REQ-276162/C-Wireless Interface Router Client1 | Software Req | Customer | What is "Providing connections to applications when central controller is not active" mean? | Shen Jie | 2019-05-31 | Medium | “Center Controller” is a role resides in the Central Gateway (ECG). It means WIR client in IVI should decide which connection approach should be applied for the applications if IVI does not receive any response (or maybe invalid response as well) from ECG(应用联网调度策略默认由ECG管理，当ECG不可用时，HU本地需要有自己的一套调度策略，目前具体调度策略还未定，不确定改功能集成在北美的so里) | ZhengWei(Ford) | 2019-06-05 | On Going
2 | WIR-CLD-REQ-276162/C-Wireless Interface Router Client1 | Software Req | Customer | Is the internal detail logic achieve by North America or need achieve by Desay? | Shen Jie | 2019-05-31 | Medium | To be discussed with Ford NA. Will get back later | ZhengWei(Ford) | 2019-06-05 | On Going
3 | WIR-IIR-REQ-289530/B-WIRClient1_Rx | Software Req | Customer | These signal status related with Can mode definited in where ,same with Can mode definition? | Shen Jie | 2019-05-31 | Medium | (can 信号用的是global的，但是对收到信号后的业务处理不清楚在北美so里实现还是在desay那边实现) | ZhengWei(Ford) | 2019-06-05 | Done
4 | WIR-IIR-REQ-289530/B-WIRClient1_Rx | Software Req | Customer | is there more information about signal status,such what we do next after as WIR receive these signal or we just need receivce and resend them? | Shen Jie | 2019-05-31 | Medium | Rx messages are sent from the other units as ECG and BCM. They are standardized globally. For WIR/ IPPT I don’t see any China specific requirements so far.(can 信号用的是global的，但是对收到信号后的业务处理不清楚在北美so里实现还是在desay那边实现) | ZhengWei(Ford) | 2019-06-05 | On Going
5 | MD-REQ-304019/A-AutosarNM | Software Req | Internal | the signal seem not defined yet | Shen Jie | 2019-05-31 | Medium | 唤醒策略还未定义，需等待对应模块ready | ZhengWei(Ford) | 2019-06-05 | On Going
6 | WIR-REQ-276054/C-Station Mode Enabling Criteria | Software Req | Customer | The criterias off require STA Mode can not understand clearly | Shen Jie | 2019-05-31 | Medium | Please refer MD-REQ-201601/A-Delay_Accy to Delayed accessory (it’s also a Rx). Extended Play Mode means Radio ON when Ignition OFF and Door Open. I guess this signal should be handled by IVI itself(客户也不是很理解对应场景，表示只需接收到信号进行对应处理就行). | ZhengWei(Ford) | 2019-06-05 | Done
7 | WIR-REQ-276055/B-Station Mode Disabling Criteria | Software Req | Customer | The second criteria off disable WLAN service can not understand clearly | Shen Jie | 2019-05-31 | Medium | 客户解答：ECU进入低电量模式或者连接设备离开范围超过范围，需要断开WLAN Service | ZhengWei(Ford) | 2019-06-04 | Done
8 | 3.1.1.7 WIR-REQ-311565/A-WIFI Availability after WIR request | Software Req | Customer | Who triggers WIFI scan and to know WIFI available or not? If WIR request WLAN services to scan wifi? | Shen Jie | 2019-05-31 | Medium | The WLAN Service resides in IVI. WLAN Service is responsible to scan the available WIFI access points. WIR will trigger WLAN Service to scan for WIFI AP in the WIR case.（该问题即为联网策略相关，具体策略feature还未release） | ZhengWei(Ford) | 2019-06-05 | Done
9 | WIR-REQ-295687/A-Periodic Scan | Software Req | Customer | Where store the configcure parmera WIR_WIFI_PERIODIC_SCAN_INTERVAL ? | Shen Jie | 2019-06-03 | Medium | This interval should be implemented as a configurable DID and we can define the default value by ourselves or follow the global setting if no specific requirements. The value should be written to vehicle according to VSCS (需要和北美确认这些宏是否在so里定义配置实现) | ZhengWei(Ford) | 2019-06-05 | Done
10 | 3.1.1.11 WIR-REQ-276060/B-Wifi Access Point Information 3.1.1.12 WIR-REQ-295688/B-WIFI Access Point Information Storage | Software Req | Customer | Can not understand what the mean | Shen Jie | 2019-06-03 | Medium | It means WIR client should be able to receive the WIFI AP information from WLAN services and store them accordingly. The WIFI APs can come from the customer searching or presetting with WIFI AP supplier by Ford (类似于联网偏好设置，即设置优先连哪个网) | ZhengWei(Ford) | 2019-06-05 | Done
11 | 3.1.1.16 WIR-REQ-276064/C-Connectivity Check Endpoint 3.1.1.17 WIR-REQ-276065/B-Wifi Latency Check | Software Req | Customer | Can not understand what the mean | Shen Jie | 2019-06-03 | Medium | WIR-REQ-276064/C-Connectivity Check Endpoint means WIR Client1 should use a public common URL to check the connectivity status. The common URL could be Baidu, CCTV or any other public URLs that we use daily (similar as we check the internet connection status on our laptop by opening Baidu website). WIR-REQ-276065/B-Wifi Latency Check means WIR client1 should also check the latency of a given connection point to support the connection quality of the application. The procedure and criteria is not defined yet.（详细的标准还未定义） | ZhengWei(Ford) | 2019-06-05 | Done
12 | 3.1.1.24 WIR-REQ-311568/A-WIR HMI | Software Req | Customer | is there HMI define about WIRClient1? | Shen Jie | 2019-06-03 | Medium | 客户回复WIR涉及的HMI只有流量开关，WiFi开关，热点开关等 | ZhengWei(Ford) | 2019-06-04 | Done
13 | 3.1.1.28 WIR-REQ-276072/A-WLAN Services To Support Disconnection | Software Req | Customer | When WLAN Servive strategy to disconnect from an access points,what is the detail trrigers state | Shen Jie | 2019-06-03 | Medium | 客户回复：WLAN Service在收到从WIRClinet传过来的对应Can消息或者遇到连接错误时 | ZhengWei(Ford) | 2019-06-04 | Done
14 | 3.3.1.2 WIR-REQ-276078/B-Local Controller Interface With Central Controller | Software Req | Customer | How the local handler privide network when central controller is not available? | Shen Jie | 2019-06-03 | Medium | To be discussed with Ford NA. Will get back later | ZhengWei(Ford) | 2019-06-05 | On Going
15 | 3.3.1.2 WIR-REQ-276078/B-Local Controller Interface With Central Controller | Software Req | Customer | May the flow chat is not fit with Android AOSP Architecture | Shen Jie | 2019-06-03 | Medium | To be discussed with Ford NA. Will get back later | ZhengWei(Ford) | 2019-06-05 | On Going
16 | 3.3.1.7 WIR-REQ-276083/A-Maintain UID’s | Software Req | Customer | Can not understand what the mean,where is the UID stored? | Shen Jie | 2019-06-03 | Medium | To be discussed with Ford NA. Will get back later | ZhengWei(Ford) | 2019-06-05 | On Going
17 | 3.4 WIR-FUN-REQ-276020/A-Intents | Software Req | Customer | is this function implement by ford ? | Shen Jie | 2019-06-03 | Medium | To be discussed with Ford NA. Will get back later | ZhengWei(Ford) | 2019-06-05 | On Going
18 | 3.5.1.7 WIR-REQ-276122/B-Intent Policy Update | Software Req | Customer | is there Detai message about Policy Update flow | Shen Jie | 2019-06-03 | Medium | To be discussed with Ford NA. Will get back later | ZhengWei(Ford) | 2019-06-05 | On Going
19 | 3.7 WIR-FUN-REQ-276030/A-Diagnostics | Software Req | Customer | is this function implement by ford ? If not ,desay need more detai related document | Shen Jie | 2019-06-03 | Medium | To be discussed with Ford NA. Will get back later | ZhengWei(Ford) | 2019-06-05 | On Going
20 | 3.8 WIR-FUN-REQ-289654/A-Data Usage | Software Req | Customer | need more detail information adount how to implement | Shen Jie | 2019-06-03 | Medium | To be discussed with Ford NA. Will get back later | ZhengWei(Ford) | 2019-06-05 | On Going
21
22
23
24
25
26
27
28
29
30
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## FNV2_PMP
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Source 问题来源 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
1 | ECGPR-CLD-REQ-302403/A-Provisioning Server | Software Req | Customer | What is ESNs (or FESNs) mean ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
2 | ECGPR-CLD-REQ-302404/A-Provisioning OnBoard Client | Software Req | Customer | OnBoard Client 1 2 3 ，each client func ？ | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
3 | ECGPR-CLD-REQ-302406/A-Provisioning OffBoard Client | Software Req | Customer | OffBoard Client 1 2 ，each client func ？ | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
4 | Physical Mapping of Classes | Software Req | Customer | diff between OnBoard Client and OffBoard Client? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
5 | Physical Mapping of Classes | Software Req | Customer | what is "UPG Cloud" mean? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
6 | MD-REQ-295854/B-PeripheralProvisioningData_St | Software Req | Customer | what about other line ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
7 | Provisioning Sequence Scenario: ProvServer Swap | Software Req | Customer | ProvServer Swap mean ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
8 | Provisioning Sequence Scenario: ECU Swap | Software Req | Customer | ECU Swap mean ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
9 | Provisioning Sequence Scenario: ECU ABA Scenario | Software Req | Customer | ABA means Swap ? | ZhouQi | 2019-06-04 | Medium
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## FNV2_LHIN
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Source 问题来源 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
1 | Introduction | Software Req | Customer | What is V-SDN mean ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
2 | LHI-REQ-264852/B-Hazard Information as part of Correlated Command | Software Req | Customer | who will push hazards ？ | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
3 | LHI-REQ-264822/A-Notifications without Distance Indication if Location is Close or Behind | Software Req | Customer | LHN_EventInfo is a struct ？ | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
4 | LHI-CD-REQ-293415/A-FNV2 In-Vehicle Architecture Deployment | Software Req | Customer | module relations all of vehicle ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
5 | LHI-UCD-REQ-257974/A-Local Hazard Information Matching | Software Req | Customer | what is "BackendHandler" function ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
6 | LHI-FUN-REQ-252059/A-Customer Connectivity Settings | Software Req | Customer | is this feature relatived with CCS SPSS ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
7 | Non-Functional Requirements | Software Req | Customer | what is Non-Functional Requirements mean ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
8 | CCOI-FUN-REQ-205048/A-PolicyGovernedFunction | Software Req | Customer | which func will relate this PolicyGovernedFunction ? | ZhouQi | 2019-06-04 | Medium |  |  |  | Open
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## Volume
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Source 问题来源 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
1 | MD-REQ-276073/A-SetVolume (LIN network only) | Software Req | Customer | How to distinguish LIN signal and CAN? It seems judge by vehicle type. | ZhongWenguang | 2019-06-06 | Medium |  |  |  | Open
2 | MD-REQ-276098/A-Audio_Vol_Updated | Software Req | Customer | How to judge the volumn is being update or not for the HMI? HMI update, then notify VSS? This function need UI/UE design first. Other source have same confusion. | ZhongWenguang | 2019-06-06 | Medium |  |  |  | Open
3 | MD-REQ-276186/A-Prompt_Vol_Level | Software Req | Customer | What means "mixable prompt"?(混合提示音) | ZhongWenguang | 2019-06-06 | Medium |  |  |  | Open
4 | MD-REQ-276188/A-TA_Vol_Level | Software Req | Customer | What means TA"Traffic Announcement “？ | ZhongWenguang | 2019-06-06 | Medium |  |  |  | Open
5 | VOLv2-FUR-REQ-026149/E-Automatic Volume Cutback (TcSE ROIN-279284-2) | Software Req | Customer | 1 Don't understand "Netcom bus" 2 Default level is a fixed value-15dB？ Does it have relation to maximum volume？ Don't know "Fixed Line Leve" means? 3 What does "volume border" means? | ZhongWenguang | 2019-06-06 | Medium |  |  |  | Open
6 | VOLv2-REQ-014817/J-User Volume Behavior (TcSE ROIN-292215-1) | Software Req | Customer | Hardly understand this chapter. | ZhongWenguang | 2019-06-06 | Medium |  |  |  | Open
7 | VOL-FUR-REQ-014819/I-Volume Attenuation/Restoration (TcSE ROIN-27919-9) | Software Req | Customer | Hardly understand this chapter. | ZhongWenguang | 2019-06-06 | Medium |  |  |  | Open
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## Other
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Models 模块 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
|  | OTA | Customer | OTA 的方案使用DESAY或SW supplier？ | Fang Zewen | 2019-05-29 | Medium
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## 多屏
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Models 模块 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
1 | 屏幕触控 | Software Req | Customer | 系统负责创建进程时间？--正常60-100ms左右 | Pan Juan | 2019-06-11 | Medium | 双屏上同时点击应用，应用启动时间相差80ms~130ms（出现Activity的启动页的时候） |  | 2019-06-14
2 | 双屏APP | Software Req | Customer | b. 应用复制：一个app的内容显示在两个屏幕。 | Pan Juan | 2019-06-14 | Medium | 目前平台底层支持一个屏幕数据镜像到另一个屏幕，没法从应用层面区分；如果复制后的两个内容需要独立操作，可以考虑应用双开； |  | 2019-06-14
3 | 系统性能 | Software Req | Customer | 德赛评估系统层面（实际）+应用（预估，并给出预估值），来评估当前硬件对我们整个系统的性能方面满足情况。 | Pan Juan | 2019-06-14 | Medium | 1）增加一块屏用于显示的内存会增加约24M，一个应用的显示占用内存24M*3，平均一个应用自身的内存约80M，所以增加一块屏且显示systemui+launcher+普通app的话，共需增加约450M； 2）其他多屏产品的内存数据： 对比一： 车和家： Total RAM:4G Free RAM:1G左右 对比二：g6ph平台： Total RAM:3G Free RAM: 1G左右 |  | 2019-06-14
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## Ethernet
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Models 模块 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
1 |  | Netcom | Customer | 关于Automotive Ethernet Topologies描述中,master和slave模式,具体通信形式是怎样,是一切数据通信发起者皆为master，slave只作响应？ | Zhu Hua | 2019-06-19 | Medium
2 |  | Netcom | Customer | 所给的文档有限，是否还有更详细的需求文档。 | Zhu Hua | 2019-06-19 | Medium
3 | AELI_AUTOMOTIVE_ETHERNET_REQ__3.3.3.1 | Netcom | Customer | "Eth0: protocol-UDP" "Eth1: Protocol- TCP" 是存在两个网卡吗？ | Zhu Hua | 2019-06-19
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## FNV2_SVS
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Source 问题来源 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
1 | Overview | Software Req | Customer | This is achieved by utilizing the vehicles SVSServer which utilizes: in 2and 3 case | Shen Jie | 2019-06-14 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
2 | Overview | Software Req | Customer | what is "Back up battery" and "Main battery" mean ? | Shen Jie | 2019-06-14 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
3 | SVS Customer Connectivity Settings Overwrite | Software Req | Customer | Can not understand clearly abount "Privacy Mode" party | Shen Jie | 2019-06-14 | Medium | According to CCS feature team this requirement is not applicable to China program as “the vehicle connectivity can never be disabled by the customer (button hidden in HMI)” 不需要关注，CSS HMI相关中国化会重新定制，对应按钮可能会消失 | Zheng Wei | 2019-06-25
4 | SVS-CLD-REQ-291017/E-Stolen Vehicle Services Server | Software Req | Customer | Can not understand clearly the last task in the list | Shen Jie | 2019-06-14 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
5 | SVS-CLD-REQ-291018/D-Stolen Vehicle Services Interface Client | Software Req | Customer | Can not understand clearly the task abount CCS and HMI (has some detail HMI spss?) | Shen Jie | 2019-06-14 | Medium | The Detail HMI spss is not yet release | Zheng Wei | 2019-06-24
6 | SVS-CLD-REQ-291115/E-Stolen Vehicle Services OnBoard Client | Software Req | Customer | Can not understand clearly the last task in the list | Shen Jie | 2019-06-17 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
7 | 2.6.1 SVS-IIR-REQ-291024/C-SVSInterfaceClient_Tx 2.6.2 SVS-IIR-REQ-291025/B-SVSInterfaceClient_Rx | Software Req | Customer | 2.6.1and2.6.2 all have MD-REQ-304069/C-getTcuDidData ,is itrepeted ? | Shen Jie | 2019-06-17 | Medium | It has implement in FNV2 module released libso likely libsvs.so | Zheng Wei | 2019-06-24
8 | 3.2 SVS-REQ-306292/A-Transport Mode SVS Disablement | Software Req | Customer | what does Transport Mode mean ? | Shen Jie | 2019-06-17 | Medium | As SVS is subscription feature offered through FordPass for which TCU should to authorized to retail customer, during vehicle transportation TCU will be put in Transport mode and SVS disabled from functioning.（该部分主要功能逻辑在TCU端实现，IVI不需要关注） | Zheng Wei | 2019-06-25
9 | 4.1 FUN-REQ-306285/A-Configuration | Software Req | Customer | Are these all DID needed in IVI ? Please help us diff which we need care | Shen Jie | 2019-06-17 | Medium | It has implement in FNV2 module released libso likely libsvs.so | Zheng Wei | 2019-06-24
10 | 4.1.2.1 SVS-UC-REQ-304493/B-Theft Mode Activation | Software Req | Customer | When Theft Mode Activation, What need IVI do after receive switch DID such as change HMI? | Shen Jie | 2019-06-17 | Medium | When Theft mode activated/enabled, TCU THEFT_MODE DID will be enabled and updated to ECG and SYNC. SYNC will grey out the Master Reset button and Reset submenu.(激活 Theft mode后，需要吧恢复出厂设置按钮置灰) | Zheng Wei | 2019-06-24
11 | 4.1.3.1.3 SVS-ACT-REQ-306769/B-Theft Mode Check Upon SVSInterfaceClient Wake-Up | Software Req | Customer | Is there some detai about "performRelative TheftMode Actions " in Activity Diagram? | Shen Jie | 2019-06-18 | Medium | It has implement in FNV2 module released libso likely libsvs.so | Zheng Wei | 2019-06-24
12 | 4.1.3.2.2 SVS-SD-REQ-306771/D-Theft Mode De-Activation | Software Req | Customer | can not understand "Post-Condition" clearly | Shen Jie | 2019-06-18 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
13 | 4.2.1.1 SVS-REQ-308660/B-Use of Pre-existing SVSServer DTCs | Software Req | Customer | Is this we need care in IVI part ? | Shen Jie | 2019-06-18 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
14 | 4.3 SVS-FUN-REQ-291043/A-GNSS Location | Software Req | Customer | Can not understand this part because it is so complex,we need clear know which IVI shoud respond | Shen Jie | 2019-06-18 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
15 | 4.4.1.1 SVS-REQ-330480/A-SVS subscribed Vehicle connectivity settings | Software Req | Customer | Can not find the CCOIv2-REQ-296876 and CCOIv2-REQ-329007 | Shen Jie | 2019-06-18 | Medium | According to CCS team this will not be impacted or implemented to china programs as vehicle connectivity can never be disabled by the customer or thief.（不需要关注，CSS HMI相关中国化会重新定制，对应按钮可能会消失） | Zheng Wei | 2019-06-25
16 | 4.4.1.2 SVS-REQ-308665/C-CCS settings priority when Theft Mode is active | Software Req | Customer | what does "take priority over current CCS Settings for Location and Data " mean? | Shen Jie | 2019-06-18 | Medium | It has implement in FNV2 module released libso likely libsvs.so | Zheng Wei | 2019-06-24
17 | 4.3.1.3 SVS-REQ-291069/D-SVSServer Unable To Obtain Location From Backup GNSS Antenna While Ignition OFF | Software Req | Customer | What is this mean IVI need power on? | Shen Jie | 2019-06-19 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
18 | 4.4.1.3 SVS-REQ-303128/E-SVSServer Theft Activation To SVSInterfaceClient while in Ignition “OFF” | Software Req | Customer | Can not find CCOIv2-REQ-312152 | Shen Jie | 2019-06-03 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
19 | 4.4.1.4 SVS-REQ-303129/B-SVSInterfaceClient changes upon “Theft Mode” Activation | Software Req | Customer | is this mean CCS HMI can setup but no functionally? | Shen Jie | 2019-06-19 | Medium | 被盗模式激活后，CCS上的HMI设置(比如Loaction ，WlAN开关)无论当前是否打开关闭，这些功能都是保存打开状态，具体HMI如何显示还未release | Zheng Wei | 2019-06-25
20 | 4.4.1.6 SVS-REQ-303130/D-SVSServer Theft De-Activation To SVSInterfaceClient while Ignition “OFF” | Software Req | Customer | what display off and display on mode mean ? | Shen Jie | 2019-06-19 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
21 | 4.4.1.8 SVS-REQ-325650/A-Location Disable pop up for SVS subscribed customers | Software Req | Customer | is it conflict with "SVS Customer Connectivity Settings Overwrite " part ? | Shen Jie | 2019-06-19 | Medium | 使用SVS功能后，在CCS设置里关闭Location设置时，需要弹出一个警告框类似“Location 关闭后会影响SVS功能的使用”具体HMI如何显示还未release | Zheng Wei | 2019-06-25
22 | 4.5.1.3 SVS-REQ-321961/A-Command & Control Blocking | Software Req | Customer | what "All Command & Control functionality " include ? | Shen Jie | 2019-06-19 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
23 | 4.5.1.9 SVS-REQ-326479/B-Master Reset/Feature Reset Blocking | Software Req | Customer | If faactory reset in process ,what IVI should do ? | Shen Jie | 2019-06-19 | Medium | The master reset workflow is not clearly , need to wait for master reset module release detail sppss | Zheng Wei | 2019-06-24
24 | 4.6 SVS-FUN-REQ-291045/A-SVSOffBoardClient Communication | Software Req | Customer | Can not understand this part because it is so complex,we need clear know which IVI shoud respond | Shen Jie | 2019-06-20 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
25 | SVS-REQ-291085/D-Power Modes | Software Req | Customer | Can not understand clearly this part,what does is Main battery and Back up battery mean ? | Shen Jie | 2019-06-20 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
26 | 4.8 SVS-FUN-REQ-318009/A-SVS Enhanced Early Theft Notifications | Software Req | Customer | Can not understand this part because it is so complex,we need clear know which IVI shoud respond,what is "Enhanced Early Theft Notifications" mean? | Shen Jie | 2019-06-20 | Medium | not in IVI Party Deasy need not care | Zheng Wei | 2019-06-24
23
23
23
23
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清

## climate&clock&vehicle setting
Requirements Questions&Answers
Questions | [6 empty] | Answers |  |  | Question Status | Remark 备注
No. | Models 模块 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
1 | Climate Control | Internal | 电话或者语音功能运行时，风扇强度要调整？调整规则是什么？ | 刘晓刚 | 2019-06-19 | Medium | 风扇运行时，App只需要把当前电话或者语音的信息告诉MCU，MCU控制风扇风量大小。不需要App去控制风量 | 王金龙 | 2019-06-24
2 | 通用 | Internal | 语音对接，科大or百度？语义是否现在可提供？ | 刘晓刚 | 2019-06-19 | Medium | 还未指定语音供应商，德赛需要封装标准接口，供语音供应商使用 | 王金龙 | 2019-06-24
3 | Climate Control | Internal | 除了座椅加热，还有座椅冷却？B-Driver or Passenger Cooled Seat adjustment。 | 刘晓刚 | 2019-06-19 | Medium | 两个功能都需要，可参考HMI | 王金龙 | 2019-06-24
4 | Climate Control | Internal | 外部温度要显示吗？还有温度传感器没有安装的情况需要考虑 3.6.1.30。 | 刘晓刚 | 2019-06-19 | Medium | 福特已有标准的CAN 报文消息提供，App可以得到外部温度信息 | 王金龙 | 2019-06-24
5 | Climate Control | Internal | Remote start 是什么功能？3.6.1.33 云端控制。 | 刘晓刚 | 2019-06-20 | Medium | 可通过手机APP连接云端，随时随地把车辆开启，空调以auto模式运行 | 王金龙 | 2019-06-24
6 | Climate Control | Internal | Rear lock selection这个功能要做吗？3.7.1.8 | 刘晓刚 | 2019-06-20 | Medium | 某些车型需要 | 王金龙 | 2019-06-24
7 | Navi Repeater | Internal | 地图向仪表发送的导航信息，需要确认这部分是德赛把CAN功能接口开放给百度使用，还是百度地图把信息发给德赛，由德赛发送CAN信号。 | 刘晓刚 | 2019-06-20 | Medium | 已有标准报文文档，根据文档格式化报文，可不依赖仪表供应商独立开发。 | 王金龙 | 2019-06-24
8 | Wrong way alert | Internal | 错误道路导航报警也是百度地图发出来的吗？ 此信号发出，除了电话audio，其他audio需要静音。同时隐藏导航信息；如果已经处于警报期，再去导航，则导航信息不隐藏 | 刘晓刚 | 2019-06-20 | Medium | ADAS或者仪表发出。具体UI，可能是Pop UP。 | 王金龙 | 2019-06-24
9 | Vehicle Settings | Internal | 要支持几种语言？ | 刘晓刚 | 2019-06-21 | Medium | 中英文两种 | 王金龙 | 2019-06-24
10 | Vehicle Settings | Internal | 氛围灯支持多少颜色？ | 刘晓刚 | 2019-06-21 | Medium | 7种，关机时的配置需要保存，此部分不依赖第三方，可独立开发。 | 王金龙 | 2019-06-24
11 | Vehicle Settings | Internal | C-ChargePortLightRing_St 没看明白。1.1.27 充电口？ 无线充电板 | 刘晓刚 | 2019-06-21 | Medium | 还未确定 | 王金龙 | 2019-06-24
12 | Vehicle Settings | Internal | 1.1.29 0-15bit 按键的作用？ | 刘晓刚 | 2019-06-24 | Medium | 相当于功能快捷键，可参考HMI | 王金龙 | 2019-06-24
13 | Vehicle Settings | Internal | 1.1.32 充电口上锁？ | 刘晓刚 | 2019-06-24 | Medium | 电动车功能，CAN信号控制 | 王金龙 | 2019-06-24
14 | Vehicle Settings | Internal | 1.1.33 长期驾驶历史信息。 | 刘晓刚 | 2019-06-24 | Medium | 指平均油耗，速度等信息。 | 王金龙 | 2019-06-24
15 | Vehicle Settings | Internal | 1.1.34 油量报警功能； | 刘晓刚 | 2019-06-24 | Medium | 设置剩多少公里报警，弹窗或者顶部栏消息显示 | 王金龙 | 2019-06-24
16 | Clock | Internal | 需要有设置时区的功能？ | 刘晓刚 | 2019-06-24 | Medium | 还未确定 | 王金龙 | 2019-06-24
17 | Clock | Internal | MFD 作为主时钟，是可以在HMI上配置的吗 | 刘晓刚 | 2019-06-24 | Medium | 车机是从时钟 | 王金龙 | 2019-06-24
18 | Clock | Internal | chapter 2.2 ,主时钟发来时间信息，从时钟负责按照朱莉安日历格式显示。 | 刘晓刚 | 2019-06-24 | Medium | 是的 | 王金龙 | 2019-06-24
19 | Clock | Internal | CAN总线唤醒后，50ms内向从时间发送时钟信息?还是750ms。 2.2.3 | 刘晓刚 | 2019-06-24 | Medium | 是50ms。750ms不适用 | 王金龙 | 2019-06-24
Note on B3: 来源(系统需求、软件需求)
Note on C3: 问题类型(客户、供应商、内部)
Note on G3: 高中低
Note on K3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清