## Sheet1
Requirements Questions&Answers
Questions | [7 empty] | Answers |  |  | Question Status | Remark 备注
No. | Req ID 需求ID | Source 问题来源 | Type 问题类型 | Question Description 问题描述 | Who 提交人员 | Date 提交日期 | Priority 优先级 | Action / Analysis 行动/分析 | Who 回复人员 | Date 回复日期 | Status 问题状态
0 |  | Security | Customer | Q: Does FordDuerOS project need to follow A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document? | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
1 |  | Security | Customer | Q:Please provide the TCU Hardware Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: about Ford part number for the TCU module hardware. The part number is generated by Ford and given to the supplier. | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
2 |  | Security | Customer | Q:Please provide the TCU Assembly Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: about Ford Assembly Part Number for the TCU module hardware. The part number is generated by Ford and given to the supplier. | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
3 |  | Security | Customer | Q:Please provide the TCU Assembly Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: about Ford Assembly Part Number for the TCU module hardware. The part number is generated by Ford and given to the supplier. | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
4 |  | Security | Customer | Q:Please provide the Destination Region Code In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
5 |  | Security | Customer | Q:Please provide the Main/Host Processor Strategy Software Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
6 |  | Security | Customer | Q:Please provide theMain/Host Processor Config Software Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: . | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
7 |  | Security | Customer | Q:Please provide the Secondary Processor Strategy Software Part Number In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: . | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
8 |  | Security | Customer | Q:Please provide the Key Rotation and Rekeying Security Specification. In A51t_Supplier_Feed_Specification_080_3G4G TCU – Embedded Modem.pdf document: . | YangHui | 2019-05-22 | Medium | A51t_Supplier_Feed_Specification 适用于TCU,不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
9 |  | Security | Customer | Q:Please provide S13b Security Specification. In Key Material Requirements.pdf document: . | YangHui | 2019-05-22 | Medium | 应该不适用 ----再确认 | Xu, Jinchi | 2019-06-05 | Open
10 |  | Security | Customer | Q:Please provide a Ford root CA. In Key Material Requirements.pdf document: .Unless otherwise noted, all certificates used shall be derived from a Ford root CA. | YangHui | 2019-05-22 | Medium | Cert/Key由Ford 提供的为：Code signing 以及Secure Boot | Xu, Jinchi | 2019-06-05 | Open
11 |  | Security | Customer | Q:Please provide ESN prefix generation (3 characters) shall be determined by Ford. In Key Material Requirements.pdf document: provide ESN prefix generation (3 characters) shall be determined by Ford. | YangHui | 2019-05-22 | Medium
12 |  | Security | Customer | Q: Does FordDuerOS project need to follow Connected Vehicle Mobile Applications Standard.pdf document? | YangHui | 2019-05-22 | Medium | 适用于Mobile APP不适用于IVI | Xu, Jinchi | 2019-06-05 | Closed
13 |  | Security | Customer | Q:Please provide App signing RSA keys from Ford In App_signing_requirements_ver 1.3 | YangHui | 2019-05-22 | Medium | Cert/Key由Ford 提供的为：Code signing 以及Secure Boot | Xu, Jinchi | 2019-06-05 | Open
25
26
27
28
29
30
Note on B3: 问题溯源到的需求ID
Note on C3: 来源(系统需求、软件需求)
Note on D3: 问题类型(客户、供应商、内部)
Note on H3: 高中低
Note on L3: 由问题提交着确定问题状态 Close--问题已澄清理解一致 Open--问题未澄清