## SW TDR Status Report
SW TDR Status Report
Program Name
Module
Version: 2018_0 |  | Supplier
Supplier Contact name, email and phone
D&R Engineer
SWTDR/TDI Engineer
Release Date
General Assessment:
Other positive & negative observations (including opportunities for improvement & identified best practices):
GPDS Milestone | Date | Item number | Overall SW Implementation Inspection process checklist for a program | Results (Green Yellow Red) | Comments | Conformance Date
Kickoff at PSC |  | 1 | discuss SW SOW with supplier
|  | 2 | discuss the ECU Software Design Rules with supplier
|  | 3 | determine the scalability of the project according to the level of change
|  | 4 | explain schedule for SW TDR to supplier based on milestones
|  | 5 | add ECU item & Milestone to the Combined Software Health Chart
UNV0/UPV0 |  | 1 | review supplier responses for the Project and Process related questions
|  | 2 | inspect the supplier Software Development Plan
|  | 3 | inspect the supplier project timing plan
M-1DJ/FDJ |  | 1 | review supplier response to questions related to different aspects of the design and implementation
|  | 2 | supplier static analysis results Inspection
|  | 3 | supplier MISRA compliance Inspection
|  | 4 | supplier functional DV test status Inspection
M-1DC/VP0 |  | 1 | review supplier response to software code related questions
|  | 2 | inspect supplier software change management process
|  | 3 | update ECU item & Milestone in the Combined Software Health Chart
|  | 4 | review IVS check list
PEC |  |  | review software release notes
Change Management |  |  | Check with D&R and supplier if the suggestions agreed during TDR have been implemented

## SW TDR Status
Software TDR Answer Status
GPDS | Assessment | [5 empty] | Completion
UNV0/UPV0
M-1DJ/FDJ
M-1DC/VP0
Overall
Trend
| Total | Red | Yellow | Green | not checked | n/a | Total | Open | Closed | not checked | n/a | Total
UNV0/UPV0 | 21 | 0 | 2 | 19 | 0 | 0 | 21 | 6 | 15 | 0 | 0 | 21
M-1DJ/FDJ | 172 | 0 | 0 | 3 | 169 | 0 | 172 | 167 | 3 | 0 | 0 | 170
M-1DC/VP0 | 37 | 0 | 2 | 0 | 35 | 0 | 37 | 37 | 0 | 0 | 0 | 37
Overall | 230 | 0 | 4 | 22 | 204 | 0 | 230 | 210 | 18 | 0 | 0 | 228
Total | 230 | 0 | 4 | 22 | 204 | 0 | 230 | 210 | 18 | 0 | 0 | 228
|  | Red | Yellow | Green | not checked | n/a | Total | Open | Closed | not checked | n/a | Total
UNV0/UPV0 | % | 0% | 9.524% | 90.48% | 0% | 0% | 100% | 28.57% | 71.43% | 0% | 0% | 100%
M-1DJ/FDJ | % | 0% | 0% | 1.744% | 98.26% | 0% | 100% | 97.09% | 1.744% | 0% | 0% | 98.84%
M-1DC/VP0 | % | 0% | 5.405% | 0% | 94.59% | 0% | 100% | 100% | 0% | 0% | 0% | 100%
Overall | % | 0% | 1.739% | 9.565% | 88.7% | 0% | 100% | 91.3% | 7.826% | 0% | 0% | 99.13%

## SW Implementation Inspection CL
Please answer this checklist (GREEN colored fields are the supplier fields) and send it back answered within two weeks. Please keep your answers short but comprehensive. If you cannot provide an answer or a requested document (and Ford agreed to that deviation of the SOW), please indicate this, and keep it ready for the review. If you cannot provide a particular answer within two weeks time, please indicate, but don't delay the submittal of the rest of the checklist answers. PLEASE DO NOT FILL ANY OTHER FIELDS or COLUMNS! This are Ford.
GPDS Milestones | Checklist reference | Ford Requirement | Question ID | Questions | Supplier Answers | Documentation Reference(s) | RYG | Comments / Discussion | Open / Closed
P.01) Project Questions
UNV0/UPV0 | Software Risk Assessment Checklist - 1. Process Questions - Item 1 |  | PRJ01001 | For new supplier that have not worked for Ford before: A) Have you ever worked on automotive software before?/ Has this development team ever released software for production for Ford Motor Co. before? B) Has anyone in your team worked on automotive software before? / Has any development team in your organization ever released software for production for Ford Motor Co. before? C) Describe any embedded software that you have developed for mass production? | A)yes, we have worked on automotive software, for example VW projects, Toyota projects and Mazda projects; but our development team didn't release software for production for ford Motor Co. B))yes, our team all have worked on automotive software, our team such as Gao Wei, Zhang Yanlan and Liu xiagang and so on have worked on VW projects, Toyota project and NEVS project.; but our development team didn't release software for production for ford Motor Co. C)we have developed many projects for mass production, for exampe NEVS and VW projects. |  | Green |  | Closed
UNV0/UPV0 | Software Risk Assessment Checklist - 2. Architecture and Strategy questions- Item 1 |  | PRJ01002 | A) Is this a complete new development , carry-over or modified development from a previous project (for other OEM's)? B) If its modified what % of SW has been modified and explain the features changed. | A)This project we need develop SOC and MCU two part. About SOC is modified development from a previous project, about MCU is nearlly new development. B)About SOC part, our platform nearly has 50%, we will modify or add interface for SW Tier1, and we will modify our Audio manager and power manager modules and so on. |  | Green |  | Closed
UNV0/UPV0 |  |  | PRJ01003 | A) To what extent was a software library (e.g., core/platform development) used in your Best Practices process? B) How is the software library (core development) maintained? | A) About SOC part, nearlly 50% reuse(G6SA Platform); About MCU part, which is nearly new development (从哪个平台reuse) B)Continuously updated and integration. The software libray is saved on gitlab server, and use repo to manage git, every project can update the software library by using git commond（平台更新，各个项目如何获取到平台的更新，用什么工具管理的） |  | Green |  | Closed
M-1DC/VP0 |  |  | PRJ01004 | A) Software completion status (in %). B) Which parts are not completed? | A)20%(The first version) B)Follow FIP documents | A) B) | not checked | This question needs to be filled out at 2 mile stones UNV0/UPV0 M-1DC/VP0 (for metrics purpose it has been marked as only VP0) | Open
UNV0/UPV0 |  |  | PRJ01005 | A) Are there more than one software development sites and where? B) If there are, how is the work split (Who is doing what)? B1) If there are, who is responsible for the software integration and where is the integration site? B2) If there are, who is responsible for the software integration testing and where is the integration testing done? | A)we have five sites, Hui Zhou, Shang Hai, Nan Jing, Cheng DU, Singapore B)Nanjing site mainly develop SOC part, Huizhou site mainly develop MCU part B1)About SOC part, Nanjing sw team responsible for the software integration in Nanjing site; About MCU part, Huizhou sw team responsible for the software intergration in Huizhou site. B2) Hui Zhou will responsible for the SW integration test in Hui Zhou, include alpha test and PTV test. | A) B) B1) B2) | Green |  | Closed
UNV0/UPV0 |  |  | PRJ01006 | A) Describe the software developer's breadboard and where it is located. B) Describe the software DV breadboard and where it is located. C) Which vehicle representative parts are being used on these breadboards? | A)Our developer will all have one breadboard during development, and for different stage, we will update the breadboard, such as A0 sample, A1 sample, B/C sample and so on（开发使用的开发板） B) Because we DV test team in Huizhou site, so DV breadboard is located in Hui Zhou(描述下dv测试的车机环境) C)需要包含台架整套设备 |  | Green |  | Closed
UNV0/UPV0 | Software Risk Assessment Checklist - 1. Process Questions - Item 12 (A) |  | PRJ01007 | A) When were you last audited by an official ASPICE auditing firm for certification? B) In which project(s)? C) Describe the results of the Audit: i) Which processes was assessed? ii) What level did you earn for each process? iii) What are the weaknesses identified for each process D) Provide a plan to achieve ASPICE L3 (according to Ford requirement) | A)Our last audit was an ASPICE Pre Assessment by TUV for certification from 03-04-2019 to 03-08-02019. B)In Mazda J59R ACU Project. C)i)VDA Scope; ii)We earned Level 1 for SYS.2 and ACQ.4 and the rest were level 0. iii)Refer to<ASPICE_FFP_20190304-08_v1.0-VDA Scope> Page 14~43. D)We plan to achieve ASPICE L3 in 2020.Refer to <DSV ASPICE Management> | A) B) C)<ASPICE_FFP_20190304-08_v1.0-VDA Scope> D)<DSV ASPICE Management> | Green |  | Closed
UNV0/UPV0 | Software Risk Assessment Checklist - 1. Process Questions - Item 11 |  | PRJ01008 | Is there at least one software engineer that fully understands the implementation ready product that is allocated to work on the software throughout the life of the project? - ( This question is asked based on review experience that when current project is developed based on a previous project, new changes would have unintended interactions that could be avoided if an experienced engineer with prior knowledge is available. Ford wants them available for the length of the project.) | yes. For example, About MCU part, Chen Xiujing have work on the software through the life of the VW-CRS3.0 project and so on; About SOC part, Ding Yunrong have work on the software through the life of the Changcheng A30 project and so on.参与那个项目 MCU/SOC |  | Green |  | Closed
UNV0/UPV0 | Software Risk Assessment Checklist - 1. Process Questions - Item 15 |  | PRJ01009 | How are you organizing/scheduling software development in order to maximize early (and stable) Test Plan development? | Desay will supervesion with ENC together. 附文档 软件测试配合开发的软件计划 |  | Green |  | Closed
P.02) Software Process Questions
UNV0/UPV0 | Software Risk Assessment Checklist - 1. Process Questions - Item 12 (B1) |  | PRO02001 | A) In general, describe your Software Development and Release Process (docs & pictures help). B1) Present your Software Project Management Plan (Project description, organization (R&Rs), reporting, WBS and project deliverables (work products), project schedule, estimation & resource planning, risk management, controlling & escalation, change control process) B2) To which standard is your Software Project Management Plan compliant? | A) B1)展示desay内部管理文件夹 B2)遵循行业内的什么标准进行管理 流程管理和质量管理，有的都可以填写 | A)附文档名 B1) | Green |  | Closed
UNV0/UPV0 |  |  | PRO02002 | A) Describe your Quality System. B) Have you been trained in using your Quality System? C1) Present your project SWQA Plan (Project scope, project quality organization (R&Rs), reporting (QA Records etc.), handling of non-conformances, escalation mechanisms) C2) To which standard is your SWQA Plan compliant? D) Present your SWQA planning (Project quality schedule) i) Which work products are under quality assurance ii) with which method (peer review, walkthrough, inspection etc.) iii) based on what criteria (e.g., Checklists based on standards) and iv) when in project lifetime (cyclic, dedicated Milestones, Releases etc.) | A) We use RDM as quality System to manange bugs,document, schedule... B) Yes, RDM training is must for each engineering before on working position. C1) Please refer to <Ford ICA2 AHU_QA Plan.A> C2) If customer have requirement, SWQA plan compliant to customer's standard; if not, SWQA plan compliant to ASPICE and Desay SV Product Life Cycle. D) i) Work products under quality assurance defined in Process Performance Report according the tailored lifecycle.（ Refer to SW PPR template for example） ii) Milestone Review: inspection; Design Review: walkthrough; Work Product assurance: Check by Quality Engineer. iii) All of above base on checklist defined by Desay SV. iv) Milstone Review: dedicated Milestones Design Review: for each design release Work Product assurance: Monthly | A) NA B) NA C1)<Ford ICA2 AHU_QA Plan.A> C2) D) <SW_PPR_Project Name_yyyymm> | Green |  | Closed
UNV0/UPV0 |  |  | PRO02003 | Supplier documents: A) Is the Software (Functional) Requirement Specification and System Requirement Specification (if written by the supplier) reviewed with Ford? B) Are other documents reviewed with Ford? C) Are there documents that should be reviewed by Ford? | A)yes, we persistent review the development progress with ford （持续review开发进度，by那个milestone） B)we review interface Document with ford；and we review some technical document with ford, eg. OTA, FIP C)we will follow ford's requirement. for example, (follow Ford要求 举几个例子) | A) B) C) | Green |  | Open
UNV0/UPV0 |  |  | PRO02004 | A) What is your configuration management/ version control system? B) For which work products is this used? C) If you are using more than one version control systems: How is a baseline across the systems drawn? | A)GitLab Community Edition 10.8.4 B)Git/GitLab, which is used on many project, for example VW CRS3.0, NEVS IHU and so on. C)Only one | A) B) C) | Green |  | Closed
UNV0/UPV0 | Software Risk Assessment Checklist - 1. Process Questions - Item 12 (B) |  | PRO02005 | How do you handle change requests? Describe your SW change control process. |  |  | Green |  | Closed
UNV0/UPV0 |  |  | PRO02006 | What is your bug tracking system? | we use RDM |  | Green |  | Closed
M-1DC/VP0 |  |  | PRO02007 | A) Present your requirements traceability process and tools. B1) Is full traceability between requirements and test cases given? B2) Provide your traceability records C) Demonstrate at least 3 samples of the traceability. | A) Traceability will be done in Polarion system, refer to ALM系统溯源操作指引 B1) Yes, between requirements and test cases should be done. B2) Refer to the Project Name_SE RD Traceability and Project Name_System TS Traceability C) Refer to the Project Name_SE RD Traceability and Project Name_System TS Traceability | A) ALM系统溯源操作指引---ALM溯源管理规范，link B1) B2) Project Name_SE RD Traceability Project Name_System TS Traceability C) The sam as above in B2). | Yellow | This question needs to be filled out at 3 mile stones UNV0/UPV0 M-1DJ/FDJ M-1DC/VP0 (for metrics purpose it has been marked as only VP0) | Open
UNV0/UPV0 | Software Risk Assessment Checklist - 1. Process Questions - Item 7 |  | PRO02008 | What Software Development Tools do you use? (e.g., Requirements Management System, Configuration Management System, Compiler Tool Set, Static Analysis, etc.) List their names and incl. version numbers. | A)Requirements: ALM; Compiler Tool set : android ap:arm-linux-androideabi-4.9; bp:gcc-linaro-arm-linux-gnueabihf-4.8-2014.04_linux 添加编译器版本号；CMS包含项目管理CM和编译配置系统；添加covertity静态扫描，MCU 的codeing工具, app的codeing工具 |  | Green |  | Closed
UNV0/UPV0 |  |  | PRO02009 | A) How do you select and validate your software tools? B) Specifically address compiler validation and linker validation. | A)工具选型的guide B)编译器 链接器 | A) B) | Green |  | Closed
M-1DC/VP0 |  |  | PRO02010 | Lines of code: A) How many lines of code does the module have? B) How many lines of code are developed by the supplier? C) How many lines of code are Ford specific? D) How many lines of code are new/changed for this Ford project? | A) B) C) D) | A) B) C) D) | not checked | This question needs to be filled out at 3 mile stones UNV0/UPV0 M-1DJ/FDJ M-1DC/VP0 (for metrics purpose it has been marked as only VP0) | Open
UNV0/UPV0 | Software Risk Assessment Checklist - 1. Process Questions - Item 8 (14A), Item 9 (14B ), Item 10 (14A) |  | PRO02011 | Static Analysis: A) Syntax and Semantics Analysis: Coding Standards Conformance Checking: i) Present your coding standards and style guide. ii) What static analysis tool do you use for code conformance checking (such as QA-C or PC-Lint)? iii) Describe how/when your software development process incorporates MISRA C compliance checks. How do you plan on becoming 100% MISRA compliant? B) Flow & Complexity Analysis: i) What software complexity metrics do you gather? ii) What static analysis tool do you use for complexity analysis (such as QA-C or PC-Lint)? iii) Describe how/when your software development process incorporates code complexity analysis. C) Formal Analysis: i) What formal dynamic analysis tool do you use (such as POLYSPACE)? ii) Describe how/when your software development process incorporates formal dynamic analysis. D) Describe how/when your software development process incorporates code reviews, walkthroughs, inspections. | A) i)编码规范 SOC/MCU ii)Synopsys Coverity iii) we can do MISRA scan, but not all regulation is included。初始版本需要全部做，交付测试 B) i)Cyclomatic complexity analysis ii)Synopsys Coverity iii)描述实施规范和计划 代码圈复杂<=15（手写的C语言代码），交付节点必须有report,内部保留月度报告 C) i) no dynamic analysis，接口条用覆盖率MCU/SOC 具备否？ ii) D)SW PL 确认 | A) i) ii) iii) B) i) ii) iii) C) i) ii) D) | Green |  | Open
M-1DC/VP0 |  |  | PRO02012 | Software Testing: A) Roles i) Who will test the software? B) Test Equipment i) Describe the test fixtures that will be used to test the software. ii) Does your test fixture use real loads or simulated loads? Justify your decision. C) Dynamic Analysis: i) What formal dynamic White Box analysis do you gather (such as code coverage (statement-, branch-, condition (single and multiple)-, path coverage))? ii) What formal dynamic Black Box tests are you performing (e.g., cause-effect-graph, stress testing, boundary checking, error injection)? iii) Describe how/when your software development process incorporates dynamic analysis. D) Describe your regression test strategy. | A) i)reference org chat ii) iii) B) i) CANoe, Signal generator，Itech ii) CANoe: simulated road; Tuner Signal generator：simulated road； ITech： Real Road 再详尽描述下 iii) iiii) C) i) Alpha test mainly do Black box testing，About white box test, which need the developer help to do---内部确认 是否会做详尽的单元测试 ii) Main use: boundary checking, equivalence partitioning，scenario methodology,error injection iii) After getting all the requirements, developers analyze and exporting the software requirements, testers will according to the software requirements and design test cases. D) Full-featured software, and after the completion of the first round of full-featured testing, the following internal software integration, focusing on change point verification, and regression testing ；CR等级的评判标准，对应于测试是否具有根据CR等级不同的测试处理guide， | A) i) ii) iii) B) i) ii) iii) iiii) C) i) ii) iii) D) | Yellow | This question needs to be filled out at 3 mile stones UNV0/UPV0 M-1DJ/FDJ M-1DC/VP0 (for metrics purpose it has been marked as only VP0) | Open
UNV0/UPV0 |  |  | PRO02013 | Software Release Package: A) What kind of conformance tests are carried out prior to delivery to Ford? B) Present your software release notes (e.g., functional content, used specifications, used message list, known errors, fixed eTrackers, not fixed eTrackers, used RAM/ROM/EEPROM/Data Flash size, current CPU load, static analysis). C) Indicate that you understand that every software release to Ford requires the supplier to submit a complete SWVD document. | A)交付节点同事输出test report给ford B)同上，交付时提供 C)交付时提供alpha &PTV 测试报告 | A) B) C) | Green |  | Open
UNV0/UPV0 | Software Risk Assessment Checklist - 1. Process Questions - Item 14 |  | PRO02014 | What level of automated testing do you have? Does it test DTCs, voltage ranges, intermittent connections, etc.? | 内部关于自动化测试没有等级定义 DTC,CAN,Voltage ranges: Part of automated testing, part of manual testing 已实施的自动化测试有哪些，可以共享下测试文档。只附文件名，文件单独打包 |  | Green |  | Open
I.01) System Context
M-1DJ/FDJ | Software Architecture Review Checklist - 1.1 System Context - Item Q:1.1-1 |  | ISC01001 | Present your system block diagram. |  |  | Green |  | Closed
M-1DJ/FDJ | Software Architecture Review Checklist - 1.1 System Context - Item Q:1.1-2 |  | ISC01002 | Present your electrical block diagram. |  |  | Green |  | Closed
M-1DJ/FDJ | Software Architecture Review Checklist - 1.1 System Context - Item Q:1.1-4 |  | ISC01003 | Present your module schematic. |  |  | Green |  | Closed
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler Item Q:1.3-15 |  | ISC01004 | Present your Hardware/Software Interface Specification. Present ASPICE peer review findings for the Hardware/Software Interface Specification. NOTE: A data-sheet is not good enough. Glue hardware and power supply timing can affect the interface. |  |  | not checked |  | Open
M-1DJ/FDJ |  |  | ISC01005 | What is your Functional Safety Classification (Safety Integrity Levels (SIL) Level)? |  |  | not checked |  | Open
I.02) Microcontrollers (to be answered for all µC that are used in the ECU)
M-1DJ/FDJ | Software Architecture Review Checklist - 1.2 Microcontroller - Item Q:1.2-1 |  | IMC02001 | A) Describe your process for selecting a microcontroller. B) Who specified which microcontroller to use? C) How is the Software Engineer involved in this process? | A) B) C) | A) B) C) | not checked |  | Open
UNV0/UPV0 | Software Risk Assessment Checklist - Item 4 (C,D), Item 6 (E,F ) Software Architecture Review Checklist - 1.2 Microcontroller - Item Q: 1.2-2 (A), Q: 1.2-5 (C), Q: 1.2-8 (D), Q: 1.2-18 (E,F) |  | IMC02002 | Microcontroller: A) What Micro is being used (provide manufacturer and exact part number)? B) What architecture has the µC (8, 16, 32, 64 bit)? C) Is this Micro an off-the-shelf product? D) What experience have you had with this Micro before? E) Is the Micro qualified? / If not, when will it be qualified and what is the backup plan ? F) Is the Micro automotive qualified (e.g., AEC Q100/Q101, Q200…)? G) Is this Micro in mass production at your company? H) Is this Micro in mass production at other companies? | A) B) C) D) E) F) G) H) | A) B) C) D) E) F) G) H) | Yellow |  | Open
M-1DJ/FDJ |  |  | IMC02003 | Availability of microcontroller over vehicle lifetime: How long is production guaranteed? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Risk Assessment Checklist - Item 2 , Item 5 Software Architecture Review Checklist - 1.2 Microcontroller- Item Q: 1.2-3 (ABC ), Q:1.2-7 (D) , Q:1.2-11 (B) |  | IMC02004 | ROM/FLASH, RAM and EEPROM/Data Flash Size: A) What is the size of the ROM/FLASH (with and without PBL sector), RAM and EEPROM/Data Flash in the microcontroller? B) What is your projected size of used ROM/FLASH, RAM and EEPROM/Data Flash? C) What is the current size of used ROM/FLASH, RAM and EEPROM/Data Flash? D) What is the next ROM/FLASH and RAM micro size that has the same footprint? | A) B) C) D) | A) B) C) D) | not checked | This question needs to be filled out at 2 mile stones UNV0/UPV0 M-1DJ/FDJ (for metrics purpose it has been marked as only FDJ) | Open
M-1DJ/FDJ |  |  | IMC02005 | Number of FLASH Cycles: A) How many FLASH write cycles are guaranteed? B) Is there a dependency on conditions e.g., temperature? | A) B) | A) B) | not checked |  | Open
UNV0/UPV0 |  |  | IMC02006 | Data Retention of FLASH Memory: A) How many years of data retention are guaranteed? B) Is there any dependency on environmental factors e.g., temperature (Profile)? C) Is there any dependency on the number of already performed write cycles? | A) B) C) | A) B) C) | Yellow |  | Open
M-1DJ/FDJ |  |  | IMC02007 | Checks: A) When are ROM checks carried out? Is there a different strategy for Application, CCC, Signal Config, Local Config, PBL etc.? B) When are RAM checks carried out? C) When are EEPROM/Data Flash checks carried out? D) What is the strategy in case of a detected failure for A,B,C? E) Please explain how each of this tests (A,B,C) are operating. | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.2 Microcontroller - Item Q:1.2-8 (A), Q:1.2-9 (A), Q:1.2-10 (C) |  | IMC02008 | Microcontroller Errata Sheet: A) What is the date of the latest errata sheet? B) Where would Ford find the latest errata information? C) Present latest errata sheet and highlight items that have affected your project. Explain what changes you made to compensate. D) How do you incorporate the information from the errata sheet into your software development process? E) How is guaranteed that a new errata sheet is automatically received in the project? | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.2 Microcontroller - Item Q: 1.2-14 (A) |  | IMC02009 | A)What programming language are you using on this project? List compiler and linker name. B) if Object-Oriented language is used, please present the preapproval from FORD | A) B) | B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.2 Microcontroller - Item Q: 1.2-15 (A, B), Q: 1.2-16 (D) |  | IMC02010 | Third party tools Errata Sheets: (This includes compiler/linker, libraries, MATLAB, Static Analysis etc.) A) What is the date of the latest errata sheet? B) Where would Ford find the latest errata information? C) Present latest errata sheet and highlight items that have affected your project. Explain what changes you made to compensate. D) How do you incorporate the information from the errata sheet into your software development process? E) How is guaranteed that a new errata sheet is automatically received in the project? | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.2 Microcontroller - Item Q: 1.2-4 (A,B) ; Software Architecture Review Checklist - 1.6 Reset Handling - Item Q: 1.6-7 (F) |  | IMC02011 | A) What is the clock rate of the crystal and of the microcontroller? B) Is a PLL being used? If so, what is the frequency? C) Do all timers have the accuracy that is appropriated for their application? D) Is a clock implemented and what is the base (crystal, ring oscillator) and how is accuracy ensured? E) Are there any differences for normal (awake) or low power mode (sleep)? F) When is the Micro clock prescalar or PLL changed? For example: immediately after reset, just before sleep. | A) B) C) D) E) F) | A) B) C) D) E) F) | not checked |  | Open
M-1DJ/FDJ | new question |  | IMC02012 | A) For multicore controllers describe affinity between the cores. What are the parameters considered for the design B) Provide IPC (Inter Process Communication) mechanism used for multicore and multiple CPUs |  |  | not checked |  | Open
I.03) Software Architecture & Scheduler
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler - Item Q: 1.3-1 , Q: 1.3-12 |  | IAS03001 | Present your Software Architecture documentation. It should include: justification for the chosen architecture, module descriptions, module interfaces (not call structure), major data structure descriptions, justification for major data structure designs, shared resource listing, description of how all shared resources will handle concurrency control, error handling conventions, key algorithm descriptions, RAM usage estimates, ROM/Flash usage estimates, timing estimates, modularity, … Explain how this architecture provides flexibility to changes in requirements and addition of extra features (churning & creep). - from I03010 |  |  | not checked |  | Open
M-1DJ/FDJ |  |  | IAS03002 | A) Which parts of your SW comply to AUTOSAR? B) Which AUTOSAR Release is supported? C) Which Implementation Conformance Class (ICC) is used? D) Is the AUTOSAR SW an in-house development or a commercial product from a SW vendor? E) For a commercial product: Which is the SW vendor? F) For an in-house development: Has this implementation been used in another project before? | A) B) C) D) E) F) | A) B) C) D) E) F) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler - Item Q:1.3-2 (A); Q:1.3-3 (B) , 1.18-14 (C ) |  | IAS03003 | A) What are the major operating modes of the software (e.g., Boot, Sleep, Active, Diagnostic, Low/High Voltage, Fault, Crash, Transport…)? B) Explain the general conditions/actions for each transition to/from each of these major modes (please use Finite State Machine Diagram/Table to document this). C) Show the test plan that tests all operation modes and their transitions (e.g., network transitions power, wake, sleep, reset) for software component bench testing. | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.2 Microcontroller - Item Q: 1.2-13 (C) 1.3 Software Architecture & Scheduler Item Q: 1.3-9 (B) |  | IAS03004 | A) Which Operating System are you using? B) Explain your scheduler design (Register refresh, task scheduling, threads, Idle task, Watchdog petting, Voltage Ranges, ...) C) What is your Sampling rate and Fastest clock-timing interrupt? D) Is the scheduler already used in other applications? | A) B) C) D) | A) B) C) D) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.17. Shared Resources Item. Q: 1.17-1 (A), Q: 1.17- 2 (B) |  | IAS03005 | Shared Resources: A) Identify and explain the techniques (critical sections, control flags/semaphores, monitors, data structures,…) used to control access to Shared Resources e.g., Variables, Registers, EEPROM/Data Flash, Hardware I/O, etc. B) Explain any convention you follow regarding the use of semaphores. C1) Provide a list of shared variables that are used by tasks and interrupts or tasks with different priorities C2) Show for each shared variable that are listed in C1) how conflicting access is handled in a safe way. D1) Provide a list of Registers that are modified by software and Low Level Controls. D2) Show for each Register that are listed in D1) how conflicting access is handled in a safe way. E1) Provide a list of shared I/O circuits. E2) Show for each shared I/O circuits in E1) how conflicting access is handled in a safe way. | A) B) C) D) E1) E2) | A) B) C) D) E1) E2) | not checked |  | Open
M-1DJ/FDJ |  |  | IAS03006 | Shared Resources on functional (Application) level: A) Provide a list of shared subfunctions that are used by more than one function/module. B) Show for each shared subfunction how conflicting access is handled in a safe way. | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ |  |  | IAS03007 | Present your buffer overflow/underflow prevention/detection technique. A) List all buffers that are used Describe for each buffer: B) How do you determine required buffer size? C) How do you detect a buffer overflow/underflow? D) What is the buffer overflow/underflow handling in that case? E) What is the effect on program execution in case of overflow/underflow? | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ |  |  | IAS03008 | Is there any program flow monitoring implemented? Is there any program supervision implemented? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.18 Miscellaneous Design Practices. Item Q: 1.18-3 |  | IAS03009 | Is dynamic memory allocation used? Do you use any memory allocation functions (e.g., malloc() in C)? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler -Item # Q: 1.3-17 |  | IAS03010 | List all of the standard library modules that have been replaced for this project by rewriting their functionality in a new module. Justify this choice. (Note: There is no need to list the libraries explicitly excluded by MISRA.) |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.18 Miscellaneous Design Practices. Item Q: 1.18-7 |  | IAS03011 | Is global memory used? How do you protect global variables as a shared resource |  |  | not checked |  | Open
M-1DJ/FDJ | new question |  | IAS03012 | Provide a list of functions/software components that are re-entrant other than interrupts |  |  | not checked |  | Open
I.04) Interrupts
M-1DJ/FDJ | Software Architecture Review Checklist - 1.4 Interrupts. Item Q:1.4.1 (A,B,C,E); Item Q:1.4-9 (A); Q:1.4-11 (D) |  | ISR04001 | Present the detailed design documents for all ISRs and explain what is occurring in each: A) List of all microcontroller interrupts B) Their source C) Expected nominal input frequency and expected worst-case input frequency – especially interrupts tied to external signals D) Do any ISRs do any hardware output? Which ones and why? E) Are the wake-up interrupts level sensitive or edge sensitive? Include the MSCAN RX interrupt in the answer. | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.4 Interrupts. Item Q:1.4-3 (A); Q:1.4-4 (D), Q:1.4-8 (B); Q:1.4-10 (C); Q:1.4-13 (E) |  | ISR04002 | A) Present your interrupt circuit worst-case analysis. Compensate for expected sources of signal degradation (manufacturing variations, time/usage, operational temperature range, mechanical vibration environment, EMC, harness routing, connectors, daughter cards, in-module jumpers, capacitor failure, water, dust, salt,…) B) How long (instructions & microseconds) are your ISRs? C) Based upon the worst-case analysis scenarios in the ECU Software Requirements document, what is the worst-case CPU load due to interrupts alone? D) What is the expected subsystem behavior if expected worst-case interrupt rate is exceeded? E) Do any of your ISRs call another software module? If so, is this software module re-entrant? If not, why not? | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ |  |  | ISR04003 | A) How long is the minimal required time of an external interrupt source to be detected by the µC? B) How long is the timing of external interrupt sources? Please list for all external interrupt sources. | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.4 Interrupts. Item Q:1.4.5 (A), Q:1.4.6 (B) |  | ISR04004 | A) Can interrupt events be lost? If yes, explain what events are lost and how this affects module/feature behavior. B1) If interrupts are disabled or masked, please explain what interrupt events are lost. B2) If so, how does the system affected by it and what is the recovery. C) Under what conditions are interrupts disabled? D) Please provide review results for race conditions where interrupts are flagged as enabled but are disabled. | A) B1) B2) C) D) | A) B1) B2) C) D) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.4 Interrupts. Item Q:1.4-7 |  | ISR04005 | Present your justification for nested interrupts. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.4. Interrupts - item # Q: 1.4-14 |  | ISR04006 | How are unused interrupt vectors managed? |  |  | not checked |  | Open
I.05) Timers
M-1DJ/FDJ | Software Architecture Review Checklist - 1.18 Miscellaneous Design Practices. Item Q: 1.18-1 (A) , 1.18-2 (B) , 1.18-19 (C ) |  | ITI05001 | A) Explain how Software Timers are implemented and any conventions used to control them. B) Do all the software timers count in the same direction (i.e., either up or down)? If not, why not? C) Explain how Software Timer overflow and underflow are managed? | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler -Item # Q: 1.3-19 |  | ITI05002 | If time must be measured longer than a task execution length, how is it measured? |  |  | not checked |  | Open
I.06) CPU Load
M-1DJ/FDJ | Software Risk Assessment Checklist - 1. Process Questions - Item 3 (A), 2.Architecture and Strategy Questions - Item 2 (E) Software Architecture Review Checklist - 1.4 Interrupts. Item Q: 1.4-2 (A) 1.11 CPU Load. Item Q: 1.11-1 (A), 1.11-2 (B) |  | ICL06001 | A) Present your Worst-Case CPU Load Analysis. Show figures for nominal and Worst-Case load. (CPU chronometrics) B) What is the CPU load if external triggered interrupts are disabled? C) Explain how the figures are determined. D) Describe how/when your software development process incorporates CPU load analysis. E) Have bandwidth and memory utilization been monitored in previous DV test of you product? Describe what and how | A) B) C) D) E) | A) B) C) D) E) | not checked | This question needs to be filled out at 2 mile stones UNV0/UPV0 M-1DJ/FDJ (for metrics purpose it has been marked as only FDJ) | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler - Item Q:1.3-13 |  | ICL06002 | Do you have a non-idle background task? If so, present you deadline monotonic analysis. |  |  | not checked |  | Open
I.07) Watchdog
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler - Item Q:1.3-11 |  | IWD07001 | Watchdog concept: A) Explain your Watchdog concept and your Watchdog strategy. B) Is the Watchdog concept already used in other applications? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler - Item Q:1.3-10(2-B,C), Q:1.3-11(2-A), Q: 1.6-12 (D) |  | IWD07002 | Watchdog Handling: A) List every software location where the Watchdog timer is serviced. B) What is the worst-case duration between Watchdog pettings? C) What is the worst-case Watchdog timeout period? D) How do you handle Watchdog timeout during initialization? (Include all types of watchdog timers. e.g., on micro/off micro, communication, etc.) | A) B) C) D) | A) B) C) D) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler -Item # Q: 1.3-18 |  | IWD07003 | Is there any condition where watchdog functions are not initialized? (e.g., Bootloader, pre-scalar, watchdog time based registers, etc.) |  |  | not checked |  | Open
I.08) Reset Handling
M-1DJ/FDJ | Software Architecture Review Checklist - 1.6 Reset Handling - Item Q: 1.6-1 A,B,C), Q: 1.6-14 (E ) |  | IRH08001 | A) Do you have a warm versus cold boot? If so why? B) Explain the difference between warm and cold boot. C) How long is the boot time for a cold and for a warm boot? D) What technique do you use to force a reset in software? | A) B) C) D) | A) B) C) D) | not checked |  | Open
M-1DJ/FDJ |  |  | IRH08002 | Are there any unexpected resets observed? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.6 Reset Handling - Item Q: 1.6-2 |  | IRH08003 | List the initialization order for warm and cold boot considering among other things: - Initialization of µC internal HW (RAM, PWM etc.) - Changing the PLL - Triggering the Watchdog - Enabling the Interrupts - Initialization/reset of off-micro HW (other µCs, ASICs, EEPROM/Data Flash etc.) Are there other situations apart from warm and cold boot where reinitialization from software or hardware parts take place? Please answer questions above for this cases as well. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.6 Reset Handling - Item Q: 1.6-3 (D) |  | IRH08004 | A) How do you ensure that RAM is initialized on reset? B) How do you ensure that RAM variables are initialized on reset? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ |  |  | IRH08005 | Is a Keep Alive RAM area used? A) For which data is it used? B) Is it initialized/set prior to first read? C) How is data consistency ensured? | n/a | n/a | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler - Item Q:1.3-14 (B) |  | IRH08006 | A) List all configurable features. B) How do you guarantee that all configuration settings are established (read from EEPROM/Data Flash, sensed from an input ...) before starting feature processing? C) Does this adversely affect overall response time? | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.6 Reset Handling - Item Q: 1.6-8 |  | IRH08007 | Can data be received during module start-up that may affect module behavior? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.6 Reset Handling - Item Q: 1.6-9 |  | IRH08008 | Can interrupts occur during module start-up that may affect module behavior? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.6 Reset Handling - Item Q: 1.6-4 ; Q: 1.6-15 (B,D) |  | IRH08009 | Present your stack overflow/underflow prevention/detection technique. A) How do you detect a stack overflow/underflow? B) Does stack overflow/underflow cause a reset? C) Is a stack overflow/underflow logged (e.g., DTC or supplier internal failure log)? D) How much stack margin is there? How do you detect it? E) How do you determine required stack resources? | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.18 Miscellaneous Design Practices. Item Q: 1.18-9 |  | IRH08010 | A) How is ‘divide by zero’ prevented? Explain your strategy to address this fault if it does occur. B) What would happen in case of a division by zero? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.18 Miscellaneous Design Practices. Item Q: 1.18-10 |  | IRH08011 | Do you use any “spin-lock” infinite loops? If so, what is the escape mechanism? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.2 Microcontroller - Item Q: 1.2-12 (A, B), Q: 1.2-17 (C), 1.6. Reset Handling - item # Q: 1.6-16 -1st part ( C) |  | IRH08012 | A) Is RAM executable? What is done with unused executable memory? B) Is EEPROM/Data Flash executable? What is done with unused executable memory? C) When unused executable memory is executed, what is the worst-case time until a microcontroller hardware reset occurs? | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-11 |  | IRH08013 | If RAM checksum is triggered from multiple sources (e.g., during initialization, Runtime, during shutdown, interrupt): A) Where in the code are the RAM checksums calculated? B) How do you ensure its not interrupted? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.6. Reset Handling - item # Q: 1.6-10 |  | IRH08014 | What is the strategy if an over-voltage condition exists when the module comes out of reset e.g., the battery is low and a 24V battery charger is attached? |  |  | not checked |  | Open
M-1DC/VP0 | Software Architecture Review Checklist - 1.18 Miscellaneous Design Practices - 1.18-21 |  | IRH08015 | Show all external control features that are used when the software is in bootloader mode |  |  | not checked |  | Open
I.09) EEPROM / Data Flash Management
M-1DJ/FDJ |  |  | INV09001 | Explain the general method for managing EEPROM/Data Flash: A) Is a shadow RAM scheme used? B) Is a EEPROM/Data Flash Manager used? C) If not: Explain how EEPROM/Data Flash read and write concurrency issues are resolved (EEPROM/Data Flash is probably a shared resource). | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ |  |  | INV09002 | From the time data to be stored in EEPROM/Data Flash is acquired, when is the EEPROM/Data Flash updated? List both nominal and worst-case. |  |  | not checked |  | Open
M-1DJ/FDJ |  |  | INV09003 | Explain how software ensures that the EEPROM/Data Flash data write cycle is not interrupted in the event of a power failure. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.6 Reset Handling - Item Q: 1.6-5 (A) ; Q: 1.6-6 (C,D) |  | INV09004 | Present your EEPROM/Data Flash fault containment strategy: A) How is EEPROM /Data Flash / NVM / KAM integrity verified? B) Is EEPROM/Data Flash data integrity done at a high granularity (such as for all of EEPROM/Data Flash) or a lower granularity (sections of EEPROM/Data Flash or logical blocks)? C) When do you determine that EEPROM/Data Flash data is corrupted? D) How do you recover? E) How does corrupted data in EEPROM/Data Flash affect the features? F) How and when are range checks/boundary checks performed on EEPROM/Data Flash data (data is correct but no valid values)? | A) B) C) D) E) F) | A) B) C) D) E) F) | not checked |  | Open
M-1DJ/FDJ |  |  | INV09005 | A) List all of the regulatory and critical software configuration flags. B) Which parameters/chunks are stored redundant? C) Are there any parameters that leads to a disabling of the system in case of corruptness? D) Which parameters are safety-critical (e.g., Power Window, Restraints)? i) Describe the impact of any failure for all safety-critical parameters to your system. E) Which parameters have default values? i) What are the limitations (e.g., reduced functionality) during the use of default parameters. ii) Is recovery from default values possible due to e.g., self learning algorithms? | A) B) C) D) i) E) i) ii) | A) B) C) D) i) E) i) ii) | not checked |  | Open
M-1DJ/FDJ |  |  | INV09006 | EEPROM/Data Flash Write Cycle Management: A) What is the maximum allowable number of write cycles for a memory location as defined by the EEPROM/Data Flash manufacturer? Is there a temperature dependency? B) What is the size (number of bytes) of a EEPROM/Data Flash block that has to be erased in case of an update of a single byte (1, 2 or more bytes)? Please provide written confirmation of EEPROM/Data Flash supplier. C) When is EEPROM/Data Flash updated e.g., directly if parameter has been changed, at ignition-off, EoL only? D) Present your expected number of write cycles calculation for each parameter over the lifetime of the product (EEPROM/Data Flash sector granularity out of question B to be considered and checksum(s) update frequency). E) If B>A: Explain your strategy you will use to prevent an excessive number of EEPROM/Data Flash write cycles. | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ |  |  | INV09007 | If Data Flash is used: A) How many data Flash sectors are you using? B) What is the size of the sectors? C) What is the filling degree of the sector for one set of complete data? D) How long does it take to copy the data of a sector to the next? E) Is there any impact on software execution time? | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ |  |  | INV09008 | Data Retention of EEPROM/Data Flash: A) How many years of data retention are guaranteed? B) Is there a dependency on environmental factors e.g., temperature (Profile)? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ |  |  | INV09009 | When is EEPROM/Data Flash initialized (at microcontroller suppliers, at module end-of-line, at Ford end-of-line)? |  |  | not checked |  | Open
I.10)Power Management ( included Over/Under Voltage , Power dropout sections)
M-1DJ/FDJ | Software Architecture Review Checklist - 1.5. Module power supplies - item # Q: 1.5-2 |  | IPM10001 | Does the module power supply use a Supervisory IC, Low voltage inhibit or Discrete Components to control the microcontroller reset line? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.5. Module power supplies - item # Q: 1.5-3 (A), Q: 15-4 (B) Q:1.9-10(B) |  | IPM10002 | A) How much time is given in software to stabilize the power supplies before I/O (sensors/actuators etc.) occur? Present the calculations for determining the hardware stabilization time for all power supplies (these should match the Hardware/Software Interface Specification). B) When verifying the power supply is stable, is only the supply request monitored or is the actual supply voltage monitored and how? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.5. Module power supplies - item # Q: 1.5-6 |  | IPM10003 | When a reset occurs (especially software reset or watchdog reset), are all the software controlled power supplies also reset? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler Item Q: 1.3-6 (A,B) , Q:1.3-7 (E,D), Q: 1.12-9 (A,C) |  | IPM10004 | OVER/UNDER Voltage behavior: A) Present your voltage range definitions for all your features and input circuits. B) When do you declare that the complete module is OVER or UNDER voltage? C) What voltage hysteresis values are you using for all transitions between OVER_V & NORM_V and UNDER_V & NORM_V for all of your inputs. D) What time-based hysteresis are you using? E) How do you recover from a module OVER or UNDER voltage condition (reset, RAM initialization, establishment of configuration settings (reading EEPROM/Data Flash data))? | A) B) C) D) E) | A) B) C) D) E) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.21 Power Dropout Management. Item Q:1.21-2 |  | IPM10005 | A) What is your method of detecting OVER or UNDER voltage? B) What battery voltage circuit is used (if multiple circuits are available)? C) What is the accuracy of the measurement system? D) How many samples are used? E) What is the sample rate? F) Are these factors taken into account in the WCCA? Provide WCCA as evidence. | A) B) C) D) E) F) | A) B) C) D) E) F) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.21 Power Dropout Management. Item Q:1.21-3 |  | IPM10006 | What actions are taken when low power is detected? |  |  | not checked |  | Open
M-1DJ/FDJ |  |  | IPM10007 | What actions are taken when over voltage is detected? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.21 Power Dropout Management. Item Q:1.21-4 , 1.21-5 |  | IPM10008 | How do you recover from a module OVER or UNDER voltage condition (reset, RAM initialization, establishment of configuration settings (reading EEPROM/Data Flash data))? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-14 (C) |  | IPM10009 | OVER/UNDER Voltage DTC (Diagnostic Trouble Code): A) Do you set an OVER or UNDER voltage DTC? B) Is the DTC pending on the absolute voltage or an offset voltage to an other module (e.g., Central Electronic Module)? C) Explain under what conditions you set the OVER or UNDER voltage DTCs (direct, filtering, debounce, time-based hysteresis, voltage-based hysteresis)? D) When do you reset the OVER or UNDER voltage DTC? | A) B) C) D) | A) B) C) D) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-1 (A) , Q: 1.10-2 (B) |  | IPM10010 | Logging the other DTC's: A) In what voltage range do you log DTCs (work backward from analog input counts)? This assumes that outside this normal voltage range, you stop logging DTCs. B) Describe any time-based hysteresis associated with the DTC Logging Voltage Range. (Hint: what is your worst-case debounce time?) | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler Item Q:1.3-8 |  | IPM10011 | What is the worst-case time delay between determining VBattState[i] and sampling the associated input circuits? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.21 Power Dropout Management. Item Q:1.21-1 (A) |  | IPM10012 | A) Present your power dropout management strategy. B) How does the software handle the 20 ms battery drop out requirement? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.21 Power Dropout Management. Item Q:1.21-6 |  | IPM10013 | How does the design ensure module outputs are not left activated indefinitely during a power dropout? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.21 Power Dropout Management. Item Q:1.21-7 |  | IPM10014 | How does the design ensure that module features are properly restored at the end of a power dropout? Note that this includes power drop transients that are long enough to initiate a load shed event, but shorter than the total time required to complete all load shedding. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-10 |  | IPM10015 | A) Does the software monitor the software controlled power supply output? B) Explain how battery voltage fluctuation does not introduce a false DTC? C) Explain the software filtering on the feedback signal. | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.5. Module power supplies - item # Q: 1.5-7 |  | IPM10016 | What SW techniques are being used to support Key-Off-Load requirements. |  |  | not checked |  | Open
M-1DJ/FDJ |  |  | IPM10017 | Provide state flow charts, activity and sequence diagram including interface and signal information for transitions between different power modes |  |  | not checked
I.11) Sleep Processing
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-1 |  | ISP11001 | Present your sleep/awake strategy. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-2 |  | ISP11002 | List all inputs that are monitored during Sleep Mode. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-3 |  | ISP11003 | A) Describe the detection methods used to monitor these inputs during Sleep Mode. B) Is the debounced value stored and compared to the new raw value read during the polling? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-4 |  | ISP11004 | For inputs which are polled during Sleep Mode, what is the sampling frequency? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-5 |  | ISP11005 | How are polled wake-up signals debounced? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-6 |  | ISP11006 | For each wake-up input, what's the worst-case time to debounce it? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-7 |  | ISP11007 | If an interrupt can wake your module from Sleep Mode, describe how do you debounce this input. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-8 |  | ISP11008 | If an interrupt can wake up your module from Sleep Mode, how do you guarantee that interrupts are enabled? (Do not place any instructions between the enable interrupt and the STOP/HALT instruction- design guideline) |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-9 |  | ISP11009 | Is a pulse train signal (pulse width or frequency measurement) used as a wake-up? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-10 |  | ISP11010 | Are the Sleep Mode debounce algorithms different from the normal debounce algorithms? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-11 |  | ISP11011 | Which microcontroller control registers are refreshed during Sleep Mode? How often are they refreshed? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.7 Sleep Processing - Item Q:1.7-12 |  | ISP11012 | When the module is in Sleep mode and a wake-up input wakes the module but the debounce indicates that there was no change of state on the input, how long does it take to re-enter Sleep mode? |  |  | not checked |  | Open
M-1DJ/FDJ |  |  | ISP11013 | Are there any timers or other controller mechanisms that should be running while the module is in sleep mode? (e.g., timers, motor control, etc.) |  |  | not checked
I.12) Awake/Active to Sleep Transition
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-1 |  | IAS12001 | What are all the conditions necessary to enter Sleep Mode (e.g., Ignition switch = OFF and Wake-up inputs are not changing, etc.)? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-13 |  | IAS12002 | List all sleep inhibitors (e.g., software based timers, FNOS, motor control, lights, thermo modules, NVM write, etc.). |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-12 |  | IAS12003 | A)Describe the sequence for transition from full awake to full sleep, including network sleep and putting the transceiver in low power mode, if applicable. B)How do you ensure that all of your wakeup mechanisms are in the correct state/mode (e.g. wake-up interrupts enabled, CAN transceiver set-up to provide wake-up signal, etc.) to correctly wake up the micro? C)List all operations/functions performed during the transition to Sleep Mode (e.g., set a wake-up timer, write to EEPROM/Data Flash, checks etc.). Be specific and include exception handling, if any. | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-2 ; Item Q:1.8-11 |  | IAS12004 | A)How long does it take for the module (ECU) to enter sleep mode when all the sleep conditions are satisfied? B) Are there any operations (such as NVM write or copy data from a Flash sector to another) which can delay the module more than twice as long as normal from entering Sleep mode? C) Provide measurements for best and worst case timings for module to enter sleep mode when all conditions are satisfied. How were these measurements performed? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-3 |  | IAS12005 | A) List all the conditions that keep the module awake i) By use case: For example, the power sliding door normally goes to sleep a few seconds after the door is closed. But if the door is left open, the module stays awake for hours or ii) By failure: For example, an error is encountered (such as during NVM write) that inhibits state transition B) How does the software guarantee in these cases that the maximum allowed power mode transition time is not exceeded? C) Is there a maximum timeout after which the module will be forced to sleep in the event that all conditions have been met and state transition does not occur? i) If the module is indeed forced to sleep even though normal state transition did not occur, what is the impact on module (could parameters be lost e.g. power window position etc.)? ii) Is this self healing? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-5 |  | IAS12006 | What have you done to guarantee an appropriate response when the module determines that all sleep conditions have been satisfied and then something changes on the transition to sleep mode? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-8 |  | IAS12007 | Can the system be interrupted during the transition to sleep, which can adversely affect wake up ability? e.g., such as not re-enabling interrupts? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-7 |  | IAS12008 | When is it appropriate for your module to let the network go to sleep even though your module isn’t ready for sleep yet? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-4 |  | IAS12009 | If the module goes through reset and all sleep conditions are satisfied, how long does it take to go to sleep? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-9 |  | IAS12010 | How does the software guarantee the EEPROM is not busy when transitioning to sleep? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.8 Awake/Active to Sleep Transition - Item Q:1.8-10 |  | IAS12011 | How does the software guarantee that DTC U1900 (missing message DTC) is not logged when transitioning from awake to sleep or sleep to awake? Explain the method for logging a missing message DTC. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-16 |  | IAS12012 | List all the conditions that keep the module awake. Are there any timers or other controller mechanisms that should be running while the module is in sleep mode? (e.g., timers, motor control, etc.) |  |  | not checked |  | Open
I.13) Sleep to Awake/Active Transition
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-1 |  | ISA13001 | A) What's the worst-case time it takes to debounce the wake-up inputs (time of the worst input)? B) What's the worst-case time it takes to activate the appropriate outputs? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-2 |  | ISA13002 | A) Is reset used in the Sleep/Awake transition? B) If so, why? C) If so, do you also debounce the wakeup and ensure the wakeup is still present before reset? | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-4 |  | ISA13003 | Will the module exit Sleep mode if there is communication on the network link? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-5 |  | ISA13004 | Can interrupts occur during the transition from Sleep Mode to Awake/Active? How can this affect the operation of the module? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-6 |  | ISA13005 | How do you guarantee feature states after the Awake-to-Sleep and Sleep-to-Awake transitions? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-7 |  | ISA13006 | What happens if two wake-up inputs change simultaneously? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-8 , Q:1.9-12 , Q: 1.15-1 |  | ISA13007 | Sequence of events when a wake-up event is received: A) List all events and operations/functions performed during the transition to Awake/Active Mode (e.g., read specific input lines for state change, check RAM, etc.). Be specific and include exception handling, if any. B) What is the total elapsed time when a wake-up event is received? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-14 |  | ISA13008 | How long does it take the ECU to be ready to receive a CAN message after the wake up (Usually a Network Management message) has been received? Show the analysis. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.6. Reset Handling - item # Q: 1.6-13 1.9 Sleep to Awake/Active Transition - Item Q:1.9-9 |  | ISA13009 | A) List all configurable features. B) How do you guarantee that all configuration settings are established before starting feature processing? C) Does this adversely affect overall response time? | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-3 |  | ISA13010 | How is ensured that all control registers are refreshed on the Sleep/Awake transition? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.9 Sleep to Awake/Active Transition - Item Q:1.9-13 |  | ISA13011 | A) If the ECU employs a PLL (Phase Locked Loop) when coming out of sleep mode, how does the software guarantee the PLL is operating correctly? B) If the PLL is not operating correctly, what is the corrective action? | A) B) | A) B) | not checked |  | Open
I.14) Diagnostics
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler - Item Q:1.3-4 |  | IDI14001 | Are you building the system without diagnostics intending to graft it on later? If so, explain how you made provisions in your design that will allow you to easily add diagnostics later. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-3 |  | IDI14002 | Exactly when is Continuous DTC logging enabled and disabled? Is it dependent on ignition switch position? If not, why not? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-4 |  | IDI14003 | How do you prevent false Continuous DTCs when circuits are killed by the ignition switch but the ignition switch debounce hasn’t finished? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-5 (A, D, F) , 1.10-6 (B) |  | IDI14004 | Defective ECU DTC(s): A) List all the conditions that could cause a defective ECU DTC to be set. B) How long does it take to set a defective ECU DTC for each of the conditions listed above? / C) Are there any recovery strategies? D) Describe the failsafe handling for each of this conditions. (What does the ECU do when the defective ECU DTC is set?) E) Is the driver notified? F) Can a defective ECU DTC be clear with a diagnostic tool or through ignition switch cycling? | A) B) C) D) E) F) | A) B) C) D) E) F) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-9 (A) , Q: 1.10-11 (B) , Q: 1.10-18 (C ) |  | IDI14005 | A) List all the possible responses to each diagnostic service request for each ECU mode (or session for CAN). List all the conditions for each response. B) For each DTC, list all detection criteria, number of samples, sample period and sample rate. C) List all the continuous DTCs and explain how it clearly directs the service technician to identify the defective part. | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-17 |  | IDI14006 | Describe the mechanism used to store and mask DTC's from reporting. Explain how a continuous or self-test DTC is masked. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-12 |  | IDI14007 | Explain how you can ensure that self-test will always complete? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler - Item Q:1.3-5 |  | IDI14008 | A) How do you insure the integrity of the feature states when exiting diagnostics – especially when event messages are ignored during the diagnostic session? B) How do you guarantee distributed feature stability when one module is in diagnostic mode and the others are not? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-8 |  | IDI14009 | Can a busy response message ever be sent to the diagnostics test tool if EEPROM is busy? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-10 |  | IDI14010 | Configuration according to Method II is not guaranteed to arrive in sequential order. Explain how the software ensures that non-sequential block download is verified to be complete. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.10 Diagnostics - Item Q: 1.10-13 |  | IDI14011 | During diagnostic self test execution, are the high current loads staggered? (This includes current through the module or driven by a relay.) Explain the strategy to stagger the output activations. Also note: This may conflict with the 100 ms timing throughput requirement of the FS. |  |  | not checked |  | Open
I.15) Input Processing
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q: 1.12-1 |  | IIP15001 | Explain general input operation (e.g., de-bounce strategy, analog data processing, PWM processing). |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q: 1.12-3 |  | IIP15002 | Based on worst-case analysis, at what battery voltage level can digital inputs be misread (i.e. logic 0 read as logic 1 and vice versa)? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q:1.12-4 |  | IIP15003 | What is the threshold for the digital input based on low voltage, nominal voltage and high voltage? (e.g., 3.0 to 3.5 volts is a switch to ground, logic 0. 6.0 volts and greater is a logic 1 at VBatt=13.5.) |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q: 1.12-2 |  | IIP15004 | Explain the voltage mapping technique for battery voltage. How is a logic level “1’ and logic level “0” determined? How does high/low battery voltage affect mapping, A/D conversion or comparator circuit? |  |  | not checked |  | Open
M-1DJ/FDJ |  |  | IIP15005 | A) Is there any input fault detection? Please explain for each input. B) If so, do you have any retry strategies associated with these input faults? Please describe for each input. C) Are sticky switches considered? | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q:1.12-5 , Q: 1.12-7 |  | IIP15006 | For all inputs (except interrupts) list: source, expected nominal input frequency and expected worst-case input frequency, “out-of-range value” |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q:1.12-6 |  | IIP15007 | For all input circuits (except interrupts), present your WCA. Compensate for: expected sources of signal degradation (time/usage, operational temperature range, mechanical vibration environment, EMC, harness routing, connectors, daughter cards, in-module jumpers, water, dust, salt, etc.) and prove that the design does not alias input signals |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.18 Miscellaneous Design Practices. Item Q: 1.18-2 (A) , 1.18-5 (B) 1.18-6 ( C) |  | IIP15008 | A) Besides EEPROM/Data Flash data, list any critical data variables that require boundary checking. B) How did you determine what requires boundary checking and what is your boundary checking strategy? C) Are out-of-bounds condition handled by the features? Is there a overall strategy or is each case unique? Should there be a consistent strategy? | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q:1.12-8 |  | IIP15009 | Which inputs are capable of “timing-out”? How were the values of time-outs determined? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q:1.12-10 |  | IIP15010 | For analog channels, are you using software or hardware ratiometric conversions? What is your reference voltage? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q:1.12-11 |  | IIP15011 | For analog channels, how do you guarantee that noise differentials between VBatt circuit and the input circuit does not adversely affect your input counts? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q:1.12-12 |  | IIP15012 | A) For any discrete analog inputs (a discrete analog input is a signal that is quantized into a finite number of expected values e.g., 2,5V/5V/7,5V/10V for coding of four discrete stages), list the possible state for each channel (including shorts, open circuits and dead bands). B) Provide a worst-case analysis showing state boundaries and nominal values for minimum, nominal, and maximum operational voltages. List each boundary/nominal value in ohms, volts at the device (not the micro pins), and A/D counts. | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q: 1.12-14 |  | IIP15013 | Are switched pull-up resistors used? Does the software wait at least + 4 worst-case time-constants before reading the input? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q: 1.12-15 |  | IIP15014 | Does the software monitor a feedback signal from a switching device (for Low Side Inputs)? How do you ensure that the appropriate voltage is available to the pull-up resistors before reading the input signal? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q: 1.12-16 |  | IIP15015 | If the software is controlling and monitoring outputs that drive 'high current load(s)': A) Explain how in-rush current is managed in the software. B) Explain how the in-rush current does not trigger false DTC's C) Explain how you account for an intermittent open circuit so it will not cause a false DTC. | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q: 1.12-17 |  | IIP15016 | If a PWM signal is controlling a feature who's feedback is read by this module, explain how the delay in state change determination is accounted for? |  |  | not checked |  | Open
I.16) Output Processing
M-1DJ/FDJ | Software Architecture Review Checklist - 1.14. Output Processing. Item Q:1.14-1 |  | IOP16001 | Explain how any PWM, or Frequency (variable or fixed) outputs are generated. What is done in software? What is done in hardware? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.14. Output Processing. Item Q:1.14-2 |  | IOP16002 | Can an output dataflow change faster than the hardware can support? How is this handled and how does it affect the feature? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.14. Output Processing. Item Q:1.14-3 |  | IOP16003 | Are all module outputs performed at the same time or are the outputs performed at the time the dataflow changes? Why? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.14. Output Processing. Item Q:1.14-4 (A) , Q: 1.10-7 (B,C) |  | IOP16004 | A) Does your module monitor output levels and compare them to predicted values? If so, how do you define a fault and what do you do when a fault occurs? B) Is there any output fault detection? Please explain for each output. C) If so, do you have any retry strategies associated with these output faults? Please describe for each output. D) Is the driver notified? | A) B) C) D) | A) B) C) D) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.14. Output Processing. Item Q:1.14-8 |  | IOP16005 | Present your FET Short Circuit Protection strategy. |  |  | not checked |  | Open
M-1DJ/FDJ |  |  | IOP16006 | A) Does the module supply an output for any remote (off-module) features? B) If so, do you protect against leaving this output active during the incorrect ignition switch states (e.g., Heated backlit control should not be ON when the ignition switch is in the OFF position?) | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.14. Output Processing. Item Q:1.14-5 |  | IOP16007 | Does a communication link (like UART or SPI) use a loop back? A) Does your module listen for your output “echo"? If so, why? B) What do you do when a mismatch occurs? | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.14. Output Processing. Item Q:1.14-6 |  | IOP16008 | If the module controls multiple high current outputs, (e.g., any individual load greater than or equal to 10 Amps) and whose loads are required to be turned ON at the same time, show that the switching times are staggered by 50 – 100mS. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.14. Output Processing. Item Q:1.14-7 |  | IOP16009 | If the software controls a PWM signal for backlighting, does the PWM value go to zero when the battery voltage is out of range? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.18 Miscellaneous Design Practices. Item Q: 1.18-15 |  | IOP16010 | Show the test plan for the FET protection strategy (if not covered in FET protection document). |  |  | not checked |  | Open
I.17) Serial Processing
M-1DJ/FDJ | Software Architecture Review Checklist - 1.12 Input Processing. Item Q: 1.12-13 |  | ISP17001 | For all off-micro resources that use multi-bit communication (SPI, SCI, UART…), describe how data integrity is preserved. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.4 Interrupts. Item Q:1.4-12 |  | ISP17002 | Do you use bit-banging? If so, what is the worst-case shortest time between bit value changes? Info: Bit-banging is a method of using general-purpose I/O lines to emulate a serial port. It is up to the user to provide the correct number of transitions and to ensure that the timing requirements are met. |  |  | not checked |  | Open
I.18) Module Network/ Communication Link Interface
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-5 (A) |  | ICL18001 | A) Explain how you verify the data integrity of every message received (beyond normal checksum, parity…). B) What is the failure mode strategy when the contents of a data packet is invalid? (e.g., Retries strategy, etc.) | A) B) | A) B) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler -Item # Q: 1.3-16 |  | ICL18002 | Explain the Master-Slave microcontroller communication strategy. A) Explain the Master-Slave communication supervisory function including timer functions. B) Can the Master microcontroller force a hardware reset on the Slave microcontroller? C) How often does the Master microcontroller communicate with the Slave microcontroller? | A) B) C) | A) B) C) | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler -Item # Q: 1.3-16 |  | ICL18003 | A) How does the Slave microcontroller determine communication lost? B) How does the Master microcontroller determine communication lost? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.3 Software Architecture & Scheduler -Item # Q: 1.3-16 |  | ICL18004 | Is the communication channel a full or half duplex? If have duplex, explain the method for signal arbitration? |  |  | not checked |  | Open
I.19) Vehicle Network Communication (Shall be moved to Feature group)
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-2 |  | IVN19001 | What does the module do when a network event message is received more than once? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-3 |  | IVN19002 | What is the failure mode strategy when the contents of a data packet is invalid? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-4 |  | IVN19003 | If not using FNOS, explain the module network message retry strategy when you get a fault transmitting network messages. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-6 |  | IVN19004 | A) What version of the message list are you using? B) What is the current message list version? | A) B) |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-7 |  | IVN19005 | How have you isolated all the event with repetition signals that you send or receive from the feature functionality? |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-8 |  | IVN19006 | How do you simulate the message traffic from the other nodes on the bus? Explain how the network interface is accomplished (e.g., Message scripts, Vector CANoe, Smart tools, Netway box, etc.). |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-9 |  | IVN19007 | Show that the module actuator respond within 30 milliseconds to a network message. List the actuators (such as relay, solenoid, lock motor, etc.) and the response time. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.15 Module Network/Communication Link Interface Item - Q: 1.15-11 |  | IVN19008 | Explain your missing message strategies. A) List all Network interfacing ECUs. List the conditions were a message(s) would not be sent? Show that the software accounts for these conditions? (i.e., Vehicle speed and PRNDL are only available when the ignition switch is in the RUN position.) B) List all periodic messages that you receive. Describe your strategy for setting missing message DTCs. C) Describe how your functionality is affected by missing messages. What failure modes exist? What is your strategy for handling these failure modes? D) If FNOS is used, are you using the missing message indication from FNOS in your missing message strategy? If so, how do you prevent erroneously setting missing message DTCs, especially for ignition switched nodes? | A) B) C) D) | A) B) C) D) | not checked |  | Open
I.20) Closed-Loop Control (Shall be moved to D&R List)
M-1DJ/FDJ | Software Architecture Review Checklist - 1.13. Closed-Loop Control. Item Q: 1.13-1 |  | ICL20001 | List all Closed-Loop control systems implemented in your module |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.13. Closed-Loop Control. Item Q: 1.13-2 |  | ICL20002 | For all the control system listed above, present the control loop diagram, transfer function of the “plant”, transfer function of the control loop, the S-domain control equations, the Z-domain control equations, and the time-domain control equations… |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.13. Closed-Loop Control. Item Q: 1.13-3 |  | ICL20003 | Present the simulation created to verify both the plant and the control system solution. |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.13. Closed-Loop Control. Item Q: 1.13-4 |  | ICL20004 | Explain how your control system accommodates expected component/system variations |  |  | not checked |  | Open
M-1DJ/FDJ | Software Architecture Review Checklist - 1.13. Closed-Loop Control. Item Q: 1.13-5 |  | ICL20005 | If your system is non-linear, explain how you “linearized” the system. Also explain how you plan to test the transitions between the “linearized” portions |  |  | not checked |  | Open
I.21) Coding Best Practices
M-1DC/VP0 | Software Code Review Checklist- 1.1 Coding Issues. Item Q:1.1-1 |  | ICO21001 | Do you use any numeric constant in you code? If so, which ones? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.1 Coding Issues. Item Q:1.1-2 |  | ICO21002 | Do any include files contain executable code? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.1 Coding Issues. Item Q:1.1-3 |  | ICO21003 | Do you use nested include files? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.1 Coding Issues. Item Q:1.1-4 |  | ICO21004 | Succinctly explain the difference between a declaration and a definition. |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.2 Static Analysis. Item Q:1.2-1 |  | ICO21005 | Present the static analyzer results |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.2 Static Analysis. Item Q:1.2-1 |  | ICO21006 | What are the Cyclomatic Complexity and Static Path Counts for the ISRs? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.2 Static Analysis. Item Q:1.2-1 |  | ICO21007 | What are the Cyclomatic Complexity and Static Path Counts for the rest of the code? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.3. MISRA. Item Q:1.3-1 |  | ICO21008 | A) List all locations where assembly language is used B) What string can be searched for that would locate every instance of use of assembly language? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.3. MISRA. Item Q:1.3-2 |  | ICO21009 | List all locations where #pragma is used |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.3. MISRA. Item Q:1.3-3 |  | ICO21010 | Please Present the MISRA compliance ex: Switch Statements - default case |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-1 |  | ICO21011 | A) List all locations where timing relies on instruction counting B) What string can be searched for that would locate every instance? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-2 |  | ICO21012 | List all global variables that are used for more than one use. For example, the global variable idx is used as an array index in both routine foo() and routine bar(). |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-3 |  | ICO21013 | List all shared resources (registers, variables, NVM, bit fields, input circuits, output circuits,…). Note: all global flags that are stored in the same byte/storage unit are shared resources. |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-4 |  | ICO21014 | A) List all variables/ports accessed by ISRs (cross reference) B) How do you protect these shared resources |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-5 |  | ICO21015 | List all routines that access the SPI/SCI ports B) How do you protect this shared resource? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-6 |  | ICO21016 | Is the SPI/SCI port shared by other off micro devices B) How do you protect this shared resource? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-7 |  | ICO21017 | Does the hardware/software interface specification clearly describe how to control the SPI/SCI port in terms of shared resources? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-8 |  | ICO21018 | Review all “awake” debounce algorithms.- this question is asked after SW Architecture review during which code may not be ready |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-9 |  | ICO21019 | Review the “sleep to wake” debounce algorithms.- this question is asked after SW Architecture review during which code may not be ready |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-10 |  | ICO21020 | Review shared variable/function list - this question is asked after SW Architecture review during which code may not be ready |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-11 |  | ICO21021 | Review ISRs, are they re-entrant? - this question is asked after SW Architecture review during which code may not be ready |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-12 |  | ICO21022 | A) Exactly which control registers (data direction, clock prescalar, PLL, UART configuration…) are refreshed and at what periodic rate? B) List any control registers that are initialized at boot but not refreshed? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-13 |  | ICO21023 | List, in detail, all operations/functions performed after reset (e.g., Interrupts Off, configure NVM in the first 64 clock cycles, write $FF to all RAM, Read inputs, deactivate outputs, etc.). Include compiler setup procedure and any exception handling. |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-14 |  | ICO21024 | For every resource that is controlled via the use of critical sections, what is the worst-case latency? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-15 |  | ICO21025 | Show how this worst-case latency has been accommodated in your worst-case CPU load and Interrupt latency analysis. |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-16 |  | ICO21026 | Do you use any third-party low-level driver software for any chips in your module (e.g., driver code that was developed by/for the chip manufacturer)? If so, how do you validate that code? ( Supplier shall make sure third-party meets Ford requirements) |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-17 |  | ICO21027 | What is done in software when a clock monitor fault exists? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-18 |  | ICO21028 | Is a RAM retention flag used? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-19 |  | ICO21029 | How it is ensured that DEBUG mode is not enabled in production code |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-20 |  | ICO21030 | Describe the standardized process for reusing elements of the software library; including the process that assures different versions of library elements are compatible. |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-21 |  | ICO21031 | Does the code plan on using a banked memory model? For example, does the code plan on using Near and Far pages? How do you define functions for each bank, and what is the default function call? What design rules guide how memory banks are used? |  |  | not checked |  | Open
M-1DC/VP0 | Software Code Review Checklist- 1.4. Miscellaneous. Item Q:1.4-22 |  | ICO21032 | Show 10 lines of source code before and after the module enters the sleep mode. |  |  | not checked |  | Open

## Glossary (Configuration)
GLOSSARY
Cell colors | Explanation
n/a | Choose 'n/a' from the dropdown menu for items not worked during a delta TDR.
not checked | Choose 'not checked' for items that are stated as not applicable by the supplier but it is not checked by SW TDR engineer that they are not applicable.
Red | Choose 'Red' for Items not completed in the correct stage and has no plan to be corrected or it will be completed in a later SWTDR event but shouldn't be deferred.
Yellow | Choose 'Yellow' for the Items not completed during the current SW TDR event but have a conformance date or implementation to be improved.
Green | Choose 'Green' for items that are assessed as sufficient based on the provided information.
n/a | Choose 'n/a' from the dropdown menu for items not worked during a delta TDR.
not checked | Choose 'not checked' for items that are stated as not applicable by the supplier but it is not checked by SW TDR engineer that they are not applicable.
Open | Choose 'Open' for items that are not finally closed.
Closed | Choose 'Closed' for items finally discussed. In exceptional cases this can be as well items that are rated as yellow but risk to improve at current state of the project is assessed higher than the improvement potential. This items should be addressed in future projects.
UNV0/UPV0
M-1DJ/FDJ
M-1DC/VP0
Overall